Type of Review: Project Completion Review

Project Title: TradeMark Southern Africa Programme

Date started:	01 November 2009

Date review undertaken: 17 June 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / The Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support did the UK provide?
Trade Mark Southern Africa (TMSA) was a 5 year (November 2009 to October 2014), £100 million Department for International Development (DFID) Southern Africa funded programme that promoted regional trade and integration in Southern and East Africa by working closely with the COMESA-EAC-SADC[1] Tripartite, its 26 member states, business and civil society organisations in implementing COMESA-EAC-SADC programmes. / The programme consisted of £33 million technical assistance, project preparation and capacity support. It was hosted by COMESA and project activities were implemented through the TMSA programme management unit (PMU), with staff based in Pretoria, in SADC (Botswana) and in COMESA (Zambia). A further £67 million of capital expenditure (Capex) was provided to the Tripartite Trust Account (TTA) for the purposes of leveraging investment into regional infrastructure networks of the North-South Corridor (NSC) Aid-for Trade Programme. The Development Bank of Southern Africa (DBSA) managed the fund, while investment decisions were taken by an Investment Committee, consisting of the Tripartite Chair, representatives of all three Tripartite RECs, TMSA, DBSA and DFID Southern Africa (DFIDSA). / Key work areas included: (i) Trade Policy Capacity Building through support to the Tripartite Free Trade Area (TFTA) negotiations and the WTO Least Developed Country (LDC) Group; (ii) Trade and Transport Facilitation: (iii) Trade-related issues, such as Non-Tariff Barriers (NTBs) and standards; (iv) Regional Infrastructure, particularly along the North South Corridor (NSC); and, (v) Industrial Development.
[1] Southern African Development Community (SADC); Common Market for Eastern and Southern Africa (COMESA); East African Community (EAC).

Decision to close TMSA
On 4 December 2013, the Secretary of State (SoS) for DFID announced her decision to commence with the immediate closure of TMSA. The programme closed 17 March 2014, six and a half months early. / TMSA was reviewed by the Independent Commission for Aid Impact (ICAI) in the first quarter of 2013. In May 2013, ICAI alerted DFID senior officials to its serious concerns about the TMSA programme, including the risk of fraud. DFID Southern Africa commissioned DFID’s Internal Audit Department (IAD) to undertake a forensic audit of the TMSA programme which was carried out in June and reported in July. It found no evidence of fraud and that all DFID funds could be accounted for, but together the reviews revealed a number of serious issues and risks in the areas of delivery, management, oversight and financial monitoring. DFID’s IAD also found that approximately £80,000 had been channelled through Government of Zimbabwe systems since 2011 via a ring-fenced account. Although this money was used appropriately for a fruit fly eradication programme to promote trade and reduce poverty, this payment was in contravention of UK Government policy. / During the second half of 2013, DFID Southern Africa worked with COMESA and TMSA management to address the weaknesses identified by ICAI and DFID’s IAD. TMSA’s operations continued during this period but were constrained. / On 4 December 2013, after she had spoken to the Heads of the Tripartite Regional Economic Communities, the Secretary of State made a written Ministerial Statement notifying Parliament that she had given notice to commence shutting down TMSA with immediate effect. / The TMSA programme closed early on 17 March 2014. A closure plan was agreed between DFID and COMESA in January 2014 which constituted essential activities needed as part of a responsible exit. For most projects, other than TMSA’s support to the Tripartite FTA negotiations and the NTB reporting system or where there were legally binding contracts, this meant either immediate or rapid closure of project activities. / As at 17 June, DFID is finalising post-closure activities with COMESA, such as the closing audit. It is envisaged that the few remaining issues will be finalised in July 2014. / DFID Southern Africa is also processing a one-off transfer of £1,000,000 from the TMSA programme to Trade for Development Department’s Trade Advocacy (TAF) to blend with existing TAF funding to support the Tripartite Free Trade Area (TFTA) negotiations until the Tripartite Summit in late 2014. Value for money (VFM) will be achieved through, for example, streamlining the negotiating schedules, introducing progress-review milestones and not paying per diems. This funding will be reported on and managed through the TAF project.

What were the expected results?
The Impact of the programme was “Sustained rapid, inclusive growth and poverty reduction in Southern Africa”. / The Outcome was “To improve Southern Africa’s trade performance and competitiveness for the benefit of poor people through regional integration”. / TMSA also aimed to achieve the following results among others by October 2014: / A 30% reduction in transit times and 20% reduction in transport costs on the North South Corridor. / At least 30% average reduction in crossing time at four border crossings in Southern Africa (including Chirundu). / Agreement of the Tripartite “Cape to Cairo” Free Trade Agreement (TFTA) by 13 countries. / 19 regional infrastructure projects financed or in the preparation for public financing, and five projects ready for financing through public private partnerships. / 2,800 Gigawatt hours of electricity traded across new cross-border inter-connectors. / 50% of reported non-Tariff Barriers (NTBs) resolved for countries in the Tripartite area. / Enhanced productive and export competitiveness – including through harmonisation of Sanitary and Phytosanitary Standards, industrial development policies and the management of fruit fly in five countries.

What was the context in which UK support was provided?
TMSA was a key component of the UK’s Africa Free Trade initiative (AFTi) http://www.dfid.gov.uk/news/latest-news/2011/uk-government-ramps-up-trading-in-africa/. AFTi, launched in February 2011, brings together regional trade initiatives from across the UK Government to cut the cost and increase the value of trade within Africa and between Africa and the rest of the world. The high cost of doing business across borders in Sub Saharan Africa (SSA) is a major constraint to trade. Transport costs range from 15 to 20% of import costs, a figure 3–4 times that of developed countries[2]; and on average transport costs add 18.7% to the unit cost of goods[3]. / TMSA was seeking to deliver an extremely ambitious programme in a very challenging environment. In Southern Africa, tariffs are relatively high and non-tariff regulatory barriers to trade – including through restrictive regulations and inefficient customs procedures - are even more restrictive, compounded by poor infrastructure at and between national borders. Beyond a few relatively advanced centres most notably South Africa, there is little economic diversity with most trade consisting of primary goods with little value addition, low levels of productivity and competitiveness, and poorly developed regional value chains. While much greater attention has been given to regional integration by countries the last decade, there is limited evidence of political commitments to integration translating into implementation at country level. Overlapping REC jurisdictions and multiple actors mean that dealing with competing initiatives, multiple jurisdictions and actors adds to the difficulties of quick implementation of agreements. / The TMSA programme design was informed by a significant body of international evidence confirming that greater openness to trade is, on average, associated with faster growth and increasing productivity[4]. For example, the Overseas Development Institute assesses that “the weight of evidence suggests that greater trade openness is an important element in explaining growth, and has been a central component of successful development. Few countries have grown over the long-term without experiencing an expansion of trade”[5] / At the same time, it is also clear that increased trade will not in itself translate into growth and poverty reduction. This requires complementary policies, including sound macro-economic management, investments in human capital and infrastructure, policies that promote economic inclusion and adjustment for those affected by changes as a result of trade reform. For the most part TMSA did not seek to address these issues, although it was pro-poor in that it concentrated its efforts on supporting the poorest countries in the region to benefit from increased trade.
[2] Teravaninthorn and Raballand, Transport Prices and Costs in Africa (World Bank 2009).
[3] Morrissey, Transport and Trade Costs in Africa (2009)
[4] Winters and Masters, Openness and Growth: Still an Open Question (2010)
[5] Higgins and Prowse, Trade, Growth and Poverty: Making Aid for Trade Work for Inclusive Growth and Poverty Reduction (2010)

## Section A: Detailed Output Scoring

Approach to Assessing the Final Score and Performance Description / This Project Completion Report (PCR) assesses TMSA’s final performance against its 2014 logframe targets. It captures the achievements over the course of the programme and the lessons learned that will inform the design and implementation of future DFID support for regional trade and integration in Southern Africa. / In reading this PCR it is important to take into consideration that TMSA closed six and a half months early on 17 March 2014 and that its activities and delivery were constrained from May 2013 following notification by ICAI of their concerns. The 2013 Annual Review, based on the interim evaluation that reported in August 2013, recommended revising the logframe targets to make them more realistic and measureable. This was not taken forward due to the decision to close TMSA early. / The PCR uses the latest available data to DFID. In most cases this is the Independent Evaluation which was finalised in December 2013.
Output 1: Strengthened trade policy implementation capacity
Output 1 final score and performance description: Overall score B – output moderately did not meet expectation. / Output Indicator 1.1: Implementation Status of Free Trade Agreement between COMESA-EAC- SADC (TFTA) / Final Results: / (i) TFTA agreed by 13 member countries of the COMESA-EAC-SADC Tripartite / Progress moderately did not meet expectations against the ambitious target of agreeing the TFTA between 13 member countries. The Tripartite aims for a signature at the Third Tripartite Summit which had been planned for June 2014 (now delayed due to the impact of the closure of TMSA), so it is possible that the target could be met in the coming months. / The Tripartite Summit is provisionally planned for October/ November 2014. What is clearer now, however, is that any agreement reached at the Summit will be substantially less ambitious and beneficial to the poorest than had been envisaged when the programme was designed, or in the earlier years of its operation. It should be pointed out that delivery of the target was largely outside TMSA’s control, since they could not directly influence the negotiating position or the degree of political will of member states to agree and implement agreements. / Good progress was made in a number of areas including the annexes on customs and Non-Tariff Barriers (NTBs), Sanitary and Phytosanitary Standards (SPS) and Technical Barriers to Trade (TBT); and, most countries have exchanged tariff offers. There are a significant number of areas which need further negotiation, including tariffs and rules of origin, so while a political agreement could be reached at the Tripartite Summit, substantially more work is likely to be needed after that to finalise the deal. / DFID has committed to supporting the negotiations through the Trade Advocacy Fund (TAF) until October, but various delays – including the need to ensure Value For Money (VFM) and renegotiate the management contract – meant that negotiations have de facto been suspended since the closure of TMSA, although as at 17 June it looks probable that TAF support will be in place so that negotiations can resume in late July. / The vision for the Tripartite FTA was to stimulate trade and wealth creation through eliminating tariffs across Tripartite countries and simplifying trade through addressing the overlapping rules between RECs, for example on rules of origin (these are used to determine a product’s origin and hence the duty that is applied). It is now clear that the negotiated outcome is likely to fall short of these ambitions. At present, the most likely scenario is that the limited liberalisation of tariffs – perhaps 60% upon launch of the TFTA and a further 25% during a phase-down period - and the limited prospect for changing SADC’s restrictive rules or origin, will mean that the TFTA if agreed and implemented could have limited impact on trade in the region. / The closest scenario (scenario 6[6]) in the TMSA-commissioned Institute of Development Studies (IDS) Computable General Equilibrium (CGE) study on the impact of the TFTA, which was published in October 2013, estimated net welfare gains of US$ 100m per year (compared to US$ 578m if all tariffs were eliminated and US$ 3.3 billion with all tariffs eliminated, plus substantial improvements in trade facilitation). Under this scenario, total intra-regional trade is forecast to increase by US$ 250m (representing 0.6 percent of existing intra-regional trade). / Even a low ambition TFTA would bring a range of benefits. It would demonstrate political commitment to regional economic integration; it could provide a useful framework for advancing harmonisation on trade facilitation measures - this is where the biggest gains could be made anyway; and, it could be possible to build in provisions to ratchet further progress in the future. / From a poverty perspective, as with any trade negotiation there may be winners and losers. Both the ICAI and Independent Evaluation reports pointed to the need for greater attention to the poverty impact of the TMSA programme at country level, particularly relating to the TFTA. In response, DFID disseminated the CGE study through DFID and FCO country offices in the region. The DFID-funded TAF is providing country-level grants able to provide analytical and capacity support in the TFTA negotiations as required to Ethiopia, Uganda, Burundi, Zambia, Malawi, Mozambique and Lesotho. A second phase grant to the EAC (following a successful phase 1) has been approved to support the EAC and its member states. The EAC and SACU have also carried out their own CGE studies on the possible impact of the TFTA. / According to the Independent Evaluation, “TMSA played an important role in supporting the RECs to put in place the building blocks for the FTA” (p. 4). TMSA played a leading role in getting the TFTA negotiations launched and assisted with the development of much of the strategy and background documents, draft agreements and principles, and institutional frameworks and principles. TMSA succeeded in ensuring the negotiating schedule was maintained with negotiating meetings well organised. This saw them absorb additional administrative and technical demands due to the decision by the Tripartite Taskforce Negotiating Forum (TTNF) to introduce Technical Working Groups (TWGs). In August 2013, TMSA secured funds from the Trade Advocacy Fund (TAF) for most of the costs related to the TWGs. / (ii) Tripartite Countries: Trade policy capacity of at least 200 trade officials in Tripartite countries improved, of which at least 50% will be women for negotiation and implementation of TFTA / By October 2013, 179 negotiators from 22 countries had been trained in total, of which 37% were women. According to TMSA reporting, those trained on average assessed the courses as very good, relevant and useful. Had TMSA not closed early, the target of training 200 trade officials would have been met, although less than 50% would have been women. (It should be noted at this point that selection of individuals at the national level was not in TMSA’s control.) / Output Indicator 1.2: Extent (frequency and quality) of participation by individual countries or groups in multilateral /continental trade agreements and programmes. / Final Results: / (i) LDCs technical and negotiating capacity strengthened / Although it is difficult to measure TMSA’s contribution to strengthening capacity, performance is assessed as having met expectations. Ahead of the Bali Ministerial Meeting, TMSA helped the LDC Group prepare its work plan and provided technical support on specific areas, including rules of origin and the LDC services waiver. Independent feedback from the Trade Advocacy Fund and the WTO praised the quality of TMSA’s training material. / (ii) favourable positions developed and/or negotiated resulting in, at least, an agreed LDC package within DDA / It is also difficult to measure TMSA’s contribution to this target, but on balance performance is assessed as having met expectations. TMSA played a significant role in supporting the LDC Group in the lead up the Bali Ministerial Meeting in December 2013 at which the Trade Facilitation Agreement and specific LDC measures were agreed. / (iii) wider scope of subjects covered in WTO by 2014 / The WTO and its members are now considering its post-Bali agenda, although talks are developing slowly and it is unlikely that the agenda will be broader than the original Doha Development Agenda (DDA). The demand for TMSA’s services remained consistently high. However, given the need to focus, and given the numerous agencies supporting the LDC group, it may have been more appropriate for TMSA to withdraw from supporting the LDC group once the chair passed from Zambia to Bangladesh in 2011. / Lessons Learned / The limited capacity of RECs and the limited capacity of rotating member state Chairs meant that negotiations were too easily dominated and derailed by the countries with the strongest capacity. Analytical support to the poorest countries, while welcomed, was insufficient. More attention should have been given at the outset to these issues. The establishment of an independent and well-resourced secretariat would have improved the process and likely outcomes. / DFID will ensure that all its trade interventions are underpinned by more robust poverty analysis to inform programme and intervention design, approach to implementation and monitoring. The impact of trade reform on poverty will depend on a range of factors, most of which will be determined by national level policies and capacity. This necessitates a much stronger focus on supporting national level analysis and ensuring that regional trade and integration commitments inform, and are informed by, the country-specific context. This implies that future DFID regional trade and integration programmes should be designed and implemented in close collaboration with DFID country offices. / A full and independent review should be carried out on the TFTA to inform the remainder of the negotiations to get the best possible outcome in terms of growth and poverty reduction. It will also be important that a comprehensive lesson-learning exercise informs the preparations for the Continental FTA. / A clearer engagement at the country level, including analysis of how country level interventions could help to promote and implement regional agreements, would have sharpened impact and delivery. This points to the importance of shared objectives with DFID country offices in terms of how regional programmes set objectives, and how regional and country offices best co-ordinate their efforts in the implementation phase.
Impact Weighting (30%): / Revised since last Annual Review? Y/N / Risk: High / Revised since last Annual Review? Y/N
[6] Scenario 6 is full liberalisation of capitals good only, 80 percent tariff cuts on intermediate goods and 50 per cent tariff cut on consumption goods. This does not factor in any effect for restrictive rules or origin which would further reduce the effects of liberalisation.

Output 2: Reduced trade transaction cost and transit times in the Tripartite region through improved and harmonised trade and transport facilitation measures
Output 2 final score and performance description: Overall score C – output substantially did not meet expectations. / Output indicator 2.1 - Reduction in transit times and costs along the NSC / Final Results: / All agreed trade and trade facilitation measures implemented in all 8 NSC countries, resulting in reduction of 30% transit times along the NSC and the average transport / transit cost by at least 20% / The Tripartite Task Force adopted the Comprehensive Tripartite Trade and Transport Facilitation Programme (CTTTFP) in 2010. Progress was made on some elements; for example, a study on road transport liberalisation was completed (during the closure period of TMSA); preparatory work began on a model law on axle loads and vehicle dimensions; and implementation arrangements for interfacing the Yellow Card (third party insurance) and Fuel Levy System were developed and implemented by Lesotho, Namibia and Swaziland. The Independent Evaluation found that “In most other areas, the initial diagnostic or technical work has begun, but implementation is far from complete. This is most notable in the raft of regulatory reforms in design to harmonise vehicle standards and customs arrangements, and to liberalise the road and aviation markets. Whereas it is expected that this effort will over time contribute to a more effective approach to standards and transport regulation, and that this will be positive for trade, it will take time for member countries to agree to and implement such measures” (p5). / The independent evaluation further found that “each intervention is being pursued in a complicated context” (p38) and “according to the evidence provided, it would seem that there has been limited demonstrated commitment by member states to agree to and implement urgent action in these areas. This is largely because the intention of the CTTTP remained unrealistic in terms of timing, content of expected outputs, organisational support and structure and the type and extent of technical assistance to be deployed” (pp 37/38). Furthermore, private sector participants interviewed raised concerns that “because the participation of the private sector is constrained, practical trade experience is not adequately applied to interrogate the feasibility of policy provisions and their operationalisation” (p. 28). / TMSA GPS data shows that transit times along the North South Corridor (NSC) between Durban and Lusaka fell by 39% and costs reduced by 27% (using 2011 South African Road Freight Association’s Vehicle Cost Schedule) between the 2009 baseline and 2013. It seems reasonable to conclude that TMSA made a contribution to this reduction through its advocacy and technical support for improvements at national level for improved customs procedures and integrated border management. However, other than the Chirundu One Stop Border Post (OSBP), the lack of implementation of the CTTTP or infrastructure rehabilitation makes it difficult to attribute more than a modest reduction in transit times and costs to TMSA. / Output indicator 2.2 - Number of border crossings within southern Africa, which cut average crossing time by 30% or more / Final Results: / Four border crossings improved within the SADC and COMESA region resulting in at least 30 % average reduction in border crossing times at these improved border sites / The Independent Evaluation found that “Chirundu is regarded as a unique example of a successful one stop border post” (p34) and that “the benefits have been tangible: the OSBP resulted in more efficient traffic circulation, increased capacity for handling large volumes of traffic, reduced costs of doing business in the region, and increased revenues for customs officials” (p34, original source OECD 2013). / Although most of the work in setting up the OSBP was completed prior to this programme, TMSA helped to ensure continued efficiency improvements in a difficult operating environment over which they had limited control. Due to factors of increased traffic flows (by around 10% between April 2012 and April 2013 on the northbound route and by 30% on the Southbound route)[7], traffic management and excessive risk control through scanning and political decisions, crossing times increased to approximately 30 hours in mid-2013 from a low of about 24 hours in 2012; however, this was still 69% below baseline (based on a 96 hour baseline). The Independent Evaluation could replicate these savings and recognised the substantial efforts made by TMSA to ensure that the methodology was transparent and sound. However, it had concerns about the comparability of data in terms of sample and collection techniques, including the baseline where, for example, World Bank data for 2007 showed a 38 hour average transit time (which would result in savings of 21%). / Limited progress was made on the three remaining border posts due to various difficulties in facilitating the necessary bilateral agreements and commitments, including the concessioning of border posts under the previous Zambian government, with TMSA only re-engaging in mid-2012: / On Kasumbalesa (a border between Zambia and the DRC), the failure to secure political agreement for the introduction of a OSBP by Democratic Republic of Congo (DRC) national and provincial governments prevented meaningful progress, although TMSA carried out scoping missions, worked on sensitising stakeholders and organised meetings to discuss how to operationalise the OSBP. / On Nakonde-Tunduma (a border between Zambia and Tanzania), TMSA carried out a situational analysis; a first round of physical border monitoring surveys; a scoping mission; and the development of work programmes. A change in responsibilities between ministries in Tanzania limited progress in early 2013. The 30% reduction would not have been met in the time remaining. / On Beitbridge (a border between South Africa and Zimbabwe), although TMSA and its predecessor programme, the Regional Trade Facilitation Programme (RTFP) supported the design of the Beitbridge Efficiency Management System (BBEMS) no progress was made on implementation. From 2011, no further role for TMSA was required by the Government of South Africa who had by now prioritised this under its Presidential Infrastructure Championing Initiative. / Alongside its work on specific border posts, TMSA also provided support to Integrated Border Management in Zambia and Zimbabwe. This was based on the principle that improvements and harmonisation of policies and procedures needed to be addressed centrally, both within and across countries. Progress was made in Zambia, but it was limited to the design of a strategy in Zimbabwe. / Output Indicator 2.3 - Percentage of non-Tariff Barriers (NTBs) reported that are resolved for countries in Tripartite area / Final Results: / (i) 50% of reported NTBs are resolved for countries in the Tripartite area and NTB system functions effectively / The NTB reporting system was initiated under the RTFP and was improved and expanded under TMSA. According to TMSA reports, 20 of the 22 participating countries now have functional NTB committees, training was provided to private and public sector focal points in 21 countries and 14 countries are able to process complaints online. The online NTB reporting, monitoring and elimination mechanism performed above expectations with 82% of reported NTBs resolved by June 2014. According to TMSA reports, the average number of days taken to respond to a complaint fell from 1,092 days in 2010 to 161 days in 2012. / All those interviewed by the Independent Evaluation team identified the NTB system as a success; specifically, the interview data suggested that accessibility, procedural formality, transparency and public accountability are the key elements that combine to make this system work” (p.37). / (ii) Operation and maintenance of the Tripartite NTB system has been transferred to stakeholders in region / The early closure of TMSA impacted on the sustainability of the NTB reporting system which is widely valued by government and private sector stakeholders in the region. The 2013 Annual Review (AR) highlighted that while the e-reporting mechanism could be transferred to another platform, e.g. one of the RECs, it was not clear how it would be resourced. Due to its importance, DFID is funding the continuation of the NTB reporting system’s website until October 2014. A number of international partners have expressed an interest in taking over the NTB reporting system, so it should be sustained, albeit through international rather than regional stakeholder funding.
Lessons Learned / Overall approach / The need for a much stronger political economy analysis at the outset to understand the drivers and blockages of regional integration at the country level. This should inform the theory of change and programme and intervention design. The role and importance of South Africa needs to be clearly understood and harnessed to ensure that regional programmes fully understand incentives for co-operation and the scope for economic and welfare gains and losses are fully factored into analysis. This would also help to set out a clear and robust influencing and risk management strategy as the programme is designed, developed and implemented. / Looking ahead, in the case of the CTTTP this would warrant a review of the potential for progressing the various initiatives and focusing down on what is achievable and likely to have the greatest return. This is likely to lead to a variable approach to implementation across countries. / Coupled with the need to focus on the political economy of regional integration, significantly more resources should have been focused at country level. So for example, the work on Zambian integrated border management and border post improvements should have been implemented by a TA team based permanently in Zambia, with appropriate delegated authority. / There are lots of actors working on trade facilitation, but no effective formal mechanisms for coordination. It will be important that future DFID support in Southern Africa is designed to facilitate improved coordination and coherence between international partners. TMEA is one model for doing that in East Africa. / For DFID, overlapping REC jurisdictions and initiatives also necessitate coherence between DFID’s support for trade and integration across Africa. Approaches, criteria, and decision-making should have a minimum coherence across Africa in a common results framework. / TMSA’s monitoring of transit times on the NSC was valuable for measuring progress and key bottlenecks. Disaggregated monitoring data to show separately benefits for accredited transporters and the rest, and also differential effects of interventions and what package of IBM interventions are optimal for generalised or specific gains. This in turn would inform increasingly effective IBM programme design. / Cross cutting issues / The impact of interventions on small scale traders (approximately 70% of which are women), should be integrated into programme design, implementation and monitoring. / Activities should be aimed at reducing or standardising fees, levies or charges imposed by member states which have a direct bearing on the cost of goods to consumers and especially the poorest. This should include an explicit focus on anti-corruption measures and activities. / The Independent Evaluation considered Chrirundu to offer an example of how the deliberate integration of cross-cutting considerations into intervention design could work. In this instance the attempt to address trans-national transport as a primary vector of HIV/AIDS by including a prevention, care and treatment intervention at Chirundu, has demonstrated some success. Despite challenges, it has also resulted in a potentially sustainable outcome, with the mobile clinic on site now managed by the Zambian national Ministry of Health. In addition, the incidental benefits to small scale traders, primarily women, have also been documented (p36). / NTBs / There are widely applicable lessons to be learnt and applied to future interventions, from the effectiveness of the NTB reporting mechanism, in particular the key elements of accessibility, procedural formality, transparency and public accountability. / Further work is needed to scale up the NTB initiative and to ensure that surveillance mechanisms established at the regional level are matched with enforcement. / Impact Weighting (30%): / Revised since last Annual Review? Y/N / Risk: Medium / Revised since last Annual Review? Y/N
[7] Zambian Revenue Authority (ZRA) statistics (p34)

Output 3: Improved regional trade infrastructure networks in the COMESA and SADC regions (especially the NSC and its spurs)
Output 3 score and performance description: Overall C – Output substantially did not meet expectations.
Progress against expected results: / Output Indicator 3.1 - Cumulative km of regional transport corridor trunk road built, rehabilitated and/or under construction along NSC in Southern Africa / 1040 Kilometres / Final Results: / TMSA can claim some contribution for 546.5km of the NSC under construction or with construction about to commence. This target measured the contribution TMSA made to increasing the focus and financing for the NSC through its convening role, advocacy and technical support. The table below sets out roads under construction in 2010 (to which TMSA did not contribute given funding decisions were taken prior to the establishment of TMSA); roads under construction since 2010 (for which TMSA can reasonably claim some contribution); and roads where construction is pending (which has been counted towards the target as contractors are being mobilised and construction will begin soon). The Independent Evaluation confirmed that the planned investments by some donors across specific areas of the NSC were formulated on the back of empirical and preparatory work of TMSA and the PPIU (p.43). / This target does not capture the impact TMSA had in terms of championing the corridor approach (focusing on both soft and hard infrastructure) and specifically the NSC. TMSA used the HMD4 study, produced by its predecessor programme RTFP, to make the case for the corridor approach calculating the net present value (NPV) and internal rate of return (IRR) of the entire corridor, and also estimated the cost of backlog maintenance and periodic and regular maintenance. The Independent Evaluation found that the NSC has been viewed as ‘best practice’ in AfT reviews (e.g. WTO, AfT at a Glance, 2009) and has led to the corridor approach being adopted by infrastructure development funders. The majority view among interviewees from RECs, governments and donors, was that the additional technical input provided by TMSA introduced a regional focus to transport infrastructure planning that previously did not exist (p41). / NORTH SOUTH CORRIDOR PROJECTS UNDER CONSTRUCTION / Under construction in 2010 / NSRo-038 Pandamatenga - Nata Link 2 135 Botswana / NSRo-073 Iringa - Iyovi Link 1 60.1 Tanzania / NSRo-074 Iringa - Iyovi Link 2 7.4 Tanzania / NSRo-075 Iringa - Iyovi Link 3 84.9 Tanzania / Sub total (underway in 2010) 287.4km / Under construction since 2010 / NSRo-040 Nata -Sebina Junction Road 140 Botswana / NSRo-042 Tonata-Francistown 40 Botswana / NSRo-006 Kitwe - Chingola Road 50 Zambia / NSRo-013 Lusaka - Chirundu Link 1a 3.8 Zambia / NSRo-014 Lusaka - Chirundu Link 1b 10.7 Zambia / NSRo-015 Lusaka - Chirundu Link 2 39.6 Zambia / NSRo-016 Lusaka - Chirundu Link 3 19.5 Zambia / NSRo-072 Igawa – Iringa Link 3 75.9 Tanzania / Sub total (since 2010) 379.5km / Construction not yet started / NSRo-070 Igawa – Iringa Link 1 60 Tanzania / NSRo-071 Igawa – Iringa Link 2 82 Tanzania / NSWb-001 Kafue Weighbridge N/A Zambia / NSR0-018 Lusaka-Chirindu Link 4 25 Zambia / Sub total (construction not started) 167km / TOTAL (all) 833.9km / Output Indicator 3.2 - Number of Infrastructure Projects in Tripartite Area financed or in preparation for financing / Final Results: / (i) 19 projects financed or in preparation for public/DFI/donor financing / 10 projects were prepared or under active preparation: / 2 project where TMSA, directly or through the Project Preparation Implementation Unit (PPIU), was involved in preparation with TTA funding (Kafue Weighbridge, Lusaka-Chirundu Link 4). / 3 projects where design virtually completed by PPIU/TMSA and funding was being sought for construction (Serenje-Nakonde links 1-3). / 1 project for which the PPIU had been supporting preparation for World Bank funding. With the closure of TMSA, the WB will also commission and finance the design the project. (Karonga-Songwe). / 3 projects with Request For Proposals (RFPs) ready for design by PPIU/TMSA subject to securing design funding (Victoria Falls-Bulawayo links 1-2, Sir Otto Beitbridge). / 1 project where TMSA was instrumental in setting up the Project Management Unit for the project and has provided further technical support (Zambia-Tanzania-Kenya Interconnector). / In addition to those under active preparation, there are 10 projects (when the individual road links are counted) identified which the PPIU/TMSA will design with NEPAD Infrastructure Project Preparation Facility (IPPF) funding and, following the closure of TMSA, with core funding from the EU until a longer-term solution can be found. / More broadly, TMSA also supported the development of the SADC Infrastructure Masterplan culminating in an Investment Summit in June 2013 and produced the Tripartite Infrastructure Database (TRIPDA) which will be sustained by NEPAD under the PIDA process. / TMSA also played an important behind the scenes role in supporting the capacity of national roads agencies. The Independent Evaluation found that “through support to national agencies and through the establishment of the PPIU, there is evidence of increased capacity to plan and manage infrastructure projects in the region” (p. 8). Specifically, the wholesale replacement of technical capacity at the Zambian Roads Development Agency, twice during the lifespan of the TMSA programme, was mitigated by the continuity of the PPIU support (p43). / (ii) 5 Infrastructure Projects in Tripartite Area financed or in preparation for public-private involvement / Just one project had public-private involvement: the DRC-Zambia Energy Interconnector, which was 45% funded by the TTA and 55% by the Copper belt Energy Company. / As with the previous target for projects prepared, in setting these targets, DFID, TMSA and the Tripartite underestimated the time it takes to prepare projects to bankability and, in the case of public private partnerships, the extent of the viability gap (the subsidy needed to make a project financially viable for private investment) for the economically important road and energy interconnector projects prioritised by TMSA and the PPIU. / (iii) £67m of CDEL in TTA committed / The Tripartite Trust Account (TTA) was a multi-donor fund set up in 2010 at the Development Bank of Southern Africa following the successful North South Corridor Conference in 2009 funded by DFID. The £67m TTA Capex element of the programme marked a DFID decision to take a first mover role to drive forward the idea of a regional corridor approach and to stimulate funding behind this to upgrade regional infrastructure along NSC. The aim was to catalyse financial resources for infrastructure projects along the NSC. Despite an overall $1.2bn pledge from donors for support, DFID committed the only new money of £100m (the TMSA programme) and the TTA did not succeed in attracting any other finance beyond a £1m contribution from the DBSA. / Only 34%[8] of the funds were committed or approved to 3 projects (Link 4 Chirundu to Lusaka, Kafue Weighbridge and the DRC-Zambia interconnector). For each project, contracts have been signed for construction and technical support, and construction is due to commence in the third quarter of 2014 and to be completed by June 2015. DFID will monitor implementation closely. / The remaining balance of the TTA had been earmarked for blending with other finance to fund the 604km Serenje-Nakonde road (estimated total cost US$600m). Ongoing problems in finalising detailed designs and the absence of ready funding from government or international partners prevented DFID TTA funding being committed to this project. / The IAD audit found that the £67m had been provided in advance of need. Although this had been approved at the time, this was contrary to HMT policy and good practice. Therefore DFID requested the return of all uncommitted funds in November 2013. DBSA returned approximately £44,000,000 in January 2014. / Output Indicator 3.3 - Number of Corridors with robust performance monitoring systems and geospatial information systems in place / Final Results: / (i) Robust performance monitoring systems for 3 corridors in place / The Independent Evaluation found that TMSA had put a lot of resources into developing a GPS corridor monitoring system that generated a unique set of performance information (p43), covering key border posts and the NSC from Durban to Lusaka. The Evaluation praised its transparency, but made a number of recommendations for improvement (see lessons learned below). The Independent Evaluation found there was substantial interest expressed in the data and its analysis, but that none of their interviewees were aware of any use being made by the corridor data being generated (p44). / TMSA did not extend its performance monitoring to corridors other than the NSC. / (ii) Comprehensive, online GIS database expanded and applied in 3 Tripartite corridors and widely accessed / The comprehensive online Geographical Information System (GIS) was extended to cover all major corridors in the Tripartite area. It was a valuable resource that was widely accessed with nearly 4000 visitors from 84 countries between April and September 2013, of which 1890 were unique visitors. It is not clear whether and how this will be maintained, but DFID understands that NEPAD may be interested in taking this forward as part of the PIDA project. / Output Indicator 3.4 - Gigawatt hours of electricity per year traded across new cross-border interconnectors / Final Results: / Additional 2800 GWh of energy traded across new / upgraded regional interconnectors in SAPP / EAPP / This is a priority regional project, featuring in the SADC Infrastructure Masterplan, which will deliver DFID’s High Level Operational Plan target of 2800 gigawatt hours of electricity traded per year. / Progress was delayed due to a range of factors including the quality of the project documentation; the quality of appraisals – meaning DFIDSA had to request additional information on a number of occasions; a negotiation-down of the grant component; and because DBSA went through a major reorganisation in 2013 which limited their ability to drive progress; and, finally, a delay in early 2014 to allow the SoS DFID to review all committed projects for VFM. / This project is due to be completed by June 2015, overseen by DBSA. We have agreed with the DBSA that they will carry out regular onsite progress reviews, reporting quarterly to DFID during construction and monthly prior to construction. This will include an early warning of risks to delivery, timelines and political risks. / Lessons Learned / The corridor approach championed by TMSA – including through its summary project sheets and diagnostics - was successful in focusing attention of national government and financiers on the NSC. / Taking a ‘developmental corridor approach’ could increase the impact on generating trade and poverty reduction (e.g. linking to the corridor to productive sectors, value chain development, growth points such as Economic Development Zones, connecting to rural roads etc.). / A lack of clarity at the outset about the specific roles, responsibilities, accountabilities and Key Performance Indicators (KPIs) around project preparation led to significant delays, duplication and inefficiencies. These need to be agreed and formalised at the outset, with payment and/or performance assessments linked to these. / Preparing successful projects to the point of finance requires specialist project finance and investment expertise. This needs to be reflected in the staffing of project preparation facilities. / Given the size of the PPIU’s pipeline and the opportunity costs of preparing projects that do not secure finance, it would be appropriate to carry out a rigorous assessment of bankability to determine the prioritisation of projects. / Before considering putting money into trust funds, DFID should carry a rigorous assessment of the strength of the project pipeline in order to avoid long lead times which may not result in successful project financing. Funding cannot be provided in advance of need. / Impact Weighting (25%): / Revised since last Annual Review? Y/N / Risk: Medium / Revised since last Annual Review? Y/N
[8] This has been reduced from 38% of funds committed as recorded in the 2013 Annual Review due to a reduction in the management fees being charged by DBSA.

Output 4: Enhanced Productive and Export Competitiveness of the Regional Economy
Output 4 score and performance description: Overall C – Output substantially did not meet expectations.
Output Indicator 4.1 - Harmonised approach on regional industrial development / Final Results: / Implementation of at least 2 regional industrial development policies / strategies and / or measures commences in the Tripartite region / In 2012, it was agreed by EXCO (TMSA’s governing board which consists of DFID, COMESA and TMSA) that TMSA would engage on this new Tripartite work stream in their role providing technical and administrative support to the Tripartite, but that their engagement would be capped. The 2013 Annual Review recommended that TMSA disengages from this area and no further activities had been planned. / Baseline studies on “Situation Analysis/Stocktaking of Industrial Policies and Programmes” and an “Assessment of Demand and Supply Situation for Agro-processing, Mineral Processing and Chemical Industries in the Tripartite Region” were completed and discussed at a regional stakeholder workshop. A technical committee on Industrial Development was established and a draft work programme and roadmap was agreed by the Tripartite Task Force, but not approved. / Output Indicator 4.2 - Progress in implementation of standards, technical regulations and Sanitary and Phyto Sanitary (SPS) measures in COMESA-EAC-SADC Tripartite. / Final Results: / (i) TFTA provides framework for implementation of technical standards for identified, priority products and SPS measures / Good progress was made on the TBT and SPS annex of the TFTA, although the outcome of the TFTA remains uncertain. At the time of its review, the Independent Evaluation found that progress towards the development of regional SPS and TBT frameworks had been weak due to the fact that implementation was still at an early stage (p45) and that these frameworks or work programmes are unlikely to be concluded by the project end date. (p6) / Most of the specific standards and SPS projects were inherited from a previous DFIDSA programme, ComMark, and were scaled back and closed down during implementation of TMSA. Although both ICAI and the Independent Evaluation considered them to be a poor fit for TMSA, a number were effective in their own right and strengthened national capacity (such as Marine Stewardship Certification in Mozambique which secured continued access for fish products to the EU market). / (ii) Enhanced capacity to implement specific standards and SPS measures, which were developed / agreed, in at least 8 Tripartite countries / No measures developed/agreed across at least eight countries. The Independent Evaluation found that “despite support given to specific products and institutions, the extent to which this has been translated into increased market access and participation in more profitable value chains is limited and uncertain. It is therefore too early to assess whether these interventions will give rise to higher and more sustainable trade flows”. (p45) / Output Indicator 4.3 - Increased use of mitigation initiatives to reduce risks to market access / Final Results: / 5 initiatives and / or pilots implemented in Tripartite countries / In 2013 progress had met with expectations with four fruit fly projects operational in 4 countries (Zimbabwe, Malawi, Swaziland and Zambia) providing among other things capacity building for officials, farmers and traders. The Independent Evaluation identified that in addition to export competitiveness the fruit fly projects would bring improvements to local markets, improve local consumption and mitigate threats to food security (p 55) / However, DFID’s IAD found that in the case of the Zimbabwe Fruit Fly Project, since 2011 £80,000 had been channelled through Government of Zimbabwe systems, in contravention of UK policy – hence this project was closed immediately. Taking this into account, progress substantially did not meet with expectations. DFID funding for all the remaining projects and the planned fifth project in Botswana ended with the closure of TMSA. / Lessons Learned / It is important to review the value of supporting a regional approach to economic competiveness. While value chains are essential to trade, it is questionable whether a regional approach to value chains works and it risks picking winners and leading to protectionism. / To improve the selection and impact of SPS projects, the Independent Evaluation recommended that: (i) there needs to be a clear linkage between the SPS issue and a trade constraint and the removal of the constraint should conceivably lead to increased trade flows; and, (ii) a business case should be made before the SPS related project is carried out. There needs to be a clearly laid out value chain map for each selected commodity (many such studies exist and merely need to be updated to take account of changing circumstances). Within the value chain map any SPS intervention can be outlined if seen as a constraint. The intervention can be mapped at various levels from higher end policy and standards all the way down to farm level actions (p49). / Impact Weighting (10%): / Revised since last Annual Review? Y/N / Risk: Medium / Revised since last Annual Review? Y/N

Output 5: Enhanced TradeMark Southern Africa processes and outcomes through effective communication, knowledge management and influencing
Output 5 score and performance description: Overall C – Output substantially did not meet expectations.
Output Indicator 5.1 - Improved Functionality and Effectiveness of Management Information System (MIS) / 2014 target - 100% timely and relevant compliance reporting (TMSA staff member project / fact sheets; TMSA update to DFID; TMSA monthly update, 4 quarterly reports, annual reports) / Considerable work was put into preparing a comprehensive MIS system, with detailed quarterly projects linked to the workplan in place by November 2012, with further iterations over 2013 improving their usefulness, including for example through improving alignment with the logframe/work plan and budget. Despite the efforts, the project sheets were not prepared on time and lacked sufficient detail in terms of milestones to monitor ongoing progress or commercial indicators (e.g. actual vs project spend). This meant they could not be used as a useful basis for analysis of higher level TMSA reporting by DFID and COMESA. / Despite progress on putting in place baselines and M&E systems over the implementation period, the Independent Evaluation considered the M&E system to be insufficient for a project of TMSA’s scale. Had TMSA not closed early, it had been intended that TMSA would work with the Independent Evaluation team to ensure impact could be measured, including where possible poverty impact – for example on informal traders at borders. This would have also included extending the utility of GPS monitoring data for measuring the impact of trade facilitation and other transit and infrastructure measures. / Output Indicator 5.2 - Extent of global and regional awareness / recognition of TMSA as regional integration resource / 2012 Milestone - 30 000 Unique Followers, 40% Loyal Followers / Milestone score and performance description: A – Output met expectations. / Progress against expected milestones: / There were 227,491 people reached by TMSA communications between 1 April 2012 - 30 June 2013 of which 26% were loyal followers (based on repeat visits, likes, followers or subscribers). The table below shows that website visitors declined by over 10% since 2011-12, but visitors to the NTB website more than doubled as did visits to the e-GIS system, demonstrating the increasing reach of these tools, particularly the NTB website. / Had TMSA continued it would have been important to amend the target to match the reporting data that was available. / 11Output Indicator 5.2 indicators by communication type: / Communication type 2010 – 2011 2011 – 2012 1 April 2012 – 30 June 2013 / Unique visitors p/m Total unique visitors Unique visitors p/m Total unique visitors Unique visitors p/m Total unique visitors / TMSA Website not measured 22316 13252 159029 11487 183800 / NTB Website not measured not measured 581 6983 1353 21648 / Tripartite website not measured not measured 424 5084 504 8015 / e-GIS not measured not measured 38 456 101 1515 / Facebook not measured not measured n.a. 150 likes n.a. 351 likes to date (201 new) / Twitter not measured not measured n.a. 30 followers n.a. 278 followers to date (248 new) / YouTube not measured not measured 3031 views (12 subscribers) at 27 videos 13409 views to date (34 subscribers) at 46 videos (19 new) / Newsletter subscriptions not measured not measured 450 subscribers 2136 subscribers (1686 new) / Newsletters sent not measured not measured 38 newsletters sent 87 newsletters sent / Total people reached: 22316 unique people reached with 24% loyal followers 175213 unique people reached (with 24% loyal followers) 227491 unique people reached (with 26% loyal followers) / Output Indicator 5.3 - Increased knowledge generation and sharing for influencing / advocacy policy reforms, strategy for RI / development in region / lesson learning for replication in Africa & Rest of the World / 2014 target - At least three complex trade & trade-related processes influenced through effective knowledge management and communication at any or all of the following levels: (i) regional (e.g. border post improvements), (ii) continental (e.g. TFTA experience influencing CFTA) and/or (iii) international (e.g. comprehensive approach to trade facilitation) / Two complex processes were influenced. / The 2011 Annual Review found that the successful piloting of the Chirundu OSBP had a powerful demonstration effect, illustrating the potential benefits for the region from integrated border management approaches, including OSBPs. / It is intended that the Tripartite FTA – both in terms of approach and the agreed FTA - will act as the building block for the Continental FTA. It will be important that it learns the lessons from the experience of the TFTA to improve on the process and the likely outcome. / At a lower level, the Tripartite Infrastructure Database (TRIPDA) will be used by NEPAD to inform the overall approach for recording key project information for PIDA projects. TMSA also produced a range of policy papers on issues covering infrastructure, trade facilitation and other areas, and participated in various technical working groups. / Impact Weighting (5%): / Revised since last Annual Review? Y/N / Risk: Low / Revised since last Annual Review? Y/N

## Section B: Results and Value for Money.

1. Achievements and Results
1.1 Has the logframe been updated since last review? NO / Despite the need to make the targets more realistic, attributable and measureable, the logframe was not updated following the last Annual Review due the focus on revising the policies and procedures in the PMM and the subsequent decision to commence closing the programme. / 1.2 Final Output Score and Description / The final output score is C - outputs substantially did not meet expectations. The score from the 2013 AR was a B, so it is reasonable to assume that greater progress would have been made had the 2013 Annual Review recommendations been taken on board and the programme continued until the end of October 2014. / 1.3 Direct feedback from Beneficiaries / This review is desk-based but it draws extensively on the Independent Evaluation which was finalised in December 2013 and it is informed by the ICAI report and the IAD audit. / These reports were informed by extensive consultations with partners and beneficiaries. As such the evidence base for the assessment of the programme’s performance is strong. / The Independent Evaluation drew extensively on direct feedback, triangulated with primary and secondary data and other sources of evidence. Interviewees included a range of government, REC, private sector, civil society and international cooperating partners, as well as TMSA and DFID Southern Africa. Feedback varied, but the independent review stated that TMSA had made an important contribution to supporting Tripartite regional integration in key areas, and had helped to improve member states trade negotiating capacity in the region. The ICAI report acknowledges that TMSA played a positive role in establishing frameworks for Tripartite negotiations and co-ordination of the North-South Corridor.
1.4 Overall Outcome score and Description / The outcome was “To improve Southern Africa’s trade performance and competitiveness for the benefit of poor people through regional integration.” / This was to be measured by the three outcome indicators set out below. These indicators were set at a very high level. In part due to over ambition and in part due to the lack of progress on the programme outputs, it is not possible to draw a credible link between the TMSA programme and the programme outcomes. / (i) Average annual un-weighted real growth in total trade by COMESA-EAC-SADC Tripartite countries / Target: 10% growth / Final result: 8.08% average un-weighted growth (using 2012 WDI data) / (ii) Logistics Performance Index (LPI) score for 20 Tripartite countries / Target: 2.49 unweighted for 2014 / Final result: 2.50[9] / (iii) Incomes from Trade-related economic activity of 1 million low income households: increase of 10% by 2014 / Target: increase of 10% by 2014 / Final result: not possible to measure. / The measurement of this indicator was problematic. Plans had been in place to measure this through a combination of qualitative border questionnaires (some of which were completed) and macro-micro modelling based on the TMSA-commissioned CGE analysis completed in 2013, but this had not been initiated by the time TMSA was closed. Also, the programme was too ambitious in its design in this respect. Poverty analysis was not comprehensive enough to track impacts or intended transmission mechanisms, either at the design stage or during the programme’s implementation. / 1.5 Impact and Sustainability / The Independent Evaluation found that “assessing the overall Impact of TMSA on poverty, growth and trade creation is problematic. The project is not large enough to have region-wide macroeconomic impacts, and in those areas where it might have such impacts (the conclusion of a region-wider trade agreement), the contribution of TMSA and the final outcome of the negotiations is difficult to measure” (p18). / The early closure impacted on the sustainability of TMSA’s work. The Tripartite is engaging with international partners to find sources of medium-term financing to support its agenda. In the interim, DFID is supporting the TFTA negotiations until October through the TAF, the EU plans to support the PPIU for an interim period (e.g. up until early 2015) and a number of international partners have expressed an interest in taking over the NTB reporting system. / Looking at longer-term sustainability, it will be important that member states, and the private sector where appropriate, take on greater responsibility for resourcing the regional integration initiatives. This would help to ensure greater ownership, translating into increased efficiency and impact. / The design of TMSA should have paid more attention to broaden the donor base so that the programme and support for the Tripartite’s objective in this area was less dependent on DFID. Sustainability could have been enhanced by a closer connection between regional and country objectives, including closer and more regular engagement with trade programmes and objectives being followed by DFID country offices: this would have better tracked the link between regional agreements and how these agreements were being translated into implementation at the country level.
[9] This is covers all Tripartite countries for which data is available, In the 2010 baseline year there were 20 countries which increased to 23 countries in 2014. The trend and score of 2.51 is very similar if taking only the 17 countries for which new data was available in both 2010 and 2014.

2. Costs and timescale
2.1 Was the project completed within budget/expected costs: Y/N: NO / The budget of the programme is £100,000,000, consisting of £33,000,000 for the Technical Assistance (TA) component and £67,000,000 for the Infrastructure Capex component. / As at 17 June 2014, the total spend was approximately £55,000,000. Of this, the final spend on Technical Assistance component was approximately £32,000,000 (including the £1,000,000 transfer to the TAF); and the final spend on the infrastructure component was approximately £23,000,000 (with all uncommitted funds returned to DFID in January 2014). / The IAD forensic audit found that there no evidence of fraud and that all funds could be accounted for. / 2.2 Key cost drivers / A large proportion of TMSA’s work programme was focussed on convening large meetings, conferences, training events and workshops on behalf of the Tripartite. TMSA had a range of measures in place to control costs: / TMSA questioned the value for money in convening events and did not fund activities that it considered would not progress the agenda– e.g. it did not fund the North South Corridor Senior Officials Meeting in 2013 due to the lack of follow up from the previous year’s meeting. / Where possible, TMSA opted to finance concurrent meetings (such as holding TWG and TTNF meetings concurrently) to reduce costs. / TMSA secured co-financing for meetings (such as with TAF on Tripartite FTA meetings and with Trade Mark East Africa (TMEA) on Nakonde-Tunduma Border post meetings. / TMSA make available documents electronically where possible to reduce the costs of printing (such as the SADC Infrastructure Investment Conference). / TMSA restricted the number of sponsored delegates (for example only 4 delegates per REC for official TFTA meetings and it did not sponsor member state participation). / Other key cost drivers of the programme include consultancy fees, funding of studies, programme administration and management costs. / The reviews found that administration costs were high in a number of areas, particularly per diems/travel expenses and salaries. While measures were in place to control these and the programme acted within the policies set out in the Project Management Manual (PMM), the policies and controls were not in line with DFID’s much more rigorous approach to VFM. These are covered in more detail in section 5.2: Commercial Improvement and Value for Money.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project / The TMSA programme was designed before the requirement to prepare a theory of change (ToC) was introduced. A comprehensive ToC was prepared by TMSA in early 2012. Analysis of the ToC by the Independent Evaluation team revealed the extent to which the programme was designed and being implemented according to a range of assumptions that were very broad and depended largely on the agency or engagement of others. The Independent Evaluation considered TMSA to be rightly ambitious in its aims and objectives, but it would appear that the ToC underestimates the complexity of the operational environment, the barriers and challenges it poses (p81)”. / To take the area of trade facilitation as an example, the effectiveness of TMSA activity in this area was premised on assumptions including “governments and other agencies have the capacity and resources to implement measures”, “border agencies are prepared to work together” and “phased implementation of harmonised road user charges can be agreed”. The Independent Evaluation found that it did not appear that this time element or complexities of the external environment have been adequately factored into the results chain, meaning that at this intermediate stage, TMSA’s achievements against the ToC were poor (p81). / Although not a change in the evidence base per se, the reviews of TMSA were clear that the programme should have had a much greater focus on poverty impact in design, monitoring and implementation. / 3.2 Set out what plans are in place for an evaluation / The TMSA Programme Memorandum provided for a Mid-Term Evaluation as TMSA was one of DFID’s highest profile and highest value programmes in the Southern Africa region. / In consultation with DFID Evaluation Department, DFIDSA decided to take a two-stage approach to the evaluation. The first stage was a predominantly theory-based evaluation which provided an interim report in August 2013 and a final report (referred to as the Independent Evaluation in this PCR) in December 2013. It had been intended that the second stage would have been an impact evaluation which had been planned for the end of the programme, but this was cancelled following the decision to close TMSA early. / The Independent Evaluation Report and DFID’s management response is available on DFID’s website at: https://www.gov.uk/government/publications/evaluation-of-trademark-southern-africa .

4. Risk
4.1 Risk rating (overall project risk): Low/Medium/High / Did the risk rating change over the life of the project? Y/N / The risk rating for the project did not change, although the 2013 Annual Review recommended that it should be reviewed given the challenge of implementing a programme of the scale and complexity of TMSA, the difficult political economy of regional integration and TMSA’s limited control over implementation. This was not acted upon due to the decision to close TMSA early. / Considering risk management more broadly, TMSA managed risks at project and logframe level but its approach to risk management was inadequate. DFID’s IAD recommended the introduction of an overarching risk register that would be integrated with project level risks and reviewed regularly at the EXCO meetings. ICAI criticised TMSA for underplaying large risks and overplaying low risks. It pointed to the risk of weak political commitment to the Tripartite as being medium, when they believed it should be high (p22). In fact in the original project memorandum, and subsequently confirmed at the 2011 Annual Review, this risk had been assessed as being of low probability. It could be argued that this fundamental overestimation of political commitment of national governments to implement regional commitments in TMSA’s design and implementation was the principle cause of its delivery failures. / 4.2 Risk of funds not being used for purposes intended / Investigations carried out by DFID’s Internal Audit Department and by the Independent Commission for Aid Impact (ICAI) revealed serious flaws in the governance and programme management of the TMSA programme. While no evidence of fraud was found, these investigations revealed a number of serious concerns including weakness in delivery, management, oversight and financial monitoring. According to DFID investigations, they in part stem from serious errors in the design and implementation phase in 2007 – 2010. TMSA guidelines were not updated to reflect ministerial priorities of value for money and good procurement practice. / Weak governance also resulted in payments amounting to £80,000 via ring fenced accounts held by the Ministry of Agriculture in Zimbabwe from 2011. Although our investigations show that this money was used appropriately and as intended for a fruit fly eradication project to promote trade and reduce poverty, this payment was in contravention of UK government policy. / 4.3 Climate and environmental impact / The most significant direct environmental impact of TMSA related to NSC infrastructure investments. These are assessed and mitigated during the project appraisal and implementation stages. Project funders, such as the international financial institutions, and the DBSA – who appraised and will be overseeing implementation of the TTA projects - apply stringent social and environmental safeguards policies to projects. / More broadly, TMSA’s contribution to increasing trade in the region and particular focus on NSC road corridor projects could have led to increased production, energy consumption and traffic flows. TMSA could not address the first two. On the third, TMSA developed a methodology for measuring the climate impact of the NSC with wider applicability. Had TMSA continued, a second-phase of this work would have modelled different scenarios to inform infrastructure planning.

5. Value for Money
5.1 Performance on Value For Money (VFM) measures / The TMSA programme was designed in 2009 before the current VFM guidance was developed, and therefore no VFM assessment was done on the programme at appraisal. The VFM section covers the main areas identified by DFID’s IAD review as key drivers of VFM: / Governance arrangements and reporting / Policies on asset management, fraud and conflict of interest / Cost management rules, procedures and policies / Procurement Performance. / TMSA’s Project Management Manual (PMM), prepared by DFID, TMSA and COMESA, was updated in February 2012 following TMSA’s move to COMESA. This set out policies relating to VFM-related areas, such as procurement, phones, travel, per diems and other expenses. COMESA’s external audits (carried out by Deloitte) identified no major issues and gave TMSA an unqualified audit and clean management report in 2011, 2012 and 2013. / However, ICAI raised serious concerns about financial management, reporting, procurement, salaries and DFID oversight. The IAD audit confirmed a number of these concerns and identified further risks relating to VFM captured below, most of which were also included in the final ICAI report. / 5.2 Commercial Improvement and Value for Money / Governance arrangements and reporting / TMSA was governed by the EXCO which consisted of DFIDSA, COMESA and TMSA. IAD judged that this did not provide sufficient scrutiny over TMSA delivery and operational issues. It was concerned that the TMSA Programme Director of the PMU had a dual role leading the delivery of the programme and making executive decisions on EXCO. It considered that the EXCO needed greater independence through the involvement of at least one non-executive member. They also identified that roles and responsibilities needed clarifying, particularly COMESA’s role as implementing partner whereby COMESA was making limited use of its own assurance systems other than in the area of finance to oversee programme implementation and VFM issues. / IAD also found that while TMSA produced a lot of reporting in response to DFID’s demands, which included the introduction in late 2011 of regular activity reports and in 2012 detailed quarterly project reports, reporting remained insufficient (in terms of coverage, quality and timeliness) to facilitate rigorous scrutiny by DFID or COMESA. / Policies on asset management, fraud and conflict of interest / The Memorandum of Understanding (MoU) between DFID and COMESA did not provide guidance in relation to the procurement, management and disposal of assets. While there was no evidence to suggest good practice had not been followed, there was a risk that that theft or misappropriation of assets might not be taken seriously thus leading to a lax attitude towards preserving assets. / None of the delivery partners maintained or managed Conflict of Interest (CoI) registers. While there was no evidence to suggest this in practice, it risked non-transparent decision-making which could in turn have led to poor value for money, collusion, fraud or other misuse of funds. Furthermore, COMESA, TMSA and PPIU did not have a clear Fraud Policy which presented similar risks. / Cost management rules, procedures and policies / The reports identified a number of areas where administrative expenditure on the programme was not in line with DFID’s current more stringent management of costs and Value for Money principles, including: / Travel costs / Per diems / Salaries / Tax / Phone charges / Travel Costs / The Independent Evaluation considered that travel costs were understandably high because TMSA was a regional programme, but significant savings could have been made on per diems/expenses in particular (see below). TMSA expenditure on travel (staff travel and sponsored delegate travel to meetings) made up around 9% of total TMSA expenditure between April 2010 to March 2013 (£2,011m). During 2012/13 travel made up 10% of the total spend, reflecting the increase in TFTA negotiation activity and costs. / Per diems / TMSA used EU per diem rates for those it sponsored and its own staff. The Independent Evaluation found that in 50% of cases benchmarked, these rates were above those of other comparators (p64). / To simplify administration it used a fixed rate of US$100 to cover expenses where TMSA had organised the event and accommodation and airport transfers were paid by the programme. The Independent Evaluation considered that although this may not be significantly out of line with other rates, it had the potential to affect programme level VFM through increasing the costs for TMSA staff that spent a considerable time out of the country on business. (p64). / From December 2013, no per diems were paid through the TMSA programme, with delegates provided with full board, airport transfers and accommodation only and TMSA staff claiming only actual expenses based on the provision of valid receipts. Savings were considerable. / Salaries / The reviews found TMSA salaries to be very high. Benchmarking by the Independent Evaluation team showed that the remuneration packages of the TMSA team, when compared with national and international comparators, exceeded those of senior civil servants in the South African government and average DFID salaries, with TMSA remuneration packages being closer to those of World Bank and IMF officials. / Tax / A significant related cost driver was that the programme paid the tax liability for staff based on South Africa. Legal advice obtained initially by DBSA in 2010 and confirmed in 2011, found that TMSA staff based in South Africa were liable for South African tax. This had a significant impact on Value For Money, increasing cost to company of South African-based staff (those based in Lusaka and Gaborone were tax exempt under COMESA’s host agreement with Zambia and SADC’s Host Agreement with Botswana). / Phone charges / Phone costs were high due to the amount of travel by TMSA staff given it’s a regional programme. Measures were in place to control costs including soft-lock levels of phones which require the Programme Director’s approval to lift, encouraging the use of local SIMS and Skype where possible and that staff pay for private calls. DFID challenged phone call bills on a number of occasions, but further VFM savings could have been found through closer monitoring and controls. / Procurement Performance / DFID’s Internal Audit concluded that the procurement policy in the PMM allowed for too much discretion which resulted in to little or no completion for the majority of contracts, accounting for 79% of spend. This was a major concern that had not been picked up in audits or by the previous Annual Review as TMSA has been operating in line with the procurement rules (albeit utilising excessively the flexibilities within the policy). The limited competition may have had a significant impact on costs, quality and consequently VFM. The following key issues were identified: / Framework arrangements/supplier databases did not require competition even though TMSA had negotiated reduced fees with most framework providers. / Procurement activities were not linked to the work-programme but there was no procurement plan in place. / Tenders were not kept in a locked up area and this increased the risk of tenders being tampered with, including access to commercial in-confidence information. / There was no separation of duties between the team that evaluated technical and commercial bids. / The Project Preparation Implementation Unit (PPIU) used both COMESA and TMSA procurement rules. / 5.3 Role of project partners / Both the technical assistance and infrastructure components of TMSA had originally been managed by the DBSA. In 2010, the decision was taken by DFID and the Tripartite to transfer responsibilities for the technical assistance programme from DBSA to COMESA, due to the lack of progress under DBSA’s management. / An MoU was signed between DFID and COMESA on 1 September 2010. The revised PMM finalised in February 2012, set out COMESA’s role as the implementing partner whereby it would be accountable for the programme to DFIDSA and responsible for providing fiduciary, legal and administrative support to for TMSA implementation. Due to the control, procedural and governance weaknesses set out above, DFID’s IAD found that COMESA had not been able to execute effectively its oversight role. / COMESA’s management fee was quite low. The MoU between DFID and COMESA set these at up to £600,000 based on actual expenditure incurred in managing the TMSA technical assistance programme of £30,600,000 (the balance remaining at that time, minus the funds retained by DFID for M&E). The final management are still being finalised with COMESA. / For the infrastructure component, a management fee of up to £2,000,000 was agreed with DBSA. At the point of the 2013 Annual Review, DBSA had charged £811,000,000 in management fees. DBSA’s performance had not been strong, in part due to a lack of clarity at the outset about roles and responsibilities and specifically DBSA’s role in project preparation. DFID renegotiated the fees in late 2013 to better reflect the services rendered which saw their charges for managing the TTA until that point in time reduced £429,000 (a reduction of 47%). It was also agreed that the DBSA will charge DFID up to £42,000, based on actual services rendered, to oversee implementation of the three committed projects. In total this equates to a 2% management fee for managing £23,000,000 in commitments. / 5.4 Did the project represent Value for Money : Y/N / TMSA did not represent VFM. While its support to the Tripartite’s agenda was much valued by the Tripartite and many national and international partners, it delivered few of the intended outputs correspondingly its impact was limited. As set out above, its performance on VFM measures was weak. Overall therefore, despite the positive feedback from key stakeholders, the project did not represent VFM to DFID. / Lessons Learned / A great number of lessons were learnt in the area of VFM. Many of these issues would not have occurred had the programme been designed and implemented according to DFID’s current policies and procedures, notably through: / Carrying out a detailed Theory of Change analysis at the outset and test this throughout project design and implementation. / Undertaking a due diligence assessment with all new and existing partners. / Ensuring detailed on-going scrutiny of management and programme costs being incurred and procedures (particularly procurement) with appropriate reporting and follow through.

6. Conditionality
6.1 Partnership Principles and specific conditions / The partnership principles do not apply to the TMSA programme. Few funds are channelled through government and their policies on the partnership principles have limited direct effect on delivery.

7. Conclusions
TMSA was seeking to deliver an extremely ambitious programme in a challenging political economy context and a highly technical and specialist area. It was an innovative programme which set out to deliver transformational change across Southern and East Africa. Feedback from the Tripartite and many national and international stakeholders was that TMSA had made an important contribution to advancing the agenda and supporting weak capacity in the region. / TMSA’s actual delivery however was limited, which coupled with its over ambition and poor governance, resulted in none of outputs being achieved and the programme scoring C. While it is not possible to measure TMSA’s impact overall, in some areas it has made a lasting and significant impact. These are captured under the respective outputs, with the following five standing out in particular: / Its support to the Tripartite enhanced cooperation between COMESA, EAC and SADC, helping to improve coordination between their respective and joint programmes. / It played an instrumental role in the TFTA process, the results of which could potentially be transformational if it is used as stepping stone for deeper economic integration in the future. / Its work on trade facilitation, while having had limited impact to date, has put in place the foundations - through diagnostic, harmonised regulatory approaches and studies - for greater progress in the future if greater attention is given to political economy and capacity needs at country level. / Its NTB reporting system is regarded as making an important contribution to increasing the transparency and resolution of NTBs. / Its championing of the corridor approach and specifically the NSC on behalf of the Tripartite, its use of the HMD4 analysis, GIS and other diagnostics and the work of the PPIU in preparing project summaries for all NSC road projects, has played an important role informing and securing investment on priority corridor infrastructure. / The reviews of TMSA however, revealed serious weaknesses in delivery, management, oversight and financial monitoring leading to the closure of TMSA six and a half months early. The key lessons learnt have been captured throughout the PCR, but the following five will be key for improving the effectiveness of future DFID support for regional trade and integration in Southern Africa: / Underpinning the programme’s delivery failures was a theory of change that saw the programme designed upon the premise that regional integration could be driven at the regional level. The Independent Evaluation found assumptions under the ToC to be many, very broad and dependent largely on the agency and engagement of others; and that it underestimated the complexity of the operational environment, the barriers and challenges it poses (p81). Since the design of TMSA, DFID has introduced the requirement to develop the theory of change during programme design and prior to the logframe. Had the assumptions underpinning TMSA’s ToC been tested/validated at the outset the fundamental design weaknesses could have been avoided, resulting in a programme that may have been of lower ambition, but could have delivered considerably more. / In particular, much greater attention needs to be given to the political economy of regional integration in the theory of change and hence design and implementation. In taking this approach, its follows that a large proportion of resources (technical and financial) would be delivered at the country level. National programmes would be determined by what countries want to do and their needs, with flexible and pragmatic programming. That would mean that REC and WTO commitments would be important focus points, but these would be part of a broader programme of support and one would expect a variable approach to implementation, with the sequencing and pace of implementation differing across countries. / Delivering such a programme would require the development of a multi-pronged strategy for delivering a diversified portfolio for supporting regional integration and cross-border cooperation. This would require close coordination and join-up between international partners, DFID country offices and wider HMG. TMEA is one model of how this could work. / The programme was designed on the premise that increased trade would generate growth which would in turn translate into poverty reduction. In future, analysis of the poverty impact of the programme should be integrated into programme and intervention design, implementation and monitoring. / DFID must ensure detailed ongoing scrutiny and oversight of implementation and VFM and that programmes that policies and procedures are reviewed at least annually to ensure they are in line with DFID best practice.

8. Review Process
This PCR was completed in June 2014. It draws extensively on the reviews carried out in 2013: the ICAI review; DFID IAD audit and in particular the Independent Evaluation which was finalised in December 2013. As such the evidence-base for this Annual Review can be regarded as very strong, although in some cases it may not reflect progress made since mid-2013. The PCR was signed off by DFID Southern Africa’s Head of Office.