Business Case

Summary Sheet

Title: Somali Health and Nutrition Programme (SHINE)
Project Purpose: / Reduce Somali maternal and under 5 mortality through the provision of services delivering an essential package of health and nutrition interventions and by creating demand for services.
Programme Value: £92,000,000			Country/ Region: Somalia
Project Code: / 204903	Start Date: / Approval date: September 2015		End Date: / March 2021
Overall programme risk rating:	Medium
Quest Number:	5129456

TABLE OF CONTENTS

# Abbreviations

AG	Accountable Grant
ANC	Antenatal Care
AR	Annual Review
CDEL	Capital Departmental Expenditure Limit
CHF	Common Humanitarian Fund
CHWs	Community Health Workers
CYP	Couple Year Protection
DPT3-	Diphtheria, Pertussis and Tetanus
EmONC	Emergency Obstetric and Neonatal Care
EPHS	Essential Package of Health Services
EPI	Expanded Programme on Immunization
FGM	Female Genital Mutilation
FGS	Federal Government of Somalia
FP	Family Planning
FSNAU	Food Security and Nutrition Analysis Unit
GAVI	Global Vaccine Alliance
GFATM	Global Fund for AIDS, Tuberculosis and Malaria
HCS	Health Consortium for the Somali People
HMIS	Health Management Information System
HR	Human Resources
IDP	Internally Displaced Persons
JCU	Joint Coordination Unit
JHNP	Joint Health and Nutrition Programme
JMP	Joint Monitoring Project
M&E	Monitoring and Evaluation
MA	Managing Agents
MCH	Mother and Child Health
MICS	Multiple Indicator Cluster Survey
MoH	Ministry of Health
MPTF	Muti-Partner Trust Fund
NPAC	Non-Project Attributable Costs
OJEU	Official Journal of the European Union
OP	Out Patient
PCA	Project Contract Agreement
PCD	Procurement and Commercial Department
PFM	Public Finance Management
PM	Programme Manager
PMU	Project Management Unit
PL	Puntland
RHO	Regional Health Officer
RMNCH	Reproductive, Maternal, Neonatal and Child Health
SBA	Skilled Birth Attendant/Attendance
SC	South Central
SDRF	Somalia Development and Reconstruction Fund
SRO	Senior Responsible Owner
SL	Somaliland
ToC	Theory of Change
TWG	Technical Working Group
U5	Under Five
VFM	Value for Money
WASH	Water, Sanitation and Hygiene

# Federal Map of Somalia

Map 1: Changing Federal map of Somalia, showing emerging states and disputed areas
# Intervention Summary

What support will the UK provide? The programme will reduce mother and child deaths in Somalia by improving the supply and demand for improved health and nutrition services. It will focus on both prevention and treatment of the main causes of mortality and morbidity, to reduce the number of women dying from childbirth related causes by 10% and reduce the number of deaths of children under five (U5) by 30%. It will make a major contribution to health and wellbeing, which is essential to human and economic development, and provide vital support health systems strengthening in Somalia. Funding will be up to £92 million over 5 years, from 2016-2021.

What are the main programme activities? The Somali Health and Nutrition Programme (SHINE) will respond to the health and nutrition needs of the Somali people. The programmes main focus will be to deliver an essential package of health services. It will also empower vulnerable populations to overcome barriers to access and help them to make healthy choices. The programme will strengthen the Somali Health Authorities oversight of service provision, which will in turn promote local accountability and allow them increasingly to respond to the needs of their populations. This programme approach aims to support long term sustainability and state building that is part of our wider strategic agenda.

Why is UK support required? Health indicators in Somalia are some of the worst in the world. Somalia is one of the worst places in the world to be a woman. One in 18 women[1] die due to preventable causes related to child birth. In addition, 178 children[2] under 5 years old die due to preventable illnesses each day. A focus on reproductive, maternal, child health and nutrition interventions will reduce these deaths. It will result in better health outcomes for children and women, allowing them to become more productive members of the community. Government spending on health is low and this will increase only gradually in the next five years as domestic revenue builds from a low base. To help Somalia in its peace and state building efforts, it will be important to build governments’ oversight of health service provision at both national and community levels in the existing, as well as emerging administrations. UK support will strengthen Somali government stewardship of the health sector promoting greater sustainability of health services in the long term.
[1] 3,900 Somali women die a year due to maternal mortality. UN Interagency mortality estimates 2013 Report.
[2] 65,000 children under 5 die a year. UNICEF level and trends in child mortality 2014 Report

What are the expected results? SHINE will make health services available to approximately 2.4 million Somali’s each year over five years. The programme will improve the supply of an essential package of health services through additional interventions to increase the number of children routinely vaccinated by 123,000; the number of women using modern contraceptives by 270,000; the number of births taking place in health facilities by 63,000; and the number of those accessing nutrition services by one million. It will also increase the demand for services, by tackling socio-economic and educational barriers to accessing modern health care. Interventions will promote the use of health services by particularly vulnerable populations (such as nomads and adolescents), increase community oversight boards at health facilities and address key behavioral determinants of poor health such as gender inequalities and poor hygiene, water and sanitation.

How does the project fit with the country programme or department’s strategic objectives set out in the Operational Plan? DFID Somalia has been the lead donor in health for the last five years, helping to set the national policy and strategic framework and successfully rolling out a routine delivery of essential services in over 50 of the 90 Somali districts. We have effectively demonstrated that it is possible to deliver essential health and nutrition services at a reasonable cost, in a complex and fragile state. The EPHS roll out, which started through a DFID funded pilot in 2011 is now delivering basic health and nutrition services covering approximately 40% of the Somali population, serving many women and children who have never experienced any form of public basic service provision for over 30 years. Through decentralised delivery mechanisms, EPHS has the potential to establish and strengthen state-citizen relations of accountability.

The programme will help deliver the UK Government’s commitments on health and nutrition and will directly contribute to reducing gender inequality in Somalia, given its strong focus on women and girls. Health is identified as a priority area in DFID Somalia’s Country Poverty Reduction Diagnostic (2014) and the draft Bilateral Aid Review (2015), with commitments to continue to engage in human development over the long term. Through this new programme DFID Somalia will also aim to open up the market to greater competition for the management of DFID health funds in Somalia. We will seek to achieve greater VfM by promoting the space for private and NGO management agents to compete and engage, while assuring that delivery mechanisms are in line with our long term strategic aims. We will prioritise a systems building approach to help rebuild state capabilities to oversee basic service delivery, contributing to the state building and recovery agenda that is central to our overall engagement with Somalia.

What are the key risks to the success of the programme? The key risks to the success of the programme are political and security risks. There is a risk that political instability at both national and sub national level may derail support to the programme. Competition and tension over sub national resource allocation may also increase and cause disruption, any breaks in services provision may increase conflict. If insecurity rises and implementation areas become inaccessible, it will be more difficult to reach the targeted and most vulnerable populations. Lastly there also the Fiduciary risk, with the possibility of fraud being committed by implementing partners and suppliers as a result of restricted direct DFID access and oversight. Flexible and adaptive programming will be key.

# Strategic Case

Somalia is one of the most fragile states in the world, rated 2nd to South Sudan on the fragile states index[3]. Following the collapse of the Barre regime in 1991 the country effectively partitioned into three separate geographical regions; North East Zone (Puntland), North West Zone (Somaliland) and South Central Somalia. In 2012 the interim transition period for the Federal Government and Puntland was ended with the formation of Parliament and a Constitution, encompassing the principles of devolution and the new Federal Government of Somalia (FGS) was established[4].
[3] www.foreignpolicy.com/fragile-states-2014/#rankings
[4] Somaliland is a self-declared independent state, which does not come under the federal Government of Somalia.

The government has defined a new six pillar strategy for peace and state building and as part of the New Deal process. The Somali Compact, between the FGS and the international community was endorsed at the Brussels Conference in September 2013[5]. The principles of the New Deal architecture focus on greater government oversight, ownership and leadership in decision making, greater use of government systems and mutual accountability.
[5] http://www.newdeal4peace.org/about-the-new-deal/

The establishment of the FGS in 2012 represented a move towards increased stability and state formation; however the government has lurched from one political crisis to the next. Establishment of sub-national federalism is now gaining pace with an already established Puntland and two interim Administrations – Interim Jubaland Administration and Interim South West Administration currently being recognised by the Federal Government with three more Administrations under formation. Somaliland, who declared independence in 1991, is not formally recognised but has relative political stability.

Much of Somalia is still an active war zone, with an ongoing military campaign in southern Somalia, with some recent progress by African Union (AMISOM) troops in moving Al-Shabaab, an extremist Islamist group, out of major towns and cities. Al-Shabaab, which is still in control of much of the territory in the south, has responded by adopting asymmetric military tactics and attacks on government officials, aid workers and infrastructure remain a regular occurrence.

The country has a population of 12.3m people of whom 3.1m are nomads with little access to basic services. There are 3 million Somalis in need of humanitarian assistance that includes 1.1m Internally Displaced People (IDP), with the highest proportion in South Central Somalia.[6] The majority of displaced women are widows and heads of household.[7] Just under half the population is aged between 10 and 29 years old.
[6] UNFPA Population Estimation Survey 2014
[7] UNICEF, Emergency Obstetric and Neonatal Care (EmONC) Needs Assessment in Selected Health Facilities in Somaliland, 2011.

Political Economy

Politics is deeply divided along both clan and politico-religious lines. Intense factional competition over the distribution of even small amounts of power and resources constantly threatens to undermine efforts to establish a rules-based system of governance. Politicisation of clan identity remains a major obstacle to durable peace and an inclusive political settlement. The need to ‘clan balance’ almost every action by the state illustrates an extreme absence of trust among clan groups. But clan is not the only dynamic that divides Somalis. There are also conflicts between different religious groups (such as between Dam’ul Jadid, an off-shoot of the Muslim Brotherhood, and Ahlu Sunna Wal Jama); and between those who believe in a vision of a centralist state and those who believe in a federalist state.

Somalia has a small economy, with limited revenue sources and a very small budget. In 2015 the FGS allocated 25% of its budget to defence with limited resources to social sectors (2% for education and 0.3% for health). South Central areas of Somalia have the greatest level of instability and the Federal Government’s Ministry of Health, based in Mogadishu, is severely lacking in capacity and resources to deal with what essentially remains a humanitarian context. In comparison, Somaliland authorities estimate that they spent USD 7.1m on health in 2014, at about 4.5% of the budget. Somaliland demonstrates strong political will to ‘manage’ the health sector but has limited technical health capacity. Similarly, the political will in Puntland has increased over the last 3 years, with significant efforts to improve the enabling policy environment. Puntland authorities estimate that they spent USD 1m on health in 2014, 2.5% of the budget[8]. In line with the New Deal, the health authorities would like to have further stewardship of the health sector and recognise that their capacity to do this, has been limited to date.
[8] Joint Health and Nutrition Programme documentation April 2015

As federalism takes further shape, the political and administrative systems in each region are beginning to be developed. It is not yet clear what the constitutional changes will mean for health and it will be hard to predict so any support to the health sector will need to be flexible. The differing levels of development at decentralised levels mean that a different contextual approach to supporting basic services is required in different areas. Newly emerging administrations will offer opportunities for expansion and support for basic services but will also present risks as competition for resources may well lead to new tensions and politicisation of the sector.

The health sector has been described as a ‘model’ sector, with the FGS, Puntland and Somaliland working together on common priorities. The Essential Package of Health Services (EPHS) is the government’s number one priority in health, as set out in the Health Strategies developed in 2011. In 2012, EPHS was identified as one of the governments flagship programmes in the FGS Economic Recovery Programme. Following the launch of the New Deal in 2013, EPHS has continued to be referred to as a ‘flagship’ approach for delivery in the health sector.

Health Status

Somalia ranks amongst the Least Developed Countries and until 2014 was considered the most fragile state in the world[9]. This fragility impacts on the health status of the population and available data positions Somalia among the lowest ranking countries for the majority of health indicators (Refer to Table 2).
[9] Failed States Index 2013 www.ffp.statesindex.org/Somalia

The maternal mortality ratio is exceptionally high across Somalia at an estimated 850 deaths per 100,000 live births. One in 18 women die due to preventable causes related to child birth[10]. Less than 10% of women deliver in a health care facility, without the help of a skilled birth attendant. Women have on average six children, a direct result of only 15% using modern contraceptive methods. Female genital mutilation (FGM) affects almost all women and can result in increased obstetric complications. The percentage of women aged 20–49 years who were first married or in union before the age of 18 was 31% in Somaliland and 38% in Puntland (MICS 2011). Early marriage and early first pregnancy both represent risk factors in the Somali context. Giving birth remains one of the greatest risks to women’s lives with 1 in 18 dying due to pregnancy related causes.
[10] Interagency mortality estimate 2013

Consequently neonatal, infant and U5 mortality rates are also high. The main causes of new-born deaths are low birth weight and premature birth, asphyxia, birth injuries, septicaemia and neonatal tetanus.[11] The infant mortality rate is estimated to be 108 per 1,000 live births. While the main causes for under-five mortality (estimated at 146 child deaths per 1,000 live births in 2014) are pneumonia (19%), diarrhoea (13%), neonatal disorders (11%), and measles (11%)[12]. Immunization coverage for Diphtheria, Pertussis and Tetanus (DPT) is 42%.[13]
[11] State of the World’s Children 2015
[12] http://www.who.int/gho/countries/som.pdf?ua=1
[13] WHO

Table 1: Key Health Indicators for 2013
Indicator	Somalia	East/Southern Africa
Maternal Mortality Ratio per 100,000 live births	850	420
U5 mortality Rate per 1,000 live births	146	74
Life expectancy at birth	55	59
Total fertility rate	6.6	4.6
Contraceptive prevalence rate	15%	33%
% of children U5 underweight	32.8%	18%
% immunisation coverage of DTP3	42%	79%
Care seeking for children with symptoms of pneumonia	13%	52%
Treatment with ORS for diarrhoea	13.2%	37%
At least 4 ante natal visits	6.3%	39%
Institutional birth delivery	9.4%	41%
FGM prevalence rate	97.9%	44%
Support for the practice of FGM	64.5%	20%
% of children married by age 18	45.3%	37%
Adult HIV prevalence rate	0.5%	7.3%

UNICEF State of the World’s Children 2015, (Pop 10,495,600), MICS 2011 Puntland and Somaliland and MICS 2006 for South Central.

Somali malnutrition rates are among the highest in the world. Malnutrition in Somalia is caused by numerous factors including little or no access to primary health care, poor hygiene and sanitation, and inadequate care and feeding practices. Only 4.8% of children in Puntland and 12.8% in Somaliland are exclusively breastfed and 51% and 42% respectively have access to an improved water source (FSNAU 2014). It is estimated that 203,000 Somali children are malnourished, of which 38,000 are severe acute, the majority of whom are located in South Central. There is a higher than national rate of malnutrition amongst IDPs and the under-five death rate among Mogadishu IDPs is six times the national average.[14]
[14] OCHA 2014

Health Funding

In 2013, total Health funds in Somalia were estimated at USD 160m a year[15]. The main funding was from the Common Humanitarian Fund (CHF), Polio Eradication plus longer-term programmes such as, GFATM, GAVI, the Joint Health and Nutrition Programme, the Health Consortium for the Somali people and the Ministries of Health[16]. Total health funding translates to approximately USD 13 per capita, significantly lower than the low-income countries’ average health spend of USD 36 per capita and the WHO recommended spend of USD 60 per capita by 2015 for delivering essential health care in low-income countries. This presents an urgent need for more multi-year financing in support of government priorities.
[15] JHNP Resource Mobilisation Strategy, 2013 (this excludes Diaspora and Out of Pocket expenses)
[16] MoH funding to health is mainly for salaries - % of budgets FGS 0.3%, SL 4.5%, PL 2.5%

Traditionally the Humanitarian system has been the main funder of Health (35% in 2013) including provision of all medicines and supplies (through UNICEF). Since the humanitarian crisis in 2011, there has been a significant drop in humanitarian funding to Health, despite 3.2 million people remaining in urgent need of emergency health provision. Health funding via the Common Humanitarian Funds (CHF) has dropped considerably. In June 2015 the Health cluster secured just 6% of the USD 71m funding required (USD 4.2m). The situation has been compounded by the abrupt withdrawal of MSF in August 2014, which ended support for health services to 1.5m people, leaving a sizeable gap which is yet to be filled. There are worrying reports of facilities and hospitals reducing services and even closing. NGOs that have historically depended on humanitarian aid have struggled to secure funds to keep services going, at the same time the UN is no longer providing regular supplies.

DFID is the largest development funder in Health, contributing a total of £ 84.5m between 2010-16. Other major funders are the GFATM and GAVI[17]. The majority of bilateral development financing for Health has been channelled via the Joint Health and Nutrition Programme (JHNP). In 2014 total donor funds to JHNP peaked at USD 48m, dropping to USD 30m in 2015 and to USD 16m in 2016. Looking ahead, donor resources beyond 2016 are very uncertain with a drop likely with risks that per capital health spend will decrease below USD 10. There are no bilateral donor committed funds for Health beyond 2016. The total known/committed Health funds for 2017 are estimated at USD 50-60m[18]. The largest committed financing is for Malaria and HIV project continuation in 2015-17 via GFATM, approximately USD 15m a year. Polio Funds have decreased to around USD 8m a year. GAVI HSS fund has ended, with ongoing immunisation support at between USD 5-7m a year.
[17] The Global Fund to fight AIDS, Tuberculosis and Malaria 2012-16 USD 75m, The Global Vaccine Alliance 2011-16 USD 20m
[18] USD 40m: GFATM, GAVI, Polio, CHF, plus USD 12m from Government – without DFID funds

DFID support to Health

DFID is the largest development donor to the health sector contributing a total of £84.5m (2010-16) through two delivery mechanisms; the Health Consortium for the Somali People (HCS) with a value of £45.5m; and the Joint Health and Nutrition Programme (JHNP) with a value of £38.9m.

The Joint Health and Nutrition Programme (JHNP) is a pooled fund focused on reproductive, maternal, neonatal and child health (RMNCH) and nutrition which aims to rebuild the collapsed health system. JHNP is managed by UNICEF and implemented through three UN agencies; UNICEF, UNFPA and WHO. It has 6 programme components in support of each of the WHO health system building blocks: governance, human resources, service delivery, medicines and supplies, health information, health financing. Priorities and plans are set jointly with the Somali health authorities in line with the Health Sector Strategic Plans. JHNP started its inception phase in 2012 and is now in year 3 of full programme implementation. USD 100m has been disbursed, the bulk of which has been from DFID (£38.9m, 60%). The current programme ends in December 2016. DFID has disbursed funding for 2015 but has no funds available for 2016. Further details on JHNP comparative advantage, achievements and key lessons are contained in Annex1.

DFID scoring of JHNP in Annual Reviews was a B during the inception phase (2012), reflecting the start-up challenges of a multi-donor pooled fund involving three Ministries of Health and three UN agencies. This was followed by an A score for year one of implementation, reflecting significant progress on governance and human resource outputs (2013). The latest score for 2014, was a B which indicates that outputs moderately did not meet expectations. Of the 6 outputs, output 3 on service delivery carried the largest weight and scored a B mainly due to slow roll out of EPHS (see Annex 1 for lessons learned). It should be noted that 5 of the service delivery indicators for Output 3 scored an A, 4 scored a B and two could not be assessed. In May 2015 JHNP reprioritised their budget given decreased funds available for 2015 and 2016. The budget is now refocused on EPHS service delivery with limited funding available for outputs 4-6. A JHNP donor update in July 2015, suggest EPHS results for 2015 are now on track with a positive trajectory expected.

The Health Consortium for the Somali People (HCS) is an NGO programme supporting the delivery of reproductive, maternal, neonatal and child health (RMNCH) and nutrition services. The consortium was brought together during the peak of the humanitarian crisis of 2010-11 but has increasingly worked with local and regional government administrations during its 5 years of implementation. The consortium consists of five international NGOs, three of which are delivering the EPHS in 10 districts in three diverse regions (in South Central, SL and PL). Further details on HCS comparative advantage, achievements and key lessons are contained in Annex1.

DFID scoring of HCS has been a consistently high, varying between A+ and A. Following a slow initial start-up for EPHS service delivery in 2010-11 (of around 1 year), the programme has been consistent in meeting its targets. The Annual Review in 2013 scored an A and the score for 2014 is an A+.

DFID Health Results

The combined results of the two DFID funded programmes has been positive, with the two programmes increasingly playing a complimentary role, based on their unique comparative advantages. DFID support has demonstrated that the EPHS package is a viable and effective approach for delivering health results in Somalia. Results specific to the EPHS service delivery components, between 2010-2014 are listed below:

- The rollout of EPHS in 51 out of 90 districts across the Federal Government’s region in South Central (20 districts), Puntland (20 districts) and Somaliland (9 districts), covering an estimated population of 4m.
- An increase of 106,698 birth spacing methods were distributed
- More than 46,000 additional births were attended by a skilled birth attendant
- Over 1.8 million visits to a health facility took place
- An additional 125,526 essential child immunisations of DTP3 were given
- 173,976 more pregnant women attended more than 2 antenatal clinics

Health Systems

The private health provision in Somalia is comprised of privately owned clinics and hospitals, pharmacies, training providers, traditional and complementary medicine practitioners. Together private providers deliver an estimated 60% of health care in Somalia[19], however it should be noted that there is no standards or regulation with large variations in service quality.
[19] http://hcsshare.org/uploads/documents/NHPCreport_Affara_December_2011.pdf pp,5

In 2013, when the new Ministry of Health was set up in Mogadishu, the Somali health system was almost non-existent, a result of over 20 years of conflict with destruction of infrastructure and loss of staff. Rebuilding the health system has been supported by JHNP using the six WHO Health Systems Building blocks[20]. Efforts have focused on upstream systems building; mostly on policy, governance and leadership and a little on human resource systems, less so on medicines, health financing and information systems. Progress has been made to set the health policy, to define the priorities for health and develop a series of strategies and plans. However, while this approach has been successful for upstream systems building it has not served to strengthen the downstream systems; the management and support services needed to improve service delivery.
[20] The WHO HSS building blocks are: leadership and governance, human resources, medicines and supplies, information, finances and service delivery.

Significant systems constraints remain. One major constraint is the lack of qualified and trained health professionals. In Somaliland there are only 0.056 doctors for every 1,000 people, far below the WHO recommended 2.28 physicians, nurses and midwives per 1,000 populations[21]. Another delivery constraint is the poor health infrastructure. According to the Somali Health Management Information System (HMIS) there are currently only 332 Mother and Child (MCH) health centres for a population of 12.3m (Annex 2).
[21] THET Health Worker Assessment preliminary findings 2015 (not yet published)

There is no government central procurement or distribution system for medicines and supplies. The provision of medical supplies is still predominantly reliant on UN agencies which frequently face lack of resources and stock outs[22]. Increasingly NGOs are also procuring their supplies to address these needs. There is some private sector pharmaceutical procurement, but this is for profit, not regulated and uncoordinated. There are also weaknesses in the system of distribution which rely predominantly on sub contracted partners. These weaknesses are well documented in the UNICEF Supply Chain Assessment Report[23] .
[22] Until 2013 the bulk of medicines and supplies for Somalia were supplied by the UN using Humanitarian funds. With the decrease in humanitarian funding available this has has a direct impact on the health sector.
[23] Assessment of the UNICEF Somalia Supply Chain System Prepared by Langdon Greenhalgh (Project Manager) & the Global Emergency Group Assessment Team.

Systems for decentralised service delivery vary considerably from Somaliland, and Puntland to south central areas where new administrations are still being formed and functions and responsibilities are still unclear. At the district level, different regions are at different stages of development, with variations in progress on decentralising responsibility for some service to district structures. Community Health Committees or Health Boards have been formed in some facilities and play a significant role in helping to define and promote health needs at the community level. Their role however has at times become politicised. Greater support is needed at the devolved level to strengthen capacity for service delivery under local leadership.

Service Delivery using EPHS

The Health Authorities’ number one priority is the delivery of the Essential Package of Health Services (EPHS) as detailed in the EPHS strategy (2009). EPHS includes a total 10 services areas[24] of which 6 are referred to as the ‘Core Package’. The package of services aims to address areas of greatest health needs by concentrating scarce resources on interventions which provide the best value for money.[25] In addition there are also 6 EPHS Management and Support services. EPHS services are delivered through Government Health Facilities which are mostly supported by NGOs that provide the inputs to run the facilities including staffing, medicines and supplies which they provide to the users free of charge[26]. A review of the evidence on EPHS interventions and efficiency of EPHS delivery to date is provided in Annex 3.
[24] Additional Services 7-10 include, eye care, dental care and mental health
[25] Essential Health Packages. What are they for? What do they change? C Waddington 2013
[26] The arrangement for NGOs to support public health facilities is the accepted approach and the NGOs manage the finds directly and are accountable.

The EPHS roll out, which started as a pilot in 2011 and began a more comprehensive roll out in 2013/14 is now delivering basic health and nutrition services to many women and children who have never experienced any form of public provision. In many parts of Somalia there has been no formal government and an absence of any basic pubic services for over 30 years. Through the decentralised delivery mechanisms EPHS has the potential to begin to establish and build state-citizen relations of accountability. EPHS can also serve to the increase the visibility of the state in service provison and as being responsive to their citizens.

During consultations with government partners (see Annex 6), there was a strong request for greater support to government to build their oversight and management capacity to coordinate, plan and monitor the roll out and implementation of EPHS services[27]. At present the health authorities have limited ability to oversee service delivery, which is implemented by others. They struggle to find the resources for such tasks and have limited technical knowledge and capacity to do this. Looking ahead, there is acceptance that EPHS service provision should continue through NGOs, but that these services need to meet the EPHS standards and support should build the government’s management and support of services. Government made a specific request to DFID to avoid a break in service delivery to communities. This is considered politically important especially given that 2016 is an election year for both the Federal Government and Somaliland.
[27] This transition to greater government ownership is reflected in the New Deal principles and the objectives of the Peace and State Building Goals on basic services (PSG5) which aim for greater state say and supervision over basic services.

With 5 years passed since the EPHS strategy was developed in 2009, the Health Authorities now need to develop an EPHS roll out strategy and common costing approach. This strategy should set the direction and priorities for the expanding the scope, coverage, quality and geographical areas of EPHS in the coming years.

Evidence of EPHS interventions

There is strong evidence that the health interventions contained in the Somali EPHS package, specifically core services 1-5, have a positive impact on health outcomes and are considered cost-effective. This is supported by international evidence that effective high coverage and an associated increased uptake of the proven RMNCH and Nutrition interventions will reduce morbidity, disability and mortality. Lancet Series[28] [29] [30]and Cochrane reviews[31] have concluded that increased utilization of RMNCH and nutrition services saves lives and reduces morbidity. Also, Bhuatta and colleagues[32] summarising the latest evidence have concluded that increased utilization of delivery care, case management of neonatal infection, clean postnatal care, and facility based pre-term care can reduce maternal mortality by 51%, neonatal mortality by 71% and still birth by 33%. The effectiveness of aid for RMNCH is also well-reported[33].
[28] Lawn, J. E., Blencowe, H., Oza, S., You, D., Lee, A. C., Waiswa, P., et al. (2014). Every new-born: Progress, priorities, and potential beyond survival. Lancet, 384(9938), 189-205.
[29] Bryce, J., Victora, C. G., & Black, R. E. (2013). The unfinished agenda in child survival. The Lancet, 382(9897), 1049-1059.
[30] Black, R. E., Morris, S. S., & Bryce, J. (2003). Where and why are 10 million children dying every year? The Lancet, 361(9376), 2226-2234.
[31] http://childhealth.cochrane.org/cochrane-reviews-child-health.
[32] Bhutta et al 2014 : Gentile, A., & Bazan, V. (2011). Prevention of pneumococcal disease through vaccination. Vaccine, 29 Suppl 3, C15-25. Bhutta, Z. A., Das, J. K., Walker, N., Rizvi, A., Campbell, H., Rudan, I., et al. (2013). Interventions to address deaths from childhood pneumonia and diarrhoea equitably: What works and at what cost? Lancet, 381(9875), 1417-1429.
[33] Bhutta Z & Aleem S. (2013), A review of external assistance and aid effectiveness for maternal and child health. WIDER Working Paper No. 099, http://www.wider.unu.edu/publications/working-papers/2013/en_GB/wp2013-99/_files/90553105651662857/default/WP2013-099.pdf.

Social determinants of health

A combination of low levels of education and literacy, particularly among women, and a distrust of information from external sources has resulted in limited knowledge acquisition. Only 44% of young women aged 15–24 years in Somaliland are literate and only 37% in Puntland. School attendance remains low, with attendance rates at primary schools of 51.4% and 43.4% in Somaliland and Puntland respectively.[34] This leads to low levels of understanding of common diseases, maternal, neonatal and child health risks, appropriate infant and young child feeding practices, and hygiene which in turn results in poor health behaviours and service utilisation.
[34] Somaliland and Puntland MICS 2011

Recent formative research conducted by UNICEF[35] suggests a number of gaps and inconsistencies in knowledge and understanding between men and women. It highlights that the role of men is key, particularly around reducing maternal mortality. For example staff at emergency obstetric and neo-natal care (EmONC) facilities may refuse to operate on women without the husband’s or father-in-law’s consent. Research also found that men have less interest in certain issues like antenatal care (ANC), breastfeeding, and child illnesses, but they do have a strong interest on issues of child vaccination, tetanus injection for women, and birth spacing methods. It was also found that community and religious leaders do have a strong influence on women’s health, however this is mediated by the male head of household. The leaders influence the men and they then make the main decisions on health in the family.
[35] UNICEF ‘Formative Research on Key Behavioural and Communication Barriers in Somalia (NWZ, NEZ and SCZ)’, 2014

The nutrition data suggests[36] there is a need for greater focus on nutrition in the first 1000 days of life, to improve information on breastfeeding, appropriate infant and young child feeding practices, and healthy eating habits for women especially during pregnancy. Investing in these early years will enhance productivity later in life[37] fostered by a combination of improved health, nutrition, and cognition, which leads to better school results, higher-paying jobs, and overall enhancement of physical, cognitive, and reproductive performance.[38]
[36] FAO-FSNAU (2009) ‘National Micronutrient and Anthropometric Nutrition Survey Somalia 2009’, WHO, UNICEF, WFP, FAO Food Security & Nutrition Analysis Unit.
[37] Killing me softly J Econ Perspect, 25 (2011), D Almond, J Currie
[38] The consequences of early childhood growth failure over the life course. IFPRI Discussion Paper J Hoddinott, J Maluccio, JR Behrman, et al.. 2011

The Somali context includes a unique mix of socio-cultural, gender and even environmental determinants, which form a series of barriers to health prevention and care. The unequal power and gender relations that operate at household and community level have a substantial impact on health-seeking behaviour. Clan, religion, gender as well as age all determine who makes decisions and controls resources in households and communities. Somalia has a youthful population of which just under 50% fall between the ages of 10-29. Traditional practices affecting young people, including FGM or cutting and early marriage can impede safe motherhood. The practice of early marriage continues to be prevalent in rural communities and adolescent pregnancies carry greater risks. These determinants (which fall outside the control of health service provision), require a creative response to demand creation and health promotion to be effectively addressed. International literature suggests that effective ways to reduce demand side barriers is an under researched area, but one where the policy implications are potentially substantial.[39]
[39] Tim Ensor and Stephanie Cooper, Overcoming barriers to health service access: influencing the demand side. Health policy and planning; 19(2): 69-79 Oxford University Press(2004)

Somalia also has some of the worst indicators for access to water and sanitation in the world with more than 90% of the population accessing water from surface and unimproved sources while more than 80% still practice open defecation.[40] Incidence of disease and fluctuation in malnutrition in Somalia show strong correlation with poor water access and sanitation and hygiene practice. Despite the strong local and global evidence on the potential for improved sanitation and hygiene to impact health and nutrition, there are few interventions linking the two in Somalia.
[40] Scoping Study for Improving Water and Sanitation in Somalia, Centre for Humanitarian Change, 2014

Given the significant gender inequalities in Somalia this programme will involve a strong target focus on women and girls and will significantly contribute towards the provision of universal sexual and reproductive health and rights, which is one of the pillars of the DFID Strategic Vision for Girls and Women. This programme will prevent maternal deaths, increase women’s bodily autonomy and counter the medicalisation of FGM. Increased access to modern contraception and birth spacing as well as lower mortality of children under 5 is expected to enable women to reallocate resources to reduce poverty, take advantage of education opportunities for themselves and their daughters, and engage more in productive economic activity. The targeted inclusion of women in local health committees could also be used to increase women’s participation in local decision-making, enabling them to benefit from the allocation of resources and augmenting their value in the community.

Climate and environment

The environment in Somalia is arid and semi-arid. Years of conflict as well as natural disasters have led to natural resource depletion. Some regions are faced both with drought and frequent flooding. Both conflict and natural disasters mean that at present 730,000 people are in crisis and nearly 2.3 million people are classed as Stressed, requiring livelihood interventions[41]. These people are vulnerable to shocks and have little access to health services.
[41] FSNAU

Energy use in Somalia is predominantly wood and charcoal (90%) with the remaining 10% imported petroleum[42]. There is major potential for solar and wind energy, as well as oil and natural gas. However development of the energy sector has been hindered by insecurity and weak institutional capacity resulting in high costs at USD 1.5 kw/h. This has had a significant impact on the overhead costs of running health facilities as well the type of equipment and health care. The HCS has been piloting the use of solar and wind power as an alternative to prohibitive electricity costs. In addition, health facilities will be used as part of a pilot within DFID Somalia’s electricity mini-grids programme (ESRES)[43].
[42] DFID S ESRES business case March 2014
[43] DFID S ESRES business case March 2014

Conflict and fragility

Evidence suggests that health programmes have the opportunity to impact on long term peace and state building. In fragile states there is often an absence of trust between the public and the state and it is possible to begin to build the state-citizen relationship through delivery of basic services to increase trust.[44] Conflict and distrust can arise when there is a lack of equity in access to basic services. Strategies to strengthen health equity are recommended to strengthen pro-equity policy and planning functions; to improve targeted provision as well reducing access and participation barriers for excluded groups.[45] Interventions to engage citizens in demand-side and accountability processes and to raise awareness on the right to health, can also help excluded and marginalised groups to be democratically aware, contributing to their political agency and to more equitable resource allocation.[46]
[44] www.gsdrc.org/docs/open/HDQ941.pdf
[45] www.sciencedirect.com/science/article/pii/S0277953609006339
[46] www.savethechildren.org.uk/resources/online-library/the-role-of-the-health-sector-in-wider-state-building-a-discussion-paper

Summarise the evidence

In preparation for this Business Case design, DFID commissioned a series of five studies to get a more comprehensive and updated understanding on a range of issues within the sector as well as potential implementation arrangements. The five reviews included: EPHS Costing Evaluation, (2014), Private Sector Assessment (2014), Demand Creation for Health Sector Reform (2014), Review of Fund Management Arrangements for EPHS in Somalia (2014), and Review of Nutrition Integration in Somalia (2015) (refer to Annex 6). Our analysis for this strategic case has drawn on these studies and the relevant issues have been incorporated within this document.

The evidence shows that:
- The delivery of health services using EPHS has been effective in Somalia and has demonstrated positive results. (See Annex 1)
- There is a need for interventions targeting the most vulnerable groups of people – women of a reproductive age, children under 5, internally displaced people, nomads and adolescents.
- Demand side interventions addressing barriers to use of essential health services are critical to improve access, change social norms, improve accountability and empower women.
- Responses need to be context specific, flexible and adaptive, able to respond to changing security circumstances and emerging administrations.
- More direct support is needed to build to government stewardship, planning and management to oversee delivery of health services.
- There is a small body of data and evidence on health and nutrition in Somalia both on the supply of health services and also on increasing demand.

The problem analysis

Government resources, capacity, leadership and governance and systems within the health sector are limited and the government alone is unable to improve the health of the most vulnerable.

By focusing on a two pronged approach to tackle supply and demand DFID support will, in conjunction with the government, expand the coverage, and establish quality and breadth of service provision of the EPHS package to the areas and the people in greatest need. The main focus will be the delivery of the 1-5 core services, with an emphasis on reproductive, maternal, neonatal and child health and nutrition service provision. New approaches are needed to break down the barriers that prevent people from using health services, by trialling innovative ways to target the most vulnerable and work with communities and boys and men to strengthen local ownership and accountability.

How will intervening contribute to addressing conflict and avoid doing harm?

Intervening to support the state to oversee services will strengthen state citizen relations, build trust and improve stability and legitimacy of the government. An EPHS expansion strategy will be developed with government, with an equity focus and identify ways to target the geographic areas of greatest need and most vulnerable populations. Services will be delivered and developed with input from communities to enhance conflict sensitivity and to ensure provision meets needs. In doing so ‘Do no harm’ principles will be adhered to. A flexible delivery model should be used to enable the programme to respond to learning from the field. It should aim to build on the strong collaboration established to date between the three Ministries of health from the Federal Government, Somaliland and Puntland to continue to jointly set priorities and build consensus across the sector. Lastly it will be important to carefully manage the gradual inclusion of newly emerging administrations in the south and central regions.

Why is it right for DFID to intervene?

As the largest donor in the health sector DFID has supported the provision of basic health services for 5 years and has lead the reform agenda during this time. Should DFID no longer support the sector, many of the other donors would lose confidence in the ability of the government to deliver and would likely withdraw their support. The health authorities in each of the three regions are not currently in a position to raise revenues to significantly increase the allocations to health.

By not supporting health and nutrition, there would be reduced health and limited access to services for those who already suffer the most. Focusing on reproductive, maternal, neonatal and child health and nutrition interventions will reduce the number of deaths and improve the health outcomes for girls and women, allowing them to become more productive members of the community, thus strengthening their rights and position in society. Working with both men and women to address the demand side barriers to health seeking behaviour by changing behaviours and social norms will also strengthen the voice of women and empower them to be a part of the decision making process, working towards greater gender equality.

Links to the UK’s strategic policy objectives for poverty reduction in Somalia

At the 2013 Brussels conference the UK pledged £15m additional funds for health in Somalia as part of the New Deal process for 2014-15. Since then the UK has continued to commit to maintain support to the social sectors as part of the ongoing peace and security work. In the DFID Somalia Operational Plan 2011-2016, DFID committed to increase the health benefits of Somali’s with targets for the numbers of women using modern methods of contraceptives and skilled birth attendants, as well as the numbers of children immunised and supported by nutrition interventions. These interventions are critical for both poverty reduction and also contribute to wider HMG priorities on improving stability, state formation and institutional strengthening.

This intervention also supports the specific UK government priorities on health, set out in ‘UK aid: Changing lives, delivering results, the priorities outlined in the Framework for Results on Reproductive, maternal and newborn health and DFID’s Strategic Vision for Girls and Women. The targeted interventions outlined in this business case also support four of the ten global health ‘best buys’.[47] Additionally this programme supports global health priorities signed up to the by the UK: Scaling up Nutrition, Every Woman, Every Child, FP2020 and the African Led Campaign to end FGM. Lastly, this intervention contribute directly to the UK’s National Action Plan on Women, Peace and Security, which has Somalia as one of six focus countries.
[47] The Disease Control Priorities Project www.dcp-3.org

Impact and outcomes

The impact is: Improved health of Somalis leads to improved human development and economic development outcomes for Somalia.

Impact will be measured by[48],[49]:
[48] Using existing data from MICS 2011 covering two regions of SL and PL and MICS 2006 for South Central Somalia which may change when baseline data is available from South Central Somalia in late 2015. Baseline data for visit figures will be established from available national data at the start of the programme.
[49] Assumptions are that CPR will increase to 25%, MMR will reduce 10%, and U5MR will reduce by 30%
- An increase in contraceptive prevalence rate from 15% to 25% by 2021
- Reduction in the maternal mortality ratio from 850 to 765 per 100,000 live births by 2021
- Reduction in U5 mortality rate from 146 per 1,000 live births to 102 per 1,000 live births by 2021

The outcome is: Increase utilisation and access to reproductive, nutrition, child and maternal health services as delivered by the EPHS.
Outcomes will be measured by the following:
- Number of visits to health facilities delivering the EPHS
- Strengthened EPHS management by the health authorities
- Additional numbers of women of a reproductive age using modern contraceptive methods
- Additional numbers of women attending 3+ antenatal clinics.
- Additional numbers of children immunised with Pentavalent.
- Unique numbers of children U5 and pregnant women receiving nutrition specific interventions.
- Additional numbers of women delivering with a skilled birth attendant
# Appraisal Case

What are the feasible options that address the need set out in the Strategic case?

There are five stages to the Appraisal Case which are outlined in Table 2 below. Stage one involves an initial identification of the high level feasible options, the types of interventions and components necessary to address the needs set out in the strategic case. Stage two involves an economic appraisal of EPHS delivery using existing information available, highlighting key gaps on VFM data. Stage three considers 5 delivery options, with an outline of possible implementation modalities to address the needs. Stage four shortlists the most practical and viable options and identifies the most cost-effective mode of implementation that best manages risk and maximises results working in Somalia. Stage four also presents the preferred option and Theory of change in support of this Option. Stage five, begins with economic appraisal of the preferred option. This is followed by appraisals of the range of potential impacts on the environment, on society, on conflict and fragility as well as gender.

Table 2: Five Stages of Appraisal

Stage-1
  - Identification of high level feasible options and best approach to respond to the identified needs
  - Essential Health services
  - Nutrition and WASH interventions.
Stage-2
  - Scoping of 5 delivery options
  - Delivery using private management agent.
  - Delivery using UN
  - Delivery using mix of modalities (UN, NGO and Private)
  - Delivery as usual (UN and NGO consortium)
  - Delivery using private sector providers
Stage-3
  - Detailed appraisal of 3 shortlisted delivery options and identification of the preferred option
  - Assessment of comparative advantages for each option
  - Assessment of the quality of evidence for each option
  - Review of costs and benefits for each option
  - Review of risks
  - Identification of the Prefered option
  - Theory of Change
Stage-4
  - Economic Appraisal of EPHS delivery to date
  - Findings of a rapid review of coverage, breadth, duration of services, management and delivery costs, plus results to date of to delivery mechanims
Stage-5
  - Appraisals of preferred option
  - economic appraisal
  - environmental appraisal
  - social appraisal
  - conflict and fagility appraisal
  - gender appraisal

Appraisal Stage 1

Stage one of this appraisal identifies the high level feasible options and best approach to respond to the identified needs. Two intervention options which are considered, one is the provision of Essential Health Services the other is support to Nutrition and Water, Sanitation and Hygiene (WASH).

Essential Health Services

Since the late 1990s there have been calls for governments to shift health expenditure from high cost, low benefit services to lower cost, high benefit interventions, combined in an essential package of public health and clinical services[50]. Since then, essential packages of health services (EPHS) have been rolled out in several countries affected by fragility to define the core, cost-effective interventions that can rapidly address high rates of maternal and child morbidity and mortality. Such a package can also be thought of as much as a political instrument as a service delivery tool by enabling a country to define a health sector strategy and encouraging government and donor dialogue on health priorities on several levels[51].
[50] .1993 World Development Report
[51] Ibid

Nutrition and WASH Interventions

Over the last decade there has been a strong call to reposition nutrition as central to development, with growing recognition that unless malnutrition is tackled it may derail other efforts in health and poverty reduction. The evidence to identify effective interventions has grown considerably, demonstrating that the ‘window of opportunity’ for improving nutrition is small (pregnancy until 18-24 months of age). There is little ambiguity on what needs to happen. Eleven internationally recognized high impact interventions are recommended to tackle nutrition directly, which if implemented to scale, through the health sector in Somalia, could significantly reduce child mortality and contribute to an increase growth/GDP[52]. In Somalia it is recognised that most serious malnutrition is not caused by inadequate food intake (although food security is a factor), it is caused by bad sanitation leading to disease and diarrhoea, especially amongst the young[53].
[52] These include, promotion activities for breastfeeding, complimentary feeding, and improved hygiene, as well as provision of micronutrients (Vit A, Zinc, Iron and deworming tablets), plus promotion of therapeutic feeding for malnutrition. In addition there is a range of indirect interventions recommended for support through other sectors.
[53] 2014, WASH scoping study, conducted by the Swedish Embassy Somalia Unit

There is an opportunity to strengthen the delivery of nutrition interventions through the health sector. Lifesaving nutrition interventions such as breastfeeding promotion and support; vitamin A supplementation; therapeutic zinc supplements; Iron folic-acid supplementation for pregnant women; treatment of severe acute malnutrition can all be effectively integrated into health service delivery. Delivery mechanisms for nutrition interventions in health will include public health campaigns, such as Child Health Days; routine health service contacts; sick child contacts; community outreach; antenatal care contact (ANC); Postnatal care (PNC); emergency health services. These contact points primarily reach women and children during the “critical window of opportunity,” when malnutrition can and should be prevented[54]. A recent review of nutrition integration in Somalia highlights the need for a more purposeful integration of nutrition activities into health service delivery, through use of joint information and supply chain management systems as well as joint financing and coordination of health and nutrition interventions.[55]
[54] Improving nutrition through health, World Bank 2013: An accompanying brief for the health module of the World Bank guidance on: Improving nutrition through Multisectoral approaches.

A review of the two options above suggests that just implementing direct nutrition and WASH interventions will not address the full health and nutrition needs of the Somali people. A large burden of deaths and ill health are caused by poor Sexual Reproductive Health (SRH) and poor pregnancy related services, such as low ANC attendance, poor access to Skilled Birth Attendance (SBA). Poor health of under-fives is linked to low levels of child immunisation; all of these require the supply of health services and commodities. This points to the need for a mixed set of interventions to respond to the Somali health and nutrition needs.

Key Needs and Best Approach

1. The priority needs that this programme aims to address are summarised below and in Chart 2.
  1. The first component will be on the supply of EPHS. This will focus at regional/district and health facility levels to improve quality and government oversight of the package of essential services (RMNCH and Nutrition).
  2. The second component will focus on demand creation, which will require working at a community and household levels. We define ‘demand creation’ to include health promotion and interventions to overcome socio-behavioural-gender barriers to increase access and uptake of health services.
  3. The third component will be on Monitoring and Evaluation to review and document best practices and demonstrate results.

Given the significant disruption to health systems it is proposed that a systems strengthening approach be adopted in all components. To respond to the significant need for services, this programme will prioritise the supply of EPHS. This will include activities to strengthen the EPHS management and support functions to embed EPHS delivery in decentralised systems. We also consider the demand creation component critical to compliment supply interventions to respond to the unique health and nutrition challenges in Somalia. In terms of delivery mechanisms, it is recognised that a flexible and adaptive programme would best suit the complex and insecure operating environment in Somalia.

Table 3: Health and Nutrition Needs

Appraisal Stage 2

To date, there has been no systematic review of the economy, efficiency and effectiveness of EPHS in Somalia or comparison of the different EPHS delivery mechanisms to assess VfM. For the purpose of this Appraisal Case, a rough and rapid review of EPHS delivery via HCS and JHNP is carried out and detailed in Annex 3.

The main conclusion of this analysis is that it is important to acknowledge that Somalia is still in the early stages of roll out of the EPHS, following over 30 years of humanitarian provision and unsystematic short term support to health. The findings of this VfM appraisal serve to identify the range of variables which need to be considered when assessing EPHS roll out. It demonstrates EPHS is an effective mechanism for delivery, with positive service delivery results.

On the costing of EPHS, the analysis showed that further work is necessary to apply a consistent costing methodology for EPHS. Preliminary data suggests that costs of delivery are comparable to similar fragile countries of Afghanistan (USD 5.50) as well as DRC, South Sudan, and even Ethiopia, Kenya, and Rwanda (which range between USD 5-12.). Rough data presented in Annex 1 refers to an HCS unit cost of USD 5.88[56] per person and a JHNP unit costs of USD 11.66[57] per person with large variations dependent on locations. We urge caution from drawing any rapid comparisons from this data given different methodologies used, plus differences on duration of EPHS services and implementation contexts. In a workshop with JHNP and HCS EPHS implementing partners held in August 2015, it was recognised that further work is necessary to take into account the main cost drivers (security, personnel and supplies), as well as to introduce a consistent measure for comparing indirect costs[58]. A consisting costing methodology is proposed, plus a more regular assessment of unit costs. Both are recommended in 2015/16, to guide future programming.
[56] With variations between US$ 5.30 in SL; US$ 6.85 in PL; and US$ 5.51 in SC
[57] With variations between US$ 5.54 in SL to US$ 18.67 in CS (JHNP 2014 report).
[58] We disagree with the statement by QAU that delivery of EPHS via JHNP is double the cost of operating through an alternative partner as this is based on incomplete data (QAU Minute 21st Aug 15, bullet 10).

The analysis also highlights the need for greater adherence to EPHS standards and the need to establish clearer priorities for EPHS roll out in future, including the quality, coverage and breadth of interventions supported and specific definitions of catchment populations. The challenges of data inconsistency is unsurprising given that implementation is taking place under three different Ministries of Health, in a highly complex and insecure implementation environment, including delivery to ‘newly recovered areas’.

Appraisal Stage 3

The appraisal has identified five potential delivery options for the programme. These are:

Table 4: Five Options for initial Appraisal
Option 1	Delivery using private management agent.
Option 2	Delivery using UN
Option 3	Delivery using mix of modalities (UN, NGO and Private)
Option 4	Delivery using UN and NGO consortium
Option 5	Delivery using private sector providers

Option 1. Delivery of the entire programme by a private management agent or supplier was identified as the first option for this new programme. Initial discussions took place with a couple of the private management agents that have a presence in Somalia, to explore their expertise and collect details on their costs of delivery. What we found is that there is expertise in centrally managed procurement of infrastructure and economic development projects, however there is no expertise in basic service delivery, which requires working at a local level in very insecure and often inaccessible locations. We also found no experience of working on social cultural issues such as demand creation. The initial findings are that private management agents do not have the presence, access and track record yet which suggests they would not be ready to enter a new sector and ramp up support to manage the entire programme within the timeframe to start in 2016. Contracting would also require at least a one year lead in time. Our assessment is that this was not an immediate option to consider for management of the full programme in 2016. We agreed that we should proceed to scope out the potential for private management agents’ engagement in specific components and a later phase of the programme.

Option 2. Delivery of the entire programme by the UN was considered a viable option, in need of more in depth appraisal.

Option 3. Delivery using a mix of modalities (UN, NGO and Private) was considered a viable option in need of more in depth appraisal.

Option 4. Delivery using UN and NGOs was considered a viable option in need of more in depth appraisal.

Option 5. The option of delivery through Somali ‘private sector’ health providers was also considered, especially given that private health suppliers are estimated to currently provide 60% of health services. The private sector consists of a few large hospitals and training schools in the big cities, with the bulk of private provision through many small pharmacies run by unqualified staff, owned by local business men[59]. This option was considered not yet viable, given that private providers are not structured or coordinated to manage or implement a project or programme. Also private Somali providers do not have the systems in place to manage donor funds. It was felt that during the implementation period it would still be possible to push for more regulation of private providers and test possible partnerships with these businesses.
[59] See Private sector management

Finally there is also the option of doing nothing. This was not considered an option given the considerable health and nutrition needs of Somali’s and DFID commitments to continue to support.

Appraisal Stage 4

Stage 4 includes a more detailed assessment of three Options that have been shortlisted as practical and viable delivery options in Somalia. These Options are 2, 3 and 4. Before going into more detail on each of the options it should be noted that the ultimate implementation partner (IP) for all components 1, 2 and 3 are likely to be NGOs, irrespective of what Management Agent is brought in (NGO consortium, UN or private management agent).

Option 2 – Delivery using UN

Support in 2016. DFID has been the donor lead and main financier of JHNP to date (60%), however we currently have no funding available for 2016. JHNP is currently scheduled to end in December 2016, which is when the other donor funding ends. This option proposes a one year contribution to the current JHNP in 2016. Any new support via JHNP in 2016 would be outlined in an MoU and would need to be tightly managed and earmarked to specific EPHS related activities, with funding tied to clear performance measures. A 2016 contribution will ensure continued EPHS service delivery of existing NGO contracts in the 9 JHNP regions.

Service delivery needs will be supported through an expansion of EPHS. It will include increased focus on delivering a quality integrated package of 1-5 core services, plus an expansion of EPHS delivery to three new regions[60] currently funded separately via HCS from March 2016 onwards. The programme would also include a range of demand creation interventions.
[60] Gedo (Jubaland), Karkar (Puntland) and Sahil (Somaliland)

Support in 2017-21. We plan to enter a new phase of support via the UN from 2017-21, including an expansion to deliver the full three components of the programme via the UN. The MTR[61] of JHNP which is currently underway (Sept-Dec 2015) will document achievements and share lessons on both HSS and EPHS delivery which will help inform future programming. Progress results from DFID’s 2015 Annual Review of JHNP (due May 16) will also be used. For any new support DFID would negotiate a new MoU and specify the terms and conditions on management fees, VfM measures and reporting. For EPHS, this may include quality measures and additional EPHS management functions and possibly a shift to a more embedded approach within the MoHs at both the zonal and then regional levels. This revised approach would still be administered by the UN[62] and monitoring would continue through a joint UN/government led monitoring process.
[61] The MTR will be a joint review involving government, the three UN agencies and all JHNP donors.
[62] UNICEF or alternatively through different UN agency such as UNDP, especially if UNMPTF begins to manage this

DFID would oversee a separate M&E component, with a robust evaluation approach, plus possible support to third party monitoring, sector-wide surveys, studies and operational research (see Management Case for full details).

Option 3 – Delivery using a mix of modalities

This option entails working through a mix of modalities and delivery partners to spread the risks, increase competition and improve VfM. The potential agencies include the UN, NGOs and private Management Agents (MA). The approach aims to engage different agencies based on their comparative advantages to respond to the needs identified. For example on service delivery, we will seek to create competitive tension between EPHS implementing modalities, to increase lesson learning and promote innovation that will incentivise the demonstration of results and improvements in quality and VFM.

The Service delivery needs will be supported through three sub components which will use a mix of modalities to deliver EPHS. The mixed approach aims to avoid the disruption of services in 2016 and to reduce the risks which would otherwise be very high if all service delivery (in 50 districts) were contracted through one MA. It will build on previous experiences of the delivery mechanisms that have worked best and will seek to explore support to the management functions of EPHS, through embedding EPHS in decentralised systems.

UN with EPHS contracted to NGOs (2016) (component 1.a)[63]: Support will be provided in 2016, to deliver 1-5 core EPHS services in the 9 existing regions (41 districts) of JHNP. It will require that JHNP meets EPHS standards for delivery, both in terms of inputs (staff, medicines and supplies) and also the outputs (quality, coverage and scope of services). Any new support will involve a negotiation of a new MoU with UNICEF for 2016, with a focus on EPHS delivery including expectations on UN reporting, demonstration of VFM as well as the identification of specific policy objectives such as the EPHS roll out Strategy.
[63] This Option proposes a Mix of delivery mechanisms. Channelling funds to JHNP for one year is not considered a ‘central proposal’ of this Option, but a small sub-component for the short term

Between 2017-21[64] a new phase of support to EPHS will follow (component 1b). We are keen to bring more competition into the market and to examine ways to improve VfM. The options for doing this will be assessed and agreed through a well-documented transparent process which will be concluded by May 2016. The assessment process will involve the following four steps:
[64] JHNP is currently scheduled to run from 2011 and end in December 2016. However it is still not clear on what happens to this programme from 2017 onwards, including whether it will transition under UN MPTF.

  1. A desk review of background documents to clearly define the need: Review of the new EPHS roll out strategy, lessons from EPHS delivery to date, update on the New Deal (incl UN MPTF), JHNP MTR, plus JHNP and HCS latest Annual Reviews.

  1. An early market engagement with potential suppliers: DFID will organise consultative sessions to discuss possible areas of support with interested and potential delivery partners, before deciding what route to take. Potential partners include the UN, private management agents and NGOs. It will explore whether there is interest amongst the delivery partners to manage this sub component, as well as the potential for joint working and collaboration between partners.

  1. An assessment according to desired capacities and specific criteria. An assessment will be conducted in a transparent way, according to the options discussed with key and capacities desired by DFID for delivery of this sub component. The criteria will essentially help assess and compare the VfM potential for different suppliers. A draft set of criteria is outlined below

Table 5. Draft Criteria
Desired Capacities	Indicative Criteria
Potential to deliver VfM	Direct and indirect costs / Indicative Unit costs for EPHS delivery[65]
Operational Capacity	Staff, Offices, Logistical / Security, duty of care arrangements
Technical Capacity	EPHS – RMNCH and Nutrition expertise / Procurement, distribution of medicines and supplies expertise
Fiduciary Risk management	Contracting capacity / Size of previous fund management / Due diligence arrangements / Flow of funds/ audit capacity
Potential to achieve expected results	M&E capacity / Track record elsewhere of delivering results
[65] This will require a clear definition of catchment population to allow a comparison of per capita costs

  1. Recommendation to HoO and Director level: The preferred delivery option for this sub component will be submitted to the Health of Office and Direct Level for approval.

Consortium with EPHS delivered through an ‘embedded’ approach (2016-21) (component 1c): Support will be provided to a new Consortium to deliver 1-5 core EPHS services, plus it will explore how best to support the 6 EPHS management functions in three regions (10 districts) for a period of five years (2016-21). The approach will include strengthening downstream systems working closely with districts and regions[66]. A move to a more ‘embedded’ approach will respond to decentralised health system capacity needs through hands on mentoring and provision of technical assistance[67] to improve local planning, information and finance systems and fund key activities like community participation and supervision. Implementation will need to meet EPHS standards for delivery, both in terms of inputs (staff, medicines and supplies), the EPHS management and support functions as well as the outputs (quality, coverage and scope of services). The consortium mechanism builds on the comparative advantage and flexibility of an NGO managed delivery mechanism, with potential high performance that has been demonstrated by HCS to date. Given the volatile operating environment it also serves as an alternative delivery channel to spread responsibility for results and risks.
[66] 3 regions are Gedo, Karkar and Sahil currently covered by HCS. By implementing in three diverse regions at different stages of state formation and decentralised reforms, learning should be generated.
[67] It will work closely with existing reform mechanisms aimed at strengthening government systems (HR and PFM), including implementing decentralised functions at regional and district levels.

The demand creation component would be managed separately covering a period from 2016-21. This would be designed to complement EPHS and be implemented in areas where service delivery is taking place. It would entail the consortium lead managing a call for proposals organised around four thematic areas to promote health and tackle socio-cultural and gender barriers that affect demand and use of services. It would aim to target the most vulnerable and underserved populations in existing EPHS areas. Since the best approach for building demand is not known, innovative approaches would be piloted to create an evidence base for sectoral long-term scale up. This may include activities to shift attitudes and practices (of men and women), to mobilise vulnerable populations (adolescents and nomads) as well as introducing community oversight boards at facilities to increase accountability.

DFID would oversee a separate M&E component, covering third party monitoring, support to sector-wide surveys, studies and research. This option will require a robust evaluation approach to build up the evidence, to record the lessons learned and demonstrate results.

The early market engagement planned for late 2015 will assess the range of possible sub component activities that could be contracted out via a private management agent, with the aim to reduce costs. Potential areas may include the procurement, transportation, distribution and stock control of medicines and supplies. Another could be as the provider of specialised TA, or specific M&E tasks such as third party monitoring or carrying out surveys. A decision would be necessary by May 2016 to proceed with the contracting for this.

Option 4 – Delivery using UN and NGO consortium

DFID support to Health for the last five years (2011-16) has been channelled using a dual track approach via the UN delivery mechanism (JHNP) and a NGO consortium delivery mechanism (HCS) (Annex 1). JHNP support ends in 2015 and HCS support ends in March 2016.

There is a consensus that there is a need to avoid disruption in service delivery. This option will entail responding to this pressure by continuing with JHNP and HCS as is until 2021, without change to the management agents, the delivery mechanisms or the geographical area covered.

This option would require a strong justification why continuing doing business as usual will deliver maximum impact. In particular the extension of the Accountable Grant for HCS would need special justification. HCS was initially contracted in 2010, later extended under the previous BC between 2011-16. HCS has had 4 contract extensions, where changes have been significant. Extension of JHNP until 2021 would also require a strong justification.

Assessing comparative advantages for each option

A review of the comparative advantages of the three Options to respond to different health needs was carried out (Annex 3 Table 3e). Using a scoring Strong-Medium-Limited, Options 2 and 4 were scored as having limited comparative advantage, whereas Option 3 has strong comparative advantage.

Assessing evidence for each option

A review of the quality of evidence for the three Options found there is limited evidence for Option 2. Option 3 and 4 scored medium (Annex 3 Table 3f).

Assessment of the costs and benefits of each feasible option

In order to compare the costs of the programme for each Option, it was first necessary to calculate the total implementation and management costs associated with delivery. To generate these we gathered the actual direct and indirect support costs from management agents[68] operating in Somalia[69]. Assumptions[70] were then made about how funds would be allocated and contracted under each of the three programme components, for service delivery, demand creation and M&E. The different components have different management and sub-contracting arrangements and different agents charge different fees for these tasks. Details of these fees and how the proportional allocation[71] of funds was calculated can be found in Annex 3 (Table 3g).
[68] Management Agents include, UN, INGOs, Private Management Agents
[69] The direct support costs are on activities delivered directly by the management agent. However for the full picture, we also need to add in the indirect costs charged on funds that either pass through their HQ, or charges on funds passed on and managed by sub-implementers.
[70] One of the assumptions made is to remove the £8m 2016 contribution to UN from this analysis, which would be common across all options.

To calculate Option 3, we have applied two indicative cost scenarios to the service provision component. 3.a is a UN managed and NGO implemented arrangement with certain fees. 3.b is a Private Management Agent and NGO implemented arrangement with different fees[72].
[72] It should be noted that this is a preliminary costing of Option3 as we will be reviewing and making the decision on delivery option for component 3b for support covering 2017-21 in May 2016.

The findings show that direct support costs are likely to be similar across all Options, with some small variations in indirect costs.

Expected benefits of the programme

Quantitative benefits
To calculate how many people would benefit from access services for each Option, we have allocated 80% of the programme funds to service delivery and then used the unit cost of EPHS USD 5.88 per capita[73]. The findings are that this programme has the potential to provide EPHS services to approximately 2.4 million people in a year, or a cumulative of number of 11-12 million people in 5 years (recognising that this will not be unique numbers). There is little difference between the options presented[74].
[73] This is potential services provided not unique number people accessing services. NB. some people may use services more than once
[74] NB there is a risk of comparing these 2.4m people covered by EPHS a year, with the estimated coverage of current programmes which is 3m as this includes estimates of populations reached through JHNP (page XX),

Qualitative benefits
The above quantitative calculations of costs and benefits exclude the more qualitative benefits, such as changed health behaviours and or opportunities gained to participate, through demand creation efforts. Demand creation efforts will help shift attitudes and practices and mobilise vulnerable populations, which will reduce preventable diseases and encourage more people to use health services.

Any of the three Options will give health results, however what will give a bigger strategic pay off, is to embed delivery in government systems and give the government greater oversight. The interventions which apply a health systems strengthening approach are more difficult to put a value on, but are important to enhance government ownership and sustainability.

The strong focus on M&E should begin to address the evidence gap in a number of areas and also begin to make expenditure on supply and demand side interventions more efficient and effective both during the programme and further into the future.

Balance of costs and benefits

The balance of costs and benefits for each of the Options has been calculated to provide an efficiency ratio of the total programme costs to resource cost. The results of this analysis show no significant variations across the three Options. A higher ratio is more cost efficient and will deliver more.

Risks and opportunities

The Implementation Risk of each Option is scored between 1 (low) and 10 (high) below. All are considered medium risk:

Table 9: Implementation Risk
Option	Implementation Risk (1-10)	Reason
2	6	Single managing agency increases risk / UN has capability and is credible with government / Some performance concerns (mixed record in MoH capacity building; reports of slow systems)
3	6	Three managing organisations spreads risk
4	5	Status quo – benchmark score

The Preferred Option

The preferred selection for managing SHINE is Option 3, delivery using a mix of modalities. The rationale for this choice is outlined below:

We are confident that delivery using a mix of modalities will achieve the best results and spread risks across a range of delivery partners. This option also ensures there should be no break in service delivery in the 40 districts, which is a major health, social and political concern as this would increase the significant risk for conflict. During 2016 we will engage in a strong reform agenda to improve quality performance and focus delivery results of EPHS and to set the Strategy (including standards and priorities) for EPHS roll out in future. We are also confident that this preferred option with support to both supply side interventions (80% of funds) and demand creation interventions (17% of funds) will deliver the expected results. We are assured that the complementarity of demand side interventions in areas where supply is being delivered, will provide good value for money. There is strong evidence of likely programme performance and high degree of confidence in the expected results.

To date there has been limited choice of delivery partners and little competition between agencies working on health in Somalia. The difficult operating environment and high costs of insecurity also result in high management and implementation costs. DFID S will also seek to push for increased transparency and a reduction in direct and indirect costs amongst all agencies. Our preferred choice aims to open the market up to greater competition; it will allow the space for private management agents to engage and will encourage opportunities to increase VfM through reducing costs.

During the process of this appraisal we have been informed that due to the multiple extensions to date under HCS we will not be granted a further cost extension for this programme. This makes Option 4 no longer viable. Full delivery of the programme through the UN using Option 2 is also not considered best VfM as it reduces choice and competition and increases risk to one management agent. The appraisal confirms that Option 3 will provide DFIDS with the best delivery mechanisms, through diversifying the mix of implementation arrangements.

The sections below outline a robust Theory of Change in support of the preferred option. This is followed by a more detailed Economic Appraisal which presents the incremental benefits of the preferred option and a plan to monitor VfM over time against comparators.

Theory of Change (ToC)

The plan is to divide funding between the three components as follows: EPHS service delivery (80%) of which 29% will follow an embedded approach, Demand Creation (17%), M%E (3%). A theory of change (ToC), reflecting this allocation split, is presented in chart 4 below. The ToC recognises that there are a series of both supply and demand processes in health that when supported, will lead to a series of outputs and subsequent outcomes and impact that will improve the health of Somali’s and contribute to wider Human and Economic Development. The ToC for the preferred option takes into consideration four critical assumptions:

Assumption 1: Investment through a mix of interventions and mechanisms allows for increased geographical reach, empowerment of both government and communities, combined with spreading of risks.

The mix of instruments through the UN, NGO and also private providers, will require agencies to demonstrate their areas of comparative advantage and encourage competition on efficiency and effectiveness, particularly on EPHS delivery. A mix of mechanisms, under one sector oversight body, will promote coherence and complementarity between demand and supply side interventions.

It is assumed that managing at least two of the components through NGO Consortia will allow maximum flexibility to trial new implementation modalities and interventions at small scale to test for effectiveness and efficiency before larger scale roll out.

Assumption 2: Improved quality and standardization of EPHS increases access to services.

The ToC assumes that by supporting an EPHS expansion strategy with improvements in the coverage, with standards on quality and breadth of services this will increase access by Somali’s to appropriate care. The assumption is that by giving priority to trial an embedded EPHS delivery model this will promote strengthened government oversight, greater accountability at devolved levels, as well as increased visibility and sustainability of MoH as the provider of EPHS. It is also assumes that nutrition interventions will be fully integrated into EPHS, to achieve maximum results.

Assumption 3: Tackling key barriers to access will increase demand for health services

The ToC assumes that through health promotion and tackling key barriers to access it will increase demand for health services. By focusing more on the demand side barriers and wider social determinants of health and trailing new methods to reach the most vulnerable populations this will serve to prevent the main causes of ill health, increase the use of services, and challenge norms and practices that endanger health, including FGM. This ToC assumes that through operational research and pilots targeting different barriers to health service utilization will not only contribute to the body of evidence in this area but also in the development of effective interventions and development of cost effective demand side policy.

This ToC also acknowledge recent developments such as the Somali Community Health Strategy present an opportunity to link community level health interventions which include demand creation to health service delivery. By leveraging on structures in place to promote community involvement in health management, it is assumed that this will strengthen community knowledge, acceptance and delivery of health services that is responsive to the needs of the community.

Assumption 4: Increased utilization of quality care will reduce morbidity, disability and mortality.

As presented in the strategic case, there is strong evidence that effective high coverage and an associated increased uptake of the proven RMNCH and nutrition interventions will reduce morbidity, disability and mortality. The assumption is that the combination of strong service delivery focus, combined with systems approach and demand side interventions will reduce morbidity and mortality in Somalia.

The evidence suggests that increased supply and demand will improve the utilization of these services; and, increased utilization of health services will lead to distinctively better health and survival experiences for women and children, impacting on poverty avoidance and economic growth.

Table 10: The theory of change for the preferred option

Appraisal Stage 5

Stage 5, begins with economic appraisal of the preferred option. This is followed by appraisals of the range of potential impacts on the environment, on society, on conflict and fragility as well as gender.

Economic Appraisal

Incremental benefits of the Preferred Option

Table 13 below provides an overview of the more incremental benefits from implementing the preferred Option. While it is not possible to quantify or monetise all the benefits of the full programme, it is very likely that the benefits will outweigh the costs. The analysis of the incremental benefits also demonstrates that the overall benefits of the preferred option, when compared to do nothing (the counterfactual) are likely to be greater than the incremental costs.

Table 11: Summary of benefits to Somali Health and Nutrition Programme
Description of main benefits	Quantification	Monetisation (undiscounted)
Improved Health and Nutrition Status: Somalis will benefit from improved health and nutrition status, as a result of reduced barriers to access and increased coverage and quality of service provision	Maternal mortality reduced from 850-810 per 100,000 / Under 5 mortality reduced from 146 to 102 per 1,000 / Contraceptive prevalence increased from 15-25% / 1 million children U5 and pregnant women accessing nutrition specific services	Convert to DALYs [75]
Increased service delivery efficiency: An evidence focused and VFM approach to EPHS will improve delivery of services for an estimated 4.6m people	Increase efficiency and effectiveness of EPHS supply interventions (measured by EPHS costs per capita) / Increased utilization of key services, measured by[76]: / SBA: 63,000 / ANC 2+ visits: 202,000 / child immunizations: 120,000 / Contraceptives distributed: 270,000 / Nutrition services: 1,000,000	Unit costs per capita of delivery of full package and specific services are within acceptable range (USD 6.00) – Annex 3.
Strengthened Demand Creation: Empowerment of beneficiaries, communities and health facility boards to prevent and treat health and nutrition needs	Improvements in Knowledge Attitudes and Practices regarding health and nutrition / Increased use of health services by vulnerable populations (# nomads and adolescents) / Increased # health facilities with community oversight boards	Not possible
Government Ownership: The embedded model will strengthen government management of EPHS at national and devolved levels, improving accountability to citizens and sustainability of delivery	Increased co-financing measured by % contributions by stakeholders at different levels	% of co contributions to the programme
Conflict/security benefits: Implementation through partners that apply conflict sensitive programming approach and build accountability at community levels	Not quantifiable	Not possible
Gender and Social benefits: Improved well being of women and children will promote gender equality, challenge harmful social norms, support poverty reduction and increase economic development at the household and community levels	Reduced expenditure on health as a % of household income	Not possible
[75] It is proposed that DALYs be calculated during the early design stage of the New Programme. Once DALY information is available we would then also be able to monetise the benefits by either using a cost benefit analysis or a cost effectiveness analysis.
[76] Details of the Results Bid are included in Annex 3, Table 3 h

Value for Money Measures for the Preferred Option

It is proposed that the preferred Option supports an enhanced VfM approach with specific well defined VfM variables for measuring EPHS overtime against appropriate comparators. The proposed VFM indicators for doing this are set out in Table 14. These indicators are build on the recommendations from two reviews[77],[78] that were commissioned in 2013 to identify a set of quantitative VFM indicators which the existing health partners. These VFM indicators remain appropriate for this new programme.
[77] Pfeiffer, J., Report on VfM technical support to JHNP, 2013
[78] Pfeiffer, J., Report on VfM technical support to HCS, 2013

Table 12: Proposed VFM Metrics for the New Health and Nutrition Programme
Cost per Community Health Worker trained
Cost per Midwife trained
Management fees as proportion of total project value
Cost per OP visit
Cost/birth attended by a skilled birth attendant
Unit costs for Nutrition intervention (tbc)
Cost per CYP Cost per new client for modern contraceptive methods
Cost per pregnant woman receiving ANC 2+

Additional VFM metrics recommended for the programme to track are: cost of EPHS per capita, cost of EPHS per user, ratio component expenditure (direct project expenditure and evaluation expenditure) to total resource cost.

Environmental Appraisal

Overall the intervention is expected to have limited impact on climate change and environment, with little change by Option.

There are opportunities for climate change issues to be integrated into policies and strategies, through district health planning and budgeting and through the remit of Community Health Committees as well as through increasing the knowledge and skills of the health workforce. In addition, there are opportunities through support for infrastructure upgrading including installation of solar panels and other green energy solutions, and water conservation measures in health facilities. These infrastructure interventions are already set to receive support in Somaliland for hybrid mini-grids for health facilities through the DFID Somalia ESRES programme (although no funding from this programme has been allocated to this).

Environmental risks are associated with (a) procurement of drugs and commodities, (b) infection control and disposal of medical waste at facility level, (c) logistics including use of transport and (d) infrastructure. Measures to mitigate these risks will include ensuring that implementing partners employ sound environmental management procedures in their procurement guidelines and select procurement options with a minimal carbon footprint and health facilities implement procedures for safe disposal of medical waste and infection control.

     Table 13: Climate change and environment risks[79]
[79] The scores are A: high potential risk/opportunity; B: medium/manageable potential risk/opportunity; C: low/no risk/opportunity; D core contribution to multilateral organisation.
Option	Climate change and environment risks and impacts, Category (A, B, C, D)	Climate change and environment opportunities, Category (A, B, C, D)
1	C	B
2	C	B
3	C	B

Social Appraisal

Overall the programme is expected to have a positive social impact

Health services in Somalia have been and are still severely impacted by conflict. Somalia’s population remains highly vulnerable. More than 730,000 Somalis are in need of urgent humanitarian assistance, a further 2 million are food insecure and cannot satisfy their basic daily nutritional requirements. Somalia is prone to regular systemic shocks including outbreaks of clan- and community-based violence and drought. The public system began to break down in the final years of the Siad Barre regime but was completely absent during the decades of civil war. Only since 2010, with the reengagement of the international community, including DFID and the UN, have health Ministries begun to reassert a role in the development and implementation of health policies. Although the regional and federal governments still have no practical role in delivery, which is carried out be non-state actors including international NGOs, the harmonisation of health policy has been one issue of productive dialogue among otherwise competitive and belligerent parties.

Somalis use a range of health services from traditional and religious healers, private providers especially pharmacies, and modern services from NGO and UN providers, including humanitarian relief services. Where public and modern health services have been unavailable, Somalis have relied on unregulated traditional healers and pharmacies. Health decisions are informed by religious and traditional beliefs, cultural and social norms, proximity and access to services, cost, and awareness of available resources. Awareness of modern healthcare, including vaccination and birth spacing methods, is very low. Traditional and religious healers are often the first port of call, especially for nomadic populations, while modern clinics and hospitals may be seen as a last resort. Usage in towns remains low (less than 0.7 visits to a modern facility per year) and is unknown in rural areas and among nomads. The support for health systems, including HMIS, will improve the monitoring and understanding of usage of modern health services. Relations between the traditional and public health sectors can be hostile and prevent transition to modern healthcare, but engagement with traditional practitioners, such as traditional birth attendants, as well as demand side interventions, will shift norms and encourage uptake of services.

As presented in the strategic case, social norms which are heavily influenced by elders and religious leaders currently impede the uptake of modern healthcare and health seeking behaviour. Men are the undisputed heads of household and have control over most health decisions for the family. This is especially true around birth spacing and early childhood health decisions, including vaccination. Women are not likely to discuss health or birth spacing with friends, health workers or anyone outside the family. The creation of demand for health services under this programme will make interventions into these normative structures, including through engaging men and religious leaders, to increase awareness and uptake of modern health services.

Community level decision-making processes in Somalia are highly exclusive determined by complex social, economic and political conditions influenced by the clan system. Women and other marginalised communities, including minority clans, non-ethnic Somalis and pastoralists, face specific and general barriers to participation. The local determination of health priorities through committees and the targeted inclusion of women provides a pathway to participation in decision-making that may develop the legitimacy, improve the effectiveness, and increase the accountability of governance systems. Demand-side creation activities should contribute toward behaviour-change in terms of both health-seeking behaviours and challenges to exclusive social norms. Women and children are the primary beneficiaries of the direct healthcare provision under this business case, but the demand creation activities should also meaningfully include boys and men as contributors to decision-making with regard to health.

The support for health and nutrition proposed under this programme is recommended to enable the most vulnerable Somalis to graduate from poverty. Poor health outcomes are directly linked to the proportion of the Somali population living in extreme poverty, an estimated 61% and 80% for urban and rural areas respectively[80]. The strain on family and community resources from high fertility rates (6.6 children per woman) and high maternal and child mortality rates is significant. This programme should seek to avoid a break in service delivery, to prevent an increase of vulnerability, which could exacerbate existing drivers of instability and conflict. Displaced, rural and nomadic populations are the hardest to reach and most excluded of Somali society. The availability of health services under this programme must extend beyond urban areas both to meet the extreme need of these populations and to encourage the spread of stage engagement with these groups.
[80] UNDP Human Development Report 2012

Conflict and Fragility Appraisal

Overall this programme is expected to have a positive impact on reducing conflict and fragility.

To ensure conflict sensitivity in the context of Somalia, implementers of development interventions need a deep understanding of drivers of conflict and fragility, which requires the extensive collection and triangulation of information from multiple sources. In Somalia, this is complicated by the diversity of local contexts and restrictions on access of some staff (including donor staff) to target locations and beneficiaries owing to insecurity. To improve effective delivery it is desirable that implementing partners have local presence and knowledge of the communities they are to serve. Beyond analysis of the context, conflict sensitive programming requires that implementing partners continuously review the potential for their interventions to do harm (for example exacerbating tensions over resource allocations or unclear targeting of beneficiaries) by applying the principles of transparency and accountability through a sustained dialogue with all relevant stakeholders. This takes time and effort and requires a sufficiently wide range of local knowledge and relationships.

The community engagement strategies proposed under this business case are expected to enhance the conflict sensitivity of interventions. The flexible delivery model will also enable the programme to respond to learning from implementation on the ground, including learning about the evolving conflict context in target locations requiring adjustments to interventions to maintain their conflict-sensitivity, as well as learning on what ‘community engagement’ entails in practice. The programme will also build on the strong collaboration established to date with ministries of health from the Federal Government, Somaliland and Puntland to continue to build consensus and collaboration across the sector and will carefully manage the gradual inclusion of newly emerging administrations in the south and central regions.

Gender Appraisal[81]
[81] The current Health Programmes have been the DFID flagship programme for gender equality in Somalia.

Overall this programme will directly contribute to reducing gender inequality in Somalia, given its strong target focus on women and girls.

Severe gender inequality is a major impediment to health in Somalia. Women’s low literacy, especially among rural and displaced populations, reduces women’s awareness and access to health services. 97.4% of women in the UN KAP study never read print media. Targeted demand side interventions are necessary to increase awareness and uptake of services and must support the empowerment of women to make health decisions. Violence against women and girls, including Female Genital Mutilation, is prevalent in Somalia. Such violence is normalised and victims may not recognise themselves as such. VAWG has impacts on health ranging from complications in pregnancy and birth to prevention or lack of access to services. Evidence reports health staff refusing to treat women without her husband’s permission. Further, there is evidence of FGM being increasingly carried out by health workers. In the strengthening of the health sector, this programme will challenge medicalisation of FGM. Improving availability of services must be achieved through an approach that takes account of these limitations and increases demand by intervening in the development and transmission of social norms.

Implementation Arrangements

Geographical coverage

The initial geographical coverage of the programme will be confined to the existing JHNP regions and historical HCS regions as outlined in Chart 1 (page 5). During the implementation period there may be possible changes in geographical focus, to respond to the new EPHS Roll Out Strategy and emerging needs and emerging administrations, however this would be decided together with the Health Authorities and MA.

Co-Funding from Others

Any DFID funding channelled via the UN, through the pooled fund, is likely to be open to receive co funding from other donors. Components 2 and 3 will be initially funded just by DFID S but there may be opportunities for other donors and stakeholders to collaborate. Co-funding of interventions will be promoted to reduce dependence and enhance sustainability. This may include counterpart contribution by the health authorities, co-contributions by INGOs as well as contributions in kind by communities.

Links to other DFID funded programmes

SHINE will compliment other DFIDS funded programmes. The links between them are:
1. Governance and Peace Building programmes. Share lessons and approaches on Accountability, Local Governance (JPLG), Capacity Building at decentralised levels.
2. Humanitarian and Nutrition Consortium programme SNS (£10m): Close coordination will be necessary to bridge humanitarian support and acute nutrition interventions with longer term routine health and nutrition prevention and treatment services, with set standards for delivery.
3. Tackling Gender inequalities (£10m): It is clear that FGM and early marriage contribute significantly to maternal and neonatal deaths. Interventions aimed at social norm change and eradicating FGM will be covered in a new Programme which is under design.
4. Economic Development: Share lessons and approaches on PFM strengthening and Recurrent Costs for Social sectors through WB MPTF. Linkages will be sought on health worker salaries, around payroll reform and lessons from working with civil service commission and MoF. Linkages will also be sought with PIMS around building human capital, given that a healthy workforce is necessary for job creation.
5. Renewable Energy - Strong links will be made with ESRES[82] mini-grids programme to provide clean energy to health facilities.
  [82] DFID S ESRES business case March 2014
6. Education (multilateral funds) – Closer collaboration will be sought to (i) improve girls understanding of Sexual Reproductive Health Rights (ii) strengthen integrated basic service delivery at decentralised levels.
7. Somalia Monitoring Programme – Collaboration will be sought around independent third party monitoring and supporting research and surveys.

Commercial Case

It is anticipated that the planned mixed delivery approach will promote greater competition and will allow DFID S to manage sustained improvements in VfM as well as a reduction in management costs.

What are the procurement and commercial requirements for this intervention?

DFID will provide up to £92 million over 5 years. The planned breakdown by component is as follows[83]:
[83] Please refer to Financial Case for the full Financial Breakdown

Component	Amount £ (%), Duration
Component 1, EPHS service delivery via Mix modalities	£73m (80%) 2016-21
Component 2, Demand Creation	£16m (17%) 2016-21
Component 3, Monitoring and Evaluation	£3m. (3%) 2016-21

   Note. Annex 4, Table 4A provides a summary of the aid instruments that will be used for each component.

Service Delivery (Component 1)

Component 1 has three procurement arrangements for service delivery support, these are:

Sub-Component 1a. EPHS will be delivered in 9 regions, through the existing JHNP/UN programme in 2016 (£8m).
- Support will be renegotiated for one additional year in 2016, to ensure continuity in service provision and to avoid significant health and political implications of withdrawal from JHNP before the end of the current programme[84].
  [84] This is especially sensitive, given that DFID was the DFID lead donor in setting up JHNP and is also leading support on the New Deal process
- A new MoU will be negotiated with UNICEF, outlining the earmarking to EPHS, the reporting arrangements and targeted results[85].
  [85] Discussions have already been going on with UNICEF on improving reporting and getting more reliable results from implementing partners.

Sub-Component 1b. EPHS Phase 2 (£38m)
Between 2017-21[86] a new phase of support to EPHS will follow (component 1b). We are keen to bring more competition into the market and to examine ways to improve VfM. The options for doing this will be assessed and agreed through a well-documented transparent process which will be concluded by May 2016. The assessment process will involve the following four steps:
[86] JHNP is currently scheduled to run from 2011 and end in December 2016. However it is still not clear on what happens to this programme from 2017 onwards, including whether it will transition under UN MPTF.

A desk review of background documents to clearly define the need: Review of the new EPHS roll out strategy, lessons from EPHS delivery to date, update on the New Deal (incl UN MPTF), JHNP MTR, plus JHNP and HCS latest Annual Reviews.

An early market engagement with potential suppliers: DFID will organise consultative sessions to discuss possible areas of support with interested and potential delivery partners, before deciding what route to take. Potential partners include the UN, private management agents and NGOs. It will explore whether there is interest amongst the delivery partners to manage this sub component, as well as the potential for joint working and collaboration between partners.

An assessment according to desired capacities and specific criteria. An assessment will be conducted in a transparent way, according to the options discussed with key and capacities desired by DFID for delivery of this sub component. The criteria will essentially help assess and compare the VfM potential for different suppliers. A draft set of criteria is outlined below

Desired Capacities	Indicative Criteria
Potential to deliver VfM	Direct and Indirect Costs / Indicative Unit costs for EPHS delivery
Operational Capacity	Staff, Offices, Logistical / Security, duty of care arrangements
Technical Capacity	EPHS – RMNCH and Nutrition expertise / Procurement, distribution of medicines and supplies expertise
Fiduciary Risk management	Contracting capacity / Size of previous fund management / Due diligence arrangements / Flow of funds/ audit capacity
Potential to achieve expected results	M&E capacity / Track record elsewhere of delivering results

Recommendation to HoO and Director level: Given the size of funding (£38m), the preferred delivery option for this sub component, will be submitted to the Health of Office and Direct Level for approval.

It is anticipated that this commercial approach will allow DFID to achieve better VfM. The potential commercial, contracting implications for sub-component 1c are outlined below:
- UN managed: Any new support by DFID via the UN would require a new MoU. It is proposed that this MoU specify the terms and conditions on management fees, VfM measures and reporting. For EPHS, this may include quality measures and additional management functions and possibly a shift to a more embedded approach within the MoHs at both the zonal and then regional levels. This revised approach would still be administered by the UN[87] and monitoring would continue through a joint UN/government led monitoring process[88].
  [87] UNICEF or alternatively through different UN agency such as UNDP, especially if UNMPTF begins to manage this
  [88] The Frameworks between DFID/ UNICEF, were renewed in 2015 with tighter reporting timelines agreed with the UN agencies.
- Given that the direct management costs charged by the UN are set at HQ (and are not open to negotiation), the main opportunities to improve VfM are through the indirect costs (for which we can push for greater transparency), plus increased efficiency and effectiveness of programme spend. To enhance the VfM of this delivery route DFIDS will:
    1. seek support from UNCD in negotiation of MoU revision to earmark funding and link funding to performance and request greater transparency on indirect costs
    2. consider linking tranche releases to assessments of achievement against the annual milestones set out in the project document. If performance is off-track, we would explore options for reducing or re-allocating funding.
    3. Agree VFM indicators for regularly reporting on service delivery
NGO managed or a Private management agent. DFID Somalia will work with PCD to hold early market engagement sessions with international NGOs with the private management agents in late 2015 early 2016[89]. We will explain the requirement in more detail, to encourage better competition and inform the most appropriate route to market. If it is decided to proceed with contracting the full sub component through an OJEU process, a ToR would be developed to specify the requirements for the 4 years of support[90]. Alternatively based on the early market engagement it may be decided that specific activities, under different components may be contracted out.
[89] This should take place late 2015 early 2016.
[90] These will provide the benchmark on quality and costs against which satisfactory performance will be measured

Sub-Component 1c. Embedded EPHS will be delivered in 3 regions through an Accountable Grant for 5 years (£27m).

- There is a strong justification that this commercial approach will deliver good VfM in Somalia. This is based on the excellent and consistent high level performance and results achieved through HCS in the last 5 years.
- A consortium of NGOs will be selected through a call for proposals, which will outline a broad scope of work using a consortium approach. A team of cross sectoral DFID Somalia staff will appraise the proposals. An accountable grant will be issued for 5 years to the NGO consortium lead and it is expected that the lead NGO will sub-grant to the other NGOs in the consortium. To prevent a break in service delivery, this will need to be in place by March 2016[91]. Due diligence will be carried out after selection of the NGOs.
  [91] When the current HCS contract ends

Component 2 - Demand creation (April 2016 - Mar 2021).

After some consideration it was decided to separate out support to Supply and Demand into two contracts. The main reason is to separate the government’s role in service provision – from the demand work at community and household levels. It was also felt that combining the two also risks reducing the flexibility and becoming too bureaucratic.

The demand creation component would be managed separately covering a period from 2016-21. This would be designed to complement EPHS and be implemented in areas where service delivery is taking place. It would entail the consortium lead managing a call for proposals organised around four thematic areas to promote health and tackle socio-cultural and gender barriers that affect demand and use of services. Since the best approach for building demand is not known, innovative approaches would be piloted to create an evidence base for sectoral long-term scale up.

The Demand creation component will be Managed by a consortium lead which will be selected through a call for proposals using a broad scope of work. A team of cross sectoral DFID Somalia staff will appraise the proposals. An accountable grant for 5 years will be issued to the lead NGO in the consortium. The consortium lead will sub-grant activities to other NGOs based on agreed thematic areas and results to be achieved. Due diligence will be carried out after selection of the NGOs.

Component 3 - Monitoring and Evaluation (2016-2021)

DFID will oversee the M&E component with a robust evaluation approach and focus on evidence (see Management Case). It may also support sector wide surveys, studies and research and independent third-party monitoring. This work will be contracted through direct sourcing or, for smaller pieces of analytical work, existing DFID call down frameworks such as PEAKs[92] will be used. Larger contracts could be contracted through the GEFA framework. All service providers will be selected on the basis of an ability to deliver a specific set of services to a high standard and at good value to DFID.
[92] Discussions with the framework will be held in advance of issuing of ToRs.

Key cost drivers that will affect the price of delivery

Somalia is known as a challenging and costly work environment and Duty of Care will be the sole responsibility of appointed Management Agents. Security costs are likely to attract a cost premium. The main cost drivers in the implementation of the EPHS vary depending on access, remoteness (urban/rural), security, or level/type of care. Differences in the costs reported between implementers have been identified for the following factors; input prices for infrastructure, equipment, human resources, drugs and medicines, and variation in utilisation of services. DFID Somalia will work closely with the Management Agents to ensure that overheads are reasonable; the organisation has the capacity to deliver services effectively and offers best value for money.

The main management cost will be from the direct and indirect costs charged by Management Agents. Through this new programme DFID will seek to drive down both the direct and indirect costs (see Table 8, p28 in the Appraisal section).

If fund management for component 1c goes to a private fund manager then the key cost drivers in these contracts will be the fees of the supplier, the types of professional services delivered through the Technical Assistance (TA) and any sub-tier suppliers, such as specialist technical support and the prices of related goods such as travel and transport. The direct cost (management fees) of the fund manager[93] are 23% (plus 3% profit plus 9% indirect support costs). PCD will benchmark proposed rates in relation to the current market and will form a significant part of the commercial evaluation.
[93] Based on information gathered from two Private Management Agents operating in Somalia

How we expect the market place will respond to this opportunity

We expect there will be a good response from the market to this opportunity.
1. The UN has expressed an interest in continuing to manage/oversee the delivery of services; however this would be through an MoU not a contract.
2. INGOs have, in preliminary discussions, expressed interest to manage the Embedded EPHS. Further discussions with INGOs would need to take place regarding their desire to bid on a contract via an OJEU process.
3. There are a couple of private management agents, working in Somalia. These organisations (plus new ones) may be interested in responding to a possible OJEU tender however this would not be until 2016.

Implementation through a third party

It is expected that the ultimate implementation partner for components 1, 2 and 3 is likely to be by NGOs, irrespective of what management agent is brought in.

For component 1 there are three third parties that will potentially manage implementation - the UN, NGOs and private management agents.

UN. Performance of the UN will be monitored against a new MoU with clear quality standards for EPHS delivery. In reality the UN will sub contract to INGOs a large part of their delivery functions. UNICEF has access to extensive operational networks on the ground and has conducted due diligence and capacity assessments to over 47 NGOs. The UN is also supported by the Risk Management Unit (RMU) which maintains a risk register of black listed INGOs and NGOs (with links to terrorism, or fraud) and they also conduct investigations on implementing partners in Somalia. The programme will require an annual approved workplan and produce quarterly/six monthly reports, including on set VfM indicators.

NGOs. Performance of the Consortium would be monitored using an Accountable Grant, with clear quality standards for EPHS delivery. The Consortium will need to set out how it will monitor risks. It will also require an annual approved workplan and produce quarterly/six monthly reports, including on set VfM indicators

Private Management Agent. DFID S will work with PCD to conduct an early market engagement to assess the options for private management agents for 2017-21. If, it is decided to proceed through an OJEU process[94] DFID Somalia would draw up robust terms of reference to maximize competition, ensure high quality services and best value for money. If the procurement process is initiated in Mid 2016, it is expected contracts could be signed by March 2017. The duration of the contracts would be for 4 years up until March 2021. Performance would be assessed on key performance indicators and payments released according to a schedule based on agreed results. Performance will be assessed by a Technical Working Group (see Management Case).
[94] We will use standard OJEU procedures and guidelines

For Component 2, DFID would issue a call for proposals to INGOs according to abroad scope of work. The INGOs would develop a workplan, which would be monitored through quarterly reports and reviews.

For Component 3, DFID Somalia would procure services, with specific terms of reference, through contractors directly or partners identified under the global DFID Framework Agreements such as PEAKs and GEFA. DFID may also work with other DFIDS M&E programmes, such as the Somalia Monitoring programme or the Humanitarian M&E Transtec.

Procurement Capability

Within the programme, the UN, the lead NGO or the private management agent could all directly procure goods and services. It is expected that the EPHS supplies, ie. drugs and equipment will take up the biggest cost of procurement. Based on existing spend through HCS and JHNP, equipment/CDEL costs is likely to be around 10% of spend and supplies 15-20% of spend. This programme does not envisage large scale support to infrastructure. However, we will consider one off small scale support to maintenance and refurbishment where this is necessary to ensure service provision. Given the scale, and the bulk of procurement, there will be need for a unified negotiation of unit costs and lowers transaction costs by the UN and the NGO conducting the procurement. In Phase 1 it is expected that NGOs will procure supplies and equipment in a joint process through an existing effective internationally recognised procurement agent. For Phase 2, the Service Provider will need to demonstrate a robust procurement and delivery mechanism to ensure value for money for supplies and equipment.[95] The supply chain will need to be thoroughly assessed with an agreed risk mitigation strategy in place.
[95] If it’s a private supplier, and goods exceed £ 111,676 any procurement will need to be done by a procurement agent

To manage this, it is envisioned that annually a consolidated procurement plan consisting of medicines, commodities, equipment and health service infrastructure will be presented to the Ministry of Health/Technical Working group for approval as part of the regular annual planning and budget cycle of the programme. Stringent criteria will be set for the construction, upgrading or rehabilitation of health service infrastructure.

How contract & supplier performance will be managed through the life of the intervention

For all agreements[96] DFID would:
[96] In the case that the private sector delivery model is chosen for component 1 in Phase 2, The contracts/ contractors with Service Providers will set out Key Performance Indicators (KPIs) linked to annual programme work plans, indicators and their milestones and targets in the logical framework.
- Conduct annual reviews to assess performance against targets
- Monitor programmatic and financial performance through quarterly reports and meetings with the implementing partners
- Put in place a risk management strategy

DFID Somalia will maintain management and due diligence of the appointed Service Provider(s). All organisations that compete for high-value work are subject to pre-qualification, a process that assesses their capability/ capacity/ resourcing to meet identified requirements, and to supplier disclosure requirements regarding convictions or legal proceedings against them including fraud, bribery and corruption.

The Management Agents(s) would be expected to demonstrate work plans to demonstrate how successful delivery will be achieved – payment will be based on successful delivery of deliverables. The Management Agents(s) will be similarly be required to manage downstream suppliers ensuring due diligence, and to coordinate returns through financial reporting, accurate forecasting, work plan reporting, sub-contract management and demonstration of how continuous quality improvement and cost reduction will be achieved and maintained over the intervention duration.

A risk management log will be maintained proactively logging risks associated with successful project delivery and identifying risk mitigation measures that can keep the project on track. Independent annual reviews and continuous independent auditing will track delivery and ensure that project investment has been used for its intended purpose. Independent monitoring and validation of project outputs will provide assurances that DFID funding is being used for its intended purpose.

Due to the long duration of the programme, the agreements used must have adequate provision for variation to adapt to changes that occur during the life of the programme.

Third Party monitoring

Under the Somalia monitoring Programme, 50 verifications have been conducted of the health programme with varying results ranging from well performing to needing attention. Overall most of the verifications have indicated a consistent and reliable delivery of services by our partners. The verification exercise has also pointed out areas where partners were not delivering as per the agreed standards, where there have been gaps in service delivery, supplies stock-outs and lack of trained personnel within health facilities. This verification exercise has proved very helpful especially because DFID staff are not able to conduct monitoring visits or spot checks in a lot of our project sites. For the new BC, there will be need for further exploration of the options for a coherent and well-structured third-party monitoring and verification exercise of project activities.
# Financial Case

A. Who are the recipients of all proposed payments? / DFID Somalia will allocate up to £92 million from programme resources over a 5-year period from 2016 to 2021 for the delivery of health and nutrition results. The ultimate recipients of support will be the most vulnerable people in particular women and children under 5. / The plan is to divide up funding between the three components in the following way – EPHS service delivery (80%), of which 29% uses an embedded approach, Demand Creation (17%), M%E (3%). Recognising that there is limited evidence available on what the optimal balance is between the service delivery and demand creation components, this is something which will monitored and subject to review during implementation. / The financial commitments will be made for the full 5 year duration of the programme for components 2, 3 and 1c. Funding for 1a, will only be for 2016. Funding for 1b will run for 4 years from 2017-21.
What are the costs to be incurred directly by DFID? / All costs will be directly funded by DFID from programme resources. The cost estimates are based on implementation of similar programmes. The main cost drivers are human resources (salaries, allowance and top-ups), followed by drugs and medicine
What are the costs to be incurred by third party organisations? / These costs for components 1, 2 and 3 will be defined once all the partners have been identified and selected as competitive costs will form part of the tender process. We will plan to push indirect costs for component 1, to below 15%. For direct management costs we plan to push these to below 20% for all management agents.
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / No. Whilst DFID supports the New Deal Principles which reinforces that ‘the development of services should be through the country’s own systems even in the challenging environment of fragile post conflict states’. DFID will not transfer any funds directly through the government systems given the high fiduciary risks. However, the UN system makes provision for transferring a maximum amount of USD 25,000 to any partner (including government) using the UN Harmonised Approach to Cash Transfer (HACT) principles. This will require close monitoring to manage the risk associated with this.
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / The programme will be funded from the DFID Somalia Resource allocations as part of the Human Development pillar. It is estimated that CDEL cost will be approximately 10% of the total Health and Nutrition budget.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / The forecast is an estimate and will be firmed up as partners are identified and agreements concluded. The UN allocations in year one are based on the costs of existing programme interventions. The Senior Responsible Owner (SRO) and the programme manager will work closely with the Implementing Partners (IP) to review and test the assumptions supporting forecasts and ensure that any variances to forecasts are supported with clear explanations and kept within the DFID targets. The IPs will also be required to adopt (where necessary) DFID’s standard procedures on accounting, audit, and reporting, for example, payment in advance rules. / IPs will provide annual forecasts at the beginning of each financial year. The SRO will work closely with the Programme manager to ensure that no funds are disbursed in advance of need.
What is the assessment of financial risk and fraud? / In terms of financial and fraud risks this programme is considered to be high. Somalia as a fragile state presents particular challenges for fiduciary risk for donor funding of health care because of the absence of a sound government public expenditure systems and financial management capacity. This will be mitigated through the use of a Management Agent in the form of UNICEF for component 1a. and in the form of the INGO Consortium lead for Component 1.c and 2 respectively. The management agent for 1b will be decided in 2016. Component 3 will be managed directly by DFID Somalia. Splitting the management of funds between the three components will spread the risk and allow for greater scrutiny of spend. / Risks will be mitigated at two levels: / Upstream: The UN system makes provision for funding directly to other partners (including government) using HACTs. UNICEF will be asked to report directly to DFID Somalia on a quarterly basis on these specific funds. A DFID due diligence (DD) procurement systems check was conducted on UNICEF in 2013. The DD check tests and evaluates the robustness of partner systems and their ability to deliver a programme in such a context. The UN also undertake due diligence assessments of their sub-implementing partners prior to contracting. / In late 2015 DFIDS plans to undertake a programme audit of JHNP. This will include a review of the use of HACT guidelines. The findings will be used to inform future risk mitigation measures via the UN. If necessary, DFIDS will agree a common position for funding use and reporting on HACT (across other DFID funded, UN managed programmes). / The INGO consortium lead agency will also undergo the DFID DD assessment and will undertake similar checks on, any sub-partners to ensure that their financial management and other systems are sufficiently robust to manage funds and deliver activities and results. The INGO will not provide any funding direct through government systems without first conducting a fiduciary risk assessment. / Downstream: Third Party monitoring by an external contractor will be put in place in order to validate results on the ground as well as undertake an annual audit of accounts. / All agreements will specify DFID requirements and timelines for reporting fraud or corruption, or any suspicion of the same. Any DFID or partner concerns about fraud and corruption will be reported within the required timeframe to the head of Internal Audit or the Counter Fraud and Whistle-blowing Unit.
H. How will expenditure be monitored, reported and accounted for? / The SRO is ultimately accountable for the expenditure of funds against this BC. The programme manager (PM) will set up an ARIES project with separate components for each programme or contract managed and with accurate funding types and sector input codes. In the implementation phase, the PM will be responsible for producing reports on actual and forecast spend against each component on a monthly basis, which will be used to monitor partner performance. / The SRO will authorise disbursements of funds based on the agreed funding profile set out in the funding agreements and contracts and upon the assessment of partner performance and reporting. All the service providers will be expected to provide proper documentation of expenses and provide evidence of satisfactory delivery of milestones and project progress reports. Expenditure will be monitored through quarterly financial reports which will be scrutinised by the DFID team to ensure value for money principles are being met. / The current advice from SMART rules requires that payments must not be made in advance of need. However, the rule does allow the SRO to make a judgement in the case where advance payment may be required by NGO partners and contractors, however this will only be done where there is adequate written justification from partners and approvals by DFID. / DFID will require the IPs to submit annual audited accounts for the specific programme funds they disburse during the programme life-time and this will provide independent assurance that funds are disbursed correctly. This will be supplemented by more rigorous forensic audits, if required, to track the flow of funds in Somalia in line with UK Anti-Terrorist financing legislation. DFID will also carry out regular spot checks. / The IPs will keep a list of all assets (defined as being of value above £1000 and have a useful life of more than 1 year) procured under this project. The assets will be disposed of in line with the respective administrative arrangements.
Other / Given the desire for an adaptive and responsive delivery approach, we will seek to set up financial management arrangements which allow for flexibility in programming, leaving open the possibility of shifting resources over time between components and sub components if required.

# Management Case

Management arrangements for implementing the intervention

Given the desire to increase government oversight of health programming, we will work through the official Health Sector Coordination and Health Advisory Board, to keep Ministers, their officials and other sector stakeholders informed and involved, sharing updates and lessons learned for wider sector use. To promote an adaptive and responsive delivery approach, we will seek to set up management arrangements which allows for flexibility in programming. The governance and management arrangements, to oversee this, are presented below:

Component 1
Component 1a. will be managed by UNICEF, by an already established programme (JHNP) for which UNICEF is the Management Agent (MA).
  1. DFID Somalia will manage an MoU with UNICEF with clearly defined terms of reference and the Joint Coordination Unit (JCU) will report quarterly to DFID Somalia on financial spend, results and programme performance. The JCU will report to the regional health authorities on performance and results on an annual basis and will be overseen by the existing JHNP Technical Coordination Group and Steering Committee.
  2. For EPHS delivery UNICEF is responsible for managing the financial, results and risks of all contracts to NGOs using their Project Contract Agreement (PCA) contracting process. All implementing partners are identified in conjunction with the regional health authority following a micro assessment.
  3. For any HSS activities. WHO and UNFPA are contracted by UNICEF, which is the primary grantee of DFID.

Component 1b. The management arrangements for Phase2 of EPHS will be set in 2016. The reporting arrangements for the MA will be based on agreed terms of reference and procedures. The MA is expected to establish and maintain good working relationships with both Government and donor partners (if this becomes a multi-donor initiative) and performance in this area will be continually assessed through stakeholder feedback.

Component 1c. will be managed by a consortium of NGOs with a lead agency as the MA. The MA will have a zonal level Coordinator and be embedded within the regional health authorities and together will govern the implementation of EPHS delivery. The MA will work with the regional health authorities and DFID Somalia to develop annual workplans, conduct assessments of possible implementing partners, conduct contracting of implementing partners, conduct financial management of the funds, ensure timely reporting of results, ensure technical input from relevant government focal points and conduct risk management. DFID Somalia will oversee and manage the accountable grant for the MA.

DFID Somalia, the MA and the three MoHs will sit on a bi-annual Technical Working Group. Quarterly review meetings will take place between DFID S and the Management Agent and Regional Health Offices to develop workplans and monitor progress against logframe objectives.

This model will become the long-term governance model covering the supply side - component 1, for the delivery of EPHS.

Table 15: Governance and Management arrangements for service delivery Component

 Technical working group
MA/MoHs/DFID S

DFID S

Management Agent

Zonal Coordinator
Zonal Coordinator
Zonal Coordinator

RHO
RHO
RHO
RHO
RHO
RHO

DFID Somalia will directly manage an accountable grant for Demand Creation, component 2. The MA for this work will report directly to the DFID Somalia team and be responsible for overall contract management, performance oversight, contracting and management of all sub implementing partners. DFID Somalia, the lead agency and implementing partners will meet quarterly to discuss progress against milestones.

The MA for the Demand Creation will need to work closely with the MAs for EPHS delivery to ensure complementarity of services in the common geographical regions. Close collaboration will be sought with regional health authorities to strengthen the linkages and monitoring of supply and demand components. The MA for Demand Creation and the regional health authorities will meet on a biannual basis to share lessons, information and technical linkages between the two components through the Health Sector Committee and Health Advisory Board (sector coordination mechanism).

Component 3 will be managed directly by DFID Somalia and will be output based contracts.

Staffing

Overall responsibility for the programme falls within the DFID Somalia Economic and Human Development Team. The Senior Responsible Officer will be the Human Development Lead and will be responsible for overall technical delivery and management of the entire programme, including the management of key risks. The programme will be managed by DFID Somalia’s Human Development team, which consists of 1 x HCS A2 Health Adviser (100%), 1 x SAIC A2L Health Adviser (100%), 1 x B1 Programme Manager (100%) and 1 x B2 Programme Officer (100%). We also expect some input from the cross-cutting adviser on Gender (40%).

Partnership Principles

DFID Somalia monitors Partnership Principles both with the Federal Government of Somalia and the Government of Somaliland, with both assessments recently updated in July 2015. As FGS has only been established since August 2012, there is a limited track record from which to draw conclusions. Somaliland has been independent since 1991, but the country’s disputed status limits the data available from international indices.

We have considered the partnership principles and support these. However, we will not be applying the partnership principles for direct management of the programme as funding will not be direct to government in the form of Financial Aid. This programme envisages only small amounts of (highly conditional and closely monitored) amounts of grant funding through the Management Agents to public authorities in Somalia. As a result, assessment of the principles is relevant but will not be explicitly built into programme implementation as a benchmark.

Managing risks

The overall programme risk rating is medium. The risk matrix will be further developed as part of the development of the programme but at this stage the analysis of risks and the possible mitigation actions outlined in Annex 5, Table 5A. The findings of this analysis are that in a fragile state like Somalia, then conflict, political and fiduciary risks are significant. Care must be taken to ensure programmes can respond to changing circumstances and risks whilst protecting ‘do no harm’ principles that prevent further conflict from arising due to programmatic decisions. As the majority of services including commodities and supplies, are provided by NGOs, it is imperative that adequate due diligence takes place and systems are in place to monitor delivery. Management of the broader, non-fiduciary/financial risks are outlined in a detailed risk matrix that covers four broad areas including: governance and political risks, operational risks and conflict and ‘do no harm’ risks. The matrix will be reviewed and updated every six months.

Monitoring and Evaluation

During the preparation for this new business case, we will review existing collaboration with the Somalia Monitoring Program (SMP) and future work planned. We will also seek to understand the opportunities for greater use of mobile cash and mobile technology and will seek to learn lessons from humanitarian M&E component (Transtec). The Somali Health and Nutrition Programme will be overseen by a monitoring and evaluation plan, which is outlined in draft below. A draft master logframe has also been developed covering all components of the programme (Annex 7).

Monitoring

For the EPHS service delivery component, the TWG will set and agree the annual workplan and progress against the workplan will be monitored quarterly by DFID S and the managing agent. It is expected that an EPHS roll out strategy will be developed at the start of this programme. This will set clear standards for the quality, scope and coverage of EPHS, especially on the 1-5 core services and the management functions. These will be used in the comparison of the two approaches to delivery and will form the basis of the monitoring efforts.

Monitoring activities will include feedback from beneficiaries and community health committees. Supportive supervision will be undertaken with the health authorities which will feed into the reporting mechanism to assess whether standards are being met. The programme will work with the authorities to support the strengthening of national monitoring systems such as the HMIS to ensure outcome level data is accurately measured.

For the Demand Creation component, DFID S and the lead agency will agree the annual workplan and progress against the workplan will be monitored quarterly by DFID S and the lead agency. Monitoring activities will include feedback from beneficiaries and community health committees.

All implementing partners will provide routine data in standardised reporting formats on a quarterly basis which will be analysed to generate conclusions and recommendations aimed at adjusting and improving the interventions. Data will also be used to triangulate national HMIS reported data.

Independent verifications

Due to the insecure and inaccessible areas of the programme, DFID S will work with an independent third-party verification organisation who will conduct quarterly verifications of activities against a pre-agreed schedule and strategy. Under the current programme, over 50 independent verifications have been conducted with varying results ranging from well performing to needing attention. Most verifications have indicated a consistent and reliable delivery of services by our partners. The verification exercise has also pointed out areas where partners were not delivering as per the agreed standards, where there have been gaps in service delivery, supplies stock-outs and lack of trained personnel within health facilities. This verification exercise has proved very helpful especially as DFID staff are not able to conduct monitoring visits or spot checks in many of our project sites. For the new BC, there will be need for further exploration of the options for a coherent and well-structured third-party monitoring and verification exercise of project activities.

Operational Research and Evaluation

As outlined in the strategic case there are significant gaps in the evidence base. The programme will invest in conducting operational research and will employ a robust evaluation approach, particularly for phase one of service delivery. The overall purpose of the evaluations conducted should be to identify the feasible, accessible, acceptable and cost-effective interventions for delivery of services. It should avoid supporting interventions that are ineffective of harmful to health (and peace and stability). To maximise learning the evaluations will need to explore how local contextual factors influence the feasibility of delivery. It will identify factors to take into account to improve replication in new settings.

Depending on the evaluation question, different methods may be used. These are:
- Formative – to assess new interventions to explore how an intervention can be refined to be feasible and acceptable
- Process – to assess both how and whether the process of implementing is feasible, reached those intended, is accessible and effective.
- Outcome – to assess whether interventions have achieved the intended results for the recipients (ideally this should involve a comparison group).

Both quantitative and qualitative data will be collected, to assess factors such as the extent of delivery and coverage of targets groups and level of satisfaction (quantitative) and to build a picture of what went well, what provision mechanism works, how to improve how services are provided and participation and incorporating the views of beneficiaries (qualitative). The demand side interventions are likely to include a wider range of qualitative methods, to solicit and explore views and understand behaviours of the vulnerable populations that it aims to target.

Beneficiary feedback mechanisms

DFID S will support independent beneficiary feedback, which will be carried out annually. All implementing partners will be expected to carry out a form of beneficiary feedback and show an accountability route to resolve issues arising from the programme’s implementation.

Other Research and Studies

Through call down frameworks, DFID S will contract out other research and studies. Specific research requirements will be determined following the assessment of proposals received for each component but could include further cost evaluation research, the role of demand creation activities on gender equality, impact of demand creation activities on changing social norms. Mini tenders will be held through call down frameworks on evaluation and health.

The evidence generated from the research will be used to feedback into the programme and the wider health sector to adapt and alter the programme’s indicators and methodologies as needed.

Surveys

Working with suitable partners, DFID S will consider supporting relevant surveys such as Demographic and Household Surveys, maternal mortality surveys, private sector surveys and other surveys to effectively measure trends and results both for the sector and for the programme.

Management of M&E

Overall the total costs allocated for M&E is £3m which is a rough calculation based on 3% of the total budget. The exact allocations will need to be worked out at the start of the programme.

Management of the M&E component will be direct by DFID. Similar with the other Components, there will be a need for an annual work plan, with an outline of the M&E priorities and what will be funded each year. The fund managers for components 1, 2 and 3 may also make recommendations on M&E work that is needed but lies outside their scope of work. Ultimately decisions on what to fund will be at discretion of SRO, but this will be done in close collaboration with the DFID Somalia Accountability and Results Team to ensure close links with other programmes and also to give a more independent input on the quality of this work.

# ANNEX 1. DFID Health Results and Spend (2010-2016)

The Joint Health and Nutrition Programme (JHNP)

The JHNP is a pooled donor funded programme which has USD123m in committed funds from donors for 2011-16. To date USD 100m has been disbursed, the bulk of which has been from DFID (£38m, 60%) followed by Sweden, Finland, Switzerland and US. JHNP is managed by the UN and implemented through three UN agencies; UNICEF, UNFPA and WHO and priorities are set with health authorities according to their Health Sector Strategic Plans.

The comparative advantage of the JHNP is the joint working with the Somali Health Authorities, in support of the New Deal principles to strengthen MoH stewardship and oversight of the health sector and build a more coordinated and systems-based response to health needs. In 2012 the initial donor commitments to JHNP were USD 34m (DFID, USAID, Ausaid). Total donor commitment to JHNP is now USD 130m, four times the original commitments. Funding from Sweden tripled, plus new funds were secured from Finland and Switzerland. The joined up working and funding arrangement of JHNP provided a vehicle for other donors to invest in the sector. This is supported by evidence that health strengthening approaches and pooled sector support modalities deliver positive benefits in terms of efficiency and sustainability arising from alignment with the government policies and programmes, and ownership by the host country government.

The comparative advantage of the UN management is that it has a well-established presence across Somalia, with many years’ experience of managing Humanitarian Aid with staff, offices, and security measures in place to operate in what is a very fragile and highly insecure environment. The UN also has the international procurement capacity to buy at bulk at discounted rates and has established the in-country distribution and quality assurance mechanism for getting drugs and supplies to facilities. Lastly the UN also has the fiduciary systems to operate where risks of fraud and corruption are particularly high, with the financial and management systems to allow programmes to expand and go to scale.

JHNP achievements include setting in place the Somali policy and strategic framework on health (including developing the first health sector strategies and policy, updating the essential drugs list, supporting the development of the community health strategy and nutrition plans) - essentially defining the health needs and establishing the Somali Health priorities to inform planning and to help mobilise resources. JHNP has supported government oversight of the heath sector through strengthening Somali Health Sector Coordination and formation of zonal coordination and health management information systems. It has improved coordination and joint planning between government, donors and implementing partners. Additional achievements on Human Resources are the development of curriculum and training of midwives and health workers, plus support to establish a regulatory framework for health workers accreditation. Since late 2013 JHNP began support to governments priority ‘flagship’ programme to deliver EPHS services in 7 (out of 9 planned) regions of Somalia, bringing routine health services to new areas, including the provision of medicines and supplies.

Key lessons from JHNP to note are:
- The ‘Pooled’ fund. Establishing a new pooled fund mechanism in Somalia took over 1 year to get the governance and operational arrangements fully functioning. The benefit of the pool fund has been that between 2012-14 donor funding commitments to JHNP quadrupled.
- EPHS contracting. JHNP support to the EPHS service delivery component started in late 2013, as the first ‘government led’ programme to bring routine services to populations in areas that have historically never seen or received government services. Delays were experienced due to the time taken to set up joint MoH/UN contracting arrangements combined with multiple political changes and periods of increased insecurity. Experience is that it takes one year to go through the 7 step Joint UN/MoH selection and contracting process for NGOs. The first contracts were issued in October 2013 covering 4 districts in Puntland. From June 2014 onwards a second wave of around 15 contracts were issued for districts in Puntland and South Central and more in November 2014 for Somaliland. By June 2015 services were being rolled through 40+ contracts in 41 districts. Service delivery results are now beginning to increase, based on 6-18 months delivery. Delays in roll out to the two remaining regions in 2014 relate to insecurity and uncertainty over implementation modalities in two politically disputed regions of Sanaag and Lower Juba (Map 1). The contracted NGOs take high risks, operating in extremely difficult, insecure environments.

Health Consortium for the Somali People (HCS)

The HCS is a DFID funded (£45m) programme delivering EPHS through a consortium of five international NGOs. The programme has a flexible response, uses innovative approaches and a variety different delivery routes to assess intervention effectiveness and share lessons learnt for the wider health sector. Demand side activities have been supported.

The comparative advantage of HCS is its flexible response to changing contexts and its ability to rapidly respond to new needs. Governance arrangements are light, with PSI fulfilling the function of consortium lead and financial manager. HCS has been able to trial and test innovative approaches, including working with the private sector pharmacies on social marketing. HCS has developed a variety of interventions using different delivery routes and has shared lessons learnt for the wider health sector. Both supply and demand side activities have been supported. The strength of this programme has been its ability to be flexible and respond to changing and emerging security and political situations. HCS has been successful at piloting activities which have been adopted by JHNP or the wider health sector.

Key lessons from HCS to note are:
- Strong MOH ownership, leadership and supervision of EPHS roll-out is essential. Functioning Regional Health Boards and their district equivalents are vital. In HCS target regions, District Health Boards have played an indispensable role in negotiating access and advising the international partners on security, as well as in overseeing effective delivery of the HCS EPHS programme.
- Effective delivery is impossible without adequate supplies. Partners have had to create regional supply chains and purchase the bulk of the medicines and supplies. HCS has had to work hard to overcome recurrent breaks in vaccine supply.
- Community ownership via District Health Boards and Community Health Committees is vital for effective sustainable gains. There is much potential for diversified co-funding of health services. Communities should be empowered to identify and use these resources. Facility ownership by communities and local authorities should be encouraged with links to regional and state MOHs structures

DFID Health Results to date
Table 1A: Health Programme Finance Summary 2010-2016
	2010/11	2011/12	2012/13	2013/14	2014/15	2015/16	Total
HCS	£1,662,876	£6,474,921	£6,809,206	£11,143,160	£10,025,000	£9,477,718	£45,592,881
JHNP		£1,487,000	£11,523,157	£9,660,000	£16,290,000		£38,960,157
Total	£1,662,876	£7,961,921	£18,332,363	£20,803,160	£26,315,000	£9,477,718	£84,553,038

Table 1B: Cumulative Results broken down by programme 2011-March 2015
			HCS	JHNP	Achieved (2011 - 16)
OP headline results	Numbers of modern birth spacing methods distributed		112,521		112,521
	Number of births attended by a skilled birth attendant		25,505	21,700	47,205
Sector Level Results	Number of children in receipt of nutrition services (potential DRF)		444,539	720,360	1,164,899
	Number of people using quality health services		1,706,671	1,045,235	1,857,826
	Numbers of children receiving DPT3 immunizations		59,121	77,323	136,444
	Pregnant women receiving ANC 2+ - L		81,367	94,647	176,014

# ANNEX 2. Strategic Case Tables

Table 2A: Health Care Facilities

The Total Facilities- South central
Hospital	Referral Health Centres	MCH/HC	PHU
13	75	151	244

Total Facilities- Puntland
Hospital	Referral Health Centres	MCH/HC	PHU
5	2	88	169

Total Facilities- Somaliland
Hospital	Referral Health Centres	MCH/HC	PHU
15	9	93	166

# ANNEX 3. Economic Appraisal, plus Tables

Economic Appraisal of EPHS delivery to date

To date, there has been no systematic review of the economy, efficiency and effectiveness of EPHS in Somalia or comparison of the different EPHS delivery mechanisms to assess VfM. For the purpose of this Appraisal Case, a rough and rapid review of EPHS delivery via HCS and JHNP is carried out below. Bearing in mind that JHNP and HCS have different scopes of work and different comparative advantages for EPHS delivery, it is still judged possible to begin to make some comparisons using five variables. These are (i) the EPHS coverage, (ii) the breadth of EPHS, (iii) duration of services, (iv) management and delivery costs and (v) results to date. For each variable we highlight where it is possible to make comparisons and where it is not. A summary table is provided below to outline the different VfM variables.

Table 3a: Summary comparison of HCS and JHNP on VfM and results
Variable	HCS (Mar 2010-Mar 2015) £ 45.5m	JHNP (July 2012-Dec2014) £ 39.8m
USD for EPHS in 2014	5m USD allocated to EPHS in 2014 (approx.)	12.6m USD allocated to EPHS in 2014 (approx.)
# Districts covered by EPHS	10 Districts* / Puntland:- Karkaar (5) / Somaliland:- Sahil (2) / South Central:- Gedo (3)	41 districts* / Somaliland (9) Togdheer, Awdal and Sanaag / Puntland (15) Bari, Nugal and Mudug / SC Somalia (17) Galgadug, Benadir (+lower juba)
Pop covered	546,000 – Catchment population	4,200,000 – Population reached (pooled fund)
Duration of EPHS	EPHS contracting started in 2010, with implementation from 2011. / EPHS implementation for 4+ years in 3 regions	EPHS contracting started in 2013, with implementation from 2014 / EPHS implementation between 6-18 months in 7 regions and 2 regions yet to start
Breadth of EPHS services	Core services 1-5 / Partial integration of nutrition / Full integration of FP	Core services 1-4 / Partial integration of nutrition / Partial integration of FP
Management and contract arrangements	Accountable Grant, implemented by a consortium of 5 international NGOs, led by PSI. / 3 NGO partners are contracted (by PSI) for EPHS delivery areas.	Pooled Fund with MoH oversight – for HSS and EPHS, implemented by UNICEF, UNFPA and UNFPA / Over 40 contracts are issued by UNICEF to over 20 NGOs (using PCAs) for EPHS delivery areas
Agreed VFM indicators	Cost of birth attended by SBA / Cost per pregnant mother receiving ANC3+ / Cost per OP visit	Cost of procurement of medicines, commodities and supplies / Cost of EPHS implementation and monitoring / Cost of CEmOC services in hospitals / Costs of medical kits for Primary Health Units and Health Centres
Unit cost data EPHS and specific services	EPHS package per capita USD 5.88 ** / (based on actual expenditure and catchment population)	EPHS per beneficiary per year is approx USD 11.66 ** / (estimates based on budgets and pop reached)
Admin fees as % overall prog	Direct costs – 19%	Direct costs 21%
EPHS Results achieved in 1 year	HCS (April 2014-March 2015) / 34,603 modern birth spacing methods distributed / 9,825 births attended by a skilled birth attendant / 104,483 children in receipt of nutrition services / 399,074 people using quality health services / 19,342 children receiving DPT3 immunizations / 17,174 Pregnant women receiving ANC 2+	JHNP (Jan-Dec 2014) / 11,710 births attended by a skilled birth attendant / 33,836 children in receipt of nutrition services / 892,080 people using quality health services / 25,949 children receiving DPT3 immunizations / 40,970 Pregnant women receiving ANC 2+
Uptake of services / Service Delivery Results achieved over the life of the programme	HCS (July 2010-March 2015) / 112,521 modern birth spacing methods distributed / 25,505 births attended by a skilled birth attendant / 444,539 children in receipt of nutrition services / 1,706,671 people using quality health services / 59,121 children receiving DPT3 immunizations / 81,367 Pregnant women receiving ANC 2+	JHNP (2012-Dec 2014) / 28,589 births attended by a skilled birth attendant / 743,457 children in receipt of nutrition services / 1,045,235 people using quality health services / 100,549 children receiving DPT3 immunizations / 94,649 women Pregnant women receiving ANC 2+

*Delivery in districts of SC is more complex, insecure and higher costs ** We urge caution from drawing any rapid comparisons from this cost data given different methodologies used, plus differences in duration of EPHS services and implementation contexts

Coverage of EPHS services.

The geographical coverage of EPHS, supported through JHNP and HCS in 2014 is shown in Map 2 below. It is estimated that 3 million people are reached by DFID support through these two programmes[97]. In early 2015 a new population estimate was released for Somalia, increasing the total population by 30% from 9m to 12m people. Work is still ongoing to calculate the new populations by districts and regions (some of which borders are still disputed), which will have a significant impact on service coverage data. To date HCS has used more precise figures of catchment populations based on populations covered by their health facilities and community outreach efforts, not total district populations (0.5 million). In contrast JHNP has used estimated populations in the 9 implementation regions as the population ‘reached’ (4.2 million). Until there is official district level population data and common measurements for coverage, any comparison of populations covered by services should be interpreted with caution[98]. For future EPHS contracts it is recommended to have a clear definition of catchment population and to compare results pro-rata based on population size.
[97] It should be noted that JHNP 2014 coverage estimates are 4.2 million, achieved through a pooled fund to which DFID is one of the donors (60% funds). Rough estimate would be 2.5m covered by DFID through JHNP, plus 0.5m through HCS.
[98] The rough comparison by QAU of the budget allocation for EPHS delivery made by the two mechanisms per capita per year showed that allocated amounts per population are similar i.e. $3.33 for HCS versus $3.00 for JHNP. However QAU’s calculation is based on a population figure of 1.5 million for HCS (rather than 0.5m target population) and the JHNP population estimate of (4.2 million).

There are 10 districts, supported with EPHS services through HCS and a further 41 districts where services are supported by JHNP. It should be noted that delivery is far more complex (and costly) in districts of South Central Somalia where insecurity is a major constraint. JHNP covers 17 districts in SC while HCS covers 3.

Map 2: Map of EPHS coverage areas with JHNP (coloured in blue) and HCS (written in red).

Sahil HCS
Karkar (HCS)
Gedo (HCS)

Breadth of EPHS package delivered.

The aim of EPHS strategy is to promote the implementation of a standard EPHS package. The package entails 10 essential health services, including 6 core services and 4 additional services. There are also 6 management and support services. These are outlined in table 5 below.

To date JHNP’s support to EPHS has focused on the first 4 core services[99]. Further work is necessary to fully integrate birth spacing interventions and Emergency Obstetric and Neonatal Care (EmONC) services into the JHNP EPHS [100]. In comparison HCS support to EPHS has focused on the first 5 services and has been more systematic at integrating these services. Under HCS, the full 10 EPHS services are also being piloted in one region (to include dental and mental care). As the EPHS is being rolled out it is important to monitor what services are contained within the package.
[99] JHNP 2014 Annual Review
[100] The reasons for this is birth spacing activities and EmONC have not been supported by UNICEF PCAs with NGOs as this responsibility rests with UNFPA, (set out in UN division of labour). UNFPA has recently begun to provide the birth spacing commodities and training but integration is just starting

     Table 3b: EPHS Package showing 6 Core and 6 Support services
EPHS Core Services for Somalia
1. Maternal, reproductive and neonatal health.
2. Child health.
3. Communicable disease surveillance and control, including WATSAN promotion
4. First aid and care of critically injured.
5. Treatment of common illnesses.
6. HIV, STIs and TB.
EPHS Management and Support Services
Finance
2. Human resource management
3. Coordination and supervision
4. Community participation
5. Health system support components
6. Health management information system

A recent Nutrition Integration study showed that nutrition services are not yet systematically integrated into EPHS core services (1-3) as set out in the EPHS strategy [101].Nutrition integration should include a range of promotion of child feeding practices, plus the provision of micronutrients and therapeutic feeding for malnutrition[102]. The challenge is that nutrition services have historically relied on humanitarian aid with a heavy focus on emergency treatment services provided outside of the health sector, with little coordination with government.
[101] MQSUN Draft review of Nutrition Integration in Somalia (May 2015)
[102] Nutrition services: promotion activities for breastfeeding, complimentary feeding, and improved hygiene, as well as provision of micronutrients (Vit A, Zinc, Iron and deworming tablets), plus promotion of therapeutic feeding for malnutrition

Lastly, EPHS delivery to date has not included explicit support to the EPHS ‘management and support services’ which include the supervision of EPHS that is critical to improve standardisation of services. The need for more support to a management services approach, was identified by a review of the EPHS (in HCS areas) which showed that ‘delivery of a set package of health services, combined with support to facility infrastructure, staff training, equipment and resources, led to real gains in maternal and child health indicators’[103].
[103] Review of EPHS implementation in Sahil Region of Somaliland, Kaarkar region of Puntland and Gedo Region of South Central Somalia. N Pearson, S Khan Nov 2013

(iii) Duration of EPHS services.

Delivery of health services using the EPHS package was identified as a health policy priority in 2009 and reinforced in the health sector strategic plans developed in 2013. However it was not until 2010-11 through HCS that EPHS began to be piloted in three regions, with an implementation period of over 4 years. Support to routine EPHS service delivery through JHNP started in late 2013 and in 2014 with a variation of implementation periods between 6-18 months in 7 regions, with implementation in 2 regions starting towards the end of 2015. Increased delivery efficiency gains are expected over time, but also require continued peace and security. While HCS has had 4 years of service delivery, JHNP is essentially still in the start up phase of service delivery.

(iv) Costs of management and service delivery.

There are two parts to this review of costs. The first looks at the management and implementation costs. The second looks at the unit costs of EPHS.

To assess the management and implementation costs, we compare what the UN and NGOs actually charge for both direct support and indirect support costs in Somalia. The direct support costs are on activities delivered directly by the management agent. These are 21% for JHNP and 19% for HCS. However for the full picture, we also need to add in the indirect costs charged on funds that pass through their HQ, or charges on funds passed on or made by sub-implementers. The findings show there is little difference in the indirect costs, while there is a 2% variation in direct support costs.

Table 3c: Estimated proportion of management and implementation costs for each Option
Costs	JHNP	HCS
Indirect costs	15%	15%
Direct support costs (‘management fees)	21%	19%

It should be noted that the management and implementation fees apply to the whole programme not just the EPHS component. Bear in mind also that PSI manages 3 EPHS contracts with 3 NGOs, while UNICEF manages 40+ EPHS contracts with 20+ NGOs, with the largest number of contracts in SC.

Work started in 2014 to begin to calculate the unit costs of EPHS delivery. Below is some preliminary data from HCS and JHNP.
  1. HCS - During 2014, DFIDS carried out a review to assess the cost of delivery of EPHS (Blaackman 2014[104]). The review showed that it is possible to deliver a package of essential services in Somalia at a reasonable cost at USD 5.88 per person (with variations between US$ 5.30 in SL; US$ 6.85 in PL; and US$ 5.51 in SC) [105].
    [104] Blaakman, Cost Analysis for EPHS in Somalia, 2014. HEART. This study used cost data from HCS implementing partners
    [105] US$ 5.30 in the Sahil region (by HPA); US$ 6.85 in Kakaar region (by SCI); and US$ 5.51 in Gedo region (by Trocaire).
  2. JHNP, in their 2014 report, has calculated the unit costs of EPHS at USD 11.66 per potential beneficiary, based the budget for EPHS contracts issued and populations to be covered/reached[106]. It found variations between US$ 5.54 in SL to US$ 18.67 in CS (JHNP 2014 report). Of this supplies cost USD 2.87.
    [106] Using contract data only does not include UN management fees.

What is positive is that the above preliminary EPHS unit costs from HCS (which uses a more robust methodology) are comparable to similar fragile countries of Afghanistan (USD 5.50) as well as DRC, South Sudan, and even Ethiopia, Kenya, and Rwanda (which range between USD 5-12.). The findings on costs of specific services such as Antenatal Care (ANC), or treatment of diarrhoea, pneumonia and immunisation are also comparable (Table 3d).

Given the information presented above, there are difficulties in comparing unit costs between HCS and JHNP as they do use different costing methods, they deliver different breadth of services in different locations and use different definitions of catchment populations. In a workshop with JHNP and HCS EPHS implementing partners held in August 2015, it was recognised that further work is necessary to take into account the main cost drivers (security, personnel and supplies[107]), as well to introduce a consistent measure for comparing indirect costs[108]. A consistant costing methodology is necessary, plus a more regular assessment of unit costs. Both are recommended in 2015/16, to guide future programming
[107] A decision needs to me made whether therapeutic feeding, should be costed as part of the EPHS package
[108] We disagree with the statement by QAU that delivery of EPHS via JHNP is double the cost of operating through an alternative partner as this is based on incomplete data (QAU Minute 21st Aug 15, bullet 10).

Results from EPHS

The specific EPHS service delivery results for JHNP and HCS are highlighted above in table 3a. The results comparing uptake of service delivery achieved from the start of HCS and JHNP show that HCS has achieved the largest cumulative numbers to date (linked to duration of implementation). It is anticipated that once the bulk of JHNP EPHS contracts have completed their first year of implementation service delivery results will rapidly increase[109].
[109] For JHNP it should be recognised that EPHS results is just one of the 6 outputs which the programme is delivering on alongside other HSS efforts.

Table 3d: Cost comparisons of health service delivery in Somalia and elsewhere. Source: Blaackman 2014

a: Average Annual Health Service Package Per Capita (2012)	b: Unit cost per ANC visit (2013)

c: Unit cost per Normal Delivery (2013)	d: Unit cost per treatment (2013)

Table 3e: Scoring of Evidence Ratings for the different Options

Option	Evidence rating	Justification for evidence rating
2 UN	Limited	We have actual implementation experience of JHNP (UN delivery) but little information on VfM or unit costs.
3 Mix	Medium	We have implementation experience of JHNP (UN delivery) and HCS (Consortium delivery) with annual appraisals. HCS VfM data is strong with data on unit costs, but not comparable with JHNP. / We have no information on EPHS delivery by a Private MA
4 / Status Quo	Medium	As the status quo option we have actual implementation experience, annual appraisals and other pieces of research.

Table 3f: Assumed Proportional Allocation of Programme Funds for Service Delivery[110]
[110] To calculate Option 3, we have applied two indicative cost scenarios to the service provision component. 3.a is a UN managed and NGO implemented arrangement with certain fees. 3.b is a Private Management Agent and NGO implemented arrangement with different fees.

		Option 2	Option 3 a		Option 3b	Option 4
Expenditure Split		UN 100%	UN 50%	NGO 50%	Private MA 100%, plus NGO impl	UN 50%	NGO 50%
Component 1b: Supply Side	Yrs 1-2	80.0%	40.0%	40.0%	80.0%	50.0%	37.1%
	Yrs 3-5	80.0%	40.0%
Component 1c: EPHS embeded	Yrs 1-2	26.0%	13.0%	13.0%	26.0%	0.0%	0.0%
	Yrs 3-5	26.0%	13.0%
Component 2: Demand Side	Yrs 1-2	17.0%	8.5%	17.0%	17.0%	0.0%	12.9%
	Yrs 3-5	17.0%	8.5%
Component 3: DFID M&E	Yrs 1-5	3.0%	1.5%	1.5%	3.0%	1.5%	1.5%

Table 3h. RESULTS BID - Service Delivery Indicators

	HCS results with £45.5m			Actual Results	Results Bid with £92m
	2011	2015	Total increase	Av increase per yr	1 Yr results	1Yr + Efficiency	TOTAL 5Yr Results + Efficiency gains
DPT3	10,918	59,121	48,203	12,050	24,100	24,944	123,031
ANC2+	2,038	81,367	79,329	19,832	39,664	41,052	202,485
SBA	872	25,505	24,633	6,158	12,316	12,747	62,873
Nutrition for Child U5	12,122	444,539	432,417	108,104	216,208	223,775	1,103,742
No of FP products	5,823	112,521	106,698	26,674	53,348	55,215	272,342

Methodology: This is a realistic results bid, based on actual results achieved through HCS with £45.5m between 2011-2015.

# ANNEX 4. Commercial Case Tables

Table 4A: Phase 1 and 2 Procurement

	Delivery Channel	Direct/ Indirect Procurement	Procurement method
Component 1a. EPHS 2016	UN	Indirect	MoU with the UNICEF
Component 1b. / EPHS 2017-21 Decided May 2016	UN / Private / NGO	Indirect	MoU / Contract / AG
Component 1c. Embeded EPHS	NGO Consortium	Indirect	AG and MoU between NGOs and lead NGO
Component 2 / Demand Creation	NGO Consortium	Indirect	AG and MoU between NGOs and lead NGO
Component 3 / M&E	DFID	Direct	Contract and DFID Framework

# ANNEX 5. Management Case Tables

Table 5A: Risk Assessment

Key risks	Probability	Impact	Mitigation Actions
Political and Conflict Risks
Civil unrest and violence spreads and causes instability in Federal Government of Somalia (FGS), Puntland and Somaliland.	Medium	High	The security gains of the past several years are real but remain incomplete and reversible. Much of Federal Government of Somalia still remains volatile. / Interventions have been designed carefully and are targeting more stable or post-conflict regions and could be redesigned if necessary to take account of new security evidence and developments / The programme will use strategic decisions based on security and conflict updates, the authorities are aware of the risk and are establishing policy frameworks help in the stabilization process / Avoid any risk of harm to partners. Activities may be changed, scaled down or reduced in instances where the risk assessment suggests such recourse. A difference approach will be used for the more inaccessible areas.
Elections in 2016 may disrupt and delay implementation due to diversion of political attention particularly in Somaliland and FGS.	High	High	The programme will work with various parts of government and will aim to maintain a focus on the provision of services to all as this is a unifying factor, and not get drawn in, on the politics. / In the case of a change in government, the impact of the political shift will be mitigated through active management by DFID Somalia to ensure the programme stays on track
Programme interventions exacerbate conflict	Low	High	All implementing partners will adopt a ‘do no harm’ approach. This will include careful selection of intervention activities and sites based on local-level conflict analysis, clear targeting of beneficiaries, as well as continual monitoring of the conflict context. If there is a risk of exacerbating conflict, a decision could be taken to withdraw.
Programme Governance and Fiduciary Risks
Failure by the Implementing partners to or their sub-contractors to spend funds for planned purpose	Medium	High	Funding is conditional on tight financial management procedures, frequent audits, due diligence reviews, robust financial reporting systems, and third party monitoring of results. / The lead agency will be responsible for managing all sub-contracts with other partners and monitoring financial flow and reporting closely.
Significant instances of fraud and corruption may undermine donor confidence especially with sub-contractors or in the use of Government systems	High	High	DFID’s Anti-corruption policy will apply to all organisations involved in the implementation of this programme / DFID will conduct due diligence on Implementing partners and in the case where the partners works with government, a Standard Operating Procedure will be developed at the inception phase to govern the process, and will take into consideration the UN Harmonized Approach to Cash Transfers (HACT) framework
Evaluation is insufficient or lack of conclusive evidence of effectiveness of interventions			Sufficient funding and expertise to support high quality evaluations. Establish baseline with existing data sources and build capacity of government to improve and strengthen data management.
Duplication or overlap of other DFID funded programmes (eg global fund)			Ensure frequent communication with other DFID funded programmes such as humanitarian and global funded programmes. Ensure participation within health sector coordination forums.
Low commercial interest in managing the interventions			Carry out early market engagement discussions with potential partners to discuss technical and operational expectations. Offer performance-based incentives.
Project Implementation Risks
Impact not sustained beyond the programme lifetime	High	High	If programme does not get adequate funding support from donors, government may not be able to sustain the impact beyond donor funding / The programme will work with government to increase resource allocation to the sector and strengthen the Public Financial Management (PFM) system
Programme exacerbates conflict/instability through inequitable delivery of services or the nature of the interventions (e.g. family planning)	Medium	Medium	Targeting of intended beneficiaries will be done through a participatory community approach and interventions will reflect both the national and community needs
Climate and Environmental Risks
Drought causes crisis and diversion of funds from routine to emergency healthcare provision	Medium	High	The DFID health team will work with the DFID humanitarian team to monitor any potential crises and support implementing partners to access Common Humanitarian Funds and the Internal Risk Financing mechanism set up for this purpose.
Energy costs are prohibitive and hinder provision of service delivery.	High	High	The programme will further explore innovative ways to support alternative energy supplies to health facilities.

# ANNEX 6. Consultations Conducted

In January 2015, the Human Development team conducted wide consultations with stakeholders in Nairobi, Somaliland and Puntland. The representatives were drawn from the wide range of stakeholders including Ministry of Health officials from the three regions, the UN agencies, INGOs, National NGOs, professional associations, universities, private sector practitioners and beneficiaries.

The DFID team met with all three Ministers of Health, to explain the BC process, to discuss their proprieties and seek inputs. This included the new Minister of Health for the Federal Government, plus the existing Ministers in Somaliland and Puntland.

The stakeholder consultations were structured to respond to what has worked well in the existing programmes and what has not and identification of the barriers to access of health services in Somalia. The team also sought to understand what the future priorities on health were for the Ministries of Health. To achieve this objective, the team held meetings with the ministry of health officials, and a 1-day workshop in both Hargeisa and Puntland with the UN and NGOs representative and other stakeholders including the private sector. Issues emerging from these consultations have formed a basis of the business case designed to respond to needs of the Somali people.

DFID also contracted several analytical reviews aimed at learning lessons from the existing programme, informing the Health Sector policy environment and majorly to inform the design the new programme. The reviews included the EPHS Costing Evaluation, Blaackman (2014), Private Sector Assessment (2014), Demand Creation for Health Sector Reform (2014), Review of Fund Management Arrangements for EPHS in Somalia (2014), and Review of Nutrition Integration in Somalia (2015). Findings from these studies have greatly contributed to the design of this BC.

During the design phase, DFID economist (CHASE), Peter De Souza supported the team in the drafting of the appraisal case.

ANNEX 7: Health Programme DRAFT logframe
PROJECT TITLE
IMPACT	Impact Indicator 1				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
Improved health of Somalis leads to improved human and economic development			Planned		850/100,000					765/100,000
	Reduction of the maternal mortality ratio		Achieved
					Source
					MICS 2206 South Central; MICS 2011 Somaliland; MICS 2011 Puntland
	Impact Indicator 2				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
			Planned		146/1,000					102/1,000
	Reduction in the U5 mortality rate		Achieved
					Source
					MICS 2206 South Central; MICS 2011 Somaliland; MICS 2011 Puntland
	Impact Indicator 2				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
	Increased contraceptive prevalence rate		Planned		15%					25%
			Achieved
					Source
					MICS 2206 South Central; MICS 2011 Somaliland; MICS 2011 Puntland
OUTCOME	Outcome Indicator 1				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)		Assumptions
Increased access and utilisation of RMNCH services through the provision of EPHS delivery	Additional numbers of women using modern contraceptive methods		Planned		112,521
			Achieved
					Source
					HMIS; Implementing partners' reports; existing data from HCS and JHNP
	Outcome Indicator 2				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
	Additional numbers of women using skilled birth attendants		Planned		47,205
			Achieved
					Source
					HMIS; Implementing partners' reports; existing data from HCS and JHNP
	Outcome Indicator 3				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
	Additional numbers of children U5 vaccinated with pentavalent		Planned		136,444
			Achieved
					Source
					HMIS; Implementing partners' reports; existing data from HCS and JHNP
	Outcome Indicator 4				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
	Unique numbers of children U5 and pregnant women receiving nutrition specific interventions.		Planned		TBC
			Achieved
					Source
					HMIS; Implementing partners' reports; existing data from HCS and JHNP
	Outcome Indicator 5				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
	Additional numbers of women attending 3+ ante natal clinics		Planned		176,014
			Achieved
					Source
					HMIS; Implementing partners' reports; existing data from HCS and JHNP
	Outcome Indicator 6				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
	No of visits		Planned		1,857,826
			Achieved
					Source
					HMIS; Implementing partners' reports; existing data from HCS and JHNP
INPUTS (£)	DFID (£)				Govt (£)		Other (£)		Total (£)				DFID SHARE (%)
	92,000,000					100
INPUTS (HR)	DFID (FTEs)
	1 x A2, 1 X A2L, 1x B1, 1 X B2
OUTPUT 1	Output Indicator 1.1				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)		Assumptions
	Management functions established and performing at the devolved level.		Planned
Strengthened the four management components of EPHS functioning in targeted areas at a devolved level			Achieved
	Output Indicator 1.2				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
			Planned
	Development of an EPHS costed strategy with clear identification of quality, scope and coverage of services		Achieved
			Source
IMPACT WEIGHTING (%)	Output Indicator 1.3				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
			Planned
	Delivery of services TBD		Achieved
			Source					RISK RATING
INPUTS (£)	DFID (£)				Govt (£)		Other (£)		Total (£)				DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)
OUTPUT 2	Output Indicator 2.1				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)		Assumptions
			Planned		Define most vulnerable populations.
Increased demand for nutrition, reproductive, maternal, and child health services	Define and implement a strategy to target vulnerable populations - nomads, IDPs, adolescents		Achieved
			Source
	Output Indicator 2.2				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
			Planned		Conduct KAP survey on health seeking behaviour
	Shift in attitudes and practice towards health seeking behaviour.		Achieved
			Source
IMPACT WEIGHTING (%)	Output Indicator 2.3				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
			Planned		Map and identify existing levels of knowledge of rights and participation in community planning processes.
	Increase knowledge of rights, mechanisms for demanding accountability and community participation in planning processes		Achieved
			Source
	Output Indicator 2.3				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
			Planned		Identify x no of CHC and develop strategy for functioning CHCs
	No of community health committees functioning and directly linked to a health facility.		Achieved
			Source					RISK RATING
INPUTS (£)	DFID (£)				Govt (£)		Other (£)		Total (£)				DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 3	Output Indicator 3.1				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)		Assumptions
			Planned		Assess options based on existing mechanisms		Contract suitable mechanism, inception period		Use results for programme analysis		Use results for programme analysis
	Develop a beneficiary feedback mechanism		Achieved
Generating evidence and lesson learning			Source
	Output Indicator 3.2				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
			Planned		Assess options based on existing mechanisms, possibly through DFID S Somalia Monitoring Programme
	Third party independent monitoring mechanism established		Achieved
			Source
IMPACT WEIGHTING (%)	Output Indicator 3.3				Baseline 2016/17		Milestone 1 2017/18		Milestone 2 2018/19		Milestone 3 2019/20		Target (2021)
			Planned
	Evaluations of process and outcomes		Achieved
			Source					RISK RATING

INPUTS (£)	DFID (£)				Govt (£)		Other (£)		Total (£)				DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)