Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Bihar Agricultural Growth and Reform Inititiative (BAGRI)
Programme Value: £10 Million		Review Date: 24 July 2014
Programme Code: 204135	Start Date:19/08/2013	End Date:31/03/2019

Summary of Programme Performance
Year	2014
Programme Score	B
Risk Rating	Medium

Summary of progress and lessons learnt since last review

Not applicable. This is the first year of the programme.

Summary of recommendations for the next year

DFID Task Team needs to complete the OJEU process is in time to enable the Technical Support Agency (TSA) to start its work from January 2015 as planned. It is expected that necessary approvals from Government of India will be received by August 2014.

In view of the delay in receiving approval from GoI and finalisation of DPR/ TOR by Government of Bihar, the team needs to revised the targets to ensure tangible progress by the next annual review.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Quest ID 3859905
DevTracker Link to Log frame:	Quest ID 3950085

Outline of the programme
Bihar is one of DFID partner states, transforming after years of conflict and stagnation. It is the poorest state in india with per capita income of roughly £309[1] and nearly 80%[2] of the population is dependent on agriculture for livelihood which contributes around 22%[3] of the GSDP (2010-13 at 2004-05 prices). The agriculture sector in Bihar needs reform, investment and regulation. One third of farm produce is wasted for want of post-harvest infrastructure. Farm operations aren’t profitable enough because individual landholdings are small. Farmers aren’t using technology to their advantage to obtain information on commodity prices and weather conditions. The farm–price realisation is very poor due to lack of infrastructure, information and market access. Lack of proper marketing outlets forces them to sell their produce through exploitative middlemen.
[1] Bihar’s Economic Survey (2013-14) highlights that the estimated GSDP at current prices in 2012-13 is Rs. 3.09 lakh crore, implying a per capita income of Rs. 30,930 (approx. £ 309)
[2] www.krishi.bih.nic.in (accessed 28 July 2014)
[3] Bihar’s Economic Survey (2013-14) pp. 6

DFID has agreed to invest £10 million in technical assistance to support Bihar’s Plan for Agriculture and Allied Sectors to raise poor farmers’ incomes. Primarily, it will do three things: mobilise farmers, build producer federations and create market access by linking with large retail chains, corporate buyers and exporters, food processing industries and; help develop institutions that provide regulation, attract investment and conduct research; facilitate technology transfer and help make finance and agriculture information more readily available to farmers through one stop shops. The desired outcome of the project are-
1. Organise more than 75000 farmers into supplier groups that are equipped to access corporate buyers in the market via 20 or more producer companies.
2. Facilitate private investment in storage and supply chain for agriculture and horticulture produce. (Private investment in agriculture storage and infrastructure increased by 100% during the project period).
3. Increased farmer’s access to credit and crop insurance by 50% or at least 1,00,000 new farmers.
4. Increased access to price information through new technologies to more than 1m farmers.
5. Improved functioning of the public extension network and increase private sector participation.
6. Introduce regulatory reforms for improved market access and farm price realisation for poor and marginal farmers.
7. More than 75,000 farmers are supported on increased production, productivity and improved farm price realisation to improve production as well as marketing.
8. At least 20 producer companies are linked with wholesale markets, big retailers, exporters and food processor.
9. Strengthen existing institutions with appropriate reforms/ restructuring or set up agency/ institutions for: regulating agricultural markets; sharing up-to-date information; attracting investments into agriculture; and commissioning research and market analysis.
10. and promote sector specific partnership between UK and Bihar Institutions.
DFID will use in house and external expert to support Government of Bihar achieve the above mentioned targets. A technical support agency is being contracted through international competitive tender. The successful bidder will need to demonstrate wide-ranging expertise – bringing best practice in agri-marketing, facilitating pubic private partnerships deals and mobilising farmers at the village level. This would be consistent with the Secretary of State’s vision of creating a ‘hub of development expertise’ in India linked to UK institutions.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

In July 2013, the MoS had approved the Business Case for £10 million Technical Assistance (TA) to support Bihar Government’s Plan for growth reforms in the Agriculture and Allied Sectors to improve poor farmers’ incomes. Subsequently, a Detailed Project Report (DPR) setting out the purpose, objectives, and expected outputs and outcomes of the programme was prepared and shared with the Department of Agriculture (DoA), Government of Bihar (GoB). DFID since then held series of meetings with the Principal Secretary and other senior officials in the Agriculture Department to discuss and finalise detailed operational plan, governance and monitoring mechanism of the intervention. GoB’s formal approval of the DPR came only in June 2014. The delay was due to frequent changes of senior officials of GoB following change in state leadership and the general elections in India during March – May 2014.

The GoB had forwarded their approval of BAGRI project to the Union Ministry of Agriculture, Government of India (GoI) and the Department of Economic Affairs (DEA) for Government of India approval. We are expecting these approvals to come towards August this year and will be able to sign the Memorandum of Understanding (MoU) by end-August 2014.

A detailed Terms of References (ToRs) for the Technical Support Agency (TSA) for providing expert technical support for the implementation of the intervention was prepared and is published on the Open Journal of European Union (OJEU) for open international competition. A joint committee with representation from GoB and DFID will select the TSA and issue an output based contract for 5 years. We expect the selection process to complete by end December 2014 and start implementation of the project by early January 2015.

Overall output score and description : B

The project is scored B for overall output based on the progress made on the mobilisation phase, including the relationships built with GoB through series of meetings and detailed discussions on the operational management and monitoring/governance of the project. However, since the project implementation has not yet started, all outputs have been rated at C.

Key lessons

Some of the key lessons learnt thus far are:

1. Need to strongly engage and create buy in from Junior Level officers in the GoB for speedy approvals and effective implementation of the programme. (TA team; TTL; PO)
2. Frequent transfer of senior level officers might affect the programme delivery; so a proper risk mitigation strategy and broad acceptance and endorsement of the strategy and activities need to be done at the highest level. (TTL;PM)
3. Regular and continued follow up with government partners both at the state and GoI level is key to speedy approvals during mobilisation phase. (PM;TTL)
4. A high quality team mostly based out of Bihar and district level is necessary for achivements of the targeted outcomes.

Key actions

1. Logframe indicators or milestones need to be revised based on the inception report and baseline studies. The following section on output scoring is tentative at the moment and detiled analysis of the progress and score will be undertaken in next review. (TA Team, TTL)
2. OJEU process need to be completed by December 2014 and technical team to be in place by January 2015. (PCD & Task team)

Has the logframe been updated since the last review?
Not Applicable. This is the first review.
## C: DETAILED OUTPUT SCORING

Output Title	Enabling effective accessibility to clear, reliable and dynamic market information in a Transparent Framework
Output number per LF		Output 1	Output Score	C
Risk:		Medium	Impact weighting (%):	To be adjusted post logframe revision
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
No. of farmers benefitted from access to real time market information	10,000	Project interventions are yet to start
No of additional farmers getting access to better inputs, knowledge and technology through ‘one stop shops’	10,000

Key Points

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations NA

Output Title	Enabling Formation of Farmers Producer Group / Co-operatives for Maximizing Profits to Farmers and Strengthening their Bargaining Power
Output number per LF		Output 2	Output Score	C
Risk:		Low/Medium/High	Impact weighting (%):	To be adjusted post logframe revision
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
No. of additional / Farmers’ groups formed / Producer companies registered	(a) 50 / (b) 0	Project interventions are yet to start
No. of farmers benefitted from access to new markets	5000
No of additional farmers getting access to institutional credit	10,000
No of additional farmers adopting new and innovative agriculture practices	4,000

Key Points

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation NA

Output Title	Strengthening the Marketing Chain and Market Infrastructure, wherein Small / Marginal & Poor Farmers are Effective Partners
Output number per LF		Output 3	Output Score	C
Risk:		Low/Medium/High	Impact weighting (%):	To be adjusted post logframe revision
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
No. of new market linkage and market infrastructure projects successfully enabled	5	Project interventions are yet to start
New institution for agriculture market development established	New institution set up as nodal agency for market development & investment facilitation
Management of agriculture-related schemes by the Department	Single integrated MIS system for all schemes designed

Key Points
Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations NA

Output Title	Establish and operationalise institutional and regulatory reforms and build the capacity of departments.
Output number per LF		Output 4	Output Score	C
Risk:		Low/Medium/High	Impact weighting (%):	To be adjusted post logframe revision
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Establish & operationalise an institution for agriculture market regulation and development		Project interventions are yet to start
Improve institutional quality in agriculture research with focus on lab-to-land transfer
Support administrative reforms in agriculture department and related agencies

Key Points

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations NA

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

Project is yet to start and onboarding of the TA team is expected around January 2015. Since spending has not started, VfM assessments cannot be done. In our contracting process we are putting enough safeguards and conditionalities to ensure economy and better VfM.
VfM performance compared to the original VfM proposition in the business case

Not applicable.

Assessment of whether the programme continues to represent value for money

As project has not started, such as assessment cannot be done.

Quality of financial management

Not Applicable

Date of last narrative financial report	NA
Date of last audited annual statement	NA

E: RISK

Overall risk rating: Medium

Overview of programme risk
Key risks	Mitigation plan
Delay in initiation of project activities by about 18 months (as onboarding of the TA provider(s) is expected from January 2015)	The TA agency can frontload the deliverables and outputs for the first two years to cover the gap due to delay in project initiation. Since, this is a full TA programme, if needed, extension of the programme could be sought post mid term assessment.
Political uncertainities post state assembly elections in 2015	One of the reasons for delay in project initiation has been our efforts to seek strong buy in of the DoA officials and senior officials in GoB pertaining to project activities. This is also one of the mitigation plans besides provision for mid term review to assess the performance of TA agency and prevailing situation in the state with its implication on the project.
Risk of poor performance by the TA provider(s)	Propoer due diligence will be undertaken before awarding the contract to TA agency. Further, the ToR issued for hiring of TA agency has an in built clause that restricts frequent changes in the team thus ensuring continuity of the human resources and their performance. Finally, the mid term review planned will assess performance of the TA team midway into the project and undertake course correction as required for the remaining project period.

Outstanding actions from risk assessment

The action taken towards mitigation of risks will be assessed during the next review.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
As stated above, the initiation of the project activities will be delayed by about 18 months. However, such a deviation from the planned timeframe was expected considering the changes in political situations in the state, national elections and frequest changes in the state bureaucracy.

Nevertheless, it is expected that large part of timelag will be covered by the TA agency through accelerated efforts.

Performance of partnership(s)

Despite frequent changes in the leadership of agriculture department of GoB, there has been very high quality engagement of from them in the mobilisation phase. The terms of reference for hiring of TA agency was critically reviewed by the GoB officials and their inputs were incorporated into the ToR before issuance.

Asset monitoring and control

Not applicable.

G: CONDITIONALITY

After the implementation of the programme begins, detailed assessment against partnership principles will be undertaken from subsequent annual reviews.

H: MONITORING & EVALUATION

Evidence and evaluation
The programme lays significant impetus on evidence guided planning and implementation. Best practices within the country and from outside will be used to design and implement the project interventions. Further, stringnet mesures will be put in place for establishing baseline and arrive at realistice milestones for the project that will be tracked and monitored throughout the project life cycle. There is also a provision for a third party impact evaluation towards end of the project. The monitoring and evaluation activities will entail participation of all the project stakeholders including all stakeholders (farmers, district level officials, concerned GoB departments at state level, TA agency and Task Team).

Monitoring progress throughout the review period
The programme memorandum proposes that project progress will be monitored on a quarterly basis by partner departments and DFID against agreed work plans; on a six-monthly basis by the Governing Council. With GoB, DFID will undertake annual Output to Purpose Reviews (OPR), in line with standard DFID requirements and based on the Programme logical framework. This will be strictly followed once programme interventions begin.

Further, a mid term review is planned for the project after 2.5 years form initiation of project implementation. This will assess the performance of the TA agency and the efficacy of partnership with GoB within the ambit of prevailing political situation in the state to take informed course corrections in the remaining project period.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process