Type of Review: Annual Review for FY 2013-14

Business Case Title: Humanitarian Preparedness & Response

Date started: 30 June 2011

Date review undertaken: May 2014

Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
Up to £20 million over a five year period (2011-2016) to support humanitarian preparedness activities and to deliver timely relief aid following a disaster event. / There are three components to the UK’s humanitarian portfolio in Bangladesh: / Rapid responses to disasters: Approximately £15 million has been earmarked for post-emergency relief activities such as cash-for-work (CFW) programmes to help communities recover from the impact of disaster events. / Institutional preparedness and logistical planning: £4.5 million in support of preparedness-type activities which enable agencies to better respond to the cyclical nature of disaster events. / Building the evidence base: Approximately £500,000 will be allocated to support DFID-B in developing a robust evidence base regarding impactful humanitarian activities.

What were the expected results?
DFID-B’s Humanitarian Preparedness & Response business case does not specify the exact or approximate numbers of people to be supported over the lifetime of the implementation period. Instead it predicts thematic-type results:
Lives and livelihoods saved, and recovery and resilience enhanced through: / A faster, more flexible model for response. / A better prepared response system. / Easier access to remote, inaccessible areas. / 2. A more effective response, including a specific focus on: / Long term resilience and recovery. / Accountability to those affected by the disaster. / More efficient funding channels (speed, quality, capacity). / Taking greater account of the needs of the most vulnerable - particularly women and girls, the elderly, sick and disabled – and of socially excluded communities and individuals. / Nutrition. / 3. An enhanced evidence base and better analysis for an effective disaster management response in Bangladesh, and globally.

What was the context in which UK support was provided?
Bangladesh is one of the most disaster prone countries in the world. Research conducted by DFID shows that during the period 1980-2010 an estimated 300 million Bangladeshis were affected by a range of disaster events – primarily natural ones but also manmade crises too. The country sustains economic losses in the region of US$1 billion per annum through the impact of shocks and stresses, DFID research has also shown (see The Economics of Early Response and Resilience: Lessons from Bangladesh available at : https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/226156/TEERR_Bangladesh_Report.pdf) . / The cyclical nature of disasters in Bangladesh jeopardises the ability of people and communities to transition out of poverty. For example, more than one million head of livestock were killed by Cyclone Sidr in 2007 impacting the ability farming communities to recover. After Tropical Storm Mahasen, in May 2013, the most commonly cited coping strategy identified in assessments was borrowing money, via informal lenders, at high interest rates. / Women and girls bear the brunt of disaster events in Bangladesh. For example, in 1970 Cyclone Bhola claimed roughly 300,000 lives. Female victims numbered males by a ratio of 14:1.[1] Approximately 90% of the 140,000 fatalities caused by the 1991 cyclone in Bangladesh were female. Since the 1970s Bangladesh has helped to address the gendered impacts of disasters but women and girls are still disproportionality impacted. For example, the ratio of female: male deaths dropped to 5:1 in 2007 following Cyclone Sidr.[2] / There is also a correlation between the geographic locations of disasters and poor human development indicators in Bangladesh. For example, areas most prone to cyclones include the worst performing Upazilas in terms of primary school attendance in Sakthira, Bhola, Noakhali, Cox’s Bazar and Chittagong. / Bangladesh has a history of major and damaging disaster events including 24 cyclones in the last 53 years. According to a World Bank study cyclones have resulted in 450,000 deaths since 1970. Since the 1970s, due Bangladesh’s focus on disaster preparedness, there has been a reduction in the numbers of casualties and deaths caused by disaster events. As noted above, Cyclone Bhola led to 300,000 deaths whereas Cyclone Sidr (which was more powerful) led to roughly 3,500 deaths. In addition, there are also frequent ‘low-level’ and slow onset events such as waterlogging, flash floods and ‘cold waves’ which affect significant numbers of people each year. In 2012 waterlogging affected an estimated 1 million people in south-west Bangladesh. / DFID-B’s Humanitarian Preparedness & Response Business Case provides the UK a platform from which humanitarian support can be delivered to help Bangladesh prepare for and respond to the risk and hazard context. The UK’s humanitarian portfolio is sufficiently flexible to enable timely responses to events as well as allowing the UK to make strategic allocations to support preparedness planning activities.
[1] http://www.worldbank.org/en/news/feature/2013/12/12/improving-women-disasters
[2] Climate Change Adaptation Actions in Bangladesh, Shaw et al

## Section A: Detailed Output Scoring

Output 1: Provision of emergency assistance and recovery support to households most affected by disasters
Outputs met expectation (A)
Final results: An overall score of A is given to Output 1 on the basis that UK funded programmes reached more beneficiaries than originally planned and delivered what we judge to have been appropriate assistance that addressed priority humanitarian needs. However, activities implemented under Output 1 were hamstrung by the inability of DFID to provide support in a timely manner following a disaster event. / During the course of 2013 DFID-B allocated £5.47 million following three separate disaster events in south-east and south-west Bangladesh. In both cases, UK support was provided following the conduct of a coordinated multi-agency needs assessment via the Joint Needs Assessment (JNA) programme. / LIFE programme / In early June 2013 DFID finalised[3] an allocation of £2 million to the NGO consortium NARRI (National Alliance for Response and Risk Reduction Initiative) which reached 18,183 households (HHs) / 80,000 individuals following a period of major rainfall in 2012 which resulted in flash floods, waterlogging and landslides in Chittagong, Bandarban and Cox's Bazar – the LIFE programme. / Assessments conducted by the JNA in August 2012 showed the wide-ranging impact of this disaster with a particular negative impact on livelihoods and food security. For example, the JNA revealed that monthly incomes in the three districts had been reduced by 12-57% due to inundation of farming land which resulted in loss of labour opportunities etc. Additional assessments carried out by NARRI to obtain union level and more up-to-date data also illustrated the impact on food security and livelihoods. The main finding of the more recent NARRI assessment was that the food security situation, 2.5 months after the disaster, remained worrying with nearly 40% of respondents having a poor Food Consumption Score (FCS) and another 40% having a borderline FCS. / DFID assesses that the design of the NARRI programme, in targeting food security and livelihood requirements, was appropriate to the prevailing context – see recommendations section, below. / NARRI’s inclusion criteria for its programme in south-east Bangladesh helped to ensure that the most vulnerable members of affected communities were reached. This was apparent during DFID monitoring to Cox’s Bazar and Chittagong where DFID staff met with beneficiaries from ethnic / religious minorities as well as female headed HHs and HHs with elderly and disabled people and young children. / The LIFE programme provided HHs with a package of financial assistance budgeted at BDT 10,000. This support was to enable HHs to make investments in either agricultural-type activities (such as homestead gardens) or small businesses (including road-side shops). / NARRI’s overall target for this intervention was 18,821 HHs although this was later revised downwards to 18,183 due to the inability of a consortium member, Solidarites, to secure FD-6 approval from the NGO Affairs Bureau (NGO AB). This is the primary reason that the programme failed to meet its overall target. / DFID assesses that the NARRI programme delivered tangible benefits to beneficiary communities. Final reporting shows that at the conclusion of the programme 93% of beneficiaries were assessed as having an “acceptable” FCS – a marked improvement in the overall food security and livelihood situation in comparison to the situation in October 2012. / Mahasen / In response to Tropical Storm Mahasen, which made landfall in southern Bangladesh on 16th May 2013, the UK provided £1.75 million to NARRI. UK support to NARRI was made following the conduct of coordinated needs assessments via the JNA (both phase 1 and phase 3 JNA assessments were conducted). The JNA phase 1 assessments revealed that 1 million people were affected by Mahasen comprising 25% of the three impacted districts (Bhola, Barguna and Patuakhali). Food security and livelihoods were identified by the phase 1 JNA as the most pressing of needs. / The phase 3 food security sectoral assessment revealed the specific impact of Mahasen in the three districts including; at least 50% of farming HHs had lost all of their crops, 65% of HHs had lost their homestead garden, wage earning opportunities and purchasing capacity had suffered which had contributed to a 20% increase in the uptake of HHs seeking loans via informal mechanisms. / Assessment data generated by the JNA was used by NARRI in the design of its proposal. NARRI’s programme provided HHs with a package of financial, in-kind and technical assistance. Beneficiaries received a total of BDT10,000 for inclusion in ‘cash-for-work’ (CFW) interventions and participation in ‘cash-for-training’ activities which focussed on “livelihood restoration” and nutrition. CFW activities focussed on rehabilitation of roads and other infrastructure. We assess that NARRI’s proposal was appropriate to the prevailing context given NARRI’s specific focus on food security and livelihoods which the JNA revealed to be sectoral priorities. / NARRI sought to deliver support to 11,500 HHs in Barguna and Patuakhali. It was able to surpass this target by nearly 3,000 HHs – reaching 14,481 HHs in total – thanks to favourable exchange rate fluctuations. It should be noted that NARRI’s very careful financial and administrative management of the programme meant that it was able to communicate to DFID the impact of exchange rate variations which it used to update its original proposal and to reach more beneficiaries. / As with its work in south-east Bangladesh NARRI’s inclusion criteria for its programme post-Mahasen helped to ensure that the most vulnerable HHs were supported. NARRI focused on landless farmers, those HHs who were showing negative coping strategies (such as high levels of loans), HHs whose property had sustained damage during Mahasen, socially vulnerable HHs e.g. female headed HHs as well as those HHs who were not benefitting from other sources of support – Government or other. / On the basis of interim and final reporting from NARRI we assess that the Mahasen programme provided beneficiaries with appropriate and impactful humanitarian services. The programme provided supported HHs with training in five thematic areas: / Kitchen gardening, scientific method of seed preservation/storage. / Nutrition, including breast feeding. / WASH, including improved hygiene practices. / Introduction to saline and flood tolerant varieties of crop, climate change and coastal adaptation measures. / Household level disaster preparedness, including early warning systems. / A total of 14,411 people were trained in total including 13,934 women and 119 disabled people. / HHs received financial support for taking part in the above trainings (as well as in-kind support such as tools, seeds and fertilisers) plus additional financial support for taking part in works to upgrade community infrastructure. / Ex-post monitoring revealed that 67% of the surveyed HHs were able to share knowledge on reproductive health and nutrition issues, 93.6% were able to share knowledge on safe sources of water and sanitation, 90.6% were able to share their learning on homestead gardening process. / The final outcome of the project was as follows: / 95% of HH able to meet their basic food requirements / 87.6% of HH showing improvement in DRR, resilient livelihoods and nutrition practices / 99 % of targeted households who restarted or scaled up their livelihood activities / Via CFW activities nearly 100km of community roads were constructed / rehabilitated. In addition works to augment and strengthen the structural integrity of five school grounds plus connecting roads and three embankments were carried out. Such works have given communities – and not just supported HHs – with improved access to markets, medical centres, cyclone shelters, schools etc. NARRI estimates that this has helped to protect 280,000 hectares of land (equivalent to more than 392,000 football pitches) from potential future flooding and from saturation of salt water from the sea. We judge that the NARRI programme could have future positive impacts on food security given the infrastructural works which have afforded greater protection to land under cultivation. / During ‘live’ programme monitoring DFID staff met with beneficiaries from the NARRI programme in Bhola, Barguna and Patuakhali. The beneficiaries we met with spoke in very positive terms about the design of the programme with specific mention of NARRI’s ability to target the most vulnerable HHs as well as positive feedback relating to the governance structures of the programme itself – the Project Implementation Committee (PIC) which was staffed by community representatives and local government actors. Beneficiaries also stressed that CFW was an effective methodology for both supporting local works to rehabilitate community infrastructure and enabling affected HHs to chart their own recovery. Beneficiaries also reported to DFID staff that the modalities for transferring cash from NARRI consortium members, via mobile phone, was effective and secure. / World Programme (WFP) waterlogging / In late March 2014, towards the end of financial year 2013-2014, DFID-Bangladesh agreed a package of support budgeted at £1.72 million with the WFP in response to persistent waterlogging in south-west Bangladesh. The decision to fund WFP was taken following the implementation of a desk-based JNA ‘light’. / WFP’s programme, as with the other activities funded during 2013-2014, seeks to tackle some of the priority needs identified by the JNA. Whilst we predict that WFP’s programme, which is implemented by a range of international NGOs, will play an important role in responding to the immediate humanitarian needs brought about by waterlogging we are not yet able to measure the actual impact of its work as it has only very recently started. / Recommendations / UK humanitarian programmes in Bangladesh have played an important role in helping communities to recover from the impact of disasters. Evidence from UK humanitarian responses in south-east and south-west Bangladesh can substantiate this claim. However, UK financial resources allocated in financial 2013-2014 towards relief operations were not done in a timely manner. / For example, in response to Tropical Storm Mahasen which occurred on 16 May 2013 the DFID supported NARRI programme commenced in early November i.e. nearly 6 months after Mahasen had made landfall. Delays in the issue of FD-6 clearances for consortium members accounted for a delay of two months. / It took five weeks for DFID and the consortium lead, Plan International, to finalise a proposal and issue an accountable grant agreement. DFID issued a call for proposals on 28 June six weeks after Mahasen had struck southern Bangladesh and one month after the release of the JNA phase one assessment had been released which provided DFID with a basic understanding of the context. DFID’s call for proposals was made two weeks after the release of the JNA phase two assessments which provided the UK and others donors with a more detailed, sector specific, appraisal of needs. Contributing factor for this delay included limited humanitarian advisory and programme management staff cover in DFID-Bangladesh with Mahasen occurring at time when there was no DFID full-time humanitarian adviser. Other external factors also played a role such as limited drive in the humanitarian architecture to respond to the after effects of this disaster. / Other parts of the approval process related to Mahasen or events which supported the ability of the UK to release funding were speedier. For example, the JNA phase one report was issued on 23 May. This would have taken place more quickly if the HCTT had met earlier. Further, DFID’s Head of Office responded to a funding submission within 5 days. / Generally speaking we assess that such delays will have exacerbated humanitarian needs in Mahasen affected communities although we also recognise that measuring the impact of delays is problematic. / DFID’s Rapid Response Facility (RRF) obliges the UK to provide financial assistance to organisations within a period of 72 hours once a decision has been taken to allocate funding. We recommend that DFID-Bangladesh adopt a similar approach once a JNA has been launched. At present there are no specific time-based targets in use in DFID relating to the provision of UK humanitarian aid beyond a commitment to timely allocations. See recommendation numbers 1, 2 and 3, regarding the timely provision of UK funded relief aid. / In addition to the above we assess that DFID could enhance the impact of its humanitarian interventions by effecting better linkages to other DFID funded programmes. For example, during a monitoring visit to Barguna it was disappointing to learn that the District Commissioner was unaware of the Local Disaster Risk Reduction Fund (LDRRF) – a component of the Comprehensive Disaster Management Programme (CDMP). The LDRRF could be used to support the maintenance of infrastructure established by DFID humanitarian CFW programmes, for example. / Other UK supported interventions which could strengthen our humanitarian work include the Community Legal Assistance programme and the Chars Livelihoods Programme. / Better integration with existing programmes might also help DFID to overcome a key issue related to inclusion criteria that we observed during assessment missions in financial year 2013-2014. By targeting only HHs without access to other forms of assistance, as DFID’s partners did in south-east and south-west Bangladesh, supported HHs run the risk of falling back into crisis following the next shock or stress. By helping HHs to access longer-term assistance we could promote more effective resilience building. See recommendation number 4 regarding linking UK funded humanitarian activities to other DFID supported interventions. / On an assessment visit to south-east Bangladesh to undertake an appraisal of the LIFE programme DFID staff discussed with beneficiaries their humanitarian needs in the context of findings from the JNA. We heard from several different communities that water, sanitation and hygiene (WASH) needs were a major concern although the JNA conducted in 2012 (which included focus group discussions with affected HHs) identified food security as a principal requirement. See recommendation number 5. / The photograph above shows a malfunctioning family latrine belonging to a HH supported via the LIFE programme in Cox’s Bazar district. Waste from the latrine is pictured leaking directly into the surrounding community. The HHs we spoke to were, rightly, concerned that if flooding should occur effluent could pose serious health implications for the community and could erode any gains that DFID’s programme has delivered. Implementation of recommendation numbers 5 and 6, which should help to give beneficiaries more voice, might help those communities we are supporting to play for an influential role in programme delivery. / Discussions are ongoing currently (as of June 2014) within DFID-Bangladesh regarding future disaster management activities that might be supported by the International Climate Fund (ICF). Given that the majority of crises that the UK responded to in FY 2013 and 2014 were climate related effective linkages must be built between activities resourced through humanitarian finances and those by future ICF programmes. See recommendation number 7. / The following table sets out recommendations for output # 1: / No. Recommendation Review date / / implementation by / 1 Following the conduct of a JNA DFID should reach a decision about whether or not to respond in programmatic terms within a period of seven days – ideally this decision should be made more quickly. This would represent an innovative approach to humanitarian action. At present there are no specific time-based targets in use in DFID relating to the provision of UK humanitarian aid. Immediate implementation. / Review after next JNA is launched. / 2 Once agreement has been reached in principle to support a specific agency / agencies DFID should finalise proposals, grant agreements, MOUs etc. within 10 days. Immediate implementation. / Review 1 October 2014. / 3 A letter of support is sent to the NGO-AB by DFID ideally within a period of 7 days following an FD-6 application by a UK funded NGO. Immediate implementation. / Review 1 October 2014. / 4 Amend the Intervention Review Sheet to include the following questions: / “How does the proposed programme demonstrate linkages to existing DFID-Bangladesh funded programmes? If not clear, then what steps will the implementing partner undertake to effect synergies between this intervention and on-going DFID funded activities?” Immediate implementation. / Review 1 October 2014. / 5 Undertake real-time monitoring for all humanitarian programmes with the objective of bringing to the fore beneficiary assessment of needs with a view to adjusting programme design if appropriate. Immediate implementation. / Review 1 October 2014. / 6 Discuss with cluster the extent to which they have sufficient human resources to support future JNAs to ensure that sector specific needs are appropriately articulated in JNA reports. Implementation dependent on funding decision regarding the future of the JNA programme. / 7 Design of future ICF disaster management programmes must dovetail with programmes supported through humanitarian finances where relevant i.e. for climate related shocks. This should be established by requiring the design of future ICF disaster management programmes to explicitly reference on-going UK humanitarian programmes setting out how linkages between the two will be brought about. / In addition, future non-disaster related programmes supported by DFID-B could articulate linkages with the UK’s humanitarian activities. Implementation dependent on funding decision regarding the future ICF programmes. / 8 DFID-Bangladesh’s Climate Change and Environment Adviser should support the Humanitarian Adviser in monitoring programme delivery of WFP’s waterlogging programme to ensure no undue environmental harm is caused in the delivery of the intervention. Review after submission of WFP’s first quarterly report. / Impact Weighting (%): 55% / Revised since last Annual Review? No. / Risk: Low. / Revised since last Annual Review? No.
[3] The programme was agreed in the first quarter of 2013 but due to major FD-6 delays implementation commenced in June.

Output 2: Improved co-ordination and information management
Outputs moderately did not meet expectation (B)
Final results: During financial year 2013-2014 the UK provided the following support which had the objective of enhancing humanitarian coordination and information management in Bangladesh: / Care, JNA programme: £268,984. / WFP / Logistics Cluster, ‘Strengthening of the Logistics Cluster: £76,103. / Office for the Coordination of Humanitarian Affairs (OCHA), Information Management Officer: £78,500. / JNA / The JNA programme has proved to be a major asset to Bangladesh and is helping DFID to deliver specific components of UK humanitarian policy, specifically our drive to improve the responsiveness and coherence of the humanitarian architecture. Through the conduct of post-disaster assessments that are based on sound and rigorous methodologies the UK has helped relief actors to better understand the impact of disaster events. We assess that the JNA has also played an important role in improving accountability between disaster affected communities, relief organisations and donors. The JNA has contributed to this via improvements in how assessments are carried out. / A key strength of the JNA has been its broad reach in terms of the numbers of relief actors it has trained in assessments. To-date 80% of planned district level trainings have been conducted in addition to three training sessions which were held in Dhaka. In total the JNA has provided training to 63 humanitarian agencies (NGOs, UN organisations and the Red Cross / Crescent). This number does not include government officials who also benefitted from JNA training. / In terms of progress toward stated objectives the JNA programme has performed soundly – although we await final reporting – this is due to a no-cost extension to the JNA meaning final reporting will follow in July. For example; the JNA has provided on-going technical support to the Information Management Work Group over the last financial year, JNA methodologies and tools have been shared via the Humanitarian Coordination Task Team (HCTT) see http://www.lcgbangladesh.org/JNA%20materials%20update.php, training workshops and on-going capacity building initiatives have been held in Dhaka, Rangpur, Cox’s Bazar, Sylhet and Khulna, the JNA has also compiled and publicised ‘Secondary Data Reviews’ (SDRs) for six disaster events – see http://www.lcgbangladesh.org/HCTT.php and http://acaps.org/resources/bangladesh-joint-needs-assessments / As well as the above the JNA also conducted two separate assessments following disaster events in 2013-2014. In May 2013 the JNA led an assessment after Tropical Storm Mahasen made landfall in southern Bangladesh. An additional JNA was carried out in October in response to waterlogging in Sakthira. Assessment reports are available at: http://www.lcgbangladesh.org/HCTT.php / See recommendation number 1, below. / WFP / Strengthening of the Logistics Cluster / There are four principal outcome areas under the programme with WFP of which two have been successfully achieved – Coordination & Information Management, and GIS Capacity Building. The remaining outcome areas, Custom Clearance Process for Emergency Relief Cargo and Military and Civil Defence Liaison and/or protocols for Cooperation, were not fully achieved. / DFID support to the Logistics Cluster enabled the national logistics capacity assessment to be updated and also led to the production of a logistics capacity atlas. Both documents provide humanitarian stakeholders in Bangladesh and externally with information which is critical to effective preparedness and response planning. Documents will be uploaded to the http://www.lcgbangladesh.org/HCTT.php / UK funds were also used by WFP to support the running of the Logistics Cluster including information management support to the cluster lead etc. In addition the UK also supported the training of NGO staff in GIS data collection as well as funding the supply of handheld GPS units to NGO staff. This training enabled NGO staff to support the update of the capacity assessment and the production of the capacity atlas which details the whereabouts of different logistics infrastructure across Bangladesh. / As noted above WFP was not able to deliver all stated objectives for work related to customs clearances processes and civil-military liaison despite its efforts to do so. Unfortunately the Government of Bangladesh was unwilling to sign the customs model agreement which if in place would facilitate the rapid importation of relief items into Bangladesh in the event of a crisis. We judge that owing to the political situation in 2013 WFP was not able to get the Government to focus on this issue. Further, the Logistics Cluster was unable to reach an agreement with the Government regarding use of and coordination of military assets to support humanitarian operations during emergencies. / We judge that the civil-military objectives were, in the context of the political and security challenges that Bangladesh faced in 2013 related to the general election were unrealistic. We discussed this issue with the UK’s Defence Adviser in 2013 who noted that, owing to the political and security challenges that Bangladesh faced last year, brokering agreement on WFP’s civil-military goals with the Government would have been extremely challenging if not impossible. / Notwithstanding the difficult political context in 2013 we assess WFP should have used the HCTT more strategically regarding advocacy around customs procedures given the HCTT is comprised of Government as well as non-government actors. For example, WFP might have requested that the Chair of the HCTT, the Director General at the Department for Disaster Management, lobby other colleagues in relevant ministries on the customs issues. / See recommendation 4 regarding brokering agreement on civil-military coordination and customs clearance processes which we judge can play an important role in improving disaster preparedness. / Towards the end of the review period DFID-Bangladesh entered into discussions with humanitarian stakeholders about preparedness for catastrophic disaster events such as a category five cyclone or a large damaging earthquake. We assess that the Logistics Cluster might be an important entry point for taking forward work that might help Bangladesh become better prepared for a mega-disaster. For example, given that the Bangladeshi military are designated first responders for major emergencies DFID should ensure that there is agreement and improved understanding relating to the use of and coordination of military assets to support humanitarian operations during emergencies. Similarly, customs clearances processes for relief actors should be addressed now rather than during an emergency. See recommendation number 2, below. / OCHA, Information Management Officer (IMO) / DFID-Bangladesh funded the secondment of an IMO to UN Resident Coordinator’s (RC) Office for a period of six months during the second half of 2013. This support was provided via the Standby Partnership Programme (SBPP) between OCHA and DFID. / The IMO played an important role in supporting the JNA assessment in relation to waterlogging in Sakthira in late 2013. The IMO was also responsible for coordinating the work of the Information Management Working Group (IMWG) and also led efforts to standardise information management related protocols and procedures across clusters. / The IMO was also responsible for supporting the RC’s Office with mapping and humanitarian analysis. We judge that these areas of the IMO’s terms of reference were only partially achieved. For example, following Tropical Storm Mahasen the IMO failed to produce a gap analysis or mapping products related to the provision of support in a timely manner but relevant documents have been subsequently produced. However, we recognise the important contribution that the IMO has made, behind the scenes, to the humanitarian system in Bangladesh in relation to the IMWG and information management protocols. / Agreement to provide further support to the IMO position was taken in March 2014. The terms of reference (ToRs) that DFID and the UN agreed included the following: / Support the HCTT and clusters with IM requirements. Specifically, oversee the use of agreed IM tools and processes by IM focal points within clusters. Provide ad hoc IM support to clusters as required. / Conduct an IM capacity assessment of clusters with SMART recommendations to maintain / augment IM functionality. This should be presented to the HCTT by Q2 and clusters should be required to report back to the HCTT on progress against recommendations. / Maintain inter-cluster IM tools and products such as ‘3W’ and ‘4W’ matrixes, to ensure that http://www.lcgbangladesh.org/HCTT.php is updated on a regular (weekly basis) and contains all relevant IM related documents / IM products developed by the IMO etc. / Coordinate and advocate with sectors and clusters for standard inputs and data collection systems for information analysis and products related to the emergency. / Provide monthly updates to the HCTT regarding the humanitarian context in Bangladesh. Updates should be both verbal and delivered through information products such as ‘Humanitarian Dashboards’, mapping products showing contingency planning efforts, gap analysis etc. The IMO will be required to respond to ad hoc IM related requests from HCTT members. / Support coordinated needs assessment efforts in the field as required by the HCTT. / Support the processing and analysis of data and information and presenting it in the format most useful for analysis (e.g. standardized templates, reports, maps) to inform evidence-based advocacy. / Provide technical advice and manage the data collection, data entry and use of standardised systems to support humanitarian operations, / Support Logistics cluster in organizing… GIS mapping training to… cluster members. / Perform other IM related tasks as required. / See recommendation number 4 relating to the above. / The following table sets out recommendations for output # 2: / No. Recommendation Review date / / implementation by / 1 Provision of follow-on funding to CARE for a future JNA-type programme. Future funding has been agreed in principle. / The current JNA has been extended until 30 June 2014. Ideally implementation of phase two should commence as soon as possible after this date. Recommendations for output number 1, regarding FD-6 applications, should be taken into account. / 2 Provision of follow-on funding to WFP / the Logistics Cluster with a specific focus on preparedness for mega crises and civil-military coordination. Future funding has been agreed in principle. / Assess WFP performance vis-à-vis civil-military coordination after the Disaster Response Exchange Exercise in September 2014. / 3 Future support to WFP / the Logistics Cluster could look at the use of military assets during humanitarian emergencies as well as customs clearance processes. DFID should work with the UK’s Defence Adviser to deliver such objectives. Future funding has been agreed in principle. / Agree a work plan for delivery following the conclusion of the Disaster Response Exchange Exercise in September 2014. / 4 DFID-Bangladesh should hold monthly review meetings with the IMO to assess performance against the above ToRs. To be implemented immediately. / Impact Weighting (%): 20% / Revised since last Annual Review? No. / Risk: Low / Revised since last Annual Review? No.

Output 3: Logistical support for NGOs and other partners providing humanitarian, risk reduction and development support to disaster-prone and vulnerable regions
Output 3: Outputs substantially exceeded expectation (A++)
Final results: During financial year 2013-2014 the UK provided £303,000 to the NGO Mission Aviation Fellowship (MAF) for support to the organisation’s seaplane service which operates throughout Bangladesh including hard to reach locations. MAF’s seaplane is the only one of its kind to operate in Bangladesh. / Latest reporting from MAF for the period January – March 2014 shows that the programme continues to outstrip targets and objectives agreed in the project proposal. For example, demand for MAF’s “southern shuttle flights” were 60% above the agreed target. In addition, passenger and flight number targets were exceeded by 20% and revenue hours by 10%. During the penultimate quarter of 2013-2014 MAF recorded a 35% increase in the numbers of passengers who used the service in comparison to quarters 1 and 2. According to MAF this increase was due to road travel restrictions that relief and development agencies imposed due to hartals. By virtue of using waterways, rivers, lakes etc. on which to access locations MAF was able to help organisations overcome travel restrictions linked to the political period. / Overall in 2013-2014 MAF satisfied all but one of its stated objectives; MAF was not able to establish a northern shuttle flight – due to the current full utilisation of the aircraft to serve the southern shuttle and charter flights. / The UK is committed to providing £1 million to MAF over the implementation period 2011-2016. DFID is the only donor to MAF at present - the organisation intends to use £1.7 million of its own internal resources to support the Bangladesh operation during the programme period. Given MAF’s reliance on UK funding DFID has encouraged MAF to build its donor base. Whilst MAF, so-far, has not been successful in doing this we assess that the organisation has taken substantive measures to understand more fully the market place, to examine quickly its VfM and to make itself more responsive to client demands, putting itself in a stronger position to attract outside funding. For example, MAF conducted an independent impact evaluation of its work “in facilitating aid accountability and project quality” which it will use to demonstrate to donor cost-effectiveness of its service and its effect on enhancing programme quality. We judge that MAF’s evaluation is of an acceptable standard. / The evaluation found that “the MAF air service has made, and continues to make significant contributions to the [wider development and humanitarian community in Bangladesh] through the reduced need for remote management and improved needs assessments, project management, monitoring, accountability, improved learning [and] advocacy.” In addition, the evaluation asserts that whilst “it is not easy to quantify savings to the overall aid programme, there was evidence that the service provided by MAF Bangladesh had been instrumental in annually gaining millions of pounds for aid agencies in grants, through improved project design, accountability and through savings in not having to use alternative transport means.” / According to MAF there are clear value for money benefits that organisations can realise by using its charter and shuttle service. “A costing model developed [by MAF] demonstrates that, for three Dhaka-based staff making a field visit of four working days to a project site accessed through Barisal… the MAF Southern Shuttle service” is 35%, 25% and 68% more cost-effective than making the same journey by road, boat or helicopter respectively. / The MAF evaluation also uses the following info-graphic to make the case for its service versus accessing locations via road. / The following table (and narrative) sets out recommendations for output # 3: / MAF has taken a proactive and creative - but as yet unsuccessful - approach to expanding its donor base. As noted above, DFID is the only donor to the organisation in Bangladesh. The following recommendations are made with the objective of effecting a more sustainable future for the organisation and to reduce its reliance on DFID funding. / No. Recommendation Review date / / implementation by / 1 MAF must convene individual meetings or a general briefing session with UN agencies, donors and NGOs that use its seaplane service to share its impact evaluation. MAF must use these meeting / briefing session to make clear what the implications of a reduced service or withdrawal from Bangladesh would mean for development partners aid agencies. To be implemented by 30 September 2014. / 2 MAF must develop HCTT and cluster specific engagement strategies with the objective of forging institutional links between MAF and clusters and with MAF and the HCTT e.g. MAF and the Logistics Cluster agree an ‘Air Users Group’, MAF becomes provider of aerial surveillance to the HCTT post-disaster. To be implemented by 30 September 2014. / 3 MAF must begin to develop a strategy setting out how it will reduce the scale of its Bangladesh operation so that when the DFID funded programmes closes there is not a major deleterious impact on users of its service. For example, it could poll users to find out which routes are seen as priorities. To be implemented by 30 November 2014. / Impact Weighting (%): 20% / Revised since last Annual Review? No. / Risk: Low. / Revised since last Annual Review? No.

Output 4: An enhanced evidence base and better analysis for an effective disaster response in Bangladesh, and globally
Output 4: Output met expectation (A)
Via the JNA programme (funding details, above) the UK has supported the development of a series of studies regarding the impact of different disaster events in Bangladesh. In 2013-2014 the JNA produced six secondary data reviews (SDRs) in-line with stated objectives, which illustrate the sector specific impact of cyclones, flash floods and landslides, haor flooding, river flooding, waterlogging and cold waves. Each of the studies, prior to release, were presented to and agreed with clusters giving the JNA’s work broad acceptance. / We assess that the SDRs provide relief and development actors with valuable insights into the impact of cyclical disasters in Bangladesh. The principal strength of the SDRs is that they are fully referenced and so help to establish a robust evidence base for humanitarian analysis. / The following table sets out recommendations for output # 4: / No. Recommendation Review date / / implementation by / 1 A sustainability plan for updating and ownership of the SDRs is developed with CARE for the next phase of the JNA programme. To be agreed with CARE by 31 March 2015. / 2 The SDRs should become an integral part of the DFID-Bangladesh toolkit. SDRs should be shared with across DFID-Bangladesh and should be used to inform the design of all future programmes where relevant. Immediate implementation. / To be reviewed by 30 November 2014 / Impact Weighting (%): 5% / Revised since last Annual Review? No. / Risk: Low

## Section B: Results and Value for Money.

1. Achievement and Results
Has the logframe been changed since the last review? No. / Overall output score and description: Output met expectation (A) / Output # Output description Impact weight (%) Output performance / 1 Provision of emergency assistance and recovery support to households most affected by disasters. 55% Output met expectation (A) / 2 Improved co-ordination and information management. 20% Outputs moderately did not meet expectation (B) / 3 Logistical support for NGO and other partners providing humanitarian, risk reduction and development support to disaster-prone and vulnerable regions. 20% Outputs substantially exceeded expectation (A++) / 4 An enhanced evidence base and better analysis for an effective disaster response in Bangladesh, and globally. 5% Output met expectation (A) / Direct feedback from beneficiaries: / DFID staff made two monitoring visits in 2013-2014 to assess performance of partners funded by the Humanitarian Preparedness & Response business case. Such visits enabled us to meet with programme beneficiaries and to discuss, amongst other things, their participation, in UK funded interventions. / See the recommendations section for Output 1 for suggestions on how DFID-Bangladesh could enhance engagement with beneficiaries. / DFID funded agencies throughout 2013-2014 ensured beneficiaries were able to inform the design of activities and played a key role in guiding implementation. All three programmes funded under Output 1 used various mechanisms for soliciting feedback from beneficiaries. DFID funded partners worked with communities (including HHs and local government officials) to identify beneficiaries. Feedback was sought regarding the selection of proposed beneficiaries. PICs were also established which were used to help inform the design of CFW programmes. During programme implementation complaint response mechanisms were instituted, specifically telephone helplines and complaints boxes, which enabled beneficiaries and the wider community to provide anonymous feedback. Case studies from Mahasen programme show that about 10% of the targeted beneficiaries were disabled (approx. 1300 people). They were supported by the programme which led to an increased source of income and reduced their vulnerability to shocks. The programme was designed in such a way that they could participate in activities such as child-minding while other able-bodied beneficiaries carried out cash for work activities, providing water etc. The seeds given to them and the training have helped them increase their confidence and options of income generation. / Summary of overall progress / During the implementation period seven individual programmes were supported via the Humanitarian Preparedness & Response business case. We assess that DFID funded programmes have performed strongly at the output level – notably the NARRI post-Mahasen programme, MAF’s seaplane service and the JNA. The LIFE programme, despite reaching fewer beneficiaries than originally planned, also proved successful at the output level. It is too early to assess the performance of the WFP programme in Satkhira. / More strategically DFID supported programmes have helped to establish an enabling environment for humanitarian actors. The JNA, for example, provides all humanitarian actors in Bangladesh with a range of tools and reference documents related to the conduct of assessments and the impact of crises. A major achievement of the JNA programme has been in helping to establish a joined-up approach to humanitarian assessments. / UK support to the Logistics Cluster in Bangladesh resulted in the production of a nationwide logistics capacity assessment along with a capacity atlas which shows their whereabouts and type of logistics related infrastructure such as warehouses (including storage capacity), roads, highways, bridges (including weight and width limitations), airports etc. The work to develop the assessment and the atlas were completed in 2013 – 2104 although the two documents were submitted in early May 2014. / We judge that UK support to the Logistics Cluster, as with the JNA, made an important contribution to the wider humanitarian community in Bangladesh and in particular the outputs are valuable preparedness tools. The work with the logistics cluster is an important underpinning of the earthquake preparedness work that we are now supporting under a resilience heading. We have shared the capacity assessment and atlas with colleagues in London from the CHASE Operations Team. / Key challenges / Coordination / Throughout 2013 – 2014 DFID officials expended significant energy and time in supporting coordination efforts particularly in relation to the HCTT - the principal coordination forum for humanitarian action in Bangladesh. Our input was not commensurate with the HCTT’s output. In addition, we judge that the HCTT inhibited the ability of actors to provide humanitarian assistance in a coordinated and timely manner. / For example, following Tropical Storm Mahasen the HCTT was slow to meet and as a result was slow in commencing a JNA. The HCTT’s terms of reference (http://www.lcgbangladesh.org/HCTT/HCTT%20TOR_10%20April%202012.pdf) make very clear that HCTT meetings can be requested by two or more members although representatives from the Department for Disaster Management, who sit on the HCTT, feel a decision to call an HCTT must be Government led. Confusion over this fundamental issue led to HCTT members questioning the efficacy and usefulness of the HCTT. Further, the HCTT was also slow to consider waterlogging in south-west Bangladesh as an issue of humanitarian importance. / Humanitarian information management and analysis / Collectively the HCTT has also proven incapable of articulating the ‘gap’ in humanitarian needs following the provision of assistance after a disaster event. DFID believes that the HCTT must be capable of providing such information given its role as Bangladesh’s primary humanitarian coordination forum. / Another major challenge DFID faced in Bangladesh last year which is linked to the weakness of the coordination architecture was the small number of donors who provided post-disaster support. The inability of the HCTT to provide an overview of needs and gaps following Mahasen contributed to the underwhelming response from the donor community – only the UK and European Commission provided financial support. Had the HCTT been able to communicate such information DFID feels other donors might have allocated funds. / Cluster capacity / Further barriers to effective preparedness and response include the differing capacities of individual clusters. For example, the Food Security Cluster benefits from having a number of full-time dedicated staff members and so in 2013 – 2014 was able to produce contingency plans, gap analyses etc. Other clusters are not similarly capacitated which inhibited their ability to deliver such outputs. See the recommendations section for Output 1 for suggested follow-up action related to the ability of the clusters to engage in JNAs. / FD-6 delays / The slowness of the Government to issue FD-6 approvals in 2013 – 2014 proved to be a challenge. DFID itself must also quicken its responses to disaster events in Bangladesh, as noted above. / A final challenge is the managing the interface between the international humanitarian architecture (as it manifests in Bangladesh), and the national disaster management capacity, that has been developed through many years of investment by partners (including DFID) in CDMP. / The likelihood of a major disaster event in Bangladesh, such as a catastrophic earthquake or category five cyclone, cannot be ruled out. Such an event would overwhelm Bangladesh’s national disaster management capacity and would necessitate a major international humanitarian response operation. For this reason DFID asserts that the role of international relief providers in Bangladesh must be ring-fenced otherwise their ability to operate in a manner consistent with humanitarian principles, will be compromised. That is to say the operational space for humanitarian agencies, including for existing and future activities, must be protected. DFID should seek to ensure that approaches to national disaster management complement activities undertaken by humanitarian agencies. / Annual outcome assessment / Humanitarian interventions supported by DFID-Bangladesh in financial year 2013 – 2014 have contributed to achievement of outcome indictors associated with the business case. Though output 1 the UK has provided effective humanitarian support to vulnerable crisis affected communities. UK funds have played an important role in helping HHs recover from shocks and stresses. Via output 2, principally through the JNA programme, DFID-Bangladesh supported the creation of an enabling environment for humanitarian actors. In a similar manner outputs 3 and 4 also provided a conducive environment for effective humanitarian action.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes – although as a measure of overall project delivery, the unpredictable nature of humanitarian intervention means that this metric is not appropriate. / 2.2 Key cost drivers / The principal cost driver in relation to the delivery of the business case in financial year 2013 – 2014 was the scale and severity of humanitarian crises affecting Bangladesh. The reporting period was, in the context of Bangladesh’s disaster history, quiet with a relatively small number of people affected by shocks and stresses. / For example, According to http://www.emdat.be/result-country-profile?disgroup=natural&country=bgd&period=2005$2014 Tropical Storm Mahasen was the sixth largest disaster event in Bangladesh during the period 2005 – 2014 in terms of numbers of affected people - Mahasen impacted 1.5 million people in-total. In real terms this is a significant number although in the context of Bangladesh’s disaster history Mahasen was not especially noteworthy event. The relatively small numbers of people affected by disaster events in the 2013 2-14 was the key determinant of the size of UK humanitarian support that was provided. / Other costs drivers which impacted on the delivery of the programme included: / Hartals, strikes and insecurity related to the election period – especially the final quarter of 2013. Hartals caused major disruption to humanitarian operations and saw a 20% reduction in the delivery of nutritional supplies in some areas of the country. Hartals also contributed to price inflation for staple foodstuffs and other essential supplies due to travel restrictions which caused markets to malfunction. / Exchange rate fluctuations both positive and negative also impacted on the programme. As noted previously, the Mahasen related programme managed by NARRI benefitted from significant exchange rate fluctuations which enabled NARRI to reach approximately 25% more beneficiaries than originally planned. / The procurement costs for post-Mahasen related CFW programmes were also a principle cost driver. By centralising procurement of in-kind supplies required for the CFW programme such as fertilisers, seeds and farming tools etc. and agreeing costs with suppliers in advance NARRI was able to ensure smooth financial management. / 2.3 Was the project completed within the expected timescale: / No. Due to the hartals, strikes and blockades, most of the projects could not complete activities within the expected timescales. For example, the LIFE project sought an extension of four months, the JNA project was also extended by two months and the Logistics Cluster programme was extended by three months.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project / The evidence base for interventions remained strong throughout the reporting period. Humanitarian response activities were all, without exception, based on JNA data. The publication of the SDRs by the JNA programme provides DFID and other stakeholders with important pre-crisis data which should contribute to more rigorous and transparent decision making in terms of preparedness and response activities. / In the future, the pattern of climate induced shocks and stresses will change; and their frequency is likely to increase. In Bangladesh, peak intensity of cyclones may increase by 5-10%, precipitation rates by 20-30%, and temperatures by 1.4 degrees by 2050. There are likely to be more erratic patterns in rainfall, with consequences for drought and agricultural livelihoods.[4] / 3.2 Set out what plans are in place for an evaluation. DFID-Bangladesh did not, directly, undertake any evaluations during the reporting period. As noted above, MAF completed an impact evaluation of its DFID funded work in early 2014. / DFID-Bangladesh felt that undertaking an evaluation of individual responses was not commensurate with the extent of support that it provided in 2013 – 2014 for humanitarian crises. / Going forward DFID should consider conducting a joint evaluation alongside ECHO of collective responses to disaster events. Such an evaluation might look at the UK and European responses to the 2014 cyclones seasons, for example. Given ECHO’s leading role as a humanitarian donor to Bangladesh, alongside the UK, a joint evaluation would provide significant coverage and oversight of humanitarian activities in-country.
[4] International Panel on Climate Change (2001) Third Assessment Report

4. Risk
4.1 Risk Rating (overall project risk): Low. / Did the Risk Rating change over the life of the project? No. / 4.2 Risk of funds not used for purposes intended: One case of misuse of UK funds was reported to DFID during the implementation period. This involved the NARRI consortium (CARE and Islamic Relief were the relevant consortium members) and occurred during implementation of the LIFE programme. / CARE and Islamic Relief were both very proactive in terms of reporting the theft of UK funds to DFID and in their attempts to seek redress. Ultimately, however, NARRI was not able to secure the return of £769 which is equivalent to 0.03% of the overall LIFE programme although it did work to ensure that £1,457 was returned to programme beneficiaries. DFID-Bangladesh worked with Risk and Control Unit on this issue from the time to issue was first reported through to field monitoring and related follow-up. / DFID-Bangladesh undertook an assessment mission to Cox’s Bazar district with CARE and Islamic Relief in an attempt to better understand the context in which the theft of UK funds took place. We met with several communities including a number of HHs whose CFW funds had been seized from them by local elites. We made clear to the communities involved that what had happened was unacceptable. / The relevant District Commissioner agreed to intervene but only if HHs first reported the theft of funds to his office and the police. Owing to fear of reprisal a number of affected HHs decided against reporting the theft meaning DFID was not able to pursue the matter further due to the lack of official reporting to the authorities. / NARRI took steps to mobilise the community ahead of the programme starting to help guard against capture by local powerful figures which we assessed as reasonable. We also judged the mechanism used to transfer funds from NARRI members to beneficiaries as secure. Beneficiaries themselves also commented positively on this aspect of the programme. / It was beyond the scope of this programme to address the power dynamics within beneficiary communities given that the LIFE programme was humanitarian in nature. To help strengthen future humanitarian programmes DFID-Bangladesh should consider developing stronger links to the CLA programme managed by the Governance Team. DFID might also request that potential partners undertake a brief political-economy analysis of targeted communities prior to implementation commencing. Doing so might help partners to think about risks related to implementation. / Climate and Environment Impact: A minority of programmes funded in 2013 – 2014 took into consideration the potential climate and environmental impact of UK supported humanitarian programmes in Bangladesh. / WFP’s proposal for its programme in Sakthira included a specific section on the environment and the measures the organisation will put in place to limit harm. The proposal also notes that in terms of identifying adaptive livelihood techniques this must be done in a way that does not damage the local ecosystem. See recommendation 8, output number 1. / MAF’s evaluation assessed the potential environmental benefits that use of its seaplane service could have in relation to vehicle use. MAF’s evaluation found that travelling by air to Barisal from Dhaka was more fuel efficient than travelling by road on the basis of MAF’s calculations. / Going forward DFID-Bangladesh must ensure that environmental considerations are taken into account during the design of programmes. The Climate Change and Environment Adviser could feed into specific components of the Interview Review Sheet (IRS) and if necessary could suggest changes to the IRS so that DFID is asking its partners relevant questions regarding their programme strategy.

5. Value for Money
5.1 Performance on VfM measures: / We judge that DFID supported programmes in FY 2013-2014 have delivered, to an acceptable level, against each of the components of humanitarian VfM – speed, cost and quality. / Speed / The conduct of JNAs, in a reasonably timely manner, following disaster events in south-east and south-west Bangladesh enabled humanitarian actors to take evidence based decisions in terms of selecting response modalities and beneficiary targeting. The JNA model we judge plays an important role – primarily via its focus on “assessment preparedness” – in facilitating timely humanitarian action. However, DFID’s own internal decision making processes need to be quickened as these impede the quick delivery of support. The same is true of FD-6 applications. / Cost / As noted above, an evaluation that MAF conducted of its Bangladesh operations demonstrated the major cost savings that organisations could realise via the use of the MAF seaplane service versus the cost of travelling by boat, road or helicopter. The use of mobile phone based systems through which to transfer cash to beneficiaries meant that organisations avoided banking charges associated with transferring funds into banks accounts. Other cost-effective components of the DFID humanitarian portfolio include shared M&E and procurement platforms under the NARRI Mahasen programme which helped to drive costs down. Unit costs for the NARRI programme compare favourably to those from organisations that were unsuccessful in applying for funding from the UK after Mahasen. However, making a direct comparison is problematic due to the difference in assistance packages that were proposed. For example, under the NARRI programme HHs received a range of different seeds (for production of chillies etc.) with a unit cost of £4. Other organisations sought to provide an in-kind agricultural package of support with a unit cost of £25. Due to the differences in proposed packages we would caution against using unit costs as comparator. The administration and management fee were found to be proportionate and within standard rates for humanitarian NGOs. / Generally we assess that DFID funded humanitarian activities in Bangladesh in FY 2013-2014 were of a good quality. For example, final reporting for the LIFE programme shows that at the conclusion of the programme 93% of beneficiaries were assessed as having an “acceptable” FCS – a marked improvement in the overall food security and livelihood situation in comparison the situation in October 2012. The post-Mahasen JNA was ranked internally by ACAPs as the second best humanitarian needs assessment conducted by the organisation in 2013. Also post-Mahasen in Barguna district DFID met programme beneficiaries who had generated income of BDT 30000 via the provision of BDT500 worth of seeds. / 5.2 Commercial improvement and Value for Money: / All of our partners have strong procurement practices embedded in their organisational policies and follow them for any procurement required for the programme. Most of the interventions in the past year have not led to large scale procurement and have either been cash support or capacity building interventions. / 5.3 Role of project partners: / All of DFID’s humanitarian work in 2013 was programmed via UN agencies and international NGOs with local partners supporting delivery. For example, the response to Mahasen saw DFID contract the NGO Plan who funded a range of NGOs including a number of Bangladeshi civil society organisations. / We assess that NARRI, during the reporting period, worked in a cost-effective manner. It struck an appropriate balance between ensuring strong administrative and financial management with appropriate spend on beneficiaries. DFID successfully negotiated with NARRI on operating costs to ensure our programmes delivered VfM. / We feel that use of the NARRI consortium enabled DFID to deliver at reasonable scale in terms of beneficiaries reached. By working through five NGOs (with another providing technical support) DFID was able to reach more HHs than working on a bilateral basis with individual NGOs. / One of the key VfM-related observations DFID observed when working via NARRI were the savings we were able to make on M&E as this was centralised with one representative undertaking M&E for the entire consortium. / 5.4 Did the project represent Value for Money: Yes. / The programme delivered effective VfM from a humanitarian perspective in terms speed, cost and effectiveness of services that were provided. See performance measures, above.

6. Conditionality
6.1 Update on specific conditions: No conditionality was linked to this programme.

7. Conclusions
DFID’s humanitarian portfolio continues to deliver successfully against stated objectives. / Weaknesses in the wider humanitarian architecture continue to inhibit Bangladesh’s preparedness for and responses to disaster events. DFID should continue to push humanitarian actors to deliver against their mandates and should make better use of the UK’s Missions in New York and Geneva to influence the UN system. Looking forward, DFID should work to ensure that Bangladesh is better placed to respond to catastrophic disaster events such as a category five cyclone or a large damaging earthquake. Future lobbying and programmatic choices should work towards this objective. / DFID should continue to work closely with ECHO in-country given our shared assessment of the humanitarian architecture and common objectives for Bangladesh. Joint UK-EC financing of future activities should be considered as should joint M&E. / The risk context in Bangladesh means a flexible and rapid financing mechanism is required for which the current business case allows for. Future financing models in Bangladesh should be based on similar principles but should be much more closely linked to other components of DFID’s work in-country including ICF supported early recovery-type activities. / DFID should also take forward the above 17 recommendations that are made in relation to the business case.

8. Review Process
This annual review was conducted by two staff members from DFID-Bangladesh and was largely desk-based. / DFID-Bangladesh should ensure that the next annual review for this business case is conducted by either by an independent consultant or by a Humanitarian Adviser from another DFID department. Doing so will bring independent analysis and oversight of the UK’s humanitarian portfolio in Bangladesh.