Extending Support to Civil Society in Tanzania: Foundation for Civil Society Programme

Business Case

August 2011

Table of Contents

# Acronyms

AcT	Accountability in Tanzania Programme
AG	Accountable Grant
AGM	Annual General Meeting
AIDS	Acquired immune deficiency syndrome
AJWS	American Jewish World Service
CIDA	Canadian International Development Agency
CSC	Critical Success Criteria
CSOs	Civil Society Organizations
DFID	Department for International Development
DPs	Development Partners
DPOs	Disabled Peoples’ Organizations
EU	European Union
FBO	Faith-based organisation
FCS	Foundation for Civil Society
GBS	General Budget Support
GoT	Government of Tanzania
HRD	Human Resource Development
IFRS	International Financial Reporting Standards
LGA	Local Government Authorities
MDGs	Millennium development goals
M&E	Monitoring and evaluation
MKUKUTAII	Tanzanian poverty reduction strategy
MOU	Memorandum of Understanding
MIE	Mid-term Impact Evaluation
NGOs	Non-governmental organisation
SDC	Swiss Development Cooperation
SIDA	Swedish International Development Agency
VFM	Value for money
# Intervention Summary

## Title: Extending DFID Support to Civil Society Organizations in Tanzania

What support will the UK provide?
The UK, through the Department for International Development (DFID), will provide £8 million over 4 years from June 2011 to March 2015 to support civil society organizations in Tanzania through the Foundation for Civil Society.

Why is UK support required?
This support is an integral part of DFID Tanzania’s efforts to implement a strengthened approach to budget support. Through this project, DFID Tanzania will implement the commitment that up to 5% of all budget support goes to promoting domestic accountability. / While the political liberalization of the early 1990’s in Tanzania have created spaces for citizens to hold state accountable, challenges remain in relation to: citizens’ access to information on roles, responsibilities and rights; low levels of citizen engagement with elected officials and government; as well as low levels of citizen’s participation in planning and budging processes at local and national levels. / To tackle the above challenges, DFID will provide support to civil society organizations in Tanzania, which play a vital role in supporting citizens to improve their lives. Civil Society Organisations are central to ensuring rights are respected, basic services are delivered, enabling citizens to be more active in their own development and ensuring that policies benefit ordinary people – especially the poorest.

What are the expected results?
The intended impact of the programme is to ensure Tanzania is democratically governed and has achieved its 2025 vision in the fight against poverty and a better quality of life for all its citizens / The outcome will be that by March 2015 more citizens (especially the poor and marginalized) are empowered to influence and monitor policies that meet the needs of the poor and participate in the budgeting processes for improvement of service delivery in Tanzania / The intervention will deliver five main outputs: / Citizens are more aware of their civic rights and responsibilities / Ability of CSOs and citizens to participate and influence policies and budgeting processes is strengthened / Increased CSOs involvement in promoting rights of women, persons with disabilities and other vulnerable groups e.g. pastoralists / Strengthened CSOs organizational capacity and effectiveness / Foundation for Civil Society delivers high quality services and is efficiently and effectively managed and governed / The key changes which are expected to result from the support include: / Two million men and women enabled by DFID to access quality and user friendly information on services, entitlements and rights / 150 new CSOs have strengthened their organizational and institutional capacity, especially in the areas of: resource mobilization, report writing, strategic planning, financial management and M&E / 200 CSOs trained to demand greater accountability and transparency from governments with 75 CSOs effectively monitoring budgets and decision-making processes at national and district levels / 200 CSOs trained to mainstream gender equality in their organizations and interventions and at least 50% showing evidence of the impact of their work on promoting gender equality. / 100 Disabled People’s Organizations (DPOs) receive grants and capacity building support to better promote rights of their members / Annual CSO Forum bringing together CSO representatives to promote learning, networking and sharing of lessons / Annual CSO Exhibition at the National Assembly (Dodoma) and House of Representatives (Zanzibar) to facilitate consultations between civil society representatives and Members of Parliament – a platform for mutual learning, exchange and advocacy / Strengthened capacity of the Foundation for Civil Society to professionally manage and deliver small grants to civil society organizations and showing evidence of improvements in the area of results monitoring and reporting.

Business Case for: Extending Support to Civil Society in Tanzania

# Strategic Case

A. Context and need for DFID intervention
Rationale / This intervention will contribute towards the delivery of HMG objectives as articulated in the DFID Tanzania Operational Plan, third priority area: ‘Getting Government to work better and helping Tanzanians hold their Government to account’. Extending support to civil society will enable DFID Tanzania deliver its governance outcome in the operational plan namely: ‘Tanzania's emerging democracy consolidated through stronger, more transparent democratic and oversight institutions and systems held to account by empowered civil society’. / Support to civil society will strengthen processes of accountability and empowerment; these processes are core Ministerial priorities. The DFID 2011 Business Plan states that DFID will ‘use the aid budget to support the development of local democratic institutions, civil society groups, the media and enterprise’. Within this, DFID will implement the commitment that up to 5% of all budget support should go to accountability institutions. / Context / Accountability and empowerment: key DFID priorities. Improving accountability and promoting citizen empowerment are top coalition priorities for DFID’s work in partner countries. As the Secretary of State outlined in his 2010 speech at the Royal Society[1], ‘the big society defines our new approach to development. An approach that delivers choice and demands accountability’. Accountability and empowerment interventions make important contributions to increasing quality and impact of DFID’s work on service delivery, supporting more inclusive political systems and ensuring that poor people benefit from growth. / DFID investment in civil society. There is good evidence of the role a strong civil society can play in improving service delivery and protecting citizens’ rights.[2] Over the last decade Tanzanian civil society has grown rapidly with much of the growth coming through large NGOs based in major cities that engage in national policy issues. DFID and its partners have made significant investment in Tanzanian civil society over the last decade through grants and capacity building. In 2002 DFID and other donor partners established the Foundation for Civil Society, an organisation set up to deliver small grants to civil society organisations (CSOs). Since then, the Foundation has become an independent, Tanzanian owned and managed entity, delivering 2,339 grants to the value of $26.2m (of which $7.1m can be attributed to DFID) since 2003.[3] / The impact of previous investment: citizen participation and the development of a ‘big society’. The political liberalisation of the early 1990s created new spaces for citizens to hold the state accountable. Since then, dramatic growth in civil society has played an important role in empowering citizens to engage in public life more actively. Data on citizens’ attitudes to democracy is available through the respected Afrobarometer survey[4] - an African led survey that looks at public attitudes towards democracy, which is repeated on a regular cycle and uses a standard set of questions to allow for systematic comparisons between countries. In 2008, 9.5% more Tanzanians engaged in collective action than in 2001.[5] Increasing rates of participation in accountability are a key indicator of Tanzanians making a shift from ‘voters’ to ‘citizens’ and suggest Tanzanian democracy is maturing.[6] Other indicators of participation also indicate this shift, between 2001 and 2008 the proportion of citizens engaging in demonstrations almost doubled from 10.6% to 19%[7]. Attribution and the direction of causation remains problematic, however the growth of civil society action occurred alongside this change in citizen behaviour. This change has been impressive, putting rates of participation now well ahead of the mean for other liberalised African states.[8] / While the last eight years have seen empowerment interventions developing an active ‘big society’, challenges remain in relation to accountability. In particular, levels of citizen engagement with elected officials and government have remained static.[9] Stronger citizen accountability is essential for Tanzania to realise improvements in service delivery and respect for rights. / Consolidating democracy. Tanzania is an emerging democracy having held just four rounds of democratic elections. Political liberalisation in the early 1990s was not significantly driven or underpinned by internal pressure,[10] making Tanzania vulnerable to democratic backsliding. The work of civil society organisations to increase citizens’ knowledge of their rights has contributed to a stronger democratic foundation. When comparing rigorous national level Afrobarometer data from 2008 to the situation in 2001, the perception that Tanzania is democratic increased from 24% to 74% of citizens.[11] Those strongly approving of one-party politics also declined by 50% to 14.2%, an important change given Tanzania’s history of one-party rule.[12] Those reporting they are now very satisfied with democracy increased from 16.9% to 29% between 2001 and 2008.[13] Quantifying the extent of civil society contribution to this is not possible but good qualitative evidence exists linking the establishment of Tanzania’s increasingly professional civil society and increasing ability for citizens to exercise their political rights.[14] / New opportunities have emerged. Trends from the 2010 election demonstrate an increasing willingness of citizens to directly hold the state accountable.[15] As a result of open primaries and increased party competition, constituents rejected 59% of incumbent MPs. This ‘turnover test’ is widely recognised as an essential milestone in the consolidation of democracy.[16] There is also some evidence that the Parliamentary performance of Members of Parliament also had implications for their re-election.[17] Yet the trend is complex, the 2010 election also saw a fall in turnout to 43% from 72% in 2005.[18] This is not necessarily due to voter disengagement but this is subject to ongoing analysis. The last five years have also seen resurgence in Parliamentary autonomy, with the work of the accountability committees leading to the resignation of the Prime Minister and other senior Ministers in 2008. There are also signs that collectively these accountability pressures from civil society, citizens, media and Parliament are leading to increased government responsiveness. The withdrawal of a Constitutional Reform Bill in April 2011 in order that it can be subjected to further public consultation is an important indicator of this. DFID will build on these changes in order to strengthen citizen’s participation in accountability. This will be essential to realising further developmental benefit from the ‘big society’ created by Tanzanian civil society over the last decade. / The need for improvements in service delivery. The budget of the Government of Tanzania has grown by 120% over the last 5 years, as a result of increased domestic revenues and General Budget Support (GBS).[19] This increase in resources has increased government capacity,[20] yet the distribution of investment has been highly uneven. The top ten Local Government Authorities (LGAs) in the health sector receive per capita allocations that are five times greater than the bottom ten. For the education sector the top ten LGAs receive eight times per capita than the ten at the bottom.[21] / The increased reach of the Tanzanian state has led to some notable successes, such as increases in Primary School enrolment yet these have not always been accompanied by increases in the quality of service provision.[22] Increasing engagement beyond the state, in accountability processes, will be essential to delivering improvements in the efficiency and efficacy of key services. / Theory of Change. DFID will support civil society organisations that ultimately deliver increased respect for rights and improvements in the delivery of services. The provision of small grants and capacity building to a diverse range of civil society groups means these impacts are achieved in a range of ways: (1) Organisations will provide citizens with information on state performance. This will enable citizens to use evidence as a basis for formal accountability decisions such as voting. Provision of information will empower citizens with sufficient evidence to effectively engage representatives directly. These accountability pressures on representatives, and the link to performance, will increase their incentive to deliver and ultimately lead to the delivery of services and respect for rights. (2) Civil society organisations, acting on behalf of citizens, engage directly in policy debates. Organisation’s engagement and influence results in new or amended legislation and policy that better meets the needs of the poor or marginalised. (3) Organisations directly monitor and defend citizens’ rights through legal aid and election observation. This ensures that individual citizens’ rights are respected and creates precedents, ensuring the rights of others are also respected. The sum of these precedents are the strong institutions necessary for democracy to function effectively.[23] (4) Organisations work with communities to develop non-state solutions to local problems such as gender based violence. This is achieved through a range of tools including community meetings and other awareness raising campaigns. By empowering work outside of the state in this way, DFID strengthens Tanzania’s, already active, ‘Big Society’. Related to this, by investing in civil society organisations, DFID ensures Tanzania civil society continues to be strengthened. / Evidence / Internationally, a growing evidence base exists for the effectiveness of local level accountability interventions including from randomised impact evaluations in Uganda (health clinics) and Madagascar (primary schools). In Uganda, the study proved the impact community monitoring of clinics can have on clinic performance and health care outcomes.[24] The Madagascar study demonstrated improvements in teacher behaviour and test scores as well as showing that bottom up accountability processes can be more effective in improving services than top down reforms.[25] In Tanzania, DFID will promote accountability work nationally, in the districts and in rural areas, to maximise performance improvements in local level service delivery. / Evidence for each step on the logic chain is strong. Public opinion surveys, notably Afrobarometer, demonstrate increasing citizen empowerment but levels of accountability remain low.[26] Good evidence exists for the role citizen action can play in delivering improvements in improved services and respect for rights. This includes an increasing number of randomised impact evaluations[27] and large surveys of multiple interventions.[28] A key emerging finding of the emerging evidence base is the importance of context; interventions from one context cannot necessarily be replicated successfully in others. In aiming to build on recent increases in political accountability and working with local CSOs, DFID will ensure interventions are tailored to local needs. / Past DFID investment in Civil Society in Tanzania, most notably delivering small grants and capacity building through the Foundation have previously yielded a range of impact.[29] As discussed above, investments over the last decade have strengthened civil society, in turn holding the state accountable. The 2007 independent impact assessment of the Foundation’s funded project [30] concluded that “overall more than 60% of assessed grantees were found to have high to very high impact capabilities (in terms of effectiveness, capacity, continuity and legitimacy); 30% had medium score while 10% were found to have poor or bare minimal impact. Results in 2010 included awareness raising around the Land Act and the Ageing Policy of Tanzania which resulted in a decrease in land seizures and increased up take of free healthcare by the elderly respectively. Over the same period, 16,783 citizens were provided with legal aid. During the 2010 election over 700 polling stations were monitored by partner organisations, reducing the risk of electoral fraud. These impacts have been at scale with The Foundation reaching over 2 million beneficiaries in 2010. / During the second half of 2011, the Foundation plans to commission an independent mid-term impact evaluation (MIE). DFID has assessed the scope of the MIE terms of reference and concluded that it will be difficult for the Foundation to genuinely quantify the overall impact of its interventions as no comparator group was set up at the start of the programme and no quantitative monitoring data is currently collected for such a purpose. DFID thinks however that the planned evaluation will be a good opportunity for the Foundation to be able to tell plausible stories about the influence its interventions may have had on its key results areas.
B. Impact and Outcome / The project will contribute toward the following impact – ‘Tanzania is democratically governed and has achieved its 2025 vision in the fight against poverty and a better quality of life for all its citizens’. / The outcome will be that by March 2015 more citizens (especially the poor and marginalized) are empowered to influence and monitor policies that meet the needs of the poor and participate in the budgeting processes for improvement of service delivery in Tanzania. / There is good evidence that the outcome and impact are achievable and this is outlined in Section A.
[1] Secretary of State for International Development Andrew Mitchell’s speech to Oxfam and Policy Exchange at the Royal Social in London, 12pm 3 June 2010
[2] Gaventa, J and Barrett, G (2010) 'So What Difference Does it Make? Mapping the Outcomes of Citizen Engagement', IDS Research Summary of IDS Working Paper 347, Brighton: IDS
[3] FCS Annual Report 2010 another $7.3m was spent on capacity development while funds totalling $42.3m were received.
[4] Afrobarometer’s rigorous survey methodology can be accessed here: http://www.afrobarometer.org/index.php?option=com_content&view=article&id=134&Itemid=30
[5] % of citizens ‘getting together with others to raise an issue’ each year has increased from 59.5% in 2001 to 69% in 2008. Q25c Afrobarometer www.afrobarometer.org
[6] ### Afrobarometer Working Paper 63: Bratton, Michael and Carolyn Logan "Voters But Not Yet Citizens: The Weak Demand for Vertical Accountability in Africa's Unclaimed Democracies." 2006. http://www.afrobarometer.org/index.php?option=com_docman&Itemid=39
[7] % of citizens’ attend a demonstration or protest martch’. Q23c Afrobarometer www.afrobarometer.org
[8] In 2010 Freedom House rated six African states as ‘free’. The mean rate of participation (Afrobarometer Q23b on ‘coming together to raise issues’) in these states, many of which are dominant party regimes, was 51.5%. Tanzania now reaches a rate of 69% participation. www.afrobarometer.org
[9] Afrobarometer 2008
[10] Democratic experiments in Africa Bratton & Van de Walle; Allen 1995 ‘Understanding African Politics’ Review of African Political Economy, 22, 65, pp. 301-320; Bratton & van de Walle 1992 ‘Popular Protest and Political Reform in Africa’ Comparative Politics, 24, 4, pp. 419-442
[11] Afrobarometer 2001 & 2008. Perception in 2008 that Tanzania is a ‘full democracy’ (40%) or a ‘democracy with minor problems’ (34%).
[12] Opinion softened, many of those ‘strongly approving’ of a one-party system are now just ‘approving’. Although many of these citizens still do not outright reject one-party politics this is important progress.
[13] Afrobarometer surveys 2001 & 2008. The overall percentage of those dissatisfied fell by 5% and overall strength of satisfaction also increased by 12%.
[14] The work of Tim Kelsall makes the link between the growth of a more professional civil society and increasing political accountability and consolidated democracy. See Kelsall 2002 ‘Shop windows and smoke-filled rooms: governance and the re-politicisation of Tanzania’ Journal of Modern African Studies, 40, 4, pp. 597 - 619.
[15] Comparable Afrobarometer data has not yet been collected, the last survey was in 2008 and the next survey is expected late 2011/ early 2012.
[16] Samuel Huntingdon’s ‘Two Turnover Test’ Huntington, Samuel P. (1991). Democracy's Third Wave. The Journal of Democracy, 2(2)
[17] There is statistical evidence to suggest that MPs who contributed more to debate in the national Parliament were re-elected. This finding is contested however, significant variations in the level of contributions mean this is not necessarily a statistically reliable finding while the impact disappears when one of the parties is removed from the dataset. Analysis of Who Returned? Performance in the Bunge and MP Re-election Twaweza Policy Brief 2011
[18] These are national figures yet turnout remained high on the Zanzibar Archipelago (2.03% of all voters) at 89% on Unguija and 85% on Pemba. EU Election Observation Mission to Tanzania Final Report October 2010
[19] International Monetary Fund – Policy Support Instrument Second Review April 2011
[20] Draft Country Governance Analysis 2011
[21] Attraction And Retention Of Human Resources In The Public Service Towards Equitable Service Delivery Joint Government of Tanzania and Development Partner Paper General Budget Annual Review 2010 & Uwazi Monitoring Brief 2 - Improving quality in secondary education: Is the money reaching schools?
[22] Uwezo Tanzania – Are our children learning? Annual Learning Assessment Report 2010
[23] An institution is a norm or a ‘rule of the game’. DFID’s work to protect rights impacts individuals aims that respect for these specific rights will become institutionalised or normalised
[24] http://www.povertyactionlab.org/evaluation/community-based-monitoring-primary-healthcare-providers-uganda
[25] http://www.povertyactionlab.org/evaluation/primary-education-management-madagascar
[26] Afrobarometer 2008
[27] http://www.povertyactionlab.org
[28] McGee, R. and Gaventa, J. (2010) 'Review of Impact and Effectiveness of Transparency and Accountability Initiatives’ A Preliminary Mapping of the Evidence Base for Empowerment and Accountability Paper presented to DFID’s Development Policy Committee February 2011
[29] DFID has supported the Foundation since it was established in 2003. The Foundation is one of the options considered in the appraisal of this Business Case. Without biasing the outcome of the appraisal, it is important that the evidence of significant previous investment is reviewed here. This backward look at the Foundation reflects the fact that it has been DFID Tanzania’s largest civil society investment over the last decade.
[30] Impact Assessment and Financial Audit of the FCS Funded Projects By EDI LTD (July 2007)

# Appraisal Case

A. Determining Critical Success Criteria (CSC) / The appraisal will compare three feasible delivery mechanisms for the provision of small grants and institutional strengthening. To achieve this, likely overheads for each option will be modelled based on DFID’s intended level of investment alongside the mechanisms’ potential reach. / Comparison will be based on four critical success criteria. The first is the extent to which the management agent will ensure a strong and consistent focus on CSO delivery of results. The second CSC is cost, this will model the likely overheads associated with delivering a fixed volume of grants and institutional strengthening work. The third is the potential reach of the fund, the capacity of each model to support work outside of Dar es Salaam and in rural areas. Finally, coordination of lesson learning and accountability work between civil society organisations can produce useful synergies, increasing the value for money of DFID’s investment. Thus final criterion is the ability of each model to facilitate CSO coordination. / Each CSC is weighted 1 to 5, where 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention. / CSC Description Weighting (1-5) / 1 Results focus - CSO proposals reviewed, funded and monitored to maximise delivery of clear outputs and outcomes. 5 / 2 Cost - for delivery of small grants and institutional development. 4 / 3 CSOs nationally, including in rural areas are reached. 3 / 4 CSO action nationally is coordinated. 2
B. Feasible options / In addition to the do nothing option, there are three feasible approaches DFID could take to deliver (A) grants and (B) capacity building to civil society organisations nationwide, these are: / Deliver small grants and capacity building through a DFID in-house unit using DFID staff and office space. / Deliver small grants and capacity building through a private sector management agent contracted through a competitive tender process. / Deliver small grants and capacity building through Foundation for Civil Society. This is a pre-existing civil society support mechanism that DFID has an established relationship with. / Do nothing / In the table below: / the quality of evidence for each option is rated as either Strong, Medium or Limited, / the likely impact on climate change and environment is categorised as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Evidence rating Climate change and environment category (A, B, C, D) / 1 There is medium evidence for this option from other DFID programmes (notably Uganda) C risk (low) and B opportunity (medium) / 2 There is medium evidence of this from Tanzania where this has been attempted for larger grants. There is strong evidence from other DFID programmes (notably Mozambique and Ghana) C risk (low) and B opportunity (medium) / 3 There is strong evidence for this option C risk (low) and B opportunity (medium) / 4 There is limited evidence from Tanzania but there is medium evidence from other DFID programmes (notably Malawi) C risk (low/medium) and C opportunity (low) / Option 4, “do nothing” is rated as low to medium risk as there are climate change and environment impacts that need to be addressed and this will fail to be addressed without the engagement of civil society. As options 1-3 are all low risk but provide an opportunity to address climate change and environment including improving the delivery of environmental services, they are therefore expected to have medium positive impact (opportunity) on climate change and environment in Tanzania. Roles that CSOs can play in addressing environment and CC particularly include: i) increasing accountability in the delivery of services including environmental services, ii) increasing accountability in management and use of natural resources, and iii) increasing accountability in the collection and use of revenues collected.
C. Appraisal of options / This appraisal looks at the feasibility and value-for-money of three delivery options for the provision of small grants and capacity development support to small civil society organisations. / Resource Costs of Options / Cost models. In order to make direct cost comparisons models have been developed to assess the overheads needed to deliver a pre-determined investment in small grants and capacity development of £2m per year for four years. The models take into account overhead costs such as staffing, travel, office space, communications and equipment.[31] Further details of these models can be found in Endnotes.[32] / Option 3, delivery through the Foundation for Civil Society (FCS), is the lowest cost option with overheads of 14% on a £2m investment. Option 1, establishing an in-house grant making unit would require more than double the overhead, totalling around 31%.[33] Delivery through a private sector managing agent, Option 2, is the most costly with 33% overheads.
Option Mean Additional Annual Overhead Cost based on £2m investment[34] Year 1 Year 2 Year 3 Year 4 Mean annual overhead costs as a % of £2m per year investment / Option 1: In- House Unit £596,763 £654,403 £577,550 £577,550 £577,550 31% / Option 2: Private Sector Agent £629,750 £765,900 £739,567 £739,567 £739,567 33% / Option 3: Foundation for Civil Society £267,961 £267,961 £267,961 £267,961 £267,961 14% / Option 4: Do Nothing (other than what would be done by other DPs) £0 - / The importance of economies of scale. The significant differential between the options largely reflects the significant economies of scale associated with the Foundation for Civil Society which delivered £4.2m of small grants in 2010 alone. The graph[35] bellow demonstrates significant savings in overhead costs as investments rise. By pooling funding with other donors, DFID can realise these significant savings. / On the other hand, if DFID were to establish a new independent grant making entity, either in-house or using a private sector intermediary these savings would only be realised if DFID could ensure other partners pooled their money through the new mechanism. This is unlikely given that other donors remain committed to the Foundation. In 2011 for instance, six other donor partners have already committed approx $6.6m[36] for 2011/12 period. / Savings associated with established mechanisms. In contrast to the other options, the Foundation (Option 3) is well established and has been able to bring down its overheads from a mean of 21% in the 2003-10 period to 14% in 2010. The decline in overheads can be seen clearly year on year: 31% in 2007, 22% in 2008, 20% in 2009 and 14% in 2010. While these performance gains are also correlated strongly with increasing investments (and thus economies of scale) they can also be attributed to the Foundation becoming a more established organisation, with well developed systems and processes and experienced staff. Newly created entities (Option 1 and 2) could feasibly realise some efficiency gains as they became more established, but the Foundation experience suggests it is likely these savings would be achieved at the back-end of the 4 year funding period. / Costs and negative effects of creating a parallel structure (Option 1 & 2) In-house delivery of grants or using a private sector agent would mean establishing a mechanism that would likely be solely DFID funded. Other donors are likely to continue to put their investments into small grants through the Foundation. It is therefore likely that DFID’s investment of £2 million through an in house mechanism would be equalled and exceeded with other donors providing between £2.5m and £3.7m to the Foundation.[37] By establishing an in-house unit, DFID would effectively be creating a similarly sized parallel structure. In this scenario, DFID’s ability to reach rural areas and organisations outside of Dar es Salaam would be broadly proportional to its investment. However, by going it alone, DFID and other donors would experience a number of additional costs including high upfront investment and new transaction costs, these are analysed below. / The high up front investment needed to reach rural civil society organisations. There is good evidence to suggest that there are significant up front costs associated with the delivery of small grants to CSOs based outside of Tanzania’s large urban centres.[38] Most significantly quality of proposals is often low, even for potentially high impact interventions. Investing in the provision of information to potential applicants and working directly with failed applicants are necessary investments for grant making outside of large urban centres. As an established organisation the Foundation (option 3) has made these investments previously. In contrast, for options 1 and 2 new investments would be required. / There is a delayed return on investments to reach organisations outside of large urban centres. Applicants have to apply and be rejected in order to be targeted and information sessions have to be sequenced due to the remoteness of locations. In a four year project such as this, a significant up-front investment may only yield significant returns, in the form of rural grant making, in the final years of programming or after it is complete. / New transaction costs imposed on both DFID and other donor investments. By establishing a parallel mechanism to the existing Foundation for Civil Society new transaction costs would be imposed on donors. This includes the costs associated with coordinating grant making and establishing separate networks to encourage, often the same, rural organisations to apply. Civil society organisations would also face higher transaction costs by having to apply and report to multiple organisations for the same resource envelope. These costs could be limited by developing common or shared processes and formats, although this would impose costs of their own and undermine the justification for a separate mechanism. / Private sector engagement is more viable with large grants than with small. The high overheads associated with Option 2, using the private sector, reflect the particularly high levels of staff input needed to deliver small grant making. This should be seen in contrast to grant making mechanisms such as the AcT programme which delivers significantly larger grants – the mean grant size of AcT grants is 48 times that of the Foundation grants.[39] While for small grants a private sector agent is the most expensive option, for large grants where specialist knowledge and less staff time per £ of grant is needed, the private sector is often most cost effective. / Additional costs associated with running a mechanism in-house. In-house grant making comes with a number of additional costs to DFID. Basing a unit within the DFID Tanzania office would also be likely to draw in senior management time, both at A1 and SCS level. This would include management time and any political handling associated with the fund. [40] / Do Nothing / The do nothing option i.e. other than what would be done by other DPs - would result in reduction in funding available for small civil society groups from current commitments. Funding to these organisations nationwide ensures accountability for DFID investments made elsewhere. By doing nothing DFID would forfeit these potential performance gains. Small groups also play an important role in guaranteeing that citizen’s rights are respected. / DFID also faces reputational risks with the do nothing option due to her strong international support for empowerment and accountability as well as a local champion who has regularly advocated for the role of CSOs to demand and hold their governments to account. / Benefits of Options / Benefits, potential contribution to impact, are analysed in three areas: (1) the extent to which grants are managed to deliver impact, (2) extent to which additional impact can be accrued from civil society coordination and (3) ability to reach civil society outside of large urban centres, to ensure impact is equitable. Collectively, these three areas will determine the extent to which policy can be effectively influenced. / Managing grants to deliver results / By providing grants in-house (Option 1), DFID would have the opportunity to ensure that partners are directly held accountable for the delivery of impact. This means DFID would not delegate this function, however the direct monitoring of small grants would require a significant investment of staff time. With this option, DFID would have to manage the important need to reduce administration costs against effective monitoring to ensure maximum value for money is delivered. This tension means that there is little evidence of previous in-house civil society funds delivering higher levels of impact than delegated mechanisms.[41] / By delivering grants indirectly, through a private sector management agent (Option 2), DFID would delegate the day to day process of managing grants. Despite this, DFID would remain accountable for achieving results and have to manage the private sector agent accordingly. A contractual arrangement is well set up to achieve this. However, the heterogeneity of impact achieved across a diverse portfolio of small grants means accountability for delivering impact would be time consuming for DFID. By holding grant management directly (Option 1) or delegating it to an organisation with a proven track record (Option 3), and with multiple donors exercising oversight, DFID could take a less time-intensive approach and be confident of impact. In this sense, the private sector option would be weaker than both the in-house and the Foundation for Civil Society options. / For Option 3, DFID has a pre-existing partnership with the Foundation, having participated in its founding in 2003. DFID has worked alongside the Foundation to ensure it meets the changing needs of Tanzanian civil society. / During the implementation of its first strategic plan (2005 – 2008), and the period preceding it, the Foundation focused on building capacity of CSOs. The Foundation’s Annual Reports contain evidence of significant and sustained investments in CSO capacity over the eight years since it was established. There is good evidence of a significant strengthening of civil society over the lifetime of the Foundation.[42] The second strategic plan (2009 – 2013) by the Foundation has focused more directly on the results that a stronger civil society will deliver. The Foundation for Civil Society has been successful in improving its measurement of impact and reach during the first two years of implementation. / The Foundation for Civil Society has refined its grant portfolio under the second strategic plan by developing three ‘result areas’ within which impact is delivered. These are (1) citizens are influencing and monitoring policy processes for the improvement of service delivery; (2) governance and accountability: citizens are aware of their rights and responsibilities and are demanding accountability in the management of public resources and (3) civil society capacity strengthening: civil society is creative, imaginative, effective, sustainable and accountable. / All options would use small grants to deliver a diverse package of results. Aggregating and quantifying this impact is uniformly challenging across all options. The Foundation (Option 3) already meets best practice on this with its ‘result areas’ to facilitate greater aggregation of results. DFID will continue to support innovation in this area and DFID would support the Foundation to recruit a full time results adviser (A2 equivalent) and encourage the Foundation to invest in better baseline data of civil society strength. / Coordinating partners / The creation of an in-house mechanism (Option 1) would limit DFID’s ability to coordinate NGO action to collectively participate in national processes, raise issues and hold the government to account for policy. An in-house unit, unlike other options here, would not be able to take an active organisational role. DFID mandate does not extend to organising collective action and as a donor rather than a Tanzanian organisation, it lacks the legitimacy to do so. / Option 2, contracting a private sector agent, would be able to coordinate action but, again, would suffer a legitimacy gap. Yet by working independently of other donors, DFID would also limit the size of its network for action, particularly in the initial period. / By supporting the Foundation (Option 3), DFID could maximise the potential synergies that result from funding large numbers of organisations across the country. By pooling its investment with other donors and contracting a well established organisation DFID will maximise the number of organisations that can be coordinated. / The Foundation is also the most respected and legitimate option which increases its potential influence over policy. These are benefits accruing from previous DFID investment through the Foundation. The Foundation has supported the building of strong links between Parliamentarians and business through both structured events and informal advocacy. By working to promote high standards for CSOs, through the CSO Excellence Award and development of a CSO Code of Conduct, the Foundation has also built trust in civil society and increased potential CSO influence. / Ensuring a national reach / As discussed under ‘costs’, Option 1 and 2 would require higher upfront investment than Option 3 and returns would likely be delayed until the later part of the programme. / As an established organisation with a strong rural focus, the Foundation (Option 3) would deliver more immediate results in this area than Options 1 and 2. The Foundation already has a genuinely national reach with applications received and grants given to organisations in every one of Tanzania’s 26 regions in 2010. 78% of grants and 66% of the total value of grants was invested outside of Dar es Salaam in 2010. In addition, by 2010 40% of grants were implemented in rural areas and 21% of grants were given to organisations based in rural areas. Given the significant challenges for grant making outside of large urban areas these figures are impressive. The trend is also positive with growth in rural grant making over the last 3 years and a target of 75% of grants being delivered in rural areas by 2013. / By pooling finances with other donors (Option 3) DFID will also continue to realise economies of scale in its rural outreach. Establishing a parallel, independent delivery mechanism (Options 1 and 2) would also impose new coordination costs on DFID, civil society and other donors. / Additional Benefits / An additional strength of the in-house model (Option 1) is that it allows direct DFID engagement with NGO partners. There are a number of benefits to this including allowing DFID to receive input from organisations with a good understanding of trends and issues in different parts of the country. Given that this input can be achieved in other ways, it seems unlikely that this benefit is worth the significantly increased overhead associated with in-house grant making. / The scale of the Foundation (option 3) has previously enabled it to support a large number of cross cutting initiatives including on gender, disability, HIV/AIDS and the environment. While all options could potentially build linkages between the different sectors DFID works in, the Foundation’s experience of effective grant making in this area is an important asset. / Summary Appraisal of Options in VfM terms / Option Costs (Quantitative and Qualitative) / over project lifetime Benefits (Quantitative and Qualitative) Benefits in VfM terms[1] Risks and assumptions Evidence rating / Option 1: In- house unit Small grants: £4.04m / Capacity Building: £1.57m / Overheads: £2.39m Direct management of results / Strengthened link between CSOs and DFID Direct contact with grantees allows realisation of synergies with other DFID projects such as AcT Significant reputational risk with DFID’s profile directly impacted by grantees conduct / Risk that secretariat is not adequately staffed to monitor grants There is medium evidence of managing grants in this way / Option 2: Private sector agent Small grants: £3.95m / Capacity Building: £1.53m / Overheads: £2.52m Independence from DFID means coordination of Civil Society action is possible Contract established with clear success criteria to ensure delivery of results Risk the private sector agent is unwilling to effectively organise collective action `There is medium evidence for the management of small grants by private sector entities / Option 3: Foundation for Civil Society Small grants: £4.99m / Capacity Building: £1.57m / Overheads: £1.07m FCS has an established reach including outside of large urban centres / Coordination of grantees to engage in collective advocacy and to build trust Significant economies of scale – by pooling funds with other donors, overheads effectively halved . / Realising previous investment made in establishing grant making outside of large urban centres and establishing a strong reputation Withdrawal of other donor’s funding reduces VfM of option There is strong evidence for this. FCS has an established track record of delivery / Option 4: Do nothing Zero direct cost, Funds directed to other areas Significant reputation risk given DFID’s role in promoting the empowerment and accountability agenda Medium evidence from elsewhere / Balance of Costs and Benefit & Optimal Design of the Intervention / Overall Option 3, the Foundation, offers both the lowest costs and the most significant benefits. / As an established fund, the Foundation has the significant advantage of avoiding the substantial start up cost associated with providing small grants to organisations outside of large urban centres. In contrast with Options 1 and 2, Option 3 allows DFID to continue to exploit economies of scale associated with pooling funds with other donors. / Based upon the strong relationship between scale of investment and overheads, the Foundation is the most financially competitive option. By working through the Foundation, utilising the significant economies of scale, an additional £1.36m of DFID’s £8m investment[43] will be invested in grants and capacity building, when compared to Option 1 (In-house mechanism).[44] When compared to Option 2, a private sector managing agent, an additional £1.52m will be invested over the 4 years. This represents good value for money / The most significant benefits are also expected from the Foundation (Option 3) which has a proven record of delivering grants nationwide, including extensive investments in rural areas and outside of Dar es Salaam. Investing in the Foundation will enable coordination of civil society action due to both the organisation of small grants through a single mechanism and the Foundation’s legitimacy and experience in this area. The Foundation also has a strong record of delivering results in its work, particularly around civil society strengthening, advocacy and its legal work to establish precedents. / The Foundation already represents best practice for small grant making. DFID will invest further in measuring impact in a systematic matter by supporting the Foundation to hire a Results Advisor. It is expected that the Adviser would further strengthen the Foundation’s emphasis on identifying results delivered by grantees. The competitive nature of the application processes and short length of grants (1-2 years) means a strengthened emphasis on results would be quickly reflected in the grant portfolio.
D. Comparison of options
The same weighting is used as for CSC above. The score ranges from 1-5, where 1 is low contribution and 5 is high contribution, based on the relative contribution to the success of the intervention. / Analysis of options against Critical Success Criteria (CSC) / Option 1 – in house Option 2 - private Option 3 - FCS / CSC Weight (1-5) Score / (1-5) Weighted Score Score Weighted Score Score Weighted Score / 1 5 4 20 4 20 4 20 / 2 4 3 12 2 8 5 20 / 3 3 2 6 2 6 4 12 / 4 2 1 2 3 6 4 8 / Totals 35 35 60 / Option Selected / Based on the evidence set out above, Option 3 – supporting civil society through the Foundation for Civil Society is the preferred option / In line with the Foundation Strategic Plan 2009 – 2013, the Foundation will continue to deliver results in the following areas: / Policy Engagement: Citizens able to influence and monitor policy processes for progressive improvement of service delivery. The main purpose of the Foundation is the empowerment of Tanzanians to effectively participate in policy processes, especially those related to poverty reduction, – such as the National Strategy for Growth and Poverty Reduction (NSGRP). The Foundation will provide grants and other capacity support to CSOs that focuses on: / Increasing involvement and participation of communities, especially women, children, people with disabilities, poor people, vulnerable and marginalised groups, in setting out priorities for policies formulation at all levels; / Increasing citizens’ access to information (on laws, government plans, budget and public policy) through translation, popularization and dissemination especially targeting remote, under-served and marginalized areas/groups; / Increasing citizens’ awareness on gender equality, translating gender policies and enabling participation of women and members of other marginalised groups in setting priorities for policy formulation at all levels; / Governance and Accountability: Citizens are aware of their rights and responsibilities, and able to demand accountability from public resources. The Foundation will give emphasis to supporting CSOs that enable citizens to participate in planning and budgeting processes at local and national levels. This will ensure that budget processes and government plans are relevant to citizens’ needs. The Foundation will also support CSOs that enable citizens to realize their rights. Key focus will include supporting CSOs to: / Increase citizens’ involvement in local government planning and budgeting cycles; / Empower citizens to ensure local government plans, budget allocations and expenditures are made publicly available; / Enable citizens realise their right to access information on social service delivery and local government expenditure; / Increase the proportion of citizens that realize their human, constitutional and legal rights; / Increase citizens participation in democratic processes in Tanzania / Civil Society Capacity Strengthening: A creative, imaginative, effective, sustainable and accountable civil society sector. A key thrust of The Foundation is to work for a strong civil society that is sustainable, creative, imaginative and widely accountable. The Foundation will use its capacity building resources to ensure the following: / Strengthen the organizational and institutional capacity of new CSOs especially in the areas of: fund raising, report writing, development of strategic plans, financial management, M&E and gender mainstreaming; / Strengthen and develop CSOs capacity to network and engage with Parliament, Members of Parliament and the Private Sector to ensure that voices of the citizens are heard by these groups; / Capacity of the Foundation: Enhanced capacity of the Foundation to deliver high quality services efficiently and effectively. The Foundation seeks to ensure that it retains its current strong position as a grant making and capacity building organization. It will continue to develop and enhance its capacity and competence to deliver excellent services while ensuring the sustainability of its operations. The Foundation will measure its success by meeting the following criteria: / Promote rural outreach and ensure at least 75% of support targeting communities outside Dar es Salaam and other major town and cities; / Overhead costs maintained at or bellow 18% / Develop and implement a Human Resources Development (HRD) Plan to ensure effective staff recruitment, development, retention and replacement; / Continue the Foundation’s adherence to International Financial Reporting Standards (IFRS) and conduct an annual financial audit by an international auditor; / Mainstream gender, disability, HIV/AIDS, and the environment in the Foundation’s operations / The Foundation will provide around 1,200 grants during the 4 years of DFID funding, number of grants directly attributable to DFID depends on the balance of grant types and the scale of other donor funding (which reduces overheads). / Further details on the Foundation is provided on the attached Institutional Appraisal (Annex 1) / Final Category for Climate and Environment Category Assessment (C) / This intervention is rated as category C: No / Low risk but medium opportunity. Most of expected outputs under this intervention (refer to page 5) will also have a positive impact on i) delivery of environmental services ii) management and use of natural resources, and iii) the collection and use of revenues collected.
E. Measures to be used or developed to assess value for money / In summary the programme will deliver value for money by: / using the least cost delivery mechanism; / maximising the resources available for civil society grants; / exploiting existing arrangements to minimise start up time; / reducing transaction costs in a basket funding arrangement for development partners; / Value for money will be monitored and assessed during implementation through a combination of measures that include log-frame targets, programme management costs, and the detailed objectives that are set in the award of individual civil society grants. For example, we will continue to monitor overhead costs whilst FCS’s recruitment of a new Results Advisor will develop other metrics that will assess VfM in relation to policy influencing.
[31] The FCS model is based on actual data from FCS and so includes all costs additional to grant making and capacity development.
[32] The model developed to compare each option assumes an investment of £1.92m of which £1.5m would be grants and £0.42m would be invested in capacity development. It assumes 379 grants would be handled over a year (new, multi year and closing grants). The model assumes a spread of grant sizes (29% of annual investment value in grants between £31,000 and £52,000, 53% in grants £19,000-£31,000, 17% in grants £100 to 19,000 and 0.05% of value in registration grants £0 to £100).. Given that even single year grants are disbursed over at least 2 financial years, the average annual disbursement per grant is often below the lower figure for each funding window. The grant numbers and value-mix for this model is based on the number of grants delivered by each £2m of existing DFID investment in small grant making through the Foundation. Each option is appraised against this model of small grant making. NB: 379 is calculated as follows: -in 2010 FCS spent £4,172,396 to deliver a total of 1,053 grants -The model assumes £1.5m is disbursed a year which is 35.95% of the 2010 figure (£4.172m). -Therefore the total number of grants dealt with a year (new, continued, ended) is 35.95% of 1053 which is 379
[33] This calculation does not include start up costs so overheads would likely be higher
[34] £1.5m would be grants and £0.42m would be invested in capacity development
[35] Economies of Scale. Each data point on the graph represents one year of FCS operation. Funding has varied year on year so the points are not consecutive through time (further underlining the strength of the correlation)
[36] This includes $900,000 from Swiss Development Cooperation, $2.5m from Netherlands, $250 from American Jewish World Service, $878,000 carried over from late disbursements in 2010 and $1,900,000 from Danida. Further funds totalling around $1m are also expected from Comic Relief and $1m from Norway.
[37] £2.5m has been the mean investment in FCS, less DFID contributions, over the previous 8 year period (2003-10). The figure represents investment by seven other donors. The scale of future investment is made unclear by the repositioning by Irish Aid and the Netherlands which have been major contributors of $5.0m and $8.9m respectively over the 8 year period. £3.7m is quoted as a possible higher figure based on expected, non DFID, commitments for 2010.
[38] Foundation for Civil Society Annual Report 2010
[39] Mean AcT grant = £611,000; mean FCS grant = £12,575
[40] The cost centre for an in house mechanism would be DFID Tanzania. Some small indirect costs could be incurred centrally, in Palace Street and East Kilbride, but are not included in this model.
[41] Seen most notably in the Uganda Civil Society Umbrella Funds I and II (in-house) and the Deepening Democracy Programme Uganda (external). Direct or indirect management was not a critical factor for the delivery of impact.
[42] Compare analysis of civil society in 2002 to 2010 for instance
[1] To include i) synergies between pillars/with other approved interventions ii) un-locking/leveraging private finance and/or technical capacity iii) economies of scale iv) likely timeframe for VfM realisation (short, medium, long-term) v) good potential for accrual of benefits after the programme lifetime etc.
[43] Over 4 years
[44] Savings over a 4 year period

# Commercial Case

## Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The Accountable Grant mechanism will be used to support the Foundation for Civil Society. The Foundation qualifies to receive accountable grant as it is registered as a non-profit making organization. / The Foundation is responsible for implementation of its Strategic Plan which DFID will support. To deliver its activities, the Foundation manages a pooled basket arrangement governed by the MoU. The MoU sets out partnership principles between funders and the Foundation, and clearly states that ‘all procurement of goods and services will be done in accordance with the Foundation’s Financial Procedures and Procurement Guidelines’[45]. / Section 2.4 of the MoU further commits the Foundation to ensure VfM in the utilisation of the funding made available by the Funding Partners.
B. Value for money through procurement / The Procurement Questionnaire completed by the Foundation in June 2011 and the Systems Based Audit[46] conducted by SIDA in September 2010 show that the Foundation procurement procedures and systems follow best practice. / The assessment of the systems of the Foundation by SIDA observed the presence and operation of sound systems and a functioning of management and control of activities among which include a sound financial management system, procurement system, functioning procurement committee, existence of budgetary system, clearly stipulated criteria for grantees selection, legislation, policies and programme strategies that govern the direction of the Foundation. / There is evidence that the Foundation is aware of the need to demonstrate efficiency and deliver value for money from its operations. It regularly monitors its overhead costs. This has been reduced from 21% in 2003 down to 14% in 2010. / The nature of the Foundation’s work means that it does not undertake large procurement exercises. The Foundation does not therefore have a discrete procurement function or responsible Procurement Officer. Responsibility for procurement is delegated to budget holders. The Foundation’s approach to procurement is set out clearly in the Financial and Accounts Manual and there is a robust budget monitoring process in place to mitigate the risk of inappropriate expenditure not being detected. / The Foundation has an adequate system for procurement for goods and services. It has a procurement committee – five staff members are appointed each year by the Executive Director representing all the departments. The committee is chaired by a member of management team. The procurement committee major functions are to establish and oversee procurement and tendering procedures; scrutinise requests and applications for tendering; and advice on stock control practices. The procurement guideline has five guiding principles: cost effectiveness; transparency and documentation; non-discrimination, zero tolerance for corruption and accountability. Competitive bidding is done. For non-regular purchases exceeding a value of USD 1,000 but less than USD 10,000, the Foundation seek independent quotations from no less than 3 independent suppliers. All large purchases exceeding USD 20,000 require a tender; bids must be sought from at least 5 suppliers. Purchases exceeding USD 40,000 require an open tender advertised in major national news papers. All tender awards are endorsed by the Finance and Legal Committee. / As a grant giving institutions, selection of grantees, disbursement and monitoring of grants are the core business of the Foundation. The SIDA’s systems-based audit confirmed that the Foundation’s grants making processes and procedures are a) transparent; b) follow pre-determined assessment criteria; c) analyses grantees organizational, financial and management capacity; and d) include an assessment of whether planned activities consider value for money. / One of the gaps identified by SIDA’s system-based audit was the absence of internal audit function at the Foundation. The Foundation has already responded to this finding through the recruitment of a full time internal auditor (IA) since December 2010. Key responsibilities for the IA include: to review the effectiveness of the Foundation’s internal controls, processes and procedures; and to conduct internal audit on various functions undertaken by the Foundation (including the procurement function). / In order to further strengthen its procurement system, the Foundation has confirmed that it will address any gaps as identified by DFID’s VfM Questionnaire. We will track their actions as part of our M&E arrangements.
[45] Paragraph 3.1 MoU between Foundation for Civil Society and the Founding Partners, January 2011
[46] The purpose of the systems-based assessment was to analyse whether FCS’s internal management and control systems guarantee the quality and accuracy of their documentation and, at an overall level, evaluating whether FCS has appropriate systems and routines for managing her organisation towards operational goals and contributing to the fulfilment of the goals of Swedish development cooperation. The assessment was done by Gracemary Bange, the Programme Administrator for SIDA for the period from 21st June, 2010 to 07th August, 2010.

# Financial Case

A. How much it will cost / DFID will contribute a total of £8m over 4 years, 2011/2 – 2014/5. £2m will be provided per year. This funding is in line with the DFID Tanzania operational plan. / The total budget for the Foundation over a four year period 2011/12 – 2014/15 is estimated at USD 52 million. This budget was calculated on the basis of a detailed implementation plan, produced annually to implement a five year strategic plan. DFID contribution of £8m (approx $13m) will constitute 25% - 33% of all the Foundation’s annual spend. / Currently, the financing structure is as detailed bellow. Indicative commitments from the DPs planning to support the Foundation over the next four year period is as follows (all figures in million USDs): / Donor 2011/12 2012/13 2013/14 2014/15 / UK 3.25 3.25 3.25 3.25 / Swiss 0.9 0.9 0.9 tbc / Denmark 1.9 1.9 1.9 tbc / AJWS 0.25 0.25 0.25 tbc / Comic Relief 1.0 1.0 1.0 tbc / Sweden 0.0 5.0 5.0 tbc / Netherlands 2.5 0 0 0 / Norway 1.0 1.0 1.0 tbc / Total 9.8 12.3 12.3 / DFID % 33% 26% 26% / In 2010, Sweden frontloaded a two years support to the Foundation at a level of $4.5 million. Canada plans to extend its support to the Foundation but is yet to confirm the financial figures.
B. How it will be funded: capital/programme/admin / The full amount will be drawn from the DFID Tanzania programme resource allocation for Governance as outlined in the DFID Tanzania Operational Plan
C. How funds will be paid out / Since the Foundation is a non-for-profit organisation and has no other sources of income to enable the disbursement of grants to local civil society organizations, (with annual budget in excess of $10 million), DFID will make funds available to the Foundation at quarterly intervals in advance, upon request. The Foundation shall provide a forecast expenditure requirement for the quarter to be covered by the advance. Subsequent expenditure will only be given once the Foundation has provided a statement of actual expenditure incurred during the previous quarter. / The Accountable Grant Letter further requires that designated officer at the Foundation must ‘certify that all the amounts detailed in the advance request have been expended under the grant and in accordance with the terms and conditions outlined in AG Letter’. DFID will fully ensure that this requirement is fulfilled.
D. How expenditure will be monitored, reported, and accounted for / MoU between the Foundation and funding partners is in place and sets out how expenditure from DFID (and other donors) will be monitored, reported and accounted for : / The Foundation will provide the Funding Partners with a semi-annual financial and activities progress report in relation to annual plan and budget covering the period of January to June, by latest end of August each year; / The Foundation will also provide the Funding Partners with a comprehensive annual narrative and financial report on activities covering the full financial year by end of May each year. This financial report will cover the extent to which the objectives, outcomes and outputs have been achieved as compared to what was planned, income and expenditure as compared to what was budgeted, problems encountered, lessons learned and success stories of grantees. Any major deviations will be explained and necessary corrective actions outlined. Any major problem or risk that may affect the successful implementation of an activity will also be identified, as well as any proposed substantial modification to any program. / Within three months after the completion of each financial year, an internationally recognised independent auditors appointed by the Foundation’s Annual General Meeting will carry out a financial audit of the Foundation. If needs arises, Funding Partners may ask to contribute to the scope of the audit to take into account specific information needs. The audited financial report should account for foreign exchange rate gains/losses and interest earned. / Funding Partners reserve the benefit to engage the service of Auditors of their own choice and expenses to examine the Foundation’s finances. In such a situation the Foundation will provide maximum co-operation to the exercise. / The Foundation will maintain in good condition all financial documentation for a period of not less than seven (7) years.

# Management Case

A. Oversight / The Governance Structures of the Foundation consist of three layers: the Members, the Board and the Secretariat / The Members of the Foundation are the highest authority in all matters related to the running of the organization. They exercise their authority mainly through the Annual General Meeting (AGM) or an extraordinary meeting. During the Annual General Meetings, Members receive and approve the Annual Report and Audited Financial Statements of the Foundation, appoint the Board of Directors including the appointment of the Board Chair, appoint the Auditors of the Foundation, and approve any changes to the Memorandum and Articles of Association of the Foundation, Vision, Mission and long term plans of the Foundation. / The Board of Directors is the second principle organ of the Foundation. It provides regular oversight to the activities of the Foundation. It approves higher level policy and changes or additions to rules, regulations and procedures of the Foundation, providing final approval of annual plans and budgets for endorsement at the AGM, review of annual reports for approval by the AGM, review and discussion of the financial report with the auditors and presenting audited financial statements for approval by the AGM; and the recruitment and performance management of the Executive Director. / The implementation of the day to day functions of the Foundation is vested in its Secretariat led by the Executive Director who reports to the Board of Directors. / The Foundation’s accountability and partnership principles with donors have been defined in the MoU. Donors review and scrutinize the performance of the Foundation through: a) bi-annual consultative meetings; b) reality check visits (minimum of two visits per year) to directly meet with beneficiaries, local officials and other stakeholders; and c) reviewing and approving annual plans, budget and implementation reports
B. Management / The DFID lead advisor for this programme is an A2 Governance Adviser. He will be overall in charge of this project. He will be responsible for management and oversight of all technical and policy work of the project. He will represent DFID Tanzania in the Foundation – DPs meetings and DPs Joint Basket Meetings. He will be reporting to the Governance Team Leader. Climate Change Advisor will provide technical support as and when required on any environmental and climate change issues. / The Deputy Programme Manager (Governance Team) will be DFID project Officer for this project. They will be responsible with all project administration. They will ensure that DFID project cycle management are followed i.e. Financial reports compliance, administrative functions and Audit requirements. / The Foundation is responsible for implementation of its Strategic Plan which DFID funding will support. The Foundation manages the pooled basket fund supporting delivery of its activities. Eight development partners – DFID, AJWS, Comic Relief, Swiss, Netherlands, CIDA, SIDA and Norway – are contributing to the basket fund and have signed a Memorandum of Understanding (MoU) that governs the partnership between funders and the Foundation.
C. Conditionality / Not applicable.
D. Monitoring and Evaluation / The Foundation has a Monitoring and Evaluation Framework that aims to ensure the relevance, effectiveness, efficiency and accountability of its programmes and grants. The Framework set out indicators of success, results to be achieved, means of verification and frequency of data collection. The M & E Framework has been approved by the Foundation’s Board. Logframe in DFID format will draw information from the Foundation’s Monitoring and Evaluation Framework. / The Foundation Monitoring Procedures / The Foundation produces quarterly reports that track activity and budget implementation as outlined in the annual plan of operation, as well as adherence to its rules, regulations and guidelines. Quarterly reports are for internal use to assist the Board and Management of the Foundation to ensure compliance with and achievement of best practices. / The Foundation has refined its grant portfolio under the second strategic plan by developing three ‘result areas’ within which impact is delivered. These are: / citizens are influencing and monitoring policy processes for the improvement of service delivery; / citizens are aware of their rights and responsibilities and are demanding accountability in the management of public resources; and / civil society capacity strengthening: civil society is creative, imaginative, effective, sustainable and accountable. / The Foundation produces a half year implementation report (financial and narrative) that mainly provides the Board and the Funders with information on the Foundation’s high level operational performance e.g. funds disbursements to grantees; applications received, processed and approved; donors disbursement; training and outreach events by the Foundation, etc. The report highlights how the Foundation is meetings its operational targets and draw attention to key challenges, lessons and experiences. / By May each year, the Foundation produces its annual implementation (financial and narrative) report. This report is much more detailed and contains information on the Foundation’s annual operational performance in relation to established plans – i.e. what the Foundation staffs have been able to achieve in terms of grants making function, capacity building of CSOs, outreach activities and monitoring, auditing, procurement, human resources and general administration and management of the organization. The second and main part of the annual report focuses on providing information on progress being made by the Foundation grantees towards implementing their funded interventions. It makes an attempt to report on number and types of beneficiaries reached under each of the three results areas above, major types of interventions done, success stories, challenges and lessons. (NB: the Foundation receives quarterly reports from grantees and uses this information to produce its annual implementation report). / The Foundation Programme Evaluation / The Foundation planned evaluation activities include a mid term and end of term impact evaluation by an independent consultant to ensure the Foundation is meeting its objectives. / During the second half of 2011, the Foundation plans to commission an independent mid-term impact evaluation (MIE). DFID has assessed the scope of the MIE ToR and concluded that it will be difficult for the Foundation to genuinely evaluate the impact of its interventions as no comparator group was set up at the start of the programme and no quantitative monitoring data is currently collected for such a purpose. DFID thinks however that the planned evaluation will be a good opportunity for the Foundation to be able to tell plausible stories about the influence its interventions may have had on its key results areas. / An end of term evaluation is planned in 2014. According to the Foundation Monitoring and Evaluation Framework, the end of term evaluation will seek to answer the following questions: / To what extent have the citizen been empowered to realize their rights and engage in policy processes that enhance their quality of life through the Foundation’s interventions? / To what extent do the CSO’s activities meet beneficiaries’ needs? Are the activities relevant in addressing poverty? What types of activities cause more impact and why? / What is the evidence of CSOs improved capacity - technical capacity, managerial capacity and financial management - in relation to the Foundation interventions? What has changed/improved in terms of the CSO’s capacity to design, implement and improve community’s life as a result of support received? / To what extent are the CSOs capable of sustaining their activities beyond the support being provided by the Foundation? / To what extent did the community members participate in the CSOs activities? Who participated, e.g. vulnerable groups, poorest of the poor? How were they involved? / What are the effects of the activities carried out by grant recipients to the community? What are the potential impacts? Any impact on climate change and environment? What has been contributed by the grants in reducing poverty at the community level? / As noted above, DFID’s review of the Foundation’s current M & E framework concluded that it will be difficult for the Foundation to genuinely quantify the overall impact of its interventions as no comparator group was set up at the start of the programme and no quantitative monitoring data is currently collected for such a purpose. DFID plans to support the Foundation to address this challenge through supporting the recruitment of a full time Results Advisor (equivalent of DFID A2) that, among other things, will work and assist the Foundation to develop the required baselines and robust a monitoring and evaluation plan to enable a proper evaluation of the programme by 2014.
E. Risk Assessment / Overall, the risks of this project not achieving its purpose should be seen as low, and is supported by the following overall analysis: / Risks Probability of Occurring (L,M,H) Impact on Success / (L,M,H) Mitigating Actions / External political / environment / 1. Space for CSO action is reduced, either formally through restrictive legislation, or informally through lower levels of state responsiveness L H DFID will mitigate this through investing in a new programme to strengthen horizontal accountability, between Parliament and the Executive, and vertical accountability to citizens. Continued DFID investment in FCS helps to support local accountability processes and doing so creates a further safeguard. / 3. Political influence undermines the governance & management of FCS L M FCS Members and Board of Directors are carefully screened at selection for party political bias, and there are sufficient checks & balances in the functioning of these structures to curb individual influence; / FCS will continue to foster an open, non-threatening relationship with GoT and politicians through events such as the Annual CSOs Forum and periodic Consultations with Members of Parliament and House of Representatives / External financial / environment / 4. Competing grant-making programmes attract funding away from the FCS L M Financial resource envelope available for civil society is increasing. By continuing to improve its systems, services and demonstration of results, the FCS will remain ahead of the game in offering a reliable, unique investment vehicle for building civil society capacity. FCS has also started to attract non-bilateral DPs and currently have two – Comic Relief and American Jewish World Service. FCS will continue to actively court new funders. / 5. Funders reduce or fail to provide agreed predictable funding to FCS L H The 6 core funders have agreed (via an MoU) to provide predictable funding into a ‘basket’ .Through the Funders Group, the FCS will report regularly on its performance and sustain the confidence of its funders. / DFID continuing its engagement in FCS and supporting a further strengthening of the FCS’s focus on results. In doing so DFID will support FCS to secure additional investment as other donors increase their emphasis on outcomes / FCS governance / structures / 7. Members and Board of Directors fail to adequately discharge their duties L M In the appointment of the new Members (owners) and Board of Directors, the FCS test comprehensively for suitability and commitment at recruitment stage, and provide a structured induction programme. Continuing membership will be tightly linked to attendance at meetings. A clearer delineation in the functions of the Members and Board has been established, setting clear expectations of the new membership. / DFID and other DPs continues to monitors and assess commitment of the Board members through participation in the AGM / FCS operations / 9. Professional malpractice in the grant selection cycle L/M M The FCS has a zero tolerance approach to corruption. The FCS has further strengthened its grant selection procedures to strengthen oversight of the system. It has revised several policies and procedures to minimise petty corruption, including establishing an independent Complaints Handling Mechanism, a Conflict of Interest Policy, a Code of Conduct with Grantees, and a Communication Campaign against corruption. FCS has also set up an Internal Audit function (from Dec 2010) to tighten its internal control systems / 10. Financial mismanagement L H The assessment of the systems of the FCS by SIDA (2010) observed the presence and operation of “sound systems and a functioning of management and control of activities among which include a sound financial management system, procurement system, functioning procurement committee, existence of budgetary system, clearly stipulated criteria for grantees selection, legislation, policies, strategies that govern the direction of the FCS”. FCS has also set up an Internal Audit function (from Dec 2010) to tighten its internal control systems / 11 Inability to demonstrate results due to inadequate capacity and complexity around monitoring a small grants portfolio of over 700 projects L/M H The FCS will increase contact with grantees and monitoring of grants by: specifying more clearly the desired outputs and outcomes from individual grants and ensuring grantees report against these; / FCS is planning to increase staff and financial resources devoted to M&E; / DFID support to the recruitment of a Results Advisor (A2 equivalent) will further strengthen FCS results and monitoring systems.
F. Results and Benefits Management / The logical framework for the 4 year period is attached.