Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to Civil Society in Tanzania: Foundation for Civil Society Programme
Programme Value: £8.8m		Review Date: July 2014
Programme Code:	Start Date: June 2011	End Date: March 2015

Summary of Programme Performance
Year	2011	2012	2013
Programme Score	A	A+	A+
Risk Rating	Low	Low	Low

Summary of progress and lessons learnt since last review

FCS supports very many small CSOs across Tanzania and has continued to record higher performance during 2013. It was able to receive and process 3007 applications on time, of which 545 were approved for funding. This brought the number of on-going projects being supported by FCS by Dec 2013 to 1,067. Through FCS-supported interventions, over 6.79 million beneficiaries were reached with different types of information on their rights, roles and responsibilities. Other key achievements are detailed under the output scores below. Overall, FCS continues to demonstrate strong performance and is meeting most of its key milestones.

During 2013, FCS reviewed and developed its strategic plan for 2014 – 2018. Through this process, FCS re-confirmed the validity of its vision and mission and appropriate fit with the current context in Tanzania. Among other areas, the new plan seeks to strengthen CSOs role in peace maintenance and conflict resolution. In recent years, Tanzania has witnessed waves of conflicts between farmers and pastoralists over land and water resources utilization; tension between Christians and Muslims; and tension between ordinary citizens and state organs (especially in areas rich in natural resources – wildlife, forests, minerals and oil/gas).

The FCS’s new strategic plan also shows increased focus on supporting interventions that will promote gender equality and women’s empowerment, not only as human rights, but also because they are a pathway to achieving sustainable development as advocated in Tanzania’s Vision 2025, National Strategy for Growth and Poverty Reduction (MKUKUTA) and Big Results Now. Through its support to CSOs, the FCS will ensure that women’s voices are heard at all levels to influence decisions that affect their future and make informed choices over use their rights, resources and opportunities.

The new FCS strategic plan will inform DFID’s next support to FCS for years 2015 to 2018.

Summary of recommendations for the next year

Key FCS Staff Transitions: DFID needs to effectively monitor any potential reputational risk that might be associated with the planned transition of the FCS’s Executive Director at the end of 2014. DFID will specifically assess the implication of this transition for results achievements and profile of the FCS.

Auditing of Grantees: FCS needs to share with DFID in a timely manner, every six months, the findings of its grantees audit reports, specifically identifying and quantifying all cases of funds misuse, abuse or fraud and clearly setting out measures to recover potential losses to DFID.

Systems Audit of FCS: FCS has commissioned independent firm (KPMG) to carry out a systems audit of its internal controls and processes. FCS needs to share this report with DFID. DFIDT will upwardly share this report with Internal Audit Unit in UK to solicit their technical assessment of the key findings and assess whether there is a need for further due diligence as DFIDT develops a new Business Case for support to FCS during the second half of 2015.

DFID will need to ensure that better synergies are established between its support to FCS to promote citizens’ civic competence and the upcoming Democratic Governance programme. Design team for the DG programme will specifically be requested to explore this element further.

DFID will invite the outgoing FCS CEO to make an office wide presentation on FCS’s new strategic plan as well as FCS’s model, key lessons and plans/thinking going forward. This presentation will be made during Oct/Nov to also provide new Head of DFID Tanzania familiarity with one of our key partners in supporting local CSOs in Tanzania

FCS will need to investigate further the reasons for lack of progress under the risk management variable (refers to chart under output 4) and develop specific measures and strategies to address identifiable gaps.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:	Logframe

Summary of programme
The UK is providing £8.8m to support Civil Society Organizations (CSOs) in Tanzania through the Foundation for Civil Society (FCS). This support aims to ensure that more citizens (especially the poor and marginalized) are empowered to realize their rights and engage in change process that enhances their quality of life. Through FCS support, citizens are enabled to monitor policies that address their needs and participate in demanding for improvement of service delivery in Tanzania. This support is an extension of a programme that started in 2009.

FCS is a Tanzanian non-profit making company that provides grants to local CSOs in Tanzania since 2003. Its vision is ‘A Tanzania where citizens are empowered to realise their rights and engage in change processes that enhance their quality of life’. Its mission is to empower citizens through the provision of grants, facilitating linkages and enabling a culture of ongoing learning to civil society. It is being governed by independent Board and has a secretariat being led by Executive Director. DFID support to FCS is through an Accountable Grant Letter.

This intervention seeks to deliver the following outputs: a) Citizens are more aware of their civic rights and responsibilities; b) Ability of CSOs and citizens to participate and influence policies and budgeting processes is strengthened; c) Increased CSOs involvement in promoting rights of minority groups - persons with disabilities and pastoralists, and marginalized groups e.g. women and girls; d) Strengthened CSOs organizational capacity and effectiveness; and e) Foundation for Civil Society delivers high quality services and is efficiently and effectively managed and governed.

During 2013, the total FCS spends was USD 9.76 million. UK support accounted for 34% of this spend. Other funders were: Swiss, Denmark, Norway, Comic Relief and American Jewish World Service. Others were Trade Mark EA, ILO and IRC

Results to be achieved by this programme by 2015 includes

- Two million men and women enabled by DFID to access quality and user friendly information on services, entitlements and rights
- 150 new CSOs have strengthened their organizational and institutional capacity, especially in the areas of: resource mobilization, report writing, strategic planning, financial management and M&E
- 200 CSOs trained to demand greater accountability and transparency from governments, with 75 CSOs effectively monitoring budgets and decision-making processes at national and district levels
- 200 CSOs trained to mainstream gender equality in their organizations and interventions and at least 50% showing evidence of the impact of their work on promoting gender equality.
- 100 Disabled People’s Organizations (DPOs) receive grants and capacity building support to better promote rights of their members
- Annual CSO Forum bringing together CSO representatives to promote learning, networking and sharing of lessons
- Annual CSO Exhibition at the National Assembly (Dodoma) and House of Representatives (Zanzibar) to facilitate consultations between civil society representatives and Members of Parliament – a platform for mutual learning, exchange and advocacy
- Strengthened capacity of the Foundation for Civil Society to properly manage and deliver small grants to civil society organizations and showing evidence of improvements in the area of results monitoring and reporting.

Context:
A major review of the Constitution of the United Republic of Tanzania was put in place in 2012. Most of 2013 was spent by the Constitutional Review Commission (CRC) gathering and analysing the public’s views and compiling a draft constitution - the 2nd and final draft constitution was submitted by CRC by Dec 2013. The constitution review process has been the focus of a lot of citizen input, CSO activity and very high media coverage. While the first stage of the review process as led by the CRC was characterized as being more inclusive and citizen-focused, the second stage – Constituent Assembly (CA) - has been dominated by party politics and control, with the unresolved issue of the structure and form of the Union polarizing the whole process. The extent to which the new mother law can deliver benefits for ordinary citizens - in terms of economic prosperity based on clear access to resources e.g. land and protection of minority rights - is yet to be seen. There are also observations that the ongoing absence of key opposition groups (popularly known as UKAWA) in the CA will effectively make CA unable to conclude its business due to lack of required quorum to pass any resolution.
Indications of government responsiveness that were observed during 2013 included: a) a major cabinet reshuffle in response to the 2013 Controller and Auditor General’s report in May 2013, and again in Dec 2013 after operation tokomeza was called off; b) the budget session was further rescheduled in a way which allows for greater opposition scrutiny; c) the Big Results Now initiative was designed with support from different parts of government and the ruling party, to deliver better public services.

Citizens are increasingly dissatisfied with the performance of the economy. The Views of the People (VOP) report for 2012 (by REPOA) provided a comprehensive assessment of Tanzanians’ knowledge and attitudes towards key public policies contained in MKUKUTA. VOP found that, while many Tanzanians see substantial progress since independence in creating social and economic infrastructure, many still lack remunerative work, adequate housing, and access to basic services, especially clean water. The majority complained that their standard of living has been seriously eroded by inflation; most see youth unemployment as a major problem.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The outcome of the programme is “more citizens are more empowered to participate, influence and monitor pro-poor policies and budgeting processes for improvement of services in Tanzania by 2015.” To achieve this outcome, FCS interventions are focusing on three key results areas (KRA) namely:

- Policy Engagement: Citizens are able to influence and monitor policy processes
- Governance and Accountability: Citizens are aware of their rights and responsibilities, and able to demand accountability from public resources
- Civil Society Capacity Strengthening: Having in place a creative, imaginative, effective, sustainable and accountable civil society sector

FCS’s own assessment of its achievements of outcome during the year under review is showing that FCS is meeting most of its outcome indicators as outlined here under:

Key Results Area (KRA)	Outcome Indicators	Annual Target	Achievement
KRA 1: Policy Engagement	OUTCOME (1) Proportion of citizens saying that they have influenced a policy	100%*	87.86%**
	OUTCOME (2) Percentage of citizens saying that they make a difference by publicly expressing their views on local issues that affect them has increased from 53% to 65% by 2013	65%	87.76%**
KRA 2- Governance and Accountability.	Outcome(1) Proportion of citizens expressing satisfaction on the quality of delivered basic services by the government institutions (increased from 44% in 2007 to 60% in 2013)	60%	54.55%**
KRA 3- Civil Society Capacity Strengthening	OUTCOME (1) Increased proportion of citizens trust of CSOs/CSOs officials from 51% to 70% (55%-2010, 60%-2011, 65%-2012, 70%-2013)	70%	59%civicus 2013
	OUTCOME (2) Percentage increase of grantee with audited accounts from 31.46% in 2009 to 50% in 2013 (Milestone: 2009-31.5%, 2010-35%, 2011-40%, 2012-45%, 2013-50%)	50%	54.3%
	OUTCOME (3) Percentage of CSOs producing annual report and circulating to stakeholders from 54% in 2009 to 100% by 2013.	100%	79.77%**
	OUTCOME (4) Proportion of FCS supported CSOs with overall impact capability increased from 55% in 2007 to 70% by 2013 (Milestone: 2007-55%, 2011-63%, 2013-70%)	70%	85%
KRA 4- Capacity of the Foundation	OUTCOME (1) Percentage of grantees who are very satisfied or satisfied with FCS services	90%	73%
	OUTCOME (2) Percentage of CSOs supported by FCS that implement projects in rural areas	75%	51%

Note: ** data collected through a survey done by the FCS. Methodology used was an online survey using QuestionPro survey software. Purposive sampling approach was used and the survey was sent out to 1300 respondents composed of grantees and non-grantees (but organizations that have applied for grants from FCS at least once) out of which 632 respondents responded to the survey.

Overall output score and description: A+.

FCS’s overall performance during the period under review has remained strong. See more details under each output below.

Key lessons
A fast-growing young and urban population and widening access to media through expansion of local FM radio and use of mobile devices are increasingly contributing towards making populations in Tanzania better informed. Local CSOs are positively utilizing these opportunities to better organize citizens and ensure their demands are heard by the state. Recent expansion of access to secondary schooling is also contributing to enabling more youths to become more active citizens. There are indications that these enabling factors are increasingly breaking down a culture of silence and fear that has characterized many ordinary Tanzanians for quite sometimes.

FCS is a mature grant-making local entity with the ability to provide both funding and tailor-made organisational support to many smaller and diverse CSOs across the country (in every district). It has a good local knowledge of the CSO sector and is well regarded by government, private sector, donors and general society. Senior staff performance, especially the Executive Director, has remained to be a key strength of the FCS. After nine years of solid performance, the current ED will resign by Dec 2014. This transition provides FCS with the opportunity to identify and recruit another vibrant ED to effectively lead and consolidate the gains of the organisation. This transition might also come with challenges if not handled properly. DFID will continue to closely monitor all risks and challenges associated with this transition.

FCS continued to receive fewer applications from CSOs with a rural focus than expected. This is largely due to absence of credible and fundable proposals coming through. DFID next support will explore ways to better stimulate more rural CSOs/populations to engage more with FCS. The next DFID support to FCS will also explore better ways for supporting a systematic citizen monitoring mechanism e.g. through tools championed by Twaweza or other similar tools to better capture citizen changes as a results of awareness creation or civic competence building etc.

Key actions
See recommendations section on page 1.

Has the Logframe been updated since the last review? No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	More citizens are more aware of their civic rights and responsibilities
Output number per LF		1	Output Score	A++
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

A = Attributable to DFID at 34%; C = Contributory
Indicator(s)	Milestones	Progress
# and quality of new CSOs supported to promote civic rights (A)	15	104
# of citizens enabled to access information on services, rights (A)	1m	2.36m
# of new CSOs supported to increase citizens involvement in local government planning and budgeting exercises (A)	15	5

Key Points
During the year, FCS reached a total of 6.79 million beneficiaries with different types of information on their rights, roles and responsibilities. Out of the total number of citizens that were reached by FCS, 2.36 million citizens are directly attributable to DFID, as UK’s support to FCS during 2013 was equivalent to 34% of its total budget. Number of citizens reached through FCS and attributable to DFID will contribute to DFID corporate indicator reporting (including DFIDT Operational Plan target). Number of citizens reached through FCS has been arrived as follows: a) a total of 674,628 citizens (49% being women) were directly reached by 470 grantees who received support from FCS and implemented activities across districts and village levels in Tanzania; b) 6.12 million citizens are estimated as those reached by FCS and grantees work through use of radio, newspapers, television and dissemination of large numbers of printed materials.

The main focus of FCS’s civic empowerment activities during 2013 was the on-going constitutional review process. FCS was the single main source of support towards citizens and CSOs across the country to increase their understanding, participation and contribution of citizens’ voice to the new constitution.

FCS funded a number of organizations to implement different activities that aim at educating the community on the 1977 Constitution of the United Republic of Tanzania and encourage them to engage in the formulation of the new Constitution. Some of the main activities funded were on; training courses, reprinting of the constitution in the normal format, reprinting of the constitution in Braille format, TV programs, radio programs, newspaper articles, and public dialogues.

195,000 (63,881 Female) citizens were enabled to directly participate in constitutional review discussions through FCS support to 308 CSOs (252 CSOs facilitated constitution forums in their respective areas while 56 organizations facilitated citizens’ dialogues on constitution-related issues). Indirect beneficiaries were estimated at 3,789,773 people. Other benefits obtained through FCS support included printing and distributing of 150,000 and 3,000 copies of the Constitution of the United Republic of Tanzania in ordinary format and Braille respectively.

Overall, most CSOs/citizens supported CRC recommendations for three-tier government, a lean cabinet and proposed limitations of the power of the president. There was a particular call by CSOs/citizens wanting the new constitution to specifically come up with better proposals on how ordinary citizens will equitably benefit from the country’s abundant natural resources including gas, oil, minerals, forests and water.

Other examples of progress under this output include:

Southern Africa Extension Unit implemented a project in Coast Region and contributed towards deepening citizens’ understanding of civic rights and corruption, and mobilized citizens’ support to promote accountability in the project area. As a result three anti-corruption committees composed of 12 people each (6 men and 6 women) were established to follow up complaints of community members against abuse of civic rights and corruption. Through the follow-up made by these committees, 3 corruption cases were taken to court. A total of 16,500 citizens in Kibaha, Mkuranga, and Bagamoyo participated in project activities.

Summary of responses to issues raised in previous annual reviews (where relevant)

FCS increased its support to CSOs to participate in the constitution review process as per the previous annual review recommendation. This was in the form of a cost extension in December 2013 to the sum of £800,000 (10% of total project value) specifically earmarked for such activities.

Recommendations

DFID will need to ensure that better synergies are established between its support to FCS to promote citizens civic competence and the upcoming Democratic Governance programme. Design team for the DG programme will specifically be requested to explore this element further.

Output Title	Increased CSOs role in contributing to improved transparency at a local level i.e. how LGAs/GoT allocate and utilize public resources
Output number per LF		2	Output Score	A++
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

A = Attributable to DFID at 34%; C = Contributory
Indicator(s)	Milestones	Progress
# of new CSOs supported to implement PETS (A)	9	22
# of new CSOs supported to implement SAM (A)	5	15

Key Points
During the period under review, the Foundation managed to approve and support 64 projects that promoted improved public resource transparency through the implementation of public expenditure tracking surveys (PETS), and another 45 that focused on social accountability monitoring (SAM), in a number of sectors such as education, health, agriculture, infrastructure and marketing. These interventions were successful in mobilizing over 298,947 people to participate and ensure proper utilization of public resources at the local level. The aims of PETS/SAM interventions were to increase transparency and accountability in utilization of public resources at all levels.

Major activities performed by supported CSOs included: conducting training on PETS/SAM, conducting training on planning and budgeting processes, formulating PETS/SAM committees, conducting actual PETS/SAM exercises, conducting feedback meetings on PETS/SAM findings, production and sensitization of communities on the use of notice boards for displaying different information, producing and disseminating various publications on PETS/SAM, planning and budgeting processes at all levels, conducting radio and television programs on social accountability and public expenditure tracking in the community, as well as conducting meetings with government officials and citizens on transparency and utilisation of public resources in the country. Issues addressed by CSOs were on: the importance of citizens’ engagement in budgeting, how to influence district councils to involve community members in Planning & Budgeting processes, planning process and the use of Opportunities and Obstacles to Development (O&OD) as the tool for people’s involvement in understanding LGA’s budget process. Following the mentioned interventions, community leaders started to be more accountable by posting information on planning and budgeting on notice boards.

Some of the outcomes from the PETS/SAM interventions as reported by FCS grantees included the following:
- 84 new notice boards were produced and used for displaying different information, mostly at the village and ward levels, through sensitisation and activities by Tabora Advocacy Centre for Development (TACEDE);
- Kijogoo Group for Community Development in Morogoro region implemented PETS activities in the water sector. The project was implemented in Gairo division in Morogoro region covering five wards of Kibedya, Chakwale, Msingisi, Iyogwe and Gairo. The PETS team observed that 12 water wells that were supposed to be drilled in 2010-2012 were not drilled, a water pump was not bought in Meshughuli village, water pumps were missing/stolen in two other villages, 2 tanks with capacity of carrying 90m3 of water in Gairo wards are not used, and renovations of water wells were done in Mlimba-Meshugi and Gairo wards. They further noted that a water project worth Tshs 6.7 billion in Gairo ward was not implemented, income and expenditure reports on funds allocated in water sector are not displayed, there is a lack of water committees in different areas and finally that the price of water per bucket is not standard as it differs from on area to another. Some of achievements achieved after the PETS exercise include the following:

  - The Gairo District Council has set aside funds for drilling 12 water wells in Gairo division.
  - The price for a bucket of water is now uniform in all five wards of Gairo:20 shillings per 20 litres of water, down from 50 shillings.
  - 13 water user committees have now been established, i.e. in all villages of Gairo ward.
  - Renovations were carried out in many water wells and hence the government has managed to rescue 580 litres of water that would otherwise have been wasted.
  - A Water officer was fired as he was misusing his position by making water available in the area for 4 hours instead of 12 hours and he was selling water to the water businessman for Tshs. 1,000 and 15,000 per gallon.
  - Citizens of Chakwale ward have fired the existing water committee following misuse of funds collected from selling water totalling Tshs. 5,000,0000/=

Summary of responses to issues raised in previous annual reviews (where relevant)

Nil

Recommendations

Nil

Output Title	Increased CSO involvement in empowering women, and addressing gender inequalities and issues affecting other vulnerable groups
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

A = Attributable to DFID at 34%; C = Contributory
Indicator(s)	Milestones	Progress
# and quality of new CSOs supported to sensitize women on their rights (C)	36	36
% of women enabled to take up leadership positions in CSOs/communities (C)	50%	36%
# and quality of CSOs supported to address issues affecting people with disability, pastoralists and other minority groups (A)	20	55

Key Points
Examples of progress from supported FCS grantees include the following:

Women Rights:

  - Society for Women Aids in Africa (SWAA) managed to lobby the Mvomero District Development Committee to establish the District Education Fund for improving levels of education, specifically targeting female students who are reported to be worse affected (by poor education levels). As a result, the formed committee is in the process of establishing hostels for girls in each secondary school across the district;

  - The Pastoralist Women’s Council (PWC) from Ngorongoro has managed to establish special committees for advocating for women’s rights in eleven wards;

  - As a result of training conducted by Upendo Disadvantage Partnership, two widows managed to repossess their properties which were left to them by their deceased husbands. The organisation has also managed to reach 2,332 people (1184 men and 1148 women) in six wards of Coast Region through training sessions and public dialogue on land and women rights.

Gender Based Violence (GBV)

  - 90 cases of Gender Based Violence (79 in Tabora and 11 in Zanzibar) were reported to authorities following awareness creation on the same as conducted by FCS grantees - the Association of Women Busy Workers (Tabora) and Zanzibar Association for People with Development Disability Centre

  - AFNET - a CSO based in Dodoma – continued to empower communities in Iringa and Dodoma to change attitudes towards GBV, including addressing issues related to female genital mutilation (FGM). The project focused on mobilizing community members to increase their awareness on GBV and willingness to report such cases to the authorities. Some achievements by AFNET included: community-based facilitators on GBV identified, trained and involved in carrying out sensitization activities with different groups in the communities; more than 50,000 people in Iringa and Dodoma reached through GBV-focused and FGM-focused interventions; 18,000 copies of print materials (including newsletters, leaflets and posters) printed and disseminated; over 100 community leaders - ward executive officers, village executive officers, police officers and magistrates - trained on GBV and FGM issues; 33 journalists trained and empowered on GBV and FGM issues. Training of journalists has led to an increase in reporting of FGM and GBV issues The project has also been able to put in place a data bank on media reporting on GBV and FGM issues as well as ensuring that victims of GBV/FGM who need legal aid are linked to legal aid organizations. Leaders from faith-based organizations were also sensitized. As a result of this project, six GBV cases were reported to the police and primary courts and hearings are in progress; two cases were resolved by ward tribunals; one case was resolved by the ward executive officer; and one case was resolved by the district education officer;

Elderly Rights: Saidia Wazee Karagwe, (CSO in Kagera Region), managed to increase the capacity of 18,750 older people (8,976 men and 9,774 women) to participate in various developmental processes through advocacy and lobbying for their rights and entitlements. One of the key results following the activities is the formulation of seven Older People’s Self Advocates Groups. So far, these groups have succeeded in meeting with the ward councillors, District Commissioner (DC) and District Police Commanding Officer to address the increased incidents of human rights violations such as raping, assaulting and killings of old persons. These efforts have resulted in decreased incidents of violations of the elderly’s rights. More elderly people are also reported to have accessed free medical services as per the National Ageing Policy of 2003;

Land Rights: During the period under review, the Foundation for Civil Society supported a total of 35 organizations to conduct awareness training to citizens on land conflict resolution, Land Policy, Land Acts No. 4 and No. 5 of 1999, land rights and governance, capacity building for women on their rights to make decisions related to land, and dissemination of land tribunals guidelines. Awareness creation was carried out using various methods, including television and radio talk shows. Some examples of results include:

Reduced land-related conflicts: Following awareness training on land conflict resolution and land laws, cases of land conflict were resolved at the ward councils due to availability of written guidelines for land conflict resolution, as shown in Table 1:

  Table 1: Summary of Land Conflict Status in two project areas

Area	Filed Conflicts	Resolved	Sent to Land Tribunal	Sent to Court
Bunda	20	11	5	4
Shinyanga	131	61	40	30
Total	151	72	45	34

Source: The Foundation Grantees reports 2013

This suggests that more than half of all filed land-related conflicts were peacefully resolved	outside tribunals and court

540 women in Shinyanga Rural and 213 women in Kiteto/Longido were supported to file applications for land ownership for the first time. FCS will track the success of their applications for the next reporting round.

13 Village Land Councils (1 in Kisarawe and 12 in Morogoro) were established, trained and are successfully functioning.

Persons with Disability (PWD): During 2013, FCS provided support to over 162 Disabled People Organizations (DPOs) (55 attributable to DFID) that implemented interventions to address issues affecting persons with disability. Examples of results generated included:

- Increased number of children with disabilities who are in schools and madrasa in 7 districts of Zanzibar as a result of Community Based Rehabilitation Program (CBR) implemented by the Zanzibar Association of People with Disabilities (UWZ). Out of 2,386 children (1,044 Female) with different disabilities reached, 1,670 children (1,084 Female) are now in schools;
- Number of schools under Inclusive Education program has increased from 86 (2010) to 119 (2013) and enrolment of children with special needs have increased from 4500 (2012) to 5002 (2013) through engagement spearheaded by the Zanzibar Centre for Development Disabled;

480 people (255 male and 225 female) were trained on sign language in Arusha in order to enable easy communication among the deaf and the community. Beneficiaries included 173 parents, 68 police officers, 102 guardians, 79 teachers and 58 government officials;

CHAVITA (Association for the Deaf) HQ conducted Training of Trainers for 34 (16 male and 18 female) sign language instructors from 19 districts (Bunda, Kibaha, Tanga Urban, Singida Urban, Kinondoni, Kigoma, Nyamagana, Morogoro Urban, Bukoba, Moshi, Mtwara Urban, Arusha Urban, Songea, Mbeya Urban, Lindi, Dodoma urban, Tabora Urban, Shinyanga urban, and Iringa Urban);

People with Developmental Disability, in collaboration with Ministry of Health and Zanzibar Centre for Development Disabled, established 6 mobile health centres in Unguja (4) and Pemba (2) to provide special health services to PWDs. A total of 253 (147 Female) PWDs obtained health services close to their vicinity;

Moshi municipal council has incorporated budget for the PWDs in the financial year 2014/2015 and a total of Tsh.4,000,000/- was set aside for purchasing appliances (white canes, wheelchairs, caps and glasses to protect albinos from sun rays, cleaning appliances for the mentally retarded, lotions to protect albinos from skin cancer, stationery and Braille papers) for people with disabilities in Moshi municipal. Furthermore, the council plans to spend TSh 72 million to construct a hostel for the 172 students with special needs in Moshi municipal in the financial year 2014/2015;

Five (5) districts (Mahenge, Ulanga, Mvomero, Kilombero and Kilosa) of Morogoro region have employed one sign language interpreter each following sensitization and advocacy campaigns on the laws governing people with disability conducted by Tanzania Cheshire Foundation;

Increased access to information regarding rights of PWD was also provided through printing and distribution of various information, education and communication (IEC) materials including National Disability Act 2010, UN Convention on the rights of the persons with disability 2006 in popular version, Zanzibar Disability Policy 2004, and The persons with disabilities (Rights and Privileges) Act 2006. Amongst the recipients were parents/guardians of children with disability, Government officials, Police officers, Teachers, Religious leaders and ordinary community members.

Summary of responses to issues raised in previous annual reviews (where relevant)

Strengthening results reporting was identified as key issue that FCS needs to address. There have been some improvements but more can be done.

Recommendations

DFID will need to ensure that there are better synergies between its supports to FCS work around rights (e.g. GBV, elderly rights etc) with its support to the Human Rights Programme through the Legal Aid Facility (LAF)

Output Title	Strengthened CSOs organizational capacity and policy engagement effectiveness
Output number per LF		4	Output Score	A+
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

A = Attributable to DFID at 34%; C = Contributory
Indicator(s)	Milestones	Progress
Number and quality of new CSOs supported on institutional and organizational capacity (A)	100	107
% of policy dialogues with active participation of CSOs (C)	80%	82%
Proportion of FCS supported CSOs with improved overall impact capability(C)	70%	85%

Key Points
Organizational Capacity: During the year we facilitated 314 CSOs to undertake self-capacity assessment with a view to enable them to better understand their strengths and areas for improvement. Through use of capacity benchmarks, supported CSOs were able to see how their organisational capacities change overtime. Generally, looking at the average capacity scores, on average, supported grantees have continued to perform better. Areas of community engagement, external stakeholder relations, strategy and mission, as well as governance, have recorded good performance, reaching the scores of 4.4, 4.2, 4.0 and 3.8 respectively. A range of factors have contributed to those achievements, including: technical backstopping support, training, ability to network and increasing learning within the sector and improving partnerships between CSOs and other stakeholders.

Figure: Organizational Capacty Assessment
Capacity Scores
Capacity Assessment Variables
Source: FCS Organizational Capacity Assessment Report 2013

Organisational Capacity of supported CSOs is improving over time. Comparing organisational capacity assessment scores for year 2009 and 2013, there is improved capacity as explained by increased variable scores as depicted in figure below. Improved capacity is particularly noted on community engagement and external stakeholders relations. Availability of skilled human resources remains a challenge as explained by only a slight improvement over the five years period, but the biggest concern is risk management, which has seen no improvement over the last 5 years. FCS will need to investigate further the reasons for lack of progress under the risk management variable and develop specific measures and strategies to address identifiable gaps.

Figure: Organizational Capacity Scores Compared - 2009 vs 2013
Capacity Scores
Capacity Assessment Variables
Source: FCS Organizational Capacity Assessment Report 2013

Learning and Development Services: Through a systematic approach towards strengthening the capacity of supported CSOs, a total of 1261 representatives from 852 CSOs were involved in various institutional and capacity building interventions to address identified organisational capacity gaps, as follows:

Manage Your Grant trainings: compulsory training for each CSO receiving grants from FCS. A total of 748 (261 female) participants from 374 CSOs (48 DPOs) participated in the training sessions;

Tailor-made training: a total of six modules in 15 sessions of tailormade training were conducted for 513 (119 female) CSO representatives from 478 CSOs. The training modules included: Organizational Development, Monitoring, Evaluation and Report Writing, Fundraising, Financial Management, Project management and Social Accountability Monitoring;

Policy Dialogues
In efforts to build a stronger, more focused sector, FCS organised platforms for dialogues between CSOs and government officials, MPs and other officials. They included:

a) East Africa Community: In its attempt to enhance citizens’ awareness and engagement on East African Regional Integration Agenda, The Foundation organized the second East African Civil Society Forum with the objective of providing a platform for Tanzanian CSOs to reflect on their role and actual engagement in strengthening the East African Regional Integration and in mainstreaming the East African Regional Integration agenda at national level.

Discussions were around the State of EAC, Challenges of Regional Integration and the respective roles of CSOs and Media in addressing Regional Integration challenges. A total of 130 participants comprising CSO representatives from Tanzania and a few others from each of theEAC partner states, academicians and private sector representatives had the opportunity to reflect on how the East African Community can benefit small scale farmers and how Education and Natural Resources can be used to strengthen East African Regional Integration.
The outcomes of the forum include:

- Increased awareness among Tanzania CSOs on the East African Regional Integration agenda and dialogue framework, which is likely to enhance participation of CSOs in issues related to EAC processes at regional and national levels.
- Increased positive image of CSOs at national and regional levels
- Improved working relationships, partnerships and networking amongst regional CSOs on issues related to the East African Regional Integration.
- Establishment of East African Civil Society Forum- Tanzania Chapter, a platform to coordinate CSOs’ engagement in the EAC agenda at national and regional levels.

b) Dialogue with Legislature: During 2013, 5 policy dialogues were held with legislatures. Three dialogues were held in Zanzibar and the focus was on the Local Government Reforms in Zanzibar and the need to have in place the Local Government Act. The Foundation supported two other dialogues between CSOs and Members of Parliament in Dodoma, one between CSOs and the Parliamentary Committee on Public Accounts. In this dialogue, contentious issues of revenue collection from extractive industries (mineral, oil and gas) were discussed.

Another dialogue was between CSOs and the Parliamentary Committee on Agriculture, Livestock and Water development. The meeting was geared to lobbying the Government to increase the agricultural budget by at least ten percent, in line with the Maputo Declaration of 2003, calling for African countries to increase agricultural budgets in their respective countries to 10% by 2010.

The outcomes of the dialogues are increased CSOs influence in policy issues. For instance, in Zanzibar, CSOs have been able to push for Local Government Reform Policy and now the Revolutionary Government of Zanzibar is developing the Local Government Reform Act, following this year’s dialogue.

e) CSOs Annual Forum 2013 FCS’s CSO Annual forum is a platform that brings together CSO representatives, Government representatives, academicians and private sector representatives to reflect on issues of national interest,while enhancing learning within the sector. As a way to celebrate the Foundation’s 10th Anniversary, the 2013 Annual Forum’s focus was on sharing and celebrating the Impact and Achievements of not only the Foundation, but also the Civil Society Sector as a whole over the past 10 years. The Forum also provided opportunities to award and celebrate success recorded by the Best-performing CSOs in serving citizens.

Key issues that were discussed were:The Impact and Achievements recorded by CSOs in areas of Governance and Accountability, Policy Engagement, Achievements recorded by CSOs in issues related to People with Disabilities, Women, Children, Orphans and vulnerable groups. Achievements recorded in Institutional Capacity Strengthening and CSOs engagement in Constitutional processes were also shared. Further, the participants had the opportunity to advise the Foundation on key issues to focus on for the next 10 years.

Generally, it was shared during the forum that brought together about 360 (163 female) people, that the sector and individual Civil Society Organisations have grown over the past 10 years. CSOs have contributed to improved policies and having pro-poor policies, enhanced governance practices, and transparency and accountability at local and national levels. Accountability within the sector is on the rise as well. CSOs have also had a positive impact in servicing and advocating for issues of people with disabilities, women, children, orphans and other vulnerable groups.
The major achievements of the forum included:

- Increased learning and networking within the sector
- Increased recognition and appreciation of the role of FCS in empowering CSOs and citizens to engage in change processes
- Increased positive image of the role of CSOs in promoting good governance and development processes.

Summary of responses to issues raised in previous annual reviews (where relevant)
Nil

Recommendations
FCS will need to investigate further the reasons for lack of progress under the risk management variable and develop specific measures and strategies to address identifiable gaps.

Output Title	Foundation for Civil Society is delivering high quality services and is efficiently and effectively managed and governed
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

A = Attributable to DFID at 34%; C = Contributory
Indicator(s)	Milestones	Progress
% of CSOs supported to implement projects in the rural areas(C)	75%	51%
number of monitoring visits to grantees (C)	450	465
number of applications received and processed on time (C)	2000	3307

Key Points
FCS continued to receive fewer applications from CSOs with a rural focus than expected. This is largely due to absence of credible and fundable proposals coming through. DFID next support will explore ways to better stimulate more rural CSOs/populations to engage more with FCS
FCS has made good progress in ensuring that the organization and services provided are of high quality and are efficiently and effectively managed and governed. Results attained under this output include the following:
- 522 support visits were conducted compared to the annual target of conducting 500 visits. The visits were aimed at providing support to grantees on various technical areas so as to enable them to improve their performance;
- In the year 2013, 10 information sessions were conducted at district level; this is equal to 100% of the annual target. These sessions were conducted in following districts/regions; Mpanda, Sumbawanga, Shinyanga municipality, Bariadi, Kigoma, Simiyu, Unguja, Geita and Babati. Each session had an average of 50 participants. The main purpose of conducting these sessions is to attract prospective grants applicants from these rural areas.
- By December 2013, a total of 3,307 grant applications were received and processed, surpassing the annual target by 65%;
- During the year, a total of 677 organisations were visited throughout the country for due diligence exercises. Of those, 291 (43%) were approved for funding. Of those approved, 148 are in rural while 143 are in urban areas.
In 2013, FCS reviewed and developed its new strategic plan for 2014 – 2018. This plan builds on the lessons from previous strategic plans and seeks to ensure that Civil Society Sector becomes a meaningful contributor in ensuring the implementation and attainment of post-2015 development Agenda, Tanzania Vision 2025, MKUKUTA 2 and Tanzania Big Result Now objectives. The new plan has identified seven key results areas that will underpin FCS support to CSOs in coming years. They include: improved social wellbeing; improved livelihoods; Citizens are influencing and monitoring policy processes for the improvement of service delivery; and Citizens are aware of their rights and responsibilities and are demanding accountability in the management of public resources. Other KRAs includes: Strengthened Civil Society role in peace maintenance and conflict resolution; Civil society is creative, imaginative, effective, sustainable and accountable; and The Foundation is delivering high quality services efficiently and effectively.
This new strategic plan will form the basis for DFID’s planned continued support to FCS, for which a business case is planned in 2015.
Another key FCS organizational development is the planned transition of its Executive Director by the end of 2014. The current CEO has served FCS over the past nine years and is well regarded for his exemplary high performance and delivery. The Board of Directors of the FCS has already initiated a search process and adverts were recently printed in key print media.

Summary of responses to issues raised in previous annual reviews (where relevant)

Nil

Recommendations

DFID will invite the outgoing FCS CEO to make an office-wide presentation on FCS’s new strategic plan as well as FCS’s model, key lessons and plans/thinking going forward. This presentation will be made during Oct/Nov to also provide the new Head of DFID Tanzania familiarity with one of our key partners in supporting local CSOs in Tanzania.

Key FCS Staff Transitions: DFID needs to effectively monitor any potential reputational risk that might be associated with the planned transition of the FCS’s Executive Director during end of 2014. DFID will specifically assess the implication of this transition for results achievements and profile of the FCS.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
FCS’ total management/overhead costs were 20% of its total spend during 2013. This level of spend is in line with the MoU agreement which FCS have signed with all its basket donors. Over 56% of these costs were payroll related (salaries, pension, post-employment benefits and skill development levy). Another 26% were spent on outreach, grantees audit/monitoring and office rent. FCS had 34 employees during 2013.

VfM performance compared to the original VfM proposition in the business case
The FCS programme business case identified the following value for money measures that are to be tracked each year.

Economy:
During 2013, the programme management/overhead costs by FCS were $2.19m compared to $1.96m in 2012, representing an increase of 11%. The main driver of this increase is related to personnel costs, as noted above, 54% of these costs were payroll related. During 2013, FCS recruited six new staff to fill in vacant position as well as promoting three others to assume different responsibilities. We have reviewed FCS’ current salary structure and it compares well with the market. Quality of FCS management remains good and was able to deliver all key targets satisfactorily.

FCS’ training and capacity development interventions to its grantees were $1.87m (or 17% of its total spend) during 2013. As reflected under Output 4 above, there is evidence that capacity of supported CSOs is improving over time and this is a good indication that trainings are representing a good value for money. Grants accounted for $6.74m (63% of the remainder of the total spend). The scale and reach of results being delivered and its direct impact on lives of beneficiaries proves that grants are also good value for money. Most grantees make effective use of volunteers to deliver its core activities and this also add to good value for money.

Efficiency
The overall assessment shows that FCS is scoring highly on almost all output indicators. FCS programme has also managed to reach more people than expected through use of radio and other mass media which can reach more people than one-to-one conversations so the cost per person reached is a lot lower.

Effectiveness:
The 2012 Social Return on Investment (SRoI) assessment of FCS interventions to assess effectiveness of its capacity building component concluded that for every dollar of investment by FCS it gives a return of 61 dollars. No new assessment was done during 2013 therefore as for 2012 are still relevant. Overall, outputs are contributing well into the achievement of the outcomes. Example: 86.76% of citizens said that they made a difference by publicly expressing their views on local issues that affect them (compared to a target of 65%). We have also noted that while most targets for output indicators were achieved and some overachieved, targets for 6 outcome indicators out of 9 were below their annual targets. This is explained by a fact that FCS was overly optimistic in setting its outcome targets which now needs to be revised to reflect the programme reality.

Assessment of whether the programme continues to represent value for money
The FCS programme has continued to offer value for money. Results achieved, including reaching over 6.79 million citizens with different types of information and direct funding of 1439 CSOs illustrate the reach/scale of FCS interventions. A wide range of beneficiaries including persons with disabilities, pastoralists, youth, women etc were reached and supported. Examples of outcome of the FCS intervention that demonstrate good VfM including 90 cases of Gender Based Violence that were reported to authorities following awareness creation by FCS grantees. The average annual management costs are at 16.8%[1] of the average total annual spending in line with the approved Business Case and furthermore with the impressive SROI ratio of 1:61.
[1] Management/Overhead costs for other DFIDT funded programmes were: a) 14.5% for Accountability in Tanzania (AcT) programme; b) 22% for Tanzania Media Fund (TMF) programme; and c) 25% for Twaweza programme.

Quality of financial management
In 2013 FCS continued to adhere to the agreed reporting requirements. Both narrative and financial annual reports for 2013 were submitted in time to enable timely scrutiny of invoices, disbursements of funds, making follow up discussions and carrying out this annual review. DFID approved a GBP 800,000 cost extension for FCS in October 2013 to support increased citizen participation in the current constitutional review process which was not part of the initial agreement, making DFID’s total contribution to FCS increase from GBP 8,000,000 to GBP 8,800,000. FCS had an overall spending performance of 71% against FCS 2013 work plan and budget and of 100% against DFID annual forecasts. DFID’s final disbursement to FCS was made in April 2014 as the programme ends in September 2015.

KPMG audited FCS financial statements for the year ending 31st December 2013 and produced a clean audit opinion. FCS met all financial reporting requirements in accordance with international financial reporting standards. FCS also commissioned KPMG to carry out a systems audit to provide assurance that it has a robust grant management system in line with the recommendations by the audit report.

Moreover, FCS has an internal audit unit that serves to ensure systematic management and control of risks, which includes monitoring of value for money and detection of fraud. During 2013 the FCS internal audit unit carried out audit of 302 grantees out of a target of 290, post-audit follow-up on 47 grantees on issues raised and recommendations made by the grantee audits, as well as due diligence of 677 grant applicants, out of which 291 were approved for funding.

Date of last narrative financial report	22/04/2014
Date of last audited annual statement	15/06/2014

E: RISK (½ page)

Overall risk rating: Low
Overall, the risks of FCS’ project not achieving its outputs should be seen as low. This is largely due to the nature of specific interventions and the current operating environment in Tanzania where at local and national levels CSOs continue to operate without state interference. CSOs have managed to effectively increase citizens’ engagement in the constitutional review process

Risk of funds not being used as intended

FCS implements a small grant scheme where applicants are supposed to provide detailed activity-based budgeting. FCS monitors and ensures proper funds utilization by grantees through:

Mandatory Manage Your Grant (MYG) training course. This course is designed to enhance the capacity of selected CSOs to properly manage their grants. A total of 748 (261 Female) participants representing 373 CSOs (48 DPOs) were trained during the period under review;

Auditing of Grantees: a sample of 302 grantees were audited by external auditors. Scope of auditing included bank reconciliation, expenditure management, proper coding, supporting documents, record keeping and cash book maintenance. Other areas include: adherence to financial management regulations and procurement procedures, and how the accounting system operates, including segregation of duties, payment vouchers etc.

Due diligence: A total number of 677 prospective grantees were visited after the initial screening. Out of those, 291 (43%) were approved for funding

FCS responded adequately to instances and allegations of corruption through the year. During period under review, DFID received a whistle-blower email with a list of allegations of fraud/corruption against FCS and its key senior staff. Allegations were centred on FCS due diligence (DD) of EQUIP grantees. DFID informed and worked with CFWU in UK in collecting and analysing all evidence and responses from FCS to respond to the specific allegations. EQUIP carried out a quality control exercise on a sample of FCS due diligence reports which found that, overall, the judgements made by FCS were acceptable. However DFID did discover that FCS had used regional NGO networks to carry out due diligence on their own members. This was contrary to FCS’s usual policy and DFID and FCS agreed that this would not happen in future. Also DFID raised some questions about the quality of the due diligence reports themselves. These will be further reviewed after the completion of a comprehensive systems audit which FCS has separately commissioned.

FCS was also able to share with DFID a list of 9 grantees that through FCS routine monitoring and auditing were identified to have issues of funds misuse/lack of proper documentation/potential fraud. After review of these list and information provided by FCS, DFID further concluded that FCS is taking appropriate measures to address identified cases of misuse/fraud by grantees. DFID will continue to monitor these 9 cases and other cases when they emerge to quantify any losses and ensure that all options are explored to recover any lost funds.

FCS was further requested by DFID to provide an updated list of CSOs with auditing queries from the 2013 audit exercise. For each grantee, FCS will clearly need to show the nature of the issue, steps/actions been taken by FCS and appropriate timing so that DFID can track better and make necessary follow up accordingly.

Overview of programme risks identified in the Business Case

	Risks	Probability of Occurring (L,M,H)	Impact on Success / (L,M,H)	Updates
	External political / environment
1.	Space for CSO action is reduced, either formally through restrictive legislation, or informally through lower levels of state responsiveness	L	H	Space for CSO action in Tanzania remains open e.g. as demonstrated with CSO participation in the on-going constitution review process
2.	Political influence undermines the governance & management of FCS	L	M	FCS Members and Board of Directors are carefully screened at selection for party political bias, and there are sufficient checks & balances in the functioning of these structures to curb individual influence; / FCS has continued to foster an open, non-threatening relationship with GoT and politicians through events such as the Annual CSOs Forum and periodic Consultations with Members of Parliament and House of Representatives
	External financial / environment
3.	Competing grant-making programmes attract funding away from the FCS	L	M	FCS has continued to improve its systems and services and has remained a competitive local grant-making institution in Tanzania. FCS has also managed to attract non-bilateral donors as its funders. They include: Comic Relief, ILO, Trade Mark EA and American Jewish World Service.
4.	Funders reduce or fail to provide agreed predictable funding to FCS	L	H	The main core funders have agreed (via a MoU) to provide predictable funding into a ‘basket’ .FCS’s performance remains strong and this has continued to sustain the confidence of its funders.
	FCS governance / structures
5.	Members and Board of Directors fail to adequately discharge their duties	L	M	FCS’s Board members’ commitment remains strong. They were active participants during FCS’s field visits during 2013, provided leadership in development of the new FCS strategic plan and are currently leading a process to recruit a new CEO for the FCS.
	FCS operations
6.	Professional malpractice in the grant selection cycle	L/M	M	No professional malpractice reported or identified during the period under review. The FCS has a zero tolerance approach to corruption. FCS has commissioned KPMG to undertake a systems audit of its internal controls and processes. Report is expected by Sept/Oct 2014.
7.	Financial mismanagement	L	H	The assessment of the internal systems of the FCS by SIDA (2010) observed the presence and operation of “sound systems and a functioning of management and control of activities within FCS”. FCS has commissioned KPMG to independently carry out a systems audit. Report is expected in Sept 2014.
8	Inability to demonstrate results due to inadequate capacity and complexity around monitoring a small grants portfolio of over 700 projects	L/M	H	FCS has continued to improve its results reporting and is keen to keep doing so going forward.

Outstanding actions from risk assessment

Systems Audit of FCS: FCS has commissioned an independent firm (KPMG) to carry out a systems audit of its internal controls and processes. FCS needs to share this report with DFID. DFIDT will upwardly share this report with Internal Audit Unit in UK to solicit their technical assessment of the key findings and assess whether there is a need for further due diligence as DFIDT develop a new Business Case for support to FCS during the second half of 2015.

FCS will share with DFID a list of CSOs with auditing queries from the 2013 audit exercise. For each grantee, FCS will clearly show the nature of the issue, steps/actions taken by FCS and appropriate timing so that DFID can track better and make necessary follow up accordingly.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
FCS is delivering within the timescales in the Business Case.

Performance of partnership (s)
A DFID support to FCS is through an Accountable Grant Agreement. FCS’s performance is detailed on a joint MoU it has signed with all the basket funders. Current funders include: UK, Swiss, Norway, Denmark, Comic Relief and AJWS Foundation. In addition, FCS received 3.4% of its 2013 income from three non-basket funders namely Trade Mark EA, ILO and IRC. All meetings and reporting responsibilities were effectively met by FCS as per MoU. In addition, FCS was able to timely respond to different requests by donors e.g. it responded well to DFID’s recommendation over the need for FCS to carry out VfM assessment of its capacity building interventions. During period under review, FCS engaged well all the DPs on the development of its new strategic plan.

FCS has been performing in accordance with the Accountable Grant Arrangement. Despite operating in a risky environment FCS has impressive capacity to scrutinize and effectively manage over one thousand grantees. However, to ensure a more effective partnership with FCS in dealing with the risk of fraud and corruption and in line with the recommendations of the DFID Tanzania 2013 NAO audit it has been agreed that FCS will be submitting to DFID detailed risk assessment reports of grantees, grantees post audit follow up as well as the systems audit report that is being carried out by KPMG.

FCS’ total management/overhead costs were 20% of its total spend during 2013. This level of spend is in line with the MoU agreement which FCS have signed with all its basket donors. Over 56% of these costs were payroll related (salaries, pension, post-employment benefits and skill development levy). Another 26% were spent on outreach, grantees audit/monitoring and office rent. FCS had 34 employees during 2013.

Asset monitoring and control
FCS does not undertake large procurements because of the nature of its work as a grant making institution. DFID did a procurement assessment of FCS in 2011 as part of extension of DFID’s support and confirmed that FCS has adequate procurement systems. In 2013 FCS continued to ensure that all procurements are done in accordance with the procurement guidelines and that suppliers are obtained through a competitive bidding process. The FCS Finance and Administration Department is in charge of the actual purchasing and managing of programme assets while the Internal Audit Unit ensures overall compliance.

G: CONDITIONALITY (½ page)

Not relevant

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
FCS’s Theory of Change remains relevant. Results during 2013 confirm that support being provided to civil society organisations is contributing to increased awareness of rights and improvements in the utilization of public resources. This will contribute to improvement in service delivery. The provision of small grants and capacity building to a diverse range of civil society groups has contributed to increasing quality and quantity of information reaching citizens about their rights, resources and policy. Results during 2013 further indicate that some CSOs have directly engaged elected representatives. There are good examples in this review which indicate how supported CSOs have contributed towards directly monitoring and defending citizens’ rights e.g. through provision of legal aid.

DFID do not plan to do an evaluation of FCS as it was not identified as a priority when compared with other programmes in the office’s portfolio.

Monitoring progress throughout the review period

Monitoring of FCS activities by DFID and other DPs included two field visits - to Mbeya/Iringa and Mwanza regions - where about 16 grantees and beneficiaries were directly visited; and two joint FCS-DPs meetings – to review and discuss progress. Development partners from DFID, Embassy of Switzerland, Embassy of the Netherlands, Embassy of Norway and a representative from the Ministry of Community Development Gender and Children (MCDGC), and Board Members of FCS attended the visits along with the FCS Management Team.

Below is a testimony by the Government official who participated in the joint monitoring visit in Mbeya:

“....In a nutshell, most of the Organizations we visited in Mbeya region are performing very well in achieving their goals. I was very impressed by the performance of the Organizations like ADP-Mbozi and IRDO which deals with Agriculture. Encouragement and financing of such NGOs could bring about positive impact in agriculture sector in this country. Furthermore, Organizations such as Kilio cha Waathiriwa na Waathirika wa UKIMWI-Mbarali and Kilio cha Mama na Mtoto-Ileje are doing very well in the areas of HIV/AIDS and Education. I think these Organizations also need more support to enable them to expand their activities in their areas”. Tausi Mwilima, from NGOs Coordination Department, MCDGC.

FCS’s own monitoring activities included 465 monitoring visits out of 450 visitsplanned . These monitoring visits were useful as they provided an opportunity for FCS to help visited organisations to identify immediate, short term and long-term capacity gaps within their organisations. The FCS team delivered on-the-job coaching and mentoring to assist grantees to address some of the immediate gaps. As a result of the support provided, 69% of the organizations visited are now using the Performance Monitoring Plan to capture and report results for better project management.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process