Conflict Pool Project Form v.2

PLEASE REFER TO THE GUIDANCE WHEN FILLING IN THIS FORM
Summary

Project title:
Safe Schools Initiative (SSI)

Country/Countries:
Nigeria

BSOS objective(s):
Early warning
Rapid crisis prevention and response
Investing in upstream prevention – one of the following: / helping to build free, transparent and accountable and inclusive political systems / Strengthening Security and Justice / Building the capacity of local populations to resolve the conflicts that affect them / Building the capacity of regional and multilateral institutions to prevent and resolve conflicts

Total Cost to CP:	Duration:
£346,050		August 2014 – November 2014

Implementing partner(s):	Lead department:
GHT Global Ltd		DFID

HMG Project Officer:	Date submitted:
Laura Brannelly, Education Adviser, DFID Nigeria		1/08/14

Approved by:

*Seen and agreed by:
Jamie Brockbank, Regional Conflict Adviser, West Africa / Uduak-Abasi Akpabio, Regional Conflict Officer, West Africa / Dan Silvey, Conflict Adviser, DFID Nigeria / Adam Drury, Conflict Adviser, DFID Nigeria

Part One: Strategic Case

Why are we carrying out the project: context, aims and background
1.1 Programme:
Africa

1.2 Results Offer:
West Africa

1.3 Result/impact the project will contribute to (taken from Results Offer):
Outcome 1 “By the end of FY 14/15, we will have contributed to a reduction in conflict and instability in Nigeria...” / Output 3 “Support for more accountable and inclusive political systems in our priority countries...”

1.4 Project outcome:
An evaluated, replicable safe schools model available for schools and communities to implement in order to improve security for teachers and students.

1.5 Theory of change (maximum 200 words):
The project theory is based on a number of assumptions that are listed below and the connections of the assumptions and strategy and the final achievement of the desired effects is summarised in the ‘if’ and ‘then’ results chain further below; / The project Theory of Change is illustrated and explained in a tabular form through Results Chain and list of assumptions below: / Input / ‘If we...’ Output / ‘then...’ Outcome / ‘then...’ Impact / ‘then...’ / …design an appropriate community and school-based response to school security A comprehensive schools security approach, with a range of interventions, will be piloted in two different school contexts An evaluated, replicable safe schools model will be available for schools and communities to implement in order to improve security for teachers and students schools will be less vulnerable to attacks and able to operate in a more secure and resilient environment enabling children to safely return to school and resume their education. / Assuming that all stakeholders are engaged in implementing the approach. Assuming that sufficient resources are made available through the Safe Schools Initiative (SSI) to be responsive to needs. Assuming that the safe schools approach is embedded in local community structures and accompanied by appropriate military and political actions, and education responses to improve quality of learning and encourage school enrolment.

1.6 Implementing partner(s):
GHT Global Ltd. GHT is a security provider which combines expertise in policing, military and community-based security solutions. They have established relationships with key stakeholders engaged in the SSI including the Ministry of Finance, National Emergency Management Agency (NEMA), Office of the National Security Adviser (ONSA) and State government officials from Borno state.

1.7 *Background (maximum 500 words):
As part of the international response to the Chibok abductions, the UK government announced £1m of support to the Safe Schools Initiative (SSI) to ensure that children can continue to safely access education in northern Nigeria. New delivery mechanisms are being developed to ensure that commitments reach those most affected by the conflict. / The Government of Nigeria and the UN Special Envoy for Education (Gordon Brown) launched the SSI in response to increased security threats to schools. The Initiative aims to ensure that children can continue to safely access education in Northern Nigeria by providing an educational and security response for the protection of schools that will build resilience within communities, promote vigilance and awareness of threats and ultimately help prevent future attacks on schools. / This project will support the development of the SSI approach, through the provision of technical assistance and piloting of the model in two schools in the north east of Nigeria. The implementers will advise on the development of a proposed design of the safe schools response. This response should create an environment with the minimum security and educational conditions to enable access to inclusion learning. It should include a combination of school-based and community interventions: / (i) school-level interventions such as secure perimeter, power and lighting, secure refuge and/or escape points, establishing communication and early warning systems, and training for school staff, students and community members emergency response planning. / (ii) community-level engagement model to foster a vigilant and supportive community that can help ensure a safe environment in which schools can operate. / The project will support the work of the design and pilot team, who are expected to be in country between August and November. / This project is for the design and pilot phase only. The SSI approach that is designed under this project will be delivered by the Government and other SSI partners. / At this stage, funding is requested for £346,050 to support this initial development of SSI. A decision is still to be made on the use of the remaining £650,000 committed to SSI.

Part Two: Appraisal Case

How the project will work theory of change, outcomes, activities, indicators and
the risks.
2.1 Outcome:
An evaluated, replicable safe schools model available for schools and communities to implement in order to improve security for teachers and students.

2.2 Outcome Indicators:
Indicator	Baseline	Target / (including date)	Source of information & who will collect
Evaluated Safe Schools Model with implementation strategy	0	1 (30/10/14)	GHT Global Final Project Report, including evaluation report and implementation strategy

2.3 Output 1: Situational Analysis
Activities
Activity	Expected date[1]
Analysis of schools, teachers and students data	22/08/14
Produce security ‘heat maps’ and analysis of locations, condition of schools and levels of need.	22/08/14
Stakeholder mapping	22/08/14
Produce stakeholder engagement and communication plan	29/08/14
Identify intervention sites for pilot and initial roll out[2].	26/08/14
Produce situational analysis report with recommendations	29/08/14
[1] All dates have assumed a contract start date of 18 August 2014. Expected delivery dates are subject to change based on length of procurement process and agreed start date. Whilst the current workplan schedules for all activities to be concluded by the end of October, an end date in November is suggested on the Summary page to allow for any potential slippage in contracting and delivery.
[2] The project will identify up to 10 schools per State (30 in total) for the model to be delivered in during the first year of operation of the SSI. Implementation of the model in these schools is beyond the scope of the project; this will be delivered by the Government of Nigeria through the SSI. However as part of this project and the situational analysis will be expected to identify these schools.

Indicators
Indicator	Baseline	Target / (including date)	Source of information & who will collect
Number of intervention sites identified	0	32 / (2 pilot, 30 for roll out from late 2014) / (26/08/14)	Situational analysis report / GHT/SSI technical committee
Number of State situational analysis completed	0	3 (29/08/14)	Situational analysis report / GHT/SSI technical committee

Output 2: Safe Education Model
Activities
Activity	Expected date
Review of evidence on school protection models	29/08/14
Design of education model, including defining community engagement processes; physical, technical and security components; and capacity development requirements	19/09/14

Indicators
Indicator	Baseline	Target / (including date)	Source of information & who will collect
Approved ‘Concept of Operation’ for safe schools	0	1 / (19/09/14)	SSI Technical Committee

Output 3: Implementation Strategy
Activities
Activity	Expected date
Develop implementation plan for pilot schools	22/09/14
Develop communication strategy, including community engagement model	26/09/14
Develop implementation plan for scale of SSI by Government of Nigeria, including state delivery plans	03/10/14
Develop monitoring and evaluation framework and tools	26/09/14
Develop risk and issue management process	26/09/14
Develop TORs for key stakeholders to be involved in implementing SSI with clear roles and responsibilities	26/09/14

Indicators
Indicator	Baseline	Target / (including date)	Source of information & who will collect
Agreed pilot work plan	0	2 (22/09/14)	SSI Technical Committee
Agreed state delivery plans	0	3 (03/10/14)	SSI Technical Committee
Approved implementation strategy	0	1 (26/09/14)	SSI Technical Committee

Output 4: Pilot of model
Activities
Activity	Expected date
Coordinate delivery of the Concept of Operations in 2 pilot schools	29/09 – 24/10
Develop and deliver training for key stakeholders	03/10/14
Evaluate implementation in pilot schools	29/10/14
Update implementation strategy and model if required	31/10/14

Indicators
Indicator	Baseline	Target / (including date)	Source of information & who will collect
Number of schools that have piloted approach	0	2 (31/10/14)	Evaluation Report, GHT

2.4 Risks
Risk	Likelihood	Impact	How we will mitigate risks	Risk owner
Insufficient stakeholder engagement and coordination (community, state and federal levels)	Medium	High	The project will start with extensive stakeholder mapping and engagement as part of the situational analysis to ensure engagement and ownership of the approach from the outset. This will build upon existing relationships already established with key stakeholders at state and federal level through the SSI Steering Committee and strong Government leadership. / Stakeholder roles and responsibilities, and coordination mechanisms will be clarified in the implementation strategy.	GHT, SSI Steering Committee
Deteriorating security levels inhibit piloting of approach	High	Medium	The project will work closely with the Government of Nigeria to monitor the security situation. Alternative pilot schools will be identified if required.	GHT, DFID, SSI Steering Committee
Delays in piloting of approach linked to third party delivery	High	High	GHT will coordinate delivery of the pilot, but implementation will be the responsibility of Government agencies. Planning of pilot activities will commence as soon as possible to avoid delays.	GHT, Government of Nigeria, implementing parties, SSI Steering Committee

2.5 * Why we should still go ahead if this is a high risk project:
There is an urgent need to improve protection so that education can continue in the north of Nigeria. The educational needs are great; even before the Chibok abductions and increased targeting of schools for attack, the percentage of out of school children was 30 times higher in the north east of Nigeria than in the south east of the country. Supporting the Safe Schools Initiative capitalises on national and international momentum to respond to the vast educational needs and also work with communities to improve their resilience to attack.

2.6 * Sustainability:
At this stage funding is only requested for the design and piloting of the SSI approach. Implementation will then be undertaken by the Government of Nigeria and other SSI partners, including NEMA, NSA and State Ministries of Education. Project deliverables include an implementation strategy that can then be applied to deliver the project beyond the design stage.

Part Three: Commercial Case

To ensure that the department meets its legal obligations in terms of procurement and contracts

3.1: Which of the Departments’ procurement and contracting regulations will be used?
DFID

3.2 Contracts: will the project implementers have a commercial contract, MOU or an accountable grant?
Commercial contract

3.3 Procurement: if using a contract, will the project involve a procurement process (Y/N)?
Yes

3.4 EU regulation: will the process follow EU guidelines (Y/N)?
Yes. Approval has been given by DFID Head of Procurement and Commercial Department for a negotiated procedure (without advertising) to take place due to the extreme urgency of the situation. Waiver Ref: WAIV14_011, 15 July 2014

3.5 Templates: has the template being used been shared with implementers? (Y/N)
Yes.

Part Four: Financial Case

How will the project be funded: who else is financing, budget, multi-year funding and activity costs. An activities-based budget must be submitted with the project form, showing activities, their cost, and timings.

4.1 Total cost to the Conflict Pool:
£346,050

4.2 * Funding breakdown by year:
Project start date: August 2014 Project end date: October 2014
2014/15
£346,050

4.3 * Other partner funding:
Project start date: Project end date:
Partner contributing:	2013/14	2014/15
	£	£
Total cost of project:

4.4 ODA/non-ODA split:
Total ODA: £346,050	As a percentage: 100%
Total non-ODA:	As a percentage:

Output-based budget
Output	Costs	Days input	Timeframe
			August				September				October
1. Situational analysis	£70,500	25
2. Design safe education model	£130,600	53
3. Develop implementation strategy	£91,750	50
4.Piloting of model	£53,200	18
Total	£346,050	146

Costs include a combination of consultancy costs + associated expenditures. The final budget is subject to change pending commercial and technical evaluation of the proposal as part of procurement processes. The number of days input required and fee rates may change as a result of this process, but the total costs will not exceed £346,050.

Part Five: Management Case

How the project will be run: monitoring, evaluation and human rights
5.1 Monitoring:
Method	Intervals	Carried out by	Follow up activity
Meetings to discuss progress	Bi-weekly	GHT and DFID (project officer)	GHT to circulate action points and any agreed revisions to workplan to all stakeholders. / Follow up to take place within DFID and with FCO to ensure cross sector working between education and conflict teams.
Reporting to technical committee of SSI	Monthly	GHT SSI technical committee (includes DFID)	Action points and feedback to be discussed with project officer
Reporting to Steering Committee of SSI	As required	GHT and SSI Steering Committee (includes DFID)	Action points and feedback to be discussed with project officer
Interim report to be submitted with completion of Output 2	End of Output 2	GHT	Feedback to be discussed with GHT and DFID.

5.2 Evaluation plan:
The project will include an evaluation of the pilot approach in 2 schools. This will be carried out by GHT as part of their activities under Output 4. / This will be a process evaluation that will also utilise a case study approach to assess whether the model is being implemented as planned and delivering the expected outputs and outcomes. Specific questions to be answered by the process evaluation will be identified by GHT during the project set up. The methodology will include a combination of interviews and observations. It is proposed that a member of the technical committee is involved in the evaluation to provide analyst triangulation to confirm interpretation of issues. / The costs of the evaluation have been included under the budget for Output 4.

5.3 * Human rights assessment (for security and justice projects only):
Ensuring children’s human right to access basic education is at the centre of this project, alongside the principle of do no harm in order to safeguard children and ensure that they are not targeted whilst trying to receive an education. This will be a consistent component of the project approach, situational analysis, safe schools design and piloting. The project will comply with OSJA Human Rights Guidance.