Type of Review: Annual Review

Project Title: Saferworld CHASE Programme Partnership Arrangement (PPA)

Date started:	June 2011 Date review undertaken: 31 August 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing £5.1m over three years to Saferworld as part of DFID’s programme to fund civil society organisations – the Programme Partnership Arrangements (PPA). / Saferworld is a not-for-profit organisation that believes that everyone should be able to lead peaceful fulfilling lives, free from insecurity and violent conflict. They work towards meeting / three ‘peace conditions’ which Safeworld believe are vital to achieve this overall vision: / people are free from fear and insecurity. / people have fair and effective paths to address their grievances. / people are central to preventing conflict and building peace. / A broad range of actors have a role to play in achieving these peace conditions. By positively influencing the behaviour of these actors Saferworld (SW) seek combined policy and practice change to ensure that: / Individuals and communities have the opportunity and capacity to influence effective responses to conflict and insecurity, and to promote peace. / National and international civil society plays an active role in influencing authorities and building capacities for peace. / National and local authorities are responsive and accountable to people’s needs and their actions help to build peace. / External actors operate in a way that supports peace, including through their aid and international assistance policies and their engagement in conflict-affected and fragile contexts. / Saferworld works directly with communities affected by instability and conflict to articulate their safety concerns and improve their sense of security. Community security is fostered by first investing sufficient time and energy to gain the trust of local communities, and then supporting them to voice their concerns and aspirations to those in power. They achieve this through developing collaborative partnerships with local organisations. They also document lessons from their work, and the work of others, to create learning and evidence to inform policy and practice more generally. International peace-building and state-building frameworks provide important standards for all actors, but must be informed by the experiences of those most affected by violence and conflict. Consequently, through their programming, policy development and advocacy, Saferworld challenge national and international actors to listen to the views and priorities of those living with insecurity, while at the same time, seizing opportunities to influence and support civil society, governments and international agencies to respond in a sensitive and accountable fashion.

What are the expected results?
Saferworld works at the intersection of conflict, security and development at both policy and programming levels, focused on 18 conflict-affected contexts across East Africa, Central and South Asia, the Caucasus, Eastern Europe and the Middle East[1]. Their advocacy work seeks to improve international policy and programming in such contexts. The strategic nature of PPA Funding enables Safeworld to: / Underpin the extensive commitment of time and energy required to influence change at the local level with communities in conflict-affected contexts. / Provide space and capacity for innovation and learning, in order to better inform practice – such as piloting new approaches which are hard to undertake with project-specific funding. / Enhance their ability to link international policy work with their in-country programming – plan for higher-capacity and more flexible and appropriate responses for fragile and conflict-affected contexts. / Be responsive to emerging policy trends and unforeseen opportunities – as they relate to conflict prevention and security building. / Make investments in their staff, operational and administrative functions – to boost effectiveness and value for money. / In terms of results, the PPA is expected to deliver the following: / Impact: A reduction in violent conflict and insecurity in Saferworld (SW) target countries. / Indirect Outcome: Civil society organisations and authorities increase the impact of their contribution to preventing conflict and increasing community security. / Outcome: Individuals and communities, civil society, authorities and external actors strengthen their approaches and capacities for preventing violent conflict, building peace and addressing the needs of conflict-affected (or at risk) communities, (in accordance with Saferworld's organisational change model), in Bangladesh, Georgia/Abkhazia, Kenya, Kosovo, Kyrgyzstan/Tajikistan, Nepal, Pakistan, Somalia, Sri Lanka, South Sudan, Uganda, Yemen. Output 1: In Georgia/Abkhazia, Kenya, Kyrgyzstan/Tajikistan, Nepal, Pakistan and South Sudan, SW and local partners provide support to community members in identifying and addressing their community security and justice needs in collaboration with local authorities. / Output 2: In Georgia/Abkhazia, Kosovo, Kyrgyzstan/Tajikistan, Somalia, Uganda and Yemen, local civil society organisations receive support from SW to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts. / Output 3: In Kenya, Kosovo, Nepal and South Sudan national and local authorities receive support from SW to assist them in developing effective policies and practical approaches for building peace, justice and security. / Output 4: External actors (incl. donors, external governments, and / or relevant multilateral agencies) receive SW analysis, policy options and training aimed at influencing and strengthening their policies and approaches for engaging in fragile and conflict-affected countries. / Output 5: SW, in consultation with DFID, develops and applies a robust monitoring and evaluation system which enables the identification, measurement and communication of results at output and outcome level, and demonstrates contribution to impact level. / Following the recommendations made in last year’s Annual Review, Saferworld have adapted their milestone indicators and increased their anticipated results substantially for some indicators. The key issues that were highlighted in the 2012/13 report that were addressed in 2013/14 include: / The importance of investing in staff. Given the growth in numbers of staff, emphasis has been placed on ensuring stronger human resource management systems and processes, with adequate support and development to retain and maintain staff commitments. A new performance management system has been rolled out, focussing on professional development and better management of staff. / SW’s risk management approach has been consistently strengthened with regional (and where relevant country) risk management teams in place with a revised set of Standard Operating Procedures (SOPs). Kenya and Somalia, for example examine risk at their team meetings while in Yemen similar processes are in place. Finally, a risk management team in London meets every 6 weeks to respond to upcoming issues. SW has also completed and updated DFID’s Overseas Security and Justice Assessment (OSJA) to substantiate organisational efforts. / The feedback from DFID last year suggested stronger emphasis on drawing out SW’s contributions to outcomes, which has been specifically addressed in the 2013/14 report. More importantly, a focus on SW contributions to outcomes has been emphasised in the outcome monitoring approach for SW (developed over the funding period), and training on this approach has been provided to country staff through workshops as well as the PPA data collection process for 2013/14.
[1] Saferworld operates in and/or on The Horn and Great Lakes regions of Africa, (regionally and in Kenya, Somalia/Somaliland, Sudan and Uganda); South Asia (regionally and in Bangladesh, India, Nepal, Pakistan and previously in Sri Lanka); Central Asia (Kyrgyzstan, Tajikistan); the Caucasus (regionally and in Georgia/South Ossetia/Abkhazia); Balkans (regionally and in Kosovo, previously having worked in Bosnia and Moldova); and the Middle East (Yemen).

What is the context in which UK support is provided?
Civil society plays a vital role in supporting citizens to improve their lives. Civil Society Organisations (CSOs) are central to delivering services, enabling citizens to be more active in their own development and ensuring that policies benefit ordinary people – especially the poorest. / To achieve DFID’s priorities, as set out in its Business Plan (Structural Reform Plan), a multi-sectoral and multi-faceted approach to delivery is required, one in which CSOs, along with governments and the private sector, play a pivotal role in helping poor people to improve their lives. / The PPA is one of DFID’s main support mechanisms to CSOs. In line with a commitment by the Secretary of State to support another round of PPAs over the 2011-14 period and following a robust selection process and implementation of a Resource Allocation Model, partners were identified for a 3 year PPA which began in April 2011. This is the last review for that reporting period. However, it should be noted that an additional two years extension has been agreed by the SoS for 2014-2016. Results from 2011-2014 will be progressed further under the extension period. / International/ UK Context for Security and Justice Interventions: / Internationally, the consensus around the contribution that safety and justice can make to stability and development has also become increasingly well established. The World Development Report (2011), for example, found that insecurity ‘has become the primary development challenge of our time’ and is a major obstacle to the successful achievement of the MDGs. The New Deal, which was agreed at the 4th High Level Forum on Aid Effectiveness in Pusan, South Korea in December 2011, also recognises the importance of security and justice as key elements of peace-building and state-building strategies. / UK aid addresses the causes of poverty as well as the symptoms. Rule of law has been identified by the UK Prime Minister as part of the Golden Thread linking open economies and open societies, which is a key enabler for successful economic and social development. Security and justice are also important considerations for poor people: the 2000 World Bank report Voices of the Poor identified that security and justice are as important to poor people as hunger, employment and lack of safe drinking water. As a result, DFID has committed to scale up its support for security and justice reform in 18 countries following the Bilateral Aid Review in 2011, and the UK Government’s 2011 Building Stability Overseas Strategy (BSOS) restates and reiterates the central contribution that functioning security and justice systems can make to creating stable and open societies and economies. Furthermore, the UK recognises the positive developmental impact that targeted investments in women and girls can make. As such, the UK has committed itself to improving access to safety and justice for 10m women and girls globally by 2015. The UK’s support to Saferworld will make a substantial contribution to the achievement of improving security and justice for poor and marginalised communities in target countries.

## Section A: Detailed Output Scoring

Output 1: In Georgia/Abkhazia, Kenya, Kyrgyzstan/Tajikistan, Nepal, Pakistan and South Sudan, Saferworld and local partners provide support to community members in identifying and addressing their community security and justice needs in collaboration with local authorities
Output 1 score and performance description: A+ Outputs moderately exceeded expectation. / Indicator 1.1 Number of action-oriented community groups formed by members of conflict-affected communities in Georgia/Abkhazia / Kenya / Kyrgyzstan/Tajikistan / Nepal / Pakistan / South Sudan - with Saferworld support - through which communities can identify their security related needs and priorities, and develop a shared purpose and vision for change / Baseline See logframe / 2011/12 2012/13 2013/14 / Milestone 10 groups formed SW continues support to the groups formed in Year 1, where appropriate, and an additional 10 formed 44 groups formed / Achieved 12 17 85 (57 in 2013/14) / Variance 2011/12: +2 2012/13: +7 2011/14: +42 / Disaggregated Data* 2011/12 / Nepal – 2 / Kyrgyzstan/Tajikistan – 4 / South Sudan – 3 / Georgia/Abkhazia – 3 Not reported on New groups formed in 2013/14 / Nepal (18): average of 6/10 women in each group and 2/11 dalit in each group) / Bangladesh (16): average 4/11 women in each group) / Kenya (3): 4/12, 9/21 and 7/20 women in each group / Yemen (2): 8/15 and 6/11 women in each group / South Sudan (10): 10/20, 8/20, 7/20, 5/11, 2/11, 8/11, 7/20, 5/20, 3/20, 8/20 women in each group) / Georgia/Abkhazia / No new groups. Old groups continued. Average 8/20 in each group. / Kyrgyzstan/Tajikistan (8) / Average 5/11 in each group / Saferworld report that it has continued to support community groups across all of the countries listed (except for Pakistan) and has also had significant success in establishing 18 more groups in Nepal, 10 in South Sudan, 16 in Bangladesh, 2 in Kenya, 8 in Kyrgyzstan/Tajikistan, and 2 in Yemen. A recent evaluation of the Nepal programme reported that authorities and community groups alike found the role and process of establishing and running these groups very important in building more trusting relations between authorities and communities. Saferworld’s community security work takes a ‘whole of community’ approach, engaging all members of the community in this enterprise, with a view to addressing common grievances, building trust and cooperation, and addressing social exclusion in the context of access to security and access to justice. / Indicator 1.2 Number of community groups in Georgia/Abkhazia, Kenya / Kyrgyzstan/Tajikistan / Nepal / Pakistan / South Sudan who have the opportunity, as a result of SW-facilitated meetings, to voice `their security and justice concerns to local authorities in order to begin identifying joint solutions and plans for action / Baseline Through previous SW support, some communities have become more aware and already formed groups, and the authorities have demonstrated a tentative willingness to listen to their concerns, as is the case in parts of Georgia and Nepal. (Other groups will progress to this stage following support reported on under Indicator 1.1) / 2011/12 2012/13 2013/14 / Milestone 8 community groups have had the opportunity to voice concerns to authorities and begin identifying joint solutions and plans for action An additional 10 40 groups formed / Achieved 12 18 75 (45 in 2013/14) / Variance 2011/12: +4 2012/13: +8 2011/14: +35 / Disaggregated Data* Not reported on 2012/13 / Nepal – 12 / Kenya – 5 / South Sudan – 1 2013/14 / Kyrgyzstan/Tajikistan: 7 with old groups / Bangladesh: 16 / Nepal: 12 with old groups / Georgia/Abkhazia: 3 with old groups / Kenya: 3 / Yemen: 2 / South Sudan: 2 / Progress against expected results: / Community groups across the countries have all had opportunities to engage with local authorities, however with varying degrees of response and involvement from authorities themselves. In Bangladesh, for example, advisory groups were set up (separate to community groups) to engage local authorities to ensure communities felt safe when voicing concerns. A significant achievement was made at a local youth initiative, which involved a meeting of young people and local authorities in South Ossetia where the young people had the opportunity to voice their concerns. At that meeting it was decided to hold a Youth Conference in April 2014 where young people from all over South Ossetia would be invited to meet with local authorities and discuss issues affecting youth in South Ossetia. In Kwajok and Tonj North, South Sudan, SW supported communities to establish a Police Community Relations Committee (PCRC) where none existed.
SW has significantly exceeded both the original and revised targets for this indicator. In South Sudan, despite the security situation 10 groups were established. The milestones have been exceeded with the application of models from Nepal being tested with success, in Bangladesh. Examples include: / Nepal: The Nepal Police overseeing Village Development Committees in Binau, Bijapur and Banke reported that alcohol-related violence cases (which frequently involve Domestic Violence (DV) and Sexual and Gender-based Violence (SGBV)) have significantly decreased, after Civil Society Working Groups (CSWGs) prioritised tackling substance abuse (including alcohol). The CSWG in Banke agreed a code of conduct for both the sale and consumption of alcohol with sellers. / Bangladesh: More villagers now walk around at night, and keep their animals outside. Night patrolling by the police has increased (prioritised in the action plans), and cases of DV have fallen in Gopalganj, (DV prioritised in the action plans). / South Sudan: In Tonj North, South Sudan, SW supported communities to establish a Police community relations committee (PCRC) where none existed. Police and the Sudan People’s Liberation Army (SPLA) have introduced and enforced a ban on carrying weapons in the market-place, including introducing unarmed patrols by authorities. / Kyrgyzstan: In Bazar Korgon, CSWGs acknowledged, for the first time, that there were problems of community relations with the police. Bringing communities and police together in the CSWGs, both actors began to discuss the issue of police abuse. Their improvement in the openness and attitudes of the police created by the project was a contributing factor in the outcome. / Bangladesh: Across project sites in Bangladesh trust and communication between communities and the police has significantly improved, which in turn has led to increased police patrols, a reduction in anti-social incidents, and increased confidence of the Community Advisory Committee (CAC) to take on complex security issues in their locality (e.g. mediating a dowry dispute). / Recommendations: Saferworld should consider the qualitative aspects of Indicator 1.1 and focus more closely on the impact of these groups forming, and what change they have brought about as a result. / Impact Weighting (%):25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: In Georgia/Abkhazia, Kosovo, Kyrgyzstan/Tajikistan, Somalia, Uganda and Yemen, local civil society organisations receive support from Saferworld to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts.

Output 2 score and performance description: A+ Outputs moderately exceeded expectation.
Indicator 2.1 Number of local CSOs in Kyrgyzstan/Tajikistan / Uganda / Yemen who receive targeted and tailor-made high-quality training / capacity-building from SW on areas such as strategic planning, advocacy, conflict analysis and monitoring and evaluation, and on the technical aspects of conflict-related issues relevant in their country / Baseline CSO capacities are generally weak in these countries. SW has provided some previous training and capacity-building in Uganda and to a lesser extent Kyrgyzstan/Tajikistan, but not yet in Yemen. SW will develop new civil society relationships in each country, of which training and capacity-building will be a major component. / 2011/12 2012/13 2013/14 / Milestone High quality, tailor-made training / capacity-building has been provided to 6 CSOs An additional 6 CSOs 13 trained over three years groups formed / Achieved 4 7 85 (74 in 2013/14) / Variance 2011/12: -2 2012/13: +1 2011/14: +72 / Progress against expected results: / Saferworld report that a substantial number of new CSOs (85 in total) have received training and capacity building over the past year while partners have continued to receive support and training from SW. Some examples of success include (by country): / Yemen: Women participated in an open discussion on women safety and security for the first time after receiving advocacy training from SW. They discussed issues sitting at the same table as authorities including representatives from the Ministry of Interior. / Pakistan: Tailor-made training was provided to 35 new CSOs in Pakistan and in addition to the training a Training of trainers manual: Transforming conflict and building peace was also developed by SW in response to the limited support for CSOs in the region. / Uganda: Training and mentoring was provided to WaterAid to help introduce conflict sensitivity in their work as well as the Gulu NGO forum and Lira NGO forum. / Somalia: An extensive needs-assessment and training activity was undertaken in Somalia for the three SW-supported platforms. / While it was suggested last year that progress may be limited in fulfilling this indictor, as a result of new work that has been developed over the past year this indicator has shown dramatic over-achievement. / Pakistan – training on Conflict-Sensitive Approaches (CSA), Negotiation and Peacebuilding; Advocacy, Understanding and Measuring Change, and Community-driven Initiatives for Peace and Security. / Uganda – training on CSA / Somalia – needs-assessment and further training on advocacy / Over-delivery of this output for this year is primarily the result of significant numbers of CSOs trained in Pakistan (35). The results in the PPA annual review over the past three years tell a story of progressive expansion in SW’s work. It would not have been possible to realise this growth without significant investments in the capacity and overall development of the organisation in the key areas listed above. Although many of these development processes are still in progress, the cumulative effect from the strategic allocation of the PPA grant in these areas is already apparent – the most immediate being an increase in the size of programmes which in turn, has increased the number of people who have benefitted. These and other investments have enabled SW to engage with more partners, and reach a greater number of intended actors, through its programming (community groups, CSOs, authorities, and international players) – as evidenced in the logframe reporting. SW’s initial logframe developed for SWs PPA included 9 countries, and now it makes reference to 15 and with 31 different partners. SW have had to revise output targets upwards year on year. These figures are evidence that the PPA has provided SW with the foundation to increase its scale and reach, and supported leveraging funds from other partners to ensure SW can start to build a more effective evidence base. / Recommendation: Saferworld should provide more narrative detail on the impact of their training/capacity-building to CSOs, including details of what the CSOs have done differently as a result. / Indicator 2.2 Number of local CSOs in Georgia/Abkhazia / Nepal / Somalia who receive support from SW to articulate and convey the needs and views of their constituents within policy development processes. / Baseline The space and opportunity for civil society to participate in policy dialogue and development is restricted in these countries. SW has provided support to select CSOs in Georgia/Abkhazia, Somalia and Kosovo to identify policy processes in which they can play a role / 2011/12 2012/13 2013/14 / Milestone A total of 5 CSOs have been supported by SW to articulate needs and views of constituents within policy development and dialogue processes An additional 3 CSOs 10 over three years / Achieved 6 3 23 (14 for 2013/14) / Variance 0 +13 / Disaggregated Data* Not reported on 2012/13 / Georgia/Abkhazia – 1 / Somalia – 1 / Kosovo – 1 2013/14 / Georgia/Abkhazia: 1 / Nepal: 10 / Somalia: 3 / Progress against expected results: / Numerous CSOs received support from SW to represent the views of their constituents. Some examples are included below: / Somalia: Training was provided to all three platforms (Puntland Non-State Actors Association (PUNSAA) Somalia South Central Non-State Actors (SOSCENSA) and Somaliland Non State Actor’s Forum (SONSAF) on skills development to conduct advocacy and develop policy briefs. As a result of this training police briefs have been developed by all three platforms that are now being used in communications and SONSAF is now providing inputs into national level environmental legislation / Nepal: A workshop was held to provide training to 10 CSOs on Conflict-Sensitive Approaches (CSA), Do No Harm (DNH), Safe and effective development in Conflict (SEDC) and on data collection and research methodology. Further support was provided to partners – Informal Sector Service Centre (INSEC) and Child Workers in Nepal (CWIN) – at a workshop on people-to-people approaches and gender and conflict sensitivity, all of which are integral to the work of community groups and authorities. / The Caucasus: Gori Information Centre (GIC) received training on community mobilisation and advocacy while Identity Caucasus (together with Eastern Abkhazia Community Reference Groups and Abkhaz authorities), received training on community-police partnership and community policing in January 2014. / Nepal (10) – training on DNH and safe and effective development / Georgia/Abkhazia (1) – training on community mobilisation and advocacy / Somalia (3) – training on conducting advocacy and developing policy briefs. / Recommendations: Saferworld has continued to make progress on reporting both qualitative and quantitative elements of indicators. It is recommended that Saferworld continue to explore ways to fully capture and articulate the qualitative impact of interventions as they relate to the intended impact of the PPA. For the next two years of PPA funding, Saferworld should scale its milestone indicators upwards to ensure they are sufficiently challenging, given the significant over-achievements this reporting year. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: In Kenya, Kosovo, Nepal and South Sudan national and local authorities receive support from SW to assist them in developing effective policies and practical approaches for building peace, justice and security
Output 3 score and performance description: A outputs met expectation. / Indicator 3.1 Number of government-led policy development processes in Kenya, Kosovo, Nepal and South Sudan to which SW provides quality technical input and support / Baseline Each of these countries is at a crucial stage in its recovery from violent conflict and building of sustainable peace. SW will build on previous support to policy development processes in these and other countries, and support and influence upcoming policy processes incl. in relation to policing, constitutional reform, and arms control) / 2011/12 2012/13 2013/14 / Milestone SW has provided quality technical input 5 policy processes SW has continued support to the policy processes reported under Milestone 1 (where they are still underway) / An additional 5 policy processes 22 processes over three years groups formed / Achieved 11 8 27 (8 for 2013/14) / Variance 2011/12: +6 2012/13: +3 2011/14: +5 / Disaggregated Data* 2012/13 / Kenya – 4 / Kosovo – 2 / South Sudan – 1 / Nepal - 1 2013/14 / Kosovo: 2 / Uganda: 2 / Kenya: 1 / Kyrgyzstan/Tajikistan: 1 / Yemen: 1 / South Sudan:1 / Progress on expected results: / There has been noticeable progress on SW’s inputs into government policies and processes, and as a result of SW’s engagement, many governments have approached SW to provide technical support. Demand for their expertise is taken as a proxy measure for ‘quality technical inputs’. Some key examples of success include: / Kosovo: SW and Forum for Civic Initiatives (FIQ) were invited by the Ministry of Internal Affairs and the Ministry of Education to join the government working group and contribute to the design of a National Strategy on School Safety (2014-19) and drafting of the Action Plan. Given increasing violence in schools this is a key strategy to address conflict. / Support provided by SW to the Ministry of Internal Affairs to design the Action Plan for raising public awareness on community safety forums. / Uganda: The National Planning Authority (NPA) requested SW’s assistance to include conflict sensitivity in the mid-term review of the national development plan at the local government level. The NPA is responsible for the development of 2015 national development plan and this plan is incredibly important for development outcomes at the local government level. The original draft of this plan had no reference to conflict sensitivity so inclusion of SW’s recommendations is essential. / Also, at a meeting of the PRDP (Peace, Recovery and Development Plan) Monitoring Committee (PMC) four issues from a memorandum, drafted by SW and an NGO Consortium were accepted by cabinet members. These four issues were recommendations that SW had specifically included into the memorandum. / Kenya: Discussions of key policy makers (Director of Kenya Vision 2030) now reflect the Saferworld and Usalama proposed business management models for transforming police stations in Kenya, after 2 key meetings were held (Director of Kenya Vision 2030 and President’s advisor on political affairs). After the meeting, the Director of Vision 2030 wrote an article highlighting the importance of investment in security infrastructure to enhance police operational efficiency and working conditions. / Kyrgyzstan/Tajikistan: The Civic Union (CU) (set up by SW) now deals specifically with police reform. They have gradually, over the year, built their capacity to where the Kyrgyz police reform law now includes excerpts from a draft police reform law that was developed by the CU. / Yemen: The 1325 team in the Ministry of Human Rights have asked SW to develop and revise their plans and help them to implement their plan. / South Sudan: On the invitation of the Ministry of Justice (MOJ), Saferworld and MoJ’s Community Securitiy and Small Arms Control (CSSAC) Bureau, attended the MoJ’s 8-member technical review of Small Arms and Light Weapons (SALW) Bill (largely lawyers with limited SALW expertise). This participation in the review process assisted in clarifying and retaining some aspects of the texts. / Saferworld has exceeded the three year target, and there are encouraging signs that SWs new whole programme approach is working effectively with links between local, sub-national and national level policy work. / Recommendation: SW should provide more detail on the changes achieved (on policy, spending etc) as a result of their technical input to government-led policy development processes / Indicator 3.2 Number of formal / informal governing institutions in Kenya / Kosovo / Nepal / South Sudan who receive quality technical support from SW to assist them in developing more participatory approaches to addressing people's security and justice needs / Baseline Approaches to security and justice are typically ‘top down’, and rarely address the needs of, nor include the participation of, conflict affected communities in these countries. SW will build on existing relationships with authorities and institutions and assist them in adopting more accountable and participatory approaches / 2011/12 2012/13 2013/14 / Milestone A total of 4 institutions have received technical support An additional 4 10 over three years / Achieved 5 4 15 (6 for 2013/14) / Variance 2011/12: +1 2012/13: 0 2011/14: +5 / Disaggregated Data* Not reported on Kenya – 1 / South Sudan – 1 / Kosovo – 1 / Nepal - 1 2013/14 / Kenya: 2 / C Asia: 2 / South Sudan: 1 / Kosovo: 1 / SW has advised a total of 6 institutions on developing participatory approaches to address people’s security needs. For example: / Kenya: There was a breakthrough with the National Police Service where a framework that SW developed (with a consultant) has now been used as the foundation for the National Police Service (NPS) Strategic plan. The plan is expected to be concluded soon, through public validation. Significant progress has also been made at various levels, working with the Internal Affairs Unit. 90 new Officers, during the reporting period, were recruited for the Internal affairs unit. Also, SW helped develop a brochure on the Internal Affairs Unit (IAU) and its functions and where people can report their complaints that has since been made publically available. The National Police Reserve (these are police hired on a voluntary basis, trained and provided arms to support regular police in their work) and Northern Rangeland Trust (NRT) have now shifted from manual to electronic registers to monitor the use of firearms. SW provided technical support and equipment. / Kyrgyzstan/Tajikistan: Technical support was provided to: the Head of Development Department at MIA in a working group on drafting a law on civilian oversight over the police, by making recommendations to the working group to develop community security plans in a participatory manner. This was included into the law itself. Support provided to the Government's Council on Police Reform suggesting that the council should include CSOs as well, which has now happened and the Civic Union (CU) (SW’s partner) has observatory status. / South Sudan: Counter books have been developed and used in Kwajok, by PCRCs and local police to enable record keeping of incidents and ensure more participatory processes used by the police. / Kosovo : Ministry of Internal Affairs to adopt the annual working plan for 2014; Ministry of Internal Affairs to design the Action Plan for raising public awareness on community safety forums / The most significant challenge this year was the security situation in South Sudan and upsurge in violence. The devolution process in Kenya means governance and funding structures at the district level are being redefined, affecting engagement with authorities at these levels. The operating environment in Sudan to work on issues of governance and conflict remains restricted with the protests in September 2013 (protests) highlighting the Government’s policy of cracking down on any call for change and reform. In Kenya, long term engagement with local authorities has helped us to build a reputation that is now reflected in the extent to which government bodies are relying on technical support from SW.
Recommendations: Saferworld operates in volatile and deteriorating environments. It may be an interesting avenue of research to test the extent to which the community-based approaches to security advocated by Saferworld have strengthened communities and made them more resilient to broader conflict and insecurity. It is recommended that SW and DFID consider developing appropriate mechanisms to capture and disseminate this research and use this as the basis for workshops and written products. Timing to be agreed but within 18 months of this review. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: External actors (incl. donors, external governments, and / or relevant multilateral agencies) receive SW analysis, policy options and training aimed at influencing and strengthening their policies and approaches for engaging in fragile and conflict-affected countries
Output 4 score and performance description: A+ Outputs moderately exceeded expectation.
Indicator 4.1 Number and quality of research papers and policy briefings / reports published or electronically circulated by SW and disseminated to external actors / Baseline SW regularly produces quality research papers, policy briefings / reports and actionable recommendations. SW will continue to strengthen this service and address new and emerging issues including the influence of the BRICS states on peace and conflict, and the links between gender, peace and security / 2011/12 2012/13 2013/14 / Milestone 12 briefings, papers / reports have been published or electronically circulated An additional 20 Additional 40 briefings in this year / Achieved 78 58 54 (for 2013/14) / Variance 2011/12: +66 2012/13: +38 2011/14: +14 / Disaggregated Data* / Progress on expected results: / SW exceeded its targets of producing briefings for the year, with some key publications generating significant interest. For example ‘It’s Dangerous to be the First’ received a total of 3083 downloads, while ‘Five Barriers to Youth Engagement in Yemen’ received 1565 downloads. Also, ‘Gender, Violence and Peace: A post-2015 Development Agenda’ was also well received and quoted. SW has successfully led and completed two products for the DFID funded Conflict, Crime and Violence Results Initiative Helpdesk and supported two further products while a further 5 reports/analyses have been developed for the Swedish International Development Co-operation Agency (SIDA) Helpdesk. / Saferworld’s research, analysis, policy development and advocacy has had considerable success informing and influencing the policies and practices of external actors at international and national levels including significant examples from: governments (8 outcomes involving the UK, US, China, South Africa,); multilateral organisations (4 involving various UN bodies); the UN High Level Panel, and International NGOs. / Recommendation: Saferworld should provide more information on who uses their research and policy papers and, if possible how this has influenced policy/practice in their next Annual Review. / Indicator 4.2 Number of external actors receiving relevant, high quality training from SW, or participate in relevant and productive SW-facilitated seminars / roundtables, on engagement in fragile and conflict-affected countries / Baseline See logframe / 2011/12 2012/13 2013/14 / Milestone 50 people representing external actors have received training from SW, or participated in SW-facilitated seminars / roundtables An additional 50 1800 in this year. / Achieved 53 1771 2999 for 2013/14 / Variance 2011/12: +3 2012/13: +1721 2011/14: +1199 / Disaggregated Data* / Progress on expected results: / SW has exceeded expected targets, with significant progress in countries where SW has been approached by external actors (INGOs etc.) to provide training and support. For example: / Yemen: The EU and UK Embassy approached Saferworld to provide support on community security programming in Yemen. / On receiving the SW issue paper entitled ‘Addressing conflict and violence from 2015’ Justine Greening, Secretary of State for International Development, made reference to SW's quality analysis and said the briefing had stimulated discussion at Chatham House workshop attended by DFID, the Foreign Office (FCO) and Ministry of Defence (MOD). SW has provided training for a multitude of organisations from government bodies, to private companies, donors, think tanks, universities, civil society actors, and multilateral organisations. / Indicator 4.3 Number and quality of products (including briefings and submissions) provided to the UK Government by SW, which build on evidence and lessons learned from SW programme implementation / Baseline See logframe / 2011/12 2012/13 2013/14 / Milestone The UK Government has received 3 products An additional 3 products 14 over three years / Achieved 3 6 38 (29 for 2013/14) / Variance 2011/12: 0 2012/13: +3 2011/14: +24 / Disaggregated Data* 2013/14 / Thematic areas / Gender-related – 5 / Conflict sensitivity – 10 / China – 5 / Turkey – 1 / India – 1 / Russia – 1 / Post-2015 - 1 / DFID helpdesk - 6 / Progress on expected results: / The majority of briefings and products were sent to the FCO, DFID and the Stabilisation Unit. Many of the briefings focussing on country issues were also made available to the FCO and DFID offices in the respective countries – China and Brazil. Finally, 3 products were developed by SW for the DFID Conflict Crime and Violence Initiative Helpdesk and a further 3 in-depth responses produced for DFID country offices. / Recommendations: SW has usefully initiated research to monitor and evaluate the impact of its influencing work e.g. ATT. It is recommended that Saferworld continue to develop innovative practice beyond quantitative measures to capture qualitative impacts of their advocacy and incorporate their findings in time for the next Annual Review. SW, in consultation with CHASE, may also wish to consider developing stand-alone reports which examine the findings of their research in to influencing / Saferworld should increase the milestone indicators in the logframe for 2014-16 in order to ensure they are stretching, and to account for the fact that this area of work has exceeded the milestone indicators this reporting year. Also for the next two years of reporting, Saferworld should give more evidence of how their products are being used, as there is limited evidence here by which to assess SW’s progress. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 5: Saferworld, in consultation with DFID, develops and applies a robust monitoring and evaluation system which enables the identification, measurement and communication of results at output and outcome level, and demonstrates contribution to impact level
Output 5 score and performance description: A Outputs met expectation / Indicator 5.1 The quality of SW's monitoring and evaluation systems and approaches and the ability of SW to report fully and meaningfully against the indicators contained within the logframe / Baseline See logframe / 2011/12 2012/13 2013/14 / Milestone SW has established an institutional framework for M&E, including tools for capturing results at the outcome level of the logframe, and is able to report against the logframe in a meaningful and robust way. / DFID and SW have shared ideas relating to M&E and learnt from each other’s’ experiences SW has further strengthened its M&E framework and approaches, based on experience during Year 1, and are adapting its programming approaches based on lessons identified through M&E. / DFID and SW have continued to shared ideas relating to M&E and learnt from each other’s’ experiences SW has a strong M&E framework in place which has provided useful lessons for DFID and enabled SW to improve overall impact and effectiveness of its work. / Achieved See narrative on progress See narrative on progress / Variance / Disaggregated Data*
Progress against expected results: / SW has made significant strides in developing and learning from the implementation of the Programming, Monitoring and Evaluation framework and tools. These include: Conflict and Peace Driver analysis, Theory of Change, Actor and Power analysis, Outcome Mapping, Advocacy and Policy Criteria for Assessment (6 types of evidence), Evidence Box, and Quarterly Outcome Monitoring and Harvesting, with ranking for significance and contribution. Four countries have participated in extensive preparation for evaluations, which sees SW collate and structure its evidence in advance of bringing in external consultants to test and validate. SW’s new PRIMP approach (Programme Review and Improvement) is being trialled and will form the basis for SW’s attention to quality in the next strategic plan. The SW strategic planning process through 2013/14 saw staff actively utilising theories of change, the number of teams conducting quarterly outcome reviews has risen significantly, and over 75% of staff have been trained in the SW outcome harvesting approach. Partner organisations NODS and BRAC have also been trained in using the SW approach and have found it helpful. / SW, via a different grant, has also supported DFID, through the CCVRI helpdesk, on better understanding of impact assessments of security and justice programming, and appropriate approaches to impact evaluation of peacebuilding. Through the DFID learning partnership SW has also supported peer organisations by contributing to developing the partnership’s theory of change and actively contributing to the work of the Measuring Policy and Advocacy group. / Recommendations: / Saferworld have done a substantial amount of work to ensure that the outputs indicated in the logframe create the building blocks needed to achieve the logframe outcomes and to ensure sustainability. It will be important to continue to test the assumptions on which these changes have been made and to record the circumstances surrounding why they were made in order to capture learning, and key results over the next two years of the PPAs as part of ongoing Monitoring and Evaluation and delivered as a report during the final year of PPA funding. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Results and Value for Money

1.1 Has the logframe been updated since last review? / Saferworld submitted one revised log frame under the current funding period as a result of the Annual Review conducted in 2013 which recommended that Saferworld revise targets upwards for 2013/14. Changes have been made to outcome and output results to better reflect the increased capacity that the PPA grant has facilitated, in order to leverage more programme-specific funds. The changes have helped SW better communicate the extent to which strategic funding has helped develop greater organisational capacity enabling greater leverage of funds, which has in turn enabled greater level of impacts and number of beneficiaries that SW has been able to reach. The results achieved over 2011-14 are testament to the orientation of the new organisational strategy and structure. These results were essential in developing and refining the 2014/16 logframe. For example, the 2011 logframe references 12 countries while the 2013/14 logframe includes South Sudan, Kyrgyzstan and Tajikistan in addition to the original 12 countries, demonstrating the effects of decisions made using the PPA funds. The 2014/16 logframe, taking into consideration the results from 2011/14 now also includes Egypt while removing Sri Lanka where SW no longer operates. / 1.2 Overall Output Score and Description: A+ Outputs moderately exceeded expectation. / 1.3 Direct feedback from beneficiaries / SW’s relationships with beneficiaries are built on partnership models that empower and develop capacity, for local actors and individuals to support longer term peace and security. Ownership of projects and their resulting outcomes is essential, for SW, for sustainable impact. To ensure sustainable solutions, therefore, the concept of beneficiary feedback is essential. Beneficiary feedback, for SW, is more than simply listening to and receiving feedback from beneficiaries. It involves giving beneficiaries the voice and tools to effect changes in their own lives, which SW supports. / Feedback from community groups is formally received through a variety of mechanisms across SW programmes. SW’s community security and mobilisation approach is built on community ownership and building relations between communities and authorities. Community security groups are developed with the support of SW and local partners but are, essentially, operated by individuals elected from within the community. Vulnerable and marginalised communities are supported to participate actively in the groups. In Nepal the Dalit community and women have significant representation in these groups while in all other countries – Bangladesh, Caucasus, Central Asia, Kenya etc. – women are adequately represented. These groups identify and prioritise programme focus areas (action plans) and are supported to deliver the plans by SW and Partners. This approach puts ‘immediate beneficiaries’ at the heart of project activities and planning. / In Kenya, feedback is acquired through community policing committees that are actively operating, with meetings held every week. These structures are organised to mobilise a majority of citizens to identify criminal groups and arms smuggling groups and locations that are hotspots. While these structures help get feedback from communities, they also serve the dual purpose of empowering communities to monitor and provide feedback on situations in their own communities, and to make changes with local authorities in the long term. This approach is also used in Central Asia, Kosovo, Caucasus and Nepal with tracker perception surveys to generate information annually on general perceptions of security in the wider community. SW recently started a project targeting the population living in direct proximity to the Armenian-Azerbaijani border/frontline by using an innovative tool - visual 3D imagery provided by Google Earth – to support them to map incidents that target civilians and their properties. SW’s has also previously used this platform on the Georgian/South Ossetian Administrative Boundary Line (ABL), allowing community representatives to share regular reports about security trends and incidents in their communities with security providers for joint analysis and response. Once again, this puts beneficiary voices at the centre of programme design and response. / When engaging with formal civil society partners, SW’s partnership toolkit provides guidance on how to regularly reflect and review the partnership to assess progress and measure success. The toolkit states that “these meetings [review and reflection] should also be seen as a way of promoting and strengthening communication and information sharing with partners” (pp30). The toolkit suggests these meetings be held every 6 months or annually. With policy makers (proximate beneficiaries) SW receives feedback through formal evaluation reviews of programmes (a recently completed evaluation for the Nepal programme) as well as more frequently at meetings and workshops through feedback forms.
1.4 Summary of overall progress / SW report that it has more than exceeded results in the logframe. Initial targets for outcome 1 (number and quality of community security plans) were set at 16 for three years and then upgraded to 85 plans for the 2011/14 period, with the final total at 110. This trend can be seen across all the indicators, representing the impacts of the investments made in organisational effectiveness through the PPA grant. The three key successes over the past year include: / Extensive reach of SW’s community security work: SW’s community security work in Kenya, South Sudan, Bangladesh, Nepal, Caucasus, and Central Asia has not only grown in numbers of communities that SW now works with but has also begun to demonstrate stronger community ownership of the approach (see Section 3, Outcome indicator 1). / Stronger relationships between communities and authorities: building relationships between authorities and communities is challenging but fundamental to SW’s community security approach. Nevertheless, SW has seen dramatic progress in shifts in relations between communities and both local as well as national authorities; where trust has grown (in the case of Nepal, for example), local authorities actively respond to community concerns (Central Asia for example) and the actors jointly work on projects (Kenya for example). / Policy achievements: SW’s policy and advocacy work has seen exemplary developments over the past year. Some noteworthy examples are: / The adoption of the Arms Trade Treaty by the UN General Assembly, and subsequent signing by Britain and 117 additional states (13 ratifications). Error! Reference source not found. SW contributed to achieving this outcome, working in key CSO coalitions, advocating ratification at every opportunity and as contributing experts on numerous bodies, / Significant in-roads into the post-2015 agenda where all of SW’s key asks for the post-2015 framework were taken up in the final HLP report, / SW’s work in China has also made remarkable progress with uptake among high-level officials, private companies like Sinohydro, and high-ranking Chinese military officers, acknowledging the need to combat diversion of Chinese SALW and ammunition and improve end-use monitoring and verification.
1.5 Key challenges / There are ongoing security concerns in most of the countries that SW works in. This includes the upsurge in violence in South Sudan, pre-election violence in Bangladesh, border skirmishes between Kyrgyzstan and Tajikistan, and general security concerns in Kenya and Somalia. / Restricted political and CSO space in a number of countries continues to compromise SW’s and partners’ ability to work, as is the case politically in Sudan, and in Pakistan and Kenya where there are also issues around CSO registration and MoU procedures. / As SW has grown, the rise in number of partnerships has also brought with it greater risks, including greater potential for corruption and other reputational issues, for example, international concerns about affiliations with terrorist groups or financing. / The key issues that were highlighted in the 2012/13 report that were addressed in 2013/14: / The importance of investing in staff. Given the growth in numbers of staff, emphasis has been placed on ensuring stronger human resource management systems and processes, with adequate support and development to retain and maintain staff commitments. A new performance management system has been rolled out, focussing on professional development and better management of staff. / SW’s risk management approach has been consistently strengthened with regional (and where relevant country) risk management teams in place with a revised set of Standard Operating Procedures (SOPs). Kenya and Somalia, for example examine risk at their team meetings while in Yemen similar processes are in place. Finally, a risk management team in London meets every 6 weeks to respond to upcoming issues. SW has also completed and updated DFID’s Overseas Security and Justice Assessment (OSJA) to substantiate organisational efforts. / The feedback from DFID last year suggested stronger emphasis on drawing out SW’s contributions to outcomes (see outcome section), which has been specifically addressed in the 2013/14 report. More importantly, a focus on SW contributions to outcomes has been emphasised in the outcome monitoring approach for SW (developed over the funding period), and training on this approach has been provided to country staff through workshops as well as the PPA data collection process for 2013/14.
1.6 Annual Outcome Assessment / Outcome indicator 1 Number and quality of community security plans developed and implemented by communities members in Georgia/Abkhazia / Kenya / Kyrgyzstan/Tajikistan / Nepal / Pakistan / South Sudan - in collaboration with local authorities - which provide for joint action to counter threats to security and build peaceful communities / There has been significant progress in the development and implementation of community security plans over three years. SW’s contribution towards outcomes using its community security model centres on close accompaniment to partners, and the communities they support, plus providing technical and financial support to partners. The quality of plans is demonstrated through three markers of progress (for which we’ve provided examples): / 1: Visible outcomes: from collaboration between authorities and communities SW has continued to support existing groups to demonstrable success. / 2: Increased trust between communities and authorities: Where communities have been hesitant they now openly discuss concerns that in the past would have been sensitive. Trust and communication has led to increased confidence in communities to take on complex security issues in their locality. / 3: The level of initiative taken by communities and authorities: Communities and authorities across SW’s programmes are taking greater initiative after seeing benefits accruing from joint ownership of action plans. / Indirect Outcome Indicator 2 No. of community security action groups (see output indicator 1.1) reporting that authorities have increased their understanding of community security needs and are addressing them more effectively as a result / SW’s community security approach bridges the gap between actors to build more trust and deliver greater potential for peace conditions. Saferworld state that changes in authorities’ understanding over the year was seen in greater and more informal contact with communities, needs-based services provided, and direct appreciation by communities of government bodies. Examples of change below are representative of changes seen across majority of SW’s work. Specific examples include: / Kyrgyzstan: The Territorial Council responded to the needs of the CSWG by raising match funding for the refurbishment of a transformer, which was causing conflict within the community and with authorities who had failed to address the issue. In addition juvenile police inspectors are directly engaging, in more social and informal ways, with communities and young people. / Nepal: there is evidence of real change in relationships and the approach of police to security. A shift in attitudes of communities towards the police is demonstrated through the following quotes from community members and police on the way they engage: ‘we need your support and want to support you to make things better here’. Police officers are more considerate towards the needs of the community, facilitating ‘newfound respect for the law thanks to better police responses and prosecution rates’. One senior policeman said ‘we have a moral responsibility to protect and serve the community, and through the CSWG we have promised to do that. They have changed the way we work’. / Bangladesh: For the first time, many communities engaged directly with local authorities and in response local religious leaders and authorities contributed to reducing gambling hotspots. All CACs reported closer relationships with police and local authorities. / South Sudan: The PCRC now has greater involvement of communities (in Tonj North a new PCRC established through SWs work), and Counter ‘Green’ Books have been established by the CSWGs, to enable record keeping of incidents, which are then reviewed and responded to by the weekly Security Committee. / Outcome Indicator 2 Number and description of civil society organisations (CSOs) in conflict-affected countries who have the skills, confidence and capacity to identify factors undermining peace and security and to effectively seek to address them / SW’s strong belief in working in partnership influences how CSOs are supported through close accompaniment, through training, small grants, and technical support on community security, oversight of police, community policing, conflict sensitivity, peace-building and advocacy. This approach, which the Capacity-building Audit rated highly, means SW builds long-term relationships with partners. This capacity-building is bespoke designed, and intended to ensure that ‘indirect’ outcomes are accomplished. Examples include: / South Sudan, Bangladesh, and Yemen: SW has invested in training of partners TOCH and KAUDA, BRAC and NODS, to ensure full understanding of and commitment to community security methodology, conflict and gender-sensitivity, and measuring and understanding change. These trainings use SW expertise, built up from work in Kosovo, Kyrgyzstan/Tajikistan and Georgia/Abkhazia with partners over the last three years, and with policy input from the Gender Adviser. / Somalia: PUNSAA (Somalia non-state actor platform) secured a mandate from the Transitional Puntland Electoral Commission (TPEC) to train and deploy Domestic Election Observers and create a Civil Society Coordination Committee. This is a transition in the role of CSOs from providing services to being watchdogs. It follows a successful trial using DEOs in Somaliland Elections set up by SONSAF. / CSOs supported by SW have established themselves as go-to organisations on peace and security issues. Government bodies now approach these CSOs as experts. / Outcome Indicator 3 Number and description of authorities who develop new or significantly improved approaches, strategies and/or policies that directly respond to and mitigate conflict, and whose practices start to change as a result / SW works directly, and through CSOs, to support authorities to adopt conflict sensitive, conflict prevention and peacebuilding approaches. SW’s approach to influence policy and practice by authorities is multipronged and functions at different levels of society. Examples include: / National level: In Kenya two of SW’s pilot sites (West Pokot and Isiolo) developing approaches for arms control were endorsed by the Kenya National Focal Point on Small Arms. The SW sites will (i) develop guidelines on stockpile management and (ii) test the implementation and thus support future arms control work of the government. In Yemen, the SW team advocating to the Head of security in the capital, members in the national dialogue (post revolution), victims and other youth and media activists, and through work in the Community Action Groups (CAGs), managed to get the government to issue the first decree to prevent carrying weapons in the street on October 5th. A notable achievement by SW was the election of two female ministers in Somalia through the advocacy efforts of PUNSAA (SW partner). In South Sudan, SW has been working with the CCSSAC Bureau for a number of years, and there has been a firm political commitment to pass the Small Arms and Light Weapons bill especially from Ministry of Interior. / Local level: In Shida Kartli (Caucasus) two villages – Atotsi and the Chvrinisi - were provided primary health care facilities by local authorities as a result of advocacy by SW and partners with Ministry of infrastructure and Regional development Interagency Commission. In Gori (Caucasus) authorities, for the first time, consulted local communities on models for municipality divisions, as a result of a meeting facilitated by SW, with community reference groups and an expert from the interagency group on decentralisation report. In Nepal the majority of CSWGs received financial support to carry out their activities. A new police post was established in Ayodhyanagar and a temporary police post was re- established in Kachanapur, under the command of a Nepal Police Assistant Sub-Inspector with 11 police officers including two female police officers. / Outcome Indicator 4 Number and description of external actors (including donors and multilateral agencies) who take up SW (and partners') recommendations on policy and practice in conflict-affected states, and in doing so increase the potential for their policies and actions to more effectively prevent conflict and build peace / Key highlights include: / African Union, UK and US on Sudan: SW’s work with policy-makers on Sudan has seen changes: as one of four civil society representatives, SW met President Mbeki, as the head of the African Union High-Level Implementation Panel for Sudan. A member of Mbeki’s staff described the meeting as “brilliant” to a third party and the Panel subsequently sought advice from Sudan Democracy First Group (SW’s partner). SW was also asked to contribute recommendations to HR 503, a US House of Representative Foreign Affairs Subcommittee Hearing on Sudan and South Sudan. / Post 2015 Agenda: All of SW’s key asks for the post-2015 framework were taken up in the final High Level Panel report released on 30 May 2013 and the final UNICEF, UNDP and PBSO ‘Report Of The Expert Meeting On An Accountability Framework For Conflict, Violence, Governance and Disaster and The Post-2015 Development Agenda’ was significantly influenced by SW. / Gender: UN Women’s Chief Adviser on Peace and Security approached SW about doing a joint briefing on gender, peace and security and post-2015 after reading and responding to SW papers on inequalities and post-2015 and on targets and indicators. Nearly all of SW’s recommendations to the FCO on the development of the 2014 – 2017 National Action Plan on Women, Peace and Security were incorporated into the Gender Action for Peace and Security submission. / Arms Transfer Controls: A significant success was the completion of the adoption of the Arms Trade Treaty by the UN General Assembly, and subsequent signing by Britain and 117 additional states. SW contributed to achieving this outcome, working in key CSO coalitions and as contributing experts on numerous bodies.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / 2.2 Key cost drivers / The core costs in the delivery of SW’s programmes is captured in the allocations below: / Staff costs £3.85m (43%) / Accommodation and meeting hire costs £830,000m (9%) / Travel costs £616,000 (7%) / Per diems for staff, partners and programme participants £529,000 (6%) / Consultants £341,000 (4%) / This represents 70% of Saferworld expenditure, and covers key cost drivers, it also reflects how SW works to realise impact: in essence, through accompaniment and support with partner organisations, through research and analysis; and by advocating for policy developments to effect long-lasting change. To be effective in all this, technical competence (as experts for example in security and justice and complex contexts) is essential, as is developing and working in dynamic partnerships. Hence, staff expertise and context knowledge is a prominent cost driver for Saferworld across all its work. / In recognition of this major cost driver, SW monitors and controls these costs by: / Creating an organisational environment conducive for collaboration and joint learning, such as through joint learning platforms and developing an intranet system / Introducing (early 2014) a new performance management system to support greater effectiveness and efficiency, with a focus on improving staff development. / Conducting annual reviews of salaries in all countries by the HR Director and Executive team by:- / i) assessing financial and salary conditions and local inflation, as informed by the country managers, to arrive at a proposal for any pay adjustment; / ii) the executive team considering proposals for each country in the light of market conditions, staff recruitment and departure, and making recommendations; / iii) a Board sub-committee review, confirming any proposed changes, which is finally voted on by the full Board in October each year / SW’s travel costs (second highest) are paid via two London-based preferred suppliers. Individual trips are planned by staff and approved by line managers. Annual reviews of both suppliers are undertaken. / Following a similar analysis in last year’s report, SW has shown a percentage reduction in overall core costs (80-70%), including staff costs (from 46% to 43%). Similar reductions are also evident in all of the other core costs cited. This reduction, as a percentage of overall expenditure, has resulted in part from an organisational focus on working through more partners. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / None. / 3.2 Where an evaluation is planned what progress has been made? / The PPAs as a whole are served by an umbrella evaluation strategy, the first of its kind for DFID, which ALSO encompasses the Global Poverty Action Fund. This strategy examines progress at fund and at individual, organisational level. Following the announcement of the extension to the PPA fund in 2013, the evaluation strategy was reviewed and, in addition to the individual progress reviews (IPRs) and meta evaluation that took place in 2012, a further two evaluations are planned for 2014/2015 and 2016/17. The evaluation is managed by an externally contracted evaluation manager. / The 2014/15 evaluation has started and focuses on the assessment of the fund-level effects of PPA grants. This fund-level evaluation will use 12 organisations to illustrate the effects of the PPA fund and evidence from all 41 organisations to evaluate progress and outcomes. The aim is to provide timely, fund level evaluation information for the design of any future strategic funding modalities in 2014/15 ahead of fund completion in 2016. The evaluation in 2016/17 will focus on the impact of PPA funding for organisations.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / From an organisational perspective, all of Saferworld’s Strategic Operational Procedures have been upgraded, and a risk management system is now in place across the organisation (Risk Management Team, security planning, security training, Security Focal Points). All SW’s working policies have been revised, reducing any reputational risk for SW, its donors, and partners. Institutional risk management generally (terrorism, corruption, auditing, procurement) have also been prioritised. SW’s partnership-model is, fundamentally, an approach to ensure sustainability of impact. It is through partners, CSOs, and various platforms that SW ensures the impact generated by its programmes is upheld. / SW’s work in-country can be severely affected by social unrest in its areas of operation. From a programmatic perspective, Saferworld has reflected that SW’s risk management approach has been consistently strengthened with regional (and where relevant country) risk management teams in place with a revised set of Standard Operating Procedures (SOPs). Kenya and Somalia, for example examine risk at their team meetings while in Yemen similar processes are in place. Finally, a risk management team in London meets every 6 weeks to respond to upcoming issues. SW has also completed and updated DFID’s Overseas Security and Justice Assessment (OSJA) to substantiate organisational efforts. / Other key areas of risk mitigation include: / Somalia and Somaliland: Recognising the limited political space for CSOs and the lack of democratic alternatives beyond clan interests, SW has long supported the development of non-state-actor (NSA) platforms in Puntland (PUNSAA), Somaliland (SONSAF) and South Central Somalia (SOSCENSA). They act above individual clan interests, focusing on issues of vital importance to all citizens in these three areas. At the time they were also meeting the demand and interest of the donor community in their efforts to address issues of participation of civil society and governance in emerging states. They have since become examples of merging traditional and modern structures: on the one hand seeking consensus within and across specific interests, and on the other introducing active citizenship and a new dynamic between government and constituents. / Kosovo and Central Asia: SW’s approach, which includes capacity building of CSOs, is sustained through the actions of local CSOs. In Kosovo, for example, SW’s partners (FIQ and AKTIV), recognised the importance of networks as an instrument of effective trust-building, using advocacy about common interests. They set up two platforms (the CPF and FS) for collaboration on security issues between the North and the South. In Central Asia, the Civic Union was set up by SW as a local network of CSOs to advocate for and provide technical support for security sector reform. SW has provided technical support and capacity. These initial efforts have been sustained by the CU, which has now established itself as a legitimate voice in police reform, and the Kyrgyz police reform law now includes excerpts from a draft police reform law that was developed by the Civic Union (CU).
Risk of funds not being used as intended / Saferworld underwent pre-grant due diligence checks carried out by KPMG. The pre-grant due diligence assessed capacity to manage the proposed level of DFID support in the following areas: / Governance / Financial Capacity / Operational Capacity / Value for Money / Results / Satisfactory completion of the due diligence process was required before any money was disbursed. This helps to reduce the risk of diverted funding while establishing an environment of accountability and transparency. Organisations also had baseline up-dated due diligence assessments carried out in March 2014 to ensure that processes and strategies were current and complementary to DFIDs due diligence framework and modules. Saferworld is adhering to the outcome of the March 2014 due diligence assessment as part of their PPA extension MOU. / Saferworld has not suffered any loss or misappropriation of funds in the year. Saferworld has a policy on Anti-Bribery and Corruption which is reviewed regularly to ensure it promotes best practice. The purpose of Saferworld’s Bribery and Corruption policy is: / 1) To set out the responsibilities of Saferworld staff and those working for us, in observing and upholding our position on bribery and corruption. / 2) Provide information and guidance on how to recognise and deal with bribery and corruption issues. / This policy applies to all Saferworld’s staff, consultants, seconded staff, interns and any other person associated with Saferworld wherever located. Top level commitment is an essential feature of compliance of the Bribery Act and colleagues with management responsibility are expected to share Saferworld’s commitment to observe and implement the spirit and terms of this policy. / The subject is actively discussed in Executive team meetings and forms part of the Programme manager finance training sessions held in the year. / 4.4 Climate and Environment Risk / As a second tier organisation working on conflict, peace and security, SW does not directly engage in traditional Disaster Risk Reduction or mitigation programming. However, SW’s primary focus is to mitigate/reduce the overall incidence of conflict, which is, in part, driven by the effects of climate change. Therefore, SW’s approach is to make communities more resilient, whatever the cause of the conflict may be, recognises the role that climate change plays in exacerbating and/or instigating conflict. Nonetheless, SW is committed to addressing its carbon footprint and impact on the environment. The main focus of this commitment is made in SW’s Environmental Policy, which is currently under review. SW staff undertakes frequent travel and a concerted effort has been made to understand the environmental impact of air travel. Over the past 12 months the total amount of CO2 emissions from SW’s travel was 564 tonnes. With this as a baseline, SW now plans to develop a plan to offset these emissions. / Closely aligned to SW’s Environmental Policy is the environmental credentials and commitment of the SW premises in London, owned and managed by Ethical Properties. Ethical properties make a formal commitment to only working with ethical businesses, which are those that do not cause damage to the environment through their activities (among other requirements). To work in an ethical properties building organisations have to fulfil one ‘essential criteria’ which is to work in line with ‘[a] defined social purpose that accords with the company’s overall objective of building a sustainable society and a sustainable environment’. There are four key components of day-to-day operations that ethical properties require tenants (i.e. SW) to commit to: / Energy and Water Efficiency: Aiming to minimise energy use, carbon dioxide emissions and water use, maintaining levels down to below the best practice recommendations of the Building Research Establishment. / Minimising Waste: Aiming to maximise recycling and minimise the use of non-reusable and non-recyclable products such as polystyrene. / Green Commuting: Ethical properties discourage car use and encourage walking, cycling, and the use of public transport. / Environmental: Tenants are expected to ‘sign up’ to environmental practices such as use of recycling facilities, ensuring heating is sensible and turning off equipment and lights when not in use.

5. Value for Money
5.1 Performance on VfM measures / The PPA grant contributed directly to the strategic development of the organisation in a number of critical areas considered necessary for the fulfilment of SW’s goals, especially in a more effective and sustainable manner, including: / 1. strengthening impact, learning and accountability, / 2. enhancing organisational structure and capacity, / 3. investing in people, / 4. strengthening financial and other operations systems generally, / 5. consolidating and diversifying sources of funding. / During the reporting period, a number of specific investments under the priority areas cited above have contributed to SW’s overall effectiveness, such as: / Further training and development of systems to gather evidence, learn about SW’s results, and communicate them more readily, has led to an increase in outcome-focused programming; / The placing of London-based roles to regional and country offices, including fundraising functions and four finance manager posts (Kenya, South Sudan, Uganda and Kyrgyzstan). An example of the VfM factors that shaped these decisions included (i) costs of finance managers in regional offices are, on average 40% less than in London, and (ii) the potential to improve financial management at project sites for better long term efficiency; / Data and analysis on organisational capacity was also enhanced in 2013-14, made possible by the restructuring of SW’s Chart of Accounts and core data in 2012-13. New analysis using headcount in each location informs us of salary cost and overhead cost per head for each country. It is used to assess whether the strategic value of the country is in proportion to the costs of operation. In addition, donor and unrestricted funding of each country can be compared. / Practical improvements in the quality of SW’s communications (internally and externally) has made SW’s advocacy more effective, and increased the numbers of people accessing its reports and recommendations. / Another example of how the strategic use of the PPA grant generated VfM was the funding directed to the South Sudan programme in 2012, when donor funding was restricted. A core (reduced) programme was put in place supported by PPA funds (for 5 months), as a strategic priority. By retaining a core capacity the programme grew in 2013/14 and is expected to be SW’s largest country programme in 2014-15 with income above £2 million and with no support from unrestricted grants. The cost and upheaval of closing the programme and reopening it when funding was available would have been significantly more than this figure, with the likelihood that the planned activity level would also not be achieved, making this strategic decision both economical and effective in the long run. / 5.2 Commercial Improvement and Value for Money / As SW is not technically a service delivery organisation, it has limited procurement functions to undertake. However, SW reports it retains up to date procurement policies (for purchases over £50,000), which are observed across the organisation. Unless pre-qualified, SW ensures consultancy tenders are published and reviewed before contracted. / 5.3 Role of project partners / Saferworld reports that the actions of others is a central and defining approach in the achievement of its goals towards greater security and peace, and lies at the heart of SW’s understanding of how it contributes to change. Saferworld achieves through a range of alliances, associations and networks, but also through a commitment to ‘partnership’ with key interlocutors with potential to positively influence SW’s ultimate target groups. Through working with a range of actors including community groups, local civil society organisations, academics, NGOs, security and justice institutions, governments, private sector organisations and international and multilateral bodies: SW views a partnership as signifying a closer relationship governed by shared regulations, values and principles – such as transparency, accountability and mutuality – and ultimately goals based on clear analyses of needs. SW states their partnerships are an important way to increase the relevance, impact and sustainability of its work, and through imparting and gaining knowledge, skills and learning to partners. The main aim of this is to build the capacity of its partners to the point where they can operate effectively without SW direct support. Over time, Saferworld expects the nature of its engagement to change, and ideally reduce, as the strength and role of its partners increases. / Saferworld recently concluded a capacity building audit which they state demonstrated the varied partnership and capacity building approaches that SW works across. These take place at different levels, with different groups, and with varying degrees of endeavour and complexity. Given their centrality to SW’s work, it has established an internal working group to upgrade and develop SW’s approach and improve SW’s resources and skills base. / Currently SW has formal partnerships with over 30 organisations, working in 16 countries, and a range of other arrangements and working agreements – such as with senior professionals (SW’s Associate Network – SWAN), strategic links with Police institutions, or collaborates with international peers such as International Alert, CDA, Search for Common Ground, Conciliation Resources, InterAction etc. Further examples include: / Partnerships to support local communities to mobilise: By working with community-security groups or community reference groups worldwide, with the aim of empowering community groups with tools to build relations with local and national authorities for long-lasting peace. SW’s role in these arrangements is to facilitate and provide platforms for community security groups to communicate and collaborate with local authorities. / Partnership to build capacity and learn: / i) By working with local organisations (such as CWIN and INSEC in Nepal, FTI and CU in Central Asia; and AKTIV and FIQ in Kosovo among others). These partnership relationships largely focus on capacity building and technical support. / ii) By working with a large southern NGO, as represented by SW’s growing partnership with BRAC (the largest development NGO in the world with operations across 69,000 villages and around 125,000 employees in Bangladesh). This is unlike any other partner SW has engaged with. / iii) While BRAC has well-developed infrastructure across Bangladesh and extensive institutional and operational systems they have limited focus and technical capacity on issues of peace and security – a central reason for the close collaboration (SW provides a distinct ‘technical assistance’ and ‘mentoring’ role), and a means to replicate key approaches to security and justice, at scale. / iv) Another example of this approach (facilitating more inclusive ways of working as a ‘community security’ specialist partner) is with NODS in Yemen. NODS has strong links to the Muslim brotherhood in country, and therefore an impressive outreach. NODS now have 2 female staff as a result of SW’s engagement. / Sustained collaboration to influence changes in approaches to conflict. / i) By working with donor-agencies in a sustained manner (such as with DFID, EU and USAID and with relevant departments in Norway, Sweden and Netherlands,) to influence policy and practice and facilitate more participatory and conflict-sensitive policy processes. / ii) By working closely with host governments such as with the Government of Kenya in order to support police restructuring and standards; or in Kyrgyzstan with the Ministry of Internal Affairs to support police reform and more participatory community security approaches. / iii) By working to bring government representatives and/or commercial players closer to SW partners such as in the case of South Sudan and China (including Sinohydro from China), to promote conflict sensitive approaches in China’s engagement with conflict-affected states. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The review team appreciated the substantial effort made by Saferworld to provide a thorough response to the self-assessment review template. The feedback below reflects our assessment of the Annual Review and of progress made to date. We concur with Saferworld’s own self-assessment that the programme should be scored an overall. Saferworld completed a self-assessment set out by DFID’s Civil Society Department. It should be noted that Saferworld has reported that word count constraints and the way the self-assessment template was laid out made it difficult for SW to create links between outputs and outcomes, as well as to identify key challenges by context. This feedback will be given to Civil Society Department to inform next year’s PPA Annual Review process. Bearing this in mind, key concluding comments on the PPA are as follows: / Saferworld should consider citing less numbers of examples but provide more detailed analysis and narrative which discusses SW’s inputs and how these have delivered the intended outcomes/puts. A more balanced and analytical narrative could be created by identifying challenges and discussing them in relation to delivery of outputs/comes. / Surrounding the challenges faced this year it would be interesting to note if there is any evidence to suggest that the work of SW meant that the declining security situation was less pronounced in those communities within which they had worked? / In relation to Value for Money, Saferworld should consider whether its analysis surrounding traditional cost-comparisons are accurate. Is it possible to track costs and benefits over time from a management perspective i.e. is it getting more expensive or less expensive over time to deliver community security plans in a particular community. / Positive gains have been made surrounding SW’s approach and rationale for delivery through local partner organisations with useful illustrative examples cited. Over the future lifetime of the PPA, it will be useful to test out the extent to which SW’s approach does lead to sustainability. / It is positive to see Saferworld considering the linkages between Climate Change and Conflict. Could SW highlight any examples where their approach to community mediation, for example, has touched on climate/ environment issues e.g. land disputes, resource disputes, and response to natural disasters? / Recommended Actions: / Where indicators mainly focus on quantitative elements of Saferworld’s work, it is recommended, for future reporting, that SW set out how the qualitative elements are determined (e.g. skills, confidence and capacity) and evaluated in order to better assess Saferworld’s achievements. / It is recommended that phrasing of the policy achievements be based on more analysis of the extent to which SW’s activities have influenced and delivered the stated policy results - citing external partners’ feedback which underlines the extent to which SW policy papers/ recommendations were directly taken on board by governments etc. / The section on beneficiary feedback provides detailed information on how beneficiary feedback is obtained. It is recommended that SW also include more of a focus on what this feedback is in next year’s Annual Review. / It is recommended that Saferworld consider planning to capture Beneficiary Feedback in specific products/reports etc. Also, more information about the approach and toolkit would be helpful to ensure we have captured SW’s approach to beneficiary feedback and how SW internalise and use that information both at the micro-project and broader macro-organisational level. / SW has usefully initiated research to monitor and evaluate the impact of its influencing work e.g. ATT. It is recommended that Saferworld continue to develop innovative practice beyond quantitative measures to capture qualitative impacts of their advocacy and incorporate their findings in time for the next Annual Review. SW, in consultation with CHASE, may also wish to consider developing stand-alone reports which examine the findings of their research in to influencing. / Saferworld has done a substantial amount of work to ensure that the outputs indicated in the logframe create the building blocks needed to achieve the logframe outcomes and to ensure sustainability. It will be important to continue to test the assumptions on which these changes have been made and to record the circumstances surrounding why they were made in order to capture learning, and key results over the next two years of the PPAs as part of ongoing Monitoring and Evaluation and delivered as a report during the final year of PPA funding. / Saferworld should consider providing an in-depth case study in the final year of the PPA on one particular country of intervention covered by the PPA (agreed by CHASE) where there has been significant ‘over delivery’ against milestone targets to test the extent to which the community-based approaches to security advocated by Saferworld have strengthened communities and made them more resilient to broader conflict and insecurity. / The extension logframe for 2014-16 was set up utilising the 2012/13 results as the baseline figure. Given that some of the milestones in 2013/14 have been substantially exceeded, it would be prudent to now revisit the logframe for the 2014-16 extension periods in order to ensure that the milestones are rigorous, challenging and set a high level of ambition for the next two reporting years.

8. Review Process
This Annual Review was conducted by the Security and Justice Team in CHASE following the guidance note issued by DFID’s Civil Society Department. Saferworld submitted a self-assessment annual report of their progress and performance against the PPA log frame during this third year of PPA funding. DFID reviewed this annual report and provided feedback to Saferworld on both strengths and weaknesses. Due to time and resource constraints, it was not possible to conduct interviews with beneficiaries or conduct field visits to verify the claims made in the self-assessment.