Annual Review - Summary Sheet

Title: / Central African Republic (CAR) Emergency Response
Programme Value: £40,000,000		Review Date: July 2016
Programme Code: 204852	Start Date: / 17 July 2014	End Date: / 31 December 2016

Summary of Programme Performance
Year	2014/15	2015/16
Programme Score	A	A+
Risk Rating	High	Severe

Summary of progress and lessons learnt since last review

Overall the programme has made good progress and achieved its stated outcome of significantly reducing suffering and saving lives among the population in CAR as well as refugees in Cameroon. The cumulative number of people reached to date under the programme is 1,422,854 vs the target of 1,460,735 indicating that already 6 months prior to the conclusion of this program the target number of beneficiaries have already almost been reached. UK funding has helped agencies provide a successful response to emerging needs and bring assistance up to minimum standards. Based on this we assess the programme is well on its way to achieving its outcomes.

In terms of progress made within the reporting year, clear achievements have been made in terms of strengthening of monitoring and evaluation as well as procurement systems. Though further push is needed in terms of pipeline management as well as gaining a better understanding of the barriers to access to healthcare, we believe that the current partners will be able to successfully deliver the desired program outcomes and we will continue to ensure that the gains made thus far are not lost. Additionally after a push from DFID partners are now reporting more cases of suspected fraud which indicates a better understanding amongst partners of the DFID definition of fraud as well as the systems and procedures around reporting and management of suspected cases and also indicates that partners are dealing with suspected fraud in a transparent manner. To date the experience has been that partners are dealing with suspected fraud cases in a timely and appropriate manner.

Summary of recommendations for the next year
CAR
- Monitor Solidarities International (SI) consortium endeavours to reinforce income generating activities (IGA) sustainability.
- Monitor Food and Agriculture Organisation (FAO) 2016 post-distribution monitoring and post-harvest monitoring to assess overall results and seed qualities.
- Monitor partner efforts to analyse and improve health service utilisation rates under the 2016-19 CAR Humanitarian and Recovery Programme (CHURP) project.
- Monitor International Medical Corps (IMC) led consortium stock levels of essential drugs and follow up on barrier analysis.
- Follow closely the implementation under Cordaid, including their plans on coverage expansion and the potential roll out performance based management system.
- Monitor progress of setting up a technical committee to ensure a cohesive approach amongst IMC consortium partners.
Follow up on protection mainstreaming in Common Humanitarian Fund (CHF) funded projects and ensure that CHF reports to board changes in their analysis on partners’ risk levels, and other relevant points including losses and fraud.
Monitor results and impact of International Committee of the Red-Cross (ICRC) community based protection.
Ensure that the CHF performance system is used and informs allocations and monitoring and evaluation (M&E).

Cameroon
- Work with World Food Programme (WFP) to look at strategies for decreasing defaulter rates in the nutrition programme and to ensure M&E adequately tracks increases in negative coping mechanisms.
- Monitor WFP pipeline management to ensure there are no ruptures in supplies.
- Follow up with UN High Commissioner for Refugees (UNHCR) both at country level and at HQ level to level to ensure that they step up in terms of improved coordination and partnerships.
- DFID to discuss UNHCR’s reporting delays with CHASE and UNHCR HQ.
- Continue to monitor UNHCR delivery in Chad and in Cameroon including funding pipelines and UNHCR’s ability to achieve coverage of assistance across operations and sectors.
- Future DFID funding to START on longer-term response should be conditioned by the implementation of lessons learnt agreed at the June 2016 workshop.

Risk
- Update the risk register in line with DFID Risk Management Framework.
- Monitor FAO’s development of a risk management framework.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204852/documents / Business Case 5084736 / Business Case Addendum 5401581
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204852/documents / Logframe 5518518

This annual review covers projects that have been implemented from 17 July 2015 to July 2016, although the programme ends in December 2016 due to the FAO cost extension. This annual review has been completed by members of the Africa Humanitarian Team in the Africa Regional Department, and is informed by quarterly and interim reporting from partners, drawing on programme visits to CAR and Cameroon.

What support is the UK providing?
The CAR Emergency Response programme was approved in 2014 and provided a package of support totalling £40 million. The programme addresses life-saving and protracted needs of conflict-affected populations in CAR and of CAR refugees in Cameroon and Chad who have fled the violent conflict since December 2013.

Agencies - CAR response	Total	Description
Common Humanitarian Fund (CHF)	£6m	Emergency multi-sectorial assistance
International Committee of the Red-Cross (ICRC)	£2.2m	Emergency and protracted assistance and protection
Food and Agriculture Organisation (FAO)	£6.1m	Livelihoods assistance
International Medical Corps (IMC)-led consortium*	£4.7m	Basic healthcare
Solidarities (SI)-led consortium**	£3m	Livelihoods and protection support
Agencies - CAR refugees
UN High Commissioner for Refugees (UNHCR) Cameroon and Chad	£9.5m	Emergency multi-sectorial assistance
World Food Programme (WFP) Cameroon	£4m	Food and nutritional support
MSF Cameroon	£1m	Emergency healthcare and nutritional treatment
START network***	£3m	Emergency multi-sectorial assistance
M&E	£0.5m
TOTAL	£40m

*NGO consortium led by the International Medical Corps providing healthcare.
**NGO consortium led by Solidarites International providing livelihoods and protection assistance.
***NGO consortium under secretariat of Save the Children UK.

An annual review of this programme’s refugee component was conducted in July 2015 and scored an “A” (QUEST 5194121). UK funding has helped agencies provide a successful response to refugee needs and bring assistance up to minimum standards. Significant mortality drivers such as malnutrition have been brought under control thanks to DFID and other contributions. On that basis we assessed that the programme is achieving its outcome.

This new Annual Review focuses on the performance of the CAR and CAR refugee components of the programme in the period running from July 2015 to June 2016.

What are the expected Results?
Impact: To save lives and reduce suffering of the population affected by the ongoing crisis in CAR, including refugees in the region. The target is to reach 1,460,735 individuals with DFID humanitarian assistance in CAR and CAR regional in 2014/2016.

Outcome: Central Africans access essential services through multi sectoral relief effort.
- Target 1: 993,728 individuals reached with DFID humanitarian assistance in CAR.
- Target 2: 467,007 CAR refugees reached with DFID humanitarian assistance.
- Target 3: Crude mortality rate in prefectures of intervention does not increase.

It should be noted that DFID calculates beneficiary reach for some partners (CHF, ICRC) as a proportion of funding against the overall appeal (ICRC) or against all funds received that year (CHF). ICRC’s mid-term review led to a minor drop in overall budget, so that by the end of the year, DFID’s contribution represents 7.9% against the total appeal and we have calculated that 7.9% of beneficiaries reported in the ICRC annual review were DFID-attributable. By the end of 2015, DFID’s contribution to the CHF represented 36.6% (after the release of surge funding to address needs in September 2015). We have therefore calculated our beneficiary reach as a 36.6% proportion of the CHF total reach.

What is the context in which UK support is provided?
From 2013, violence in CAR took a sectarian turn with increasing inter-communal incidents and violence by self-defence militias (anti-Balaka) systematically targeting Muslim populations. The conflict forced the displacement of more than a million people, of which 415,000 are still internally displaced and 472,000 are refugees. Since September 2014 a 12,000-strong UN peace-keeping operation (MINUSCA) has endeavoured to stabilise CAR. Armed and sectarian violence continue however to threaten the population and humanitarian actors and hinder economic recovery.

Presidential and legislative elections took place in 2016 ending the transition that began in 2013. President Touadera was successfully inaugurated in March and nominated a Prime Minister and government in April. Despite this progress, needs remain extremely high and food insecurity affected 50% of the population in 2015. The health system is reliant on humanitarian organisations and the country’s gross national product is still 30% lower than in 2012. CAR’s refugee population were welcomed in Cameroon, Chad and the DRC, with needs in Cameroon proving particularly serious and acute malnutrition reaching in 2014 30-40% of children in some locations.

The UK has provided £63 million in humanitarian aid to CAR and CAR refugees since 2013 (and £2.5m in development funding through central programmes), making the UK CAR’s third largest humanitarian donor in 2015 and its fourth in 2014. In 2016, DFID approved a multi-year business case that provides £36 million in assistance to CAR populations and refugees from 2016 until March 2019, and plans for a £24 million contingency reserve to address surges in needs.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Under this programme, DFID has a target of reaching 1,460,735 people with humanitarian assistance. This includes Central Africans in CAR, Central African refugees as well as other vulnerable people affected by the crisis including Chadian returnees and vulnerable host communities. The final reporting, to enable DFID to assess whether this has been reached will only be available at the end of the project.

There is one outcome indicator that we can report on during this annual review, which is detailed below.
Outcome Indicator 3: Crude mortality rate in prefectures of intervention does not increase
Milestone 2 – March 2016: Crude Mortality Rates in 3.14 (Ouham), 3.34 (Nana Gribizi), 0.82 (Basse Kotto), 0.75 (Haute Kotto), <1 (Bangui)
Progress: We are currently awaiting the results of a SMART survey carried out by UNICEF in April/May. As these results have not yet been made official we are unable to evaluate this outcome at this time. We will follow up and evaluate this in the PCR. The logframe will be amended to be clearer on the targets and the prefectures they refer to.

Overall output score and description

This project has scored an A+ – outputs moderately exceeded expectations. The breakdown per output is below.

CAR
Output 1: Livelihoods and Food security A – outputs met expectations
Output 2: Health and Nutrition B – outputs moderately did not meet expectations
Output 3: Protection A+ - outputs moderately exceeded expectations
Output 4: Performance of system and humanitarian coordination A – outputs met expectations

CAR refugees
Output 5: Food Security A – outputs met expectations
Output 6: Health and Nutrition A+ - outputs moderately exceeded expectations
Output 7: Multi-Sector (UNHCR) A++ - outputs substantially exceeded expectations
 Output 8: Multi-Sector (START) A+ - outputs moderately exceeded expectations

Key lessons
DFID Field visits continue to be critical in capturing the experience of beneficiaries at the receiving end of assistance and highlighting programme quality issues. This information is not always captured in partner reports but has enabled DFID to remain sighted and support quality assurance.

Great advances have been made in terms of pushing partners on monitoring as well as procurement however pipeline breaks and stock-outs continue to be an issue for many of our partners and hence require further monitoring by DFID. Fraud reporting amongst partners has also improved.

Maintaining access to intervention areas continue to be an issue for many of our partners due to the challenging security situation. Continued effort needs to be made by partners and monitored by DFID on ensuring that security management processes are ongoing and effective and that contingency plans are in place in order to reduce impact when access is temporarily lost.

The scale and severity of refugee needs in this crisis led DFID to make the decision to start funding in a new country. The success of the intervention so far in providing life-saving assistance in the targeted areas justify this decision to intervene.

Has the logframe been updated since the last review?
Yes - The logframe was updated first to integrate the expected results linked to additional funding provided in September 2015 (£7m) and in February 2016 (£5m). In addition, the UNHCR beneficiary targets had been based on refugee arrival extrapolations and were revised down to align with actual trends. Finally, the calculation methodology was reviewed and harmonised with new tranches of funding so that beneficiary figures are expressed cumulatively. This means that people who participated in different projects might be counted more than once, although under any given partner programme, they will not be counted more than one time. The weighting between the outputs in the logframe have also been revised to reflect budget distribution.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Livelihoods and food security. The agro-pastoral production in the targeted areas is improved and reinforced The agro-pastoral production in the targeted areas is improved and reinforced
Output number per LF		1	Output Score	A
Risk:		Severe	Impact weighting (%):	20%
Risk revised since last AR?		Yes – previously “high”	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Progress
Number of people reached through general food distribution and cash transfers by ACF/DRC/SI	480 - June 2016	570 – June 2016
Number of people reached through livelihood assistance by ACF/ DRC/ SI	158,750 - June 2016	Milestone June 2016: 108,847 (single counting) / Final reach: To be provided in Project Completion Report (PCR)
Proportion of the targeted population improving their Coping Strategy Index Score	50% - June 2016	To be provided in Project Completion Report (PCR)
Number of people reached through general food distribution, cash and voucher (GFD) by the ICRC	8,932 - March 2016	5,633
Number of people reached with livelihood assistance by ICRC	4,015 - March 2016	5,842
Number of people reached in food security/livelihood sector by CHF	3,540 - March 2016	8115
Number of people who have received livelihood assistance through the FAO	Milestone July 2016- 172,060 / Target Dec 2016 - 372,060	Milestone: 304,500 – May 2016 / Achieved: To be provided in PCR.
Proportion of FAO project beneficiaries that are not induced to resort to negative mechanisms at least for six to eight months	95% - March 2016	To be provided in PCR.

Key Points
This component started in April 2015 with some aspects lasting until December 2016. We are therefore not in a position at this stage to score all of the indicators against key milestones or to review the impact achieved by all partners. Only CHF and ICRC have completed their programmes along with FAO for their 2015/16 component.

ICRC reviewed its targets and objectives at the mid-term review point in 2015, leading to a slight decrease in budget and in turn a higher beneficiary share for DFID (7.9% of overall appeal value instead of 6.6% at onset of the programme). ICRC completed their seed assistance operation in 2015. Their overall livelihoods reach proved higher than planned (by 20%) while their food and voucher assistance ended up much lower (50%), reflecting changing needs. Positively, ICRC provided substantial assistance in Bangui in the form of cash. Due to the changing context/security ICRC had to refocus their food security and livelihoods intervention towards the end of 2015 to focus on more straightforward food and NFI assistance (including some emergency food distributions end of 2015) and had to put some of the more longer-term activities on hold. This illustrates well the organisation’s capacity to adapt to a changing and difficult context and ensuring their activities are relevant. Insecurity also impacted the 2015 post-harvest monitoring which could not be carried out. ICRC finally launched a wave of cattle vaccination that was successfully carried out.

FAO’s 2015/16 project is due to be completed in June 2016 and the final report is still to be received. A second project was agreed and will run until December 2016. There were initial challenges in 2015 due to delays with the signing of the grant; this delay resulted in the seed multiplication activity having to be run through other funding instead of through DFID. Meanwhile, FAO was able to sign many agreements with partners that entailed in-kind donations only and were complemented by other funding sources to cover support costs. This enabled FAO to make savings, which were used to reach additional beneficiaries. This led to a reach almost twice as high as initially envisaged. Due to issues around targeting criteria FAO have planned on refreshing partner training on this topic in order to increase adherence to the selection criteria. The post-harvest survey results for the 2015 agricultural campaign were positive. However, the data collection was weak and the methodology allowed for some overrepresentation of under-served areas which FAO strived to address in 2016. Overall the activities towards the agricultural season in 2015 were implemented on time but some seeds had a lower germination rate than expected. This was most likely due to the heavy load of the trucks leading to damaged seeds and to suppliers mixing higher and lower quality seed supplies. Following this FAO tightened their quality check protocols in 2016 which in turn has led to higher germination rates. In 2016, FAO piloted seed fairs for 1,000 households which proved successful (though PDM is still pending) and opens the door for greater voucher assistance in the future. The vegetable gardening project progressed with some delay due to surges in violence in September/October 2015 and further incidents in Bambari, and required a no-cost extension. All distributions were completed by end of April. FAO have had some staffing problems throughout the year and began addressing this in 2016 by recruiting key senior positions and expanding their M&E capability.

The SI Consortium initially planned to end their programme in March 2016 but has been granted 2 no cost extensions due to insecurity and slow procurement. Their programme will be completed in September 2016. Partners experienced difficulties harmonising baseline data for income generating activities (IGA) which has led to their data not being fully comparable. The activity is nearly completed for ACF and SI however DRC’s is still under way. The capacity building component has varied in length and been fairly short for some beneficiaries, so we will need to compare the impact and sustainability of each partner’s activity. In terms of staple crop production some issues were faced in terms of poor germination rates. On vegetable gardening, good progress has been made however there have been some difficulties linked to procurement delays (caused by insecurity) and some crops resisting less well to the heat after a late delivery. In the future more attention could go into harmonising design and strategy among the partners and where possible adapting procurement to the season. The refurbishment of markets, access bridges and cassava drying areas is under completion, as is the construction of multi-sectorial platforms. In terms of livestock a do no harm study was carried out which helped identify key hurdles. The purchasing process took longer than expected for both SI and DRC leading to a no-cost extension for 3 months for DRC. Both partners had to take in to account the origin of the suppliers to ensure they are accepted by the recipient community and not perceived to have links to armed groups. Agricultural cooperatives were in the process of being trained for subsequent hand over of the animals. The veterinary component will continue under a new ECHO grant. In terms of livestock vaccination SI and ACF completed their operation. DRC had issues with breakdown of fridges leading to a lower beneficiary reach than expected. Though impact results are still pending, beneficiary feedbacks collected on the ground indicated the relevance of the assistance and suggested positive early results in supporting livelihood recovery.

The CHF fund reached approximately 22,173 DFID-attributable beneficiaries with food security and livelihoods programmes during the year. This total is 8 times higher than planned targets, which DFID extrapolated based on reach in 2014. This increase reflects a drastic increase in livelihoods interventions to support returnee and displaced populations.

Summary of responses to issues raised in previous annual reviews (where relevant)

-	SI to ensure its team have access to technical advice from an agronomist.
SI recruited in 2015 a new livelihoods coordinator who has been in place since.
-	DFID to monitor additional seed distribution and post-harvest monitoring.
FAO has tightened their quality checks which led to a higher germination rate in 2016. Post-distribution and post-harvest monitoring results will be needed to assess overall reach.

Recommendations

- DFID to monitor SI consortium endeavours to reinforce IGA sustainability.
- DFID to monitor FAO 2016 PDM and post-harvest monitoring to assess overall results and seed qualities.

Output Title	Health and Nutrition. Affected population have an improved access to healthcare
Output number per LF		2	Output Score	B
Risk:		Severe	Impact weighting (%):	10%
Risk revised since last AR?		Yes – previously “high”	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of beneficiaries reached in the healthcare sector by ICRC	30,422 – March 2016	13,252
Number of beneficiaries reached in the healthcare sector by CHF	120,888 – March 2016	110,690
Number of beneficiaries reached in the healthcare sector by the IMC consortium	269,354 - Sep 2016	256,828
Health service utilization rate (based on number of beneficiaries reached with new consultations)	1/person/year - Sep 2016	Primary: 0,38 / Secondary: 0,1 / iCCM: 0,29 / MMU: 0,74
Number of acute malnutrition cases from the targeted areas that gain access to treatment	1,277 – March 2016 / 1795 – Sep 2016	Milestone 1: 2,866 / Final reach: See PCR.
2.6. Cured rate among children treated for MAM and SAM	>75% - Sep 2016	SAM:100% Haute Kotto , 84% Basse Kotto / MAM: 100% Haute Kotto
Number of health facilities with access to sanitation with a ratio of 1 latrine/ 20 users	10 - June 2016	Milestone: 9 / Final reach: See PCR.

Key Points
This component started in April 2015 and is currently run by three partners (CHF, ICRC and IMC consortium). ICRC and CHF have finished their activities at the end of 2015, however IMC consortium were granted a cost extension and will be running their programmes until September 2016.

In addition to supporting primary health centres and community-based malaria treatment activities ICRC continued running the hospital in Kaga Bandoro and the war-wounded programme at the hospital in Bangui. The partnership had to be partially frozen several months with the Kaga Bandoro hospital after challenges with the local health authority, but was resolved in 2016. Across the country, ICRC focused on a communication campaign around acceptance of humanitarians and particularly around respect for the medical mission after several incidents in September last year. Due to increasing instability ICRC refocused their activities on life-saving projects and preparedness for war-wounded and mass casualty situations. ICRC’s overall reach proved much lower as catchment areas for health centres assisted this year turned out to be half the size of those of 2014. (DFID’s results were extrapolated based on 2014 catchment areas.) ICRC also covered 2 health centres fewer in their activities than had been planned under their appeal.

In total over the year the CHF reached 112,341 beneficiaries with nutrition services and 190,092 beneficiaries with health services. The DFID share represents 110,690 people, slightly below the extrapolated target for 2015.

During the reporting year one of the partners in the IMC-led consortium, Save the Children (STC), decided to pull out of their operation in the areas of CAR covered by the consortium and therefore handed over their activities to INGO Cordaid who commenced operations in April 2016. OXFAM GB was also replaced by OXFAM Intermon, from the same OXFAM network. These transitions were overall organised cooperatively, and did not lead to gaps in operations or drastic staffing gaps. For all the consortium partners, stock-outs of essential drugs have been a recurring issue. The consortium members have therefore been asked to carry out a barrier analysis to determine where the major bottle necks lie and what can be done to address them to ensure a regular supply of drugs to the health facilities. Additionally there have been concerns around lack of harmonisation on approaches used by the different partners. DFID is therefore in discussion to ensure that future programming involves a solid technical platform and adequate harmonisation.

For IMC utilization rates were impacted by limited access due to worsening security. For this reason a network of healthcare workers was set up to be able to diagnose and provide treatment in the community for most common childhood diseases (ICCM). Access to the health facilities continue to be an issue due to insecurity forcing IMC to temporarily shift its area of operation from two of the original health facilities to different localities also hosting a number of IDPs. Since January IMC has a psychologist working with them so they are working on reinforcing their management of mental health. IMC has not been able to maintain a 1 month buffer stock of medical supplies which has led to frequent stock-outs of essential supplies. Additionally they have had problems with over consumption in several health facilities and hence have planned for a workshop on rational prescription as well as special emphasis on this issue during supervision visits.

More details on consortium partner’s performance are included in QUEST 5524222.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID to monitor solutions implemented to tackle mortality at Alindao hospital.
DFID encouraged consortium members to work together to understand the high case fatality rate and discuss it in the quarterly report and identify and monitor solutions. In Alindao, STC felt like key problems had been a high MoH staff turnover (over which they have little control), lack of resuscitation material and referral at a critical stage. The quality of care was also deemed inadequate. STC has worked on strengthening further training and staff retention and has ordered additional material and the case fatality rates in Alindao hospital has since dropped to acceptable levels.
DFID to monitor that water storage facilities are adapted to health centres’ water needs.
OXFAM has planned to distribute water storage material where needed.

Recommendations

- DFID to monitor partner efforts to analyse and improve utilization rates under 2016-19 project.
- DFID to monitor IMC consortium stock levels of essential drugs and follow up on barrier analysis.
- DFID to follow closely the implementation under new partner Cordaid, their plans on coverage expansion and the potential roll out performance based management system.
- DFID to monitor and follow up on the progress of setting up a technical committee to ensure a cohesive approach amongst IMC consortium partners.

Output Title	Protection - Central Africans enjoy an improved protection environment
Output number per LF		3	Output Score	A+
Risk:		Severe	Impact weighting (%):	10%
Risk revised since last AR?		Yes – previously “high”	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of beneficiaries supported in the protection sector by the CHF	43,080 – March 2016	137,381
Number of beneficiaries supported in the protection sector by the SI consortium	74,600 – June 2016	Milestone 1 - 78,764 (single counting) / Final reach: See PCR.
Increase in the % of people who have perceived an improvement in their protection and safety situation	+25% - June 2016	Final reach: See PCR.
Number of GBV survivors who access remedial services through IMC, DRC and ICRC.	N/A	Milestone 1 - 1682 / Final reach: See PCR.

Key Points
This component started in April 2015. CHF and ICRC completed their activities in December 2015, IMC and SI consortium will complete their activities by September 2016.

CHF reached 375,360 beneficiaries with protection interventions during the year. This amounts to 165% of the planned target, demonstrating a trend in the humanitarian coordination system to prioritise protection (seen as the overarching problem in this crisis). OCHA and the CHF have also endeavoured to promote protection by rolling out gender mainstreaming and protection mainstreaming training for all partners. Due to insecurities in September 2015, protection mainstreaming training that had been planned was postponed until 2016. A gender specialist has supported clusters and partners in developing their proposals and has been working with the CHF to strengthen their gender M&E. A first round of sensitisation on protection mainstreaming was organised for CHF partners. The CHF will need to further develop its M&E and capacity building in this area in 2016-17 to continue strengthening partners’ capacity.

SI Consortium partner Danish Refugee Council (DRC) has formed protection committees tasked to progressively take over protection monitoring. Capacity building of these committees has however been impacted by insecurity as well as limited buy in as members expected financial compensation for their work. Overall, this component suffered severe delay in the launch of committees, though all were expected to be effective by the end of the project. There have been needs identified to reinforce their capacity and hence trainings have been conducted on child protection and GBV. Protection committees have in turn begun sensitising on these topics as well as FGM and social cohesion and referring protection cases for support. DRC also runs bimonthly communication campaigns on GBV and human rights. Listening centres for survivors of GBV as well as child friendly spaces are functional however there have been concerns raised on the accessibility of the youth centre in Batangafo for the Muslim youths. DRC has been monitoring to ensure the centre is accessible to all. Social cohesion activities have had to be placed on hold after September following a surge in violence and incidents in Batangafo in November 2015. Activities resumed in 2016 but it appeared longer-term support would be needed to help establish a dialogue with communities, which has been severely impacted by the tense security situation.

IMC is working with a limited team to do some protection monitoring and deliver GBV services. IMC have also launched a series of public health education sessions on SGBV among other topics. MI has also conducted sensitization on SGBV to heads of health centres and midwives to ensure referral to adequate services. Also STC conducted training for the health staff on medical referrals of SGBV and skills training on empathetic listening. Oxfam has implemented protection mainstreaming activities into their community mobilization activities.

ICRC’s approach to SGBV in Nana Grebizi has shifted the evidence burden, from requiring proof that there is an SGBV problem to start a psycho-social response, to starting a psycho-social response and requiring proof that there is no SGBV problem to stop it. Integrating the programme in wider healthcare provision has also been beneficial, enabling lower profile and easier access to the services. Additionally, improved information gathering has also fed into the organisation’s sessions on IHL to armed groups.

ICRC’s protection work in prison was affected by September events (which led to prison escape) but resumed thereafter. The ICRC is also looking to get support from an armed forces delegate in country and from a regional delegate to strengthen their work with internal security services. Some CAR authorities were sent to a regional workshop to help set up a cross governmental platform for management of mortal remains. Family reunification activities have continued but with some delay due to insecurity.

ICRC organised training in community-based protection (CBP) and is beginning to pilot this approach in CAR. Starting from the premise that populations are experts of their own lives, this approach aims to map with populations their problems, threats and coping mechanisms. Communities identify leading priorities, which can then inform programming in risk education, self-protection measures, risk reduction activities, protection engagement, community self-organisation and so on. Though this approach is in its early days, it is a positive example of participation and accountability in action and should be monitored and supported.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

- DFID to follow up on protection mainstreaming in CHF funded projects.
- DFID to monitor results and impact of ICRC community based protection.

Output Title	Performance of the system and coordination - The CHF actively contributes to strengthened humanitarian coordination and response
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		Yes – previously “high”	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1. Percentage of overall funding received from all donors by 30 June 2015 is allocated before 31 December 2015/ received by 31 December 2015 and allocated before 30 June 2016.	> 80% - March 2016	82.8%
4.2. Percentage of projects monitored through field visits within their project duration	40% - March 2016	39%

Key Points
This component was completed in December 2015.

In 2015, US$ 27.74 million was transferred to participating organisations through the CHF, and US$ 25.90 million was reported in expenditure. With a delivery rate of 82.8% this is a solid indicator of the CAR Common Humanitarian Fund’s robust financial performance. In 2015 DFID contributed US$ 9,132,207 to the CHF which totals to 36.6% of total CHF funds for 2015. 77% of funding was channelled through NGOs and 23% to UN agencies and the International Organization for Migration (IOM), making the CHF a solid channel to support NGO partners. Reflecting widespread needs, projects were fairly evenly allocated across sectors, with protection, health, food security, early recovery and WASH taking the bulk of funding.

During the year 39% of the projects were visited for monitoring purposes. Targets are still at 40% making this year only slightly below target. The CHF began strengthening their M&E team and planned in 2016 to expand it and rely more heavily on Office for the Coordination of Humanitarian Affairs (OCHA). The CHF also started strengthening the gender and protection monitoring aspects in 2016.

The CHF management team focused heavily in 2015 on developing a solid partner performance and risk management system. Those were up and running and fully rolled out by end of 2015, and began informing funding decisions. The CHF also diligently followed up on incidents and losses affecting projects after the September 2015 events in Bangui. By mid-2016, the CHF presented the final CAR CHF guidelines to their advisory board for validation, which will ensure that partner risk management systems are understood.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

- Continue monitoring that partner performance system is used and informs allocations and M&E.
- Ensure that CHF reports to board changes in their analysis on partners’ risk levels, and other relevant points including losses and fraud.

Output Title	Food security - Central African refugees receive basic food assistance in Cameroon.
Output number per LF		5	Output Score	A
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		Yes – previously “medium”	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of people reached through general food distribution (GFD) in Cameroon.	145,567 – December 2015	154,000 – December 2015

Key Points
The WFP programme aimed to deliver urgent food (general food distribution or GFD) and nutrition commodities (blanket and targeted supplementary feeding) to meet the basic food and nutrition needs of CAR refugees in Cameroon. DFID started its support to WFP in July 2014 until December 2015.

In Cameroon, WFP’s response was implemented in the East, Adamawa and North regions and targeted CAR refugees who arrived in 2014 as well as CAR refugees who arrived and settled prior to the conflict and are still identified as severely food insecure. Vulnerable host populations were also targeted through nutrition programmes. In 2015, WFP provided monthly GFD to refugees in seven established UNHCR refugee sites, border entry points and in local villages, scaling up over time as new refugees arrived. WFP has scaled up its nutrition program from 8,700 beneficiaries per month in early 2014 to more than 60,000 in 2015.

For the nutrition component the operation focused on refugee populations located along border regions of CAR (East, Adamawa and North regions) providing general food distribution. Children and pregnant and lactating women amongst refugees and host populations alike received nutrition support aimed at preventing and treating moderate acute malnutrition. Additionally, WFP supported malnourished individuals living with HIV. Around 25,000 malnourished women and children received treatment for moderate acute malnutrition (MAM) in 2015. Among the beneficiaries the global acute malnutrition prevalence decreased from 17% in May 2014 to below 5% in 2015 and less than 1% at the end of 2015 (far below the 15% emergency threshold).

In Cameroon, the post-distribution monitoring (PDM) carried out in December 2015 indicated improvements in the food security situation of refugees targeted through food assistance. Since April, the proportion of households with poor food consumption has decreased by seven percent. Through nutrition programmes implemented at scale and along other partner activities, WFP managed to reverse an alarming nutrition situation which prevailed at the onset of the crisis. Global Acute Malnutrition (GAM) rates of over 30% registered at the early stage of the crisis dropped to below 5% among beneficiaries receiving assistance. Monthly screening using mid upper arm circumference (MUAC) indicated less than 1% GAM in several sites in December 2015. Furthermore, a steady decline in the number of newly admitted moderately malnourished and severely malnourished children was registered in health centres, from over 200 registered per month in January to below 100 in December. Cure rates for women and children in target supplementary feeding programme (TSFP) was 71.2% which is slightly lower than Sphere minimum standards (>75%) but still an improvement from last year. Defaulter rates (patients leaving the program before being cured) were high at 26% (Sphere standard <15%). Mortality rates were well below sphere standard at 0.2% however due to high defaulter rates this figure may not be reliable. Non-response rate was at acceptable levels well below target 2.5%.

Supply chain challenges constituted a major hindrance for WFP's operations during the first half of the year, resulting in pipeline breaks from March to May. A complete break in May delayed WFP from performing food distributions during the month. Refugees’ difficult living conditions combined with breaks in assistance coincided with anecdotal evidence of a rise in negative coping mechanisms. However, WFP ensured GFD support through the remaining 11 months of the year and augmented nutritious rations to compensate for the reduced food support. Nutrition activities in east Cameroon continued without interruptions through the year. Monitoring evidence also suggested this positively impacted refugees’ ability to avoid negative coping mechanisms. While treatment programmes were prioritised over prevention, major efforts were made to scale up blanket supplementary feeding from initially 25 sites to 60 sites in the East, Adamawa and North regions. Under TSFP, 35 outreach sites were created to adequately provide MAM treatment packages to beneficiaries located in remote villages.

WFP’s operations face regular challenges due to chronic underfunding, which will continue to require regular monitoring and where possible adequate DFID response.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID to prioritise engagement in country with WFP on overall pipeline management and opportunities for local procurement and cash assistance. DFID to monitor challenges for delivery likely to result in ration reductions and pipeline breaks and opportunities to help address these challenges.
According to WFP reports a series of initiatives put in place by WFP and partners succeeded in improving the situation and supply chain procedures went smoothly through the second half of the year during which no breaks in the pipeline were registered. The challenges encountered in 2015 led WFP to reflect on the importance of combining food assistance projects with cash and voucher modalities for a more efficient response. Consequently, in 2016, WFP will introduce cash-based programmes for the first time in Cameroon. According to WFP reports, augmented nutritious rations were given to compensate for the reduced food support.

Recommendations

- DFID to work with WFP to look at strategies for decreasing defaulter rates in the nutrition programme.
- DFID to continue monitoring WFP pipeline management to ensure there are no ruptures in supplies.
- DFID to work with WFP to ensure M&E adequately tracks increases in negative coping mechanisms.

Output Title	Health and nutrition - Central African children in Cameroon receive treatment for acute under-nutrition.
Output number per LF		6	Output Score	A+
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		Yes – previously “medium”	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Progress	Output score
2.1. Rehabilitation recovery rate (%) for children suffering SAM who have received MSF Community Based Management of Acute Malnutrition.	September 2014: 65%. / October 2014: 75%.	September 2014: Garoua Boulai 97% and Batouri 80% (MSF areas of intervention). / October 2014: Garoua Boulai 97% and Batouri 93%.	A+
2.2. Number of people reached with MSF health interventions.	30,000.	30,000.	A

The MSF programme aimed to deliver emergency healthcare and therapeutic treatment for severe acute malnutrition. MSF was the first INGO to respond to the crisis in 2014 by setting up mobile clinics and providing medical care on refugee sites complemented by water and sanitation activities to address the crisis.

MSF has met and exceeded agreed targets by reaching 30,000 people with urgent health interventions[1] and exceeding the final 75% recovery rate for children with SAM.
[1] The overall beneficiaries for MSF programme for Central Africans in Cameroon is 50,000 (30,000 people reached with UK funding).

Central Africans generally arrived in Cameroon in an extremely poor condition with very high rates of malnutrition: GAM reached up to 25-30% and SAM rates 10% in June 2014. The baseline recovery rate for children suffering SAM was 59% in Garoua Boulai and 61% in Batouri at July 2014. By September MSF had exceeded their 65% recovery rate for children suffering SAM. MSF’s overall programme objective was to stabilise and reduce mortality and morbidity rates amongst Central Africans. Mortality rates were reduced to acceptable levels across the MSF area of intervention to 0.1 - 0.3 by October (against a target of under 5 mortality rate <1). A small cholera outbreak occurred in November 2014. However a multi-partner response plan was immediately implemented with MSF leading on health and the outbreak was successfully contained.[2]
[2] MSF reporting to DFID.
While the immediate emergency phase has passed, MSF has noted that attention is still needed to ensure the stability and quality of healthcare. At the end of the DFID funded MSF programme the number of patients in the intensive therapeutic feeding centres remained high and with a still unstable situation in Central African Republic, MSF has extended its operations in Cameroon to at least the end of 2015, but these aspects of the programme are not funded by DFID.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID to monitor MSF handover to more development orientated partners over 2015.
DFID has monitored the handover the UNHCR partners and after some adjustments, UNHCR has made ACF the lead to maintain quality of care.

Recommendations
None.

Output Title	Multi-sectorial (UNHCR) - Central Africans arriving in Cameroon and Chad as refugees have their most basic needs met, including shelter and water and sanitation.
Output number per LF		7	Output Score	A++
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		Yes – previously “medium”	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1. Average supply of water per person per day in the 7 refugee sites reaches a minimum of 15 litres per day in Cameroon (WASH).	>15 – March 2016	19 litres per person per day
3.2. Number of emergency shelters provided in Chad (Shelter).	636 – March 2015	3,386
3.3. Number of people reached with UNHCR multi-sector assistance in Chad.	56,000 – March 2015	72,068
3.4. Number of people reached with UNHCR multi-sector assistance in Cameroon.	Milestone 1: 60,000 / Final reach: 68,704 – March 2016	Milestone 1: 60,000 / Final reach (March 2016): See PCR.

Key Points
UNHCR and its partners have been implementing a multi-sectorial response on and off sites for CAR refugees and host communities and for returnees in Cameroon and Chad in 2014/15. The UNHCR programme in Cameroon aimed to ensure the protection of refugees, including through registration, the provision of shelter and non-food items, access to water, sanitation and hygiene as well as healthcare. UNHCR also supported access to education through the rehabilitation and construction of school buildings. In Chad, the programme supported the needs of refugees and ‘returnees’[3] across sectors, including shelter and infrastructure, water and sanitation and protection. In 2015/16, UNHCR received DFID support to continue its multi-sectorial response. UNHCR are implementing multi-sectorial activities in East, Adamaoua and North mainly in biometric registration, self-reliance and livelihood activities, and support to local authorities through capacity building, in order to respond to the identified needs linked to the protracted displacement of CAR refugees.
[3] Returnees are people of Chadian nationality who have had to flee CAR during spikes of sectarian violence in 2013-14. Many are second or third generation migrants and no longer have family or social ties in Chad.

In terms of WASH in refugee sites 115 boreholes and 3,450 latrines have been built resulting in provision of water at 19l/p/d and an average of 20prs/Latrine, only 66 boreholes have been built in refugee-hosting villages.

With the aim of improving services to beneficiaries UNHCR in Cameroon introduced a biometric registration system in late 2015 with financial support from DFID to cover the first phase of the exercise. It consisted in the setting up of the main registration centres, the purchase of main biometric registration equipment, and trainings and workshops of the staff on the methodology/features of biometric registration. The switch to biometric registration has so far given a much more accurate picture of the number of refugees and is expected to have a wide range of key protection impacts, including continuous access to asylum.

UNHCR Cameroon has prioritised self-reliance and livelihoods as one of the main pillars of intervention in the assistance to CAR refugees in the East, Adamaoua and North regions. In 2015 the intervention targeted various groups of refugees supporting livelihood activities such as: (a) agricultural extension and distribution of agricultural tools-kit and food seeds, seed-kit market gardening; (b) Income-Generating Activities; (c) capacity building for IGA groups and organisations; (d) training in profitable trades and first starter kits to the training participants.

DFID funds also provided vehicle and assets to Cameroonian authorities to improve their capacity to respond and facilitate the operation assistance in the East, Adamaoua and North.

In terms of coordination there have been improvements. These improvements only apply however to the livelihoods sector whilst all other sectors still leave much to be desired. Additionally the situation in terms of partnership appears to be deteriorating as UNHCR partnership management has proved insufficiently cooperative, poorly communicated and some NGOs have raised concerns about the length of the contracting process. These concerns were already identified in 2014 and call for drastic improvements in partnership management.

Despite exceeding logframe targets administratively UNHCR have been weak. Their specific final project report was due on 30 June 2016 and is now significiantly overdue and has still not been received before completion of this review. Evidence on UNHCRs performance was drawn from their mid-term report which was due by 31 December 2015 and was submitted on 10 February 2016 and ad hoc information gained by our humanitarian advisers.

Summary of responses to issues raised in previous annual reviews (where relevant)

Continue to monitor UNHCR delivery in Chad and in Cameroon including funding pipelines and UNHCR’s ability to achieve coverage of assistance across operations and sectors.
Underfunding continues to be an issue. There remains a very strong need for DFID to continue monitoring the situation and supporting the response.
Continue to monitor the situation of refugees both inside and outside of the camps in Cameroon including any arising assessments on nutrition and specifically the potential causes of under-nutrition, e.g. limited water and sanitation.
This remains part of ongoing monitoring using nutrition surveys.

Recommendations

- DFID to follow up with UNHCR both at country level and at HQ level to ensure that they step up in terms of improved coordination and partnerships.
- Continue to monitor UNHCR delivery in Chad and in Cameroon including funding pipelines and UNHCR’s ability to achieve coverage of assistance across operations and sectors.
- DFID to discuss UNHCR’s reporting delays with CHASE and UNHCR HQ.

Output Title	Multi-sectorial (START) - Central Africans receive multi-sector assistance both in refugee camps and outside of camps in communities in Cameroon
Output number per LF		8	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Yes – previously “medium”	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (March 2016)	Progress
4.1. Number of people reached with multi-sector humanitarian assistance with START network activities.	179,526 people (91,196 female, 88,330 male)	455,515 (249,842 Female, 202,137 Male) No double counting
4.2. / Network mechanisms deliver rigorous decision-making for selecting projects and learning.	June 2015. Decisions made by the Project Selection Committee are well-documented in meeting minutes and transparent selection criteria are used. Decisions are based on needs analyses, evidence of the project’s engagement with affected people and the technical strength of proposals. / March 2016. Lessons learned have been documented with evidence of adjusting programmes in response to emerging needs analyses, engagement with affected people and the findings of their technical teams. Programmes are course-corrected if needed.	Project selection was clear and documented but technical criteria for project selection not always clear and decisions only moderately based on evidence. Learning Workshop took place in August 2015 to reflect on inception period and strengthen collaboration between stakeholders. / Problems were documented and there is some evidence that adjustments were made where needed.
4.3. Proportion of beneficiaries (5481) who report an increase in vegetable production and acceptable food consumption score at the end of the project.	At least 80% beneficiaries report increased vegetable production and have an acceptable Food Consumption Score at the end of the program. – March 2016	80.6% report an increase in vegetable production / 91% have an acceptable FCS by end of the programme.

Key Points
An MOU was signed with the START network in April 2015 to conduct activities for the CAR refugee crisis in the East and Adamawa states of Cameroon covering a period between 01 April 2015 and 31 March 2016. There have been delays in the transfer of funds as DFID did not disburse the funds to START until late May. Following on from this there was then a more than two months delay until full implementation was initiated in August which can not entirely be explained away by late transfer of funds from DFID. This led to several of the partners suffering severe delays in their project implementation. Most of these delays were caught up by the beginning of 2016 though this might have impacted the sustainability of some activities.

Additionally there have been serious concerns raised on the issue of the monitoring, evaluation & learning component within START as it was more focused on processes rather than proper implementation and did not substantially contribute to improved overall management. A lesson learning workshop was organised by DFID and START to take stock of areas requiring improvements for future collaboration, including in contracting, project selection process, M&E, staffing and in deciding the localisation of START staff.

The lessons learned exercise gave some clear recommendations for both the START network and DFID. START is making changes to their Standard Operating Procedures to formalise exit strategies, payment plans, capability assessments of partners and review of projects. DFID and START both committed to agree a more formal model of partnership in any future collaboration, including regular calls and communications. The full lesson learning document is saved on QUEST 5534027.

In terms of project implementation, most outputs were met, and some exceeded, indicating an overall positive performance of the programme. START were particularly successful in significantly exceeding targets for sessions on WASH, nutrition, education and protection. START only met 53% of their target to deliver primary health care consultations through IMC due to delays related to security concerns and poor road conditions during the rainy season (July 2015 - November 2015). START also acknowledged the slow launch of health services was due to delays in signing the agreement between IMC/PLAN and the START network; this also led to delays in developing an agreement with the local MoH representatives to facilitate the provision of health services to refugees.

Key successes reported by Start Network implementing partners centred on advocacy work with community leaders, local authorities, government bodies and UN agencies, which fostered their cooperation, notably on protection and gender-based violence issues. Support from community leaders was particularly beneficial for smooth programme implementation. There were several programmatic adjustments such as developing an integrated approach for WaSH and nutrition activities that demonstrate the programme’s successful adaptation to the needs of the targeted populations and the programme context.

Some of the specific key successes included:
- Changes in hygiene practices with the implementation of community-led total sanitation activities.
- Securing access to health by providing services for the most vulnerable communities (refugees and host communities).
- Mitigation strategies to compensate for shortages of therapeutic food by focusing on preventative measures and orientated programming on Infant and Youth Child Feeding (IYCF).
- Collaborative farming projects where 10 to 15 farmers would farm on one piece of land with members learning and coaching their peers.
- Focussing on income generating activities where household groups could gain income from farming and business activities.
- Successful advocacy campaigns to draw attention of UNHCR and government representatives on the importance of integrating child protection.
- Increasing awareness and access to GBV prevention and response services.
- Advocacy against discrimination towards girls and women through the promotion of girls’ access to schools.
- Positive coping mechanism among children through Child Protection Officers.
- Integrating parenting education as part of the education curriculum in Cameroon, with endorsement of the Ministry of Education.

Some of the key challenges included limited access to target communities, especially in the north due to security. Access was also a challenge to populations in constant displacement outside the refugee camps; impeding targeting and meaningful community involvement in specific activities. It was reported that the status of affected people and their living conditions (weather, insecurity and constant displacement across hard-to-reach areas) was a recurrent challenge during implementation. The increasing size of the displaced population also impacted on project delivery. Finally, ensuring the sustainability of specific activities was challenging due to the short programme timeframe.

Summary of responses to issues raised in previous annual reviews (where relevant)
Monitor impact of delays at DFID, START and partner level on operations and review process of integration of lessons learned into the START network’s processes.
START lesson learning workshop was carried out in August 2015 and a wider lesson learning event was carried out in June 2016.

Recommendations
It is the recommendation based on this review that future DFID funding on longer-term response should be conditioned by the implementation of lessons learnt agreed at the June 2016 workshop.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

In CAR, primary cost drivers were and remain the result of poor capacity, insecurity, and being landlocked. In addition, fraud risks also contribute to cost drivers. Poor capacity combined with fraud risks require a disproportionately heavy expatriate presence to oversee and implement operations and run compliance mechanisms. The quasi collapse of the private and transportation sector means most goods must be procured overseas leading to greater transportation costs for this landlocked country. In addition, transportation costs within CAR are still very high due to poor infrastructure, insecurity and the limited number of transporters.

 CAR went through three months of relative chaos in September-November 2015 after a series of coordinated attacks in Bangui and other parts of the country left a dozen organisations looted and required the relocation of 300 staff. This and ensuing insecurity drastically affected presence, movements, cash movements and procurement across the country until early December, severely delaying most partners. Despite this, only two contracts needed no-cost extension: FAO and the Solidarites international (SI) consortium.

VfM performance compared to the original VfM proposition in the business case

The business case followed DFID’s approach to VfM, the Economy, Efficiency and Effectiveness (3Es) model. Equity is also considered under this annual review. An assessment of projects proposed in the business case focused on speed, quality/appropriateness and cost.

Economy (spend less) – The Business case stressed the high operational costs in CAR linked to HR and transportation (see above) which negatively affect the cost of operations in country. This problem is less prevalent in Cameroon. The operational cost of scale-up is also extraordinary given all challenges associated to the context. Partners have endeavored to do more local procurement where possible (for instance in livelihoods). In 2015, it led however to complaints around some of the deliveries, thus suggesting that the savings accomplished were insufficient if not accompanied by much tighter procurement processes. In 2016, FAO strengthened its quality check systems to address this problem. In terms of HR, partners’ operations have demonstrated time and again that inadequate experience and poor support would lead to poor implementation and increase fraud risks. All partners have therefore had to endeavor to avoid staffing gaps and ensure they recruited people of adequate seniority. Most partners faced some difficulties in this regard, but had reasonably well staffed team by the time of this AR, along with solid systems to ensure continuity of operations. The CHF in particular strived to strengthen its systems and staffing throughout the year. FAO also set up an M&E team and began consolidating M&E processes. They revised their organogram and improved staffing. These investments leading to better functioning institutions are adequate economic choices.

Speed was also a key element, to respond quickly to high levels of needs, while predictable procurement is essential to sustain operations. In this regard, WFP faced some substantial struggles with their pipeline in early 2015, but endeavored to address these and improve assistance predictability in the second half of 2015. The pace of delivery for FAO this year was noted by beneficiaries and partners as an improvement, though there is still room for improvement in signing partner agreements earlier. To support these improvements, DFID has agreed to launch the 2017 programme much sooner to ensure FAO is able to take these recommendations fully on board.

Finally, the location of most projects has constrained the possibility of providing cash and voucher assistance due to poor market absorption capability. The SI consortium and ICRC have however endeavored where possible to channel aid (food support and income-generating activities) through cash and/or voucher, which has in particular been beneficial to help with the resumption of trade. In 2016, FAO also piloted a seed fair for which initial results have been positive. In 2017, DFID and FAO have agreed to scale up this fair approach after this successful pilot, in order to increase beneficiaries’ choice.

Efficiency (spend well) – DFID’s Value for Money guidelines consider the average output cost and fluctuations therein a good reflection of efficiency. Equity in aid distribution is also important in order to assess whether aid is reaching the right beneficiaries and leaving no one behind.

If we look at the average beneficiary reach, we can see that ICRC, UNHCR, WFP, MSF and the SI consortium are generally meeting their targets. FAO and START have substantially exceeded their targets. The IMC consortium is slightly below its target. This should mean that the output cost if the same for the first group, lower for the second and higher for the third, but we need to unpack these trends a little.

First, for FAO, the difference in beneficiary number can be explained by the number of no-cost contracts they were able to grant, which led to savings reinvested in seed purchases. FAO’s capacity to identify early savings and make timely reinvestments is a strength of their management. For the START network, there were some savings made enabling an expansion of activities. However the main reason for the project’s very large reach appears to be linked to soft activities and the very large number of water points disinfected (an activity implemented at a very low cost) rather than more efficient delivery. As for the IMC consortium, an area of concern (see narrative in the health output above) is linked to challenges in achieving the target of 1 consultation per person per year so whilst the target population in an area has access to health services, they are not necessarily using them in large numbers. The obstacles towards access are still under identification, from access to limited needs, to poor performance of MoH personnel to the high performance on community care leading to low attendance at health centres. (On this last point, in the area of intervention of Mentor Initiatives for instance, local stakeholders noted that trust levels towards community health workers were such that people would rather consult them than go to the MSF-run hospital where they would have to queue.) Partners have been sensitive and sensitised to use M&E and accountability tools to address these trends, which will continue to be monitored by DFID.

Finally, with regard to efficiency, the question of speed intervenes once again. Some partners, notably ICRC and MSF as well as the IMC consortium have repeatedly adapted their response to address surges in needs, with in the case of MSF spectacular results on mortality. In Cameroon, UNHCR and WFP were not far behind and the pace of their intervention initially fed by internal funding was crucial in saving lives in 2014.

Effectiveness (spend wisely) – It is still early to fully elaborate on the impact of the actions supported by DFID. This is made even more difficult because of security impediments which have negatively impacted M&E in 2015. This section will be populated once all final evaluations are available for the PCR.

We should however note some evidence collected from DFID partners during field visits. In particular, in 2015-16 the assistance provided under the SI consortium was noted as very relevant by beneficiaries in terms of targeting and type of assistance. Anecdotally, DFID could see that the combined impact of activities was leading to a revival of trade in some areas covered by the end of the project. FAO’s assistance was greeted as more timely and of better quality in 2016, a reflection of earlier contracting and improved quality control processes. Assistance provided by the IMC consortium was also positively greeted, with in particular MENTOR Initiatives beneficiaries hailing the programme as life-saving in their region, which had been entirely deprived of healthcare access.

Gender and equity
From the implementing partners that did provide consistent disaggregated data, we have calculated that the female beneficiaries to overall beneficiary coverage ratio is approximately 5:9, indicating that women and girls, are being targeted slightly more than males across the programme.

Institutional practices surrounding gender were discussed with partners. Very poor overall capacity in country combined with uneven access to education for women translate into gender imbalances within partners’ teams – though partners might have overall about 30% female staff. In terms of beneficiary targeting, most partners had fairly gender sensitive policies with some livelihoods activities (IGA, resilience) targeting women. There were substantial discrepancies in how gender is considered throughout M&E and accountability so this will require greater attention in the future. In particular, whilst local committees usually include female representation (in addition to youth, religious leadership, local authorities, economic stakeholders etc.); in practice females are frequently under-represented due to the lack female local leaders. Partners imposing targets may still be necessary to correct these biases. We should however keep in mind that some women (for instance widows) are twice marginalised due to their gender and social status, making them more likely to be sidelined. This is the sort of bias that is difficult to correct through programmes, but sustaining conversations on tools and mechanisms used to ensure no one is left behind is probably key to ensure that isolated women, the elderly, handicapped people and so on benefit from DFID funded programmes.

Another challenge with regard to equity is ensuring that populations in need, be they sedentary or pastoralist, are all catered for. Within CAR this is made very challenging by poor access (with pastoralist populations choosing to remain in forest areas for their protection). Some partners endeavored to monitor this: for instance, in Basse-Kotto, the IMC consortium worked with the religious platform and tried to analyse obstacles to access to care for Peuhl populations. The ICRC, FAO and the SI consortium have all undertaken cattle vaccination campaigns that provide entry points to assess the needs of pastoralist populations, whilst responding to a priority need identified by them. The SI consortium also implemented under DFID funding a useful assessment in June/July 2016 to better understand the needs and challenges of pastoralist populations, which will be distributed across the humanitarian community.

Finally, a key aspect of effectiveness has been to avoid harming beneficiaries in the course of DFID funded actions. Whilst intuitively logical, this has proved less than straightforward in a high-insecurity environment, riddled with social divisions and violence. ICRC’s practice of twinning protection and assistance is inherently designed to see that both actions complement each other. Their launch of community-based protection in 2016 could further contribute to helping to foster positive coping mechanisms. The SI consortium was asked to implement do-no-harm studies for some of their activities. This was done with great diligence and the implementation of these activities (cattle assistance) adapted according to findings. DRC has generally also tried to tailor their protection and assistance activities to reinforce each other. DFID noted however that DRC might have been too quick in pushing for concrete outputs under their social cohesion project without having a complete grasp of the situation (thus presenting some risk for the population). DRC also operates in a very difficult area of agro-pastoral disputes, and it was noted that their social cohesion work still needed reinforcing in the long term to try and address underlying factors. With regard to the CHF, early efforts towards strengthening protection mainstreaming in 2016 go in the right direction to ensure partners do no harm. Among CAR refugees, there has been much attention from partners, UNHCR and WFP in particular towards negative coping mechanisms among beneficiaries.

Assessment of whether the programme continues to represent value for money
We should keep in mind the outstandingly difficult context under which DFID assistance is delivered, with partners forced to change programmes several times a week to respond to insecurity and requiring three contingency plans for their procurement. Recruiting staff to work in CAR has also proved remarkably difficult and the fact that we have not seen big staffing gaps is a reflection of the professionalism of our partners. In the circumstances, the fact that most partners continue to meet most objectives, at times exceeding them, is not short of remarkable.

Quality of financial management
Payments were made based on agreed schedules in the memoranda of understanding and accountable grants. Financial statements are received and reviewed along with progress reports before payments are made. In general partners provided financial reporting on time, with accurate forecasts and explanations where reallocations were required. This allowed DFID to make timely disbursements. However, some partners needed follow up due to late reporting, for example START provided their final financial report one month late due to an internal misunderstanding of dates, FAO had also been chased for reporting in the past and WFP’s standard project report was provided on 31 March 2016. The final financial SPR will be produced when the EMOP project will be financially closed, that is three months after its operational closure. The Start Networks final report shows an underspend of £1,096 which will be returned to DFID.

DFID is going to fully spend against the project and Ministers have recently approved a new multi-year Humanitarian programme in CAR and the region for up to £36m between 2016-2019.

Date of last narrative financial report
Solidarites International Consortium	17 May 2016
IMC consortium	16 May 2016
FAO	16 July 2016
CHF	13 May 2016
ICRC	09 May 2016
MSF	05 February 2015
WFP	31 March 2016
UNHCR	Specific financial report due on 30 September 2016
START	15 July 2016
Date of last audited annual statement	Will be included in PCR.

E: RISK (½ page)

Overall risk rating: Severe
A comprehensive risk matrix was developed as part of business case process approved in 2014 and updated in 2015. The overall risk level for the programme is considered severe for the components of the programme operating inside CAR. For the components supporting refugees in Cameroon and Chad, where the operating environment is much less insecure, the risk rating is better described as Major/Moderate. Risks in CAR remain very significant and where security is concerned, mitigation measures can somehow reduce risks but our partners are only able to implement activities because they accept a very substantial residual security risk. Most partners have in turn endeavoured to have a set-up to address associated stress (regular leave, debriefings) and take measures when staff are subjected to incidents (psychological support etc.). While there are significant risks including an unpredictable situation in CAR mitigation measures are in place. DFID quarterly monitoring visits and a greater focus on due diligence and UK engagement in CAR and the region all contribute to mitigating risks. DFID has amended its Risk Management Framework, amending the risk levels from low, medium and high to minor, moderate, major and severe. This project was previously a “high” risk and is now deemed to be “severe”.

Overview of programme risk
Strategic risks and in particular underfunding remain a key concern. In Cameroon and CAR, DFID is regularly engaging across the donor spectrum to try and see this addressed. In light of the protracted nature of the crisis, DFID also approved in 2016 a 3-year business case to help sustain the humanitarian response.

Implementation related risks have proved the greater problem including insecurity in all its forms (hindering access, operations, M&E, delivery and leading to losses for partners). Financial risks linked to fraud have also been a concern. DFID has allocated substantial capacity to keep tab of partners’ due diligence processes and compliance mechanisms. Any suspected instance of loss or fraud has been followed by DFID’s counter-fraud unit and used to review partners’ compliance mechanisms. Increasingly effective compliance monitoring also means that a greater number of small fraud cases have come to light, and great efforts have been undertaken by partners to mitigate risks. For example, the CHF’s roll out of a full risk management framework. FAO’s early efforts in 2016 to create a similar tool should also be monitored. We should also note that where challenges arose (for instance with regard to IMC’s partner Save the Children) a professional plan was devised and fully implemented to bring all bases up to standard. The IMC consortium has also conducted compliance checks among its partners. Partners have also systematically rolled out sensitisation sessions on fraud where cases were detected creating a better space to talk about these problems. The ICRC noted for instance that repeated sessions have led to improved HR dialogue over any kind of problem. Where FAO’s operations are concerned, they have not hesitated to share concerns at the cluster level and across their bases, to ensure all were sensitised where risks were identified.

Outstanding actions from risk assessment
- Update the risk register in line with DFID Risk Management Framework.
- Monitor FAO’s development of a risk management framework.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme, and subsequent cost extensions to IMC, FAO was delivered against the planned timeframe with the exception of the Solidarities International Consortium, which was provided with two no-cost extensions due to unfinished activities.

Performance of partnership (s)
START: A lesson learning workshop was organised by DFID and START in August 2015 to take stock of areas requiring improvements for future collaboration, including in contracting, project selection process, M&E, staffing and in deciding the localisation of START staff. A further workshop was concluded in June 2016.
IMC: During the year IMC had a vacancy of the consortium manager position that subsequently had to be temporarily filled by other staff before a new consortium manager could be recruited. This meant that management and coordination of consortium partners was not as strong as it could have been. This issue was evident both in the lack of harmonisation among the partners as well as through concerns raised by consortium members.
UNHCR: While improvement in the coordination/performance/partnership was noted last year, the situation in term of performance partnership is deteriorating as of 2016. UNHCR contracting with downstream partners has been a concern, and lack of funding is not sufficient to explain the coordination issues observed by DFID’s Humanitarian Advisor. Operational delivery has taken place at a reasonable standard however, and in the face at times of severe underfunding. UNHCR reporting was generally late and DFID relied heavily on field visits for an update on operations. These issues have been followed up at HQ.

Asset monitoring and control
All assets will be dealt with as per DFID’s asset disposal guidance in the Smart Rules during the closure of the project.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Not relevant.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The theory of change remains relevant to the project design in place for this project and did not require review. The project design did not require any major modifications. DFID has not planned an external evaluation of the programme, however, during final reports we expect some project evaluations from partners. Evidence shows that refugee operations have been underfunded and DFID field visits show that agencies have chosen to prioritise life-saving food, shelter, WASH and healthcare and protection assistance. This means that there has been limited support for refugees to resume income generating activities.

Monitoring progress throughout the review period
DFID does not have a country office in CAR, Cameroon or Chad. Since 2015 DFID has engaged a humanitarian adviser based in Yaoundé who continues to provide oversight of programmes in the region.

Since 2014, UK based staff have undertaken quarterly visits to programmes in CAR and Cameroon to check project progress. Visits to CAR and Cameroon include meetings with beneficiaries and other stakeholders, national government officials, DFID partners and other humanitarian agencies. DFID also undertakes calls with partners on a regular basis and when field visits are not possible. Direct beneficiary feedback has been an important element of the programme, including with women, with men, and young people. Partner performance has been monitored, reviewed and captured in the intervention review sheets before financial allocations have been made. Agencies have provided DFID-attributable results however for some UN partners this is challenging as practically, in their operations, they do not internally demarcate DFID vs. other donor funding against specific projects.