Type of Review: Annual Review

Project Title: International Alert Programme Partnership Agreement

Date started:	01 April 2013	Date review undertaken: 31st August 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK, through the Department for International Development (DFID), is investing in a 3 year Programme Partnership Arrangement (PPA) with International Alert between 2011 and 2014. An investment of £1,739,160 for each year has been agreed. This type of strategic investment can leverage much greater impact than traditional project funding by playing a key role in shaping how International Alert uses its non-DFID resources.

What are the expected results?
International Alert work to help people find peaceful solutions, bringing together communities divided by conflict to find ways of resolving their differences without violence. They also advise companies, governments and international organisations on how their policies and operations can better support peace. To do this effectively, International Alert research the root causes of conflict around the world and address key issues that affect lasting peace and stability in high risk places. / DFID support to International Alert contributes core funding in order to contribute to lasting conditions for peace by raising global standards of policy and programme engagement in fragile and conflict affected states by international institutions and actors. The expected outcome is that International Alert will target international institutions, governments, private sector actors and civil society agencies so that they apply concepts and methodologies, which reduce conflict and promote peacebuilding, in at least ten fragile and conflict affected states

What is the context in which UK support is provided?
Civil society plays a vital role in supporting citizens to improve their lives. Civil Society Organisations (CSOs) are central to delivering services, enabling citizens to be more active in their own development and ensuring that policies benefit ordinary people – especially the poorest. / To achieve DFID’s priorities, as set out in its Business Plan (Structural Reform Plan), a multi-sectoral and multi-faceted approach to delivery is required, one in which CSOs, along with governments and the private sector, play a pivotal role in helping poor people to improve their lives. / The PPA is one of DFID’s main support mechanisms to CSOs. In line with a commitment by the Secretary of State to support another round of PPAs over the 2011-14 period and following a robust selection process and implementation of a Resource Allocation Model, partners were identified for a 3 year PPA which began in April 2011. This is the last review for that reporting period. However, it should be noted that an additional two years extension has been agreed by the SoS for 2014-2016. Results from 2011-2014 will be progressed further under the extension period.

## Section A: Detailed Output Scoring

Output 1: Policy and Programme Recommendations developed through participatory country level analysis provided to at least four key international institutions and to civil society groups to support practical reforms in institutional peacebuilding practice.
Output 1 score and performance description: / A++ outputs substantially exceeded expectation.
Progress against expected results: / PROGRESS AGAINST INDICATORS / Indicator Statement Milestone/target for 2013/2014 Actual Achievement / No. and description of planning and consultation processes with stakeholders (4 target institutions as well as relevant civil society stakeholders in each case study country) 12 14 / Number and description of reports disseminated to target institutions 4 9 / Number and description of dialogue processes with institutional representatives and stakeholders facilitated by International Alert to promote take up of recommendations 4 7 / Indicator 1.1 – Target exceeded: International Alert has held planning and consultation processes with the Asian Development Bank (ADB), civil society, African Union (AU) officials and United Nations (UN) and World Bank (WB) project staff. All are important institutions, in which we would wish to see sound policy and programmatic approaches to Fragile and Conflict Affected States (FCAS). / Indicator 1.2 – Target exceeded: Four papers were disseminated and discussed with target organisations and stakeholders, including UN Peacebuilding Support Office, ADB, International Development Assistance (IDA 17) and members of the international community in Mali. These reports included policy or programme recommendations. A further two research – advocacy reports will be published early in year four. / Indicator 1.3 - Target exceeded: Highlights include IA’s work: engaging with the World Bank (WB) on their strategy and implications in FCAS at their annual meeting; mobilising the AU (at the January 2014 summit) to engage in the New Deal for Engagement in Fragile States implementation; and operationalising conflict sensitivity in the ADB. / Recommendations: None / Impact Weighting (%): 30% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 2: Reports, training and guidelines that will help economic actors in at least three fragile and conflict affected countries to strengthen their peacebuilding contribution are developed and disseminated.
Output 2 score and performance description: / A+ Outputs moderately exceeded expectation.
Progress against expected results: / PROGRESS AGAINST INDICATORS / Indicator Statement Milestone/target for 2013/2014 Actual Achievement / No. and description of companies/industry bodies provided with capacity building support in conflict sensitivity 8 14 / No. and description of Multinational Companies (MNCs) in Extractive Industries accompanied by International Alert to incorporate conflict sensitivity into their business practice. 3 3 / No. and description of published strategies for local economic development which are responsive to the conflict context and peacebuilding objectives in conflict affected countries. 12 13 / Indicator 2.1 – International Alert has exceeded this target, focussing capacity building activities with specific companies (Anglo Gold Ashanti, Repsol, Tullow and China Offshore National Oil) and industry bodies such as Kampala City Traders Association (KACITA) and the Mining and Energy Security Committee for Human Rights in Columbia. In this year, they have extended the reach of this activity beyond the original target. / Indicator 2.2 – Target met: ISAGEN, opted to work without support from International Alert in the reporting period. However there has been continued engagement with Anglo American in Peru and South Africa, with International Alert providing training, analysis and advice. International Alert has initiated a new relationship with Total in DRC and Uganda, providing conflict sensitive analysis on operations and anticipates a framework agreement with Total in year four. / Indicator 2.3 – Target exceeded: this year four new reports were published and disseminated to government, business, international actors and civil society. / Recommendations: If ISAGEN no longer need a partnership with International Alert (indicator 2.2) then International Alert should work towards identifying a new partner in order to reach future milestones. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: In South Asia and at least one other region, development and exchange of information on obstacles to climate change adaptation in fragile and conflict affected contexts through research, networking and consultations.
Output 3 score and performance description: / A++ Output substantially exceeded expectation
Progress against expected results: / PROGRESS AGAINST INDICATORS / Indicator Statement Milestone/target for 2013/2014 Actual Achievement / No. and description of local communities incorporated into study 6 districts across 4 countries 15 districts in 7 countries / No. and description of identifiable institutional interest groups (political parties, national ministries, and private sector) consulted in research and engaged in dialogues. 12 17 / No. and description of dissemination forums with donor agencies and other relevant programme providers to share findings and recommendations from study. 6 14 / Indicator 3.1 – Target exceeded: International Alert maintained research attention on South Asia, building on year one and two research data, to develop additional academic research publications. They also expanded the ongoing Tajikistan research to a new region. New research was initiated in East Africa (Rwanda and Kenya) engaging with local community members, government officials and Non-Governmental Organisations (NGOs). / Indicator 3.2 – Target exceeded: International Alert continues to consult with a range of donors/International NGOs (INGOs), academic and think tanks, practitioners (NGOs), national and local government agencies and the private sector. In this period, this has included additional interest groups including Arup Group Ltd, ActionAid, Kenya and Rwandan Governments, Adelphi and Koukeney Development Initiatives (KDI). / Indicator 3.3 – Progress has exceeded the target, with outreach through academic forums, events, engagement on climate diplomacy strategy (FCO and German Foreign Ministry), through thematic working groups (such as Interagency Resilience Working Group) and through traditional and social media. / Recommendations: None / Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? Yes - recommend that the risk rating is changed from medium to low.

Output 4: Major analytical report, to establish evidence base and provide practical guidelines on ways in which peacebuilding outcomes are strengthened by the incorporation of gender analysis into peacebuilding programmes.
Output 4 score and performance description: / A Output met expectation.
Progress against expected results: / PROGRESS AGAINST INDICATORS / Indicator Statement Milestone/target for 2013/2014 Actual Achievement / No. and description of country case studies where detailed research and analysis are undertaken. 4 4 / No. of peacebuilding programme areas (e.g. security, politics, economics) included in research and analysis. 4 4 / No. of and description of consultation and dissemination processes with donors and stakeholders to discuss research and findings and to share and test programming recommendations. 6 11 / Indicator 4.1 – Target met: Field research and analysis in Burundi and Nepal in year three informed the publication “Rethinking Gender in Peacebuilding” in March 2014. This was launched in the UK parliament (by the Parliamentary Under Secretary of State, Lynne Featherstone) and at presentations in Canada and the US. / Indicator 4.2 – Target met. International Alert increased the number of peacebuilding and programme areas from two to four in year two to include different permutations of violence and inter-generational conflicts. In year three, these two themes were re-visited in the initial target countries (Nepal and Burundi). / Indicator 4.3 – Target exceeded. Consultation throughout the year took place during the research phase, through a number of interactions with stakeholders in Burundi and Nepal and through dissemination and validation of the “Rethinking Gender in Peacebuilding” report. This has led to: follow up requests from the Geneva Centre for the Democratic Control of Armed Forces (DCAF), the Organisation Economic Cooperation and Development (OECD) and the United Nations Environment Programme (UNEP); input to MoD training; and International Alert acting as an advisor on the UK National Action Plan and for the East Africa Regional Office of UN Women. / Recommendations: This output to be substantially reviewed in order to set realistic targets for the remainder of the programme (year 4 &5) given that a major publication has already been achieved in March 2014. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 5: Engagement in inclusive dialogue processes in conflict-affected countries that address how to build a peaceful state and incorporation of lessons/experiences into advisory work with international agencies to support on-going strengthening of international peacebuilding.
Output 5 score and performance description: / A+ output moderately exceeded expectations
Progress against expected results: / PROGRESS AGAINST INDICATORS / Indicator Statement Milestone/target for 2013/2014 Actual Achievement / No. of countries and description of dialogue processes 6 6 / No. and description of policy development processes involving international actors which Alert engages in. 7 8 / No. and description of training and learning processes with foreign ministry staff and other key officials engaging in bilateral relationships in conflict affected states. 12 23 / Indicator 5.1 – Target met: International Alert continues to work on building state–citizen relationships through dialogue, citing their engagement in Myanmar and DRC as good examples of different themes potentially driving conflict (economic development and cross border trade). / Indicator 5.2 – Target exceeded: International Alert continues to engage on policy processes such as the Sustainable Development Goals and producing and, for example, distributing a post 2015 policy paper. They continue to build cumulatively in engagement of eight different international policy processes (UN Peacebuilding Commission review, International Dialogue on Peacebuilding and Statebuilding etc.). This is through a variety of mediums including advocacy, engaging on policy discussions, promoting conflict sensitivity or providing advice on institutional structures (for example to the European External Action Service). / Indicator 5.3 – Target exceeded: International Alert continue to deliver across a range of training courses and learning events for key officials engaging in conflict affected states. This includes the UN, Europe’s New Training Initiative for Civilian Crisis management (ENTRI) and UK, WB and INGO’s ‘understanding of conflict and fragility’ training courses. Of 275 participants in 2013, the analysis indicates increased understanding of conflict and peace issues, including the application of conflict sensitive principles and increased ability to conduct conflict analysis and incorporate findings into strategy and programmes. / Recommendations: None / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? / Outcome indicator #4 referring to gender was revised to make it more realistic and measurable. The essence of the indicator was changed from evidence of target organisations actually adopting changes, to evidence of their interest in exploring International Alert’s recommendations, as illustrated by requests for International Alert’s guidance. / 1.2 Overall Output Score and Description: / A+ outputs moderately exceeded expectation. / 1.3 Direct feedback from beneficiaries / The 2013 Annual Review (AR) identified the lack of beneficiary feedback and encouraged International Alert to do more with regards to independent feedback on measuring impact. The International Alert PPA focuses primarily on generating institutional change to enable longer term benefits for people affected by violent conflict in fragile and conflict affected countries. / The direct target group is therefore people and intermediate organisations, whose behaviours International Alert aim to change / International Alert applies an iterative approach to their research and influencing, seeking to collect feedback through the regular planning and consultation meetings with stakeholders and tailoring their advocacy work accordingly. / In year 3, International Alert have therefore continued to solicit direct feedback from beneficiaries, and additionally engaged a consultant to obtain independent feedback through a beneficiary feedback exercise. Proximate beneficiaries were identified by International Alert staff and nineteen semi structured interviews conducted. Findings are detailed in the longer report submitted by International Alert, as evidence for this review.
1.4 Summary of overall progress / International Alert has made good progress over the last year, and the self-assessment was particularly strong in referencing the evidence of activities against outputs. The approach to mainstreaming the overall management of the PPA, as opposed to designating a PPA manager, has enabled greater clarity of how PPA funding is linked to specific outputs and overall impact. As the funding continues for a further two years, it should enable progress to continue to be monitored effectively.
1.5 Key challenges / One significant and two more minor challenges are identified: / Capturing higher level impact: International Alert seeks to promote institutional and organisation reform in target organisations. Feedback has highlighted the challenge in evaluating such as approach, in particular, in directly attributing International Alert’s work, to changes in target beneficiaries. Current PPA reporting (logframe based) is very focused on measuring activities and related outputs, with little monitoring and evaluation of higher level impact. Whilst measuring influence is challenging, as the International Alert PPA seeks to influence behavioural change, future monitoring and evaluation efforts should focus on higher level impacts. In September 2013, International Alert also adopted a new Monitoring and Evaluation Improvement Plan. Building on this work, DFID and International Alert should agree a realistic monitoring and evaluation plan, to enable a focus on impact, over the next 2 years of the programme. This will be a significant challenge. / Flexibility: Overall the objectives of the International Alert PPA are to influence behavioural change, working closely with people and organisations to integrate peacebuilding and conflict sensitivity into their programmes. Working in and on FCAS requires a certain level of flexibility to respond to the evolving nature of conflict and the challenges this presents. This was specifically highlighted for example on output 1. Some states remain resistant to FCAS concepts, because of the political constraints in labelling member states as “fragile”. Whereas some donors are more ready to promote a FCAS approach, aligned with the International Alert PPA goals. The recent World Bank Strategy represents an important opportunity for change. International Alert therefore continues to adapt their approaches – through research, opportunity, evidence and feedback - to the variable nature of working in FCAS. / Managing demand: In year 3 there has been an increase in demand for International Alert’s engagement, in particular on conflict sensitivity, gender and peace-sensitive climate balance. This has presented an additional challenge, in terms of resources, but also an opportunity to further contribute.
1.6 Annual Outcome Assessment / The expected outcome is that International Alert will target international institutions, governments, private sector actors and civil society agencies so that they apply concepts and methodologies, which reduce conflict and promote peacebuilding, in at least 10 fragile and conflict affected states. Recommendation: / Based on the International Alert Annual Review Report, and the significant progress made in each output, if the theory of change and related assumptions hold, we expect the PPA to achieve its Outcome. Future reviews should focus on outcome and impact level indicators, to better enable an assessment of higher level impact.

2. Costs and timescale
Is the project on-track against financial forecasts: / Yes, annual funding through the PPA is disbursed in four equal amounts on a quarterly basis. The full annual allocation was disbursed as expected. / Key cost drivers: / International Alert has identified expenditure on staff, travel, consultants, ICT, office costs, meetings and grants to partners as the key cost drivers. This is particularly driven by operating costs overseas, which vary due to external drivers (such as insecurity). International Alert monitors and aims to improve cost effectiveness, through their management systems. This includes: / Monitoring core costs as a % of total costs (metric): this information forms part of the annual budget approval process and is tracked regularly by Senior management and the Board. From 2009 – 2013 International Alert’s total expenditure increased 40% (£9.7 million to £13.5 million) while the core costs as a percentage of total costs reduced from 23% to 19%. / Procurement: providing clear guidelines which ensure competitive bidding. / Implementing partners: seeking to reduce costs associated with implementing partners, through evaluating their management capacity, VFM and financial management. / 2.3 Is the project on-track against original timescale: / Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / International Alert has significantly increased the amount of evidence provided in support of their PPA activities and outcomes (a separate submission from International Alert provides more detail and background to the information briefly summarised in this review). This increased evidence helps to fully support the funding provided as being effective and VFM. There were no implications for the future of the project. / 3.2 Where an evaluation is planned what progress has been made? / The PPAs as a whole are served by an umbrella evaluation strategy, the first of its kind for DFID, which ALSO encompasses the Global Poverty Action Fund. This strategy examines progress at fund and at individual, organisational level. Following the announcement of the extension to the PPA fund in 2013, the evaluation strategy was reviewed and, in addition to the individual progress reviews (IPRs) and meta evaluation that took place in 2012, a further two evaluations are planned for 2014/2015 and 2016/17. The evaluation is managed by an externally contracted evaluation manager. / The 2014/14 evaluation has started and focuses on the assessment of the fund-level effects of PPA grants. This fund-level evaluation will use 12 organisations to illustrate the effects of the PPA fund and evidence from all 41 organisations to evaluate progress and outcomes. The aim is to provide timely, fund level evaluation information for the design of any future strategic funding modalities in 2014/15 ahead of fund completion in 2016. The evaluation in 2016/17 will focus on the impact of PPA funding for organisations.

4. Risk
4.1 Output Risk Rating: / Medium / 4.2 Assessment of the risk level / The risk rating for indicator 3 has been reduced from medium to low in year 3. This is to reflect the good progress that International Alert has achieved on this specific indicator, and the limited challenges identified. The overall risk level on the project has remained the same (medium). There is no evidence to suggest that this should change in the future.
Risk of funds not being used as intended / International Alert underwent pre-grant due diligence checks carried out by KPMG. The pre-grant due diligence assessed capacity to manage the proposed level of DFID support in the following areas: / Governance / Financial Capacity / Operational Capacity / Value for Money / Results / Satisfactory completion of the due diligence process was required before any money was disbursed. This helps to reduce the risk of diverted funding while establishing an environment of accountability and transparency. Organisations also had baseline up-dated due diligence assessments carried out in March 2014 to ensure that processes and strategies were current and complementary to DFIDs due diligence framework and modules. International Alert is adhering to the outcome of the March 2014 due diligence assessment as part of their PPA extension MOU. / Climate and Environment Risk / Output 3 of this programme specifically relates to climate adaptation as a peace and security issue. The environmental impacts of climate change are having, and will have, significant effects on political, social and economic aspects of people’s lives, which can lead to conflict and violence. International Alert’s research and advocacy has focussed on the obstacles to climate change adaptation in fragile and conflict affected contexts. And they continue to promote this agenda internally within their organisation on how to integrate climate and environmental issue into other areas of work. / International Alert also has a simple Environmental Policy, under which they aim to reduce their carbon footprint through energy efficiency measures. Examples of activities include avoiding unnecessary travel, reducing energy consumption in headquarters and publishing documents online to reduce the size of print runs.

5. Value for Money
5.1 Performance on VfM measures / International Alert has made significant efforts to focus on VFM across the PPA. This has included improving business practices, decentralising budget management, implementing a four year business plan with clear targets for internal cost ratios and establishing a flexible consultants and associates database. In 2014 they have committed to an organisation-wide VFM approach and and explicit VFM strategy. This will have particular emphasis on staff awareness, efficiency gains through process improvement, review and further implementation of the business plan and sharing and collaborating with others on VFM. In terms of overall programme effectiveness, International Alert will also integrate VFM into their M&E, piloting a review to assess the value of a project outputs and outcomes against the project value. And they will seek to link this to further beneficiary feedback to improve projects. International Alert have responded to feedback on previous ARs to further improve monitoring and evaluation of impact and linking this directly to VFM. / 5.2 Commercial Improvement and Value for Money / International Alert has been an active member in the PPA Learning Partnership sub-group on VFM, participating in VFM mapping, benchmarking and checklist tool development. International Alert carries out regular salary and benefits benchmarking surveys and has set commercial fee rates for consulting work in addition to developing “product sheets” for the different services they provide. / 5.3 Role of project partners / International Alert adopts 4 models for engagement with project partners: / Partnership with advocacy targets (whose approaches they aim to change), for example international organisations (AU, UN PBSO), private sector (Total, Anglo American) or governmental departments (FCO, DFID). / Partnership around policy advocacy with other organisations, such as NGOs, who share advocacy goals. For example on post 2015, New Deal, OECD Expert Group on Resilience. / Project consortia, implementation of large projects by a mixture of NGOs and consulting companies. This is critical for future funding and programming opportunities. / Local implementing partnerships with organisations in most of the countries where Alert works, combining International Alert’s globally informed skills and knowledge with those of local actors. / 5.4 Does the project still represent Value for Money : / Yes / 5.5 If not, what action will you take? / Not Applicable

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
International Alert is required to submit a final extension logframe by 30 September 2014 incorporating any feedback given on it in the annual report feedback letter and subsequent discussions. They must ensure that learning and results from this PPA period are reflected in their milestones and targets for 2014/2016. Organisations have also been asked to set out the substantive and measureable steps they will be taking to enhance work on transparency and value for money.

8. Review Process
International Alert submitted a self-assessment annual report of their progress and performance against the PPA log frame during this third year of PPA funding. DFID reviewed this annual report and provided feedback to International Alert on both strengths and weaknesses reminding organisations of the need to improve year-on-year on VfM, results and transparency. The feedback incorporated comments from a range of officials in relevant country and policy teams.