Annual Review – post April 2018

Title: / Title: Unlocking the potential of groundwater for the poor in Africa (UPGro)
Programme Value £ (full life): £8m (+ £2m NERC and £2m ESRC)		Review Date: October 2018
Programme Code: 203774	Start Date: 10/12/2012	End Date: 31/03/2020

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018
Programme Score	A	A	A	A	A+	A+
Risk Rating	Low	Low	Low	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203774/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203774/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

DFID is contributing £8million to support research that will unlock the potential of groundwater for the poor in Africa (UPGro). The Natural Environment Research Council (NERC) and the Economic and Social Research Council (ESRC) are providing £2million each, giving a programme total of £12million. NERC is also providing in-kind resources and systems to commission and manage the research calls and related procurement throughout the life of the programme. The programme will run over seven financial years from December 2012 to March 2020 and is open to UK and non-UK researchers.

UPGro delivers knowledge and information required to help better access and manage groundwater resources to enhance water security for the 300 million poor people without access to improved water in Sub-Saharan Africa, and to better exploit the potential role groundwater can play in Africa’s economic development.

Water resources are critical to economic growth and social development. A study on groundwater in Africa has shown that there is possibly 20 times more water available as groundwater compared with that available in lakes and rivers[1]. Groundwater provides most of the domestic water supply in parts of rural Africa and supports poverty reduction through access to clean drinking water and irrigation[2]. It is estimated that groundwater provides water for domestic supplies and livestock for more than 100 million people and is the source of drinking water for 75% of Africa’s population (although this varies in proportion by country/sub-region)[3]. Ensuring availability and sustainable management of water resources has been enshrined in the UN Sustainable Development Goals (SDGs) under SDG 6. In 2015, 6.6 billion people, or 91 per cent of the global population, used an improved drinking water source, versus 82 per cent in 2000. Despite that improvement, an estimated 663 million people were using unimproved water sources or surface water that year. Groundwater has the potential to provide an improved source of drinking water for those in SSA who are currently without access.
[1] MacDonald et al. 2012. Quantitative maps of groundwater resources in Africa. Environ. Res. Lett. 7. 024009
[2] Hunter et al. 2010. Water Supply and Health PLoS Med7 (11): e1000361
[3] UNECA African Climate Policy Centre 2011 Management of Groundwater in Africa including transboundary aquifers: Implications for meeting MDGs, livelihoods goals and climate change adaptation. Working Paper Number 6.

With increasing pressures on water resources, the potential pressure on groundwater as the solution to the water security challenge in Africa is high. As the population grows, water security in SSA will become increasingly important and demands on groundwater are likely to surge. Poorly managed water resources will constrain opportunities for development, including better services and livelihoods for poor people. Despite the importance of groundwater in meeting water security needs for poor communities in Africa, there remain big challenges to realise this potential, including substantial knowledge gaps[4].
[4] MacDonald AM, Bonsor HC, Calow RC, Taylor RG, Lapworth DJ, Maurice L, Tucker J and Ó Dochartaigh BÉ. 2011. Groundwater resilience to climate change in Africa. British Geological Survey Open Report, OR/11/031. 25 pp.

Without addressing some of these core gaps in the evidence and data, it will be hard to identify and manage the full implications of increased groundwater use. UPGro is funding high quality environmental and social research to address these issues. The programme aims to deliver robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa. All research supported under UPGro will deliver outputs that can be used by policy makers and other stakeholders to inform effective decision-making and planning. The UPGro programme has two phases, the initial phase (2013-2015) comprised 15 initiator ‘Catalyst’ projects that investigated different aspects of how the use and understanding of groundwater in Africa interacts with socio-economic conditions. Phase II was launched in 2015 and comprises five substantial ‘Consortium’ research projects, which will run until 2019-20 and are undertaking detailed research on several aspects of ground water in Sub Saharan Africa (SSA). The table below provides further details on each project and a brief explanation of their area of research.

#	Consortium Projects (2015-2019)
	Project Title	Area of Research/Problem statement
1	Gro for GooD: Groundwater Risk Management for Growth and Development	To design, test and transfer a novel, interdisciplinary and replicable Groundwater Risk Management tool to improve governance transformations to balance economic growth, groundwater sustainability and human development trade-offs.
2	Grofutures: Groundwater Futures in Sub-Saharan Africa	To develop the scientific evidence and inclusive groundwater management processes by which groundwater resources can be used sustainably for poverty alleviation in Sub-Saharan Africa (SSA).
3	BRAVE: Building understanding of climate variability into planning of groundwater supplies from low storage aquifers in Africa	To develop water demand scenarios to inform the modelling of water resources and availability in future years. This work will be based on current domestic, agricultural and productive use needs and will be set within the context of the current impacts on existing needs and demands.
4	T-GroUP: Experimenting with practical transition groundwater management strategies for the urban poor in Sub Saharan Africa	To investigate the social, technical and political changes needed to make the shift towards sustainable urban groundwater management. Using “Transition Management theory” to find radically new and collaborative ways of using and managing urban groundwater.
5	Hidden Crisis: unravelling current failures for future success in rural groundwater supply	To achieve a more complete understanding of how to keep water flowing from boreholes, reducing waste and improving water services for Africa’s poorest communities, reducing wasted investment by water users, charities and tax-payers due to water point failure.

Additionally, the UPGro-funded Africa Groundwater Atlas and Literature Archive (http://www.bgs.ac.uk/africagroundwateratlas/index.cfm) continue to prove to be an invaluable resource for African groundwater researchers. A list of the catalyst grants can be found at: https://upgro.org/

Summary supporting narrative for the overall score in this review (1/2 page)
The UPGro programme is performing strongly. Milestones have typically been met or exceeded. While progress varies across the consortia, there are already examples of impact. Further impact level achievement and consolidation in due course, can be expected based on the solid progress at outcome level and the strong co-production and partnership processes that have been developed with stakeholders and users.

2018 Highlight(s)
UPGro-led groundwater monitoring has identified the threat of declining groundwater levels to Addis Ababa. This is now being acted on by DFID and the World Bank in the design of new programmes.

Gro for GooD team secured additional resources to develop smart monitoring technology. The award winning “Smart Handpump” work has explored the links between handpump use and rainfall (quantifying how and when handpump use decreases and recovers after a rainfall event), and also between handpump handle movement and groundwater level in the borehole. These data-driven insights are helping to improve the sustainability and service level of the Fundifix water supply enterprise, which is being incubated by Oxford University team as part of Gro for GooD (UPGro) and REACH.

Tools and methods for groundwater data organization and analysis developed by University Milano Bicocca during the Catalyst UPGro project have been put into practice to set up the national groundwater database in Guinea Bissau (through a joint collaboration with UNICEF and Direccao Geral Recursos Hidricos) and DRC (in collaboration with UNICEF and SNHR). In both cases they have been used to explore the potential for manual drilling in the shallow aquifer and start the process to create a standardised groundwater information system.

Road drainage techniques developed under an UPGro Catalyst grant are now being adopted and applied by road authorities in Ethiopia, Kenya, Nepal and Bangladesh and is also under active development in Malawi and Uganda. This has influenced the international Roads for Water consortium which is now launching the Green Roads for Water Initiative. The main goal is to have roads systematically used for water management, re-greening and climate resilience as an industry standard in at least 50% of countries in the world by 2025.
.

Gender. The UPGro team have worked proactively to include and address gender issues within the programme approach. The main dimensions of the approach and progress relate to:

- Girls and young women. For example, Gro for Good consortium has established School Water Clubs in the Kwale County study area in Kenya. Outreach has involved around 120 students (66% girls) and there is interest to replicate the Club and associated Water Module training approach more widely in Kenya.
- Women as (ground) water users. For example, the Hidden Crisis Consortium project is enabling women’s voices in the study areas to be heard by the Government in Ethiopia, Malawi and Uganda: Following study investigations, the issues are discussed jointly with community representatives and the District Water office, and women’s voices are empowered by the combination of independent evidence from the forensic analysis and their opportunity to discuss with the government officials. In addition, these experiences have been combined and analysed and enabled WaterAid, to bring these voices to multi stakeholder fora and discussions with the national water ministries
- Women as leaders and decision-makers: For example, T-GroUP’s Learning Alliance inclusive and participatory approach is gaining recognition and adoption as a safe space for engagement and contributing to developing woman leadership skills and women empowerment. Another example is the relationship the BRAVE project has developed with the Director of the Women in Agricultural Development Directorate (WIAD) at the Ministry of Food and Agriculture MoFA, Ghana. She is helping the researchers to better reflect gender issues in groundwater utilization and provide a pathway to support policy change.
- Empowering Female researchers within the programme. Within its development of Early Career Researchers (ECRs) UPGRo is seeking to is support female researchers, in a challenging historical context of dominance of male academics in the groundwater arena (See output 2). An African female researcher presented at Africa Water Week, illustrating opportunities being given at high level technical and political events.

Champions for uptake. UPGro’s approach of using select ‘Ambassadors’ – recognised African experts from government or academia – is proving successful in driving awareness of groundwater issues through raising awareness of UPGro research and in facilitating uptake and influence on policy and practice. Two UPGro Ambassadors played a key role in the 7th Africa Water Week (AWW) conference, sitting on various panels for a range of conference sessions. UPGro Knowledge Broker (KB) worked strategically to get a significantly stronger focus on groundwater in the conference content than has been the case for past events. This included an inclusive set of sessions on ‘Groundwater Thursday’ which culminated in a set of groundwater messages for AMCOW and its secretariat to take into account in their continental planning and prioritisation. In another example an UPGro Ambassador was able, in addition to chairing several sessions, to give a key-note presentation on African groundwater (which followed the opening keynote by the President of Zambia) in a Catalyst grantee organised International Conference on Mining, Minerals and Groundwater. Such a well-positioned keynote would not have been offered to the Knowledge Broker or consortia PIs..

Cross-programme collaboration. The UPGro team are not only harnessing synergy between the different Consortia’s activities within the programme but additionally fostering collaboration and learning with other DFID supported research programmes. For example, with Future Climate For Africa (FCFA), REACH (improving water security for the poor) and SHEAR (Science for Humanitarian Emergencies And Resilience) – where joint work to strengthen research uptake and participation of southern partners has been supported. (See also Annex B.)

Awards: UPGro’s notable performance is also reflected by members of the team achieving a number of awards during the reporting period:
- Oxford University Vice-Chancellor’s Innovation Award 2018 (Gro for GooD) for Smart Handpumps initiative
- Golden Jubilee Award for Dr Robinah Kulabako (T-GroUP) – Women in Science
- 2nd Place Zilient Resilience Award: Roads for Water (Catalyst)
- UPGro Ambassador invited to give prestigious 2017 Ineson Lecture at UK Geological Society
- UPGro Knowledge Broker, Dr Kerstin Danert, wins International Association of Hydrogeologists (IAH) Distinguished Associate Award

Recommendations for the year ahead (1/2 page)

Undertake early preparatory discussion and planning to help make the most of the final UPGro year, especially regarding dissemination and uptake facilitation work. Pick up explicitly at next Project Executive Board (PEB) in early 2019. This should include:

- Explore merit of focused effort to better harness, articulate and leverage UPGro work on climate change. For example, produce a synthesis product on groundwater and climate change, potentially in conjunction with other programmes such as FCFA and REACH.
- Ensure UPGro collective attention (PEB/PCG/KB) to maximising the prospects of the relatively limited work under the Agricultural Impact theme delivers to its full potential.

KB to further assess the impact of the earlier Catalyst Grants through some further longitudinal analysis via for example, a status update on any further influence Grant outputs have had since the last assessment, and where any involved Early Career Researchers now are. (Action by July 2019.)]

BGS to refresh survey of use of the Groundwater Atlas and archive (to get better picture of diversity and depth of use beyond the known immediate academics). (Action by April 2019)]

BGS in conjunction with PEB to continue the ongoing exploration of ways to embed long term sustainability of the Groundwater Atlas & Archive. (Progress update by next PEB meeting)

Increased attention on African female authorship is warranted in the coming year as this year’s milestone was missed. [PCG]

The Consortia no-cost extensions, while still within the overall Programme timeframe, now mean that the residual time for the Knowledge Broker to maximise synthesis, dissemination and facilitation of uptake is compressed. The significance of this should be kept under review via the PEB.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Research contributing to sustainably managed groundwater resources for poor people in Sub-Saharan Africa of a high academic quality is generated and disseminated
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

OUTPUT 1		INDICATOR		Baseline (2014)	Reported for 2017	Milestone 2018	Progress 2018
Research contributing to sustainably managed groundwater resources for poor people in Sub-Saharan Africa of a high academic quality is generated and disseminated	1.1	Peer-reviewed papers: Cumulative number of peer-reviewed articles in journals, book chapters.
			Catalysts	2	17	15	20
			Consortia	-	16	35	41
			(Knowledge Broker)	-	0	None	2
			TOTAL	2	33	50	63
	1.2	Conference presentations: Cumulative number of presentations (oral or poster) at international academic, policy or practice conferences disaggregated by project: KB/At/Am = Knowledge Broker, Atlas Team, Ambassador
			Catalysts	44	77	60	77
			Consortia	-	115	140	159
			KB/At/Am	2	15	25	22
			TOTAL	46	206	180	258
	1.3	Peer-reviewed papers (interdisciplinarity): Cumulative number of papers where the authors are from different disciplines and/or the paper Combines social/policy and physical/natural sciences.
			Catalysts	1	5	6	7
			Consortia	-	8	10	12
			(Knowledge Broker)	-	0	None	2
			TOTAL	1	13	16	21
	1.4	Peer-reviewed papers (author representation): Cumulative no. of papers with lead (first or second) authors are:
	Catalysts		[1.4.1] Female	0	6	6	9
			[1.4.2] African	2	6	5	7
			[1.4.3] African female	0	2	2	3
	Consortia		[1.4.1] Female	-	7	17	19
			[1.4.2] African	-	2	11	8
			[1.4.3] African female	-	1	5	1
	1.5	Data: Number of DMPs in place and being satisfactorily implemented		-	5	5	5
	1.6	Dissemination: Cumulative number of research document downloads from UPGro website, RWSN websites and Africa Groundwater Atlas.		1,122	6,859	7000	8677

2018 Highlight(s)
- The academic output from the programme is making a substantive contribution to physical, social and interdisciplinary science around African groundwater resources, management, governance and use. This has been effectively communicated through face-to-face and online means.
- Online dissemination of research and findings to UPGro countries has also been done through the stories of Early Career Researchers and enhanced through selective targeting, including use of Facebook advertising. This approach was trialled in 2018 and achieved success at reaching online users in Kenya, Tanzania, Malawi, Uganda and Rwanda. Targeting capability through Facebook advertising is proving effective to reach women in particular. ResearchGate is used to target researchers specifically.
In the reporting period there has been strong performance in publications - with 29 papers and book chapters were published: 10 physical science, 11 interdisciplinary and 8 social science. Of these 29, 4 were from Catalyst projects, 2 from the Knowledge Broker and 23 from the Consortia. There were a further 3 papers reported that are indirectly UPGro[5]. Total milestones have typically been exceeded. The sub-milestone for African authorship was narrowly missed, but there are 4 papers pending that qualify that have been accepted or have been submitted for review and this milestone is expected to be met in the next 3-6 months. The milestone on African female authorship was missed and needs to be addressed in the coming year.
[5] i.e. UPGro researcher is author on related research but not funded by UPGro for that work
There were fewer presentations in the 2018 period than in the previous year, but this reflects the focus of the research teams on analysis of their field data this year; and also that the 2018 IAH Congress was held in South Korea, making it more expensive and less relevant than previous years so fewer researchers attended. The Knowledge Broker/Ambassadors and Atlas team did not quite reach the milestone of 25 presentations as of reporting in October, but this will have been achieved by now given events in late October/early November when the Ambassadors will have presented at various sessions at the Africa Water Week in Gabon and the Knowledge Broker team will have convened a session at the UNC Water & Health Conference. The progress of this indicator also reflects the increasing emphasis to get ECRs presenting rather than the Ambassadors / KB themselves.

UPGro continues to pursue proactive online dissemination, exceeding the 2018 milestone. The UPGro website (upgro.org) is the gateway to the programme, and is also a management tool which is updated on a regular basis to provide a comprehensive store of materials emerging from the programme and links to organisations, articles and events where UPGro is visible. Visits to UPGro platform shows steady growth (and this does not include visits to the four Consortia’s own project websites[6]). The cumulative total number of individual visitors detected by the Wordpress analytics to upgro.org is 31,792. The top 10 of visitor countries to upgro.org in 2018 (1 Jan – 2 Oct) are as follows:
[6] http://t-group.science/ https://braveupgro.org/ https://upgro-hidden-crisis.org/ http://grofutures.org/

1	UK	6	South Africa
2	USA	7	Tanzania
3	Kenya	8	Malawi
4	India	9	Canada
5	Netherlands	10	Uganda

Lessons identified this year, and recommendations for the year ahead linked to this output

Facebook advertising has been tested and is proving good value, particularly as a means to reach and inspire young women in Africa. For example, blog posts featuring an interview with a young T-GroUP researcher from Pakistan who did UPGro research in Tanzania could be advertised exclusively to women Facebook users between the age of 18-35 in Tanzania and Pakistan. Other filters are also available, including interests and education level. Another advantage of targeted online advertising is that through “likes”, sharing and click-throughs it is possible to see what types of post or advertising is interesting and engaging to the target demographic.

Indicator 1.4.3 on African female authorship was missed and needs to be addressed in the coming year.

Output Title	UPGro early career researchers (ECRs) equipped with the skills to collaborate and communicate their work in the wider context of poverty and groundwater science and governance
Output number per LF		2	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

OUTPUT 2	INDICATOR	Baseline (2014)	2017[7]	Milestone 2018	Progress 2018
	International events: Cumulative % of Early Career (EC) researchers from each project giving at least 1 presentation research findings at international conferences. (disaggregated by sex and nationality)
	[2.1.1] % of all EC Researchers	0	19 / 28%	60%	34 / 50% 
	[2.1.2] % of female EC researchers	0	10 / 38%	60%	15 / 65% 
	[2.1.3] % of African EC researchers	0	7 / 19%	60%	14 / 36% 
	[2.1.4] % of African female EC	0	1 / 11%	60%	3 / 38% 
	Training, coaching and mentoring: Cumulative % of Early Career (EC) UPGro researchers receiving training or systematic coaching and mentoring (disaggregated by sex, nationality).
	[2.2.1] % of all EC Researchers	0	34 / 51%	60%	51 / 75% 
	[2.2.2] % of female EC researchers	0	14 / 54%	60%	16 / 70% 
	[2.2.3] % of African EC researchers	0	31 / 72%	60%	34 / 87% 
	[2.2.4] % of African female EC	0	7 / 78%	60%	7 / 88% 
	Knowledge sharing: Cumulative number of UPGro Early Career (EC) that have actively participated in at least one international knowledge sharing event, such as a PCG workshop/webinar; (disaggregated by sex and nationality).
	[2.3.1] % of all EC Researchers	0	33 / 49%	60%	54 / 79% 
	[2.3.2] % of female EC researchers	0	13 / 50%	60%	21 / 91% 
	[2.3.3] % of African EC researchers	0	14 / 39%	60%	26 / 67% 
	[2.3.4] % of African female EC	0	2 / 22%	60%	6 / 75% 
[7] Note that 2017 Milestone for these indicators was 30%

2018 Highlight(s)
- An MSc student from Pakistan and the T-GroUP project is now full time staff at the Dutch NGO, Aqua for All, on the REACH programme junior global advisory, and is President of the Water Youth Network. She took part in plenary panel on the theme of partnerships at the 2018 UNC Water & Health Conference.
- 8 Early Career Researchers presented their work at the WEDC conference in Kenya, in a special UPGro session and separately, two of them presented their own UPGro-based papers.
- Interviews with ECRs have been used as the basis for UPGro blog posts and new articles that have been published in national and international newspapers.
- A Hidden Crisis researcher from Chancellors College, University of Malawi was chosen to be the Malawian Ambassador for the Next Einstein Forum (see below)
UPGro have continued to give due attention to enabling ECRs to fully participate in the programme and then proactively provide diverse opportunities for their further development (see examples below for the various indicators). Specific effort continues to be made within the ECR programme to ensure adequate emphasis on female and on African ECRs. The majority of milestones have been met; for those that haven’t there is still an improvement compared to last year (see table below), and in one case the milestone has only just been missed. Moreover: the relevant milestones were significantly higher than last year (from 30% to 60%) representing an ambitious step-up; it has become relatively harder to reach the log frame % milestones targets because of both the absolute increase in number of ECRs and the cohort turnover over the course of the last three years. Overall, numbers of ECRs, opportunities given, and their level of participation are still impressive. In this context the progress made is deemed to have met expectations overall.

No. of ECRs who have participated in qualifying activities, by year
	Year
Log Frame Indicators – no. of ECRs	2018	2017	2016
2.1.1 per year - all ECRs	31	14	12
2.2.1 per year - all ECRs	44	12	10
2.3.1 per year - all ECRs	51	33	10

#### Indicator 2.1 International events - number of early career researchers presenting
ECRs presented their UPGro work at the following international face-to-face and online events:
- UNC Water & Health Conference, October 2017 [x1]
- Ineson Lecture, London, November 2017 [x3]
- RWSN-UPGro Webinar, online, March 2018 [x2]
- European Geosciences Union (EGU) 2018, Vienna, Austria, April 2018 [x1]
- 41st WEDC International Conference, Nakuru, Kenya, July 2018 [x8]
- 10th Session of the Learning Platform on Water Security and Society, Ouagadougou, Burkina Faso, 4th August 2017 [x1]
- International Association of Hydrogeologists Congress 2018, Seoul, South Korea, September [x2]
#### Indicator 2.2 - Training, coaching and mentoring of Early Career Researchers
Example training activities undertaken include:
Type	Trainer	Content/Description
Field-based	BGS	Training in Detailed Hydrogeological science methods (pumping tests, groundwater chemistry sampling; borehole CCTV surveys; metallurgy testing). Training conducted by BGS, for Hidden Crisis - Survey 2.
Workshop	Sheffield University	Training in coding and interpreting social science survey data, Kampala.
Research visit	BGS	Capacity building in research analysis, networks and publications
Workshop	Oxford-Man Institute	Machine Learning
NERC Workshop	NERC	Social Science Techniques for Natural Scientists
NERC Workshop	NERC	Media Training
Workshop	ISGEAG project	ISGEAG Training (Improving Sustainable Groundwater Exploration with Amended Geophysics - Kwale site)
Workshop	GroFutures	Social science training by in Niamey, Niger
Workshop	GroFutures	A training on groundwater flow modelling with MODFLOW FREEWAT software environment was conducted as a side event during the GroFutures' 3rd Annual Workshop in Niamey, Niger. Ten participants attended the training workshop. The training workshop was run by GroFutures' manager,and was co-run/assisted by an early career member of GroFutures
Field-based	GroFutures	Use of automated data-loggers for groundwater-levels, soil moisture and rainfall
PhD Supervision	Senior UPGro staff	PhD Supervision

#### Indicator 2.3 Knowledge sharing by early career researchers
The PCG coordinator continued the series of internal webinars held in previous years with one specifically for ECRs to share ideas and experiences on interdisciplinary groundwater research. In addition, ECRs are reported to have taken part in the following events (not necessarily as presenters)
- RWSN Side Session and Oxford-led session on Future Technology for Water Quality Monitoring at UNC, USA
- Schools Water Club Event, Kwale, Kenya
- UNC Webinar on Remote Monitoring of Handpump Functionality, online
- RWSN Webinar Series Late 2017 and early 2018, online
- 7 x T-GroUP Arena meetings in Tanzania and Ghana
- T-GroUP Uganda Workshop, CEDAT, Makerere University, Uganda
- International WATERS network Webinar – Groundwater and equity, exploring barriers to access to water in the global south, Online
- Kampala International Project Workshop (Hidden Crisis), Uganda
- OII Symposium on Big Data and Human Development, Oxford, UK
- Women in Machine Learning, Monday, December 5, 2016, Co-Located with NIPS in Barcelona, Spain[8]
  [8] http://wimlworkshop.org/2016/
- Mary Douglas Seminar at University College London's Department of Anthropology. "How can rival institutions cohabit? Plurality and settlement in social relations, policy making and the state".[9] London, UK
  [9] https://www.water.ox.ac.uk/a-cultural-theory-of-drinking-water-risks-values-and-institutional-change/
- GroFutures 3rd Annual Workshop, Niamey, Niger
- Training DEIE and DGRE staff on improving groundwater monitoring, Ouagadougou, Burkina Faso
- Training 2iE staff and students from U. of Ouagadougou in IWR and crop monitoring, Sanon, Burkina Faso
- AMCOMET Africa Hydromet Forum 2017, Addis Ababa, Ethiopia

Lessons identified this year, and recommendations for the year ahead linked to this output

- The KB has reported that the indicators used to reflect progress under this output have been time-intensive to collate and quality control because of the large number of individuals, activities and interpretations of definitions. Factors like staggered recruitment of ECRs, junior ECRs early into the programme and not ready to present at major events, turnover of ECRs etc have complicated matters. While the programme team have undoubtedly worked hard and in suitable ways regarding ECR inclusion and development, current gross data may under-represent the effort and achievement.
- Adjustment in indicator structure and methodology are probably not worth undertaking, despite the issues noted above, given implementing actors are familiar with the requirements and next year is the last year. However, the PEB should consider downward adjustment of the final milestone target.

Output Title	Targeted awareness-raising of policy-makers, practitioners and change makers on the realities and potential of groundwater for the poor in Sub-Saharan Africa (SSA)
Output number per LF		3	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

OUTPUT 3		INDICATOR	Baseline / (2014)	Progress Reported in 2017	Milestone 2018	Progress 2018
Targeted awareness-raising of policy-makers, practitioners and change makers on the realities and potential of groundwater for the poor in Sub Saharan Africa (SSA)	3.1	Involvement in research: Cumulative Number of stories of SSA stakeholders involved in the development of the research plans and the testing and validation of practical tools, manuals, handbooks, guidelines and frameworks for groundwater management.	0	14	L: 7 / M: 10 / H: 30	12  (M)
	3.2	Briefing materials produced: Cumulative Number of policy and practice briefing materials and syntheses produced by UpGro research projects.	15 Catalyst project + 1 overall Catalyst flyer / UPGro leaflet / UPGro pull-up banner	29	L: 20 / M: 25 / H: 35	44  (H)
	3.3	UPGro (co-)organised events: Cumulative Number of UPGro project events/sessions with policy-makers, practitioners and change makers where research findings are presented.	Africa:/ Intl: 1 UK: 2	25	L: 20 / M: 25 / H: 35	42 (H)
	3.4	Decision-making processes: UPGro projects actively involved in national (and sub-national) sector processes and events (e.g. sector reviews, planning and policy meetings).	0	+15	At least 2 processes or events per project	23

L=Low;M=Medium;H=High ambition scenario
2018 Highlight(s)
- Active learning alliances established in Arusha, Tanzania and Dodowa, Ghana alliances have developed into valued platforms for dialogue and decision-making for stakeholders and researchers.
- Use of radio programmes and learning alliances in Burkina Faso is helping connect government with farmers and with the researchers.
- Government bodies at national, city and local levels in Ethopia, Malawi, Uganda, Tanzania, Kenya and Ghana have been active actors within the research processes.
#### Output 3.1 Sub-Sahara African Stakeholder Involvement in UPGro research
The key stakeholder groups that UPGro is currently engaging with are as follows[10]:
[10] These represent a consolidation from previous reporting - the number of (stories of) stakeholder engagement processes has reduced from 14 reported last year to 12, organised around specific stakeholders (or stakeholder groups) and reflecting the evolution of their involvement.
1. Ethiopian irrigation authorities
2. Government of Tanzania Ministries of Water & Irrigation and Agriculture, Rufiji Basin Water Board
3. Water Ministries in Ethiopia, Uganda, Malawi
4. WaterAid country offices in Ethiopia, Uganda, Malawi
5. 2iE and WASCAL in Ghana and Burkina Faso
6. Ghana Meteorological Agency
7. Water Resources Management Authority (WRMA) and The Environmental Monitoring Network, Kenya
8. Oromia Irrigation Development Authority, Ethiopia
9. Arusha city authorities and residents (Arusha Learning Alliance)
10. Dodowa city authorities and residents (Dodowa Learning Alliance - DLA)
11. Improving Sustainable Groundwater Exploration with Amended Geophysics project (ISGEAG), Kenya
12. Government Farmers, NGOs and Water Users in Burkina Faso
#### Output 3.2 Briefing Materials
UPGro has produced a diverse set of briefing material this year, as illustrated in the table below. In addition to this there have been other newsletters from the projects and the Knowledge Broker as part of the RWSN newsletter sent 4 times a year to the whole network (members: 10,568), and then separately to the RWSN Sustainable Groundwater Development community (members: 1,279).
Hidden Crisis	Review of handpump-borehole implementation in Uganda, British Geological Survey Open Research Report, 96pp	Liddle E, Fenner R
Hidden Crisis	A political economy analysis of Uganda's rural water supply sector, Overseas Development Institute Report	Denis Le Seve, M
Hidden Crisis	A political economy analysis of Malawi's rural water supply sector, Overseas Development Institute Report	Oates, N. and Mwathunga, E
Gro for GooD	How has devolution fared in its first term? Responses from Kwale County at the end of the transition period, UPGro Policy Brief	Johanna Koehler, Gro for GooD project
Gro for GooD	Poverty transitions in Kwale County, Policy Briefing Note	Jacob Katuva, Gro for GooD project
Gro for GooD	Risk Factors associated with rural water supply failure, Research Brief	Tim Foster
Gro for GooD	A critical mass analysis of community-based financing of water services in rural Kenya, , Research Brief	Tim Foster
Gro for GooD	Evaluating waterpoint sustainability research, , Research Brief	Tim Foster
Gro for GooD	Gro for GooD Newsletter June 2018
Gro for GooD	WaSH Policy Research Digest, Issue #8, MAY 2018: Remote monitoring of Handpump Functionality	Patrick Thomson
Gro for GooD	The Water Module (training)	Gro for GooD project
T-GroUP	T-GroUP Brochure & Poster for community level dissemination of research results in Dodowa	T-GroUP Dodowa Transition Team
GroFutures	Uncertainty in the sustainability of Dodoma's water supply (in press)	Richard Taylor, Japhet Kashaigili
Knowledge Broker	4 Infographic posters (English and French versions available)	KB + Project teams
BRAVE	BRAVE Newsletters 4-11 2018	BRAVE team

#### Output 3.3 UPGro at Events
In the reporting period, in terms of logframe reporting, there have been 17 events at which UPGro has been an organiser, co-organiser or convener of either the whole event or a part of it. It should be noted that UPGro has participated in some form in a much larger number of events.
#### Output 3.4 Decision-Making Process
The numbers in the Log Frame are derived from UPGro engagement in the following processes:
Stakeholder	Issue/Process
Kenya Water Act	Informed process of drafting national water act to include private sector models for rural water provision
Kenya Country Water Bill	Drafting of prototype County Water Bill
Kenya Devolution Process	Informing 3rd Annual Devolution Conference on impact of devolution on water sector
White Volta Basin authority 5 year planning process	Review/expansion of groundwater and incorporation of gender issues in 5 year planning process
Ethiopia WASH sector working group	Informing working group on defining and measuring functionality
Bwaise Church Group, Uganda	Decision on where to drill in study area
WWF Water Stakeholder Platform, Kenya	Building common understanding of water management issues in Kwale (Mkurumudzi River catchment)
Ethiopia: Multi-stakeholder forum WASH Cluster (MSF8)	Informing functionality definition
Ethiopia One WASH Programme (Ministry of Water Irrigation and Electricity)	Informing technology choice and management arrangements for the planned Lowland Resilient WASH programme
Uganda: National Working Groups [National standards and RWS] and District coordination meetings	Informed drafting of 2 national directives (use of galvanised iron pipes for RWS & drilling contracts procedure)
Planning and policy meeting with DUWASA (Dodoma Urban Water Supply and Sewage Authority) and Ministry of Water & Irrigation	Informing monitoring, operation and abstraction policies for the Makutapora Well Field
Ghana Parliamentary Select Committee	Raising awareness of key Water Resource Management issues
MOLE Water Users Stakeholder Platform, Ghana	Informing WASH sector on sustainable groundwater use for national WASH policies
Meetings with DEIE (DIRECTION DES ETUDES ET DE L’INFORMATION SUR L’EAU) and 2iE, Burkina Faso	Agreement to co-develop tools for analysis of long-term groundwater level to feed into water resource management process
Water World Day Malawi National Meeting	Informing Ministry of Water on research findings and progress to inform definition and measurement of functionality
District Water Offices , Malawi	Informing district water officers of research findings and progress to inform definition and measurement of functionality
National Government, Ministry of Water Resources, Malawi	Informing technical group meetings of research findings and progress to inform definition and measurement of functionality
Kwale County Coast Water Service Board	Informing CWSB, mandated to develop GW infrastructure, on potential GW resources in Kwale
Sub-catchment Water Resources Management Plan workshop	Participation in the Mkurumudzi Sub-catchment Water Resources Management Plan workshop to review and validate the management plan
Arena meetings series 4 – AGENDA SETTING - Communities Dodowa, Ghana: Wedekum, Obom, Zongo, and Aperkon (4 separate meetings)	Defining community actions to achieve envisaged futures
Arena meetings series 5 – COALITION BUILDING FOR TRANSITION EXPERIMENTS - Dodowa, Ghana: Communities Wedekum, Obom, Zongo, and Aperkon (4 separate meetings)	Defining short-term community actions to achieve envisaged futures
Policy Roundtable in Accra, Ghana with National Disaster Management Organization, MOFA-WIAD and CONIWAS	Discussion on unlocking the potential of groundwater for the poor
African Development Bank: Rural Water Supply & Sanitation Initiative (RWSSI) Strategy 2018-2025 consultation	Participation in RWSSI strategy consultation

Lessons identified this year, and recommendations for the year ahead linked to this output

See Learning, section G.

	Output Title		Current and potential groundwater users participate and influence the UPGro research and are presented with the findings
	Output number per LF				4	Output Score				A+
	Impact weighting (%):				25%	Impact weighting % revised since last AR?				N
OUTPUT 4				INDICATOR			Baseline / (2014)	Progress Reported in 2017	Milestone 2018		Progress 2018
Current and potential groundwater users participate and influence the UPGro research and are presented with the findings		4.1		Groundwater users engaging with researchers: Cumulative number of stories where users have participated and influenced the methodology and results of the UPGro research (stories should highlight participation of women and of the poor)			0	Catalyst: 1 Consortia: 13	At least 15		Catalyst: 1 Consortia: 15 
		4.2		Reporting of research progress and findings to water users: Cumulative number of face-to-face events and activities that give feedback on the research progress, findings and practical implications to the groundwater users that are/were the target of the research.			0	12	15 or at least 3 per consortium project		19
		4.3		Media coverage in UPGro countries: Cumulative number of programmes or articles on UPGro work in local media (radio, newspapers, TV). Blog posts not included due in unknown reach/impact			2 articles in UK/Int.	12 / (+31 Int.)	15		17 / (+ 34 int.)

2018 Highlight(s)
- T-GroUP ‘Transition Management’ workshops undertaken in two slum areas (Dodowa, Ghana; Arusha, Tanzania) have been effective in putting groundwater users at the centre of the research and decision-making process.
- The role of groundwater users in shaping farmer radio programmes in Ghana and Burkina Faso is helping to make it a more effective and engaging means to support farmers in those areas on different aspects of water and climate resilience for their livelihoods – particularly pollution prevention to reduce aquifer contamination, and more effective use of groundwater for productive and domestic uses.
#### Output 4.1 Groundwater users engaging with researchers
Progress reported against this milestone is derived from the following distinct engagements with users as part of the research process:
1. Niger farmers brought onto campus
2. Building consensus with the Groundwater Game in Tanzania
3. Working with Ward and Street communities to find the best sampling points in Dodowa
4. Water users helping steer the fieldwork in Ethiopia, Uganda and Malawi
5. Water User Focus Groups in rural Ghana and Burkina Faso
6. Women as community-based researchers, in Malawi and Uganda
7. Interdisciplinary fieldwork with rural communities in Ethiopia
8. Water users help design environmental monitoring network, Kenya
9. Water users in Tanzania. Niger and Ethiopia help researchers find and explore groundwater development pathways
10. Farmer groups come together to help shape educational radio outreach programmes for Burkina Faso and Ghana
11. Science Cafés in Dodowa slum build trust and balance gender representation
12. Water diaries to record water stress in Malawi and Uganda
13. Federation of the Urban Poor actively represent groundwater users in Arusha, Tanzania
14. Transition Management opens up a space for debate and discussion for urban water uses in Dodowa, Ghana
15. Community-based environmental monitoring in Burkina Faso and Ghana
#### Output 4.2 Reporting of research progress and findings to water users
Progress reported against this milestone is derived from the following.[11]
[11] For simplicity each meeting or set of meetings is treated as one, however, Hidden Crisis systematically reported back their survey findings back to the communities they visited (ca. 140 meetings)
Year	No.	[Year reported/updated] Description	Project
2016	1	Stakeholder workshop in Ukunda, Kwale County, Kenya	Gro for GooD
2016	1	Informal communication of results to borehole/well owners on groundwater water by UPC water quality researchers.	Gro for GooD
2016	1	Project meeting with BASE Titanium staff (major corporate groundwater user)	Gro for GooD
2017	42	Ethiopia: 42 individual meetings with community members including water committees and wider representation of water users of individual water points to discuss the results of the 2 days of forensic investigation of their failing boreholes.	Hidden Crisis
2017	45	Uganda: Individual meetings (45 )with community members including water committees and wider representation of water users of individual water points to discuss the results of the 2 days of intensive investigation of their failing boreholes.	Hidden Crisis
2017	1	On 3rd March 2017, the Gro for GooD project held a stakeholder workshop in Ukunda, Kwale County at which local organisations and community representatives were provided with an update on the monitoring and modelling that will underpin the Groundwater Risk Management Tool, and how the research can contribute to county-wide planning for improved water supplies.	Gro for GooD
2017	1	20 members of the Rotary Club of Diani (business people in Kwale County) received a presentation from Gro for GooD hydrogeologist Mike Lane. The presentation covered drought, groundwater use and sustainability using evidence from the Gro for GooD project. The club requested this input to gather advice about a borehole they are planning to drill for a local school.	Gro for GooD
2017	1	In May 2017, 35 representatives from the East African Women's League (EAWL) gathered to hear a presentation on Shallow Wells and Handpumps by Mike Lane, Gro for GooD hydrogeologist.	Gro for GooD
2017	1	BRAVE team led by Lorna Young Foundation ran meetings (start of rainy season) in Ghana (April) to initiate provision of information about groundwater to communities through face to face training, co-ops/reps/education guides and local level platforms including community radio.	BRAVE
2017	1	BRAVE team led by Lorna Young Foundation ran meetings (start of rainy season) in Burkina Faso (May) to initiate provision of information about groundwater to communities through face to face training, co-ops/reps/education guides and local level platforms including community radio.	BRAVE
2017	1	BRAVE researchers and project staff participated in Celebration DRR, Burkina Faso helping to enhance understanding of sustainable use of groundwater in Burkina Faso (in parallel to MOLE conference)	BRAVE
2017	?	Early 2017, a number of science café's and knowledge dissemination meetings were held in T-GroUP areas in Ghana and Tanzania with the aim to inform communities of research findings, to make the project more visible and to prepare the ground for the next phase of the project.	T-GroUP
2018	50	Malawi: Individual meetings (50) with community members including water committees and wider representation of water users of individual water points to discuss the results of the 2 days of intensive investigation of their failing boreholes.	Hidden Crisis
2018	1	On 17th March 2018, an event to celebrate the School Water Clubs set up in Kwale County was held. Outreach by Gro for GooD and local partners including BASE Titanium has involved around 120 students (66% girls). Professor Dan Olago gave a keynote on groundwater, followed by student presentations on club activities including water quality testing, rain gauge installation, and demonstration of a solar still.	Gro for GooD
2018	12	12 Arena Meetings with slum residents in Dodowa, Ghana	T-GroUP
2018	3	Kampala, Uganda, December 2017: Dissemination of T Group Project findings in 3 meetings with the community members in 3 parishes in Bwaise slum.	T-GroUP
2018	3	Kampala, Uganda, March-April 2018: Second community arena meetings with selected actors from 3 different parishes in Bwaise slum	T-GroUP
2018	1	Kampala, Uganda, May 2018: An arena meeting in which all the actors from the three communities. The T group project members present at the meeting were Dr. Robinah Kulabako, Dr. Philip Nyenje, Ms Jennifer Isoke, Dr. Joel Kinobe, Peter Kiyaga and PhD student Felix Twinomucunguzi	T-GroUP
2018	6	6 Arena meetings with slum residents in Arusha Tanzania	T-GroUP

#### Output 4.3 Media coverage in the UPGro countries
The Knowledge Broker team continue to use their regular column in trade magazine “GeoDrilling International” to raise awareness of African groundwater issues. An article published in December 2017 focused on the views about the priorities for African groundwater by the UPGro Ambassadors at the meeting in London[12]. While the Consortium teams have engaged less directly with the media than in previous years, the Knowledge Broker team has worked with a freelance journalist based in Kenya who is a regular correspondent for the Reuters international news agency and the PAMACC regional climate change news agency. In the reporting period he has focused on the work of Gro for GooD in Kwale County, Kenya, especially through the voices of the Africa researchers. The resulting stories published through Reuters were published in Kenyan newspapers – The Daily Nation, Star Newspaper and The Standard, as well as internationally in the Spanish broadsheet, El País[13]. Examples include:
[12] https://upgro.files.wordpress.com/2017/12/gdi1712_lr1011.pdf
[13] https://elpais.com/elpais/2018/07/03/planeta_futuro/1530632022_962959.html

- PAMACC/Isaiah Esipisu (2018) Scientists interrogate why boreholes often fail soon after construction, 24 July 2018
- The Daily Nation/Isaiah Esipisu (2018) Let’s tap underground water with caution, 19 July 2018
- El País/Isaiah Esipisu, Robert Carmichael (2018) Kenia busca agua bajo sus pies, 19 July 2018
- PAMACC/Isaiah Esipisu (2018) Young African geology researchers share experiences on an international platform, 12 July 2018
- Reuters/Isaiah Esipisu (2018) Kenya takes a look into the unknown: Its underground water reserves, 2 July 2018:
- Star Newspaper/Isaiah Esipisu (2018) Kenya takes a look into the unknown: Its underground water reserves , 2 July 2018
- The Standard/Isaiah Esipisu (2018) Kenya takes a look into the unknown: Its underground water reserves  2 July 2018
- Gulf News (2018) Kenya takes a look into the unknown: Its underground water reserves, 2 July 2018
- Oman Daily Observer (2018) Kenya takes a look into the unknown: Its underground water reserves, 8 July 2018
- Brits in Kenya (2018) Kenya takes a look into the unknown: Its underground water reserves, 16 July 2018
- Africa Renewal/Ihuoma Atanga (2018) The Internet of everything water, May-July
- The Christian Science Monitor/Isaiah Esipisu (2018) In sustainability search, Kenya studies the unknown depths of its aquifers, 2 July 2018
- Taipei Times/Isaiah Esipisu (2018) In sustainability search, Kenya studies the unknown depths of its aquifers, 3 July 2018
- GeoDrilling International/Sean Furey (2017) Politics of Water, December 2017
- Science, Vol 358, Issue 6366, 24 November (2017) Valuing water for sustainable development, pp. 1003-1005 OI:10.1126/science.aao4942, Dustin E. Garrick, Jim W. Hall, Andrew Dobson, Richard Damania, R. Quentin Grafton, Robert Hope, Cameron Hepburn, Rosalind Bark, Frederick Boltz, Lucia De Stefano, Erin O’Donnell, Nathanial Matthews, Alex Money

Lessons identified this year, and recommendations for the year ahead linked to this output

See Learning, section G.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

UPGro’s overall approach can be broadly summarised as follows:

Each of the 5 Consortia has developed a ‘Pathway to Impact’ which specifies the particular approach for the issues they are addressing. There have been no major changes to these in the last reporting period. The PCG will be recommending that the Consortia revisit their Pathways by early next year for any refinements to help maximise uptake in the last 15 months or so of the Programme.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

UPGro is on track and already showing evidence of impact (see Highlights in Summary and Overview Section). Different dimensions of impact are emerging across a range of themes/stories as illustrated below.

Story	Description	Project
Socially inclusive and sustainable rural water services
1	How water-point functionality is measured and reported has been improved: Three African governments have taken ownership of their water point functionality problems; Uganda has taken action; International organisations are taking note.	Hidden Crisis + KB
2	Influencing how UNICEF WASH programmes consider groundwater data, water point functionality and sustainability.	Hidden Crisis, Gro for GooD + Catalysts + KB
3	The Fundifix model of rural water service delivery is changing how services are delivered – and how they are documented.	Gro for GooD + KB
4	UPGro has been a catalyst for greater academic rigour and exchange between researchers and practitioners through its thematic and financial inputs to the Rural Water Supply Network (RWSN)	All
Urban Groundwater Security
5	UPGro monitoring and research informs response to Addis Ababa declining groundwater levels.	GroFutures/ Hidden Crisis
Groundwater for Agricultural Growth and Transformation
	In process, see outcome discussion below.	BRAVE/Gro for GooD
Groundwater Resources Monitoring and Management
6	Africa Groundwater Atlas & Grey Literature Archive.	Atlas
7	Kwale County Water Master Plan.	Gro for GooD
Groundwater & Climate Change
8	Roads for Water recharge.	Catalyst

This progress at impact level is underpinned by strong performance at outcome level (see table and highlights below)

OUTCOME		INDICATOR		Baseline (2014)	Reported for 2017	Milestone 2018	Progress 2018
Use of robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa	O.1	Use of evidence by other researchers: Citation of UPGro research in briefing papers, working papers and conference proceedings and peer-reviewed articles and book chapters.[14]
			Catalysts	7	117	110	222
			Consortia	-	41[15]	L:30 / M:50 / H:75	151
	O.2	Use of evidence by national decision-makers: Number of National Sector Performance Reports, Joint Sector Review reports or other key reports, strategies and plans that directly or indirectly reference UPGro research.		0	2	3	9
	O.3	Use of evidence by international decision-makers: Number of key international documents, such as JMP, GLAAS, UN World Water Development Report that directly or indirectly reference UPGro research.		0	1	1	4
	O.4	Use of evidence contributing change: Number of stories of changes to groundwater use that have affected the poor in Sub Saharan Africa, which were influenced by UPGro or where UPGro research has influenced policy, the institutional framework, practice, groundwater monitoring and research.		0	1	3	10
[14] Note: Self-citations are included so that collaborative work is not discouraged
[15] Note that the 2016 figure didn’t include self-citations and combined the catalysts and consortia into a single figure

2018 Outcome Highlight(s)
Through UPGro:
- Reports on handpump functionality prepared for Uganda and Malawi have now been adopted by the appropriate ministries and published as official documents.
- Completion of an unprecedented analysis of 14 multi-decadal, groundwater-level records from 9 countries including Benin, Burkina Faso, Ghana, Namibia, Niger, South Africa, Tanzania, Uganda and Zimbabwe has shown that most current hydrological models are underestimating groundwater recharge in arid and semi-arid areas.
- Improved monitoring Ethiopia is revealing that the groundwater resources supporting Addis Ababa are facing rapid decline.
- At the continental scale, analysis of satellite data has revealed no large scale aquifer depletion, but this does not discount localised over-abstraction because of the coarse resolution of gravity-derived measurements.
- Improved understanding and management of the aquifer supplying Dodoma, the Capital of Tanzania.
- New groundwater resources discovered and mapped in SW Kenya.
- Improved monitoring for agriculture in Ethiopia (GroFutures/Hidden Crisis).
- Use of radio programmes in Burkina Faso and Ghana is showing promise for improving the climate resilience of farmers.
- The Transition Management approach is generating interest as mechanism to engage and empower slum residents to improve access to improved WASH services.
- The University of North Carolina Water Institute researchers have continued to promote UPGro research and researchers and it has also informed their own research on water point sustainability.

Explain major changes to the logframe in the past year (1/2 page)

Following discussion with PIs and PEB, impact level indicators have been consolidated down into success stories, allowing for more thematic impact reporting – see Theory of Change section for current emerging themes. (This change does not preclude covering previous indicator attributes within the broader impact stories where relevant.)

Describe any planned changes to the logframe as a result of this review (1/2 page)

The following adjustments/clarifications will be considered:
Outcome indicator 3 - clarifying that reporting on this attribute should allow progress made with coalitions or networks to be reported, not just single entity decision-makers.

Output indicator 1.2 - consider adjustment of the milestone/target, given the increased emphasis on enabling ECRs presenting rather than the lead PIs or the KB themselves.

Output 2 ECR indicators – consider downward adjustment of the final milestone targets, given these are very ambitious (and see output section for explanation of current challenges).

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The original UPGro Business Case identified the following key elements of VfM:

- Leveraging of Research Council UK funds.
- Use of well-developed and robust RCUK systems.
- Competitive research calls to identify and fund the highest quality research.
- Value for money guidance at the peer review and panel stages.
- Wired link between research and impact to ensure UPGro delivers benefits for poor people through research uptake in developing countries.

These have not changed and the UPGro programme continues to deliver good results against all criteria.

The programme leverages resources from both the Natural Environment Research Council (NERC) and the Economic and Social Research Council (ESRC), which are DFID’s co-funding partners and who continue to provide additional pro-bono resources to ensure the effective and smooth management of all activities. This is particularly relevant for the administration and management of all research calls and associated activities, such as peer reviewing of proposals, financial management and supervision of contracting / granting arrangements with all implementing partners. Over the lifespan of the programme, management costs are expected to equate to approximately 4% of the total cost.Given that this is provided as an in kind contribution from NERC, in addition to their cash contribution, this represents significant VfM for DFID. The linkages between research and impact are delivered through a joint effort between DFID, NERC and ESRC and all impact strategy plans agreed at the Programme Executive Board (PEB) level.

Key cost drivers and performance
The key cost drivers originally identified for UPGro include research staff costs, costs of equipment and consumables, and travel and subsistence. These have not changed since the programme was approved and NERC assess these as part of the grant review process to ensure costs are kept down. The Moderating Panel for the major consortium round scrutinised costs requested in the grant proposals and deemed the costs for the 5 projects awarded to be justified. Any significant future variations to the project plans have to be agreed by the PEB, who will take VfM into account.

Furthermore, the programme aims to deliver strong value for money against the following five criteria of: economy, efficiency, effectiveness, cost-effectiveness and equity. This is currently achieved as follows:

- NERC exerts pressure for economy (minimising input costs) through close scrutiny of budgeted and actual costs of each grant. Where it is possible to identify unit costs that are comparable between projects (for example, in travel budgets or day rates of senior staff), NERC provides guidance on what is reasonable and what is excessive. NERC reviews budgets and expenditures (at application and peer review) and will ask grant holders to reduce high costs. Highly competitive research commission also keeps costs competitive;
- Efficiency (maximising research outputs in relationship to budget inputs) is a function of ensuring that research grants are of high quality. Stiff competition due to the heavily over-subscribed nature of the scheme; due diligence assessment of the delivery capacity of contracted researchers; and clarity (between DFID, ESRC and NERC) and transparency (between NERC and applicants) regarding the purpose and priorities of the UPGro programme all help to ensure that efficiency is maximised. Effectiveness (the translation of research outputs into outcome) and cost-effectiveness (the ratio between inputs and impact). As can be seen from sections A and B, the programme is now starting to achieve at outcome and Impact levels, providing assurance that by programme end the research is likely to be effective in (i) helping to shape understanding of groundwater issues across an number of countries and contexts in Africa and (ii) exerting a positive influence upon practice (programmes and policies).
- Since the Business Case was approved, DFID has introduced equity as a fourth dimension of its approach to framing VfM. UPGro’s strategy includes non-UK researchers from Sub-Saharan countries as key partners in the research which contributes to sound performance on this dimension of VfM. See also Equity section below. Furthermore, relevant to the equity dimension is UPGro proactive work on gender and Early Career Researchers (see Overview and Output 2 sections respectively). UPGro researchers are very active in stakeholder and community engagement,and using interdisciplinary research in which the social science fieldwork combines with the physical sciences to co-create new knowledge and enhance reporting back to stakeholders.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

This programme is assessed as continuing to deliver good VfM. The firm base established, including through the use of the robust RCUK peer review and cost control systems for competitive research calls, has delivered high quality research. These are now seeing emerging success at the outcome and impact levels.

VfM measures have continued to evolve during programme implementation. Beyond the overarching approach on VfM in the set-up of UPGro as highlighted above, UPGro team members have continued to try and enhance VfM in the technical implementation of the programme. Examples include:

Economy: Successful elements in one part of the programme have been deployed elsewhere in the programme. For example: Tryptophan-like Fluorescence (TLF) groundwater quality monitoring tool developed by an UPGro catalyst has been used in other UPGro and NERC/DFID programmes (including the equipment). There has also been sharing of logistics, equipment and workspace between different programme and projects (e.g. in Ethiopia between Hidden Crisis, GroFutures and the REACH programme). Equipment, such as borehole cameras, has been shared between country teams.

Efficiency:
- A programme coordination group (PCG) was established to integrate the 5 consortia to ensure that the outcomes of the programme are greater than the sum of its individual parts, and to enable efficient engagement with the funders and the knowledge broker, while enhancing the link between research and impact.
- Research Output Clustering - To make the body of work emerging from UPGro easier to find and navigate, three online clusters are curated by the Knowledge Broker:

- UPGro website publications page – a simple list ordered chronologically: https://upgro.org/publications-papers/peer-reviewed-journal-papers/
- ResearchGate UPGro project – an online profile to increase discovery of research by other researchers: https://www.researchgate.net/project/UPGro-Unlocking-the-Potential-of-Groundwater-for-the-Poor
- Kumo – an online mapping tool that where research outputs are clustered thematically: https://kumu.io/Sean-skat/upgro-research-publications

There are various examples of links between UPGRO and other DFID Programmes and use of UPGRO Projects in other Programmes - see Annex B.

Effectiveness: Leveraging in additional funding attracted/influenced in 2017/2018:
- Gro For GooD has attracted additional funding from UNICEF to help develop the smart handpump sensor technology further.
- The contribution of UPGro to the effectiveness of the Rural Water Supply Network (RWSN) was acknowledged in the independent external evaluation of the network undertaken during 2017. As a direct result, the Swiss Agency for Development & Cooperation (SDC) increased their funding contribution to Skat Foundation and made a commitment to support the network to 2030. This new agreement was signed in April 2018.
- Because of the Knowledge Brokering expertise developed by Skat through UPGro (and REACH), the African Development Bank commissioned the Skat KB team to facilitate and document their 2nd Rural Water Supply & Sanitation Initiative (RWSSI) Forum in Abidjan in November 2017 and support the RWSSI team to strengthen the Research-into-Use elements of their emerging strategy and working groups.
- The Hidden Crisis project team has been successful in leveraging funds for three additional PhD students and a spin off project to help develop a sensor for estimating E-Coli contamination. The success of the Hidden Crisis project is due to the care taken in developing a statistically robust sampling strategy for rural water points in Uganda, Ethiopia and Malawi. This has provided an attractive framework for other projects to build upon, adding in other measurements and analysis into the surveys. The leveraged funds now amount to approximately £300k.

Equity
DFID has continued to emphasise this aspect to UPGro. In turn, UPGro PIs and KB have proactively worked to enable and enhance the African researchers, from junior to senior levels, role in leadership and as active voices in communicating and influencing. This has included:
- Of the 148 researchers and project staff in the programme, 80 (54%) are African + 4 African Ambassadors;
- There are 19 African women in the programme, of which 9 are mid to senior and 10 are Early Career.
- Overall there are currently 49 women working in the UPGro programme, which is 33%. This is not ideal but a reflection of the male-dominance in the natural sciences, particularly at a more senior level. This justifies the investments being made in providing opportunities for career development and profile among all the women
- Making presentations at international conferences; and media interviews for local and international stories.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The overall risk rating of the project is assessed as Moderate. The table below provides a description of assessment against principal risk categories:

Risk category	Risk Analysis and description	Risk level
External context	The external context for this project is generally favourable and the broader area of research well developed and mature. Conducting research in country specific contexts will always entail a degree of risk, which will vary from country to country. The programme is operating in potentially difficult contexts (e.g. Kenya, Nigeria, Niger Ethiopia), which present some challenges and could affect the delivery of activities for some projects. This issue is being tackled at two levels: i) the project level where each consortium is following the security procedures and ‘duty of care’ guidelines employed by each research institution and ii) the programme level where the PEB has revised the risk associated with each proposal and periodically reviews any changes in circumstances that may affect the work and/or safety of any of the research team involved.	Moderate
Delivery	The risk related to the delivery chain for this programme is low. This is mostly due to the streamlined and simple structure of the programme, which involves a first layer of consortia (5 in total) that are led by at least one UK or European research institution and a second layer of sub-contracted service providers/institutions, mostly based in SSA. Because of the granting arrangements employed by NERC all second layer delivery partners and service providers are accounted for and are requested to sign agreements that meet RCUK and DFID standards. Non-UK or other unrecognised institutions funded under such arrangements are required to gain full RCUK recognition before contracts can be issued and funding can commence and full due diligence checks are in place to complete these checks. In order to ensure compliance, NERC operates a number of sanctions against institutions or individuals that fail to comply with the terms and conditions of their grants. The NERC risk assessment strategy also recognises this as an important issue in the current research funding environment.	Moderate
Operational	Ensuring high levels of transparency and strict standards with the sub-contracting of second tier implementing partners has resulted in low levels of risk in the delivery category but has had an impact on the programme operations both in terms of delays and morale among consortium members. The programme has developed an approach to overcome this challenge and ensure mitigation of any impacts on the programme. More specifically, they have realised that they need to ensure the project PIs build sufficient time into proposals to allow for appropriate contracting of second tier partners and contractors. The Research Councils also engage with Higher Education Institutions to improve collaborative working practice that ensures good financial management of ODA grants and sub-contracts. This risk was initially ‘Major’ but has been downgraded to Moderate given the actions undertaken over the last reporting year.	Moderate
Safeguards	UPGro is a research programme and as such it involves intrinsically low levels of risk in this category. Its subject matter which aims to attain environmental sustainability in the use and management of water resources is a further guarantee that all the standards and environmental safeguard principles are adhered to. Social and environmental safeguards are also guaranteed through the mandatory principles that all UK and EU based research intuitions must follow in order to retain their ISO accreditations and respect EU funding rules. UKRI (under which NERC falls) Central Services Policy Team is currently exploring options for an enhanced safeguarding policy elements of which would cover conduct of researchers receiving UKRI funding. UKRI representatives attended the safeguarding Summit in October 2018 to help inform this further strengthening of existing safeguarding policy, and UKRI was a signatory of the safeguarding summit statement.	Minor
Fiduciary	The fiduciary risk associated with the granting /contracting of both layers of suppliers and partners is managed by NERC in accordance with the strict rules set by RCUK and has been revised in full to ensure it satisfies DFID due diligence requirements. To this date there have been no reported issues in this area and NERC remains confident of its level of oversight and ability to intervene in case of any reported incidents.	Moderate
Reputational	Reputational risk for this programme is very low. All research proposals have been thoroughly reviewed and scrutinised in line with the strict standards imposed by the UK Research Councils and are implemented by internationally recognised research institutions. The subject matter of the research is uncontroversial and there is very little scope to generate outputs that may have an adverse impact on any specific group of stakeholders in partner countries. On the contrary, the research funded under UPGro is expected to deliver substantial benefits to government agencies and local communities alike, by producing evidence that can significantly improve the management and availability of water resources for economic and social development purposes.	Minor

Overview of programme risk
Through peer review and expert advice, the NERC only give grants to institutions recognised as bona-fide research institutions through due diligence checks, and on the condition that those institutions and award holders are willing to adhere to NERC comprehensive terms and conditions. In general, only accredited UK institutions are eligible for NERC Research grants. Non-UK or other institutions funded under this scheme are required to gain full RCUK recognition and are subject to a due diligence process before contracts can be issued and funding awarded.

Update on partnership principles [[if relevant. If it’s not – delete this section, but only having read the text in the Smart Guide at the end]] (1/2 page)
Not applicable. There have been no changes to established partnership principles. It should also be noted that UPGro is a multi-country programme and does not provide funding through government systems.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Delivery against planned timeframe
The project is on track to deliver within overall planned timescales and spending levels are also on track and in line with agreed schedule. This said, while still within the UPGro timeline, the main consortia have typically been awarded limited no-cost extensions have been granted and this compresses the residual time for the Knowledge Broker to maximise synthesis, dissemination and facilitation of uptake. The significance of this issue should be revisited at the next PEB meeting early next year.

Performance of partnership (s)
Partnerships are overall performing well given the trusted relationships that have developed. UPGro is co-funded by NERC and ESRC, which provide contributions of £2 million each to the total £12m programme. NERC additionally provides in-kind support in the form of the Programme Secretariat that is responsible in major part for the implementation. The programme is overseen by a Programme Executive Board (PEB), with an independent chair. Skat Foundation are contracted to perform the Knowledge Broker role. The NERC Secretariat manages the portfolio of funded scheme awards. The same team manage communication with award holders from the application stage, granting successful awards and then throughout the course of the funded project. As such good working relationships have been established and continue with the community of award holders.

All live projects are required to submit biannual reports via the knowledge broker. These report on project progress and provide an opportunity to highlight emerging findings and flag up where there has been evidence of research impact or uptake. NERC review for any necessary action and raise any significant aspects with DFID.

The Secretariat also deals with ad hoc issues raised by award holders. The NERC finance team is responsible for the financial management and oversight of scheme awards. Where no-cost extensions are awarded this does not impact upon the profiling of award spend or DFID payments. In the case of a no-cost extension, the award profile remains the same: the extension affects the final reconciliation payment only which will be delayed according to the amount of the extension. DFID payments will remain in line with the original profile; NERC will manage the slight variation in final reconciliation payments within its own accounting systems.

Asset monitoring and control
Not applicable – UpGro does not have Capital Expenditure subject to NERC rules on Assets.

Financial Performance
Financial management is good with no issues arising during the reporting period. Disbursement, monitored on a quarterly basis, is broadly on track (and Financial Year 2018\19 is the last major year of spending). When NERC conducts reconciliation review next year this may warrant a slight adjustment in DFID’s disbursement profile regarding the last payment. NERC ensures sound financial management at the level of individual grants through a combination of pre-conditions imposed at procurement stage and ongoing annual reporting requirements, as set out in the RCUK-standard terms and conditions attached to grant awards. NERC contracts are concluded with a lead institution: this institution assumes responsibility for ensuring good financial management (and avoiding project-level under- or over-spend) through any ‘sub-contracts’ with other project partners. In addition, a range of processes and safeguards are in place to ensure value for money is assured throughout the application, review and award granting process:

- At the application stage value for money (VFM) is a stated assessment criterion in the scheme specification and applicants are required fully cost all elements of their proposed research and provide detailed justification for each item of expenditure. Peer reviewers and panel assessors are asked to consider VFM as part of the grant assessment and is one of the factors which panel members consider when making final funding recommendations.
- At the award contract stage all costs are subject to detailed scrutiny by the NERC Secretariat. Any unjustified or excessive costs may be removed from the budget.
- Grants are only held by institutions which have passed RCUK recognition processes, which include checks on financial management and capacities. Details of the information organisations are required to provide as part of the Due Diligence process.
- Grants are contracted with RCUK standard T&Cs which include financial management and reporting requirements. In addition, the RCUK-wide Funding Assurance Programme conducts checks at an institutional level (see NERC’s annual report and accounts - http://www.nerc.ac.uk/latest/publications/strategycorporate/annualreport/annualreport/ ).
- Where awards have contracted project partners the NERC contract is with the host institution. The host institution will set up ‘sub-contracts’ with any partner organisation. The host organisation will thus take the financial responsibility of tracking partner spend and the risk of any overspend or default.

Date of last narrative financial report(s)	11/10/2018
Date of last audited annual statement (s)	N/A - NERC is a UK Research Council and part of HMG

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

A light touch review of DFID’s water security research portfolio, including UPGro, was undertaken in 2018. Promising impact areas emerging through UPGro identified in the review centred around: filling critical groundwater data gaps; improving understanding of why water points fail; conceptualising better groundwater management;	groundwater recharge potential of managing road drainage; informing new financing models; and speeding up monitoring of groundwater quality. This more outcome and impact related review complements the NERC led mid-term management oriented review of UPGro programme in 2017, which determined that UPGro is meeting the programme objectives and represents good value for money.

Evidence (1/2 page)

The importance of water security remains unchanged since the initial design of UPGro and the challenges are recognised in the Global Goals. It is reasonable to assume that the benefits of UPGro work will increase over time, as research findings emerge and are taken up by implementing partners. Uptake is being tracked as part of the logframe reporting over the lifetime of the programme. The performance of the consortia and catalyst projects and dissemination of emerging results including some media uptake, awards and use in national planning is demonstrating the quality of UPGro research and interest to key audiences.

The UPGro “Knowledge Exchange Strategy” produced in 2016 is still relevant and frames the work of both the PCG and the Knowledge Broker. The strategy addresses three key activity areas: a) Internal Knowledge Exchange (incorporating science integration and capacity strengthening); b) External Knowledge Exchange, and; c) Data Exchange. The UPGro Ambassadors, and the National Geoscience Data Centre are also key actors in managing UPGro Evidence.

Learning (1/2 page)

The independent water security portfolio review noted above identified some areas of research that could benefit from increased attention in any future programming. These principally related to managing trade-offs between groundwater users (beyond community scale and simply provision of basic services) and how this can play out in different political-economy and economic development contexts. It also observed that while notable progress has been made on enabling improved access to quality data and literature, there is still considerable potential to deepen and expand this.

Investing in partnership can enhance prospects of uptake. The design of the programme and choice of grantees has been successful at creating good south-south and south-north partnerships between researchers and universities and between these academics and wider stakeholders. All five consortium projects engaged with government and civil society from the very beginning and this has led to the uptake of preliminary research findings and methods well before final results are published academically. The Gro for GooD and Hidden Crisis approach illustrate this well where government partners in Kenya and Uganda have been actively part of the co-creation of evidence. The role of the Knowledge Broker has been to help plug some gaps nationally and to support awareness raising at the continental/international level.

Having programme ‘Ambassadors’ can add real value. Having Ambassadors who are senior specialists in government and/or academia is valuable in terms of a “critical friend” role and in catalyzing and exploiting impact opportunities in ways the Knowledge Broker can’t. The earlier they are brought on board, the earlier they can help shape research priorities, design and uptake strategy.

Operationalising truly interdisciplinary research can be hard but is still important. Social and physical sciences – particularly at the fieldwork level – work in different ways and different timescales that can impede effective collaboration., However interdisciplinary research that links groundwater science to social/cultural issues helps makes outputs more relevant to potential users and associated development decision-making. This poses a question for future research programme design regarding the extent to which social science components should be more explicit from the outset and should address economics and risk management/trade-offs.

Catalyst grants can be effective and impactful. For a relatively small investment, some of UPGRO’s grants have seen a great ‘return’– e.g grants concerning TLF monitoring, Remote Sensing, Roads for Recharge etc;

Networks can enable adaptive management. Networks are not just uptake pathways for the static/initial view of envisaged products, but also mechanisms that also allow intelligence gathering for more dynamic and opportunistic adaptive adjustment during implementation. Flexibility in the Knowledge Broker budget and mandate has been important to be able to take advantage of influencing opportunities, drawing in relevant expertise as necessary to capitalise on these.

Attention to enabling environment can be key to Impact trajectory. The Fundifix model experience demonstrates that innovation needs to consider the wider context in which it will be applied, along with potential intervention to help to shape the wider enabling environment. If the Gro for GooD team had not invested time in working with government on the wider enabling environment, then even with the compelling evidence emerging from the Fundifix action-research, the business model would have remained without legal legitimacy in Kenya.

The extensive relationship and partnership building by the programme has achieved some early outcomes and even impacts. However,many deliverables currently in the pipeline are only expected to emerge in 2019/2020. There is a risk is that without support for targeted KB and uptake work for a sufficient period beyond this, the maximum potential won’t be achieved. This should be taken into account in wider and/or future programming such that preferably there would be scope for the partnerships developed under UPGro to be built on for further influencing.

Progress on recommendations from previous reviews (1/2 page)

2017 Recommendation	Progress	Further actions Planned
1. The Knowledge Broker will make the visibility and capacity development of UPGro Early Career Researchers (ECRs) a high priority in 2018, as part of a wider Young Water Professional initiative that is / planned for the Rural Water Supply Network (RWSN). Lead: Knowledge Broker, with on-going review by the PEB.	Good. 2 ECRs presented in RWSN-UPGro webinars in early 2018; 7 presented at the WEDC Conference in Kenya, which included a special UPGro session convened by the Knowledge Broker. A Kenya journalist joined the KB team and interviewed ECRs from across the programme for blog posts, news articles and a forthcoming podcasts.	Having interviewed ECs in Kenya and Ethiopia, it is planned for Isaiah Esipisu to visit T-GroUP and GroFutures ECRs in Tanzania or Ghana. / Encourage ECRs to be active within the new RWSN Young Water Professionals initiative, launched mid 2018.
2. PCG to continue to manage the relationship with the Ambassadors. The role will be discussed with the Ambassadors to work out good win-win plans. Lead: PCG, with regular and on-going review by the PEB.	Good. 3 of the Ambassadors participated in the special meeting held in London around the Ineson Lecture at the end of 2017. In 2018, Dr Tindimugaya presented UPGro at the 1st SADC Groundwater Conference in Johannesburg; Prof. Diene was a tutor in an online RWSN-UNICEF training course on drilling professionalisation. Both have actively supported preparations for Africa Water Week.	The Ambassadors will continue to be needed in 2019 to assist with the follow-up to Africa Water Week 2018, where UPGro is a lead convenor with AMCOW to elevate the status of groundwater in political discourse and priority action.
3. On-going learning from other programmes to strengthen research uptake and participation of southern partners: Continued collaboration with FCFA and REACH in particular, including uptake of the recommendations of the planned review of the impact of the UPGro, REACH and FCFA programmes. Lead: DFID, NERC and KB/PCG..	Good. A full list of interactions is presented in Annex B
4. Based on responses from stakeholders within a NERC-led UPGro mid-programme review: / i. Where possible, the programme secretariat should be the main contact between the projects regarding all aspects of post-award funding queries and if this is not possible, the programme secretariat should be informed on funding assurance and reporting requests so that the secretariat can liaise with the lead project PI and PCG to ensure that all requests are met to deadline. All parties.	Ongoing – The UKRI Funding Assurance Team are working with the Councils and the UKRI International Team (with responsibility for GCRF), liaising with other funders, including Wellcome Trust and DFID, to develop a more harmonised and best practice approach to international funding assurance processes. The UKRI Funding Assurance Team would manage any post-award process. The process should ensure that Council secretariats are informed of any specific grant post-award activity to enable as much support as possible to the overseas organisation and grant holders..
ii. Programme Coordination Group (PCG) to target UPGro ECR group and encourage direct contact between them at the project and programme level. Develop coordinated training for this group as well as those in African organisations. Training plans to be agreed by March 2018. Lead: PCG	Good. An Early Career group was established and has been used by the PCG coordinator and Knowledge Broker to identify interests and needs. This has led to the development of a programme-wide ECR learning event to be held in London in November 2018.
iii. Funders to consider data management of ODA initiatives and large interdisciplinary projects. NERC is currently reviewing its whole data management process and this programme will fall part of the revised process. DFID and NERC. To be reviewed by the PEB.	Ongoing. Restructuring of NERC data centres has mostly been implemented. Including identification of a preferred option for dealing with data from ODA programmes. A data management plan is agreed at grant outset for all NERC-funded/administered projects, including for interdisciplinary projects. This is set out in the NERC data policy and guidance notes; ESRC also have a similar data policy. NERC has also been supporting the development of Google’s dataset search tool, to aid easier access by users.

Annex A Glossary
2iE	An international non-profit association of public utility that has a Headquarters Agreement with Burkina Fas
AfDB	African Development Bank
AfriAlliance	An EU-funded Water & Climate project
AfWA	African Water Association
AfGWNet	African Groundwater Network
AMCOMET	African Ministers’ Conference on Meteorology
AMCOW	African Ministers’ Council on Water
BGR	German Federal Geological Agency
BGS	British Geological Survey
BMZ	German Foreign Ministry
BRACED	Building Resilience and Adaptation to Climate Extremes and Disasters (programme)
CapNet	Network for capacity development in the water sector (part of the United Nations Development Programme)
CARE	International NGO
CGIAR	Consortium of International Agricultural Research Centres
DEIE	Direction Des Etudes Et De L’information Sur L’eau
DFID	Department for International Development
DGIS	Netherlands Ministry for foreign affairs and development cooperation
DMP	Data Management Plan
DRC	Democratic Republic of Congo
DUWASA	Dodoma Urban Water Supply and Sewage Authority
ECR (or EC)	Early Career Researchers
EGU	European Geosciences Union
ESRC	Economic & Social Research Council
EU	European Union
FCFA	Future Climate for Africa (programme)
GCRF	Global Challenges Research Fund
GIZ	German Agency for Development Cooperation
GRACE	Gravity Recovery and Climate Experiment (Satellite programme for measuring gravity anomalies, which can be caused by changes in groundwater storage
GRECHLIM	Groundwater Recharge in the Limpopo River Basin
GRIPP	Groundwater Solutions Initiative for Policy and Practice
GWOPA	Global Water Operators’ Partnerships Alliance (part of UN-Habitat)
HUC	Himalayan University Consortium
HyCRISTAL	A FCFA project
IAEA	International Atomic Energy Agency
IAH	International Association of Hydrogeologists
IM	Impact (Log Frame)
IRC	International NGO
IRD	Institute of Research for Development (French Research Institute)
ISO	International Organisation for Standardisation
ISGEAG	Improving Sustainable Groundwater Exploration with Amended Geophysics
IWMI	International Water Management Institute (part of CGIAR)
IWRM	Integrated Water Resource Management
JMP	Joint Monitoring Programme
KB	Knowledge Broker
LA	Learning Alliance
MWE	Ministry of Water & Environment, Uganda
NERC	Natural Environment Research Council
NGO	Non-Governmental Organisation
ODA	Overseas Development Assistance
PAMACC	Pan African Media Alliance for Climate Change
PCG	Programme Coordination Group (for UPGro) – PIs + KB +PCG Coordinator
PEB	Programme Executive Board (for UPGro) - Funders
PI	Principal Investigator
REACH	Improving Water Security for the Poor (programme)
RIGSS	A GCRF project
RWSN	Rural Water Supply Network
SADC	Southern Africa Development Community
SDC	Swiss Agency for Development and Cooperation
SDG	Sustainable Development Goal
SDI	Slum Dwellers International (International NGO)
SHEAR	Science for Humanitarian Emergencies & Resilience (programme)
SNHR	National Rural Water Supply Service, Democratic Republic of Congo
SNV	Netherlands development organisation (International NGO)
TLF	Tryptophan-like Fluorescence
UCL	University College London
UKRI	United Kingdom Research Institutions (includes all Research Councils)
UMFULA	A FCFA project
UNC	University of North Carolina
UNESCO-IHP	United Nations Educational Scientisic and Culture Organisation – International Hydrological Programme
UNICEF	United Nations Fund for Children
UPGro	Unlocking the Potential of Groundwater for the Poor (programme)
USAID	United States Agency for International Development
WASCAL	West African Science Service Centre on Climate Change and Adapted Land Use – German funded programme
WASH	Water, Sanitation & Hygiene (also known as WaSH)
WEDC	Water, Engineering & Development Centre, Loughborough University
WHO	World Health Organisation

## Annex B
### UPGro, FCFA and REACH and other DFID, NERC, ESRC programmes
UPGro Project	Other	Details
Knowledge Broker	FCFA, REACH, SHEAR	In 2018 there were 2 online between UPGro, FCFA, REACH and SHEAR on knowledge management and brokering and a face-to-face meeting at the Adaptation Futures conference in South Africa for those attending. / The
Knowledge Broker	FCFA, REACH	There has been correspondence around Africa Water Week, which is a high priority for UPGro, but not for REACH and FCFA decided to convene a separate session because their emphasis and objectives are different.
Knowledge Broker	REACH	The Knowledge Broker pulled together findings from UPGro and REACH into a poster[16] that was presented at the 2018 AGUASAN Workshop, the annual thematic conference of the Swiss global water sector (http://www.aguasan.ch/)
BRAVE	FCFA HyCRISTAL	Through shared investigators, BRAVE’s groundwater modelling, KE learning platforms and social science approaches are being applied between the Sahel and Lake Victoria Basin. Partnership work with government agencies common to both programmes is benefitting from more nuanced understanding of the political economy in both regions.
T-GroUP	FCFA HyCRISTAL	HyCRISTAL: In Uganda, Makerere University actively work together with HYCristal partners in the UK to collect data in the Libigi catchment, whereby the groundwater monitoring network which was developed by T-GroUP, is used by HyCRISTAL for additional data collection. This involves joint data collection and analysis of groundwater quality and water levels Through this collaboration, the two consortiums are also working together to understand and model the impact of climate change on springs in a selected catchment in Uganda. The T-group project participated and contributed to the 3rd HyCRISTAL annual general meeting (24 – 26 April 2018).
GroFutures	FCFA UMFULA / FCFA HyCRISTAL	GroFutures is well linked to two of the consortium projects under the Future Climate for Africa programme, UMFULA and HyCRISTAL, which feature allied scientists (GroFutures/UMFULA; GroFutures/HyCRISTAL). This year, direct research engagement resulted in the completion of a research paper assessing the contrasting impacts of ENSO on groundwater storage in the Limpopo Basin of South Africa and the Makutapora Basin of central Tanzania that involves UMFULA/GroFutures, UMFULA, GroFutures, and GroFutures/HyCRISTAL.
Gro for GooD	REACH	REACH climate scientist has discussed opportunities to link ongoing rainfall risk analysis in Turkana, Kenya, with the multi-decadal rainfall data collated under Gro for Good. This would be a collaboration with JKUAT and link to the wider FCFA modelling work in East Africa which is supporting in her new role across REACH/FCFA with Reading University and the Met Office.
GroFutures, Hidden Crisis	REACH	At a meeting hosted by Oxford University on 16th July 2018, GroFutures (and Hidden Crisis) agreed to collaborate and share results and data with REACH in the Awash Basin of Ethiopia where all three consortia have active research programmes. Specific lines of collaboration include: / • development of groundwater development scenarios: comparative review of procedures for quantifying development pathways; / • characterisation of groundwater users: potential comparison of evidence collected from household questionnaires and PRA (focus-groups discussions); / • climate change impacts on terrestrial water balances: opportunity to share methods and models for quantifying climate change impacts on water resources using WEAP under REACH and MIKE-SHE by GroFutures; / • climate change scenarios: opportunity to review the identification of GCMs/ESMs to be used in climate change analyses; and / • hosting an integrated, joint workshop (late 2019?) with key stakeholder, the Awash Basin Authority / A joint publication on groundwater in the Upper Awash is being prepared between REACH, UPGRO Hidden Crisis and UPGRO GroFutures combining datasets and research from the three projects. The three projects have agreed to work together, sharing data and information for the Upper awash.
Hidden Crisis	REACH	Tryptophan Sensors bought with a capital grant from UPGro as part of the Hidden Crisis project are being used on the REACH programme in Malawi, Kenya and Bangladesh – and training was provided
Hidden Crisis	FCFA HyCRISTAL	Tryptophan Sensors bought with a capital grant from UPGro as part of the Hidden Crisis project are being used on the REACH programme in Malawi, Kenya and Bangladesh – and training was provided
[16] http://www.rural-water-supply.net/en/resources/details/812

### UPGro links to other DFID, NERC, ESRC programmes
UPGro Project	Other	Details
BRAVE	IDAPS	Newly funded NERC grant “IDAPS – Integrated Data Platform for African Policymakers” (http://www.walker.ac.uk/news-events/connecting-policymakers-with-rural-communities-to-support-long-term-decision-making/) led by the Walker Institute is developing methods to integrate groundwater information with livelihoods and climate data. This approach may well be translated for the inclusion of the groundwater information on the RAINWATCH platform.
BRAVE	BRACED	The BRAVE team has been subcontracted to conduct work for the BRACED project, to support their delivery of a number of key objectives. Crucially, it enables BRAVE to extend groundwater monitoring to 2 additional communities in Burkina Faso and pilot the new vulnerability indices in additional these additional communities and draw comparisons.
BRAVE	ASPIRE	Investigators work on BRAVE as well as the DfID funded, People Centred Climate Service in the Sahel (see http://www.walker.ac.uk/projects/people-centered-climate-services-in-the-sahel/ ) focusing on Adaptive Social Protection Project, ASPIRE – the vulnerability indices, shared geographies, and ongoing development of RAINWATCH to include the groundwater monitoring could be usefully extended to ASPIRE.
BRAVE	NERC/BGS ODA-National Capability Programme	Hydrogeological conceptual understanding of crystalline basement aquifers being developed within the NERC-funded BGS ODA-National Capability Programme and the subsequent modelling undertaken using this conceptualisation is using data from Northern Ghana as validation and is linking with the BRAVE project.
Gro for GooD	GCRF	RH from Oxford University is a member of the Expert International Development Group (EIDEG) for ESRC’s GCRF panel. He provides input and guidance from UPGro, REACH and ESRC/DFID poverty programmes on funding priorities and gaps, and reflections on suitable funding modalities across different geographies, themes and partnership networks.
Hidden Crisis	NERC El Niño	The joint social and physical survey methods developed in the Hidden Crisis project in Ethiopia are being used by a project within the NERC El Nino programme to investigated water-point failure during drought in the Ethiopian Highlands
Hidden Crisis	GCRF RIGGS	The hidden crisis rural survey techniques have been used to inform an GCRF Building Resilience Catalyst project (RIGGS) in urban Nigeria
Hidden Crisis	AfriWatSan	Tryptophan Sensors bought with a capital grant from UPGro as part of the Hidden Crisis project are being used by AfriWatsan (royal Society/DFID) in Uganda Kenya and Dakar.

### Links and use of UPGro research/researchers in other programmes
UPGro Project	Other	Details
Knowledge Broker	RWSN/UNICEF/ CapNet	The UPGro Knowledge Broker team ran an online course on “Drilling Professionalisation” for UNICEF country staff and other development professionals. An UPGro Ambassador was one of the course leaders. Full report available on the RWSN website[17].
BRAVE	WASCAL	BRAVE has very close ties with the German Govt-funded WASCAL Programme (West African Science Service Centre on Climate Change and Adapted Land Use) – see Highlights above. This is a large-scale research-focused Climate Service Centre Programme designed to enhance the resilience of human and environmental systems to climate change and increased variability. It does so by strengthening the research infrastructure and capacity in West Africa related to climate change and by pooling the expertise of ten West African countries and Germany.
BRAVE	WaterAid	BRAVE is also liaising with WaterAid Regional Learning Centre For Water Resources Management, West Africa on their programme on community management of groundwater resources.
BRAVE	IWMI	Advice on initiating the economic argument for groundwater use has been provided from an IWMI expert based at the Accra office who has researched extensively in the economics and management of groundwater resources, including in northern Ghana. BRAVE will add value to the existing work that focuses on the economic debate about the role of groundwater for agricultural resilience. This will be supported by the KB consultant.
Gro for GooD	USAID SWS	Oxford University is a partner in USAID’s Sustainable WASH Systems Learning Partnership (2016-21) with evidence from the Gro for GooD programme informing the global learning network. On August 23rd, the UPGro PI drew on work at the Gro for GooD study site in Kwale County during his presentation in a USAID webinar on Preventative Maintenance Models. This event reached an international audience of over 100 participants including representatives from the World Bank.
GroFutures	IWMI Water, Land & Ecosystems	GroFutures work is linked to and supported by the IWMI-led CGIAR Research programmes: Water, Land & Ecosystems. It is also aligned with the IWMI-led partnership initiative Groundwater Solutions Initiative for Policy and Practice (GRIPP) through the direct co-participation of the Principal Researcher at IWMI, co-PI GroFutures, and Coordinator of GRIPP. This work is further pursued as part of a new Project funded by Danida, ESGUSA (Enhancing Sustainable Groundwater Use in South Africa).
GroFutures	USAID GRECHLIM	GroFutures work is also linked to the USAID-funded GRECHLIM (Groundwater Recharge in the Limpopo River Basin) Project, led by IWMI. The project works to understand recharge dynamics in prevalent, but not very productive aquifers in the Limpopo basin, where climate change and economic development puts high pressure on water resources, including groundwater. Understanding renewability of groundwater and the relationship with rainfall variability at various timescales is critical for sustainable use and management of the resource.
T-GroUP	SNV	In Arusha, SNV (Netherlands Development Organisation) is entering the Learning Alliance. This large international NGO is at the start of a 5 year action research programme funded by the Dutch DGIS on city wide sanitation. In their view, the Learning Alliance can be an important entry point or stepping stone for getting on-board the most important water actors in Arusha.
T-GroUP	World Bank WIRES	In Arusha, knowledge generated from the T-GroUP project is directly used in the World Bank funded capacity program called Centers of Excellence. More specifically, NM-AIST, which is part of the T-GroUP consortium, operates one of the Centers of Excellence on Water and Energy (WIRES). WIRES is currently in the process of establishing an MSc degree in Hydrogeology, whereby Arusha is not only an important case, but also, an important part of the students are employees of groundwater stakeholders in the Arusha area.
Hidden Crisis	IWMI GRIPP	Building on BGS’s involvement in three UPGro consortium projects they accepted an invitation by IMWI to become part of GRIPP, and develop case studies for publication by GRIPP from the UPGro work.
[17] http://www.rural-water-supply.net/en/resources/details/814

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided