Type of Review: Annual Review

Project Title: UPGro – Unlocking the potential of groundwater for the poor in Africa

Date started: March 2012	Date review undertaken: April 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £8million over seven years (2012-2019) for a programme of knowledge, research and innovation that will improve access to and management of groundwater resources in Sub-Saharan Africa. The UPGro Programme (Unlocking the potential of groundwater for the poor in Africa) is a partnership with NERC (the Natural Environment Research Council) and ESRC (the Economic and Social Research Council), each of whom are providing £2million towards a total programme of £12million. The Research Councils also contribute in-kind resources and systems to competitively commission and manage the mix of research required.
What are the expected results?
The expected impact is that more sustainably managed groundwater resources support increased water security for poor people in Africa. UPGro will deliver the knowledge and information required to better access and manage Africa’s groundwater resources to enhance water security for around 10 million people currently without access to improved water supplies in sub-Saharan Africa, and maximise the potential role groundwater can play in Africa’s economic development, including agriculture (which contributes to approximately 20 % of GDP in Africa). / The outcome expected from the project is robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa. All research supported will demonstrate that the outputs can be used by policy makers and other stakeholders to inform decisions on the access to and management of groundwater in Africa. This focus on how research will be taken up is hard wired into the application and reporting processes and the NERC secretariat will play a key role in ensuring that this aspect is delivered well. Specific areas include: / Targeted groundwater research will help improve the value for money of investments in groundwater drilling as the poor siting of wells and boreholes (primarily linked to poor data/information on the resource itself) increases the unit cost of successful boreholes. / Strengthening of the data set on existing resource quality and quantity will provide an important baseline for future analysis of the impact of longer term trends which need to be based on long term data sets for proper analysis and adjustment of response mechanisms in the future. / Researchers and research institutions in developing countries will benefit from capacity building which will be a core component of the programme through participation in research with Universities and other research institutions and/or leading the research itself. Local networks and institutions will be key partners in delivering the research and considering how best to implement the findings into policy. / What are the outputs that can be attributed to the UK? / UPGro will deliver high quality research across the social and physical sciences which will provide an increased data set for groundwater. Specifically, UPGRO will deliver: / at least two freely available, online groundwater atlases (one physical and one social/economic) and the underlying data sets of the groundwater resources in critical areas of sub Saharan Africa - in terms of quantity, quality, accessibility, unit costs, risk management and long term sustainability; / at least 70 peer reviewed articles that fill critical evidence gaps in: / the physical science: issues of groundwater recharge, interactions between groundwater and surface water, groundwater quality; / socio-economic aspects: questions of access (who and how), inequality, management, regulation, incentives; / impact of future drivers and stressors, such as climate variability, urbanisation, population growth, agricultural intensification; / improved hydrogeological research capacity in Africa coupled with skills in communicating science into policy.

What is the context in which UK support is provided?
Water resources are critical to economic growth and social development. A recent study on groundwater in Africa has shown that there is possibly 20 times more water available as groundwater compared with that available in lakes and rivers[1]. Groundwater provides most of the domestic water supply in parts of rural Africa and supports poverty reduction through access to clean drinking water and irrigation[2]. It is estimated that groundwater provides water for domestic supplies and livestock for more than 100 million people and is the source of drinking water for 75% of Africa’s population (although this varies in proportion by country/sub-region)[3]. Only 19 of the 50 countries in Sub-Saharan Africa (SSA) are on track to meet the UN Millennium Development Goals target for drinking-water provision. Groundwater has the potential to provide an improved source of drinking water for those in SSA who are currently without access. It is also often naturally protected from contamination, so is generally of good quality and needs no treatment. / However, groundwater is under pressure in many parts of Africa and in some cases is being abstracted faster than it can be replenished. Water withdrawal for agriculture is generally the most water-intensive productive/economic activity, although use in SSA varies by region (e.g. 90-95% in GHA and Sahelian regions, 75-80% in east Africa region) [4] . Demand for irrigation is increasing[5] and linked to agricultural growth and intensification which will be needed to ensure food security for the rapidly growing world population in the face of climate change. Water is also central to most industries and a vital commodity for tourism, both of which are important sources of income for many African countries. / Groundwater sources are often resistant to drought and act as a natural buffer against rainfall variability. Groundwater is therefore used as a flexible resource to provide on-going water availability when surface sources dry out, with little regard for sustainability. Droughts are also a significant cause of humanitarian disaster in SSA, often leading to mass population movements and considerable health, social and economic stress on many developing nations. Groundwater is also one of the preferred options for the provision of water supplies for refugee camps[6]. These humanitarian disasters are likely to grow in scale as populations grow and climate and land use change accelerate. / With these increasing pressures on water resources, the potential pressure on groundwater as the solution to the water security challenge in SSA is high. As the population grows, water security in SSA will become increasingly important and demands on groundwater are likely to surge. Poorly managed water resources will constrain opportunities for development, including better services and livelihoods for poor people. Despite the importance of groundwater in meeting water security needs for poor communities in Africa, there remain big challenges to realise this potential, including substantial knowledge gaps[7]. Key questions are: / •Where is the groundwater, how and at what rate is it recharged, and how can it be more effectively and efficiently abstracted to meet local needs? / •What management and institutional arrangements are needed to support this access in an inclusive and sustainable way, in particular to reach the poorest and most marginalised groups? / •What is the state of the resource - quality and quantity - and how will it respond to future trends in abstraction, impact of growing population, climate change etc.? / Without addressing some of these core gaps in the evidence and data, it will be hard to identify and manage the full implications of increased groundwater use. Abstraction of groundwater could accelerate out of control and bring with it some of the harm experienced in other regions. The sinking of bore holes is likely to remain ad-hoc and costly without data to help guide their placement and management of how much can be extracted, so the likelihood remains that boreholes and hand-pumps may fail after limited use. / UPGro will fund high quality environmental and social research to address these issues. The programme aims to deliver robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa. All research supported will deliver outputs that can be used by policy makers and other stakeholders to inform decisions on the access to and management of groundwater in Africa.
[1] MacDonald et al. 2012. Quantitative maps of groundwater resources in Africa. Environ. Res. Lett. 7. 024009
[2] Hunter et al. 2010. Water Supply and Health PLoS Med7 (11): e1000361
[3] UNECA African Climate Policy Centre 2011 Management of Groundwater in Africa including transboundary aquifers: Implications for meeting MDGs, livelihoods goals and climate change adaptation. Working Paper Number 6.
[4] http://www.fao.org/nr/water/aquastat/data/query/index.html?lang=en
[5] S. Siebert, J. Burke, J. M. Faures, K. Frenken, J. Hoogeveen, P. D¨oll, and F. T. Portmann (2010) Groundwater use for irrigation – a global inventory (Hydrol. Earth Syst. Sci., 14, 1863–1880, 2010 www.hydrol-earth-syst-sci.net/14/1863/2010/ doi:10.5194/hess-14-1863-2010)
[6] Tuinhof, A; Foster, S; van Steenbergen, F; Talbi, A and Wishart, A (2011) Appropriate Groundwater Management Policy for Sub-Saharan Africa in face of demographic pressure and climatic variability. World Bank GW MATE Strategic Overview Series Number 5
[7] MacDonald AM, Bonsor HC, Calow RC, Taylor RG, Lapworth DJ, Maurice L, Tucker J and Ó Dochartaigh BÉ. 2011. Groundwater resilience to climate change in Africa. British Geological Survey Open Report, OR/11/031. 25 pp.

## Section A: Detailed Output Scoring

Output 1: Improved groundwater data in priority areas of SSA in terms of quantity, quality, accessibility, unit costs, risk management and long term sustainability
Output 1 score and performance description: A / The LF has three indicators: i) Number of up to date (post 2012) quality groundwater data sets (available, withdrawal etc) produced for SSA countries and freely available online and in other sources; ii) Cumulative number of peer reviewed articles, working papers and policy briefs published on issues of groundwater science; iii) Uptake of data generated as measured by references in conference proceedings / The first milestones were set for 2014 at 0, 5 and 2 respectively.
Progress against expected results: / Although this Business Case was approved November 2012, The UPGro MoU was not signed until April 2013 due to negotiations around the specifics of the contracting process for baseline studies. There has therefore been a significant slippage to the schedule as set out in the Business Case and the programme is still at a very early stage. / This output relates to the first of three research themes. Despite delays outlined above, progress on this output is reasonable and the programme is now on target for meeting the initial milestones in 2014. A baseline study to develop a groundwater atlas for Africa is underway with a dedicated post created at British Geological Survey (BGS) to manage the work. A web database structure has been developed for storing the reports and publications, which includes functionality for georeferencing, detailed QA and copyright trails, keywords searches, and different languages. Appropriate BGS data holdings have also been identified and digitised, with 4000 records available so far for Africa. A subcontract has been set up with UCL to digitise and QA some Ugandan datasets. The atlas will be available online (trials are underway with Media Wiki to test functionality and form) and as a publication (Initial discussions have taken place with IAH and CRC Press, and have proved positive. A formalised case will be presented later this FY). / A call for proposals for catalysts grants has also been carried out, with 15 grants now funded. The grants were required to start by the end of July 2013 and the majority achieved this. The aim was to provide small amounts of funding to develop new methodologies, metrics and tools or undertake pilot studies that will be available to the large research consortia, which are expected to deliver the bulk of UPGro research. The catalyst projects will run for one year so results and publications are likely to appear over the following year from July 2014. The main global competitive call for outline proposals for the large multidisciplinary research consortia is due to be issued by the end of 2013, with work ultimately expected to start by end January 2015. / Recommendations: The slippage from the timings set out in the business case has implications for both spend profile and achievement of milestones for log frame outputs (particularly milestone 2 which is dependent on initial results emerging from the main research consortia). The PEB should meet to amend and tighten up the log-frame milestones now the programme is underway. Spend profiles and schedule has been adjusted to reflect the start-up delays as part of the Annual Review. / Impact Weighting (%):25 / Revised since last Annual Review? n/a / This is the first AR. / Risk: Low / Revised since last Annual Review? N / This is the first AR. There is no reason to change the risk at this stage.

Output 2: Improved understanding of monitoring and management (including social and economic) systems needed to manage groundwater systems sustainably
Output 2 score and performance description: A / The LF has three indicators for this output: i) Cumulative no of peer reviewed articles, working papers, policy briefs etc on understanding of socio economic opportunities and constraints to sustainable groundwater management; ii) Number of new or improved tools/frameworks/ diagnostics for groundwater management (including physical and social components) tested for application in SSA; iii) Cumulative number of peer reviewed research outputs that specifically address gender and other issues of equality, access and voice. / The first milestones were set for 2014 at 5, 2 and 3 respectively.
Progress against expected results: / This output relates to the second of the three research themes so implications relating to slippage in the Business Case schedule, as outlined for Output 1, apply here also. The projects under catalyst grants are spread across all 3 research themes and the programme should meet initial 2014 milestones for indicators 3.i and 3.ii when results start to emerge next year. However, the catalyst grant projects focus strongly on physical/natural science rather than social science aspects. The call for catalyst grants was successful in attracting high quality bids but did not attract strong proposals focussing on the social, economic or humanities side. It is also not clear at this stage whether the gender indicator 3.iii will be met for 2014 since there are no catalyst grants specifically focusing on gender, equity or voice. ESRC has now agreed that its International Development Team will represent ESRC on the PEB. The identification of a clear lead together with lessons learnt from the catalyst grant call will ensure that socials aspects of research are more explicitly addressed in the main call for research consortia. / The business case originally envisaged that a baseline study would be commissioned in the first year to develop a Social-economic atlas that would sit alongside the Groundwater Atlas as a resource for the main research consortia. Initial scoping suggested that much of the work anticipated was already available and the original proposal was modified to a literature review to bring this together in a form that would be useful for UPGro. This work has not yet been commissioned although ToRs were developed. / Recommendations: The lack of social science led proposals for the catalyst grants highlights the need for a more proactive, targeted approach with the main call for research consortia. The PEB should ensure that the Knowledge Broker (now in place subject to signing contract this week) takes a lead role on this once the Announcement of Opportunity (the call for main research consortia) is published, working together with ESRC to utilise their networks and external partners in a more proactive approach. / The Knowledge Broker should also start to liaise with researchers working on catalyst grants to ensure that sufficient focus is given to key cross-cutting issues such as gender and equity over the next 6 months. It has also been agreed that a workshop will be held for shortlisted bidders for the main call for research consortia to ensure these issues are more integral to proposals and that there is a clear understanding of requirements and expectations of future UPGro research. / There is a risk that indicator number 2.ii provides a perverse incentive for developing new frameworks/toolkits rather than taking a more integrated approach, and experience with ESPA has been cited as an example. However, this will be managed as research consortia are commissioned through the structures that are now set up to ensure programme integration. At this stage it was agreed that milestones are set relatively low so this is not considered a major risk and can be revisited in future reviews as research findings emerge. / Since the Social-economic baseline study has not yet been commissioned, results will not be available to inform the preparation of proposals as originally anticipated. DFID, NERC and ESRC have therefore agreed to postpone this component now until the main research consortia are commissioned. ESRC argued strongly that this would be more likely to provide value for money given the potential breadth of social issues which could be considered at this stage. Commissioning this activity alongside the initial work of the main research consortia will promote programme coherence and value for money by avoiding duplication, enable the work to target specific areas of UPGro focus and identify potential critical gaps at this stage. / Impact Weighting (%):25 / Revised since last Annual Review? N / This is the first AR. / Risk: Low / Revised since last Annual Review? N / This is the first AR.

Output 3: Better understanding of impacts of longer term trends and response mechanisms which work to support groundwater use in Africa.
Output 3 score and performance description: A / The draft LF has three indicators for this output: i) Cumulative number of peer reviewed articles, working papers and policy briefs published on impact of long term trends, eg. socio economic stressors and drives such as migration and physical stressors such as climate variability.; ii) Cumulative number of peer reviewed articles, working papers and policy briefs published on socio economic and physical responses to long term trends; and iii) Number of policy events where UpGRO research on trends is referenced / The first milestones were set for 2014 at 5, 3 and 0 respectively.
Progress against expected results: / This output relates to the third of the three research themes so implications relating to slippage in the Business Case schedule, as outlined for Output 1 & 2, apply here also. Also as above, the range of catalyst grant projects which are looking at impacts of long term trends should ensure the first milestones are met next year. / Recommendations: The recommendation under output 2 to make sure that the focus on social and economic research is increased in proposals received under the main call for research consortia applies here also and is perhaps most critical for this output. Social and economic factors are likely to be as, if not more, important than physical drivers in understanding long term trends. ESRCs input to the main call for research consortia and the workshop proposed for short listed bidders will be critical. / UPGro is intended to stimulate multidisciplinary research that cuts across the three programme themes and includes social and natural sciences. The log-frame outputs are however structured with milestones for each theme and this may present issues with double counting or overlap in monitoring programme achievements in the future. This will need to be considered more carefully in future reviews once results start to emerge. / Impact Weighting (%): 25 / Revised since last Annual Review? N / The project is at too early a stage to make revisions to the impact weightings. / Risk: Medium / Revised since last Annual Review? N / This is the first AR and the project is not yet at a stage when it is appropriate to review this risk rating.

Output 4: Improved hydrogeological capacity in Africa coupled with skills in communicating science into policy
Output 4 score and performance description: A / The draft LF has three indicators for this output: i) Proportion of UpGRO researchers from African / other LD Countries communicating research findings to policy makers at workshops/policy events; ii) Proportion of institutions successfully accessing UpGRO funding coming from Africa and/or developing countries; and iii) Proportion of high quality UpGRO policy relevant research produced and published by southern partners in international journals / The first milestones were set for 2014 at 0, 20% and 10% respectively.
Progress against expected results: / It is too early to make an assessment against this output, given the slippage in the start date and since the main call for research consortia is still in progress. However, the Announcement of Opportunity for outline proposals makes it clear that capacity building of African consortia partners and stakeholders in sub-Saharan Africa must be central for a successful bid. The Pathway of Impact section in the proposals is required to set out a clear strategy for this. This was not an express requirement for the catalyst grants but out of 16 institutes receiving funding in this round, there are 3 African leads and others have African co-investigators. This gives a likely value for indicator 4.ii of 18.75% in 2014 based on leads only and in total should exceed the 20% milestone. / Recommendation: The knowledge broker will need to liaise with catalyst grant researchers over the next 6 months to ensure that southern partners are encouraged to lead on publishing research if milestone 4.iii is to be met. / Impact Weighting (%): 15 / Revised since last Annual Review? N / The project is at too early a stage to make revisions to the impact weightings. / Risk: Medium / Revised since last Annual Review? N / This is the first AR and the project is not yet at a stage when it is appropriate to review this risk rating.

Output 5: Effective management of the research programme, including M&E of impact and value for money
Output 3 score and performance description: A / The draft LF has three indicators for this output: i) Number of recommendations by Independent Advisory Group leading to measures taken to improve programme; ii) % of research projects with of research into use pathways/VFM statements/independent evaluations which illustrate action to improve VFM / The first milestones were set for 2014 at 2 and 60% respectively.
Progress against expected results: / It is too early to make an assessment against this output, since the independent advisory group has not yet been appointed and research under catalyst grants is at an early stage. All research programmes under the main call will need to have research into use pathways but it will important to at the quality of these statements and progress in terms of delivery. / Recommendation: This output should be discussed with programme partners, the knowledge broker and programme integration group once the main consortia are appointed. It may be possible to agree better value for money indicators that capture the coherence and management of the UPGro programme as a whole once the shape of the main research programme is clearer. It is recommended that this is considered at the next annual review. / Impact Weighting (%): 10 / Revised since last Annual Review? N / The project is at too early a stage to make revisions to the impact weightings. / Risk: Medium / Revised since last Annual Review? N / This is the first AR and the project is not yet at a stage when it is appropriate to review this risk rating.

## Section B: Results and Value for Money.

h
1.1 Has the logframe been updated since last review? No. / It is a key recommendation of this Annual Review that the PEB and newly installed knowledge broker meet to revise and tighten milestones in the logframe in early 2014. The logframe may need to be revisited once again after the main research consortia have been contracted and completed an initial inception stage – when there will be a clearer picture of the overall shape and balance of the research that UPGro will generate. / 1.2 Overall Output Score and Description: A / The project is at an early stage in its implementation with the main competitive call not yet issued. It is difficult to make any objective assessment of overall performance except that a review of the systems and process used indicate that these are appropriate and robust and that the project is now on track. / 1.3 Direct feedback from beneficiaries / At this stage the project is not expected to obtain direct feedback from beneficiaries. Bidders for the main research consortia will be expected to identify stakeholders and ultimate users of research and are required to ensure voice/demand is factored into research proposals and focus.
1.4 Summary of overall progress / There was a significant delay in start-up of the programme and use of NERC funds has meant that proposed DFID disbursement has been slower than anticipated. Some milestones have not yet been met, but this would not have been expected until early next year. However, the key decisions have now been made and appropriate structures and processes are in place so that the programme will now to pick up pace and deliver results.as expected. Competitive calls have been handled efficiently so far and management has benefitted from NERC’s experience of managing similar programmes. The main call for research consortia is underway and progressing well. It is expected that contracts for successful consortia will be issued towards the end of 2014 and that work will begin in January 2015. For this reason the programme has been rated overall as an A (meeting expectations).
1.5 Key challenges / Again it is important to stress that the programme is still at too early a stage to be making significant assessments. However, a number of challenges are emerging. These reflect both challenges identified in the business case appraisals and also DFID/NERC’s wider experience of managing large research programmes of this type. / Generating profile to attract sufficient high quality and truly interdisciplinary proposals. Feedback has implied that there was a perceived low profile for the UPGro Programme with the call for catalyst grants. There were no social science led proposals despite an emphasis on this in the call. In addition, only one application was received for the Knowledge Broker role. Possible reasons for this were insufficient publicity and lack of clarity about NERC funding rules – it will be critical to address these issues for the main call for research consortia. In terms of publicity, adverts were placed through NERC’s usual channels perhaps missing the normal development partners. On funding, under RCUK rules - for UK institutions only 80% of Full Economic Cost (FEC) is funded through NERC with eligible institutions, e.g. universities, able to claim remaining 20% from the Higher Education Funding Council for England (HEFCE) or devolved equivalents. UK institutions not eligible for RCUK funding, e.g. Met Office or ODI, are expected to find the additional 20% from other sources, which may be a barrier to applying in some cases. Overseas organisations, e.g. African institutions, are eligible to apply for 100% of the Full Economic Cost. / Recommendations: / Knowledge Broker and ESRC to take a proactive role in identifying networks/ potential partners to help raise the profile of the main call and to shift focus to attract participation of more social science institutions. / NERC to confirm how the FEC funding issue is addressed within other DFID programmes such as EPSA and ensure options are made clear in main call. This issue will be easily resolved as with other programmes. / Ensuring the programme is more than a sum of its parts. The Knowledge Broker role is intended to work with researchers funded through UPGro to ensure effective coordination across projects and dissemination of outputs. It will also aim to ensure that the programme maximises its impact through connecting and communicating with relevant users. However, there is a gap between capacity of the Secretariat to oversee the Programme and the Knowledge Broker role of focussing on research into use. A mechanism will be required to ensure that individual project partners or consortia to come together on a systematic basis to share methods, exchange knowledge and learn lessons effectively. This needs to be made explicit under the main call for research consortia. / Recommendation: / NERC to withhold a small proportion of funds from the call for research consortia to allow a representative from each consortium to sit on a Programme Integration Group which will be the formal interface between the research consortia and Knowledge Broker and external advisory group. This model is often used by NERC and has been approved at the PEB in November 2013. / Tracking impact and value for money. The knowledge broker role will be key in developing a clear theory of change for the UPGro programme as a whole and ensuring that information required to track outcomes and impacts is collected. There is also a clear need to ensure that women and girls are properly considered in research plans and that this goes beyond basic data disaggregation by gender and includes, where appropriate, work specifically focused on gender issues. / Recommendation: / DFID and Declan Conway (Independent Chair to PEB) to meet with Knowledge Broker team once contracts have been signed to discuss value for money approach and DFID expectations on monitoring and evaluation. / Funding Partners to hold a workshop for shortlisted bidders between outline proposal and full bid stage to discuss priorities of the programme, including gender, research capacity development, value for money and impact assessment, to facilitate the effective use of tools and methods in proposals. / Maintaining momentum with staff changes. There has been a considerable flux in staff across funding partners, including DFID. The role of the ESRC programme lead will be critical if UPGro is to ensure the envisaged focus on social sciences, Craig Bardsley (Head of International Development) has recently taken over as the ESRC lead, which will hopefully address this issue. The NERC lead Ned Garnett (Head of Atmospheric and Polar Sciences) will hand over to Ruth Kelman (Head of Freshwater Sciences), but NERC are managing this transition with a long handover period to ensure continuity. Lizzie Jones will replace Jess Surma as the NERC Senior Science Programmes Officer on the programme when Jess goes on maternity leave in the New Year. It will also be important to ensure that calls continue to be issued in a timely fashion so that the programme does not fall further behind schedule and the disbursement of funds remains on target.
1.6 Annual Outcome Assessment / It is too early to make any assessment of progress in terms of outcomes. The assessment of the review team is that the project is now on track, but that it is very early days in terms of an outcome assessment.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / No. Delay in start-up and a requirement from NERC to use its £2 million contribution in the 2013/14 financial year means that disbursement of DFID funds has not yet started. NERC has provided revised schedules for DFID spend and these are now reflected in the CET’s financial forecasts. Overall the programme is on track. Expected spend for financial year 2013/14 was: £2.34million and anticipated actual spend is £1.62 million (although this includes 1 quarters payment to Knowledge Broker which is yet to be confirmed). The following profile has been agreed to ensure funds from all partners are prioritised equally in future years but should be reviewed at next PEB meeting since it is based on a number of assumptions. / Pre-2013 2013/14 Actual 2014/15 2015/16 2016/17 2017/18 2018/19 2019/20 2020/21 Total All Years £million / NERC (257) 1,610,492 0 0 0 100,000 165,000 90,000 35,000 2 / DFID 0 0 940,000 2,175,000 2,000,000 1,800,000 1,085,000 0 0 8 / ESRC 0 0 0 500,000 600,000 900,000 0 0 2 / (257) 1,610,492 940,000 2,175,000 2,500,000 2,500,000 2,150,000 90,000 35,000 12 / 2.2 Key cost drivers / Key cost drivers are expected to be researcher costs (salaries and associated expenses) and travel and subsistence costs related to implementing the individual projects. Given the stage of the project, these are not yet identifiable in any detail. However costs proposed in individual project bids (submitted as part of the competition process) will be scrutinised against benchmarks available to NERC/ESRC and DFID. / Programme Management costs are expected to be around 4% for the entire project, but are provided in the large part (i.e. cost of secretariat) as a payment in kind by NERC in addition to NERC’s £2m financial contribution.. Overhead costs should be considered in more detail at the next annual review when contracts are signed and rates/overheads for the main research consortia will be known. / 2.3 Is the project on-track against original timescale: N / There has been some slippage against the original schedule as set out in the Business Case. This was due to delays in signing the MoU and an overambitious expectation for the first year. A breakdown of the revised schedule is summarised below. Against this revised schedule, the project is where expected it to be at this point in the calendar year. Financially the project is on track with what was laid out in the Business Case and the MOU between DFID and NERC. NERC has proved to be flexible when dealing with funding arrangements or changes that DFID has requested and DFID has confidence in the financial management of the project. / Overview of the procedure: First stage: preliminary application / Baseline Study – GroundWater Atlas / Catalyst Grants (1 year) / Baseline Study – Socio Economic Literature review and datasets (6 months) Commissioned June 2013 / Started July 2013 / To be postponed until start of main consortia / Second stage: full application / Main Research Consortia (4 years) / Outline Proposal / Full Proposal / Start date / Future Calls 2015-2019 / By March 2014 / Autumn 2014 / Prior to 31st Jan 2015 / 2016/17

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / At this stage there is no change in the evidence and implications for the project. / 3.2 Where an evaluation is planned what progress has been made? / No formal evaluation is planned although an independent review is scheduled for around the mid-point of the programme.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / Key risks, derived principally from the Business case risk assessment are presented below, along with an assessment of the current status / Risk Probability Impact How risks will be minimized/mitigated (including who responsibility for mitigating action is assigned to) / Management Risks / Funding leaks to unsound institutions Low High No change to risk status. Adherence to NERC terms and conditions. / Knowledge of institutions by Independent Advisory Group members; proposal assessors, etc. / Too few Southern bid leaders Mod Mod No change to risk status Publicity through networks of partners; wide advertising; call open for significant length of time / Dedicated support in the application process, / Ongoing learning process to strengthen support in subsequent calls, including from other programmes like ESPA / Southern partners not involved in partnerships in a meaningful way Mod Mod No change to risk status Key assessment criteria to incorporate equity and other relevant concerns, and verified throughout / Research Risks / Poor quality research funded Low High No change to risk status Clear assessment criteria and process / Quality a key criteria for project selection / Research findings too disparate to ‘add up’ to anything Low High No change to risk status – main call not yet issued. Dedicated resources set aside for further calls to target gaps and emerging priorities. Funds held back for integration across consortia. / Synthesis and knowledge management key function of Knowledge Broker. / Research funded does not have any discernible impact on policy makers. Mod High No change to risk status at this early stage. The need for research to generate usable and relevant outputs will be clearly stated in the assessment criteria / Detailed impact plan required for each project funded / Peer reviewers and panel guidance will emphasise the need for research utility for policy makers and stakeholders / Research does not have an impact on potential users. Mod High No change to risk status. Clear plan for engaging End users and demonstration of how they have informed project design to be key criteria for assessing impact plans / Lack of inter-disciplinary partnerships Mod High No change to risk status. Interdisciplinarity a key part of Assessment criteria and process. / Initial catalyst grants will enable formation of new interdisciplinary teams
Risk of funds not being used as intended / This programme is being implemented through NERC, which has robust fiduciary risk systems in place to effectively mitigate this area of risk. Systems comply with the requirements of the UK government and are equivalent to those of DFID. / 4.4 Climate and Environment Risk / The direct climate and environment risks of this programme are largely related to travel and other activities of the researchers themselves and are assessed as being modest. With the project still in its initial stages and the main call for proposals not yet complete, it is difficult to assess in more detail likely risks and benefits associated with individual projects supported as these are yet to be identified.

5. Value for Money
5.1 Performance on VfM measures / The Business case identified the role of the Knowledge Broker, leveraging of Research Council funds, the use of established Research Council systems for programme management and peer review and monitoring and evaluation procedures as the principle vfm aspects of the programme. / At this initial stage of the programme the principal means of ensuring vfm is through ensuring a robust, transparent and open competitive process. NERC has a strong track record of robust monitoring and evaluation systems including a commitment to good value for money. / 5.2 Commercial Improvement and Value for Money / Contracts for catalyst grants were negotiated in line with NERC procedures for commercial improvement. / 5.3 Role of project partners / UPGro is cofounded by NERC and ESRC who provide contributions of £2million each to the total £12million programme. NERC provides the Secretariat as a payment in kind and is responsible in major part for the implementation and the routine management of the programme, including managing the competitive calls process (from developing the TOR, advertising, and the various assessment stages of the calls process). The whole process is overseen by a Programme Executive Board (PEB) on which there is DFID representation (CET Team) and an independent chair nominated by the PEB (Declan Conway). / 5.4 Does the project still represent Value for Money : Y / This is difficult to assess at this stage. However, given that there has been no significant change in the approach and model of implementation proposed by the programme, and that most expert commentators assess the outlook on water scarcity and resource management to remain unchanged since the conception of UPGro, it is reasonable to assume that original vfm assessments remain unchanged. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
Although the project has experienced some slippage when assessed against the original time-frame in the Business case, the programme is now up and running and on track to deliver outputs as expected. Against the revised schedule agreed with NERC, the process is on-track to commission the main research consortia which will start work no later than Jan 2015. / No changes to the agreed tender and selection processes are proposed as the result of this review, and actions required on DFID’s part are to continue to engage as required on both the operational level (especially with the newly appointed Knowledge Broker) and as representatives on the PEB to ensure that DFID’s interests and policies are suitably accommodated. / The main actions required following this review is for the management team, including the Knowledge Broker, to meet to tighten up the log-frame and ensure systems are in place to capture and monitor programme impacts. Adopting a proactive approach to ensuring future proposals are truly interdisciplinary and focus as much on social economic aspects as the natural science will be the major challenge over the next year.

8. Review Process
This review has been undertaken by the following DFID, ESRC and NERC staff: / Anna Nileshwar – lead Adviser / Andrew Leslie – Project Officer / Jean Paul Penrose – Water Resources/Adaptation Team / Ned Garnett– NERC / Ruth Kelman - NERC / Jessica Surma – NERC / Craig Bardsley - ESRC / Declan Conway- Independent advisor/PEB Chair / The review has drawn on a specific Annual Review visit to NERC on 28th November 2013, attendance at a Project Executive Board meeting (held at DFID on 14/11/13), desk research and inputs from a number of meetings and interactions with NERC/ESRC over the course of the year. The Review has also engaged with the Water Policy Team and Climate Adaptation Team in RED. / Relevant documents included in the review include: / TORs for the Review (Quest no:4225843) / UPGro Business Case (Quest no.3692739 ) / UPGro draft logframe (Quest no.3655334 ) / Draft Announcement of Opportunity for UPGro Research Consortia (Quest no. 4262550) / Draft Workplan for Knowledge Brokers (Quest no.4262573 ) / Summaries of Catalyst Grants http://gotw.nerc.ac.uk/list_them.asp?them=UPGro&cookieConsent=A / PEB November 2013 meeting minutes (Quest no. 4262564) / BGS Groundwater Atlas Progress Report (Quest no. 4262592)