Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Unlocking the potential of groundwater for the poor in Africa (UPGro)
Programme Value: £8m (+ £2m NERC and £2m ESRC)		Review Date: November 2016
Programme Code: 203774	Start Date: 10/12/2012	End Date: 31/03/2020

Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	A	A	A	A
Risk Rating	Low	Low	Low	Moderate

Summary of programme

DFID is contributing £8million to support research that will unlock the potential of groundwater for the poor in Africa (UPGro). The Natural Environment Research Council (NERC) and the Economic and Social Research Council (ESRC) are providing £2million each, giving a programme total of £12million. NERC is also providing in-kind resources and systems to commission and manage the research calls and related procurement throughout the life of the programme. The programme will run over seven financial years from December 2012 to March 2020 and is open to UK and non-UK researchers.

UPGro will deliver the knowledge and information required to better access and manage groundwater resources to enhance water security for the 300 million poor people without access to improved water in Sub-Saharan Africa, and maximise the potential role groundwater can play in Africa’s economic development.

Summary of progress and lessons learnt since last review

Overall UPGro is progressing well. Outputs 1 and 4, which focus on academic research quality, dissemination and use, scored an (A). This was due to the continued strong results and performance of the catalyst projects but also to the emerging results from Consortium projects, which are still at various stages of development but steadily moving towards a more mature phase of delivery.

Output 3 exceeded expectations and scored a solid (A+), which was mostly due to the good outreach activities led by the Knowledge Broker and the Consortium projetc’s Principal Investigators (PIs), who engaged with a variety of key stakeholders on the ground. This aspect of the programme is also setting a clear and encouraging path towards strong impact of research on the ground, which for programmes of this type is not always a given and should be duly noted, as a significant achievement.

Output 2 scored a (B). This was not entirely due to underperformance against the programmes indicators but also to some technical issues with performance metrics, parameters and definitions, which caused an inability to monitor and report progress against two of the indicators’ milestones for this financial year. More specifically, we noted the need to better clarify the definition of indicators 2.2 and 2.3, which refer to the training, coaching and mentoring of early career researchers, and knowledge sharing by early career researchers respectively. At the moment this is too generic and lacks a clear definition for early career researchers, which according to some PIs should include young professionals with less than 10 years experience, whereas according to others should only include researchers with less than 5 years experience. We also observed how the monitoring and evaluation method that is currently being used is failing to capture changes in the number of early career researchers from one year to the next, and to account for the fact that not all early career researchers will remain throughout the life of the programme.

This resulted in an overall output assessment score of (A).

BOX 1: Main achievements of the past year (October 2015 - October 2016)

- Between October 2015 and October 2016, 6 peer review journal articles were published (15 in total for UPGro).
- New published evidence from the GroFutures project demonstrated that intense rainfall (from thunderstorms, for example) is very important for groundwater recharge, on which groundwater users depend, which is critical during El Niño events.
- The Africa Groundwater Atlas was published online by BGS. This has been promoted by BGS and the RWSN. It will be a focus of attention at upcoming events (Africa Water Week, IAH Congress, RWSN Forum) and the focus of a learning exercise as part of the RWSN-UNDP CapNet “Writing for Water” online course.
- UPGro had a major presence at the 42nd International Association of Hydrogeologists (IAH) Congress in Rome, with 14 oral and poster presentations, thus maintaining the profile of the programme amongst the international hydrogeological community.
- The Catalyst/Consortium Gro for Good won the prize for best poster at the 25th World Water Week event in Stockholm. Where UPGro also had a major presence through a large exhibition stand in collaboration with the Rural Water Supply Network (RWSN) and Unicef.
- UPGro received exposure through a detailed World Water Day article in The Guardian, as well as other online news sources, and the GroFutures launch was featured on Tanzanian TV news.
- In February, Gro for GooD research student Johanna Koehler provided a briefing on Water policy choices in Kenya’s 47 Counties to over 6000 people attending Kenya’s 3rd Annual Devolution Conference. Johanna also featured in Kenya’s Sunday Review newspaper: “To get clean water for all, draw on the 3 streams of finance, groundwork, climate.”

Summary of recommendations for the next year

The milestones for outputs 1, 2 and 4 should be revised to ensure that they are realistic and reflect the right level of ambition for the programme at the stage it is at now and will be in future years. The Programme Executive Board (PEB) should also consider whether to request some ad-hoc input from a M&E specialist to ensure the fine-tuning of all indicators and milestones going forward (To be discussed at next PEB in January 2017 and actions agreed if needed).

The PEB should ensure that the programme has a clear strategy on how to tackle and monitor progress on gender issues. This should focus on understanding impact of programme activities on women and girls but include also disaggregation by gender in the Programme Co-ordination Group (PCG) work plan and monitoring plan (To be completed by February 2017).

There is a need to further refine methodology to measure progress against indicator 2.3, as well as how it is reported on, in order to properly report a numerical value (To be completed by December 2016).

1. Going forward the PCG and PEB should consider expanding the role and reach of the programme ambassadors, especially as two more are recruited (To be reviewed in June 2017). This may involve more collaboration with other large programmes implemented by other international development agencies.
2. Where possible, the UPGro programme should make use of metrics and indicators from similar DFID-funded programme, but ensuring that these are adapted to reflect UPGro’s needs and requirements adequately. In terms of monitoring impact we agreed that UPGro should use the metrics and indicators that have been developed for the REACH/IWSP (Improving Water Security for Poor People) programme and adapt these as described (To be completed by February 2017).
3. The PEB should also consider whether the programme needs to allocate more time and resources to the Knowledge Broker agent (SKAT Foundation) to ensure that some of the most pressing issues concerning monitoring and evaluation and gender impact are addressed promptly and effectively (To be agreed by Next PEB in January 2017).

_______________

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203774/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203774/documents

Water resources are critical to economic growth and social development. A study on groundwater in Africa has shown that there is possibly 20 times more water available as groundwater compared with that available in lakes and rivers[1]. Groundwater provides most of the domestic water supply in parts of rural Africa and supports poverty reduction through access to clean drinking water and irrigation[2]. It is estimated that groundwater provides water for domestic supplies and livestock for more than 100 million people and is the source of drinking water for 75% of Africa’s population (although this varies in proportion by country/sub-region)[3]. Ensuring availability and sustainable management of water resources has been enshrined in the UN Sustainable Development Goals (SDGs) under SDG 6. In 2015, 6.6 billion people, or 91 per cent of the global population, used an improved drinking water source, versus 82 per cent in 2000. Despite that improvement, an estimated 663 million people were using unimproved water sources or surface water that year. Groundwater has the potential to provide an improved source of drinking water for those in SSA who are currently without access. It is also often naturally protected from contamination, so is generally of good quality and needs no treatment.
[1] MacDonald et al. 2012. Quantitative maps of groundwater resources in Africa. Environ. Res. Lett. 7. 024009
[2] Hunter et al. 2010. Water Supply and Health PLoS Med7 (11): e1000361
[3] UNECA African Climate Policy Centre 2011 Management of Groundwater in Africa including transboundary aquifers: Implications for meeting MDGs, livelihoods goals and climate change adaptation. Working Paper Number 6.

‘Water stress’, which is calculated as the ratio of total fresh water withdrawn by all major sectors to the total renewable fresh water resources in a particular country or region. Currently, water stress affects more than 2 billion people around the world and hinders the sustainability of natural resources, as well as economic and social development. Groundwater is no exception and is already under pressure in many parts of Africa in some cases being abstracted faster than it can be replenished. Water withdrawal for agriculture is generally the most water-intensive productive/economic activity, although use in SSA varies by region (e.g. 90-95% in Horn of Africa and Sahelian regions, 75-80% in east Africa region)[4]. Demand for irrigation is increasing[5] and linked to agricultural growth and intensification, which will be needed to ensure food security for the rapidly growing world population in the face of climate change. Water is also central to most industries and a vital commodity for tourism, both of which are important sources of income for many African countries.
[4] http://www.fao.org/nr/water/aquastat/data/query/index.html?lang=en
[5] S. Siebert, J. Burke, J. M. Faures, K. Frenken, J. Hoogeveen, P. D¨oll, and F. T. Portmann (2010) Groundwater use for irrigation – a global inventory (Hydrol. Earth Syst. Sci., 14, 1863–1880, 2010 www.hydrol-earth-syst-sci.net/14/1863/2010/ doi:10.5194/hess-14-1863-2010)

With these increasing pressures on water resources, the potential pressure on groundwater as the solution to the water security challenge in SSA is high. As the population grows, water security in SSA will become increasingly important and demands on groundwater are likely to surge. Poorly managed water resources will constrain opportunities for development, including better services and livelihoods for poor people. Despite the importance of groundwater in meeting water security needs for poor communities in Africa, there remain big challenges to realise this potential, including substantial knowledge gaps[6].
[6] MacDonald AM, Bonsor HC, Calow RC, Taylor RG, Lapworth DJ, Maurice L, Tucker J and Ó Dochartaigh BÉ. 2011. Groundwater resilience to climate change in Africa. British Geological Survey Open Report, OR/11/031. 25 pp.

Without addressing some of these core gaps in the evidence and data, it will be hard to identify and manage the full implications of increased groundwater use. UPGro is funding high quality environmental and social research to address these issues. The programme aims to deliver robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa. All research supported under UPGro will deliver outputs that can be used by policy makers and other stakeholders to inform effective decision making and planning. The UPGro programme has two phases, the initial phase (2013-2015) comprised 15 ‘Catalyst’ projects that investigated different aspects of how the use and understanding of groundwater in Africa interacts with with socio-economic conditions. Phase II was launched in 2015 and comprises five ‘Consortium’ research projects, which will run until 2019 and are undertaking detailed research on several aspects of ground water in Sub Saharan Africa (SSA). The table below provides further details on each project and a brief explanation of their area of research.

#	Consortium Projects (2015-2019)
	Project Title	Area of Research/Problem statement
1	Gro for GooD: Groundwater Risk Management for Growth and Development	The overarching project aim is to design, test and transfer a novel, interdisciplinary and replicable Groundwater Risk Management tool to improve governance transformations to balance economic growth, groundwater sustainability and human development trade-offs.
2	Grofutures: Groundwater Futures in Sub-Saharan Africa	Groundwater Futures in Sub-Saharan Africa (GroFutures) will develop the scientific evidence and inclusive groundwater management processes by which groundwater resources can be used sustainably for poverty alleviation in Sub-Saharan Africa (SSA).
3	BRAVE: Building understanding of climate variability into planning of groundwater supplies from low storage aquifers in Africa	The BRAVE project will develop water demand scenarios to inform the modelling of water resources and availability in future years. This work will be based on current domestic, agricultural and productive use needs and will be set within the context of the current impacts on existing needs and demands.
4	T-GroUP: Experimenting with practical transition groundwater management strategies for the urban poor in Sub Saharan Africa	Improving access to safe water in slums is really complex and challenging. “Transition Management theory” embraces that complexity to find radically new and collaborative ways of using and managing urban groundwater. The project will investigate what social, technical and political changes are needed to make the shift towards sustainable urban groundwater management.
5	Hidden Crisis: unravelling current failures for future success in rural groundwater supply	Millions of pounds of investment by water users, charities and tax-payers are wasted each year by water points failing soon after construction. Getting a more complete understanding of how to keep water flowing from boreholes will reduce waste and improve water services for Africa’s poorest communities.

#	Catalyst Projects (2013-2015)
	Project Title	Area of Research/Problem statement
1	Hidden crisis: Strengthening the evidence base on the sustainability of rural groundwater services	Rural water boreholes with handpumps suffer high failure rates. Understanding the causes of these failures is necessary to carry out more effective service provision.
2	Groundwater recharge in Africa: identifying critical thresholds	Groundwater recharge: will the pumps run dry? The problem Groundwater recharge is one of the most difficult parameters to measure in the assessment of water resources yet is critical for reliable projections of sustainable resource development.
3	Mapping groundwater quality degradation beneath growing rural towns in Sub-Saharan Africa	Shallow hand dug wells and boreholes in urban areas are potentially at high risk of contamination. Mapping of groundwater contamination and understanding the key risk factors remains a priority.
4	BRAVE: Building understanding of climate variability into the planning of groundwater supplies from low storage aquifers in Africa	The problem Increasing water demands set in a context of variable climate and changing land use, together with dependence on low-storage, low-yield aquifers.
5	Optimising Road Development for Groundwater Recharge and Retention	Road construction interferes with local runoff and recharge, to the detriment of farming and livelihoods. At the same time roads suffer serious water-related damage. The project has attempted to address both issues.
6	ARIGA: Assessing Risk of Investment in Groundwater Resources	Groundwater investments are often pursued without adequately considering the associated risks. These investments then frequently fail to meet their development objectives. A broader, inclusive socio-hydrological approach is needed.
7	Sustaining groundwater safety in peri-urban areas	As urban populations outgrow the ability of utilities to supply piped water, the growing dependence on privately developed urban groundwater raises questions of water safety for consumers.
8	AMGRAF: Adaptive management of groundwater in Africa	Productive use of groundwater in Africa offers many opportunities. Much information on groundwater exists in the form of global remote sensing products, while local indigenous knowledge also has much to offer. These two information sources need to be combined with hydrological modelling and appropriate social and governance systems to achieve sustainable development
9	Towards groundwater security in Coastal East Africa	Groundwater resources in coastal East Africa are at risk from growing populations and from climate change. Groundwater resources need to be understood and monitored, and sustainable management approaches designed.
10	Improving access to safe drinking water prospection for low-fluoride sources of groundwater	High levels of fluoride in groundwater cause dental and skeletal fluorosis in those who consume it. It is necessary to find ways to mitigate this problem for the estimated 8m people who are exposed to it in Ethiopia alone.
11	Groundwater risks and institutional response in rural Africa	In locations with limited groundwater resources, but where large-scale demands are increasing, the question arises as to how groundwater can be sustainably managed to the benefit of both the wider economy and the rural poor. Can water risks be managed for both growth and development?
12	Use of remote sensing and terrain modelling to map manual drilling potential in Senegal and Guinea	Extending groundwater supply to more people is expensive using conventional technologies. Manual well drilling offers cost-saving opportunities, but the techniques involved can only be used in specific ground conditions.
13	GroFutures: Groundwater Futures in Sub-Saharan Africa	Despite the importance of groundwater for growth and development, substantial uncertainty concerning the renewability, accessibility and management of groundwater resources remains.
14	INGROUND: Evaluating an inexpensive biosensor to detect anthropogenic pollution in groundwater	The majority of the urban population in Africa uses on-site sanitation systems which pose a threat to groundwater quality and safety. The monitoring of water quality in such environments needs to be made easier and cheaper.
15	Resource limitations to sustainability of groundwater well-points in basement complex regions of sub-Saharan Africa	Despite the many advantages of groundwater, including its resilience to climate variability and change, a recent analysis in Malawi has cast doubt on its universal sufficiency, in the Basement Complex regions of southern Africa, where the aquifer has limited storage and demand is high.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome for the UPGro programme is: “Use of robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa”. In spite of some minor set-backs at the output level, the programme is on course to achieve its outcome and is currently either meeting or exceeding all of the four milestones, which have been set against the outcome indicators for this reporting period. The table below and the related narrative sections that follow provide a detailed illustration and description of progress against each milestone.

OUTCOME		Indicator	Baseline	Progress	Milestone 1 (2016)
			-2014
Use of robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa	O.1	Use of evidence by other researchers: Citation of UPGro research in briefing papers, working papers and conference proceedings and peer-reviewed articles and book chapters.	0	32	L: 5 M:10 H: 20 In total
	O.2	Use of evidence by national decision-makers: Number of National Sector Performance Reports, Joint Sector Review reports or other key reports, strategies and plans that directly or indirectly reference UPGro research.	0	2	2
	O.3	Use of evidence by international decision-makers: Number of key international documents, such as JMP, GLAAS, UN World Water Development Report that directly or indirectly reference UPGro research.	0	1	0
	O.4	Use of evidence influencing change: Number of stories of changes to groundwater use that have affected the poor in Sub Saharan Africa, which were influenced by UPGro or where UPGro research has influenced policy, the institutional framework, practice, groundwater monitoring and research.	0	1	1

Use of evidence by other researchers
The University of North Carolina (UNC) has used UPGro project findings on hand-pump functionality monitoring (prepared by Vincent Casey, WaterAid and Alan MacDonald (British Geological Survey - BGS from the Hidden Crisis project) in its briefing note[7] targeted at the Sanitation & Water for All (SWA) partnership. In addition UPGro research has been cited in 31 academic papers by others. This makes up a total of 32 external citations of UPGro research, which substantially exceeds the multilevel target of 5 (Low), 10 (Medium) and 20 (High) set for this year.
[7] University of North Carolina WaSH Policy Research Digest ISSUE #3, March 2016 - https://upgro.files.wordpress.com/2015/09/wash-policy-research-digest-3.pdf

In addition the Gro for GooD project has played an influential role in establishing the DFID-funded REACH programme, but this is not captured by the logframe. We have now agreed that we will revise the logframe to ensure this captures all success stories.

Use of evidence by national decision-makers
In this reporting period there is one example of reference to national reports, strategies or plans directly or indirectly reference UPGro research:
Participation of BRAVE at the Volta Basin Authority 5 year Planning Meeting have resulted in the next 5-year IWRM Plan to include groundwater, and not just surface water as was the case previously.

This brings the total number of examples to two, which is in line with the target for this reporting period.

Use of evidence by international decision-makers
So far, there is one case of evidence from UPGro projects being used by international decision-makers, which is already in line with the target set for next year. This is related to findings from Hidden Crisis, which are cited in the Guidance Note on Professional Drilling due to be published by UNICEF in late 2016.

Unfortunately, no other major WASH international documents (e.g. UN Global Analysis and Assessment of Sanitation and Drinking-water, the World Health Organisation Joint Monitoring Report on water, UN World Water Development Report) have been published during this reporting period, but it is likely that at least some of this will pick up evidence from UpGro research when they are published. For example, the new UNICEF WASH strategy[8] recognises that long-term changes to groundwater availability threaten existing water and sanitation systems and notes the need for continued support for specific adaptation measures in communities such as groundwater research.
[8] UNICEF (2016) Strategy for Water, Sanitation and Hygiene 2016-2030, UNICEF, http://www.unicef.org

Use of evidence influencing change:
In this period, UPGro can report on one story where the research has influenced policy, the institutional framework, practice, groundwater monitoring or research. This refers to the Makutapora Wellfield, Tanzania, where the GroFutures project is enabling the managed aquifer recharge to increase the sustainability of water supply for Dodoma. Previous research by the GroFutures Team showed that Makutapora Wellfield, which is the sole, perennial source of safe water to this city of over 400,000, depends upon episodic, heavy rainfalls associated with the El Niño Southern Oscillation (ENSO)[9].
[9] http://www.nature.com/nclimate/journal/v3/n4/full/nclimate1731.html

An improved understanding of groundwater recharge process and gained through high-frequency monitoring, is now enabling the design of ‘Managed Aquifer Recharge’ strategies to enhance the frequency and magnitude of replenishment to the wellfield and thus the sustainability of intensive groundwater use for Dodoma.

It should be noted that milestones for this indicator are yet to be set as this was expected to be a ‘longer term’ indicator and therefore that this result is already exceeding expectations of this reporting period.

Continuation of catalyst research
Although not captured by the log frame, the catalyst research from six of the twelve projects has continued in different forms:

- The tryptophan groundwater quality sensor (D. Lapworth, BGS) is being used by the UPGro Hidden Crisis and T-Group projects and Future Climate for Africa (FCFA)[10] HyCRISTAL project, and in India by BGS and Water for People.
  [10] http://www.futureclimateafrica.org/
- Dr Fussi (Milano Biococca) is in the process of publishing his catalyst work on remote sensing for manual drilling and continuing follow-up work in Senegal, Guinea-Bissau and Guinea in partnership with UNICEF and the Cheikh Anta Diop University, Dakar.
- The Road Recharge Catalyst (Meta Meta Research/Mekelle University) is continuing with funding from NWO/WOTRO (The Netherlands) and the Global Resilience Program (GRP).
- Dr Comte (Aberdeen) from the Coastal Groundwater catalyst (J. Obando, Kenyatta) has been a research grant from the Royal Geographical Society for “East African groundwater resources under climatic and human pressure: A comparative study bringing field evidence to water sustainability in Kenya (2016-2017).”
- Dr Wright (Southampton) has received a Royal Society exchange programme grant with the University of Ghana that is informed by experiences from the peri-urban groundwater catalyst.
- AMGRAF Catalyst work is continuing through PhD research[11]. Newcastle University and IWMI continue to explore further funding opportunities and have been awarded a REACH Catalyst Grant[12].
  [11] Walker, D., Forsythe, N., Parkin, G. and J. Gowing (2016) “Filling the observational void: Scientific value and quantitative validation of hydrometeorological data from a community-based monitoring programme” Hydrology Journal,  Volume 538, July 2016, Pages 713–725
  [12] http://reachwater.org.uk/funding/catalyst-projects-call-1/water-security-risk-science-local-monitoring-for-participatory-resource-management/

Researchers involved in the Catalyst projects have also continued to publish papers related to their UPGro work after the Catalyst projects have officially ended. This resulted in a further 13 papers being published since 2014[13].
[13] https://upgro.org/publications-papers/not-directly-funded-by-upgro/

Overall output score and description: (A Outputs met expectations)

The performance against the indicators set against the outputs was slightly mixed but resulted in an aggregated score of (A).

Output 1 and output 4 scored an (A) and could have scored more highly if the milestones for this reporting period had been set more accurately to reflect an adequate level of ambition for the programme at this stage of implementation and capture a number of achievements that were missed.

Output 3 scored an (A+) as it exceeded most of the milestones set for this reporting period and generated an impressive level of impact through its activities on the ground.

Output 2 scored a (B) as it did not report progress against two of its three indicators. This difficulty was triggered by technical issues pertaining the framing of the indicators and the milestones for this reporting period and reflected the lack of an adequate response to the recommendations that were made in last year’s annual review. These issues have been duly noted and a number of additional recommendations have been made to try and address the underlying issues that generated these problems. Close monitoring will required over the next reporting period to ensure that these issues are rectified.

Key lessons

Key lessons for this reporting period were as follows:
- The Catalyst grants, even though they were smaller in size, added a lot of value to the programme and generated some excellent results.
- Having a specialist knowledge broker has proven to be a good model and was deeply appreciated by the project PIs who felt relieved from tasks that may have otherwise diverted vital resources from implementation of research activities thus diluting the overall success and impact of the programme.
- We also learned lessons about the management structure from other programmes co-funded by DFID, ESRC and NERC, where uneven power dynamics between various programme actors led to management issues and delays.
- We learned some hard lessons from the issue of sub-contracting implementing partners in the regions and the impact that this can have on the programme in terms of delays and morale. We have now developed an approach to overcome this challenge and ensure mitigation of any impacts on the programme. More specifically, what we have realised is that we need to ensure that the project PIs build sufficient time into proposals to allow for the contracting of second tier partners and contractors. The Research Councils are also in discussion with Higher Education Institutions to improve collaborative working practice that ensure better financial management of Overseas Development Assistance (ODA) grants and sub-contracts, Global Challenges Research Fund (GCRF) has been the driver for this, but outcomes of the discussions will also apply to grants in programmes co funded by the Research Councils (RCs) and DFID.

- Delays with setting up the programmes were discussed and we reflected on the impact that this can have further down the line in terms of meeting programme deadlines and adhering to the original programme timeline. This led to the learning of valuable lessons which should be applied to future programmes and added to the already significant cache of lessons we have learned from other programmes. In particular we realised that some of the timings involved cannot be shrunk significantly and that we should be more upfront and realistic when setting timelines at the design stage of programme.
- The commissioning of the mid-term review will happen in this reporting period and will be an important milestone for the programme. Here we reflected on the hard lessons we learned from other programmes and agreed to follow a different course, which should be based on mutual trust and understanding between partners. We also reflected on the methodologies to be used for this exercise and the best choice of consultants/service providers for the job.
- Finally we reflected on the importance of tools that the programme will produce and looked at best-practice examples from other programmes as a model and inspiration to ensure maximum impact and value for money.
Key actions

- Review the milestones for outputs 1,2 & 4 to ensure that they are realistic and reflect the right level of ambition for the programme at the stage it is at now and will be in future years (To be completed before next PEB in January/February 2017).
- PEB to ensure disaggregation of data by gender and a strengthened definition for women early career researchers are included in the PCG work plan and monitoring plan (To be completed by February 2017).
- PCG to ensure early career researcher definitions are consistent across all projects to enable future collation of data (To be completed by December 2016). This will have to be reviewed and approved by PEB at next meeting (in January/February 2017).
- PCG to agree plan of action to further refine methodology to measure progress against indicator 2.3, as well as how it is reported on in order to properly report a numerical value (To be completed by December 2016). This will have to be reviewed and approved by PEB at next meeting (in January/February 2017).
- PCG to agree a plan of action to refine the methodology needed to measure progress against indicator 2.3, as well as how this is reported, in order to properly report a numerical value (To be completed by December 2016). This will have to be reviewed and approved by PEB at next meeting (in January/February 2017).
- The PEB and PCG will need to draft a gender action plan, which will need to include a viable solution on how to improve the monitoring of impact of programme activities on gender (By February 2017).
Has the logframe been updated since the last review?

The logframe has had some minor revisions since last year. We have now agreed further and more detailed changes to be made, to ensure that all milestones and indicators are appropriate and reflect the correct level of ambition for the programme going forward (See recommendations for outputs 1, 2 and 4).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Research contributing to sustainably managed groundwater resources for poor people in Sub-Saharan Africa of a high academic quality is generated and disseminated.
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Peer-reviewed papers: / Cumulative number of peer-reviewed articles in journals, conference proceedings or book chapters.	Published: / Catalysts: 15 / Consortium: 0	Published: 15 / Catalysts: 12 / Consortium: 3 / Submitted: 1 / Catalysts: 1 / Consortium: 0
Peer-reviewed papers (impact): / Number of citations / Number of NON self-citations	20 / 15	44 / 32
Peer-reviewed papers (interdisciplinarity): / Proportion of papers where the authors are from different disciplines.	20%	33%
Peer-reviewed papers (African authors): / Proportion of papers with lead (first or second) authors based in African institutions.	1st or 2nd author: 20%	33%
Data: / Proportion of data collected by UPGro studies uploaded to NERC and ESRC data centres.	L: 0% / M: 0% / H: 0%	Catalysts: 7% (1 of 15) / Consortia: 0
Dissemination: / Cumulative number of research document downloads from UPGro websites.	4000	2454

Key Points

Peer reviewed papers
A total of 15 peer-reviewed papers have been published in various journals to date. Out of these 12 were published by Catalyst projects and 3 by Consortium projects, which is reflective of the fact that Catalyst projects are now in a mature phase, whereas the consortium projects are still at various stages of development. It should also be noted that the rate of publication for the whole programme has been growing steadily with four papers published in the last 12 months. These include the first project papers from two consortium projects, namely T-Group and Hidden Crisis. The milestone for this year consisted of 15 papers, but with a slightly different distribution between consortia and catalyst projects (i.e. 0 and 15 respectively). Even though the project fell short very slightly of the target for the catalyst project, this was very well compensated by the uplift in publications from consortium projects, which puts the project well on course to meet and possibly exceed next year’s milestone.

Peer-reviewed papers (impact)
The number of citations is increasing and currently stands at 44 across 15 papers. Of these, 32 are non-self-citations and contribute to exceeding the milestone against indicator 2.2 above (peer reviewed papers impact). The most cited work so far is “Emerging contaminants in urban groundwater sources in Africa” by Sorensen et al. (2015)[14] with 16 citations (12 non self-citations). In addition, and not captured in the log frame, the British Geological Survey (BGS) project report for the Hidden Crisis catalyst has been cited in several online articles, blog posts and conference presentations[15].
[14] http://www.sciencedirect.com/science/article/pii/S0043135414005569
[15] Bonsor H C, Oates N, Chilton P J, Carter R C, Casey V, MacDonald A M, Calow R, Alowo R, Wilson P, Tumutungire M, Bennie M. “A Hidden Crisis: strengthening the evidence base on the sustainability of rural groundwater supplies – results from a pilot study in Uganda” BGS report reference: OR/15/019

Peer-reviewed papers (interdisciplinarity):
Of the 15 published papers, five (33%) have been co-written by authors from different disciplines, and have covered areas of investigation that cut across a ‘single discipline’ thus exceeding the milestone of 20% for interdisciplinary papers.

Peer-reviewed papers (African Authors)
Since the start of the programme, 33% of the papers have an Africa 1st and/or 2nd author, thus noticeably exceeding the target of 20%. Here it should also be noted that all African authors were involved in catalyst projects and none yet in Consortium projects. This is not yet a cause for concern, especially given that Consortium projects have only just started publishing papers (totalling to three up to now) but is something that should be monitored going forward and may need addressing in the future.

Data
Efforts are on-going for submission of data from the catalyst projects and although this is proving somewhat challenging, this is not unexpected and the milestone for this year was exceeded and progress continues to be made. It should also be noted that the Catalyst grants were started before NERC provided funding to proactively manage data and introduced the Data Management Plans, which are now mandatory for all Consortium projects. Funding has been provided to the UK National Geoscience Data Centre (NGDC)[16] to manage UPGro data since the catalyst grants began. The Catalyst projects all produced data management plans (this is a requirement for all NERC-funded projects), but the scale of the projects meant that not all created data that needs to be archived. A programme-level data management for the consortia grants is currently being developed
[16] The National Geoscience Data Centre (NGDC) collects and preserves geoscientific data and information, making them available to a wide range of users and communities. NGDC is hosted by the British Geological Survey (BGS) and is recognised as the NERC Environmental Data Centre for geoscience data.
No data from the consortia projects has currently been submitted to the National Geophysical Data Centre (NGDC). Even though this is to be expected at this stage of the projects when the data is still being collected, we discussed that close monitoring of the evolving situation will be needed to ensure that all of the consortia projects will implement the provisions under their data management plans, which we observed, have been developed on time. There is also a need to clarify the data sets definition, and adjust the milestones in the logframe to ensure consistency with the Data Management Plans.

Dissemination
There have been 2454 cumulative research document downloads from UPGro websites, which is 60% of the milestone for 2016 but still quite remarkable if considered in absolute terms. We discussed the reasons for this shortfall at the AR meeting and we concluded that the target for this year was too ambitious for this early stage of implementation of the Consortium projects and that this should be reviewed accordingly.

In addition, it should also be noted that visits to the Africa Groundwater Atlas website are not captured in the log frame and that these attracted an average of 684 visitors every month, with the top 62 pages (including hydro-geology Kenya, Nigeria, Somalia, Ethiopia, Sudan, Algeria, Tanzania, Benin, Uganda and Zambia) all having more than 1,000 visitors. We are now considering revising the logframe accordingly to make sure this captures progress more comprehensively.

The UPGro website (www.upgro.org) is the gateway to the programme, and is also a management tool which is updated on a regular basis to provide a comprehensive store of materials emerging from the programme and links to organisations, articles and events where UPGro is visible. From November 2015 – October 2016, there were 61 posts, which were also broadcast through the UPGro and Rural Water Supply Network (RWSN) twitter accounts, LinkedIn profiles and other social media. The top visitor countries in 2015/16 have been: UK, USA, Netherlands, Kenya, Germany, India, Tanzania, Ethiopia and South Africa.

Furthermore, an UPGro YouTube channel[17] was launched in July 2016 to bring together all the video resources from across the programme. This included new edited versions of the UPGro presentations given through RWSN webinars and key researcher interviewers done by GroFutures.
[17] https://www.youtube.com/channel/UCTv5uGIhSsEiZ2ktSTn3jhA

Summary of responses to issues raised in previous annual reviews (where relevant)

At last year’s AR we made a recommendation aimed at ensuring that catalyst projects uploaded data to NERC and ESRC data centres. As noted above this is still an issue but we feel that the current level of engagement is starting to produce results. We have agreed that we will keep monitoring this issue and we will think of alternative solution at the mid-point next year if results are still below expected levels.

Recommendations

The milestones for this output should be revised to ensure that they are realistic and reflect the right level of ambition for the programme at the stage it is at now and will be in future years (To be completed before next PEB in January/February 2017).

The situation concerning the upload of data should also be monitored closely in the next few months and an alternative plan of action to ensure higher rates of compliance form Catalyst projects should be put in place (by March 2017) if no significant improvement is recorded.

Output Title	UPGro early career researchers equipped with the skills to collaborate and communicate their work in the wider context of poverty and groundwater science and governance
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	10 %
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
International events: / Cumulative number of Early Career (EC) researchers from each project presenting research findings at international conferences. (disaggregated by sex and nationality)	Early Career presentations: 30 / Proportion of Consortium Early Career who have presented: / 7 of 25 (28%) / EC Women: 3 of 9 / EC Africans: 4 of 14 / EC African Women: 1 of 3	Early Career presentations: 33 (30%) of which : 12 women / 7 African, 1 African woman / Consortium: / 6 of 45 (13%) / EC Women: 3 of 6 / EC Africans: 1 of 6 / EC African Women: none
Training, coaching and mentoring: / Cumulative Number of Early Career (EC) UPGro researchers receiving training or systematic coaching and mentoring (disaggregated by sex, nationality).	7 of 25 / EC Women: 3 of 9 / EC Africans: 4 of 14 / EC African Women: 1 of 3	No harmonised/amalgamated data available. Due to technical issues with the definition of EC researchers it was no possible to have consistent data that could be measured and reported reliably.
Knowledge sharing: / Cumulative number of UPGro Early Career (EC) that have actively participated in at least one international knowledge sharing event (disaggregated by sex and nationality).	10 of 25 / EC Women: 5 of 9 / EC Africans: 4 of 14 / EC African Women: 1 of 3	No harmonised/amalgamated data available. Due to technical issues with the definition of EC researchers it was no possible to have consistent data that could be measured and reported reliably.

Key Points

Overview of researcher profiles
The number and profile of researchers has changed within this reporting period. There are currently 113 researchers, of which 45 (40%) are early career (defined as having less than ten years of experience from January 2015). Of these 45, 15 are women, 25 are African and only three are African women.

International events - number of early career researchers presenting
There have been a number of UPGro presentations at international events and conferences. Of the 114 presentations made, 33 (30%) were given by early career researchers.

To date 16 early career researchers have presented at international events. However, only six out of the current 45 (consortium) early career researchers have presented. At 13%, this is under half the target of 28%. Of these six, three are women, one is African, and none is an African woman. Considerable effort will be needed to improve this in the future.

Additionally, given that the number of early career researchers’ changes from one year to the next, and that not all early career researchers will remain throughout the project, the unit of measurement and milestones should be revised to ensure that the data capture the full extent and impact of capacity building activities and adequately reflects the efforts made at the programme level.

Training, coaching and mentoring of early career researchers
No data was presented against this indicator (i.e. 2.2) this year due to technical issues in monitoring and reporting progress, which produced incongruent and thus invalid data. We discussed the reasons behind this and it emerged among other things that not all PI’s have the same understanding about early career researchers and that some PIs were using different definitions from others. We agreed that this is an issue which needs resolving and that should be discussed as a priority agenda item at both the Programme Co-ordination Group (PCG) and the Programme Executive Board (PEB).

Knowledge sharing by early career researchers
No data was presented against this indicator (i.e. 2.3) as well. This was due to the same issue, which impeded the gathering of data for indicator 2.2, namely that it was not possible to gather comparable and uniform data about early career researchers. One reason for this was the difference in criteria underscoring the definition of ‘early career’ used by different PIs and between the UK and Africa. Going forward it was also noted that the indicator should be revised to account for the changes in number of early career researchers throughout the life of the programme. Now that the knowledge exchange strategy and workplan have been prepared, it was agreed that better defined parameters can be set and this indicator can be fine-tuned accordingly.

Summary of responses to issues raised in previous annual reviews (where relevant) n/a
There were three recommendations in the last AR, which focused on ensuring that gender was included in the PCG workplan and that future monitoring of activities included disaggregation of data by gender and early career researchers. The final recommendation was also to ensure that early career researcher definitions are consistent across to enable future collation of data.

Having reviewed the PCG Workplan we could only found one mention of gender under the ‘activities’ section (page 6), even though this was an improvement from last year, we should conclude that this does not represent a significant step-change.

With regard to the other two recommendations on disaggregation of data and refining of definitions of early career researchers, it can be concluded that these were not implemented or adequately addressed and this is also the reason why monitoring of progress against indicators 2.2. and 2.3 was not possible this year. This is disappointing and addressing these issues must now become a priority task for both the PCG and the PEB. All recommendations from last year have been rolled out to this year (see below recommendations 1-3) and have been complemented by two more.

Recommendations
The PEB should ensure disaggregation by gender is included and strengthening of women early career researchers is included in the PCG work plan and monitoring (To be completed by February 2017).

1. PCG to ensure early career researcher definitions are consistent across to enable future collation of data (To be completed by December 2016).
2. There is a need to better clarify the definition of training, coaching and mentoring in indicator 2.2 (To be completed by December 2016).
3. There is a need to further refine methodology to measure progress against indicator 2.3, as well as how it is reported on in order to properly report a numerical value (To be completed by December 2016).
4. The PEB should consider whether to get some technical input from an M&E specialist to help fine-tuning of all indicators and milestones going forward.
Output Title	Targeted awareness-raising of policy-makers, practitioners and change makers on the realities and potential of groundwater for the poor in Sub-Saharan Africa (SSA)
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Involvement in research: / Number of stories of SSA stakeholders involved in the development of the research plans and the testing and validation of practical tools, manuals, handbooks, guidelines and frameworks for groundwater management.	L: 3 / M: 5 / H: 10	6
Briefing materials produced: Number of policy and practice briefing materials and syntheses produced by UPGro research projects.	L: 5 / M: 7 / H: 10	11
UPGro events: / Number of UPGro project events with policy-makers, practitioners and change makers, where research findings are presented.	5	11
Decision-making processes: / UPGro projects actively involved in national (and sub-national) sector processes and events (e.g. sector reviews, planning and policy meetings).	At least 1 processes or events per project / (NO=0 / YES=1)	4

Key Points
This output saw the best level of performance across the programme with strong progress against all indicators.

Sub-Sahara African Stakeholder Involvement in UPGro research
In this reporting period, there were six stories of Sub-Saharan African stakeholders, who were involved in the development of research plans for UPGro projects, as well as the testing and validation of practical tools, manuals, handbooks, guidelines and frameworks for groundwater management. These were as follows:
1. The Irrigation Development Authorities (Oromia), the “Woreda” (i.e. district) level water user associations and agricultural offices, as well as the River Awash Basin Authority in Ethiopia have informed the research questions for the ‘GroFutures’ project. Their participation at the Inception Workshop in July 2016 has informed the priority science questions and design of physical basin observatories to be constructed in upland and lowland parts of the Upper Awash Basin.
2. At the GroFutures Inception Workshop in Tanzania in April 2016, the Rufiji Basin Water Board and the research team agreed to share details of proposed monitoring infrastructure constructed by the Ministry itself and under GroFutures, which will be used to optimise representative coverage of groundwater monitoring facilities in the Great Ruaha River Sub-Catchment and to facilitate the long-term adoption of monitoring infrastructure.
3. Officials from the Water Ministries in Ethiopia, Malawi and Uganda have reviewed the selection process for identifying a sub-sample of water-points to survey and provided valuable insights to enable an efficient but statistically robust survey for the Hidden Crisis project. District officials have also been involved in the process and in most cases also provided local engineer staff to accompany the team and contribute to the research.
4. WaterAid is contributing to each and every Hidden Crisis project discussion and workshop, helping to shape the research questions and outputs to be more valuable to the WASH sector.
5. The BRAVE project is undertaking detailed monitoring and related research at three experimental catchments within Burkina Faso and Ghana in collaboration with the Institut International d'Ingénierie de l'Eau et de l'Environnement (2iE), and the German Government funded West African Science Service Centre on Climate Change and Adapted Land Use (WASCAL) Programme.
6. The decision-support tool for managing hydrological and agricultural risk has been piloted by a partnership between BRAVE and the Ghana Meteorological Briefing Materials[18].
  [18] See Project Reports & Briefings - https://upgro.org/publications-papers/project-reports/ for links to all briefing materials.
Three briefing notes have been published by UPGro within this reporting period, bringing the total to eleven (just above the high milestone of 10):

- Groundwater use and climate: the Makutapora Record  (GroFutures)
- Hidden Treasure: 10 reasons to know more about groundwater / 2 priorities to take seriously – briefing note  (Knowledge Broker)
- SSEE Water Programme (August 2015) Distributed Monitoring of Shallow Aquifer Level using Community Handpumps (Gro for Good)

UPGro at Events
There have been 40 events[19] to date with an UPGro presence, of which 11 have had at least three UPGro papers, presentations and posters or an UPGro stand and have thus been captured in the log frame. It should also be noted that this definition has been proposed by the Knowledge Broker so as to make sure that the metric represents what the indicator is trying to measure, rather than all events attended by UPGro researchers, which are numerous and would have produced a much higher scoring against this indicator.
[19] # Details of all presentations and peer-reviewed conference abstracts, papers and posters https://upgro.org/publications-papers/conferences/

Decision-Making Progress
This indicator measures UPGro projects actively involved in national (and sub-national) sector processes and events (e.g. sector reviews, planning and policy meetings). The milestone has been set at one process per project per year throughout the life of the project. So far, four projects have done this, with the fifth engaging stakeholders in its planning processes:

- JK (Gro for Good female early career researcher) attended and presented at 3rd Annual Devolution Conference in Kenya which was attended by 6000 people. In collaboration with the Water Services Trust Fund, she delivered a statement on devolution and its impact on the water sector, sharing some key findings of the research;
- RC (BRAVE female PI) participated in the Volta Basin Authority 5 year planning meeting;
- Hidden Crisis presented at the WASH sub-group of the Water Sector Working Group in Ethiopia;
- TGroup requested permission to drill at a church meeting in Bwaise, Kampala, Uganda.

Summary of responses to issues raised in previous annual reviews (where relevant)
The was only one recommendation against this output last year, which concerned the appointment of UPGro ‘Programme Ambassadors’ to be made in time to be effective and maximise impact. The role of the Programme Ambassadors will be to reach out to and engage with policy-makers and government offficals across SSA to ensure that they become aware of UPGro and the evidence it is generating with a view to ensure that this and other programme outputs are put to use and inform decisions, policies and action plans regarding the use and management fo water resources with a focus on ground water.

Two ambassadors have already been recruited and the recruitment process for a further two is current under way. Our discussions revealed that the two appointees have so far made very positive contributions to the programme and contributed to the success of this outputs.

Recommendations

There are no specific recommendations or action points against this output for this year.

However, it is noted that the implementation of activities under this output was highly successful and that going forward the PCG and PEB should consider expanding the role and reach of the programme ambassadors especially as two more are recruited. This may involve more collaboration with other large programmes implemented by other international development agencies.

Output Title	Current and potential groundwater users participate and influence the UPGro research and are presented with the findings
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Groundwater users engaging with researchers: / Number of stories where users have participated and influenced the methodology and results of the UPGro research (stories should highlight participation of women and of the poor)	At least 5 from the total stories collected, of which 20% are about women and 20% are about the poor.	4
Reporting of research progress and findings to water users: / Cumulative number of face-to-face events and activities that give feedback on the research progress, findings and practical implications to the groundwater users that are/were the target of the research.	5 in total (or at least 1 per consortium project)	Too early to judge progress. (Indicator to be revised see comments below)
Media coverage in UPGro countries: / Number of programmes or articles on UPGro work in local media (radio, newspapers, TV).	5	8 / (+15 international)

Key Points

Groundwater users engaging with researchers
Up to now four stories of groundwater users, who have participated and influenced the methodology and results of the UPGro research were recorded. These are as follows:
1. Residents of Dangesheta (Ethiopia) were involved in the siting new rain and river gauges, and identifying wells that were suitable to be monitored in the AMGRAF catalyst project.
2. In Niger, GroFutures engages with users through workshops and field research. Of particular note is the August 2016 a workshop at Abdou Moumouni University (UAM) of Niamey. Farmers including representatives from agricultural cooperatives (Coopérative périmètre irrigué in Maradi, Coopérative agricole in Gaya) were hosted on campus for the first time. They discussed agricultural use of water and specifically groundwater. The Groundwater Game was run with the purpose of helping all participants better understand the benefits of groundwater development for irrigation, the challenges of sharing a common resource, and the adverse environmental consequences arising from a lack of cooperation and unsustainable groundwater withdrawals. This engagement with users has influenced how the research team will examine current and projected groundwater withdrawals, as well as the fundamental socio-political context governing access to groundwater in this Sahelian border region with Nigeria.
3. TGroup has been working with Ward and Street communities to find the best sampling points in Dodowa, Ghana. Nothing can be done without their permission and the process of finding suitable sampling points emerges through interactions and relationship building between the researchers and the groundwater users.
4. Water users are helping to steer the fieldwork for the Hidden Crisis project. To date, 600 rural communities have been visited across the three countries: Ethiopia, Uganda and Malawi. In each community, groundwater users work with the research teams to carry out a series of tests on their water point. The community researchers provide valuable expertise on the optimal length of time for a test and the ‘tolerance levels’ for achieving a steady pump rate. The project then optimises the test to give maximum information for acceptable downtime within the community. Women from the water point committee in each community then work with the researchers to map out the water points across the village and record the history of performance and management of each water point. The contributions from the rural groundwater user community, many of whom are amongst the poorest within their countries, are being used to help define the second phase of the research.
Reporting of research progress and findings to water users
During the discussions we held at the annual review meeting it emerged that even though the programme is performing well against this output and is obviously making good progress in involving users to influence the UPGro research, it was not possible to record any progress against this indicator (i.e. 4.2).

We discussed the reasons for this and it emerged that the indicator for this year was probably misjudged and the milestone should have been pushed back to next year. This was a repeat of the problem we have seen and discussed in relation to output 1 and to a lesser extent output 2. Even though this should not be used to lower the scoring against this output, it still raises some valid concerns about the robustness and validity of the current logframe, which may benefit from a thorough review and perhaps some input from an M&E specialist.

Media coverage in the UPGro countries
In terms of media coverage, UPGro has exceeded the milestones set with eight media articles in the UPGro countries, plus 15 articles in the international media including professional magazines and broadsheet newspapers such as The Guardian and The Conversation.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A there were no recommendations against this output in the last annual review.

Recommendations

As per output 1 and 2 the milestones and indicators for this output should be revised, to ensure that they match the programme requirements and activities (To be completed by December 2016).

The PEB should also consider whether to request some ad-hoc input from a M&E specialist to ensure the fine-tuning of all indicators and milestones going forward (To be completed by December 2016).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers originally identified for UPGro include costs of equipment, consumables and workshops, and travel and subsistence. These have not changed since the programme was approved and NERC assess these as part of the grant review process to ensure costs are kept down.

The Moderating Panel for the consortium round scrutinised the requested costs of the consortium grant proposals and decided that the costs for each of the 5 projects awarded were fully justified, i.e. all the resources requested (e.g. staff time, equipment and field costs) were required to deliver the stated programme of work. Any significant variations to the project plans will have to be agreed by the PEB, who will take VfM into account.

Over the lifespan of the programme management costs are expected to be approximately 4% of the total cost and are an in kind contribution from NERC in addition to NERC’s cash contribution. This figure remains true.

VfM performance compared to the original VfM proposition in the business case

The original UPGro Business Case identified the following key elements of VfM:

- Leveraging of Research Council funds.
- Use of well-developed RCUK systems into which there has been considerable investment.
- Competitive research calls to identify and fund the highest quality research.
- Value for money guidance at the peer review and panel stages.
- Wired link between research and impact to ensure UPGro delivers benefits for poor people through research uptake in developing countries.

The VfM criteria have not changed since last year and remain the same as they were in the original Business Case. In terms of performance, the UPGro continues to deliver good results against all criteria.

The programme is still leveraging resources from both the Natural Environment Research Council (NERC) and the Economic and Social Research Council (ESRC), which are DFID’s co-funding partners and continue to provide additional pro-bono resources to ensure the effective and smooth management of all activities. This is particularly relevant for the administration and management of all research calls and associated activities, such as peer reviewing of proposals, financial management and supervision of contracting arrangements with all implementing partners. The linkages between research and impact are delivered through a joint effort between DFID, NERC and ESRC and all impact strategy plans agreed at the Programme Executive Board (PEB) level.

Furthermore, the programme aims to deliver strong value for money against the following five criteria of: economy, efficiency, effectiveness, cost-effectiveness and equity. This is currently achieved as follows:

- NERC exerts pressure for economy (minimising input costs) through close scrutiny of budgeted and actual costs of each grant.  Where it is possible to identify unit costs that are comparable between projects (for example, in travel budgets or day rates of senior staff), NERC provides guidance on what is reasonable and what is excessive.  NERC reviews budgets and expenditures (at application and peer review) and will ask grant holders to reduce high costs.
- Efficiency (maximising research outputs in relationship to budget inputs) is a function of ensuring that contracted research is of high quality.  The heavily over-subscribed nature of the scheme; due diligence assessment of the delivery capacity of contracted researchers; and clarity (between DFID, ESRC and NERC) and transparency (between NERC and applicants) regarding the purpose and priorities of the UPGro programme all help to ensure that the NERC can choose the strongest and most relevant proposals from amongst those submitted.
- Effectiveness (the translation of research outputs into outcome) and cost-effectiveness (the ratio between inputs and impact) is hard to judge for this phase at this point.  However, evaluations of the impact of the UPGro programme research during earlier phases suggests that this research has been and is likely to still be effective in (i) helping to shape understanding of groundwater issues and (ii) exerting a positive influence upon practice (programmes and policies).
- Since the Business Case was approved, DFID has introduced equity as a fourth dimension of its approach to framing VfM.  UPGro’s strategy to include non-UK researchers from Sub-Saharan countries, have helped to ensure a good performance on this dimension of VfM.

Assessment of whether the programme continues to represent value for money

This programme continues to deliver good VfM. The use of the robust RCUK peer review systems for competitive research calls has delivered high quality research, demonstrated by the emerging outputs of the catalyst research projects and the calibre of the consortium research teams. The costs of the consortium projects were scrutinised as part of the moderating panels.

Challenges in managing the admin of the programme occurred due to the additional administration needed to implement the changes in the due diligence process requested by DFID. NERC are now exploring how to minimise the additional work for both NERC and the project teams of setting up grants in overseas organisations, while still ensuring appropriate due diligence checks are in place. Strengthened due diligence should enhance VfM by minimising the potential for misuse of funds to the absolute minimal.

The management of the programme presents some innovative elements and has been structured with the aim of delivering the highest possible level of outputs, whilst keeping costs down and thus ensuring high VfM. This was inspired partly by lessons learned from other programmes co-funded by DFID, NERC and ESRC, which involved a more structured and cost-heavy management set-up. The model used for UPGro is virtually cost free, because the members of the Programme Co-ordination Group (PCG) and the Programme Executive Board (PEB) do not charge any direct costs to the programme. The main costed element is related to the Knowledge Broker (KB) services, which are provided by SKAT (a Swiss consultancy outfit). The total costs for KB services are approximately £43,000 per year, which is significantly lower than those incurred by other programmes of a similar size and scope. This in itself represents good VfM, although the rates in £/day (at £375-500 per day) and overheads (at £117 per day) are mostly in line with those paid by DFID on average across the board. The only point to be raised in this area is related to the number of days that we are currently contracting the KB services for, and whether these could or should be increased to ensure a closer level of involvement with programme activities, especially in regard of monitoring and evaluation. This is something that should be discussed at the next PEB meeting in February 2017.

A programme coordination group has been created to integrate the 5 consortia to ensure that the outcomes of the programme are greater than the sum of the parts, and to enable efficient engagement with the funders and the knowledge broker, enhancing the link between research and impact. Funding for the PCG is through amendments to the existing grants, minimising the administration for both the funders and project teams

At this phase of the programme with commissioning largely completed, it can be safely concluded that the programme continues to deliver VfM and is on track to meet its output targets for the anticipated level of funding.  VfM metrics will shift over the coming years as the volume of outputs increases and it becomes possible to examine progress towards higher-level outcome and impact objectives.  Going forward it is expected that the highest VfM (and return on research investments) will be delivered at this level.

Quality of financial management

NERC ensures good financial management at the level of individual grants through a combination of pre-conditions imposed at procurement stage (institutions receiving grants which are not already eligible for RCUK funding have to have passed the RCUK recognition process and its due diligence checks) and ongoing annual reporting requirements, as set out in the RCUK-standard terms and conditions attached to grant awards.

NERC contracts are concluded with a lead institution: this institution assumes responsibility for ensuring good financial management (and avoiding project-level under- or over-spend) through any ‘sub-contracts’ with other project partners.  In addition, a range of processes and safeguards are in place to ensure value for money is assured throughout the application, review and award contracting process:

- At the application stage value for money (VFM) is a stated assessment criterion in the scheme specification and applicants are required fully cost all elements of their proposed research and provide detailed justification for each item of expenditure.  Peer reviewers and panel assessors are asked to consider VFM as part of the grant assessment and is one of the factors which panel members consider when making final funding recommendations.
- At the award contract stage all costs are subject to detailed scrutiny by the NERC Secretariat.  Any unjustified or excessive costs may be removed from the budget.
- Grants are only held by institutions which have passed RCUK recognition processes, which include checks on financial management and capacities. Details of the information organisations are required to provide as part of the Due Diligence process.
- Grants are contracted with RCUK standard T&Cs which include financial management and reporting requirements. In addition, the RCUK wide Funding Assurance Programme conducts checks at an institutional level (see NERC’s annual report and accounts - http://www.nerc.ac.uk/latest/publications/strategycorporate/annualreport/annualreport/ ).
- Where awards have contracted project partners the NERC contract is with the host institution. The host institution will set up ‘sub-contracts’ with any partner organisation. The host organisation will thus take the financial responsibility of tracking partner spend and the risk of any overspend or default.

Finally, following a review of the programme spending profile and performance, it was observed that up to the date of this annual review, all payments and disbursements were made in accordance with the original schedule and the spending profile is reflecting the original forecasts. Over the past couple of years there have been some challenges with ensuring the sub-contracting of second tier implementing partners satisfied DFID and RCUK strict standards and this caused some delays. However these issues have now been resolved and as already outlined the programme is now meeting agreed spending targets and forecasts.

Date of last narrative financial report	20/02/2016
Date of last audited annual statement	Not required NERC is a HMG institution

E: RISK (½ page)

Overall risk rating: the risk level for the programme was reviewed in accordance with the latest Smart Rules guidance on risk, which now spreads risk levels across four levels and six categories and was assessed as Moderate.[20] The table below provides a description of how we assessed risk against each of the six categories now included in the Smart Rules:
[20] Revised risk levels under the SMART rules are: minor, moderate, major, severe.

Risk category	Risk Analysis and description	Risk level
External context	The external context for this project is quite favourable and the broader area of research well developed and mature. Conducting research in country specific contexts will always entail a degree of risk, which will vary from country to country. The programme is operating in volatile countries (e.g. Nigeria, Niger Ethiopia), which present some challenges and could affect the delivery of activities for some projects. This issue is being tackled at two levels: i) the project level where each consortium is following the security procedures and ‘duty of care’ guidelines employed by each research institution and ii) the programme level where the PEB has revised the risk associated with each proposal and periodically reviews any changes in circumstances that may affect the work and/or safety of any of the research team involved.	Moderate
Delivery	The risk related to the delivery chain for this programme is low. This is mostly due to the streamlined and simple structure of the programme, which involves a first layer of consortia (5 in total) that are led by at least one UK or European research institution and a second layer of sub-contracted service providers/institutions, that are mostly based in SSA. Because of the contracting arrangements employed by NERC all second layer delivery partners and service providers are accounted for and are requested to sign contracts that meet RCUK and DFID standards. Non-UK or other unrecognised institutions funded under such arrangements are required to gain full RCUK recognition before contracts can be issued and funding can commence and full due diligence checks are in place to complete these checks. In order to ensure compliance, NERC operates a number of sanctions against institutions or individuals that fail to comply with the terms and conditions of their grants. The NERC risk assessment strategy also recognises this as an important ssue in the current research funding environment.	Moderate
Operational	Ensuring highlevels of transparency and strict standards with the sub-contracting of second tier implementing partners has resulted in low levels of risk in the delivery category but has had an impact on the programme operations both in terms of delays and morale among consortium members. We have now developed an approach to overcome this challenge and ensure mitigation of any impacts on the programme. More specifically, we have realised that we need to ensure the project PIs build sufficient time into proposals to allow for the contracting of second tier partners and contractors. The Research Councils are also in discussion with Higher Education Institutions to improve collaborative working practice that ensure better financial management of ODA grants and sub-contracts.	Major
Safeguards	UPGro is a research programme and as such it involves intrinsically low levels of risk in this category. Its subject matter which aims to attain environmental sustainability in the use and management of water resources is a further guarantee that all the standards environmental safeguards principles are adhered to. Social and environmental safeguards are also guaranteed through the manadatory principles that all UK and EU based research instutions must follow in order to retain their ISO accreditations and respect EU funding rules.	Minor
Fiduciary	The fiduciary risk associated with the contracting of both layers of suppliers and partners is managed by NERC in accordance with the strict rules set by RCUK and has been recently revised in full to ensure it satisfies DFID due diligence requirements. To this date there have been no reported issues in this area and NERC remains confident of its level of oversight and ability to intervene in case of any repoted incidents.	Moderate
Reputational	Reputational risk for this programme is very low. All research proposals have been thoroughy reviewed and scrutinised in line wit the strict standards imposed by the UK Research Councils and are implemented by internationally recognised research institutions. The subject matter of the research is uncontroversial and there is very little scope to generate outputs that may have an adverse impact on any specific group of stakeholders in partner countries. On the contrary, the research funded under UPGro is expected to deliver substantial benefits to government agencies and local communities alike, by producing evidence that can significantly improve the management and availability of water resources for economic and social development purposes.	Minor

Overview of programme risk
Through peer review and expert advice the NERC only give grants to institutions recognised as bona-fide research institutions through due diligence checks, and on the condition that those institutions and award holders are willing to adhere to NERC terms and conditions.

Normally, NERC Research grants are only given to UK institutions.  Non-UK or other unrecognised institutions funded under this scheme are required to gain full RCUK recognition before contracts can be issued and funding can commence and full due diligence checks are in place to complete these checks. In order to ensure compliance, NERC operates a number of sanctions against institutions or individuals that fail to comply with the terms and conditions of their grants. The NERC risk assessment strategy recognises this research funding environment.

Outstanding actions from risk assessment

On-going learning from other programmes to strengthen research uptake and participation of southern partners.

PEB needs to agree and programme most effective use of remaining funds, including the budget for the independent mid-term review.

The programme will need to ensure that its indicators, metrics, milestone sand associated definitions are reviewed to ensure that they are fit to enable proper monitoring of progress absent all outputs.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The initial delays in awarding the consortia due to changes in due diligence requirements, delayed the signing of the grants by 5-6 months. However the consortia are now on track to deliver within planned timescales. Spending levels are now back on track and in line with agreed schedule.

Performance of partnership (s)
UPGro is co-founded by NERC and ESRC who provide contributions of £2 million each to the total £12m programme. NERC provides the Secretariat in kind and is responsible in major part for the implementation. The programme is overseen by a Programme Executive Board (PEB), chaired by Professor Declan Conway (LSE). Skat Foundation are contracted to perform the Knowledge Broker role.

In terms of managing and administering the programme UPGro follows a clear and structured division of labour between its funding partners. The NERC Secretariat manages the portfolio of funded scheme awards. The same team manage communication with award holders right through from the application stage, contracting successful awards and then throughout the course of the funded project.  As such good working relationships have been established and continue with our community of award holders.

All live projects are required to submit biannual reports via the knowledge broker.  These report on project progress and provide an opportunity to highlight emerging findings and flag up where there has been evidence of research impact or uptake.  The NERC team pick up on any issues which require action from the reports and raise any significant impact stories to our Communications team and DFID.

Award holders are also contracted “to attend any conferences, seminars or workshops that the scheme funders might arrange for the purpose of dissemination of the research” and “to develop their impact strategy for their project in consultation with the programme funders for the benefit of both academic and non-academic audiences.”

The Secretariat is also responsible for dealing with ad hoc issues raised by award holders.  The most common requests are for short no-cost extensions to the project end date.  Other common project amendment requests relate to virements within the research budget.

The NERC finance team is responsible for the financial management and oversight of scheme awards.  Where no-cost extensions are awarded this does not impact upon the profiling of award spend or DFID payments.  In the case of a no-cost extension, the award profile remains the same: the extension affects the final reconciliation payment only which will be delayed according to the amount of the extension.  DFID payments will remain in line with the original profile; NERC will manage the slight variation in final reconciliation payments within its own accounting systems.

Asset monitoring and control
N/A the programme does not have any material assets that require monitoring.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable there were not changes on any specific partnership principles. A detailed description of the functioning of the partnership between DFID, NERC and ESRC has been provided in the relevant sections above.

It should also be noted that UPGro is a multi-country programme and does not provide funding through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The importance of water security remains unchanged since the initial design of UPGro and the challenges are recognised in the Global Goals. It is reasonable to assume that the benefits of UPGro work will increase over time, as research findings emerge and are taken up by implementing partners.

Uptake will be tracked as part of the logframe reporting over the lifetime of the programme. The performance of the catalyst projects and dissemination of emerging results including some media uptake, awards and use in national planning provides an assurance of quality of UPGro research and interest to key audiences.

The revision of the logframe with the Knowledge Broker and research consortium allowed updating of the impact indicators and output/outcome levels in line with a better understanding of the planned main research phase. This provides a stronger basis for ongoing M&E. This ongoing process will be supported by the independent mid-term review, which is currently being discussed and planned by the PEB and should take place at some point during the next FY (2017-18).

Furthermore, since the last annual review the UPGro Programme Coordination Group (PCG) has produced and published a “Knowledge Exchange Strategy” for the programme. This strategy builds on the PCG Programme Management Plan and incorporates the four priority themes for the PCG: i) science integration, ii) knowledge exchange, iii) capacity strengthening and iv) data management.

The Knowledge Exchange Strategy is also divided into three key activity areas: a) Internal Knowledge Exchange (incorporating science integration and capacity strengthening), b) External Knowledge Exchange, and c) Data Exchange and will be accompanied by annual work plans, which will outline and cost a detailed set of activities for each area.

The PCG will be working closely with the UPGro Knowledge Broker, the consortia research teams, the UPGro Ambassadors, and the National Geoscience Data Centre to achieve the aims and objectives defined in this strategy.

On gender issues, the programme has a clear potential to achieve good results and generate positive change. An example of this can be seen in the Hidden Crisis project, which involves women from water point committees in each community/village in the process of mapping out the water points across the village and record the history of performance and management of each water point. However, so far evidence of such examples is weak and sparse and the programme will need to improve the way in which he monitors impact of programme activities on gender issues. This should be underpinned by a clear action plan, which should also help the refining of indicators on gender disaggregated data under output 2.

Monitoring progress throughout the review period

Over the past year the Knowledge Broker, in consultation with the consortium, has led a revision of the UPGro logframe and data collation processes. This has been discussed and approved by the PEB and based on a trial reporting process run with the catalyst projects last year. The DFID SRO led this review with input from NERC, ESRC and the Knowledge Broker, who provided a report against the revised logframe.

This Annual review has been shared with NERC and ESRC and will be discussed at the next PEB meeting in January 2017.