Annual Review – post April 2018

Title: Science for Humanitarian Emergencies and Resilience (SHEAR)
Programme Value £ (full life): £17.87m / (+£6m from NERC)		Review Date: November 2018
Programme Code: 201884	Start Date: 10 December 2014	End Date: 30 September 2020

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	A	A	A	A
Risk Rating	M	M	Moderate	Moderate

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201884/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201884/documents/

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The SHEAR programme supports improved disaster resilience and humanitarian response by advancing the monitoring, assessment and prediction of natural hazards and risks across Sub-Saharan Africa and South Asia, and through working with users, brings this into use in reducing the impacts of disasters. SHEAR aims to catalyse earlier and more effective action to respond to imminent natural hazards and enable greater and more effective investment in disaster resilience and preparedness. SHEAR has three ‘pillars’: SHEAR Applications, SHEAR Research, and SHEAR Applied & Innovation (see below). The programme also has a knowledge broker (KB) and a research consortium coordination team (CCT) to drive better learning, information exchange and coherence between the different research projects and activities. A large component of the programme is a partnership between DFID and the Natural Environment Research Council (NERC). More information on the programme can be found at http://www.shear.org.uk.

DFID is providing £17.87 million over five years to enable greater and more effective investment in disaster resilience and earlier action to respond to imminent natural hazards by providing decision makers with enhanced risk mapping and analyses, and more reliable warning systems. The programme focuses on flood and drought risk monitoring and warning systems in sub-Saharan Africa and multi-hazard risk assessment and monitoring across South Asia, with a focus on the interaction of ‘cascading hazards’ such as landslides, which can be triggered by heavy rainfall. It also supports work on more global early warning and risk assessment systems such as El Nino. It covers four areas: disaster risk assessment (mapping and analyses), sub-seasonal to seasonal forecasting, disaster risk monitoring, and the integration of these into practical decision making. The three principal pillars comprise:

1. SHEAR Research: working with the NERC to support world-leading international research to: improve the underpinning understanding of risk in DFID priority countries to inform disaster preparedness and resilience; enhance the reliability of seasonal (up to 6 months ahead) forecasts to strengthen early warning systems; and demonstrate the practical application of these within decision making on preparedness and resilience. DFID is providing £7.5 million to support work in Africa and South Asia with additional funding from NERC of £6 million. This partnership has secured sizeable in-kind contributions, including leveraging the Natural Environment Research Council’s existing project portfolio and programme commissioning, contracting and management capability.
2. SHEAR Applied and Innovation (SHEAR A&I) Fund: to support a portfolio of targeted, rapid-response relevant projects to seize opportunities to utilise emerging technologies and respond to evolving user needs in knowledge and tools to support disaster preparedness and resilience, with a facility to provide knowledge management, coordination and M&E activities for SHEAR. Following the 2015 Nepal earthquake and the onset of one of the strongest El Niño events on record, the Fund was substantially drawn down to fund research in these areas and as a result, DFID replenished the fund, giving a total Fund allocation of approximately £7.5 M.
3. SHEAR Applications (SHEAR Apps): partnering with the Global Facility for Disaster Reduction and Recovery (GFDRR) at the World Bank to deliver an innovative toolkit of new open data and tools to support preparedness and resilience through a competitive challenge fund (£2.5 million). This partnership leverages GFDRR’s on-the-ground expertise and networks to ensure that the outputs are demand-led and deliver value for money through building upon existing projects and leveraging contributions. It is delivered through a Challenge Fund (CF).

In implementing SHEAR, DFID works through trusted partners with strong delivery and oversight capability. Within DFID, RED’s expertise in commissioning high quality science is brought together with CHASE and Country Offices’ operational experience to ensure that the science delivers tangible development impact on the ground. SHEAR aims to leverage sizeable financial and in-kind contributions, including computational resources and technical expertise, and the programme has worked to coordinate with other actors and donors to deliver greater collective impact.

Summary supporting narrative for the overall score in this review (1/2 page)

The programme is performing well and meeting, if not exceeding, expectations. Decision-relevant science is being advanced and applied to enable improved humanitarian and development action regarding natural disasters and extreme events. In the reporting period, all projects awarded under the first and major round of the Challenge Fund were completed, with many successful results. The SHEAR consortia projects continue to make good progress. Projects under the Disaster Risk Financing call are now fully into implementation; and the 11 projects under the Catalytic Grant call are now mobilized. The responsive facility element of SHEAR Applied & Innovation continues to generate outputs that are well received.

# Illustrative examples of SHEAR Value added risk Information for Decision Making

The open-source, DIY remote weather stations project by International Water Management Institute (IWMI) in Sri Lanka to help improve flood resilience is an example of a successful SHEAR Apps Challenge Fund project with good initial uptake and where prospects of wider replication are very promising. The evaluation on the project noted it had: demonstrated adaptive learning, management and improvement during implementation; established or strengthened partnerships with six local organizations who co-developed the tool; conducted gender analysis identified gaps that were communicated to government; trained 144 targeted beneficiaries and leveraged over $700,000 in additional financing. Decision-makers in the local government Irrigation Department are now regularly accessing the information from the devices. In addition, officials in the Irrigation Department Headquarters, many regional offices, the Meteorology Department, Lanka Rainwater Harvesting Forum and its funder USAID, the Coordinating Secretariat for Science, Technology and Innovation (COSTI), the University of Moratuwa, and A&T Labs are investing in the further development and use of the approach.

Volcanic risk information through films. The University of Bristol created a total of 19 films under CF support. First phase films were scientific films to educate people on volcanic hazard and its impacts; the second phase focused on sharing stories and experiences from people and communities affected by volcanoes. The films have already been used by over 50 websites; and have also been ‘linked to’ multiple times on Twitter and by monitoring institutions. (This project also is being scaled by another donor, providing additional CF leveraging of USD $200,000.) Examples include:
- During the December 2017 Mount Agung crisis on Bali, Indonesia, the CF films were used frequently on social media, and by a popular risk communicator on Twitter, who reported that on sharing the CF films, she received fewer questions because the type of questions she most frequently received were addressed in the films.
- Following the recent lava activity on Mont Pelée, Martinque (French West Indies), in only one month there have been over 19,000 views of the lava hazard and impact films in French, based on the local Observatory alerting the community to the films.
- In just four days after the Fuego eruption in Guatemala, the Spanish language films on pyroclastic flows have had 1.7 million views on social media.
These illustrate effective delivery of CF risk information, via the medium of film, for use on the ground in times of disaster to help reduce risk for affected populations.

The French Research Institute for Development (IRD) successfully piloted its Urban Flood Early Warning System based on a Cell Phone Network in Burkina Faso. The Burkina Faso National Weather Service (ANAM) has now integrated the tool into its work. IRD also conducted a vulnerability analysis in the country. Taken together, these tools are helping ANAM make timely decisions, provide targeted early warning and prioritize rescue efforts to those most in need. The tool is also utilised in the work of the national Committee for Monitoring Extreme Hydro-meteorological Events. The cell phone operator has signed a formal agreement with ANAM and IRD to collaborate on the Rain Cell App beyond this project, enhancing prospects of sustainability.

New York University (NYU) developed an extreme weather events communication toolkit, which included a strong gender focus[1] so that all community members can participate in accessing and sharing important knowledge. The toolkit was tested and implemented in the Philippines and Bangladesh. It has been adopted by emergency preparedness agencies and action, such as the Cyclone Preparedness Programme (CPP) of the government of Bangladesh and the Office of Civil Defence (OCD) in the Philippines. In addition, the Philippines Department of Education is adopting a version of the toolkit as part of its science and environment curriculum. CPP requested adaptation and translation of the toolkit for use in Cox’s Bazaar, where hundreds of thousands of Rohingya refugees are encamped in denuded hilly areas that are prone to dangerous floods and mudslides. Funding has been identified for this action – evidence of further scaling and leverage of the initial project.
[1] https://docs.wixstatic.com/ugd/0c6e1a_5e51e5e9702843c0995f75eb1d29b433.pdf

The Deltares CF project successfully incorporated one of its risk information tools into a local university in Tanzania, Ardhi University. It credits a process of knowledge co-creation with local partners for its ability to achieve this result. Specifically, Deltares created a course curriculum around a customized critical infrastructure exercise, modelled on a local game, called Circle Bao. There are plans within the university to modify the tool and curriculum to use for other hazards, as well as a plan to continue working with the university to establish a resilience academy in which this curriculum and tool will play a part. The Deltares project credits the GFDRR CF team for helping to develop on-the-ground partnerships and catalysing funds for the continued development of this tool, successfully adopted by local systems in Tanzania.

The flood predictive capability of the Global Hazard Map (GHM) produced by the ForPAC project was found to be very useful during a recent flood events across Kenya in March-April 2018 and in coastal Kenya in October 2018. ICPAC (Climate Prediction and Application Centre) and Kenya Meteorological Department (KMD) highlighted that the GHM was useful in indicating possible floods scenarios in Mombasa 5 days beforehand, which KMD then used to issue an advisory. The GHM captured the event well.

Production of Monthly Climate Outlooks.  SHEAR has funded the continued production and improvement of monthly bulletins on extreme weather to Humanitarian actors.  Improvements were made to the scientific underpinning - to strengthen the reliability of the forecasts - and the presentation of the information was enhanced to be more tailored, impact-oriented and actionable for decision-makers.  This involved a strong partnership between RED and CHASE within DFID, and with the UK Met Office and Reading University.   The support has been instrumental for layering weather information over other risk data to identify the humanitarian risk in contexts of concern and help decision-making on whether to issue specific alerts in the monthly Humanitarian Early Warning Note (HEWN).  The HEWN has a wide distribution across DFID Country offices and beyond to a range of international actors, and the Climate Outlooks are recognised as an important source of reliable seasonal forecasts by HEWN recipients.

Complementing this support SHEAR has also funded Reading University to provide historical analysis of impacts of analogous El Niño events to inform appropriate planning and early action ahead of the emerging 2018/19 El Niño. The report has been shared externally, including with the Global ENSO Analysis Cell, mandated by the UN to analyse the impact of any likely El Niño event and coordinate preparedness and response interventions. This has enhanced shared understanding with DFID partners of potential impact, contributing to better coordination and action.

Gender
In multiple Challenge Fund projects the teams have worked to incorporate gender into their project planning. An example is the New York University (NYU) project on enabling institutions to manage storm surge risks. The project produced a paper exploring gender gaps related to natural disasters in general and how the project could potentially tackle some of those these. At an operational level, in the Philippines, project workshops included segments where participants practiced crafting messages that were contextualized and tailored to women (including as heads of household) in the community. In Bangladesh, workshops were conducted specifically with female community leaders and also so that a panel of women could consider how the current emergency response program did not consider women's needs, especially regarding the state of evacuation centres. This led to recommendations for practical improvements to the operation and set-up of the cyclone shelters, such as security measures, a special partitioned area, and separate facilities. These types of discussion were then built into workshop design elements of the overall communication toolkit developed by the project, for use by others elsewhere. Lastly the project interviewed women survivors of recent storm surge events. These were digitally recorded and put online[2], to help increase understanding of the pathways by which women are vulnerable to extreme weather.
[2] https://www.environmental-communication.space/digitalnarratives

Another example is the IWMI project on open-source mobile weather stations for flood resilience. IWMI examined a sample of four out of the eight villages that were affected by severe flooding in December 2014 in Anuradhapura. The analysis identified a number of gender specific issues in the affected populations downstream from project reservoirs; and in discussion with the communities considered how timing and content of warning messaging could be improved. These findings were then communicated to local and national Government of Sri Lanka counterparts.

Recommendations for the year ahead (1/2 page)

Resources are potentially available to explore and deliver more synthesis/dissemination/uptake. Consider appropriate blend of actions to achieve this, such as through a NERC synthesis research call and additional KB activities (PEB by April 2019)

Consortia Projects to pay explicit attention/revalidating Pathways to Impact statements and associated co-production processes. Share experience more widely, including with Catalyst grants to help strengthen enhanced delivery on respective pathways (CCT by April 2019).

KB work has a base platform of planning documents to deliver on its mandate. These need refinement and the KB needs to accelerate actual implementation to be well positioned/ready for timely action, for example when clusters of papers are published/come on-stream.

KB to explore how to better profile existing gender related work and strengthen proactive effort and reporting by the Research Consortia, Catalyst and DRF projects.

Explore options and partnerships to institutionalise the monthly Climate Outlooks for HEWN (DFID, by Sept 2019)

Agree with DFID Management an approach to managing, as the programme enters its final period, the balance of retaining funds for reactive flexibility versus proactive deployment and achieving full budget utilisation. (DFID, by July 2019)

Logframe review and reporting:
- Review milestone targets for next year, refining relevant indicators if necessary (by March 2019)
- Programme to improve systematic reporting on partnerships and co-production, including refined indicators and targets for increased clarity if required. (PEB/KB by March 2019)
- SHEAR Consortium Coordination Team (CCT) to ensure adequate attention given to ensuring ECR presentations in external fora (ongoing).

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Improved understanding of risk and more reliable predictions of hazards like floods, droughts and landslides across South Asia and Sub Saharan Africa (or other regions)
Output number per LF		1		Output Score		A
Impact weighting (%):		40		Impact weighting % revised since last AR?		Y(↑*)
Indicator(s)			Milestone(s) for this review		Progress
1.1 Advances in risk assessment science, monitoring and forecasting: new methods, more comprehensive assessments and increased robustness and reliability;			5 articles submitted and 5 new working papers (in addition to the 2017 milestone).		Exceeded / 11 articles/working papers: / FATHUM (1), / Landslide-Evo (3) / Mitigating basis risk in weather index-based crop insurance (1 article) / DRiSL (1), / Landslip (2), / ForPAc (3)
1.2 Improved understanding of (multi) hazard risk and response in two regions (risk / response maps, (multi-) hazard risk assessments).			At least 5 working papers (WP) describing new / improved approaches to (multi-) hazard risk assessment and responses in 2 regions.		Met / 6 working papers: / Mitigating basis risk in weather index-based crop insurance (1 WP in progress), / ForPAc (1) / EACDS SRF (2) / FloodFinJava (1 in progress) / DRiSL (1 in progress)

* Outputs were consolidated from 4 to 3 so relative weighting has increased.

The programme continues to make good progress in production of academic and technical papers. This is principally happening through the ongoing work of the main consortia projects (LANDSLIP, Landslide Evo, ForPAC and FATHUM)[3], but also more recently through the Disasters Risk Financing cluster of projects now that these are operational (see below for full listing of these projects). An example from ForPAC is the Kilavi, M et al paper submitted to the journal ‘Atmosphere’ on ‘Extreme rainfall and flooding over central Kenya including Nairobi city during the 'long rain' season 2018: Causes, predictability and potential for early warning and actions’.
[3] See http://www.shear.org.uk/research/home.html for more information on these projects

Under SHEAR Applied and Innovations component, further work has been advanced around scientifically based forecast information on climate and weather patterns to assist better programming and decision making by DFID and partners. This is being well received by the Humanitarian Early Warning Network (HEWN) in particular in DFID participates. Examples include:

- Further technical improvement to production and presentation of the Monthly Regional Climate Outlook Notes, including through the incorporation of additional seasonal forecasting models (European Centre for Medium-range Weather Forecasts (ECMWF) and Meteo-France) so as to enhance the robustness of forecasts and decision-relevance of the information.
- El Nino 2018-19 Impact Analysis report - this has provided a stand-alone analysis of the potential impact of 2018-2019 El Niño development based on historical analysis of analogous El Nino events (building on and enhancing the analytical framework applied in 2015 for the 2015/16 El Niño Impact report and also learning from the Monthly Climate Notes process).
- Finale Event for the suite of 14 studies on the impacts of the 2015/2016 El Niño. Through this event, in addition to the formal papers that will be published in due course, the researchers have agreed to prepare a set of 4 synthesis papers to facilitate user uptake[4]
  [4] This will be: 1) Developing a framework for conceptually situating El Niño resilience research — a tool for researchers and practitioners; 2) Socio-ecological resilience of tropical smallholder agricultural systems; 3) Ecosystem-based adaptation and resilience to El Niño climate extremes; 4) Operational research assessment tool for organic resources (ORATOR): application across small-scale cropping and animal-based systems from the El Niño programme

Disaster Risk Financing – Innovation call - projects now operational (see here for more details):
- Coastal Ecosystem Recovery Financing for the Future (CERFF): developing insurance products to enhance response and recovery from tropical cyclones (Global)
- DRiSL: The Drought Risk finance Science Laboratory (Global; test sites in Pakistan, Zimbabwe, Madagascar)
- Financial planning for natural disasters: the case of flooding risk in Central Java
- Improving the Role of Information Systems in Anticipatory Disaster Risk Reduction (IRIS) (Global)
- Integrated Threshold Development for Parametric Insurance Solutions for Guangdong Province China (INPAIS)
- Mitigating basis risk in weather index-based crop insurance: harnessing models and big data to enable climate-resilient agriculture in India
- Satellite data for Weather Index Insurance-AgricuLtural EaRly warning system (SatWIN-ALERT) (Africa)

Catalyst grants
Another major element of progress this year is that the SHEAR catalyst grants, designed to complement the existing four main research consortia projects, have been awarded and mobilised, including an introductory and cross-grant familiarisation workshop to enable linkages and synergies to be developed from the outset. These projects focus on weather-related hazards (such as floods, droughts and heatwaves) and the events weather can trigger (such as landslides) and improving resilience to these in sub-Saharan Africa and South Asia. The awarded grants are as follows (more project details can be found here):

Accounting for boulders in Landslide-flood Disaster Evaluation and Resilience (BOULDER)
- Climate service for resilience to overheating risk in Colombo, Sri Lanka: a multi-scale mapping approach (COSMA)
- Compound flooding from tropical cyclone-induced sea surge and precipitation in Sri Lanka (C-FLOOD)
- Connect4 water resilience: connecting water resources, communities, drought and flood hazards, and governance across four countries in the Limpopo basin
- Improving Preparedness to Agro-Climatic Extremes in Malawi (IPACE-Malawi)
- National-scale Impact-based forecasting of Flood Risk in Uganda (NIMFRU)
- Next generation flood hazard mapping for the African continent at hyper-resolution (HYFLOOD)
- Nowcasting FLood Impacts of Convective storms in the Sahel (NFLICS)
- Predicting Impacts of Cyclones in South-East Africa (PICSEA)
- Towards resilience to pluvial flood events
- Web-based natural dam-burst flood hazard Assessment and foreCasting sysTem (WeACT)

Lessons identified this year, and recommendations for the year ahead linked to this output

Adequate support needs to be provided to in-country partners to play a fuller role the academic aspects of the project and in developing and leading academic papers and articles. Projects have already made a good start by introducing closer line management and integration of the team through weekly skype calls etc to discuss case study details, scientific developments and progress against deliverables.

Adaptive management is often required as implementation unfolds: for example on the LANDSLIP project, the quality and quantity of data already available in India were less than had been thought when starting the project, requiring strategies to be developed to manage this and still enable process of the Landslide Early Warning system.

Output Title	More effective application and utilisation of risk assessments and predictions / forecasts by stakeholders at various levels from local to regional.
Output number per LF		2		Output Score		A+
Impact weighting (%):		30		Impact weighting % revised since last AR?		Y/(↑*)
Indicator(s)			Milestone(s) for this review		Progress
2.1 New toolkit of demand-led, open data, tools and products for resilience, preparedness, response and recovery;			(a) At least 20 new / improved data/tools/products for resilience, preparedness, response and recovery; / (b) At least (25%) of data/products are free/open data compliant.		(a) Exceeded. / The Challenge Fund supported 33 new/improved risk information tools for resilience, preparedness, response and recovery. / Mitigating basis risk in weather index-based crop insurance in India (x1) / SatWIN ALERT (x2) / ForPAc (x1) / Landslip (x1) / Nepal Earthquake – Landslide project (Durham) (x1) / (b) Exceeded. / 100% of the risk information tools supported by the Challenge Fund are free and available on open platforms. / Data from Consortia projects and DFID direct funded projects will be made available in due course
2.2 Increased application of data, products and tools in practice by target beneficiary users			(b) At least 5 case studies identifiying potential users and demand for new tools and products and plan for engaging.		Exceeded. / Mitigating basis risk in weather index-based crop insurance in India (x1) / SatWIN ALERT (x2) / Landslide-EVO (x2) / ForPAc (x2) / Landslip (x1) / All 18 Challenge Fund implementers, covering both Round 1 and 2, identified potential users and demand for new tools and products, as well as developed plans for engaging.
2.3 new evidence on what works in developing demand-led data, tools and products to support effective risk assessments.			at least 5 working papers on best practice with emerging guidance		Met. / Round 2 of the Challenge Fund produced x 3 papers on data schema and data for multi-hazard, global exposure and vulnerability functions (& Round 1 also published two case study performance evaluations on remote weather stations and drought risk visualization tools). / ● Landslide-EVO (x1) / ● ForPAc (x1)

* Outputs were consolidated from 4 to 3 so relative weighting has increased.
Performance under this output has been strong. The Challenge Fund (CF) has demonstrated delivery on its aim to connect innovation to local contexts to help better identify changing climate and disaster risk and enable more effective decision-making to build resilience. All 15 projects in Round 1 were completed by April 30, 2018. Within this cohort a phased VfM and performance based approach was applied with 7 of the more successful projects being given a Phase 2 grant and finally 3 of the most successful of these 7 projects given limited sustainability awards to support the last mile of risk information tool uptake and influence within targeted local systems.

The CF Round 2 competition focused more on data management for a framework that enables a multii-hazard view of risk. 3 grants were awarded, concerning:
- data schema and data for multi-hazard database (British Geological Survey)
- data schema and data for global exposure database (Global Earthquake Model Foundation)
- data schema and data for a global database of vulnerability functions (University College London Consultants)

After initial scoping, testing and development of the ‘pilot’ schema(s) and reports, a workshop in Tanzania was then held, including government decision-makers from Tanzania, Uganda, Malawi, Mozambique and Nepal, and representatives from local academic institutions, as well as the members of the 3 teams. The workshop explored proof of concept including populating the schemas with data for Tanzania and other countries in East Africa. Participants discussed possible use cases and future extensions of the results of the three CF pilots, with planning and policy making emerging as a core priority. Participants also indicated that they would like to contribute datasets to the databases, which is indicative of the value that members of the community see in the work. To further explore interest and demand of the global disaster risk management community in the data schema, a side event was held at the 2018 Understanding Risk Conference in Mexico City - attended by 80 representatives of the public, private, academic and NGO community. The provided additional insight regarding requirements to reach global coverage, and to ensure that the data schemas developed under the Challenge Fund become the standard in disaster risk assessment and reduction.

Based on such consultative and participatory work, a data explorer visualisation tool for the data schema, is currently under development, and can be accessed at http://assess-risk.info/.

The Consortia Projects are also tangibly now contributing to the generation and testing of data and tools, and facilitating their uptake. Similarly, while overall at an earlier stage, some of the Disaster Risk Finance related cluster of projects are now starting to contribute, such as the India basis risk mitigation project and the SatWIN ALERT project. The Durham University project on mapping earthquake-triggered landsliding in Nepal is also performing well.

Lessons identified this year, and recommendations for the year ahead linked to this output

See programmatic level recommendations in Section A.

Output Title	Maximise the impact of the SHEAR programme through capacity building, connecting and communicating across consortia as well as promoting the uptake of SHEAR programme research beyond those directly engaged in the consortia work.
Output number per LF		3		Output Score		A
Impact weighting (%):		30		Impact weighting % revised since last AR?		Y (↑*)
Indicator(s)			Milestone(s) for this review		Progress
3.1 Promotion of knowledge exchange and learning within the SHEAR programme (focusing on the 4 main research consortia) and synthesis, dissemination and uptake of results externally.			Audience mapping and outreach strategy completed. Communication channels established and providing regular knowledge exchange and learning across consortia; 1. newsletter (200 subscribers), 2. Website (50 visitors per month). 3. SLACK (users registered), Twitter (300 followers). 4. Webinar series. 5. Engagement in key events (5).		Met / Audience mapping and outreach strategy completed and shared with DFID+NERC. / Newsletter (internal 105, external 169), / Website (av. daily visitors 41). / SLACK (52). / Twitter (296), / Webinars (6). / Events engagement (5)
3.2 Improved capacity of the community to deliver demand-led, co-produced products that have an impact in practice			(a) 7 new partnerships developed, including at least half involving local (developing country) partners. (b) at least 50% of products co-designed with users.		Exceeded. / FATHUM (2), / Landslide-EVO (4), / LANDSLIP (2), / ForPAc (4), / SatWIN ALERT (2) / Mitigating basis risk in weather index-based crop insurance in India (1) / Nepal Earthquake – Landslide project (Durham) (1) / Outlooks & El Nino support / Challenge Fund implementers developed 91 partnerships, including 60 (66%) with local, developing country partners.
3.3 SHEAR Early Career Researchers and studentships have the capacity to share SHEAR research through relevant channels and fora to promote uptake of results			50% of ECR's and studentships have given 1 international presentation		Not met / 32% (for 4 consortia projects)

* Outputs were consolidated from 4 to 3 so relative weighting has increased.

With many SHEAR projects now well underway, there has been knowledge and learning exchange both within and beyond the programme. The KB has identifed six[5] key themes for channelling learning and relevant expertise into and beyond the programme. Newsletters, web-portal based groups and webinars are being used to share relevant resources and facilitate knowledge exchange on these themes. Six webinars have been conducted for SHEAR consortium members and recordings posted on line – 3 internal (project reporting requirements, demonstration of Global Hazard Model for LANDSLIP and discussion on forecast based financing), and 3 external - landslide early warning systems presented by Italy’s National Research Council, risk data for early warning, and using seasonal rainfall forecasts for forecast based action. Proactive exchange between project teams is happening. For example FATHUM and ForPAc have been interacting regularly, presenting early stage research findings and jointly led sessions the international Forecast-based Financing Dialogue Platform events. Similarly LANDSLIP and Landslide-EVO have also collaborated, such as on stocktake of landslide Early Warning Systems and new work on visualisation for decision makers; and Landslide-EVO early career researchers visited to Wageningen University (including participants from Nepal) to learn about the concepts of resilience and adaptive governance. The KB also participated in an introductory and cross-grant familiarisation workshop for the recently mobilised suite of Catalyst Grants, to enable linkages and synergies to be developed from the outset.
[5] Hydrometeorology, Earth Surface Processes/Dynamics, Multi-Hazard EWS, Participatory Monitoring/Risk Reduction and Resilience, Forecast-based Financing/Action, Impact-based Forecasting

The KB has completed a draft outreach strategy for actors beyond the programme. To support this key SHEAR communication channels and products have been developed including PowerPoint materials, logo, brand guidelines, twitter account (296 followers), external newsletter (169 subscribers) and SHEAR website (41 daily visitors on average) which is updated regularly. The SHEAR programme had good exposure at key events including both the American and European Geo-sciences Annual Meetings, the major Adaptation Futures conference and the Regional and Global Dialogue Platform events on Forecast Base Financing. Next year the focus will be on advancing key knowledge products which synthesise strands of SHEAR research.

SHEAR projects continue to embed a wide range of existing and develop new partnerships. Examples include those of LandslideEVO with schools in difference districts in western Nepal to implement the “Citizen Science in Schools” project element; or the partnership FATHUM is developing with the Bangladesh Flood Forecasting and Warning Centre (FFWC). While reporting has not been as systematic as desired, the reporting provided is indicative of a strong degree of partnership with developing country actors and users, contributing to a solid platform for longer term application and replication.

The support on Monthly Climate Outlooks and El Nino impact analysis are further examples of how SHEAR has further developed partnerships and improve products that are having an impact in practice, both within and beyond DFID.

Regarding Early Career Researcher support, to date 13 studentships have been successfully awarded, of which 7 went to overseas students. Personal Training, Development and Impact Plans (PTDIP) are completed for 11 of the 13 students, with 2 recently started students finalising their PTDIPs. ECRs presenting at international conferences has not met the desired target milestone. This is due to a combination of factors including late starting PhDs due to administrative issues and other PhDs only being in fieldwork phase (so the conference presentations will only come later).

Lessons identified this year, and recommendations for the year ahead linked to this output

Programme to improve systematic reporting on partnerships and co-production, including refined indicators and targets for increased clarity if required. PEB/DFID/KB by March 2019

SHEAR Consortium Coordination Team (CCT) to ensure adequate attention given to ensuring ECR presentations in external fora (ongoing).

Coordinating information emerging from a broad set of projects led by a wide spectrum of organisations in diverse geographies constitutes a challenge. The Knowledge Broker will need to be proactive, targeted, articulate and efficient in its action.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

SHEAR’s hypothesis of change is essentially that appropriate research leads to improved knowledge, data and tools to support disaster preparedness and resilience; and that - coupled with producing the right outputs delivered to the right people - uptake is enhanced, leading to improved decision-making. The 2011 Humanitarian Emergency Response Review emphasized the need to make better use of science in predicting and preparing for natural disasters and in informing investments in resilience. Good risk information and warnings, communicated in a clear and relevant way, will contribute to increased investment in disaster preparedness and resilience. Yet, there are still major gaps in the availability and accessibility of high-quality information and tools, particularly in the poorest countries. SHEAR helps to address these gaps, with the Knowledge Broker and CCT enabling synergy between components for enhanced impact. The general theory of uptake into use is as illustrated in the schematic below.

Each of the four Consortia and the Catalyst Grants have developed a ‘Pathway to Impact’ statement which specifies the particular approach for the issues they are addressing. There have been no major changes to the statements of the Consortia in the last reporting period (the Catalyst Grants were initiated this year so reviewing them at this point is not relevant). Similarly, GFDRR uses a results framework approach to maintain focus on progression towards achieving tangible development outcomes.

Recognising the rapid and dynamic way in which emergency situations can evolve, delivery arrangements under SHEAR includes flexibility to respond to emerging needs in a timely manner, quickly commissioning discrete and targeted pieces of analysis and evidence to inform decision-making

An example demonstrating general validity of the theory of change is the research project on landslide mapping, hazard and risk modelling in Nepal, undertaken by Durham University. This involves mapping, monitoring and modelling the development of the more than 20,000 landslides triggered by the 2015 Gorkha earthquake, delivering risk-based decision-relevant outputs which are proving useful to the Government of Nepal National Reconstruction Authority (NRA), municipalities, and humanitarian actors in ongoing planning and response. The project is providing user-friendly products, such as household level maps and key policy messages, but also making the underlying data widely available. It is already feeding directly into reconstruction and development initiatives, including DFID supported ones, such as the Housing Reconstruction and Recovery Platform and the Supporting Durable Solutions consortium.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

SHEAR is on track and making good headway towards outcomes and impact (see also examples in Summary and Overview Section).

	Outcome Title	Risk monitoring and early warning systems and actions improved by: / - integration of new science, data and tools into systems and practice and; / - improved awareness and use by practitioners and decision makers.
	Outcome number per LF		Outcome 1		Output Score
	Impact weighting (%):				Impact weighting % revised since last AR?		Y/N (if Yes, indicate if ↑or ↓)
Indicator(s)				Milestone(s) for this review		Progress
Outcome Indicator 1: Improved science. (a) More reliable science, data and tools [e.g.sub-seasonal to seasonal forecasts] available to users and independently evaluated by an honest broker and applied in practice; (b) new science operationalised in the field and (c) demonstrated value for decision making.				Trials of new technologies in at least 2 operational systems		Exceeded. The Challenge Fund successfully conducted trials of new risk information tools in 11 operational systems ranging from an Urban Flood Early Warning System based on a Cell Phone Network within the Burkina Faso National Weather Service to remote weather stations within the Irrigation Department in Sri Lanka. / On track: the 4 main research consortia are on track to achieve this outcome by 2020 – see supporting narrative below.
Outcome Indicator 2: Improved use/application: / (a) number of decision makers and practitioners accessing and utilising SHEAR outputs; / (b) demonstrated value of improved systems and practice through case studies and research.				Tools and products co-designed with users (at least 12 from 4 countries) / Case studies to assess value of improved systems and practice identified and agreed.		Exceeded. Challenge Fund implementers co-designed risk information tools with 199 users from 27 countries. / Exceeded. Two CF case studies were not only identified and agreed, but conducted, completed and published. / On track: the 4 main research consortia are on track to achieve this outcome by 2020 – see supporting narrative below.
Outcome Indicator 3: Improved capacity in target stakeholders for understanding risk and uncertainty and to develop and apply/utilise SHEAR type research and outputs.				i) At least 8 identified key stakeholders actively engaged with SHEAR activities / ii) At least 8 individuals / institutions from DCs: / - participate actively in research work / - participate in learning events or similar / iii) at least 8 case studies (or similar) evidence of individual/organisational or institutional change in capability / resources.		Exceeded. i) 1,411 stakeholders were trained by CF implementers. / ii) 232 stakeholders participated in learning events. / iii) evidence of organisational change in capability/resources in 11 cases. / On track: the 4 main research consortia are on track to achieve this outcome by 2020 – see supporting narrative below.

Development results at a programme’s higher-outcome levels typically do not occur quickly.  SHEAR Challenge Fund project results exceeded targets, and this was achieved over a relatively short implementation period.  Additional results beyond those already reported can be anticipated to occur as national and local actors systems integrate CF tools into their daily operations.

Learning from the SHEAR Challenge Fund implementation experience is already informing new programming, such as the DFID Asia Regional Resilience to a Changing Climate (ARRCC) programme which will include a Hydro-Met and Climate Services Challenge Fund component aimed at better understanding ‘last mile’ delivery. There is also scope under this programme to facilitate replication and scaling of successful hydro-met related CF projects from SHEAR.

Several learnings from the Challenge Fund Program are being incorporated into the ARRCC planning, namely:
- Local partnerships were found to be key to project success and the sustainability of results.   Mutually-beneficial partnerships enable sustainable capacity building, co-development of tools, gender integration, and even leverage to occur – all leading to better access to and use of Challenge tools to increase resilience
- Local champions and communities of practice were also found to increase the likelihood of sustainability of Challenge Fund efforts.
- Experience of failure may not be a bad thing.  Many Challenge Fund projects reported that there were difficulties along the path to uptake of their risk information tools within targeted local systems.  Project implementers learned from these apparent failures and adapted their projects to achieve results within their new project reality.  Being willing to learn from both success and failure and adapt based upon that learning was found to be key to project success. Allowing a level of flexibility to projects to adapt is therefore advantageous.
- Conducting primary stakeholder research can inform project implementation so that projects can be more targeted and effective.  This allowed greater access and use of their risk information tools.  In addition to other outputs such as local partnerships and co-creation, primary research helps to ensure risk information tools are tailored to the local context and therefore have maximum impact on resiliency among beneficiary populations.

The SHEAR programme is also delivering learning and products, such as the data schemas and associated explorer and visualisation tools, which are of key relevance and utility to foundational strategy and activity of the recently established Centre for Global Disaster Protection. There has been collaboration in the development of ToR for research calls and in the selection of research projects.

Good progress towards outcomes is also being made by the main research consortia. To take one example as illustration – the LANDSLIP project. Through the extended knowledge exchange visit of GSI (Geological Survey of India) to UK (BGS), Italy (CNR) and Met Office, GSI staff are now using this knowledge to help shape and develop a business model for the Indian Landslide Research Centre where GSI plan to further develop the LANDSLIP EWS after the end of the project. Development of preliminary weather patterns for India will contribute to the longer-term (14 days) landslide EWS. While the system is not yet operational, the underpinning work is on track, and the targeted and collaborative engagement with key users ensures uptake and application once the system is live. Landslip pathway to impact has planned work for wider uptake and replication beyond project sites. Landslip close partnerships with Indian actors including Indian Met Department, Geological Survey of India and Indian academic researchers (including Amrita University) is ensuring cross learning and mutual capacity development between countries.

ForPAC and FATHUM joint participation at the Global Platform Dialogue on Forecast based Financing hosted in Berlin by the Red Cross and German Government – facilitating key sessions in the agenda - is indicative that their outputs and partnership approach are proving fit for purpose. See also Section A for an example of uptake and application of ForPAC

Taken together with the portfolio of projects under the Catalyst Grants and the Disaster Risk Financing call, SHEAR is on track to trial and test a diverse range of technologies and tools, and build associated capacity through strong partnerships and co-production processes for more sustainable benefits.

Explain major changes to the logframe in the past year (1/2 page)

SHEAR is demonstrably delivering improved science tailored to advance resilience planning and response to disasters and emergencies. Nevertheless, the diversity of work conducted under SHEAR driven through a demand-led approach, and the key need to retain ongoing flexibility for evolving situations, has posed challenges in formulating an appropriate logframe and in associated reporting. As a result, in early 2018 elements of the logframe were revised to simplify it into three broad output areas (improved science, application of the science and capacity building), together with adjustment of some indicators, including an additional outcome indicator to better capture capacity building dimensions.

Describe any planned changes to the logframe as a result of this review (1/2 page)

Further refinement of particular indicators and associated milestones may still be warranted given recent feedback received in light of experience this year of reporting against the revised logframe for the first time.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

Key cost drivers are still seen as those identified by the Business Case. This includes research staff costs, costs of equipment and consumables, and travel and subsistence for implementing activities,and associated management, administrative costs and monitoring and evaluation costs.

As outlined in the Business case, value for money is ensured though several processes:

- At the application stage value for money (VfM) is a stated assessment criterion in the scheme specification and applicants are required to fully cost all elements of their proposed research and provide detailed justification for each item of expenditure. Peer reviewers and panel assessors are asked to consider VfM as part of the grant assessment and panel members are asked to consider the requested costs to ensure that they are fully justified when making final funding recommendations.
- At the grant award stage all costs are subject to detailed scrutiny by DFID (if directly procured), the NERC Secretariat (for NERC co-funded components), and by GFDRR (for the World Bank led component). Any unjustified or excessive costs are removed from the budget.
- Grants are only held by institutions which have passed UKRI or GFDRR recognition processes, which include checks on financial management and capacities. Details of the information organizations are required to provide as part of the Due Diligence process are communicated by funders prior to recognition.
- Grants are awarded with NERC standard T&Cs which include financial management and reporting requirements. In addition, the UKRI-wide Funding Assurance Programme conducts checks at an institutional level (see NERC’s annual report and accounts - http://www.nerc.ac.uk/latest/publications/strategycorporate/annualreport/annualreport/ ).
- Where awards have sub-contracted researchers at partner institutes, the organisation that holds the NERC grant will set up ‘sub-contracts’ with any partner organisation and thus take the financial responsibility of tracking partner spend and the risk of any overspend or default.

NERC contributes £6m to the programme as well as providing at no cost to the programme or DFID the application of its robust systems in commissioning and management of large elements of the Research conducted under SHEAR, which further drives overall value for money.. Furthermore, there is alignment of SHEAR funding with wider NERC research funding – which in the case of the El Nino research and the Innovation related Disaster Risk Finance calls amounts to an additional £3.2million - resulting in a greater cumulative momentum and body of relevant research to inform resilience and development planning. Similarly, there has also been collaboration with Economic and Social Research Council (ESRC) through joint calls around themes of a) Disaster Risk Finance and b) Big Data for Resilience, with ESRC contributing about £140,000.

Work commissioned though the GFDRR managed Challenge Fund utilises strong competitive process which contributes to ensuring good value. Furthermore, the GFDRR Challenge Fund has to date also leveraged approximately £10.1 million in cash and kind through partnership on its projects.

The major spending so far on project has been through GFDRR (Challenge Fund) on SHEAR Apps, through NERC on SHEAR Research and direct through DFID on the Applied and Innovation interventions. The major costs for GFDRR are on software development, multimedia, data gathering, data mining, workshops and application developments. NERC associated costs on the main Research grants are on research staff costs and travel and subsistence. The A&I costs are mainly Research staff, travel and subsistence and Equipment.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

This programme continues to represent good VfM. The GFDRR Challenge Fund commissioning was undertaken through an open global competition. The use of the robust UKRI peer review systems for competitive research calls is delivering high quality research under the SHEAR research component. The follow on work that is happening and also the additional resources already leveraged are indicative of the strong partnerships that have been developed and recognition of the quality of the work undertaken.

The central thrust across the programme on better understanding, reducing exposure and vulnerability, improving preparedness for more effective response and action - rather than waiting for crises’ to hit with more costly and less effective and efficient response - is fundamentally consistent with sound VfM and responsible application of Development Assistance finance.

E: RISK (½ to 1 page)

Overall risk rating: Moderate
Review of progress thus far suggests no change in the overall risk assessment from last year.

Potential risks identified regarding the SHEAR programme primarily relate to external context, delivery, operational and fiduciary risk categories. Overall, the principal implementers NERC and GFDRR are well placed in general to manage relevant risks. And the diverse portfolio helps spread some of the risks. The DFID Risk Register, comprising identified risks and associated mitigation measures, can be found here.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Delivery against planned timeframe
The project is largely on track to the existing timeframe. The Knowledge Broker (KB) & Consortium Coordination Team (CCT) are both fully operational. With the decision by NERC and DFID to utilise standard NERC smaller ‘catalyst grants’ to fill remaining gaps rather than re-run a main research project call, a successful round was run in 2018, resulting in the award of 11 new catalyst grants. GFDRR Challenge Fund rounds have been successfully undertaken, with Round 3 on track. DFID direct commissioned work (such as the El Nino impact update analysis, and the monthly Climate Outlook for Humanitarian actors) have been conducted in a timely and effective manner.

It is worth noting that the programme needs to maintain flexibility for additional reactive response to new developments concerning climate extremes, natural disasters and emergencies, which by nature can be very dynamic with changing requirements. As such, the programme must retain a level of funds to cater for such situations. As the programme enters its final period, this balance of retaining funds for reactive flexibility versus proactive deployment (for example to add further value to existing performing elements) will need to be kept under careful review.

Performance of partnership(s)
The partnerships have been performing well. Both GFDRR and NERC governance and management structures and mechanisms are proven. Feedback on initial CCT meetings and planning is positive. It is relatively early stages in the new arrangement with the KB implementing partners, but draft communication plan and stakeholder engagement plans have been prepared and under finalisation.

Asset monitoring and control
Given the type of research it is not expected that the project will purchase significant assets and implementation so far has borne this out. Where these are occasionally required, as in the case of one of the Nepal earthquake projects, the required assets have been borrowed from other NERC funded programmes. If required standard World Bank (GFDRR) or NERC asset management and monitoring procedures and rules are applied.

Quality of financial management
DFID has received reliable and accurate financial information from NERC over the reporting year which has allowed for stable and accurate forecasting which matches the agreed spending profile. Any agreed changes to forecasts are initiated months before the payments are requested.

All planned spending on GFDRR has been completed.
Date of last narrative financial report(s)	11 October 2018 (NERC)
Date of last audited annual statement (s)	12 July 2018 (NERC)

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

This annual review has been compiled based on review of a range of online and hardcopy documentation and follow up discussions with relevant actors such as NERC, the Knowledge Broker, GFDRR Challenge Fund team, sample PIs and users of SHEAR outputs. DFID also participated in sampled stages of the research commissioning and molbilisation, such as that of the Catalyst Grants, and also in ‘Finale Events’ such as the concluding event on the suite of El Nino research.

A new contract for the Knowledge Broker is now in place which, in tracking, harnessing and synthesising knowledge and progress under SHEAR will also contribute to effective ongoing M&E.

During GFDRR CF implementation sample performance evaluations have been conducted: an evaluation of NIWA’s Phase I project was completed in April 2017[6]; and a second performance evaluation was completed on open-source, DIY remote weather stations in Sri Lanka project in February 2018.[7] More generally, complementing a learning document produced in 2017[8];.a final report for Round 1 of the Challenge Fund was submitted May 2018.
[6] https://www.gfdrr.org/sites/default/files/publication/CF-NIWA-Case-Study.pdf
[7] https://www.gfdrr.org/sites/default/files/publication/Remote-Weather-Station-Evaluation-CF.pdf
[8] GFDRR Challenge Fund Phase 1 Results and Learnings https://www.gfdrr.org/sites/default/files/publication/Challenge-Fund-Phase-I-Results-and-Learnings.pdf

Gender Equality
SHEAR was designed before the introduction of the Gender Equality Act in 2014. However, the Business Case was clear that research and uptake strategies would need to incorporate a strong gender analysis in order to better understand the interrelationships between risk, resilience and women’s vulnerability. For example, in some natural disasters, many more women have been killed than men, underlining the differentiated vulnerability. In addition, it noted that there is some evidence that uptake of strategies can be improved through designing communications strategies that reflect potential differentiated gender roles of target beneficiaries. As a result, a strong consideration of gender equality was incorporated into the various competitive calls that have been issued through SHEAR. This is also a core role for the KB and CCT functions going forward.

GFDRR, who manage the SHEAR Apps component, are guided by their 2016-2021 Gender Action Plan and have ensured gender integration is occurring in all seven Phase 2 projects. Specifically, three projects are conducting surveys which collect gender-sensitive data; one implementer is conducting a study including extensive interviews on gender dynamics as they relate to the project; and three projects are conducting gender analyses. A paper produced under the New York University’s (NYU) Risk Communication Toolkit project has explored gender gaps related to natural disasters in general and how the project could possibly help tackle some of those gaps[9]. See section A for further information on practical examples.
[9] https://docs.wixstatic.com/ugd/0c6e1a_5e51e5e9702843c0995f75eb1d29b433.pdf

Commissioning under other major components of the programme flags gender. While there is some evidence of a proactive approach, it is variable and reporting on this aspect by the projects and KB could be improved.

Evidence (1/2 page)

The importance of disaster resilience and early action remains unchanged since the initial design of SHEAR and the challenges are recognised in the Global Goals. If anything, recent events (El Niño/La Niña and a series of major hurricanes and flood events) have emphasised the importance of this area of work. Already, the total costs of disasters faced by developing countries are estimated at $29 billion a year for 77 countries[10]; equivalent to one third of total global official development assistance. Global economic losses from disasters are now reaching an average of over US$300 billion a year, with vulnerable countries, and particularly their poorest communities, experiencing an increasing burden from adverse impacts on household incomes and government balance sheets. Disaster related risks for lives and livelihoods further increase the challenge, particularly for the poor and vulnerable.[11] September 2017 was the most intense month on record for extreme weather events. The World Economic Forum 2018 Global Risks Report identifies both Extreme Weather Events and Natural Disasters as the highest in combination of impact and likelihood in comparison to a range of other risk (and also within a broader trend of Environmental risks growing in prominence over the 13-year history of their reporting on risk). It is reasonable to assume that the area of focus of the SHEAR programme will continue to grow in relevance, given both global change processes and the steady increase over time in exposure of poor people to natural hazards.
[10] Risk Management Solutions (2017) Mapping the Role of Insurance in Managing Disaster Losses
[11] World Bank (2016) Unbreakable. Building the Resilience of the Poor in the Face of Natural Disasters.

Learning (1/2 page)

Across the SHEAR projects, teams have shown a strong commitment to learning. Below is some emerging learning from the Knowledge Broker from across the programme:

- While there has been a lot of literature on the different components of early warning systems (eg. risk knowledge, monitoring and warning, communication, and response capability etc), the SHEAR projects, via inter-disciplinary research groups, are taking more of an end-to-end approach, considering not only the information itself, but who can produce it on a regular basis, how it can be visualized and communicated, and whether it is actually actionable.
- While these are research projects, they typically have focused at least as much on the institutional landscape of risk management as they have on the scientific aspects of the topic. This requires additional time compared to a purely intellectual exercise focused only on drivers of predictability but is seen as key for projects to achieve uptake of research results and ultimate impact.
- SHEAR researchers are making progress at working with national forecast providers to improve the science (e.g. weather regimes preceding landslides in Nepal, drought forecasts in Kenya). But there is more to be done than can be tackled by the SHEAR researchers. In this context, there has been effort to influence other interested PhD students and other research consortia to help tackle priority topics. These groups have been an encouragement for several other research programmes.
- Non-technical challenges to building resilience to extreme events are equally, if not more important than technical challenges. Research and collective problem-solving on sociocultural and governance aspects has been prioritized by all of the main consortia.
- Local partnerships are key to project success and the sustainability of results. Developing a strong community of practice has also been core to learning among and between projects.

Progress on recommendations from previous reviews (1/2 page)

Recommendation	Progress
As we move closer to programme conclusion (March 2020), to keep a close eye on the unspent component of the SHEAR A&I (emergency preparedness and response research) budget, ensuring strategic spending on ad hoc necessary work as time progresses but also ensuring sufficient funds are retained in order to be able to respond efficiently to any unforeseen emergency throughout the next 2 years. DFID CEW team. Ongoing.	Actioned. Additional strategic work/initiatives have been supported or are in process (Eg El Nino Impact review; Forecast based Action against Cholera). There are still funds available for unforeseen events and further more a ‘Facility’ arrangement has also been set up to enable faster contracting.
In order to ensure the Knowledge Broker is effective at facilitating information exchange within the programme and to external stakeholders, the contract has been agreed for one year only (until June 2018) during which time they will establish a SHEAR website and process of knowledge exchange; prior to the conclusion of this trial year we will take stock of the effectiveness up to that point and either amend the ambition or resources available before embarking on any continuation. DFID and NERC teams to review and make a decision on future years. By May/June2018.	Actioned. A new contract for the Knowledge Broker is now in place.
It has been broadly acknowledged and was highlighted in the last AR that the initial SHEAR lograme is too complex for all reportees and arguably not well suited to the overall objectives of the programme. We have therefore proposed a much-simpler alternative that more closely fits the design of the various programme strands and are discussing with the Knowledge Brokers and various PIs, working towards settling on a modified logframe suitable to all. All partners and key suppliers. Revised log frame to be agreed by end Jan 2018.	Actioned. A revised logframe has been agreed (and used in this years reporting).
As a result of feedback from medium-term climate/weather outlook notes for CHASE and others, we will ensure that the results of the outlook-note improvement research, along with feedback and information regarding new climate impacts research capabilities, inform a step-change improvement in the notes, in their communication, representation of model skill (confidence over forecasts in particular regions) and the extent to which they include forecasts of socio-economic impacts such as possible floods, crop failure, water resources stress and human health threats. We seek to commission a refreshed forecast note before July 2018, when the current note provision contract comes to an end. DFID CEW team to agree future arrangements. By April 2018.	Actioned. A new arrangement is in place for ongoing for production and dissemination of an improved monthly Climate Outlook.

Annex A

Acronym List

AGU	American Geosciences Union
AIC	Agriculture Insurance Company of India
ANAM	Burkina Faso National Weather Service
ARC	African Risk Capacity
ARRCC	Asia Regional Resilience to a Changing Climate Programme (DFID)
ASTCDRR	Asian Science and Technology Conference on Disaster Risk Reduction
BGS	British Geological Survey
BNPD	National disaster agency of Indonesia
CCAFS	Climate Change, Agriculture and Food Security Programme
CCT	Consortium Coordination Team (SHEAR)
CEW	Climate Energy and Water team (DFID)
CF	Challenge Fund
CHASE	(DFID) Conflict Humanitarian and Security Department
CIMMYT	The International Maize and Wheat Improvement Centre
CNR	Italian National Research Council
CPP	Cyclone Preparedness Programme in Bangladesh
CSSP	Climate Science for Service Partnership China
DFID	Department for International Development
DREE	Disaster Response and Exercise and Exchange (US Army-led)
DRF	Disaster Risk Finance
DRR	Disaster risk reduction
DST	Decision Support Tools
EACDS	Expert Advisory Call Down Services
ECMWF	European Centre for Medium-range Weather Forecast
EGU	European Geosciences Union
ESRC	Economic and Social Research Council
EWS	Early warning system
FATHUM	Forecasts for Anticipatory Humanitarian action
FbA	Forecast based action
FbF	Forecast based finance
ForPAc	Forecast-based Preparedness Action: Probabilistic Forecast Information for Defensible Preparedness Decision-Making and Action
GAR	Global Assessment Report
GFDRR	Global Facility for Disaster Response and Recovery
GHM	Global Hazard Map
GPC	Global Producing Centres
GSI	Geological Survey of India
HEWN	Humanitarian Early Warning Note
HRRP	Housing Reconstruction and Recovery Platform
ICPAC	IGAD Climate Prediction and Application Centre
ICT	Information Communication Technology
IFPRI	The International Food Policy Research Institute
IRD	The Research Institute for Development
IRI	International Research Institute for Climate and Society and Columbia University
IWMI	International Water Management Institute
KB	Knowledge Broker (SHEAR)
KMD	Kenya Meteorological Department
KRCS	Kenya Red Cross Society
Landslide-EVO Citizen Science for Landslide Risk Reduction & Disaster Resilience building in Mountain Regions
LANDSLIP	Landslide Multi-Hazard Risk Assessment, Preparedness and Early Warning in South Asia:
Integrating Meteorology, Landscape and Society
MELD	Monitoring, evaluation, learning and project design
MoU	Memorandum of Understanding
NCEO	National Centre for Earth Observation
NCMWRF	National Centre for Medium Range Weather Forecasting
NERC	Natural Environment Research Council
NIWA	National Institute of Water and Atmospheric Research
NSET	National Society for Earthquake Technology
NOAA	National Oceanic and Atmospheric Administration
NRA	Nepal National Reconstruction Authority
NYU	New York University
OCD	Office of Civil Defence
ODA	Overseas Development Aid
PIs	Principle Investigators
PTDIP	Personal Training, Development and Impact Plans
RCO	Resident Coordinators Office (UN)
RED	(DFID) Research and Evidence Department
SHEAR	Science for humanitarian emergencies and resilience
SLACK	Slack is an online collaboration hub
SSC	SHEAR Student Cohort
SRF	SHEAR Responsive Facility
TAMSAT-ALERT Tropical Applications of Meteorology using SATellite data and ground‐based observations AgriculturaL EaRly warning sysTem
TIGGE	THORPEX Interactive Grand Global Ensemble
ToC	Theory of change
UAVs	Unmanned aerial vehicles
UKRI	UK Research Institutions
UNCTAD	United Nations Conference on Trade and Development.
UnDIP	Diponegoro University Indonesia
UNISDR	United Nations Office for Disaster Reduction
UNOPS	United Nations Office for Protected Services
UoR	University of Reading
USAID	United States Agency for International Development
WHH	Weithungerhilfe
VfM	Value for Money
WFP	World Food Programme
WiTRACK	Windfeld-Transport- und Klimatologiesystem (Wind field transport and climatology system)
WP	work package

Annex B – supplementary progress information for Logframe milestone reporting
Main Consortia projects:

LANDSLIP:
1.1
2 submitted peer-review papers:
  - Melillo M., Brunetti M.T., Peruccacci S., Gariano S.L., Roccati A., Guzzetti F. (2018): A tool for the automatic calculation of rainfall thresholds for landslide occurrence, Environmental Modelling & Software, 105, 230-243, doi: 10.1016/j.envsoft.2018.03.024 &
  - Alvioli M., Mondini A.C., Fiorucci F., Cardinali M. & Marchesini I. (2018) Topography-driven satellite imagery analysis for landslide mapping, Geomatics, Natural Hazards and Risk, 9:1, 544-567, DOI: 10.1080/19475705.2018.1458050)
1.2
●	The project is also in the process of developing case studies on single (one case study) and multi-hazards (one case study) based on social media, archival work and reports. These will be completed in the next reporting period.
FATHUM:
1.1
The new seasonal timescale part of the Global Flood Awareness system is now fully operational and freely available at www.globalfloods.eu. Stephens and Cloke supervised the development and write-up of the system. The paper is available here (1):
  - Emerton, R., Zsoter, E., Arnal, L., Cloke, H. L., Muraro, D., Prudhomme, C., Stephens, E. M., Salamon, P., and Pappenberger, F.: Developing a global operational seasonal hydro-meteorological forecasting system: GloFAS-Seasonal v1.0, Geosci. Model Dev., 11, 3327-3346, https://doi.org/10.5194/gmd-11-3327-2018, 2018.

LANDSLIDE EVO
1.1
2 papers published:
  - Paul, J. D., Buytaert, W., Allen, S., Ballesteros-Cánovas, J. A., Bhusal, J., Cieslik, K., Clark, J., Dugar, S., Hannah, D. M., Stoffel, M., Dewulf, A., Dhital, M. R., Liu, W., Nayaval, J. L., Neupane, B., Schiller, A., Smith, P. J. and Supper, R., 2017. Citizen science for hydrological risk reduction and resilience building. WIREs Water 5 (1), January/February 2018, e1262. doi:10.1002/wat2.1262
  - Mao, F., Clark, J., Buytaert, W., Krause, S., Hannah, D.M., 2018. Water sensor network applications: time to move beyond the technical? Hydrological Processes, 32, 2612-2615.
1 paper submitted:
  - Zogheib, C., Ochoa-Tocachi, B.F., Paul, J.D., Hannah, D.M., Clark, J., Buytaert, W., In review. Exploring a water data, evidence, and governance theory. Water Security.

ForPAc:
1.1
3 journal papers - 1 published, 2 in review (one led by Kenyan partner) all covering advances in hazard risk forecasting science.
  - MacLeod, D. (2018). Seasonal predictability of onset and cessation of the east African rains. Weather and Climate Extremes.
  - Kilavi, M et al. (In review) Extreme rainfall and flooding over central Kenya including Nairobi city during the 'long rain' season 2018: Causes, predictability and potential for early warning and actions. Atmosphere.
  - Kolusu, S., et al. (in review) The El Nino event of 2015-16. Climate anomalies and the impact on groundwater over Eastern and Southern Africa. Hydrology and earth System Science
1.2
1 technical report / working papers
  - MacLeod, D. & Palmer, T. (2018) Diagnosing sub-seasonal to seasonal predictability of the East African long rains. ECMWF Special Report.

Disaster Risk Finance Projects

Black_Satellite data for Weather Index Insurance-AgricuLtural EaRly warning system (SatWIN-ALERT)
- A set of research questions and case studies were identified jointly with practitioner partners during our workshop.
- Significant progress has been made with adapting the TAMSAT-ALERT (Tropical Application of Meteorology Using Satellite Data and Ground-Based Observations) decision support system for supporting replanting insurance.
- Questionnaires have been developed for the planned participatory research.
- A set of case studies/regions of interest has been designed, targeting key issues in insurance, including basis risk.
- Development of methodologies for improved soil moisture estimation through synergies with the National Centre for Earth Observations of the Overseas Development Aid (NCEO ODA) national capability project.
- Development of methodologies for utilisation of seasonal and sub-seasonal forecast information in risk assessment through synergies with the NCEO ODA national capability project (ACREW)

Mitigating basis risk in weather index-based crop insurance: harnessing models and big data to enable climate-resilient agriculture in India
1.1
1 journal paper accepted (subject to minor revisions) in Agricultural and Forest Meteorology, which describes the outcomes of research to utilise smartphone imagery to assess crop phenology and damage in smallholder agricultural systems.
1.2
1 working paper in process that highlights the implications of weather dataset choice when assessing agricultural exposure to climate variability and change.
- For work package 2, completed a review and analysis of weather dataset accuracy/reliability for the Indian region,
- For work package 3, completed the development and assessment of approaches for monitoring crop status and damage using farmer-reported smartphone imagery. A key finding from this work is that smartphone imagery provides a more accurate approach for crop monitoring than satellite-based imagery and can also be used to identify localised idiosyncratic crop damage that is an important driver of basis risk in index-based crop insurance.

Financial planning for natural disasters: the case of flooding risk in Central Java – FloodFinJava
1.2
1 working paper in progress providing an overview of the financial management of flooding and other natural hazard risks in Indonesia, focusing on both the needs of stakeholders and the current tools already available to them for meeting these needs and reviewing the tools of economic loss and financial instrument modelling.
DRiSL: The Drought Risk Finance Science Laboratory
1.1
- 1 publication: Wilkinson, K.; Weingärtner, L; Choularton, R.; Bailey, M.; Todd, M.C.; Kniveton, D.; Cabot Venton, C. Forecasting hazards, averting disasters: Implementing forecast-based early action at scale. Overseas Development Institute, London, UK, 2018, 38pp.
- Work in progress on several work packages involving papers due to be published early 2019.
1.2
- 1 draft report ‘A framework and typology of Drought Risk Finance decision-making in WP1
- Desktop research for technical report on relationship in food security and drought in the 3 test sites through qualitative and quantitative regression analysis ongoing. Target completion November 2018.

White Coastal Ecosystem Recovery Financing for the Future (CERFF): developing insurance products to enhance response and recovery from tropical cyclones
- Good progress made with identifying patterns of risk reduction through development of updated wave models that can be used to simulate the impacts of storm surges from tropical cyclones. Progress has been slightly delayed in finalising these due to difficulties in simulating the effects of dynamic winds, and we are developing a solution for this.
- 1 database compiled of hurricanes in the Caribbean and their impacts since the 1950s. The dataset covers the type of hurricane, pressure, wind speed, and for some sites also duration, radius, maximum wave height and surge.
- 1 historical database on coral cover and condition that can be integrated with the hurricane database and allow us to quantify the changing coral condition over time and the impacts of hurricanes on this in terms of damage and loss. These databases will together provide essential underlying information for the insurance products.

INPAIS
Progress in set up of applied tracking methods for severe Typhoons in the newly used Thorpex Interactive Grand Global Ensemble (TIGGE) multi-model multi-member dataset. In detail:
- The subset of TIGGE data that is suitable for this study has been identified. We are now collecting the data from European Centre for Medium-Range Weather Forecasts (ECMWF) via ECaccess and ecgate.
- The necessary algorithms to restructure the TIGGE source data have been developed.
- Preliminary study, using JRA-55, on the effect of different choice of Windfeld-Transport- und Klimatologiesystem (Wind field transport and climatology system) WiTRACK parameters and the effect of using different levels of wind data has been conducted. Results have been compared to the existing literature – Befort et al. 2018 [submitted].

Durham Earthquake-triggered landsliding in Nepal during and post-monsoon 2016-17
1.1/1.2
New set of metrics developed for deriving landslide risk to individual buildings that uses building data to assess changing landslide risk over time. To our knowledge, this has not been done in the aftermath of any previous earthquake, and the approach is gaining a great deal of interest in Nepal. The underlying method is currently being prepared for publication in a peer reviewed journal.
EACDS – SHEAR RESPONSIVE FACILITY:
1.1
Underpinning research by University of Reading (N.Klingaman) for Monthly Climate Outlook Notes (nb Commissioned prior to establishment to Facility, but links to below work so presented here)
1.2
●	(1) Production of Monthly Regional Climate Outlook Notes for three key regions – these continue to improve upon the provision of scientifically based forecast information on forthcoming weather patterns to assist better programming and decision making by DFID and partners.
●	(1) El Nino 2018-19 – Impact Analysis report - this activity has provided a stand-alone analysis of the potential impacts of the 2018-19 El Niño, reflecting the analytical framework and method used in 2015 in the ‘El Niño 2015/16: Impact analysis’ report.
Output 2

Indicator 2.1 GFDRR Challenge Fund # Tools Breakdown
Challenge Fund Round 1
Bristol Films (x15):
1. Lahars: human experiences
2. Lahars: the hazard
3. Lahars: the impacts
4. Pyroclastic flows: the hazard
5. Pyroclastic flows: the impacts
6. Explosive eruptions: the hazard
7. Explosive eruptions: the impact
8. Lava: the hazard
9. Lava: the impacts
10. Volcanic gases: the hazard
11. Volcanic gases: the impacts
12. Experience: Living with volcanic gases: Masaya, Nicaragua
13. Experience: Lahars: “A river of rock”
14. Experience: Pyroclastic flows: “A glowing cloud”
15. Experience: Ashfall: “An eclipse”
DFO Web Map Services of Global Flood Data Products (interactive online flood portal with Web Map Service (WMS) tool = x2 tools, with the following products within:
1. Current daily water extent data
2. 2-week accumulated flooded area
3. January till current flooded area
4. Annual flood inundation area extent
5. Flood hazard (frequency) map
6. Flood heat map
7. Regular water layer
8. Flood event layers
9. Satellite River Discharge Measurements
10. Integration VIIRS satellite derived water product to guarantee product sustainability
NIWA Drought Risk Visualization Tools (DRVT) (x6 tools):
1. DRVT Samoa
2. DRVT Solomon Islands
3. DRVT Fiji
4. DRVT Vanuatu
5. DRVT Kiribati
6. DRVT Papua New Guinea
New York University Risk Communication Toolkit (x2 tools)
1. Risk Communication Toolkit Philippines
2. Risk Communication Toolkit Bangladesh
IRD Flood Early Warning System (x2 tools * not currently included for logf reporting)
1. Flood Early Warning System Burkina Faso
2. Flood Early Warning System Niger
3. Open-source, DIY remote weather station*
Deltares (x7 tools, * not currently included for logf reporting)
1. Digital Terrain model
2. Circle Bao game and curriculum in Tanzania
3. Floodtags Twitter analysis platform in Philippines
4. UNESCO VISUS school survey in Indonesia*
5. American Red Cross Crowdsourcing platform in Indonesia, Myanmar and Philippines*
6. University of Reading Learning Framework
7. Future Water flying sensors for flood risk identification in Mozambique*
8. IBIMET Crop Monitoring System for Mali and Niger
9. iMMAP Online Operational Disaster Risk Assessment in Tanzania
10. GNDR e-learning platform
Challenge Fund Round 2 (x4 tools)
1. BGS: Hazard data schema
2. GEM: Exposure Data Schema
3. UCL: Vulnerability data schema
4. Data Explorer tool

Cumulative Round 1 CF results (Reported Oct 2018).
Challenge Fund Indicator	Target	CF Actual
# local policies, plans or investments informed
by project-funded risk information tools	6	35
# of decision makers regularly accessing tools	30	107
# of tools available on open platform	6	50
# downloads of tools	70	47,370
# of new tools developed	10	42
% DFID priority countries for which tools developed	50	67
# of partnerships developed with local partners	5	60
# of local beneficiaries involved in co-development	15	199
All Phase II projects consider gender	7	7
# targeted beneficiaries trained	20	1,411
Amount of leverage	£1million	£10,585,348 (but inc $650k from DFID)

Disaster Risk Financing Projects

Mitigating basis risk in weather index-based crop insurance: harnessing models and big data to enable climate-resilient agriculture in India
Indicator 2.1
(x1) Development of new approaches to enable assessment of crop growth stage and damage to be assessed on the basis of farmer-reported smartphone imagery. This approach is currently being practically implemented as part of a related set of pilot trials for a picture-based crop insurance product for wheat growers in Northern India, led by Co-I Berber Kramer at IFPRI in conjunction with our practitioner partner in India (HDFC-Ergo).
2.2
(x1) Other stakeholders in the Indian insurance sector, including AIC and Haryana State government expressed interest in working collaboratively to explore development and application of technological approaches for yield loss estimation.

Black_Satellite data for Weather Index Insurance-AgricuLtural EaRly warning system (SatWIN-ALERT)
Indicator 2.1
- (x1) A planting date decision support tool has been adapted from TAMSAT-ALERT (Tropical Applications of Meteorology using SATellite data and ground‐based observations AgriculturaL EaRly warning sysTem), based on requests from PULA project[12], One Acre Fund[13] and CIMMYT (International Maize and Wheat Improvement Center).
  [12] Pula Project: Extreme rainfall and floods in arid regions: replenishment or contamination of water resources? University of Aberdeen
  [13] Acre is a non-profit social enterprise that supplies smallholder farmers with asset-based financing and agriculture training services to reduce hunger and poverty.
- (x1) Bulletins based on the outputs of the decision support tools (DST) were circulated to the One Acre Fund during the long rains in Kenya for a region in Western Kenya for which robust data is available.
2.2
- (x1)Stakeholder workshop to identify how TAMSAT-ALERT system can be implemented into various types of insurance scheme. As a result, the systems developed in SatWIN-ALERT will be integrated into major insurance schemes in Malawi (through Pula), Zambia (Risk Shield) and Senegal/Ethiopia (World Food Programme).
- (x1)In addition, we are working with African Risk Capacity (ARC) to implement TAMSAT-ALERT methodologies into their Africa Risk View portal.

Main Consortia Projects
LANDSLIDE-EVO
2.2
(x1) Landslide-EVO is collaborating with the Department of Hydrology and Meteorology of the Government of Nepal to support the improvement of the national flood forecasting system. Joint workshops and training sessions are planned for 2019.
(x1) Landslide-EVO is developing and planning a citizen science-based training activity for schools that will be implemented in 10 communities in the Karnali basin in Nepal during the period of February – March 2019.
2.3
(x1) Landslide-EVO has produced a first draft of a policy paper on “The role of science, technology, and innovation in building resilient communities through citizen science” for the United Nations Conference on Trade and Development (UNCTAD).

ForPAc:
2.1
(x1) A toolkit of forecast products that are under development / available to partners through ForPAc includes:
- Extended range seasonal forecasts for Oct-Dec (with skill statistics)
- ‘Optimised’ multi-model seasonal forecast product (with skill statistics)
- Downscaled seasonal forecasts (with skill statistics)
- Forecasts of wet season onset/cessation
- Forecasts with seasonal lead times of satellite-derived vegetation index (EVI) (with skill statistics) for forecast of county ‘Alert’ phase classification
- Forecasts of multiple agricultural drought indicators (soil moisture, WRSI, maize yields) in gridded format over Kenya using the TAMSAT-ALERT modelling system
- Skill assessments of ECMWF and Met Office forecast models at seasonal-to-sub-seasonal lead times. Similar sill assessment for the entire GPC multi-model ensemble underway
2.2
(x2) New tools and platforms available to partners through ForPAc :
- Global Hazard Map (GHM) Access by ICPAC & KMD
- ALERT platform access and use by KMD to provide forecasts to users
2.3.
(x1) Contributed to a report providing an assessment of the global FbA landscape and recommendations for scaling-up FbA: Wilkinson, K.; Weingärtner, L; Choularton, R.; Bailey, M.; Todd, M.C.; Kniveton, D.; Cabot Venton, C. Forecasting hazards, averting disasters: Implementing forecast-based early action at scale. Overseas Development Institute, London, UK, 2018, 38pp.

LANDSLIP
2.1
(x1) LANDSLIP gathered metadata and primary/secondary data for pilot study areas (draft review report produced) and has produced preliminary weather patterns for India (report & webinar).

(x1) LANDSLIP conducted detailed institutional mapping (national, state, regional) (including draft report & webinar) to ensure identification of target users. GSI (Geological Survey of India) is the nodal agency for landslides in India, and both a Co-I of LANDSLIP and a beneficiary user (in terms of legacy). 3 extended knowledge exchange visits in one year of GSI (Geological Survey of India) to UK (BGS) and Italy (CNR).

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided