## Logframe
Logframe (MULTI-SHEET VERSION revised in Jan 2019 from the May 2018 DFID-approved version)
JOBA - SKILLS FOR EMPLOYMENT (S4E) PROGRAMME
IMPACT | Impact Indicator 1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Higher income among JOBA beneficiaries, especially young women, in the context of a more effective skills training system | Percentage of JOBA Employment Fund training programme graduates who see a real increase in income due to their training, disaggregated by gender |  |  |  | JOBA and Impact Assessment baseline tracer surveys designed | JOBA and Impact Assessment baselines for tracer surveys implemented | 50% | 75% | 75% | This indicator focuses on the first part of the Impact Statement. Of the total # of graduates, what proportion experienced an increase in income following training? Broken down by demographic measures. Broken down by circumstance and location. Income effects do not have to come just from employment status, if the training has effects on other aspects of earnings and livelihoods | 1) One assumption is that even short-term training can effect income impacts, despite a lack of empirical evidence from Mozambique. Any such impact could be militated by an economic downturn, so even if effects are established, they might be such that they protect from income declines. Protection from decline would also be measurable via the tracer surveys. 2) A second assumption is that income gains are broadly linked to skills acquired and are evident within two years of training. 3) The percentages offered for 2019/20 and 2020/21 do not have an evidence base at this time. Evidence mapping of the Theory of Change will be does to provide available evidence.
Achieved
Means of Measurement
Tracer survey data from grantees and from independent evaluation disaggregated by gender. 2018 cohort 1 first quarter baseline, 2018 year 1 measure and baseline cohort 2; 2019 cohort 1 year 2 measure and cohort 2 year 1 measure, 2020 cohort 1 year 3 measure, cohort 2 year 2 measure, cohort 3 year 1 measure; 2021 cohort 1 year 4 measure, cohort 2 year 3 measure, cohort 3 year 2 measure. Note: a separate, indepdendent evaluation will continue to monitor income gains over 2021.
| Impact Indicator 2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
| Changes that evidence improved effectiveness* in the skills training system. |  |  |  | JOBA puts into place mechanisms to engage with, and strengthen over time, skills market actors | JOBA strengthens government systems that regulate TVET and improve the quality of service delivery, and strengthens governance, accountability and voice in the non-state TVET sector | Private sector TVET service providers and representative bodies are able to have their voices heard in the TVET sector, and that this voice represents the values and interests of its members. State authorities are more able to enable quality in the TVET system. Private and public sector TVET service providers improve the quality of TVET service delivery | Private sector TVET service providers and representative bodies are able to have their voices heard in the TVET sector, and that this voice represents the values and interests of its members. State authorities are more able to enable quality in the TVET system. Private and public sector TVET service providers improve the quality of TVET service delivery | Vibrant TVET system with voices heard | This indicator focuses on the second part of the Impact Statement. Effectiveness is measured on a five point scale: 1) very effective (value = 10); 2) somewhat effective (value 7); 3) somewhat ineffective (value 4); 4) very ineffective (value 2); 5) completely ineffectively (value 0). Will be measured through stakeholder interviews where scale values will be established over a period of time (2019, 2020, 2021). Elements of effectiveness to be agreed during the design of the stakeholder interview instrument. | 1) One assumption is that JOBA-supported activities serve to catalyse other development actors to support a more effective skills training system. 2) A second assumption is that activities aimed at strengthening the skills training system enhance effectiveness in the sector, thereby contributing to economic development through more people accessing skills that lead to more productive employment.
Achieved
Means of Measurement
JOBA Reporting System, as this information will be reported on as part of quarterly and annual reporting. In additional, qualitative interviews will be conducted with GoM and non-state training providers and others. Tools developed under Record 2 of the JOBA Monitoring System include results monitoring, interviews with relevant government officers, interviews were employers, interviews with grant recipients, and special studies. Evidence mapping against the Theory of Change.
* Examples of improved effectiveness include greater availability of TVET training opportunities, more TVET service provision in priority sectors, improved quality of graduates as reported by private sector, changing perceptions among key actors in the TVET sector including employers, and more women completing TVET training.
OUTCOME 1 | Outcome 1 Indicator 1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
More Mozambicans, especially young women, have marketable skills applied to productive work | Proportion of JOBA Employment Fund beneficiaries who enter productive employment or who are engaged in more productive work, disaggregated by gender |  | na | na | Baseline Tracer Survey questionnaire to measure engagement in productive employment is prepared and implemented for first cohort of enrolled trainees. | First baseline is set: The proportion of surveyed trainees at baseline by type of employment. | 50% of VSCE graduates from 2018 are engaged in productive employment, or more productive activities one year after training compared to their baseline | 70% of VSCE graduates from 2019 are engaged in productive employment or more productive activities one year after training compared to their baseline. 80% of TT graduates in 2019 are engaged in productive employment or more productive activities one year after training compared to their baseline | 70% of VSCE graduates are engaged in productive employment or more productive activities one year after training compared to their baseline. 80% of TT graduates in 2020 are engaged in productive employment or more productive activities one year after training compared to their baseline | Baseline establishes type of employment, or no employment, and insights on the nature of this employment. Tracer survey data will thereafter be used to establish whether more are in what type of employment, and whether graduates are in a better employment situation even if they have not changed their jobs. Measure will include protection from decline in position and decline in income. | 1) The first assumption is that there are sufficient numbers of young people who would demand TVET. 2) A second assumption is that there are sufficient training organisations suitably focused to support these services. 3) A third assumption is that the economic problems facing Mozambique do not overwhelm trainees in their ability to contribute economically to their households. 4) A fourth assumption is that grantees successfully deliver courses that match the needs of employers. 5) A fifth assumption is that improved skills improve chances of employment.
Achieved
Means of Measurement
Tracer survey data, disaggregated by gender. Baselines to be set through programme monitoring with grantees and augements with evaluation. 2018 Quarter 1 baseline cohort 1; 2018 2nd quarter cohort 1 year 1 measure and baseline cohort 2; 2019 cohort 1 year 2 measure and cohort 2 year 1 measure; 2020 cohort 1 year 3 measure, cohort 2 year 2 measure, cohort 3 year 1 measure; 2021 cohort 1 year 4 measure, cohort 2 year 3 measure, cohort 3 year 2 measure
OUTCOME 2 | Outcome 2 Indicator 1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Strengthened Mozambican skills training system | Proportion of TVET providers who demonstrate improved quality of market relevant training |  | na (no association) | na (no association) | AMEPP Statutes approved and AMEPP registered as a national association. AMEPP 3 year Strategic Plan developed. MoU signed with ANEP that defines programme of support to ANEP to roll out their national quality assurance and accreditation systems within the TVET sector. | The TVET sector begins to demonstrate TVET enabling attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability | The TVET sector demonstrates TVET enabling attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability | The TVET sector demonstrates TVET enabling attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability | The TVET sector is characterised by positive attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability | Improved quality and market relevance is defined as gains made in terms of trained teachers, partnerships with industry in place, relevant curriculum focused on market needs, and management that has received training on quality management systems. The main means of measurement for this comprise a panel design of informed stakeholders rating the sector's attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability on a to-be-established scale, measured in 2018, 2019, and 2020 | 1) The key assumption is that the Association will be able to function effectively. 2) A second assumption is that information flows will be effective, strengthening Association members performance. 3) A third assumption is that the operations of the Association will enable higher quality service provision by Association members.
Achieved
Means of Measurement
JOBA Reporting System, as this information will be reported on as part of quarterly and annual reporting. In addition, qualitative interviews will be conducted with non-state training providers and others. Tools will be developed under Record 2 of the JOBA Monitoring System that includes results monitoring, interviews with employers, interviews with grant recipients, and special studies.
For Outcomes 1 and 2, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £13.6m + £1m for T4R (NOTE: based on expected budget amendment) |  |  | Value of grant recipient in-kind contributions estimated at £2m (ie. 25% addition to JOBA contribution to Employment Fund). |  |  |  | £16.6m | 88%
INPUTS (HR) | DFID (FTEs)
A1 (0.05) A2 (0.5) B2 (0.2)
OUTPUT 1 | Output Indicator 1.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Expanded access to inclusive, market relevant, quality training and wrap-around services by non-state training providers | Number of graduates who are provided with training comprising 2 or more years at appropriate competence levels (technical or vocational) combined with wrap-around services through the JOBA Employment Fund |  | 0 | 0 | Grants awarded that make provision for additional 1800 persons to be enrolled in the technical training system, with targets disaggregated by gender | JOBA completes follow up on findings of due diligence for all Round 1 and 2 grantees delivering technical training. Routine monitoring of grants implemented in line with workplans for MEL | Graduated 250 Female: 125 Male: 125 Technical advisory support provided by JOBA to all grantees to improve quality of training provision, and of wrap around services | Graduated: 250 Female: 125 Male: 125 Strategies supported by JOBA for linking technical /vocational graduates to employment opportunities | Graduated: 500 Female: 250 Male: 250 Disaggregated by Competence level achieved by end of JOBA | Total number of graduates, broken down by female and male, of all Technical Training programmes. This number will include those whose graduation is imminent near the programme completion month of April 2021. Technical /vocational / professional training is defined under the TVET Reforms as including theory, practical skills, and attitudes. Technical training provides pathways to higher education levels. A technical qualification must include at least 120 credits (1200 hours of contact learning). | 1) The first assumption is that training organisations can mobilise in time to deliver enhanced training offers to target numbers. 2) The second assumption is that training organisations are able to successfully recruit enough trainees.
Achieved
Means of Measurement
Source: JOBA monitoring system. Data disaggregated by age and gender.
| Output Indicator 1.2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration
| Number of graduates who are provided with more than 6 months and less than 2 years of training at appropriate competence levels (technical, vocational, occupational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund |  | na (prior to grant awards) | na (prior to grant awards) | Grants awarded that make provision for additional 2000 persons to be enrolled in voational/occupational training, with targets disaggregated by gender | Graduated: 500 Female: 200 Male: 300 JOBA completes follow up on findings of due diligence for all Round 1 and 2 grantees. Routine monitoring of grants implemented in line with workplans for MEL | Graduated: 750 Female: 300 Male: 450 Measures introduced by grantees to improve quality of training provision, and of wrap around services and plan for sustainability, in line with grant business plans | Graduated: 1150 Female: 460 Male: 690 JOBA grantees delivering training have successfully achieved ANEP accreditation of JOBA funded programmes where relevant | Total Graduated: 2400 Female: 960 Male: 1440 Disaggregated by Competence level achieved by end of JOBA | Total number of graduates, broken down by female and male, and by qualification level of all TVSCE training 6-23 months in length. Wrap-around services will also be measured. Occupational training offers training in skills only, without theory. The qualification carries less than 120 credits, ie. less than 1200 contact learrning hours.
| Number of graduates who are provided with 3-6 months of training at appropriate competence levels (technical, vocational, occupational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund |  | na (prior to grant awards) | na (prior to grant awards) | First Round 3 proposal presented to Investment committee | Graduated 220 Female: 110 Male: 110 20% of JOBA grantees delivering short vocational or technical training establish tracer surveys to establish the effectiveness of training and wrap around services in transition to employment | Graduated 1400 Female: 700 Male: 700 80% of JOBA grantees delivering short vocational or technical training courses have evaluated training and/or wrap around services and identified areas for improvement | Graduated 1180 Female: 590 Male: 590 80% of all JOBA grantees delivering short vocational or technical training courses implement at least two improvements identified in self-assessments. | Total Graduated: 2800 Female: 1400 Male: 1400 Disaggregated by Competence level achieved by end of JOBA | Total number of graduates, broken down by female and male, and level of training, of all TVSCE training 3-6 months in length. Wrap-around services will also be measured. Occupational training offers training in skills only, without theory. The qualification carries less than 120 credits, ie. less than 1200 contact learrning hours.
Achieved
|  | Planned (T4R) |  | T = 608 M = 264 F = 344 |  |  |  |  | T = 608 M = 264 F = 344
Achieved (T4R)
Means of Measurement
Source: JOBA monitoring system. Data disaggregated by age and gender.
| Output Indicator 1.3 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration
| Number of partnerships that are led or catalysed by JOBA with a particular focus on linking skills providers with the private sector |  | na (prior to Round 3) | na (prior to Round 3) | Strategy for Round 3 developed and Criteria for Round 3 grants revised | 3-4 partnerships brokered with concept notes developed, and at least one business plan submitted to the Investment committee for subsequent contracting | 3-4 additional tangible partnerships leveraged/brokered with contracts signed | JOBA disseminates evidence of sustainable partnerships and of uptake of new partnering strategies by employers, AMEPP and other key stakeholders. Dissemination strategies target training providers, employer networks, AMEPP and ANEP, and relevant Ministries | 6-8 contracts signed for brokered/ leveraged partnerships | Number of contracts signed between private sector entities and TVET service providers, or between private sector entities and representative agencies, that reflect a transformation in relationships between the two parties.
IMPACT WEIGHTING (%) |  | Achieved
80% |  | Means of Measurement | [8 empty] | Risk Rating (Minor, Moderate, Major, Severe)
|  | Source: JOBA monitoring system. Qualitative interviews under Record 2 with training providers | [8 empty] | Moderate
For Output 1, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| Additional £1m for T4R. £8m Employment Fund. Approx £3.6m service provider inputs under JOBA to Output 1 |  |  | Value of grant recipient in-kind contributions estimated at £2m. |  |  |  | £14.6m | 86%
INPUTS (HR) | DFID (FTEs)
A2 (0.3) B2 (0.1)
OUTPUT 2 | Output Indicator 2.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Association of Non-State Training Providers is established and strengthened to support achievement of its mandate and improve the training offers of its members | Association operational and better able to deliver services valued by its members |  | Operational Plan for Association complete | Progress towards Association establishment (interim committee established, statutes agreed by constituent assembly, constitutent assembly held) | Association legally established and formally launched. AMEPP strategic plan is developed, including the identification of services to be supported by JOBA over the period 2018-2020 | AMEPP Executive Director is appointed. Mid-year review of performance of AMEPP secretariat by AMEPP officials is completed and recommendations agreed. Costed annual workplan completed. | AMEPP sustainabiltiy plan is approved by General Assembly in March 2020. | Progress towads AMEPP sustainability is implemented as planned. | AMEPP is financially sustainable, and has staff capacity to deliver services required by members. | The focus in this indicator is on the support JOBA can provide to build sustainablity of AMEPP. This indicator will be informed by JOBA reporting and engagement with AMEPP, as well as two Record 2 tools as follows: 1) key informant interviews with Association officers; 2) key informant interviews with Association members. | 1) One assumption is that there are sufficient numbers of training providers who are interested in joining the Association and engaging in Association activities. 2) A second assumption is that the Association would be willing and able to collect data on members. 3) A third assumption is that Association members are in a position to improve training quality. 4) A forth assumption is that the Association is able to remain relevant and valuable to the majority of its members.
Achieved
| Output Indicator 2.2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
| Number of instructors who have completed a module in the Association’s Training Programme or are beneficiaries of the JOBA Learning Fund activities, disaggregated by those who work for an AMEPP member (part time or full time), and those who do not |  | 0 | n/a | Assessment of AMEPP member priority needs conducted and informs approach to Learning Fund disbursements | JOBA finalises at least one ToR for a Learning Fund contract following consultations to deliver training to AMEPP members and non-member non-state providers. Terms of Reference for two additional contracts to deliver training are drafted. The Learning Fund Guidelines and Implementation Manual revised to reflect revised approach to support to AMEPP. | At least three contracts for delivery of training are awarded with work plans. 200 instructors have accessed at least one module of training through the Learning Fund, disaggregated by Learning Goal. JOBA monitoring confirms that participant institutions are implementing new practices as a result of the training. Lessons learned through JOBA monitoring are shared with AMEPP, ANEP and other relevant bodies. | 200 instructors have had access to additional training through the Learning Fund, disaggregated by Learning Goal. Lessons learned through JOBA monitoring are shared with AMEPP, ANEP and other relevant bodies, and have informed further developments to the training modules implemented through the Learning Fund. | AMEPP (and non-AMEPP) instructors have completed competency-based training courses funded by the Learning Fund. Instructors have completed training on quality management offered via the Learning Fund. Members have completed gender training with support from the Learning Fund. Non-state training providers are implementing the new practices shared through Learning Fund training. | Total number of AMEPP member training providers where 1 number of trainers have received competency-based training. Total number of TVET training providers where 1 number of trainers has received quality management training. % of AMEPP members is calculated based on the total number of members on 1st April at the start of the year being reported. | 1) One assumption is that there are sufficient numbers of training providers who are interested in joining the Association and engaging in Association activities. 2) A second assumption is that there are suitable providers to deliver training under the Fund.
IMPACT WEIGHTING (%) |  | Achieved | [8 empty] | Risk Rating (Minor, Moderate, Major, Severe)
10% |  | Means of Measurement | [8 empty] | Moderate
Source: JOBA monitoring system. Qualitative interviews under Record 2 with the Association and selected members to add further information
For Output 2, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £1.0m approx |  |  | membership fees (value TBC) |  |  |  | £1.0m | 100%
INPUTS (HR) | DFID (FTEs)
A2 (0.1) B2 (0.5)
OUTPUT 3 | Output Indicator 3.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Government of Mozambique functions related to TVET skills sector strengthened | Key government agencies better able to deliver quality maangement and accreditation services |  | 0 | 0 | MoU signed with ANEP to agree specific TA support | Two consultants are appointed to work with ANEP in the areas of quality management and accreditation services. Terms of Reference are agreed. ANEP monthly reports to JOBA confirm progress against the ToR. Activity-based workplan of JOBA support to ANEP to manage quality of TVET provision is agreed. | Proportion of TVET institutions that apply for accreditation who are reviewed is doubled from baseline value (baseline = April 2018) | Proportion of TVET institutions that apply for accreditation who are reviewed remains at 2019/20 levels | Proportion of TVET institutions that apply for accreditation who are reviewed remains at 2019/20 levels | Better able to deliver quality management and accreditation services' refers to the total number of TVET institutions that apply for accredication who are reviewed. It should be noted that ANEP's interest in the nature of JOBA support may change as implementation proceeds. If this changes, the milestones and target would need to be adapted in response. | 1) One assumption is that ANEP officers are available and interested in working with the TA advisers. 2) A second assumption is that ANEP will activate and support the Sector Training Advisory Committees. 3) A third assumption is that the limited financing for government and constraints on the availability of government officers does not constrain these activities. 4) A fourth assumption is that TA support can effectively and sustainably strengthen GoM capacity related to certification. 5) A fifth assumption is that other development partners will be attracted to supporting this sector because of this intervention.
IMPACT WEIGHTING (%) |  | Achieved
10% |  | Means of Measurement | [8 empty] | Risk Rating (Minor, Moderate, Major, Severe)
|  | Source: JOBA monitoring system. Qualitative interviews under Record 2 with stakeholders within and outside Government | [8 empty] | Moderate
For Output 3, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) |  |  |  |  | Total (£) | DFID SHARE (%)
| £1.0m approx | [6 empty] | £1.0m | 100%
INPUTS (HR) | DFID (FTEs)
A2 (0.1) B2 (0.5)

## Changes to Logframe
Impact | 2016 | 2017 | 2018 (March) | 2018 (July) | Explanation
Impact Statement | Higher income among JOBA beneficiaries especially young women and adolescent girls | Higher income among JOBA beneficiaries, especially young womn, in the context of a more effective skills training system | No change | No change | 2016 to 2017: 1) The original Impact Statement only covered the first of the two impact indicators. The revision, adding 'in the context of a more effective skills training system', covers the second indicator. 2) The phrase 'and adolesent girls' was removed from the Impact Statement because it raised a concern that the target was non-legal age adolescents who were not supposed to be in the labour force. 2017 to 2018: no change March 2018 to July 2018: no change
Impact Indicator 1 | Higher income of JOBA Employment Fund ultimate beneficiaries - disaggregated by age, gender, and poverty quintile | Percentage of JOBA Employment Fund training programme graduates who see a real increase in income due to their training | Added 'disaggregated by gender' to the Impact Indicator | No change | 2016 to 2017: 1) The original Impact Indicator 1 did not accommodate income trends unrelated to JOBA and those of relevance to JOBA effects. For this reason, 'real increase in income' was added to the 2017 indicator. 2) The original Impact Indicator 1 did not indicate whether the effect was anticipated across all trainees, or some. This was changed in 2017 to reflect 'percentage of'. 3) All findings, as possible, are presented by age, gender, and poverty quintile, as well as by other measures of interest (e.g., location, length of training, etc.). This component of the 2016 indicator was therefore out of place. Reference to these other measures have been included in the Impact Sub-Sheet. 4) 'Ultimate' was dropped from the phrase because the target was clearly graduates. 2017 to 2018: 1) addition made by DFID/Mozambique March 2018 to July 2018: no change
Impact Indicator 2 | Higher income of graduates from National Association Members - disaggregated by age, gender, and povery quintile | Changes that evidence improved effectiveness* in the skills training system. * referred to: examples of improved effectiveness could include: greater availability of TVET training opportunities, more TVET service provision in priority sectors, improved quality of graduates as reported by private sector, changing perceptions among key actors in the TVET sector including employers, and more women completing TVET training. | No change | No change | 2016 to 2017: 1) The original Impact Indicator 2 focused on an indirect aspect of the JOBA Programme, rather than the element that the JOBA Programme could more specicially focus on. Aiding in the establishment and operations of the Association was already a considerable task, and the multitude of factors that could affect Association members and, therefore, the incomes of graduates from these Association members, meant that including these trainees as a second 'treatment' group was not consistent with the Theory of Change (original or revised). Instead, the emphasis was on systems improvement, consistent with the intent as noted in the Theory of Change. This made Impact Indicator 2 consistent with JOBA Programme actions, focused on systems improvement. 2) At the time that the 2017 Logframe was issued, there was nevertheless ambiguity in what actions would be taken under Output 2 and Output 3 that would strengthen TVET systems. For this reason, it was agreed that this indicator would be revisited at the end of 2017 with an eye to refining it and adding more specificity, along with milestones and a target. For this reason, examples of what systems strengthening might look like were included as a footnote from the end of 2017. 2017 to 2018: no change March to July 2018: no change
Impact Indicator 3 | Rate of return to training (calculated as the difference in total income of S4E Employment Fund ultimate beneficiaries before entering training and (one year) after completion of training, divided by the total unit cost of training | Deleted. | NA | NA | 2016 to 2017: 1) It was felt that a wider range of VfM measures would need to be considered in terms of JOBA Programme returns. 2) It was further considered that this measure of rate of return did not adequately reflect the investments and returns from these investments. 3) It was also felt that this was not an Impact level issue, but rather a JOBA Programme implementation issue. 2017 to 2018: not applicable March to July 2018: not applicable
Outcome Statement 1 | More youth especially young women and adolescent girls acquire marketable skills leading to (self-)employment or further training and education | More Mozambicans, especially young women, have marketable skills applied to productive work | No change | No change | 2016 to 2017: 1) It was felt that the measure was too narrowly focused on employment rather than the application of skills to a wide range of livelihoods actvities. This led to the change from 'self/employment' to 'productive work'. The emphasis remains on employment, including self-employment, but other applications, including for those employed, are also considered. 2) 'Further training and education' was removed because this was not the focus of the Programme. 3) The scenario of 'training --> employment' in the original Statement did not account for those already in employment/self-employment. 4) The phrase 'and adolesent girls' was removed from the Statement because it raised a concern that the target was non-legal age adolescents who were not supposed to be in the labour force. 2017 to 2018: no change March to July 2018: no change
Outcome 1 Indicator 1 | Number of JOBA Employment Fund ultimate beneficiaries in employment (inc. self-employment) or further training or education disaggregated by age, gender, poverty quintile, sector, type of employer, etc. measured 1 year after completion of training | Proportion of JOBA Employment Fund beneficiaries who enter productive employment or who are engaged in more productive work. | Added 'disaggregated by gender' | No change | 2016 to 2017: 1) 'Ultimate' was removed as it was clear that this referred to graduates. 2) All findings, as possible, are presented by age, gender, and poverty quintile, as well as by other measures of interest (e.g., location, length of training, etc.). This component of the 2016 indicator was therefore out of place. Reference to these other measures have been included in the Outcome 1 Sub-Sheet. 3) The focus only on employment was expanded with the phrase 'more productive work', which included those already in employment and the application of skills outside of formal/informal/self-employment. 4) Measurement timing was left to milestones and means of measurement. 2017 to 2018: 1) addition made by DFID/Mozambique March to July 2018: no change
Outcome Statement 2 | Strengthened Mozambican skills training market | No change | Changed 'market' to 'system': Strengthened Mozambican skills training system | No change | 2017 to 2018) Changed 'market' to ' system' to reflect JOBA's concern with support to services that are systemic, particularly the regulation of quality.
Outcome 2 Indicator 1 | Number of systemic changes* in the Mozambican skills training market facilitated by the JOBA Programme. * referred to: improvements in: i) labour market information systems; 2) private sector integration into TVET systems; iii) inclusive training-to-employment models. It as further noted that these changes will be measured by their adoption and integration as standard or best practice by a majority of public and/or non-state skills training providers | Number of non-JOBA grantee National Association members who report positive changes to their training ** aimed at improving the efficacy of training. ** refers to the following examples: measures to retain more women; adoption of more competence-based training approaches; curricula reflect industry inputs and stated needs; number of memorandums of understanding signed with industries; graduates find a job in less time than before; increased number of internships accepted by companies. | Proportion of TVET providers who demonstrate improved quality of market relevant training | No change | 2016 to 2017: 1) The revised 2017 indicator focused more specifically on the National Association, as this was tied more closely to the activities of JOBA. 2) Examples of positive changes were included reflecting likely results of JOBA actions, and National Association member actions, designed to improve training. 2017 to 2018: 1) Significant progress was made on better definition activities under Component 2 of JOBA. 'Market relevance' referred to better matching supply and demand and the financial sustainability of TVET offerings. Financial sustainability is a key challenges for private providers, particularly in TVET where unit costs of delivering training are high. Private providers gain income through fees, and therefore their courses must be relevant to the skills employers are looking for. Students will seek out training that leads to jobs. Employers will use training providers that offer relevant training not only for new entrants but also for ongoing training of employees. The indicators in 2017 listed features of provision which can be considered aspects of quality. Indicator revision in 2018 revised the indicator wording, with the aspects of quality being subsumed into the definitions.
Output 1 | Expanded access to inclusive, affordable, market relevant, quality training and wrap-around services by non-state training providers | No change | No change | No change | 2016 to 2017: no change 2017 to 2018: no change March to July 2018: no change
Output 1 Indicator 1.1 | Number of graduates who were provided technical training combined with wrap-around services through JOBA Fund - disaggregated by age, gender and poverty quintiles | Number of graduates who are provided with Technical Training comprising a norm of 2 or more years of training at appropriate competence levels combined with wrap-around services through the JOBA Employment Fund Disaggregation by age, gender and poverty was removed and included in sub-sheets | No change | No change | 2016 to 2017: 1) Technical training was defined, but only in terms of length of training programme (i.e. over 2 years). This reflects the JOBA team's understanding of the definition of technical training in 2017, and reflects a tradition to deliver technical courses as single programme delivered over three years (and no interim exit opportunities). 2) All findings, as possible, are presented by age, gender, and poverty quintile, as well as by other measures of interest (e.g., location, length of training, etc.). This component of the 2016 indicator was therefore out of place. Reference to these other measures have been included in the Impact Sub-Sheet. 2017 to 2018: no change March to July 2018: no change
Output 1 Indicator 1.2 (part A) | Number of graduates who were provided vocational, second chance or entrepreneurial training combined with wrap-around services through JOBA Fund - disaggregated by age, gender, and poverty quintile | Added from May 2017: Number of graduates who are provided with a norm of more than 6 months to under 2 years of training at appropriate competence levels (vocational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund. | No change | No change | 2016 to 2017: 1) Training was more precisely defined. 2) All findings, as possible, are presented by age, gender, and poverty quintile, as well as by other measures of interest (e.g., location, length of training, etc.). This component of the 2016 indicator was therefore out of place. Reference to these other measures have been included in the Impact Sub-Sheet. 2017 to 2018: no change March to July 2018: no change
Output 1 Indicator 1.2 (part B) | (There was no Part B in the 2016 logframe) | Number of graduates who are provided with a norm of 3-6 months of training at appropriate competence levels (vocational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund. | No change | No change | Output 1 Indicator 1 was divided into two components, A and B, referring respectively to training that lasted more than six months up to two years (A), or 3-6 months (B). This indicator refers to vocational training (as opposed to technical) [defined as 2 years or less of training]. The distinction between A and B reflects the JOBA team's concern with testing the relative effectiveness of shorter courses (less than 6 months) with longer courses (more than 6 months).
Output 1 Indicator 1.3 | Additional private sector resources leveraged for JOBA interventions | Number of partnerships that are led or catalysed by JOBA, with a particular focus on linking skills providers with the private sector. | No change | No change | 2016 to 2017: 1) The original indicator was abandoned because it was not a viable output of the JOBA Programme as it emerged. 2) A new Indicator 1.3 was added that focused on partnerships arising from the actions of JOBA, to generate new forms of partnership, to be supported the Employment Fund. 2017 to 2018: 1) Provided more specific description of how partnerships would proceed. March to July 2018: no change
Output 2 | Strengthened delivery capacity of non-state training providers | Association of Non-State Training Providers is established and strengthened to support achievement of its mandate and improve the training offers of its members. | No change | No change | 2016 to 2017: 1) Output Statement 2 revised to better align with JOBA-specific outputs. 2) Revised Statement included both Association establishment and strengthening. 3) Focus specifically on the quality of training offered by Association members. 2017 to 2018: no change March to July 2018: no change
Output 2 Indicator 2.1 | Association of Non-State Training Providers established and number of active members | Association becomes functional and active, demonstrated by retention of members and entry of new members. | Association better able to deliver services valued by its members | No change | 2016 to 2017: 1) Indicator refined and refocused from JOBA having to show 'number of active members' to rather focus on 'retention' and 'entry of new members', which it can encourage. 2) The actual number of members cannot be determined, but trends in membership can. 2017 to 2018: 1) Shifted to focus specifically on Association services to its members. Measurement at Output level is focused on the extent to which JOBA delivered services aimed at this, as the actual 'better able to deliver services' or whether these services were 'valued by its members' both fall outside of JOBA's control March to July 2018: no change
Output 2 Indicator 2.2 | Number of training providers with improved training quality and/or financial sustainability resulting from Association membership and support*. * referred to: association membership provides a range of benefits including: access to the £500,000 Learning Fund and support to improve: i) training quality; ii) financial sustainability; and iii) gender inclusion | Number of members of the Association of Non-State Training Providers who have completed a module in the Association's Training Programme or are beneficiaries of the JOBA Learning Fund activities. | No change | No change | 2016 to 2017: 1) The 2016 Logframe included outputs that the JOBA Programme could not directly deliver. The 2017 Logframe reflects elements that can be delivered by the Programme. 2017 to 2018: no change March to July 2018: no change
Output 2 Indicator 2.3 | % of training providers with increased number of female graduates as a result of Association membership and support*. * referred to: association membership provides a range of benefits including: access to the £500,000 Learning Fund and support to improve: i) training quality; ii) financial sustainability; and iii) gender inclusion | Deleted | NA | NA | 2016 to 2017: The intent of Indicator 2.3 has been subsumed under indicators 2.1 and 2.2. 2017 to 2018: not applicable March to July 2018: not applicable
Output 3 | Strengthened collaboration on skills training between GoM and the private sector | Government of Mozambique functions related to TVET skills sector planning strengthened. | No change | No change | 2016 to 2017: 1) The 2016 Logframe included outputs that the JOBA Programme could not directly deliver. The 2017 Logframe reflects elements that can be delivered by the Programme. 2017 to 2018: no change March to July 2018: no change
Output 3 Indicator 3.1 | Number of activities to support GoM's implementation of private sector elements of new TVET law*. * referred to the up to 1% levy, public-private-partnerships, sector skills councils, autonomy of state training schools, and the inclusion of the Permanent Secretary on their new governing bodies | Completion of relevant TA support to GoM's implementation of private sector elements of new TVET law. | Key government agencies better able to deliver quality management and accreditation services | No change | 2016 to 2017: Changed to reflect the direction of support from JOBA. However, definitions of the specific types of support were not identified by the end of 2017. 2017 to 2018: 1) Progress made in determining the specific focus for Output 3 occurred in the second half of 2017, allowing a more specific indicator to be developed for March 2018. Focus was specific to accreditation in ANEP, and ANEP's delivery of 'quality services'. March to July 2018: no change
Impact Weightings | No impact weightings were included | 80% Output 1, 10% Output 2, 10% Output 3 | No change | No change | 2016 to 2017: Impact weightings were added. 2017 to 2018: No changes March to July 2018: No changes
Milestone Timelines | Revised from 2015 to 2016 | Revised from 2016 to 2017 | Revised from 2017 to 2018 | No change | 2016 to 2017: A range of milestones were reviewed and revised. 2017 to 2018: Virtually all milestone timings were adjusted from 2017 to 2018 to reflect the status of the Programme timeline post-Inception. March to July 2018: No change
Milestone Content | Revised from 2015 to 2016 | Revised from 2016 to 2017 | Revised from 2017 to 2018 | Revisions from March - July 2018 for 1.1, 1.2A, 1.2B, and 2.2 | 2016 to 2017: A range of milestones were reviewed and revised. 2017 to 2018: Virtually all milestone timings were adjusted from 2017 to 2018 to reflect the status of the Programme timeline post-Inception. March to July 2018: changes to 1.1, 1.2a, 1.2b, and 2.2 based on comments from DFID/Mozambique.
Sources | Revised from 2015 to 2016 | Revised from 2016 to 2017 | Revised from 2017 to 2018 | No change | 2016 to 2017: Sources have been extensively elaborated and are implementable. 2017 to 2018: Sources further refined. March to July 2018: No change
Assumptions | Revised from 2015 to 2016 | Revised from 2016 to 2017 | Revised from 2017 to 2018 | No change | 2016 to 2017: Assumptions were initially elaborated. 2017 to 2018: Assumptions extensively elaborated based on meetings with DFID/Mozambique to ensure that all assumptions are 'unpacked' (separated) and clear. March to July 2018: No change

## Overall Fig.
MAP OF LOGFRAME (COMPONENTS & DATA SOURCES)
UNDER CONSTRUCTION (TIMELINE OF DATA COLLECTION & SOURCES)

## Summary&Responsibilities
IMPACT | Impact Indicator 1 | Summary Focus | Data Source(s) | Frequency (Temporal) | Who Leads | Who Supports
Higher income among JOBA beneficiaries, especially young women, in the context of a more effective skills training system | Percentage of JOBA Employment Fund training programmed graduates who see a real increase in income due to their training, disaggregated by gender and age | Proportion of graduates who show improved income | Coffey Impact Evaluation Tracer Surveys; Course Initiation Survey (Form 1) & JOBA-Tracer Surveys | JOBA team for Course Initiation Survey (Form 1) & JOBA Tracer surveys for all students follow up 2x (6 months). Coffey: Baseline, Endline, and Tracer (1 year after training completion); | Coffey International for Impact Assessment; JOBA M&E Lead; M&E Adviser | International MEL Advisor supported questionnaire development with external evaluator; ODK (Form 2) Consultant
| Impact Indicator 2 | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
| Changes that evidence improved effectiveness in the skills training system | TVET system effectiveness (Improved access, market relevance, quality and inclusiveness) | Coffey Impact Evaluation; Coffey Qualitative Evaluation; Course Completion Survey (Form 2; JOBA Qualitative Study (Record 2) with graduates and employers; JOBA-Tracer Surveys (6 months); ANEP monthly reports on accreditation; | Coffey: Impact Evaluation (Baseline, Tracer & Endline); JOBA: Course Completion, timing varies per grantee; JOBA Tracer, 6-months post-graduation, timing varies per grantee; JOBA Qualitative Study (2x collection, 2019/2020); Monitoring Data (Supplemental) Quarterly and annual reports; ANEP monthly reports) | Coffey International for Impact Assessment; JOBA Team Lead & JOBA M&E Lead; M&E Adviser | JOBA Officer responsible for leading Outcome 2; ANEP/AMEPP staff responsible for quarterly/monthly reporting
OUTCOME 1 | Outcome 1 Indicator | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
More Mozambicans, especially young women, have marketable skills applied to productive work | Proportion of JOBA Employment Fund beneficiaries who enter productive employment or who are engaged in more productive work, disaggregated by gender and age | Graduates able to secure better employment, or improved employment/business/livelihoods | Coffey Tracer & Endline Surveys; JOBA Tracer Survey | Coffey: Impact Evaluation (Baseline, Tracer & Endline); Coffey Qualitative Study (Baseline/Endline), barriers and employment; JOBA Tracer Survey, 6-months post-graduation, timing varies per grantee; | Coffey International for Impact Assessment; JOBA Team Lead & M&E Lead | International MEL Advisor, National MEL Manager; Tracer Survey Consultant
OUTCOME 2 | Outcome 2 Indicator | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
Strengthened Mozambican skills training system | Proportion of TVET providers who demonstrate improved quality of market relevant training | Improved quality and market relevance of training offers | Coffey Qualitative Study; ANEP monthly reports to JOBA on accreditation and QMS scores; Course Completion Survey (Form 2); JOBA Qualitative Study (Record 2 (Employer panel discussions on quality of JOBA beneficiaries/trainees)) | Coffey Qualitative (Baseline & Endline); JOBA Qualitative Study (2x collection, 2019/2020); Monitoring data (ANEP & service delivery): Monthly & quarterly | Coffey International; JOBA Team Leader to lead various information collection and reporting; ANEP/AMEPP Accreditation Data | JOBA Component Lead (2&3); JOBA M&E Adviser; Grantee Quarterly Data (Required Monitoring)
OUTPUT 1 | Output Indicator 1.1 | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
Expanded access to inclusive, market relevant, quality training and wrap-around services by non-state training providers | Number of graduates who are provided with Technical Training comprising a norm of 2 or more years of training at appropriate competence levels combined with wrap-around services through the JOBA Employment Fund | Trainees who completed technical training course (at least 2 years of training) and graduated, with wrap-around services offered | Coffey Impact Evaluation Surveys (Baseline, Tracer & Endline); JOBA Course Completion Survey | Coffey: Impact Evaluation (Baseline, Tracer & Endline), phased collection; JOBA Course Completion Survey, varies per grantee; Secondary data: Retention/Dropout & Graduation Rates monitored quarterly | Coffey International; JOBA Grants Manager & JOBA M&E Lead/M&E Adviser | Component Leads; Grantee Quarterly Data (Required Monitoring)
| Output Indicator 1.2 (Part A & B) | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
| Part A: Number of graduates who are provided with a norm of more than 6 months to under 2 years of training at appropriate competence levels (vocational, occupational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund. Part B: Number of graduates who are provided with a norm of 3-6 months of training at appropriate competence levels (vocational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund | Trainees who completed course (vocational, occupational, second chance or entrepreneurial) of 6 mo.-2 years OR 3-6 mo., who graduated, with wrap-around services offered. | Coffey Impact Evaluation Surveys (Baseline, Tracer & Endline); JOBA Course Completion Survey | Coffey: Impact Evaluation (Baseline, Tracer & Endline), phased collection; JOBA Course Completion Survey, varies per grantee; Secondary data: Retention/Dropout & Graduation Rates monitored quarterly | Coffey International; JOBA Grants Manager & JOBA M&E Lead/M&E Adviser | Component Leads; Grantee Quarterly Data (Required Monitoring)
| Output Indicator 1.3 | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
| Contracts/memorandums of understanding issued for partnerships that are catalyzed by JOBA, with a particular focus on linking skills providers with the private sector | High level partnerships leverages via JOBA between the private sector and TVET providers | JOBA monitoring/reporting system (Grantee quarterly reporting & specifically asked about during bi-annual reviews (facilitator-lead performance reviews)). | Quarterly and annually | JOBA Team Leader, JOBA M&E Lead | JOBA officer responsible for Indicator 1.3 activities
| Output Indicator 1.4 | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
|  | High level partnerships leverages via JOBA between the private sector and TVET providers | JOBA monitoring/reporting system (Grantee quarterly reporting & specifically asked about during bi-annual reviews (facilitator-lead performance reviews)). | Quarterly and annually | JOBA Team Leader, JOBA M&E Lead | JOBA officer responsible for Indicator 1.3 activities
OUTPUT 2 | Output Indicator 2.1 | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
Association of Non-State Training Providers is established and strengthened to support achievement of its mandate and improve the training offers of its members | Association better able to deliver services valued by its members | AMEPP able to deliver quality services to its members | Documentation on the establishment of AMEPP; AMEPP Quarterly & Monthly Reporting of Activities: Submitted performance reports; AMEPP voluntary member survey (annual; 2019, 2020) | Quarterly and annually from April-June 2018 quarter; Annual AMEPP member survey | JOBA Officer responsible for Output 2 | JOBA National MEL Manager; JOBA M&E Lead; M&E Adviser
| Output Indicator 2.2 | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
| Number and percentage of members of the Association of Non-State Training Providers who have completed a module in the Association’s Training Programme or are beneficiaries of the JOBA Learning Fund activities | Completion of training modules from AMEPP | Training Module Registration & Attendance Logs; Training exit surveys; Supplemented by JOBA quarterly AMEPP reports | Trainings hosted (2-3x per year) (JOBA/AMEPP)- Registration/Attendance & Exit Surveys | JOBA Officer responsible for Output 2; AMEPP Executive Director (requirement of monthly reports on secretariat) | JOBA National MEL Manager
OUTPUT 3 | Output Indicator 3.1 | Summary Focus | Data Source(s) | Frequency | Who Leads | Who Supports
Government of Mozambique functions related to TVET skills sector planning strengthening | ANEP better able to deliver quality management and accreditation services | Strengthened quality management system and accreditation services | ANEP Monthly Reports to JOBA; JOBA Qualitative Study (Record 2) (with grantees/TVET providers; Exit Survey of Participants of QMS/ANEP Training; Coffey Qualitative Study (grantees reflect on accreditation process) | Coffey Qualitative (Baseline & Endline); JOBA Qualitative Study (2x collection, 2019/2020); Monitoring data (ANEP & service delivery): Monthly & quarterly | Coffey International; JOBA Officer responsible for Output 3; JOBA Team Leader; JOBA M&E Advisor; AMEPP Executive Director (liaison); ANEP staff (liaison and coordination) | JOBA National MEL Manager

## Impact
Impact | Statement/Indicator | Definitions | Measurement
Impact Statement | Higher income among JOBA beneficiaries, especially young women, in the context of a more effective skills training system
Impact Indicator 1 | Percentage of JOBA Employment Fund training programme graduates who see a real increase in income due to their training, disaggregated by gender | Real income increase: is defined as an increase in a graduate's actual financial earnings. Because of the difficult economic conditions in Mozambique, it also includes the ability of a graduate to protect her/his income, whether that is in cash or in kind. While the measurement refers to the individual graduate, measurement of impacts cover household level effects and not just individual contribution. | Income increase: Coffey Impact Evaluation (comparative income between Baseline & Tracer Survey (12 months post-graduation), measured as household income, improvement measured against baseline levels and above PPI; Form 1 & JOBA-Tracer Surveys (6 months post-graduation); This is measured in detail in the Impact Assessment Tracer Surveys among a subset of cohorts. Income will be measured at individual and household levels. Increases will be compared by gender, grantee & course completed (technical, vocational, etc.), local market landscape/geography, sector and wrap-around services offered. Findings would be presented across gender of trainee, gender of household head, location, socio-economic status, and vulnerability measures.
Impact Indicator 2 | Changes that evidence improved effectiveness in the skills training system | Effectiveness: refers to greater availability of TVET training opportunities (access), more TVET service provision in priority sectors (market relevance), improved quality (of graduates and TVET training institutions), and more women completing TVET training. | Greater Availability of TVET (Access): Coffey Impact Evaluation of number of students and graduates, compared across cases (grantees) and controls; Coffey Qualitative Evaluation (questions included for student and employers about access and barriers); Course Completion Survey (Form 2_ (student response on increased access, including scholarship details/models); Quarterly Grantee Reports on scholarship assistance distribution and number of students/graduates/retention rates. Service Provision in Priority Sector (Market Relevance): Coffey Impact Evaluation (Improved transition to work rates (young people); Coffey Qualitative Evaluation (questions included about market, job fit and appropriateness of training modules); Findings of 6-month tracer survey (questions about skill use and fit-of-market training); Record 2 (Employer panel discussions on quality of JOBA beneficiaries/trainees) Improved Quality: ANEP monthly reports on accreditation and QMS scores (specifically Leadership & Student Success/Satisfaction scores) reported by grantee institutions (compared to average/mean of all institutions); AMEPP's/JOBA's training modules exit survey; AMEPP & Implementation of New TVET Law: Number of grantees and AMEPP members with active or approved accreditation applications (increased by the translation toolkit and trainings on the new TVET law provided by JOBA and AMEPP in partnership with ANEP) Results from Form 2 (student satisfaction module/section); Bi-annual performance reviews of grantees (assessing components of quality training delivery, scored are red, amber or green); More Women: Coffey Impact Evaluation (assessing increased number of women, case-control of graduates; also assessing employment status case-control of women graduates); Coffey Qualitative Evaluation (Students and grantees about recruitment, retention and specific barriers to access of training and employment, disaggregated analysis by gender and age); Form 2 & JOBA-Tracer Surveys of women graduates over time in accordance with Targets and job placement.

## Outcome1
Outcome | Statement/Indicator | Definitions | Measurement
Outcome 1 | More Mozambicans, especially young women, have marketable skills applied to productive work | Marketable skills: refer to skills that are identified as relevant to formal, self or other employment that contribute to employability.
Outcome 1 Indicator 1 | Proportion of JOBA Employment Fund beneficiaries who enter productive employment or who are engaged in more productive work, disaggregated by gender and age (youth) | Productive Employment: Applied to productive work: refers describes productive employment as ‘employment yielding sufficient returns to labor to permit the worker and his/her dependents a level of consumption above the poverty line' and/or contribute to the family livelihoods of being more productive. Youth: All Mozambican individuals age group from 15 to 35 years. | Productive Employment/More productive work: proportion of graduates who report employment (formal, self-employed or contributing to household livelihood) in Tracer Survey (6 months) compared to reported employment and income status in Form 1; Coffey Tracer Survey (12 months), compared to control Tracer Survey (12 months) 'More' is defined as the type of 'work' graduate is engaged with in comparison to reported 'work' in Coffey Baseline Survey and/or Form 1. Findings would be presented across gender of trainee, gender of household head, geography, socio-economic status, and age (youth, non-youth).

## Outcome2
Outcome | Statement/Indicator | Definition | Measurement
Outcome 2 | Strengthened Mozambican Skills Training System
Outcome 2 Indicator 1 | Proportion of TVET providers who demonstrate improved quality of market relevant training | TVET provider: Any organization or institute (public or private) that provides technical and vocational training that are registered with ANEP, including the institutions formerly registered with DNET/IFBELAC (accreditation is not a requirement) Quality is defined in Output 1&2. Market relevant training: deliver training relevant to labour market needs and design courses specific to the different sectors and types of employment. | Improved quality: Coffey Qualitative Study (Baseline/Endline) on training experience; ANEP monthly reports on accreditation and QMS scores (specifically Leadership & Student Success/Satisfaction scores) reported by grantee institutions (compared to average/mean of all institutions); AMEPP's/JOBA's training modules exit survey; Results from Course Completion Survey Form 2 (student satisfaction module/section); Bi-annual performance reviews of grantees (assessing components of quality training delivery, scored are red, amber or green) Market relevant training: Coffey Impact Evaluation (Improved transition to work rates (young people); Findings of 6-month tracer survey (questions about skill use and fit-of-market training); JOBA Qualitative Study (Record 2) (Employer panel discussions on quality of JOBA beneficiaries/trainees)

## Output1
Output | Statement/Indicator | Definitions | Measurement (how/what tool, data collection process)
Output 1 | Expanded access to inclusive, market relevant, quality training and wrap-around services by non-state training providers | Access': 'Inclusive: is defined as providing opportunities for all trainees to learn, through strategies that address constraints faced by particular groups of learners depending on training area (needs to include gender and youth). Market relevance & Quality of Training (defined below) Wrap around services: Training provision and support services which are additional to technical training and which enable the learner to access training, benefit from it, and enter employment. With reference to the JOBA Programme, they include: access to employment networks, HR support (preparing CVs, interview techniques, etc.), work placements / internships / apprenticeships and support to set up or expand a business (preparing a business plan, angel investing, access to finance, etc.).
Output 1 Indicator 1.1 | Number of graduates who are provided with Technical Training comprising a norm of 2 or more years of training at appropriate competence levels combined with wrap-around services through the JOBA Employment Fund | Technical training: normally considered to be part of tertiary education (post-secondary). The qualifications offer a bridge from secondary to higher education levels. Wrap-around services defined above. | Number of graduates: Measured by Coffey Endline Surveys per grantee (4-5) on competence and wrap-around services, compared to control; Course Completion Survey Form 2 (completed upon course completion), captures competence level completed and the wrap-around services provided (self-reported by graduate, survey format by enumerator) Drop-outs and retention rates will be generated based on quarterly reported metrics from grantees and completed Form 2.
Output 1 Indicator 1.2 Part A | Number of graduates who are provided with a norm of more than 6 months-2 years of training at appropriate competence levels (vocational, occupational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund | Vocational Training: normally considered to be part of upper secondary education Occupational Training: training that develops specific competences that a learner must be able to do to perform a work role competently Entrepreneurial Training: training on designing, launching and running a new business. Second chance: A trainee who missed out on the level of training earlier in life, and needs to resume learning later in life in order to engage successfully with the labor market or improve their employment or self-employment prospects. education levels. Wrap-around services defined above. Note: The Employment Fund there are two categories of graduates: ‘technical’ (2000) and ‘vocational/second chance/entrepreneurship’ (3000). ‘Second chance’ learners, while accommodated in distinct programmed that may attract a grant, should be supported to become ‘vocational’ graduates. In some cases vocational graduates could become trainees in technical training programmes. | Number of graduates: Measured by Coffey Endline Surveys per grantee (4-5) on competence and wrap-around services, compared to control for 6 months-2 year norm/competence level, disaggregated by vocational, occupational, second chance and entrepreneurial; Form 2 (completed upon course completion), captures competence level completed and the wrap-around services provided (self-reported by graduate, survey format by enumerator). Drop-outs and retention rates will be generated based on quarterly reported metrics from grantees and completed Form 2.
Output Indicator 1.2 Part B | Number of graduates who are provided with a norm of 3 months-6 months of training at appropriate competence levels (vocational, occupational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund | Same definitions as above (Indicator 1.2 Part A). | Number of graduates: Measured by Coffey Endline Surveys per grantee (4-5) on competence and wrap-around services, compared to control for 6 months-2 year norm/competence level, disaggregated by vocational, occupational, second chance and entrepreneurial; Form 2 (completed upon course completion), captures competence level completed and the wrap-around services provided (self-reported by graduate, survey format by enumerator). Drop-outs and retention rates will be generated based on quarterly reported metrics from grantees and completed Form 2.
Output 1 Indicator 1.3 | Number of partnerships that are led or catalyzed by JOBA with a particular focus on linking skills providers with the private sector | Partnerships: A formalized contract/MoU between a TVET provider and the a private sector entity that was facilitated or brokered by Joba personnel or through JOBA-specific activities. | Reported and tracked number of contracts/MoUs agreed form the measurement. The purpose of partnerships between providers and the private sector is to improve the relevance, quality and effectiveness of skills training. This reporting will be noted in the grantee quarterly reporting & specifically asked about during bi-annual reviews (facilitator-lead performance reviews).
Output 1 Indicator 1.4 | Improved access to inclusive, market relevant, quality training and wrap-around services by non-state training providers | Inclusive: is defined as providing opportunities for all trainees to learn, through strategies that address constraints faced by particular groups of learners depending on training area (needs to include gender and youth). Market relevance (training): deliver training relevant to labour market needs and design courses specific to the different sectors and types of employment. Quality Training: skills development provision is considered to be good quality if it trainees develop skills required, at the level of skill required, to be employed or self-employed, engaged in decent work, and is relevant to their economic and social context. Quality in Mozambique includes compliance with TVET law; Use the ANEP quality system to measure quality) QMS, self-assessment); Gender-inclusion (access for all) Wrap around services: Training provision and support services which are additional to technical training and which enable the learner to access training, benefit from it, and enter employment. With reference to the JOBA Programme, they include: access to employment networks, HR support (preparing CVs, interview techniques, etc.), work placements / internships / apprenticeships and support to set up or expand a business (preparing a business plan, angel investing, access to finance, etc.). | Appropriate competency level is measured via a checklist employed on field visits to check the extent to which the training institution is offering training services relevant for the course and for the trainees, and also Expanded Access: Coffey Impact Evaluation of number of students and graduates, compared across cases (grantees) and controls; Inclusion: Establishment of policies and strategies for inclusion; record completion and compliance with 'best practices' for grantees (according to JOBA Gender strategy or Gender Adviser); completion and implementation of Safeguarding Policy and Procedures Wrap-around services: Coffey Tracer & Endline Survey assessing the fidelity of wrap-around services offered and student preferences. Coffey In-depth Interviews (IDIs) with Employers and Students inquiring about the validity and value of wrap-around services; Level/Course Completion Form 2 (student feedback on wrap-around services); Record 2 (Grantees IDIs and Employer panels) about the delivery, quality and appropriateness of wrap-around services (differ by grantee); generation of comparative table of wrap-around services offered by all grantees Improved quality: ANEP monthly reports on accreditation and QMS scores (specifically Leadership & Student Success/Satisfaction scores) reported by grantee institutions (compared to average/mean of all institutions); AMEPP's/JOBA's training modules exit survey; Results from Form 2 (Training Level Completion Form, specifically student satisfaction module/section); Bi-annual performance reviews of grantees (assessing components of quality training delivery, scored are red, amber or green) Market relevant training: Coffey Impact Evaluation (Improved transition to work rates (young people); Findings of 6-month tracer survey (questions about skill use and fit-of-market training); Record 2 (Employer panel discussions on quality of JOBA beneficiaries/trainees); Wrap-around services

## Output2
Output | Statement/Indicator | Definitions | Measurement
Output 2 | Association of Non-State Training Providers is established and strengthened to support achievement of its mandate and improve the training offers of its members | Association of Non-State Private Providers: is considered established when its statutes are passed by the first meeting of a General Assembly. AMEPP's work is guided by a Strategic Plan. The activities prioritized within this Plan form the basis for JOBA support in agreed areas. Quality: Skills development provision is considered to be good quality if it trainees develop skills required, at the level of competency required, to be employed or self-employed, engaged in decent work, and is relevant to their economic and social context. Components of quality are defined by ANEP using the Quality Measurement Survey (QMS)
Output 2 Indicator 2.1 | Association is operational, and better able to deliver services valued by its members | AMEPP's work is guided by a Strategic Plan. The activities prioritized within this Plan form the basis for JOBA support in agreed areas. These will be included in a version of the Strategic Plan shared with DFID/Mozambique, and elaborated in JOBA's quarterly reports. | Operational: Documentation on the establishment of AMEPP, and placement of JOBA-supported staff in secretariat role (Executive Director). Delivery of services: AMEP Quarterly & Monthly Reporting of Activities: Submitted performance reports will be tracking achievement of activities agreed upon in AMEPP's strategic plan, notably, function of the secretariat, financial capacity and training modules for members. Elective AMEPP Member Survey: Results from an elective AMEPP member survey reporting on the valued services and opportunities for improvement by members.
Output 2 Indicator 2.2 | Number and percentage of members of the Association of Non-State Training Providers who have completed a module in the Association’s Training Programme or are beneficiaries of the JOBA Learning Fund activities | Number of members: refers to the number of trainees from AMEPP members (institutions currently paying the fees) who completed training. Number of training organizations refers to the number of training organizations with at least one trainer who has completed training. Percentages are of the total number of trainees and total number of training organizations. Training Program (Association or through the JOBA Learning Fund) will be ToT trainings on key institutional topics such as CBT, gender training and quality management. | Training Module Registration & Attendance Logs: The number and percentage of members of AMEPP completing the module or benefitting from the JOBA learning fund form the measurement of progress against this indicator. Module Curriculum: Submitted module curriculum with noted alignment of international and national standards for accreditation, certification, and best practices. Training exit surveys: Attendees will be requested to submit a exit survey on the training module.

## Output3
Output | Statement/Indicator | Definitions (Indicator) | Measurement
Output 3 | Government of Mozambique functions related to TVET skills sector strengthened | TVET skills sector: Encompasses the TVET skills sector: encompasses more than just the formal through work; Labor market information and regulation of quality of training provision.
Output 3 Indicator 3.1 | Key government agencies (ANEP) better able to deliver quality management and accreditation services | Better accreditation services: refers to the total number of TVET institutions that apply for accreditation who are reviewed by ANEP in an agreed timeline in a competent manner Quality Management: refers to transparent communication about standards and processes of accreditation, as well as a timely and fair handling of the accreditation procedures by ANEP | ANEP Monthly Reports to JOBA: Number of providers accredited (cumulative, by public/private); number of providers evaluated; number of providers supported to prepare self-assessment; JOBA Qualitative Study (Record 2) (with grantees/TVET providers) on the challenges of getting accredited; QMS & Accreditation Training- Exit Survey of Participants;

## May2016Logframe
ANNEX 1 - S4E LOGICAL FRAMEWORK EDRM: 4719601 revised 31May16
SKILLS FOR EMPLOYMENT (S4E) PROGRAMME
IMPACT | Impact Indicator 1 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01
Higher income among JOBA beneficiaries especially young women and adolescent girls | Higher income of JOBA Employment Fund ultimate beneficiaries - disaggregated by age, gender and poverty quintile | 10% increase of income 1 year after completion of training with wrap-around services | 0 | 0 | no result yet | 10% | 10% | 10% | 10%
Achieved
Source
Regularly updated Tracer systems' reports, Sample surveys
| Impact Indicator 2 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01
| Higher income of graduates from National Association members - disaggregated by age, gender and poverty quintile | 5% increase of income 1 year after completion of training in a training programme from an Association Member | 0 | 0 | no result yet | 5% | 5% | 5% | 5%
Achieved
Source
Regularly updated Tracer systems' reports, Sample surveys
| Impact Indicator 3 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01
| Rate of return to training (calculated as the difference in total income of S4E Employment Fund ultimate beneficiaries before entering training and [one year] after completion of training, divided by the total unit cost of training) | All non-state TVET 18% | To be established | All non-state TVET - 18% | All non-state TVET - 18% | All non-state TVET - 18% | All non-state TVET - 18% | All non-state TVET - 18% | All non-state TVET - 18%
Achieved
Source
Regular data from grantees
OUTCOME 1 | Outcome 1 Indicator | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01 | Assumptions
More youth especially young women and adolescent girls acquire marketable skills leading to (self-)employment or further training and education | Number of JOBA Employment Fund ultimate beneficiaries in employment (including self-employment) or further training or education disaggregated by age, gender, povery quintile, sector, type of employer, etc. measured 1 year after completion of training. | TT: 1700 (of which 25% are women) VSCE: 2100 (of which 50% are girls/women) | 0 | 0 | TT: 0 VSCE: 0 (Too early to report) | TT: 970 (of which 25% are women); VSCE: 1050 (of which 50% are girls/women) | TT: 1250(of which 25% are women) VSCE: 1470 (of which 50% are girls/women) | TT: 1530 (of which 25% are women) VSCE: 1960 (of which 50% are girls/women) | TT: 1700 (of which 25% are women) VSCE: 2100 (of which 50% are girls/women) | 1. Better skills lead to more and better employment in the formal sector; 2. Better skills lead to higher levels of gainful employment in the informal sector; 3 Wrap-aound assistance facilitates training-to-work transition.
Achieved
Source
Tracer systems' data from Employment Fund grantees
OUTCOME 2 | Outcome 2 Indicator | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01 | Assumptions
Strengthened Mozambican skills training market | Number of systemic changes* in the Mozambican skills training market facilitated by the JOBA Programme | 5 | 0 | 0 | 0 | 1 | 2 | 4 | 5
Achieved
Source
Employer surveys; Quarterly Reports of systemic interventions and their effects
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £17m |  |  | TVET Provider Costs - £4.8m |  |  |  | £21.8m | 78%
INPUTS (HR) | DFID (FTEs)
A1 (0.05) PSD A2 (0.4) EA A2 (0.05) B2 (0.2)
* Examples of systemic changes in the Mozambican skills training market includes improvements in: i) labour market information systems (LMIS; ii) private sector (PS) integration into TVET systems; and iii) inclusive training-to-employment models. These changes will be measured by their adoption and integration as standard or best practice by a majority of public and/or non-state skills training providers.
OUTPUT 1 | Output Indicator 1.1 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01 | Assumptions
Expanded access to inclusive, affordable, market relevant, quality training and wrap-around services by non-state training providers | Number of graduates who were provided technical training combined with wrap-around services through JOBA Fund - disaggregated by age, gender and poverty quintile | 2000, including 25% women | 0 | T = 0 M = 0 F = 0 | T = 225 M = 170 F = 55 | T = 970 M = 728 F = 242 | T = 1,420 M = 1.065 F = 355 | T = 1,870 M = 1,403 F = 467 | T = 2,000 M = 1,500 F = 500 | 1. Non-state TVET is attuned to labour market demands; 2. Increased access leads to increased successful completion and acquisition of skills; 3 Wrap around assistance facilitates training-to-work transition NOTE: Targets are based on one-year courses. If courses are shorter, the numbers will increase, and if the courses are longer the numbers will be lower.
Achieved
Source
JOBA Employment Fund management information system
| Output Indicator 1.2 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01
| Number of graduates who were provided vocational, second chance or entrepreneurial training combined with wrap-around services through JOBA Fund - disaggregated by age, gender and poverty quintile | 3000, including 50% adolescent girls and women | 0 | T = 0 M = 0 F = 0 | T = 350 M = 175 F = 175 | T = 1,516 M = 758 F = 758 | T = 2,216 M = 1,108 F = 1,108 | T = 2,916 M = 1,458 F = 1,458 | T = 3,000 M = 1,500 F = 1,500
Achieved
Source
JOBA Employment Fund management information system
IMPACT WEIGHTING (%) | Output Indicator 1.3 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01
| Additional private sector resources leveraged for JOBA interventions | £4.8m | 0 | 0 | £1m | £2m | £3m | £4m | £4.8m
Achieved
|  | Source | [7 empty] | RISK RATING
|  |  | JOBA Employment Fund management informations system | [6 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £9.8m | Additional £1m for T4R; possible additional funding from other development partners |  | TVET provider costs = £4.8m |  |  |  | £14.6m | 67%
INPUTS (HR) | DFID (FTEs)
A2 (0.2) B2 (0.1)
OUTPUT 2 | Output Indicator 2.1 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01 | Assumptions
Strengthened delivery capacity of non-state training providers | Association of non-state training providers established and number of active members | Association self-reliant with more than 100 members | 0 | Business Case for Association complete | Association established |  |  |  | Association self-reliant with more than 100 members | 1. Sufficient non-state training providers are interested in participating actively in the association; 2. The association can be effective in collecting information about non-state training; 3. Non-state providers appreciate the importance of improving: quality, financial sustainability and gender inclusion
Achieved
Source
Programme monitoring reports
| Output Indicator 2.2 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01
| Number of training providers with improved training quality and/or financial sustainability resulting from Association membership and support* | 50% of the association's members offer improved quality training or are more financially sustainable | Quality indicators to be determined with participation of subjects | association not yet established | 10% of the association's members offer improved quality training or are more financially sustainable | 20% of the association's members offer improved quality training or are more financially sustainable | 30% of the association's members offer improved quality training or are more financially sustainable | 40% of the association's members offer improved quality training or are more financially sustainable | 50% of the association's members offer improved quality training or are more financially sustainable
Achieved
Source
Association data, signed charter, membership records, financial accounts; Training Providers’ annual accounts, training records; JOBA Programme national M&E reports
IMPACT WEIGHTING (%) | Output Indicator 2.3 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01
| % of training providers with increased number of female graduates as a result of Association membership and support* | 75% of the association's members have higher female intake | Baseline data to be established with weighting for traditionally male and female courses and occupations | association not yet established | 10% of the association's members have higher female intake | 40% of the association's members have higher female intake | 50% of the association's members have higher female intake | 60% of the association's members have higher female intake | 75% of the association's members have higher female intake
Achieved
|  | Source | [7 empty] | RISK RATING
|  | Association data, signed charter, membership records, financial accounts; Training Providers’ annual accounts, training records; JOBA Programme national M&E reports | [7 empty] | Low/Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £1.0m | [6 empty] | £1.0m | 100%
INPUTS (HR) | DFID (FTEs)
A2 (0.06) B2 (0.06)
* Association membership provides a range of benefits including: access to the £500,000 Learning Fund and support to improve: i) training quality; ii) financial sustainability; and iii) gender inclusion.
OUTPUT 3 | Output Indicator 3.1 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01 | Assumptions
Strengthened collaboration on skills training between GoM and the private sector | Number of activities to support GoM's implementation of private sector elements of new TVET law* |  | TVET Act passed by Parliament | Total of 0 activities to support GoM's implementation of private sector elements of new TVET law implemented | Total of 2 activities to support GoM's implementation of private sector elements of new TVET law implemented | Total of 3 activities (cumulative) to support GoM's implementation of private sector elements of new TVET law implemented | Total of 4 activities (cumulative) to support GoM's implementation of private sector elements of new TVET law implemented | Total of 5 activities (cumulative) to support GoM's implementation of private sector elements of new TVET law implemented | Total of 5 activities to support GoM's implementation of private sector elements of new TVET law implemented | 1. Adequate resources from other development partners available to implement the development, piloting and implementation of labour market information system, including support for the IT systems. 2. Continued agreement between JOBA and DOMT about prioritisation of skills planning systems within the overall LMIS.
Achieved
Source
GoM - promulgation of the TVET Law implementation plan; plan for TA to GoM
IMPACT WEIGHTING (%) | Output Indicator 3.2 | Planned | Baseline | 2016-06-01 | 2017-06-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 | 2020-12-01
| Number of activities to establish a labour market information system contributing to effective skills planning |  | 0 | 1 activity (**) in context of Labour Market Observatory | 3 activities in context of Labour Market Observatory | 3 activities in context of Labour Market Observatory
Achieved
[6 empty] | Source |  |  |  | RISK RATING
|  |  | Programme monitoring reports; programme evaluation report | [6 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £1.0m | [6 empty] | £1.0m | 100%
INPUTS (HR) | DFID (FTEs)
A2 (0.06) B2 (0.06)
* Private sector (PS) elements of the new TVET law include: the up to 1% levy, PPPs, sector skills councils, and autonomy of state training schools and the inclusion of PS on their new governing bodies.
** Activities in context of LMO include: TA recruited; TA briefed and assigned to LMO Directorate; development of indicators in relation to skills planning; organising staff development; producing 1st and 2nd year workplans; producing a Labour market Bulletin with strong focus on skills related information etc.

## May2017Logframe
Logframe (26 May 2017)
JOBA - SKILLS FOR EMPLOYMENT (S4E) PROGRAMME
IMPACT | Impact Indicator 1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Assumptions
Higher income among JOBA beneficiaries, especially young women, in the context of a more effective skills training system | Percentage of JOBA Employment Fund training programme graduates who see a real increase in income due to their training | [5 empty] | 50% | 75% | 75% | That even short-term training can effect income impacts, noting a lack of empirical evidence from Mozambique. Any such impact could be militated by an economic downturn, so even if effects are established, they might be such that they protect from income declines. Protection from decline would also be measurable via the tracer surveys. Income gains can be broadly linked to skills acquired and are evident within two years of training.
Achieved
Source
Tracer survey data from grantees and from independent evaluation disaggregated by gender. 2017 baseline cohort 1; 2018 cohort 1 year 1 measure and baseline cohort 2; 2019 cohort 1 year 2 measure and cohort 2 year 1 measure, 2020 cohort 1 year 3 measure, cohort 2 year 2 measure, cohort 3 year 1 measure; 2021 cohort 1 year 4 measure, cohort 2 year 3 measure, cohort 3 year 2 measure. Note: a separate, indepdendent evaluation will continue to monitor income gains over 2021.
| Impact Indicator 2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target
| Changes that evidence improved effectiveness* in the skills training system. |  |  |  | Early evidence of improved effectiveness. Milestones to be determined as the programme's expected contrbutions to 'improvements in effectiveness' are better defined during 2017. | Evidence of improved effectiveness (TBD - by end of 2017) | Evidence of improved effectiveness (TBD - by end of 2017) | Evidence of improved effectiveness (TBD - by end of 2017) | Evidence of improved effectiveness (TBD - by end of 2017) | That JOBA supported activities serve to catalyse other development actors to support a more effective skills training system. Activities aimed at strengthening the skills training system enhance effectiveness in the sector, contributing to economic development through more people accessing skills that lead to more productive employment.
Achieved
Source
JOBA Reporting System, as this information will be reported on as part of quarterly and annual reporting. In additional, qualitative interviews will be conducted with GoM and non-state training providers and others. Tools will be developed under Record 2 of the JOBA Monitoring System that includes results monitoring, interviews with relevant government officers, interviews were employers, interviews with grant recipients, and special studies. Information made available via the LMO would also be used to assess this impact.
*Examples of improved effectiveness could include: greater availability of TVET training opportunities, more TVET service provision in priority sectors, improved quality of graduates as reported by private sector, changing perceptions among key actors in the TVET sector including employers, and more women completing TVET training.
OUTCOME 1 | Outcome 1 Indicator | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Assumptions
More Mozambicans, especially young women, have marketable skills applied to productive work | Proportion of JOBA Employment Fund beneficiaries who enter productive employment or who are engaged in more productive work |  | na | na | First baseline to be set: The proportion of all graduates who are in productive employment or other productive activities before the start of training | Percentage of VSCE graduates engaged in productive employment or other more productive activities 10% higher than at baseline | Percentage of VSCE graduates engaged in productive employment or other more productive activities 45% higher than at baselines | Percentage of VCSE and technical graduates engaged in productive employment or other more productive activities 70% and 80% higher than at baseline respectively | An estimated 80% of technical training graduates and 70% of VSCE graduates are in productive employment or other more productive activities compared with baselines** | The main assumption is that there are sufficient numbers of young people who would demand TVET. A second assumption is that there are sufficient training organisations suitably focused to support these services. A third assumption is that the economic problems facing Mozambique do not overwhelm trainees in their ability to contribute economically to their households. A further assumption is that grantees successfully deliver courses that match the needs of employers and that improved skills improve chances of employment.
Achieved
Source
Tracer survey data, disaggregated by gender. Baselines to be set through programme monitoring with grantees and augements with evaluation. 2017 baseline cohort 1; 2018 cohort 1 year 1 measure and baseline cohort 2; 2019 cohort 1 year 2 measure and cohort 2 year 1 measure; 2020 cohort 1 year 3 measure, cohort 2 year 2 measure, cohort 3 year 1 measure; 2021 cohort 1 year 4 measure, cohort 2 year 3 measure, cohort 3 year 2 measure
*Milestones to be revisited once baselines are set.
**The proportion of technical training graduates in more productive work who are women rises to 25% of all graduates. The proportion of VSCE training graduates in more productive work who are women rises to 50% of all graduates.
OUTCOME 2 | Outcome 2 Indicator 1* | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Assumptions
Strengthened Mozambican skills training system | Number of non-JOBA grantee National Association members who report positive changes to their training** aimed at improving the efficacy of training. |  | 0 | 0 | 0 | 30 | 10 | 10 | 50 | Association is able to function effectively and quality of information flow and training enables providers to improve their offers.
Achieved
Source
JOBA Reporting System, as this information will be reported on as part of quarterly and annual reporting. In addition, qualitative interviews will be conducted with non-state training providers and others. Tools will be developed under Record 2 of the JOBA Monitoring System that includes results monitoring, interviews with employers, interviews with grant recipients, and special studies.
*Outcome indicator to be revisited at end 2017 to consider enhancing with expected outcome impacts from support to Government of Mozambique
**Examples include: measures to retain more women, adoption of more competence-based training approaches, curriculua reflect industry inputs and stated needs, number of MoU signed with industries; graduates find a job in less time than before; increased number of internships accepted by companies
For Outcomes 1 and 2, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £13.6m + £1m for T4R (NOTE: based on expected budget amendment) |  |  | Value of grant recipient in-kind contributions estimated at £2m (ie. 25% addition to JOBA contribution to Employment Fund). |  |  |  | £16.6m | 88%
INPUTS (HR) | DFID (FTEs)
A1 (0.05) A2 (0.5) B2 (0.2)
OUTPUT 1 | Output Indicator 1.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Assumptions
Expanded access to inclusive, market relevant, quality training and wrap-around services by non-state training providers | Number of graduates who are provided with Technical Training comprising a norm of 2 or more years of training at appropriate competence levels* combined with wrap-around services through the JOBA Employment Fund |  | 0 | 0 | 0 | 0 | Graduated: 250 Female: 125 Male: 125 | Graduated: 250 Female: 125 Male: 125 | Total Graduated: 500 Female: 250 Male: 250 | That training organisations can mobilise in time to deliver enhanced training offers to target numbers. Training organisations are able to successfully recruit enough trainees.
Achieved
Source
JOBA Employment Fund Monitoring System. The measurement of the indicator will include establishing the age and sex of each trainee. Case studies to give information on the people behind the numbers
| Output Indicator 1.2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target
| Number of graduates who are provided with a norm of more than 6 months-2 years of training at appropriate competence levels* (vocational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund |  | 0 | 0 | 0 | Graduated: 1000 Female: 400 Male: 600 | Graduated: 1000 Female: 400 Male: 600 | Graduated: 800 Female:320 Male: 480 | Total Graduated: 2800 Female: 1120 Male: 1680
| Number of graduates who are provided with a norm of 3 months-6 months of training at appropriate competence levels* (vocational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund |  | 0 | 0 | 0 | Graduated: 1000 Female: 500 Male: 500 | Graduated: 1000 Female: 500 Male: 500 | Graduated: 800 Female: 400 Male: 400 | Total Graduated: 2800 Female: 1400 Male: 1400
Achieved
|  | Planned (T4R) |  | T = 608 M = 264 F = 344 |  |  |  |  | T = 608 M = 264 F = 344
Achieved (T4R)
Source
JOBA monitoring system. Data disaggregated by age and gender. Case studies to give information on the people behind the numbers
| Output Indicator 1.3 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target
| Number of partnerships that are led or catalysed by JOBA, with a particular focus on linking skills providers with the private sector |  | 0 | 0 | 5 tangible partnerships leveraged/ brokered, with a particular focus on linking skills providers with the private sector | 10 tangible partnerships leveraged/ brokered, with a particular focus on linking skills providers with the private sector | 10 tangible partnerships leveraged/ brokered, with a particular focus on linking skills providers with the private sector | 5 tangible partnerships leveraged/ brokered, with a particular focus on linking skills providers with the private sector | 30
IMPACT WEIGHTING (%) |  | Achieved
80% |  | Source: Monitoring Officer interviews with team members to record progress in this regard. Periodic interviews with organisations involved in TVET and linked to JOBA and/or the Association | [7 empty] | Risk Rating
Moderate
For Output 1, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| Additional £1m for T4R £8m Employment Fund. Approx £3.6m service provider inputs under JOBA to Output 1 |  |  | Value of grant recipient in-kind contributions estimated at £2m. |  |  |  | £14.6m | 86%
INPUTS (HR) | DFID (FTEs)
A2 (0.3) B2 (0.1)
OUTPUT 2 | Output Indicator 2.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Assumptions
Association of Non-State Training Providers is established and strengthened to support achievement of its mandate and improve the training offers of its members | Association becomes functional and active, demonstrated by retention of members and entry of new members |  | Operational Plan for Association complete | Progress towards Association establishment (interim committee established, statutes agreed by constituent assembly, constitutent assembly held) | Association legally established and formally launched. Learning fund activated. 60 members join the Association. | 25 new members join the Association | 20 new members join the Association | 20 new members join the Association | 125 members join the Association, and 100 remain as members (80% retention). | 1) that there are sufficient numbers of training providers who are interested in joining the Association and engaging in Association activities; 2) that the Association would be willing and able to collect data on members; 3) that Association members are in a position to improve training quality. 3) That the Association is able to remain relevant and valuable to the majority of its members.
Achieved
| Output Indicator 2.2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target
| Number of members of the Association of Non-State Training Providers who have completed a module in the Association’s Training Programme or are beneficiaries of the JOBA Learning Fund activities |  | 0 | n/a | n/a | 30 discrete members of Association complete at least 1 module of the Association’s Continuous Professional Development programme or are beneficiaries of the Learning Fund | 10 discrete members of Association complete at least 1 module of the Association’s Continuous Professional Development programme or are beneficiaries of the Learning Fund | 10 discrete members of Association complete at least 1 module of the Association’s Continuous Professional Development programme or are beneficiaries of the Learning Fund | 50 discrete members of Association complete at least 1 module of the Association’s Continuous Professional Development programme or are beneficiaries of the Learning Fund | That there are sufficient numbers of training providers who are interested in joining the Association and engaging in Association activities. That there are suitable providers to deliver training under the Fund.
IMPACT WEIGHTING (%) |  | Achieved | [7 empty] | Risk Rating
10% |  | Source | [7 empty] | Moderate
JOBA monitoring system. Qualitative interviews with the Association and selected members to add further information
For Output 2, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £1.0m approx |  |  | membership fees (value TBC) |  |  |  | £1.0m | 100%
INPUTS (HR) | DFID (FTEs)
A2 (0.1) B2 (0.5)
OUTPUT 3 | Output Indicator 3.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Assumptions
Government of Mozambique functions related to TVET skills sector planning strengthened | Completion of relevant TA support to GoM's implementation of private sector elements of new TVET law |  | 0 | 0 | 0 | TBD in 2017 following agreement with GoM. Likely to include: Sector data collected and analysed for demand and supply of skills in 5 sectors with LMO | TBD in 2017 following agreement with GoM. Likely to include: 5 sector skills plans developed with ANEP that draw on new LMO data. Plans made available to stakeholders | 0 | TBD in 2017 following agreement with GoM. Likely to include: 5 sector data reports 5 sector skills plans | 1) That the LMO officers are available and interested in working with the TA advisers on planning, data collection, and analysis. 2) That ANEP officers are available and interested in working with the TA advisers 3) That ANEP will activate and support the Sector Training Advisory Committees. 4) That the limited financing for government and availability of government officers does not constrain these activities. TA support can effectively and sustainably strengthen GoM capacity 6) Other development partners will be attracted to supporting this sector because of this intervention. While the JOBA intervention can proceed without the ILO, it is expected that the planned ILO Programme will enhance the efficacy of activities and build on JOBA activities.
IMPACT WEIGHTING (%) |  | Achieved
10% |  | Source | [7 empty] | Risk Rating (Minor, Moderate, Major, Severe)
|  | LMO TA quarterly reports, sector plans. Committee minutes. Reports from field data collection. | [7 empty] | Moderate
For Output 3, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) |  |  |  |  | Total (£) | DFID SHARE (%)
| £1.0m approx | [6 empty] | £1.0m | 100%
INPUTS (HR) | DFID (FTEs)
A2 (0.1) B2 (0.5)

## March2018Logframe
Logframe (MULTI-SHEET VERSION revised in July 2018 from the May 2018 DFID-approved version)
JOBA - SKILLS FOR EMPLOYMENT (S4E) PROGRAMME
IMPACT | Impact Indicator 1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Higher income among JOBA beneficiaries, especially young women, in the context of a more effective skills training system | Percentage of JOBA Employment Fund training programme graduates who see a real increase in income due to their training, disaggregated by gender |  |  |  | JOBA and Impact Assessment baseline tracer surveys designed | JOBA and Impact Assessment baseline tracer surveys implemented | 50% | 75% | 75% | This indicator focuses on the first part of the Impact Statement. Of the total # of graduates, what proportion experienced an increase in income following training? Broken down by demographic measures. Broken down by circumstance and location. Income effects do not have to come just from employment status, if the training has effects on other aspects of earnings and livelihoods | 1) One assumption is that even short-term training can effect income impacts, despite a lack of empirical evidence from Mozambique. Any such impact could be militated by an economic downturn, so even if effects are established, they might be such that they protect from income declines. Protection from decline would also be measurable via the tracer surveys. 2) A second assumption is that income gains are broadly linked to skills acquired and are evident within two years of training. 3) The percentages offered for 2019/20 and 2020/21 do not have an evidence base at this time. Evidence mapping of the Theory of Change will be does to provide available evidence.
Achieved
Means of Measurement
Tracer survey data from grantees and from independent evaluation disaggregated by gender. 2018 cohort 1 first quarter baseline, 2018 year 1 measure and baseline cohort 2; 2019 cohort 1 year 2 measure and cohort 2 year 1 measure, 2020 cohort 1 year 3 measure, cohort 2 year 2 measure, cohort 3 year 1 measure; 2021 cohort 1 year 4 measure, cohort 2 year 3 measure, cohort 3 year 2 measure. Note: a separate, indepdendent evaluation will continue to monitor income gains over 2021.
| Impact Indicator 2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
| Changes that evidence improved effectiveness* in the skills training system. |  |  |  | JOBA puts into place mechanisms to engage with, and strengthen over time, skills market actors | JOBA strengthens government systems that regulate TVET and improve the quality of service delivery, and strengthens governance, accountability and voice in the non-state TVET sector | Private sector TVET service providers and representative bodies are able to have their voices heard in the TVET sector, and that this voice represents the values and interests of its members. State authorities are more able to enable quality in the TVET system. Private and public sector TVET service providers improve the quality of TVET service delivery | Private sector TVET service providers and representative bodies are able to have their voices heard in the TVET sector, and that this voice represents the values and interests of its members. State authorities are more able to enable quality in the TVET system. Private and public sector TVET service providers improve the quality of TVET service delivery | Vibrant TVET system with voices heard | This indicator focuses on the second part of the Impact Statement. Effectiveness is measured on a five point scale: 1) very effective (value = 10); 2) somewhat effective (value 7); 3) somewhat ineffective (value 4); 4) very ineffective (value 2); 5) completely ineffectively (value 0). Will be measured through stakeholder interviews where scale values will be established over a period of time (2019, 2020, 2021). Elements of effectiveness to be agreed during the design of the stakeholder interview instrument. | 1) One assumption is that JOBA-supported activities serve to catalyse other development actors to support a more effective skills training system. 2) A second assumption is that activities aimed at strengthening the skills training system enhance effectiveness in the sector, thereby contributing to economic development through more people accessing skills that lead to more productive employment.
Achieved
Means of Measurement
JOBA Reporting System, as this information will be reported on as part of quarterly and annual reporting. In additional, qualitative interviews will be conducted with GoM and non-state training providers and others. Tools developed under Record 2 of the JOBA Monitoring System include results monitoring, interviews with relevant government officers, interviews were employers, interviews with grant recipients, and special studies. Evidence mapping against the Theory of Change.
* Examples of improved effectiveness include greater availability of TVET training opportunities, more TVET service provision in priority sectors, improved quality of graduates as reported by private sector, changing perceptions among key actors in the TVET sector including employers, and more women completing TVET training.
OUTCOME 1 | Outcome 1 Indicator 1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
More Mozambicans, especially young women, have marketable skills applied to productive work | Proportion of JOBA Employment Fund beneficiaries who enter productive employment or who are engaged in more productive work, disaggregated by gender |  | na | na | Baseline Tracer Survey questionnaire to measure engagement in productive employment is prepared and implemented for first cohort of enrolled trainees. | First baseline is set: The proportion of surveyed trainees at baseline by type of employment. | 50% of VSCE graduates from 2018 are engaged in productive employment, or more productive activities one year after training compared to their baseline | 70% of VSCE graduates from 2019 are engaged in productive employment or more productive activities one year after training compared to their baseline. 80% of TT graduates in 2019 are engaged in productive employment or more productive activities one year after training compared to their baseline | 70% of VSCE graduates are engaged in productive employment or more productive activities one year after training compared to their baseline. 80% of TT graduates in 2020 are engaged in productive employment or more productive activities one year after training compared to their baseline | Baseline establishes type of employment, or no employment, and insights on the nature of this employment. Tracer survey data will thereafter be used to establish whether more are in what type of employment, and whether graduates are in a better employment situation even if they have not changed their jobs. Measure will include protection from decline in position and decline in income. | 1) The first assumption is that there are sufficient numbers of young people who would demand TVET. 2) A second assumption is that there are sufficient training organisations suitably focused to support these services. 3) A third assumption is that the economic problems facing Mozambique do not overwhelm trainees in their ability to contribute economically to their households. 4) A fourth assumption is that grantees successfully deliver courses that match the needs of employers. 5) A fifth assumption is that improved skills improve chances of employment.
Achieved
Means of Measurement
Tracer survey data, disaggregated by gender. Baselines to be set through programme monitoring with grantees and augements with evaluation. 2018 Quarter 1 baseline cohort 1; 2018 2nd quarter cohort 1 year 1 measure and baseline cohort 2; 2019 cohort 1 year 2 measure and cohort 2 year 1 measure; 2020 cohort 1 year 3 measure, cohort 2 year 2 measure, cohort 3 year 1 measure; 2021 cohort 1 year 4 measure, cohort 2 year 3 measure, cohort 3 year 2 measure
OUTCOME 2 | Outcome 2 Indicator 1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Strengthened Mozambican skills training system | Proportion of TVET providers who demonstrate improved quality of market relevant training |  | na (no association) | na (no association) | AMEPP Statutes approved and AMEPP registered as a national association. AMEPP 3 year Strategic Plan developed. MoU signed with ANEP that defines programme of support to ANEP to roll out their national quality assurance and accreditation systems within the TVET sector. | The TVET sector begins to demonstrate TVET enabling attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability | The TVET sector demonstrates TVET enabling attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability | The TVET sector demonstrates TVET enabling attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability | The TVET sector is characterised by positive attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability | Improved quality and market relevance is defined as gains made in terms of trained teachers, partnerships with industry in place, relevant curriculum focused on market needs, and management that has received training on quality management systems. The main means of measurement for this comprise a panel design of informed stakeholders rating the sector's attributes associated with inclusiveness, market relevance, matching supply to demand, and financial sustainability on a to-be-established scale, measured int 2018, 2019, and 2020 | 1) The key assumption is that the Association will be able to function effectively. 2) A second assumption is that information flows will be effective, strengthening Association members performance. 3) A third assumption is that the operations of the Association will enable higher quality service provision by Association members.
Achieved
Means of Measurement
JOBA Reporting System, as this information will be reported on as part of quarterly and annual reporting. In addition, qualitative interviews will be conducted with non-state training providers and others. Tools will be developed under Record 2 of the JOBA Monitoring System that includes results monitoring, interviews with employers, interviews with grant recipients, and special studies.
For Outcomes 1 and 2, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £13.6m + £1m for T4R (NOTE: based on expected budget amendment) |  |  | Value of grant recipient in-kind contributions estimated at £2m (ie. 25% addition to JOBA contribution to Employment Fund). |  |  |  | £16.6m | 88%
INPUTS (HR) | DFID (FTEs)
A1 (0.05) A2 (0.5) B2 (0.2)
OUTPUT 1 | Output Indicator 1.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Expanded access to inclusive, market relevant, quality training and wrap-around services by non-state training providers | Number of graduates who are provided with Technical Training comprising a norm of 2 or more years of training at appropriate competence levels combined with wrap-around services through the JOBA Employment Fund |  | 0 | 0 | Grants awarded that make provision for additional 1815 persons to be enrolled in the technical training system | JOBA completes follow up on findings of due diligence for all Round 1 and 2 grantees delivering technical training. Routine monitoring of grants implemented as planned. | Graduated 250 (F: 125; M:125) JOBA monitoring provides evidence of technical advisory support provided to all grantees to improve quality of training provision, and of wrap around services. | Graduated: 250 Female: 125 Male: 125 JOBA monitoring provides evidence about different strategies for linking technical graduates to employment opportunities. | Graduated: 500 Female: 250 Male: 250 | Total number of graduates, broken down by female and male, of all Technical Training programmes. This number will include those whose graduation is imminent near the programme completion month of April 2021. Technical /vocational / professional training is defined under the TVET Reforms as including theory, practical skills, and attitudes. Technical training provides pathways to higher education levels. A technical qualification must include at least 120 credits (1200 hours of contact learning). | 1) The first assumption is that training organisations can mobilise in time to deliver enhanced training offers to target numbers. 2) The second assumption is that training organisations are able to successfully recruit enough trainees.
Achieved
Means of Measurement
Source: JOBA monitoring system. Data disaggregated by age and gender.
| Output Indicator 1.2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration
| Number of graduates who are provided with a norm of more than 6 months-2 years of training at appropriate competence levels (vocational, occupational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund |  | na (prior to grant awards) | na (prior to grant awards) | 2180 (rounds 1 and 2) (60% female, 40% male) places supported by JOBA. | Graduated: 1000 Female: 400 Male: 600 JOBA completes follow up on findings of due diligence for all Round 1 and 2 grantees. Routine monitoring of grants implemented as planned. | Graduated: 1000 Female: 400 Male: 600 JOBA monitoring provides evidence of technical advisory support provided to all grantees to improve quality of training provision, and of wrap around services, and the sustainability of vocational providers. | Graduated: 800 Female: 320 Male: 480 | Total Graduated: 2800 Female: 1120 Male: 1680 | Total number of graduates, broken down by female and male, of all VSCE training 6-24 months in length. Wrap-around services will also be measured. Occupational training offers training in skills only, without theory. The qualification carries less than 120 credits, ie. less than 1200 contact learrning hours.
| Number of graduates who are provided with a norm of 3 months-6 months of training at appropriate competence levels (vocational, occupational, second chance or entrepreneurial) combined with wrap-around services through the JOBA Employment Fund |  | na (prior to grant awards) | na (prior to grant awards) | First Round 3 proposal presented to Investment committee | Graduated 1000 Female: 500 Male:500 20% of JOBA grantees delivering vocational training establish tracer surveys to establish the effectiveness of training and wrap around services in transition to employment | Graduated 1000 Female: 500 Male: 500 50% of JOBA grantees delivering vocational training have evaluated training and/or wrap around services and identified areas for improvement | Graduated 800 Female: 400 Male: 400 80% JOBA grantees delivering vocational training implement at least two improvements identified in self-assessments | Total Graduated: 2800 Female: 1400 Male: 1400 | Total number of graduates, broken down by female and male, of all VSCE training 3-6 months in length. Wrap-around services will also be measured. Occupational training offers training in skills only, without theory. The qualification carries less than 120 credits, ie. less than 1200 contact learrning hours.
Achieved
|  | Planned (T4R) |  | T = 608 M = 264 F = 344 |  |  |  |  | T = 608 M = 264 F = 344
Achieved (T4R)
Means of Measurement
Source: JOBA monitoring system. Data disaggregated by age and gender.
| Output Indicator 1.3 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration
| Number of partnerships that are led or catalysed by JOBA with a particular focus on linking skills providers with the private sector |  | na (prior to Round 3) | na (prior to Round 3) | Strategy for Round 3 developed and Criteria for Round 3 grants revised | With Round 3 contracting, 3-4 contracts signed that enables tangible partnerships leveraged/brokered, with a particular focus on linking skills providers with the private sector | 3-4 contracts signed that enables tangible partnerships leveraged/brokered | JOBA disseminates evidence of sustainable partnerships and of uptake of new partnering strategies by employers, AMEPP and other key stakeholders. Dissemination strategies target training providers, employer networks, AMEPP and ANEP, and relevant Ministries | 8 contracts signed | Number of contracts signed between private sector entities and TVET service providers, or between private sector entities and representative agencies, that reflect a transformation in relationships between the two parties.
IMPACT WEIGHTING (%) |  | Achieved
80% |  | Means of Measurement | [8 empty] | Risk Rating (Minor, Moderate, Major, Severe)
|  | Source: JOBA monitoring system. Qualitative interviews under Record 2 with training providers | [8 empty] | Moderate
For Output 1, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| Additional £1m for T4R. £8m Employment Fund. Approx £3.6m service provider inputs under JOBA to Output 1 |  |  | Value of grant recipient in-kind contributions estimated at £2m. |  |  |  | £14.6m | 86%
INPUTS (HR) | DFID (FTEs)
A2 (0.3) B2 (0.1)
OUTPUT 2 | Output Indicator 2.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Association of Non-State Training Providers is established and strengthened to support achievement of its mandate and improve the training offers of its members | Association operational and better able to deliver services valued by its member |  | Operational Plan for Association complete | Progress towards Association establishment (interim committee established, statutes agreed by constituent assembly, constitutent assembly held) | Association legally established and formally launched. AMEPP strategic plan is developed, including the identification of services to be supported by JOBA over the period 2018-2020 | AMEPP Executive Director is appointed. Mid-year review of performance of AMEPP secretariat by AMEPP officials is positive. Costed annual workplan completed. | AMEPP sustainabiltiy plan is approved by General Assembly in March 2020. | Progress towads AMEPP sustainability is implemented as planned. | AMEPP is financially sustainable, and has staff capacity to deliver services required by members. | The focus in this indicator is on the support JOBA can provide to build sustainablity of AMEPP. This indicator will be informed by JOBA reporting and engagement with AMEPP, as well as two Record 2 tools as follows: 1) key informant interviews with Association officers; 2) key informant interviews with Association members. | 1) One assumption is that there are sufficient numbers of training providers who are interested in joining the Association and engaging in Association activities. 2) A second assumption is that the Association would be willing and able to collect data on members. 3) A third assumption is that Association members are in a position to improve training quality. 4) A forth assumption is that the Association is able to remain relevant and valuable to the majority of its members.
Achieved
| Output Indicator 2.2 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
| Number and percentage of members of the Association of Non-State Training Providers who have completed a module in the Association’s Training Programme or are beneficiaries of the JOBA Learning Fund activities |  | 0 | n/a | Assessment of AMEPP member priority needs conducted and informs approach to Learning Fund disbursements | JOBA and AMEPP approve at least one Learning Fund contract to deliver CBT training to AMEPP members and non-member non-state providers. CBT training has been delivered to at least one cohort of 25 instructors from AMEPP members. Terms of Reference for contracts to deliver QMS training are agreed with AMEPP. | Contract for gender training approved. 25% of AMEPP members have had access to CBT and QMS training through the Learning Fund. | 50% of AMEPP members have had access to CBT training through the Learning Fund, 30% of AMEPP members that have had access to QMS training through the Learning Fund. 20% of AMEPP members that have had access to gender training through the Learning Fund. | AMEPP members have completed competency-based training course offered by AMEPP. Members have completed quality management system training offered by AMEPP via the Learning Fund. Members have completed gender training offered by AMEPP. Non-state training providers are implementing the new practices shared through LF training. | Total number of AMEPP member training providers where X number of trainers have received competency-based training. Total number of TVET training providers where Y number of trainers has received quality management training. | 1) One assumption is that there are sufficient numbers of training providers who are interested in joining the Association and engaging in Association activities. 2) A second assumption is that there are suitable providers to deliver training under the Fund.
IMPACT WEIGHTING (%) |  | Achieved | [8 empty] | Risk Rating (Minor, Moderate, Major, Severe)
10% |  | Means of Measurement | [8 empty] | Moderate
Source: JOBA monitoring system. Qualitative interviews under Record 2 with the Association and selected members to add further information
For Output 2, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  |  | Total (£) | DFID SHARE (%)
| £1.0m approx |  |  | membership fees (value TBC) |  |  |  | £1.0m | 100%
INPUTS (HR) | DFID (FTEs)
A2 (0.1) B2 (0.5)
OUTPUT 3 | Output Indicator 3.1 | Planned | Baseline September 2016 | July 2016 - March 2017 (9 months) | April 2017 - March 2018 | April 2018 - March 2019 | April 2019 - March 2020 | April 2020 - March 2021 | Target | Definition and Elaboration | Assumptions
Government of Mozambique functions related to TVET skills sector strengthened | Key government agencies better able to deliver quality maangement and accreditation services |  | 0 | 0 | MoU signed with ANEP to agree specific TA support | Two consultants are appointed to work with ANEP in the areas of quality management and accreditation services. Terms of Reference are agreed. ANEP monthly reports to JOBA confirm progress against the ToR. Activity-based workplan of JOBA support to ANEP to roll out QMS across TVET is agreed | Proportion of TVET institutions that apply for accreditation who are reviewed is doubled from baseline value (baseline = April 2018) | Proportion of TVET institutions that apply for accreditation who are reviewed remains at 2019/20 levels | Proportion of TVET institutions that apply for accreditation who are reviewed remains at 2019/20 levels | Better able to deliver quality management and accreditation services' refers to the total number of TVET institutions that apply for accredication who are reviewed. It should be noted that ANEP's interest in the nature of JOBA support may change as implementation proceeds. If this changes, the milestones and target would need to be adapted in response. | 1) One assumption is that ANEP officers are available and interested in working with the TA advisers. 2) A second assumption is that ANEP will activate and support the Sector Training Advisory Committees. 3) A third assumption is that the limited financing for government and constraints on the availability of government officers does not constrain these activities. 4) A fourth assumption is that TA support can effectively and sustainably strengthen GoM capacity related to certification. 5) A fifth assumption is that other development partners will be attracted to supporting this sector because of this intervention.
IMPACT WEIGHTING (%) |  | Achieved
10% |  | Means of Measurement | [8 empty] | Risk Rating (Minor, Moderate, Major, Severe)
|  | Source: JOBA monitoring system. Qualitative interviews under Record 2 with stakeholders within and outside Government | [8 empty] | Moderate
For Output 3, inputs are as follows:
INPUTS (£) | DFID (£) |  | Govt (£) |  |  |  |  | Total (£) | DFID SHARE (%)
| £1.0m approx | [6 empty] | £1.0m | 100%
INPUTS (HR) | DFID (FTEs)
A2 (0.1) B2 (0.5)