Annual Review - Summary Sheet

Title: Punjab Economic Opportunities Programme
Programme Value: £ 30 million		Review Date:15- 25th May 2014
Programme Code: 114384	Start Date: 28/01/2008	End Date: 31/12/2015

Summary of Programme Performance
Year	2010-11	2011-12	2012-13	2013-14
Programme Score	3	A	A	A
Risk Rating	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

The Punjab Skills Development Fund (PSDF), the main component of the Punjab Economic Opportunities Programme (PEOP), continues to make satisfactory progress in challenging circumstances.

Over the past 12 months, PSDF has trained 28,500 poor and vulnerable people[1] (40% women) in a range of skills and trades. Following the approval of the PC-1 revisions in August 2013, PSDF has rolled-out activities to additional 10 districts in South and Central Punjab. Close to 10,000 beneficiaries from the new districts are currently enrolled in courses and are expected to complete training in the next few months.
[1] Definition of poor and vulnerable: Earning less than $4 per day.

PSDF has also refined its business model with the establishment of a job placement cell to develop stronger linkages between trainees, microfinance organisations prospective employers and placement agencies. This will enhance the likelihood of achieving the programme objective.

Early results from the programme evaluation show that 67% of PSDF graduates are employed within 6 months of completing their courses and of those 43% are earning above the minimum national wage. Increased competition amongst training providers has brought down cost per trainee by 38% in the past year alone.

Lessons learnt and recommendations:
- Disbursement Linked Indicators (DLIs) that are tied to additional DFID funding to PSDF, can help strengthen GoPb’s commitment to PSDF and ensure continued support to make skill delivery more cost effective, innovative and market-oriented.
- PSDF should initiate a plan for building the technical and institutional capacity of the private training providers to further develop a competitive private skill providers market.
- PSDF should develop an employment facilitation strategy particularly for women. Building on its current initiatives will help sustain current employment rates. These might otherwise be at risk in a low economic growth and unstable political environment.
- PSDF should develop an institutional vision and a sustainability plan to ensure that there is an ongoing mechanism for competitively financing skills training in the long run.

Actions on previous recommendations of Annual Review 2012-13

In line with the recommendations of the last AR, institutional systems and capacity of PSDF has been strengthened and the fund has scaled up to additional 10 districts. Institutional linkages with other stakeholders (e.g. the World Bank, Giz-EU, and priority industrial sectors such as garments, and construction) have been developed. Progress is being made on creating an enabling regulatory environment in the province. DFID’s programme management of PEOP has improved through quarterly annual reviews which monitor and make recommendations for programme progress and financial spend.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

The Punjab Economic Opportunities Programme (PEOP) is a partnership between the Government of Punjab (GoPb) and DFID. The objective of the programme is to enhance the income earning opportunities of the poor and vulnerable in the target districts. The total size of the programme is £55m with DFID contributing £30m (incl. £5m technical assistance) and GoPb contributing £25m. The programme started in October, 2010 and is expected to close in December 2015.

Initially, the programme envisaged two components, namely (i) the (pilot-) Punjab Skills Development Fund (PSDF) to train and support workforce development; and (ii) a livestock and dairy component to support a range of interventions across the sector. Funds were split equally across both components with operations focused on 4 districts in southern Punjab.

Due to poor performance the livestock component was closed in mid- 2012. The remaining funds were allocated to PSDF and allowed the expansion of PSDF to 10 additional districts in southern and central Punjab, with an increased focus on addressing skills gaps in growth oriented industrial sectors.

PSDF is the first competitive skills financing fund in Pakistan. It was established in response to the inefficiencies in public sector skills delivery and seeks to encourage private sector training providers to enter the market. Stipends are provided to registered students to cover the cost of their training (incl. lodging/ travel). DFID sees PSDF as anchoring a fundamental shift towards ‘delivering longer-term, transformational and sustainable institutional change’ in the skills sector.

Expected results:

- Reduce poverty by 5% in headcount (defined as those earning an income of 2 $a day), increase individual earnings by 15% and household consumption by 7%. (at the impact level)
- Develop an effective funding model;
- Train 135,000[2] with a gender focus (40% women);
  [2] 50% of which i.e. 67,500 is attributable to DFID.
- Mobilize private training places;
- Support GoPb for improving skills policy and regulations.

The programme is contributing to the Wealth Creation Pillar of DFID’s Operational Plan by contributing 40,000 skilled people to the economy, 40% of which will be women.

## PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The programme evaluation is ongoing with results are expected towards the end of the programme. Initial findings from tracer studies show that 67%[3] of trainees find employment within 6 months while 83% are employed after 16 months. 43% of graduates are earning above the minimum national wage which is significant as 83% were unemployed prior to training. While these results are not definitive, they compare well with similar employment/training funds in other countries and indicate a positive results trajectory.
[3] 17% of whom are self-employed.

PSDF has increased its focus on employment facilitation and has aligned the training offered more closely to the requirements of growth sectors/clusters in the Punjab economy. As these linkages are enhanced it is expected that employment rates will increase further and improve value for money (VFM) metrics at the outcome level.
 Overall output score: A

1. Effective model for funding competitive training delivery:	Score: A
2. Cumulative number of persons trained in PEOP districts:	Score: A
3. Private training places mobilized:	Score: A+
4. Support to the GoPb for skills policy and regulatory reform:	Score: A
5. Generation of evidence to inform skill delivery Score: A

Overall output description

Effective model for funding competitive training delivery: PSDF’s management and operational systems have been strengthened in preparation of the scale-up to additional 10 districts. New products focusing on growth oriented sectors have been launched, while preparatory work is underway for introducing additional skill schemes including those involving businesses (i.e. employers) as trainers. Vacant positions on the Board have been filled and the Board is providing robust strategic support. Recommendations from a series of audits and organizational assessment studies are being implemented to deliver a scaled-up programme.

Cumulative number of persons trained in PEOP districts: PSDF has exceeded the cumulative target of 48,500 poor and vulnerable trained since inception by training over 50,000 poor and vulnerable men and women. Almost 40% are women. A placement cell has been established to facilitate graduates’ employment. It is piloting various approaches for increasing employment rates including working with placement firms, circulating a graduates directory among potential employers and assisting foreign firms that are looking to employ Pakistani skilled labour. Meanwhile the RCT experiments are helping to identify effective models for linking rural women with markets.

Private training places mobilized: A key achievement has been the engagement of 46 firms as training providers. Meanwhile, PSDF is engaged with 120 training providers of which 34 have been contracted over the last 1 year.

Support to the GoPb for skills policy and regulatory reform: PSDF has been part of all GoPb initiated skills policy and regulatory forums and has influenced the decisions made by them. DFID also provided TA to help improve the governance of the skills sector in Punjab. A study for determining the institutional capacity of the Industries Department (ICA) was conducted recently to strengthen its role in the skills policy formulation and coordination of the various agencies involved in delivering skills training and workforce development. The GoPb agrees in principle with the report’s recommendations which will help improve the governance of the skills sector in Punjab.

Key lessons

- When targeting the skills gap in industrial sectors, firms operating in that sector are well placed to be engaged as trainers. Engaging closely with businesses also helps improve employment prospects for graduates.
- Employment probabilities of the graduates can be enhanced by initiating job placement efforts earlier in the programme life.
- Effective programme delivery can help leverage political support and ownership for more challenging policy and regulatory reforms.
- Stipends are not a key determinant for improving skills uptake among serious potential trainees. Socio-economic contexts of the potential trainees including job prospects post-graduation may matter more to people when deciding whether to enrol in a course or not.

What would we do differently if redesigning the programme?

- Comprehensive employment facilitation for graduates from the outset.
- Comprehensive capacity and institutional development plan for skill providers.
- Introduce DLIs linked with DFID’s funding to PSDF as a mechanism for increasing GoPb’s stakes in the fund and the government’s commitment to making the skills sector more cost effective and innovative.
- Develop a long term institutional vision and sustainability plan for PSDF.

How lessons learnt will be shared more widely

In order to share lessons learnt at the institutional level of implementing a programme through a Section 42 company, the PEOP team is instituting a regular cross learning arrangement with the Education Fund for Sind (EFS). EFS, like PSDF is also a section 42 company. Lessons from PSDF’s operational experience will be shared more broadly with public sector skill providers, donors and international NGOs with skills programmes and provincial governments desirous of reforming the skills sector, for example, the government of KPK. Lessons learnt through the ongoing RCT experiments will continue to be shared with skill sector stakeholders including donors and the government through dissemination of reports and through skills policy discussion forums.

Has the log frame been updated since the last review?

YES: The log frame was updated in March 2014. The logframe milestone for number of people to be trained during 2013-14 was revised by reducing the target from 52,000[4] to 48,500 for the original 4 PEOP districts while for the new districts the milestone was reduced from 15,000to 0. However, the outer year target of 135,000 for the programme to be delivered by Dec. 2015 remains unchanged.
[4] 50% attributable to DFID.

The milestone was revised as procurement of skill providers to deliver training was frozen by over 3 months. The Auditor General Punjab’s office did not recognize the PSDF Board’s authority to make procurement rules to suit PSDF’s business operations, while PPRA Rules were inadequate to cover PSDF’s business. The matter took over 3 months to resolve. Additionally, the approval of the revised PC-1 was delayed by almost a year that delayed roll-out of training in the new districts.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective model for funding competitive training delivery
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 No. of evidence based products rolled out by PSDF (Cumulative)	2 (for 13-14)	3
1.2. Number of PSDF Board meetings/annum	4	4
1.3. No. of operational partnerships developed (Cumulative)	5 / (3 for 13-14)	5
1.4. No. of unqualified reports by independent auditors per annum	1	report expected this month

Key Points

Output 1.1:
PSDF launched 3 new training schemes this year in the health, renewable energy and garment sectors. The product design has been informed by beneficiary feedback and evidence from the first phase of trainings in these sectors.
- In addition, the second rounds of Skills for Jobs (SfJ) and Skills for Markets (SfM) were launched with design improvements.
  - SFJ focusing on trades like driving, welding, cooking for which there is demand in the jobs market. The training is certified by the Punjab Board of Technical Education. Entry requirements have been relaxed to grade 8 from grade 10. Participants include mostly urban men, though 25% trainees are women. On-the-job training is also part of the SFJ and will help in improving employment prospects of graduates.
  - SFM targets primarily rural women with little or no education. The skills covered include dairy farming, stitching, and beauticians. The new round of SFM is helping to address issues of access, employers’ bias against women, improving women’s market linkages, and their literacy, numeracy and business skills.

Output 1.2:
3 new members were appointed to the Board of Directors to fill vacant positions. This brings the total number to 14 (with 3 women) and allows for all the statutory sub-committees to be fully constituted.
The Board provides proactive oversight. It approves the RCT evaluation experiments, product design, work plan and budgets and overseas financial management, and human resource policies and needs of PSDF.
PSDF hired 14 new staff, bringing the total staff strength to 53 with 4 vacant positions. It is managing staff turnover by incentivizing performance, updating employee service rules and HR policies. A salary survey has been concluded recently and results are awaited.

Output 1.3:
- Four operation partnerships[5] have been developed with organisations to support curriculum development and jointly deliver trainings
  [5] Kamata Pakistan ; Punjab Board of Technical Education (PBTE); Turkish International Cooperation and Development Agency (TIKA) ; Allied Services International Limited (ASIL)
- PSDF has collaborated with GiZ for curricula development in biogas training scheme and has offered GiZ a platform to implement its updated curricula.
- Certification for some courses are provided by international organizations[6]
  [6] City and Guilds; EdExcel; European Aviation Safety Agency (EASA); Pearson Education LtD. (LCCI-EDI)

Output 1.4:
- In preparation of scaling up PSDF to new districts, a number of audits/reviews were conducted in 2012/13. These included a due diligence, an ASP/FRA, Board commissioned audit, and a number of Government (AG) Audits. Recommendations from these were consolidated in a single matrix and progress reviewed during quarterly reviews over the last one year. Out of a total of 100 recommendations, 72 have been completed, with a further 23 listed as “amber” and 5 as “red”. Actions to address the out-standing recommendations are underway.
- The audit report for FY 12-13 commissioned by the Board has been unqualified. Audit report for 2013/14 is awaited. Observations of the Audit Generals Office have pertained mostly to procedural issues and do not imply any fiduciary risks associated with the fund.

Issues:
In order to ensure that PSDF functions as an ongoing mechanism for competitively financing skills, the Board should define the long term vision for the fund and a plan for making PSDF sustainable.

Recommendations

Draft organizational vision and sustainability strategy needs to be circulated to GoPb and DFID by the next annual review in 2015.

Output Title	Poor and vulnerable trained
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress[7]
Cumulative number of persons trained in PEOP districts in / (a) South Punjab / (b) Phase 1 districts	a) Cumulative 48,500 / (incremental 28,500) / 40% women / (b) 0	a) Cumulative 50,964 completed / 39% women (incremental 30,964) / (b)0
[7] 50% results are attributable to DFID.

Key Points

- The milestone for this Output was revised downwards in March 2013. This was due to two reasons:
  - Delay in approval of the revised PC-1 (which was expected by mid-2013). However, government approvals for initiating activities in the new districts were not provided until November 2013. Hence activities in the new districts were initiated much later than had been expected.
  - A 3 month procurement freeze in early 2014 as the AG audit did not recognize the authority of the PSDF Board to supplement Governments PPRA procurement rules where these did not meet PSDF requirements. Due to limited capacity, no single training provider could deliver an entire training scheme advertised by PSDF. Additionally, to diversify the training provider market, the Board had agreed to cap the number any winning bidder could train for a particular trade/skill. PPRA rules, however, allow contracting only the top bid winner. An amendment to the Exchange of Letters between DFID and GoPb was finally approved by the GoPb, and PPRA to allow PSDF the flexibility to continue its operations

- Almost 10,000 students are currently enrolled under Skills for Garments course expected to be completed in the coming months. These numbers have not been included in the current review.
- 161 students graduated with Diplomas under the Veterinary Assistant Scholarship scheme (VASS) in June 2014. This was the only outstanding activity of the livestock and dairy component. When this component was closed, students had already begun their training so it was decided to continue support for this activity. Tracers will be conducted for VASS students as part of the evaluation. With the completion of the VASS all activities of the Livestock and Dairy component have come to a complete close.
- As PSDF expands its operation to new districts, in the absence of an effective labour market information system, it is adopting a more proactive approach for aligning its skills training with the needs of growth sectors/clusters in the Punjab economy. To inform its offer it has conducted 3 sector studies in textile and garments, construction and logistics to better understand employment needs. Sector studies for other growth oriented sectors (such as beverages, furniture making, food processing, livestock and dairy) with employment potential are also planned.

Issues:

The roll-out of PSDF to additional districts with a more robust economic base and aligning training to key growth sectors in those districts is highlighting a number of issues:

- Firstly, it is likely to result in more specialised, and expensive training. This may have an impact on cost of training while improving employment prospects of graduates. It may also impact on the entry qualifications required and thus exclude large numbers of poor with low educational qualifications. This will need to be monitored carefully to assess the impact.
- Secondly, as linkages with the formal (and industrial sector) are strengthened it is likely that due to the socio-economic challenges that women face in getting employment, women may be excluded from training. To date gender results have been satisfactory based largely on tailored training targeting women in traditional sectors.

Recommendations

- When targeting industrial sectors, PSDF should conduct sector analysis to ensure it identifies training opportunities for the less educated and illiterate poor and women along the value chains in that sector. This will help ensure that the poor and women within those sectors are not excluded.
- PSDF should prepare a gender mainstreaming strategy by the next annual review in 2015. This will help ensure that all segments of poor women with training potential are covered, women’s market linkages are improved, that they are introduced to non-traditional skills and that their chances of formal employment are also strengthened.

Output Title	Private training places mobilized
Output number per LF		3	Output Score	A+
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Percent of private sector places created as a result of PSDF funding	70% of total PSDF funded training places	76% of total PSDF funded training places.

Key Points
- Target moderately exceeded expectation. In all there are 120 training service providers, out of which 34 new training providers have been contracted this year. The capacity of the skill providers is generally growing due to the rigorous monitoring and contract compliance requirements of PSDF, though there has been no formal institutional assessment of the training providers yet. In less than a year 46 firms have also been contracted by PSDF as training providers.
- Given that overall there is limited training capacity in the private sector, PSDF’s approach of encouraging businesses to serve as training providers is a positive development. PSDF also encourages training delivery through consortiums which helps cross learning among skill providers and gain more leverage from the existing and nascent skill training capacity.

Issues:
- There is a likelihood of demand exceeding supply and technical capacity of the existing skill providers particularly as PSDF expands into new districts and offers more specialized new skills.
- Private sector lacks adequate facilitation and incentives to make capital investments in the skills sector and offer more specialized vocational skills.
- A network of over 300 TEVTA training institutes exist in Punjab but their capacity is almost 20% underutilized and they are by and large not market oriented.

Recommendations
- PSDF should share its operational, management and monitoring systems with TEVTA and PVTC for improving public sector skill providers efficiencies and market orientation.
- PSDF should offer incentives to providers for forming innovative partnerships to increase skill delivery capacity. Additionally, businesses/firms should continue to be mobilized to offer training.
- In order to build the technical capacity of the training providers, PSDF should conduct a performance ranking of the providers and accordingly initiate TSP conferences for exchange of ideas and lessons learnt among them.

Output Title	Support to the GoPb for skills policy and regulatory reform
Output number per LF		4	Output Score	A
Risk:		High	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1. Percentage of skill policy committees (govt. formulated) on which PSDF is represented	PSDF represented on 50% of the committees	PSDF represented on 100% of the committees:
4.2. No. of skills related briefings/advisory notes made to the Government of Punjab and other stakeholders per annum	4	5
4.3. No. of skills related sector studies and workshops conducted by PSDF (Cumulative)	Workshops= 3 / Sector Studies=1	Workshops= 3 / Sector Studies=1

Key Points

Output 4.1:
PSDF has been instrumental in shaping the decisions made by the skills policy forums organized by the GoPb. For example, based on PSDF’s feedback the idea of creating the Youth Skills Development Authority was dropped. The proposed authority had an overlapping mandate with existing skills related organizations including the federal apex skills body.

Output 4.2:
- Recommendations were made to the National level skills apex body regarding revising the potential provincial and federal skills policy and regulatory responsibilities post 18 Amendment (to the Constitution of Pakistan). However, negotiations remain inconclusive and will be pursued further.
- PSDF also provided briefing notes to the GoPb on restructuring the Punjab Board of Technical Education, garments skills sector and for removing contradictions in the TEVTA mandate.
- The initial success of PSDF has created demand within the GoPb to reform the skills policy and regulatory environment. As a result DFID provided TA support for improved coordination and governance of the skills sector in Punjab. Recommendations of this report (Assessment of the Industries Department) have been in principle agreed by the GoPb and the relevant stakeholders.

Output 4.3:
3 workshops were held in construction, logistics and garments sectors and were followed by sector studies of the garment and construction sectors. While these studies will help shape the skill schemes introduced in these sectors they will also provide valuable information for shaping future skills policy and strategy in Punjab.

Issues
- Donors need to improve coordination and develop a joined-up approach for improving the policy and regulatory environment governing skills.
- The skills sector stakeholders recognize the need for coordinating, monitoring and strengthening the skills sector in Punjab. However, they are sceptical about recommendations for improving the sector’s performance, given concerns about how any sector level changes may affect their own organizational mandate. For example the recommendations of the Department of Industries assessment report though well received in principle also evoked concerns regarding changes in the sector and how the skills organizations may benefit by any new arrangements.

Recommendations
- DFID in partnership with the GoPb will need to ensure that the concerns regarding implementation of the Industries Department report recommendations are addressed and that adequate support of the donors and the skills sector stakeholders is mobilized for implementing the report’s recommendations.
- DFID must continue to strengthen skills policy and regulation and provide TA support to the GoPb as required.
- Labour market intelligence being collected through PSDF should be available on its website and disseminated to other relevant government departments with labour and skills related mandates.

Output Title	Generation of evidence to inform skill delivery
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1. No. of survey and experiments related reports shared by CERP	3	3
5.2. No. of presentations made to BOD drawing on CERP results	3	3

This output pertains mainly to the Centre for Research, Pakistan (CERP) and its partnership with PSDF/PEOP.

Output 5.1:
- Skills For Market- SFM-A Village-based training and uptake report has been shared. Insights from this report are helping to improve the skills schemes of PSDF for targeting the rural and illiterate/semi-literate women.
- Skills For Jobs- SFJ Differential Stipend report has also been delivered by CERP. This report indicates that the opportunity cost of training for urban men is very high. Rather than increased stipends to lure men serious about training, assurance of a job after graduation may be more meaningful in getting them to enrol. Additionally, on- the- job trainings (OJT) may be another option for upgrading the skills of urban employed men. RCT experiments are underway to test these assumptions.
- CERP has disseminated the skills baseline household report to a variety of skills related stakeholders and the government.

Output 5.2:
SFM-A uptake experiment and SFJ stipend delivery experiment reports were presented to the Board for discussion and for sharing CERP’s approach for follow on experiments. Design of SFM- B was also presented to the Board for discussion and approval. The work plan for additional evaluation experiments covering an agriculture/livestock and dairy based intervention at the village level and evaluation of skills in select industrial sectors was also approved by the Board.

Issues
As the scale of experiments expands there will be increased need for CERP and PSDF to ensure field level coordination for timely and smooth implementation of the experiments and for PSDF to continue its operations without being held up due to RCT experiments.
- The experiment reports by CERP may be delayed as it becomes engaged in managing new experiment rounds and tracers studies.
- CERP’s existing staff capacity may be insufficient to manage the ongoing evaluation rounds in addition to the new evaluation plan covering the sector focused approach of PSDF.

Recommendations
The new evaluation proposal of CERP should adequately address the issues raised above. CERP and PSDF will need to delineate their roles and responsibilities so that there are no ambiguities about what roles need to be performed by whom.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

PSDF delivers good value for money. Since June 2011, PSDF has trained 50,964 poor and vulnerable people (40% women) in a range of skills/trades. The average cost per trainee is £336 and is roughly half of the cost of public sector for similar skills/trades. Increased competition in the training service provider market, due to PSDF’s intervention, has driven down unit costs by 38% within the past 12 months alone. Operational costs (excluding evaluation) are capped at 7%[8] which compares favourably with the DFID sponsored Employment Fund for Nepal which has an operational cost of 7.5%.
[8] DFID-P’s Education Fund for Sind has operational costs of 20%

Stipend offered to trainees (excluding lodging) are between half to one-third of the BISP and TEVTA stipends, depending on whether trainees are resident in the district where training is offered or need to travel from elsewhere. To improve retention rates, stipends are paid in tranches and training service providers are paid through an output based methodology for the number of trainees who actually complete their courses (validated by a third party monitoring).

PSDF market surveys ensure training provision is closely linked to employer’s needs. Initial findings from tracer studies indicate that 67% of graduates find employment within 6 months with 83% employed after 16 months. 43% of graduates are earning above the minimum national wage of £60 which is significant as 83% were unemployed prior to training. In 6 months a graduate can earn the cost of training spent on her/him by PSDF. This fact can help establish the market value of PSDF sponsored training and increases the scope for exploring partial (or even full) cost recovery of costs from trainees or employers. While these results are not definitive, they compare well with similar employment/training funds.

The Benefit-Cost Analysis conducted for the original PEOP programme is not valid any more as total costs of the programme and associated assumptions have changed substantially. However, a BCA conducted in preparation of additional funding support to PSDF establishes robust qualitative and quantitative returns for the programme.

Key cost drivers and performance

The key cost drivers are duration of training, type of trade, accommodation and stipend. About 10% of PSDF training is internationally certified which is significantly more expensive than the national testing authorities. In case PSDF offers more internationally certified training and more sophisticated vocational skills cost per trainee will increase further. Capacity of local trainers continues to remain an important cost driver as it determines the scale of training conducted by out-of-district providers. Inflation and electricity shortages are also expected to increase training costs resulting in higher average unit prices.

Bidding is crucial for reducing costs of training fee. A cost review conducted by PSDF in 2014 suggests a decline in average per trainee per month costs by more than a third (i.e. by 38%) in SFJ 2013-14 compared to SFJ 2012-13. This is also attributed to increased competition in market as more providers have become interested in working with PSDF.

Quality of financial management

PSDF: Overall PSDF has good financial management and oversight. A finance committee of the Board approves 6 monthly work plans and budgets and monitors their delivery. PSDF has had unqualified annual audit reports to date. Audits are conducted by independent auditors engaged on a competitive basis.

As of June 2014, 75% of the released funds were spent. Financial forecasts have exceeded actual spend due to more than expected cost savings realised through increased competition among training providers and cost negotiations by PSDF.

Recommendation

For improved financial management in future, PSDF will need to make more realistic forecasts and share the projected financial needs with DFID on a quarterly basis. Financial forecasts should also be directly linked with the numbers of people currently enrolled and expected to be enrolled in a particular quarter.

Audits and Accounts

During FY 2012-13, unqualified audit has been awarded to PSDF by KPMG (a certified firm of International Chartered accountants) which was appointed as the company auditor for these years. The audit reports state that “all business conducted, investments made and expenditures incurred during period were in the accordance with the objects of the company”. All independent audits of the CERP to date have also been unqualified. Audit of the VASS was conducted in July 2014 by the Auditor General’s office and the report is expected in the last quarter of this year.

Audit reports for 2013/14 for the programme are awaited.

Date of last narrative financial report	June 14
Date of last audited annual statement	2012-13

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk.

The overall programme risk is medium due to minimal risks associated with the operations and financial management of the fund. Given the high political insecurities and a potentially low growth economic environment, the risk of graduates not finding employment is high. However, PSDF is making concerted efforts to mitigate this risk by training people as per employers and market requirements.

New risk categories identified during course of implementation:

- There is the risk of PSDF’s sustainability as an effective and efficient organization beyond DFID’s period of support. A sustainability plan for PSDF needs to be developed to ensure that the fund continues to play a significant role in the future.
- As the fund expands to new districts, students who can afford to pay for training may also benefit from PSDF training. Well considered selection criteria need to be adopted to ensure only poor & vulnerable benefit from the subsidized training offered by PSDF.
- As the fund establishes operations in new districts, the risk of political interference in PSDF operations is likely to increase. This risk is however expected to be managed by a strong and proactive Board that has prevented such interference in the past.

Outstanding actions from risk assessment

A Fiduciary Risk Assessment was carried out by DFID in 2011 and the Fund was assigned a “Medium” risk category in its first year of operation. An action plan was prepared to address the following risk categories identified by the FRA: Management information system, internal assurance, automating the procurement system, and strengthening the communications department, Most of the recommendations from the Due Diligence assessment and the Annual Statement of Progress conducted last year have been followed through.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

No: The target for skills in the original programme memorandum (PM) was to train 250,000 at a cost of £100 per trainee. This estimate was unrealistic and did not factor in the depreciation costs of the rupee, and cost drivers such as training duration, location of training and type of trade. The per trainee costs where therefore revised keeping in mind the key cost drivers.

The project was originally approved for 48 months from Jan 2010- Dec 2013. However, the programme had a cost and time extension as fund made available with the closure of the livestock and dairy component (£24.3 million) were diverted to PSDF. The programme duration was increased by 2 years until December 2015.

Remedial actions

In order to control costs, PSDF has established a pricing mechanism that enables it to negotiate costs with potential training providers without compromising the quality of training.

Performance of partnership (s)

DFID has been working closely with PSDF for refining its reporting formats and linking financial progress with reported physical activities. PSDF has recently created a dashboard with an MIS. The remote link facility is being pilot-tested. Results of that would become available to DFID by Oct 14.

Asset monitoring and control

Assets are checked by the independent auditors of PSDF and through the audit of the office of the Attorney General Punjab. The 2012/13 audit reports no irregularities vis-à-vis the purchase and maintenance of assets. Audit report for 2013/14 is awaited. An asset verification spot check was recently conducted by DFID. The asset inventory was up to date and 95% items were functional (5% of dysfunctional assets included furniture items). 92% of the assets of the livestock and dairy component transferred to PSDF are in use.

G: CONDITIONALITY (½ page)

No official conditionality applies. However the Government of Punjab has committed to providing 50% of the financing of PSDF operations and thse contributions are reconciled with DFID disbursements at 6-monthly intervals. For the technical assistance to PSDF, spending conditionality applies to the judicious use of funds. The release of a subsequent tranche is conditional upon satisfactory spend of up to 80% of the previously released amount.

Update on partnership principles (if relevant)
Not relevant to the programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The Centre for Economic Research Pakistan (CERP) carried out baseline household and employers surveys in 2011. These surveys along with workshops with businesses and the field operations of PSDF are the evidence guiding PSDF operations and the course corrections that it makes.

CERP is also conducting the RCT evaluation of the programme. Presently voucher based experiments are underway to help build a robust sample size for the final evaluation of the programme in late 2015. The ongoing experiments are helping to understand the reasons for low uptake of skills among the general population, particularly rural women and the employed men. The findings from the initial experiments are feeding into the design of skill schemes being offered by PSDF.
An evaluation proposal for evaluating returns on skills delivered for industrial sectors are being developed by CERP. An agriculture/livestock and dairy based intervention at the village level ‘the Big Push’ is also being planned to assess the impact of agriculture related interventions on the village level GDP.

Meanwhile PSDF has a robust third party monitoring system covering its regular training schemes. Extensive contract compliance frameworks have been developed with penalties varying from nominal fines to black listing a training provider. PSDF is also conducting graduate tracker studies to determine graduates employment/income status.

Recommendation

It is challenging to track women graduates due to their cultural reservations about sharing contact details with third parties conducting tracker studies for PSDF. In the next rounds of trackers, PSDF will need to put in place a culturally more sensitive mechanism to determine women’s employment/income status.

Beneficiary feedback

The team visited the Sheikhupura Livestock Training Institute and 4 training providers based in Lahore to meet with the students and the faculty. Students were enrolled in a diverse range of trades such as veterinary sciences, fashion and clothing, air hostess, steward, production of confectionaries and beverages. Triangulation of information through student interviews shows that students belong to poor families. Overall students were satisfied with the training and doing well (all reported achieving 80-90% grades in exams). Feedback from students indicates that social mobilization/advertising efforts by the training providers and word of mouth advertising by graduates have been helpful in creating awareness about trades on offer.

Recommendations

- There is a need to ensure that women enrol in trade that they can find employment/self-employment after graduation. For example, women training to be air hostess expressed reservations about leaving their home districts, while their home towns provided limited employment opportunity for the skills they are learning. Initiatives for diversifying trades women are engaged in need to have well considered selection criteria accompanied with employment facilitation in order to ensure women can be employed in the trade that they are learning. They should also be accompanied with employment facilitation.
- Top-up courses in soft skills such as spoken English, presentation skills, and preparing resumes will be helpful in improving the job readiness of students. A few training providers have already initiated such courses in response to students’ demands.

Review Team

The review was led by Mehrunnisa Hashmi, Programme Officer PEOP with inputs from the PSDF management team, Jan Wimladharma, Team Leader Finance Market and Jobs team, Fatimah Afzal, Private Sector Development Adviser, Sohail Wajid, Programme Manager FMJ and Raza Khan, Statistics advisor.

Review Methodology

The review builds on the quarterly reviews conducted over the past 12 months with the PSDF and CERP management teams. Field visits to training providers were confined to greater Lahore (and Sheikhupura) and did not include visits to southern Punjab (as these had been conducted during the last annual review). Further inputs were provided through a series of audits and assessments of PSDF/PEOP that had been conducted in 2013/14 and by consultants designing the proposed scale-up of PSDF. Information was collated through discussions with the PSDF staff and review of the following reports:

Documents informing this review

- Programme monthly financial and progress reports by PSDF and P&DD
- Quarterly performance reports of the TA for PSDF
- CERP evaluation reports: SFJ & SFM 2012-13: Skills Intervention Reports
- PSDF Tracer Report 2014, PSDF’s scheme summary reports, student assessment reports, graduate reports and PSDF Dash Board Report
- Quarterly management reports
- Value for Money analysis of PSDF
- Draft Options Paper and Review of Skills Market report
- Minutes of Board meetings

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process