Business Case

Summary Sheet

Title: UK Membership of the OECD Development Centre (the ‘Centre’) in 2019 and 2020.
Programme Summary: This programme will pay assessed contributions for UK membership of the OECD Development Centre in 2019 and 2020. Membership allows the UK, with other member countries, to support and influence the activities of the Centre in its provision of global public knowledge, in reflecting developing country “voices” in its work, and in improving its contribution to wider OECD thinking on policies relevant to development.
Programme value: EUR 1,543,775		Country/ Region: N/A
Programme code: 300260	Start Date: 1 January 2019	End Date: 31 December 2020
Overall programme risk rating:	Moderate
Vault Number:	46439762

Intervention Summary (2 pages max)

The OECD Development Centre (the Centre) designs innovative solutions to global development challenges. Its overarching goal is to improve well-being through sustainable, inclusive growth and poverty reduction in developing and emerging countries. To achieve this, the Centre informs development policy and practice through expert analysis and shapes the development discourse by convening countries at different stages of development to share knowledge and experience on economic and social policies.

The Centre has 54 member countries: 27 OECD member countries and 27 emerging and developing economies. Members finance the Centre and serve on its Governing Board, which sets the biennial work programme and oversees its implementation. The Centre is part of the OECD Development Cluster which mainstreams development across the OECD.

In framing the Programme of Work and Budget (PWB) 2019/20, the Centre considered emerging trends, development challenges and the evolving international agenda, as well as member country (including UK) priorities. In particular, the PWB has been shaped to help members’ implementation of the Sustainable Development Goals (SDGs).

Expected results of this programme will be for UK and other members to have an improved understanding of the binding constraints affecting developing countries’ economic growth and well-being and of the policy choices available to address them. The UK will also engage in knowledge sharing and learn from the relevant experiences of non-OECD economies in the face of common development challenges. The expected impact is for improved policy formulation and implementation to tackle policy impediments to economic growth and social cohesion, and to promote well-being in emerging and developing economies.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?

Yes. As a forum promoting north-south and south-south co-operation, the Centre’s platforms will support DFID’s strategic objective of promoting global prosperity by identifying challenges to economic growth and prosperity and policy solutions to address them. The Centre’s inclusive societies workstream will support DFID’s strategic objective of tackling extreme poverty and helping the world’s most vulnerable, particularly through its work on advancing the gender equality agenda (see Strategic Case).

What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?

- None. As a multilateral organisation, the Centre’s PWB is not specifically focused on delivering DFID’s Single Departmental Plan (SDP). Therefore, the programme’s outputs are not directly framed or adjusted to deliver the SDP results targets.
- However, outputs of the Centre’s PWB 2019/20 will support Strategic Objectives three and four in line with DFID’s global prosperity and poverty agenda. Members feed into and shape the PWB during the drafting process each biennium. The UK therefore has the opportunity to shape the planned outputs of PWBs so that the Centre’s products inform policy linked to UK development priorities.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?

- The Centre’s work programme is not directly linked to programmatic interventions.
- During the PWB 2019/20, the Centre will continue to contribute to and enhance OECD efforts to support the global development architecture, including Agenda 2030 and the SDGs, the G20 Development Working Group, and South-South and Triangular Co-operation agenda.
- Exit strategy: the programme is financed by members’ assessed contributions. To withdraw funding, a member provides12 months’ notice of its intention to leave the Centre.

Has the programme considered working with HMG Departments and accessing cross-HMG funds?

- We have tested other HMG Departments’ (FCO and HMT) appetite to take over funding for the Centre. However, while the FCO contributes to the OECD’s central budget, DFID is seen as the most suitable HMG funder.
- UKDEL policy leads engage DFID and wider HMG in the Centre’s work. Current examples of joined-up work include the African Economic Outlook (DFID/FCO), the OECD Latin American Regional Programme (DFID/FCO) and the Policy Dialogue on Natural Resource-based development (DFID/Cabinet Office).

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?

As part of the Development Cluster, the Centre collaborates with the OECD Development Assistance Committee (DAC), to which the UK provides assessed (FCO) and voluntary (DFID) contributions.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?

- There is little flexibility to adjust the Centre’s biennial PWB once all members have approved the activities and budget. Funding of outputs reliant on voluntary contributions (non-core budget) could ensure completion of any UK priority work at risk due to limited resources.
- The renegotiation of the PWB every two years allows for review of the successes and failures of the previous PWB and for future activities to reflect the current development context. As a member, the UK feeds in its priorities and influences each iteration of the PWB.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?

- The Centre is a long standing, established forum and is subject to the same rules and standards as the rest of the OECD with regard to its financial controls, rules and procedures. Financial risk to the success of the programme is therefore low.
- The Centre’s output areas in PWB 2019/20 present low reputational or political risks to HMG. The UK reviewed and commented on the PWB drafting process prior to approval. UK representation at the Centre’s Governing Board meetings, along with close monitoring and engagement of its activities reduce this risk further.
- The programme has been rated medium risk overall because the Centre has struggled to get much traction with HMG policy makers through its work. There is therefore a delivery risk of the work programme not greatly increasing DFID policy formation abilities.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?

No. This is a multilateral organisation with its own branding, so it will not be UK branded. The Centre has a communications strategy which promotes member engagement and wider awareness of its workstreams.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?

- To ensure the quality of the programme, the Centre aligns a Results Framework (a tool introduced at the UK’s request) to its PWB. A tracking document also measures interim progress of the programme against the Results Framework at different stages in the biennium.
- The Centre draws on a wide range of expertise to deliver the programme. Staff experts work with colleagues from the OECD and partner countries to produce policy analysis relevant to current development issues. A wide variety of partners (including policy makers, institutional partners, civil society, private sector) also help build capability and contribute skills and resources to the delivery of the programme.
- UKDEL’s Development Team is able to monitor the delivery of the programme on the ground and to ensure that quality work is being undertaken.

Do the SRO and team have the capability and resources to deliver this programme?

- Yes. The SRO is based within UKDEL and is therefore able to closely monitor the delivery of the programme. The SRO has support from the programme manager in the Global Partnerships and Multilateral Effectiveness Department (GPMED), as well as programme and policy support from UKDEL.
Strategic Case

UK membership of the Centre provides a number of benefits. Its key workstreams align with DFID’s thematic priorities, including inclusive growth, gender equality, social protection, development in transition and migration. The Centre also undertakes regional and national analysis and produces a range of reports, such as its regional economic outlooks, which the UK has the opportunity to contribute to, shape and learn from. The Centre’s Governing Board brings together countries at different levels of development on an equal footing. The Centre also has broad outreach as a dialogue platform and convenes diverse development partners (for example, United Nations Development Programme, Regional Development Banks) and actors (policy makers, private sector, foundations). The Centre adds value to the OECD development debate through its multi-sectoral and multi-dimensional approach to addressing bottlenecks to development, as well as through its wide convening power.

Membership enables the UK to influence and shape the Centre’s workstreams in line with UK priorities. The Centre also provides a forum for the UK to engage with development partners from non-OECD countries such as China and India. Active UK membership also ensures that the Centre’s outputs provide added value to the OECD Development Cluster and to the OECD’s strategic response to member implementation of the 2030 Agenda.

If the UK decided to withdraw its membership, several opportunities would be lost, including: influence to shape key workstreams to better inform UK thematic and regional policy priorities; full access to a platform for promoting UK development agenda; using Centre’s broad outreach to enhance development co-operation; capital to influence the wider OECD development debate.

Impact and Outcome
Impact
The overarching goal of the Centre’s PWB 2019/20 is to improve well-being through poverty reduction and sustainable, inclusive growth in developing and emerging economies.

Expected outcome
The Centre contributes to shaping the global development architecture, contributing valuable research and analysis to the evidence-based debate, both within the OECD and the wider international context.

Expected outputs
Work agreed in the PWB is delivered to a high quality, supported by good transparent governance of the Centre.

The Centre effectively brings low income countries (LICs) as well as middle income countries (MICs) into the development debate

The Centre’s work adds value to the development debate through strong performance by the organisation, work being valued and used by stakeholders to inform development debates.

The programme’s long-term goal aligns with the objective of promoting global prosperity in DFID’s Single Departmental Plan (2015-2020). The following workstreams will contribute to this objective in the PWB 2019/20:

- Inclusive Societies – outputs (focusing on gender equality and women’s economic empowerment, social protection, inclusive growth, employment and youth-wellbeing and migration) will contribute to DFID’s agenda on inclusive growth.
- Competitive Economies – outputs (production transformation for development, natural resource-based development and infrastructure and rural-urban linkages) aim to deepen understanding of how trends (such as digital technologies and automation) impact structural transformation, and how effective strategies and policies can promote diversification and better integration in global markets for job creation and sustainable development.
- Regional work with Africa – main components will include a new continental Report (aimed at informing the design and implementation of policies to meet Africa’s development targets), two editions of Revenue Statistics in Africa, and policy discussions within the Initiative with Africa (further developing engagement with African governments, organisations and non-state actors).
- Emerging Markets Network (EMnet) – provides a platform for dialogue between OECD-based multinationals and emerging market counterparts, with the aim of strengthening private sector engagement in the work of the Centre and wider OECD.

Theory of change
Context:
The Centre is an established international forum (created in 1961). Membership is open to both OECD and non-OECD countries and currently has 52 members from diverse stages of development. The Centre’s Secretariat provides the policy and analytical support. Decision-making is based on consensus.

Long-term change
To measure progress towards the long-term goal, the Centre’s PWB is structured around four objectives:
1. Identify and frame issues critical to the development dialogue
2. Influential analysis and evidence base
3. Mobilise and translate global and OECD expertise to support non-OECD decision makers
4. Mobilise development knowledge to influence OECD thinking

- In order to achieve long-term change, the UK prioritises the Centre’s role in providing clear benefits to LICs and Least Developed Countries (LDCs), including enabling an exchange of practices between MICs and LICs; convening a wide range of development actors, in particular providing a space for dialogue with emerging donors; and in complementing DAC outputs as part of the OECD Development Cluster.
- UK assumptions about how long-term change might happen include DFID’s targeted and consistent engagement with priority workstreams of the Centre; UK engagement with other members to ensure quality and relevance of the Centre’s products; and a Governing Board that allows open and constructive exchange between all members.
- The Centre produces a yearly report that tracks progress made towards achieving the objectives of the four overarching objectives of the PWB. For the programme biennium, an interim report will be issued in early 2020 and the final report in early 2021.
- The Centre aims to boost development and poverty reduction around the world through influencing policy makers towards higher quality policy decisions. Concrete examples of how the Centre has informed policy makers in current biennium (2017/18) include:

1. launch of new Thematic Dialogue on Commodity Trading Transparency at meeting of Policy Dialogue on Natural Resource-based Development in June 2017, in line with commitments made at UK Anti-Corruption Summit it May 2016. A Mid-Term Self-Assessment Report found general consensus among countries that made commitments that OECD should host and convene the international dialogue on commodity trading transparency.
2. Centre’s appointment by UN Group on SDGs as one of the custodian agencies to track progress on gender equality, notably on SDG 5.1.1, which measures whether legal framework promote, enforce and monitor gender equality.
3. Providing, on request of Ethiopia’s Ministry of Labour and Social Affairs, assistance in development of a financing strategy for the implementation of Ethiopia’s National Social Protection Strategy. Results of next phase of analysis to follow.
4. Centre’s partnering with EU and UN Economic Commission for Latin America and the Caribbean (ECLAC) to lead work on exploring the concept of ‘development in transition’ including the launch of a Regional Facility for LAC Countries in Transition. The Facility will support the design and implementation of public policies to achieve the SDGs as LAC countries transition to higher income levels.

We anticipate similar levels of influence and progress under the current PWB 2019/20.

Gender Equality
The Centre’s work on gender equality highlights the central role of discriminatory social norms in perpetuating gender inequalities in non-OECD countries. In the 2019/20 PWB the Centre’s work will focus on:

- measuring and transforming social institutions, building on the 2018 Social Institutions and Gender Index (SIGI) to offer targeted guidance; and
- investing in women’s economic empowerment, as part of the cross-OECD Policy Dialogue on Women Economic Empowerment, focusing specifically on unpaid care work.

The Centre’s gender inequality work has international standing since its appointment by the UN as one of the custodian agencies for the collection, collating and tracking of data to demonstrate progress on gender equality under SDG 5.1.1.

Risk
The programme will operate in a low-risk context. The Centre is an established forum and is subject to OECD standards and regulations including on staff conduct in relation to safeguarding. To ensure delivery of the programme, the Centre applies a Results Framework, an internal management tool that guides planning and monitoring of activities, collection of evidence, and regular assessment of results with respect to progress towards achieving the objectives of the PWB. UKDEL Paris monitors the delivery of the programme and engages with the Centre’s Secretariat and members at quarterly Governing Board and informal meetings. UKDEL Paris will also use these meetings to assess and improve Development Centre processes to identify, assess and escalate risks, including safeguarding risks. OECD measures in place to control financial flows ensure fiduciary risks are minimal (see Financial Case).

Terrorism and financing
Risk of UK resources being diverted for terrorist-related activities is very low. There are a number of mechanisms in place across the OECD to ensure due diligence in the use of, and provide reasonable assurance to members that,  resources provided to the OECD are used in an appropriate manner and in accordance with generally accepted ethical standards of the international civil service.

The Centre operates within the OECD-wide institutional framework. As such, the OECD’s corporate control and accountability mechanisms, ensuring appropriate use of members’ resources, apply to the Centre and its staff.

Working with partners
The UK will work with the other 51 member states and the Centre’s Secretariat to oversee the delivery of the programme. As a member of the OECD and the DAC, UK engagement with the Centre’s work programme will ensure that the outputs inform the wider OECD development debate and that a clear division of labour is maintained within the Development Cluster and notably, with the DAC.

Disability

There are no specific outputs related to disability inclusiveness in the programme. The Centre’s Inclusive Societies workstream focuses on enhancing social cohesion of the most vulnerable populations but this does not specifically address people with disabilities.

Appraisal Case

The UK was a member of the Centre from its establishment in 1962 until 1996. At this time the UK withdrew with others (including US and Japan) as a result of a number of concerns about the Centre’s performance. Following a positive independent evaluation and internal DFID assessment of the Centre, the UK re-joined in February 2007. Since then, DFID has tracked the performance of the Centre closely and UK membership has been influential in helping the Centre implement a substantial reform programme.

In December 2013, following an internal review by DFID, the Secretary of State for Development wrote to the OECD Secretary-General requesting stronger evidence of the Centre’s impact and the value-added of its work in order to secure UK support beyond 2015. A Performance Improvement Plan (PIP) was subsequently agreed with the Centre, specifying the actions that needed to occur.

Following a final assessment in 2014, the Centre was found to have been highly responsive to UK requests, having designed and implemented a Results Framework, carried out a benchmarking exercise and agreed a short-term budgetary deal with agreement on a revised scale of assessed contributions forecasted by end 2015. After the Centre failed to reach this target, the Secretary of State wrote again to the OECD Secretary-General setting out UK expectations for an agreement on the scale of assessed contributions by early 2016 at latest. The Centre’s Governing Board reached an agreement in March 2016 and the UK confirmed continued membership and funding of the Centre whilst still monitoring for improvements of demonstrable benefits to LICs and the impact of its outputs.

The Project Completion Review (PCR) for the Centre’s PWB 2015/16 outlined a number of achievements. These included the expansion of the social dimension of its work programme, membership growth, agreement on a revised scale of assessed contributions of the Centre and improved mechanisms to track the uptake and impact of policy advice. Despite these achievements, the programme scored a B (moderately did not meet expectations) in the overall outcome assessment of the PCR. Factors influencing this score included governance issues limiting efficiency and effectiveness of the Centre’s Governing Board, concerns that the Centre is not providing a sufficient platform for LIC voice, a target for an In-Depth Evaluation which the Centre did not meet, as well as limited and irregular engagement from DFID with the Centre’s workstreams.

In 2017 and early 2018, UKDEL has engaged with the Centre’s Secretariat to seek improvement in lower performing output areas. On governance issues, the Secretariat has improved communication on Governing Board procedures, for example with membership applications, and UKDEL has engaged with the Chair on UK priorities for the Centre. In response to the UK call for a greater focus on LICs, the Secretariat has produced a mapping of current LIC/LDC engagement, launched the 2018 flagship Africa regional report in Addis Ababa and is reviewing its engagement with this economic grouping. Progress is now being made on the In-Depth Evaluation, with the core evaluation stage now underway and a draft report scheduled to be submitted to OECD Evaluation Committee by mid-2019. A mapping has now been produced of DFID engagement with the Centre and UKDEL continues to monitor and seek opportunities for outputs that align with UK priorities and complement the work of the wider Development Cluster.

A DFID Portfolio Quality Review in the first half of 2017 supported the continuation of UK funding for this biennium (2017/18). In December 2017, DFID reviewed UK membership and recommended continued UK membership of the Centre for the 2019/20 biennium, with the condition of a PIP being agreed with the Centre’s Secretariat. Given the performance improvements achieved since then as outlined above, we do not believe that a further PIP is required at this stage. We will however continue to monitor the performance of the Centre closely.

The alternative option of the UK withdrawing membership of the Centre would only apply from 2021 onwards given that the OECD requires at least 12 months’ notice.

Value for Money

Membership of the Centre provides opportunities to both inform and promote the UK development agenda. Considering this, the Centre’s achievements in the 2015/16 biennium, its improved performance in the 2017/18 biennium, the intervention is judged to offer satisfactory value for money.

Commercial Case

The Centre has completed a value for money plan (VfM) highlighting several efforts to achieve cost-savings and effective use of resources, and forms part of an OECD-wide project which aims to give members maximum value and impact from the resources they provide. VfM is focused on sustainability, and reinforcing the culture of continuous improvement and ‘value for money consciousness’ in the OECD. The Centre implemented a series of VfM initiatives during the PWB 2015/16 and PWB 2017/18. For example, a new OECD development topic webpage and joint blog platform were created to achieve a more strategic and coordinated approach to OECD communications on development. VfM initiatives for 2019/20 biennium include rationalisation of office space with the departure and non-replacement of staff working on projects funded by voluntary contributions that ended in 2018; revision of the Results Framework to maximise impact and VfM of PWB outputs; and reinforcing the Centre’s partnerships and collaboration with stakeholders to advance the Centre’s priorities and contribution to the international development debate.
Following successful UK lobbying, the Centre’s Governing Board agreed to a revised system for determining assessed contributions in 2016. This agreement met the UK’s objectives for a fairer and more logical methodology, which will be updated annually to reflect capacity to contribute. Consistent with OECD rules, the criterion used to determine capacity to contribute is annual national taxable income. The new system for calculation of assessed contributions was applied at the start of the OECD financial period 2017 (calendar year). The need for further reform will be assessed in 2022.
Governing Board members decide biannually on whether Zero Real Growth (ZRG) or Zero Nominal Growth (ZNG) adjustment rate should be applied to the biennium’s budget. Members agreed to ZRG for the PWB 2017/18. For the 2019/20 core budget, members agreed on the application of a 1% intermediate annual adjustment as a compromise between support from a majority of members to adopt a budget of ZRG (adjustment of 1.5% in 2019 and 1.9% in 2020) and a preference from others (including the UK) for a Part II core budget based on ZNG (0% annual adjustment). The UK will pay an estimated €17k less in its assessed contributions for the 2019/20 biennium with the application of the 1% intermediate annual adjustment, than if ZNG has been applied.
Poor performance by the Centre in achieving VfM would result in the UK reconsidering its membership beyond delivery of PWB 2019/20.

Financial Case
Overview of costs
The OECD budget is comprised of Part I and Part II programmes of work. All OECD member countries contribute to the funding of the Part I budget. Part II budgets include programmes of interest to a limited number of members - or relates to special sectors of activity not covered by Part I. The Centre is an OECD Part II body and is funded according to a scale of assessed contributions based on capacity to pay. The criteria used to determine capacity to contribute is annual national taxable income in Euros.
DFID will pay an €772,056 in assessed contributions for UK membership of Centre in calendar year 2019 and an estimated €771,719 in calendar year 2020. The final value for 2020 will be confirmed in early 2020, when the OECD issues the UK with its call-up of assessed contributions for the calendar year. All member contributions to OECD are paid in Euros. Payments will be made in arrears following submission of annual invoice and so will not be made in advance of need. Approval will be sought from DFID Financial Accounting before Euro payments are confirmed. UK funds will contribute to the delivery of outputs identified as core work under the PWB and will constitute around 10% of the budget envelope for assessed contributions.
The vast proportion of UK assessed contributions will be used to fund the employment of technical and policy experts working on the programmed activities. A proportion of member assessed contributions (core budget) is used to cover central OECD support services (legal, HR, financial/accounting services etc.), office space rental and other staff-related operating costs (furniture, IT equipment, phone usage etc.). The estimated ratio of administrative and overhead costs is 15% for 2019/20. This is an indicative figure, as the amount of central support costs covered by members’ assessed contributions fluctuates depending on the amount of voluntary contributions received during the programme biennium.

Decisions on changes in OECD salaries and allowances are undertaken in line with recommendations of the Coordinating Committee on Remuneration (CCR)), an external body on which the UK also sits. The CCR has developed a remuneration adjustment methodology that seeks to ensure that salary adjustments are in line with civil servants in eight European countries (including the UK, Germany and the Netherlands).   Following repeated concerns by the Secretariat that they are having problems recruiting for certain positions, the UK is now encouraging the OECD to undertake a Strategic Workforce Review, which will include benchmarking OECD salaries against civil services and other talent pools.
OECD monthly basic salaries according to grade are published in the staff manual available online (see p.52, https://www.oecd.org/careers/Staff_Rules_EN.pdf).
OECD travel policy is set out in the staff manual (see p.116-136). Officials travelling on duty are entitled to a daily subsistence allowance at a rate determined on the basis of the country or countries to be visited. The travel subsistence allowance takes the form of a fixed sum, calculated for various destinations, on the basis of the following breakdown: 50% accommodation; 15% lunch; 15% dinner; 20% miscellaneous. Normal mode of transport is by air or train, with Directors determining the class of travel depending on the duration of the journey, the length of the mission, the time difference and other elements that may influence the conditions of travel. Internal guidance (not detailed in the staff manual) states that officials may travel business class for flights of more than six hours, or for night flights of more than five hours.

As with similar core contributions to multilaterals, this is 100% ODA eligible.

The programme will be Programme RDEL funded. GPMED’s Programme RDEL Resource Budget for 2019/20 is currently over-programmed, this will need to be managed from within the International Relations Division’s resources. As part of the programme is out with the current Spending Review we will be seeking HMT approval for this part.
Financial and fraud risk
The Centre is subject to the same rules and standards as the rest of the OECD with regard to its financial controls and administration. Compared to other international organisations, the risk profile of the OECD is low: 95%+ of staff are based at the OECD Headquarters in Paris, and 80% of costs are payroll/pensions and therefore automated. There is no expenditure in countries that we might consider high risk. The financial and fraud risk is therefore deemed to be minimal.
The OECD is currently in a sound financial situation. Financial Accounts for 2017 for the whole Organisation (Part I and Part II Bodies) were approved at OECD Council in December 2018. An external auditor reviews the accounts of OECD Part I and Part II bodies.
The OECD Audit Committee (a sub-group of OECD Council consisting of five Ambassadors, including the UK, and three representatives from supreme audit institutions) oversees the work of the internal and external auditor. The Audit Committee is kept updated on the status of the implementation of internal and external audit recommendations. The Audit Committee Chair provides a report to Council after Committee meetings, which is then made available online. The UK has the opportunity to participate in and influence audit discussions at the OECD Audit Committee, Budget Committee and Council.
When exercising their functions in the framework of PWB implementation, OECD staff may, through appropriate delegation of authority, be responsible to mobilise and execute the management of the OECD’s financial resources. This inherently entails compliance with the OECD Financial Regulations as adopted by Council, which govern the administration and management of all financial flows (both in terms of income and expenditure), within the OECD.  These regulations highlight principles of accountability for Officials (Directors, Heads of Programmes) to whom the Secretary-General has entrusted the responsibility of a budget by delegating authority and provide for ways to ensure effective segregation of duties is followed. The measures put in place to control financial flows across the OECD provide, inter alia, reasonable assurance that:

- the transactions relate to the implementation of the PWB;
- they represent the best value for the Organisation;
- the transaction envisaged can be carried out in conformity with the Financial Regulations, the Financial Instructions or other rules applicable to the Organisation;
- the supporting documentation required for the expenditure is available and appropriate;
- carry no reputational risk for the Organisation.

Monitoring, reporting and accounting for funds
In addition to the above monitoring frameworks, the Centre applies various accountability and evaluation mechanisms. In particular these include:

- the Governing Board is provided with regular reporting on advancement of activities and status and nature of income and expenditure through the Governing Board Progress Reports prepared by the Secretariat;
- members are invited to provide feedback on the rating of the quality and impact they attribute to the outputs delivered through the Programme Implementation Report;
- In-depth Evaluation of the Centre, designed to support Council in its oversight of Committees’ performance (see Management Case).

Management Case

Monitoring and evaluation

The programme will be monitored by DFID officials through the Project Management Cycle. A final Project Completion Report is due in April 2021. The SRO represents the UK at Governing Board meetings and being based in UKDEL in Paris, is able to closely monitor the implementation of the programme and engage with its partners. A programme manager and policy officer provide policy and programme support to the SRO. DFID policy leads engage bi-laterally with the Secretariat to review and shape the delivery of outputs under key workstreams. UKDEL disseminates products, such as flagship publications, to relevant policy leads and seeks to secure HMG participation at key events (both in Capital and overseas) and meetings at OECD.

The Centre and its members monitor progress against the PWB through quarterly Progress Reports, which provide detailed information on the budget and status of progress achieved at the level of outputs in the PWB. To track progress, the Centre’s Secretariat uses a Results Framework as an internal management tool which enables an easier assessment of how the proposed activities in the 2019/20 PWB contribute to realising the Centre’s objectives, outcomes and goals. The report for 2019 (combining results for the first and second quarter) will be available in March 2020 and the final report covering the full biennium will be available in March 2021.

Every two years the OECD carries out a Programme Implementation Report (PIR). The PIR is a survey which gives end-users of the OECD’s work the opportunity to provide feedback to the Organisation. It is intended to be a systematic output reporting mechanism of Output Results of previous PWBs and an evaluation tool by which member countries, end-users in member governments and other stakeholders can evaluate completed Output Results with respect to quality and impact/potential impact, and provide some insights into the usage of the Centre’s outputs in policy development processes. The Centre has now completed two rounds of PIRs which together cover its work programme from 2011-2016. The PIR results are now being analysed and will be taken into account in planning subsequent programmes of work, and therefore allow the Centre to strive to continually improve its performance and effectiveness.

The Centre volunteered and paid to undergo an OECD internal In-Depth Evaluation (IDE) in 2014. The IDE is a major reporting and evaluation exercise which should provide members with further insights into the level of satisfaction on the quality and impact of the work. Following a delay in the process, outside of the control of the Centre, the core evaluation process is now underway and a draft final report to OECD Evaluation Committee is expected for mid-2019.

The UK’s position as an active and respected member of the Governing Board will help ensure strong performance by the Centre during the 2019/20 biennium. In addition, bi-lateral engagement with the Secretariat will allow the UK to carry out regular stock takes of the Centre’s progress against outputs and identify actions for improvement. If the Centre’s performance proves unsatisfactory at any point, UKDEL will escalate the issue at Ambassador-level and seek support from likeminded development partners to address the issue, as well as informing senior civil servants in DFID. The Centre’s Secretariat stands ready to engage with the UK identifying and implementing measures to enhance the performance of the programme.

Risks

Governance issues limit members’ opportunities to use the Governing Board as a platform for open and constructive dialogue. This risk will be mitigated by active UK participation in the Centre’s activities as well as regular engagement with the Centre’s Secretariat, the Chair of the Governing Board and with likeminded development partners on the Bureau of the Governing Board.

Inconsistent engagement by DFID policy officers with the Centre’s workstreams risks limiting the VfM that the UK receives through its membership of the Centre. UKDEL will continue to monitor, identify and promote opportunities to support UK priorities with relevant HMG policy leads.

A propensity to focus on the MIC voice limits the value-added of the Centre’s workstreams for LICs. UKDEL will continue to engage with the Centre’s Secretariat, the Chair of the Governing Board and with likeminded partners to ensure that its work programme is providing demonstrable benefit for LICs.

(iv)	Insufficient horizontal collaboration between the Centre and outputs of the DAC and wider OECD.
UKDEL will continue to engage with the Centre’s Secretariat, the Chair of the Governing Board, the newly-elected DAC Chair (UK-sponsored) and likeminded partners to ensure DEV work programme complements the work plan and outreach of the DAC and wider OECD.

Smart Guide
## The Business Case:
- Sets out the case for a programme, adapted to suit the context
- Explain clearly and succinctly what the programme will do within what timeframe and is explicit about the risks and uncertainties and how they will be managed
- Records an understanding for DFID, our partners and intended beneficiaries about what we are planning to do and the results we expect to achieve
- Allows DFID to report to the UK public on what we are doing with taxpayers’ funds
- It should be as proportionate as possible. Consider using sub headings and paragraph numbers.

The Business Case is structured around the Treasury 5-case model. Within this broad framework the design should be adapted to suit different contexts and investment types. The content is indicative, not prescriptive and teams are encouraged to use judgement in making a logical argument to make the case in a way that suits the individual investment.

Refer to the considerations below, and the 10 delivery & 10 approval questions in the Smart Rules.
Intervention Summary (2 Pages)
Start with a half page maximum narrative summary of what the programme will do, ensuring you cover the points set out at the top of that section. Then use bullet points to answer the ten approval questions that follow. Do not delete the headings/questions in bold, but do delete any square brackets which provide steers about what to think about.
Strategic Case
This makes the case for DFID intervention by setting out the overarching context and the problem to be addressed. It should be clear what the programme will do (impact and outcome) and how with evidence. It should link to, but not repeat, the Business Plan with a clear illustration of how the programme contributes to DFID’s global and portfolio priorities. Retain the two sub-headings and provide the information required under each of them (deleting the square brackets). It is up to you where in the Strategic Case the sub-headings go. But it might make most sense at the end.
Appraisal Case
The Appraisal Case explores how we will address the need in the Strategic Case in a way that optimises value for money. It appraises genuinely feasible options for achieving the objectives, including high level commercial choices, with a summary of the quality of evidence. The appraisal considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a summary VfM statement for the preferred option.
Commercial Case
This section provides more detail on implementation and how value for money will be achieved. It sets out the procurement approach and requirements, proposed funding instrument and how the choice of instrument will be used to ensure VfM. It considers the market place response to this intervention with an explanation of how supplier performance would be managed. It sets out the procurement policies, capabilities and systems of the third party entity to ensure we get VfM.
Financial Case
This section sets out issues of affordability and the sources of funding. It includes a high level budget which does not impair VfM in procurement exercises for individual contracts. It sets out how funds will be disbursed and how expenditure will be monitored, reported and accounted. It highlights the evidence underpinning a judgement that funds will be used for the intended purposes.
Management Case
This section focuses on governance and management arrangements and the ability to deliver. It sets out the management implications for the business unit/ level of effort with realistic timings for mobilisation and start up. It outlines the expected roles and responsibilities, including DFID’s own resourcing strategies (SRO, programme team etc). It sets out how it will respond to changes in context and the key elements of the Delivery Plan, key milestones and decision points where we can course correct. It includes a clear illustration, ideally set out in a risk matrix, of the risks and risk appetite. It should include the envisaged approach to escalating risks and issues as well as exit and possible closure scenarios.