Type of Review: Annual Review

Project Title: Mobilising for Development (M4D) Programme

Date started:	June 2012
Date review undertaken: February 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / The Business Case or earlier project documentation. / The Logframe. / The detailed guidance (How to Note) - Reviewing and Scoring Projects. / The most recent annual review (where appropriate) and other related monitoring reports. / Key data from ARIES, including the risk rating. / The separate project scoring calculation sheet (pending access to ARIES). / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID will provide £20 million for a period of 6 years from April 2012 to March 2018, with a review in the third year. Mobilising for Development (M4D) is made up of two component: / Mobilising for Development (M4D) main programme delivered by GRM (£17.7 million 2012-18) / Voice to the People (V2P) is funded from the strategic fund and is delivered by Christian Aid (£2 million 2013-15) / The review team undertook an annual review of the main M4D programme against its individual logframe. The Voices to the People programme is reviewed separately.

What are the expected results?
The programme will strengthen social accountability and tackle social exclusion. It will work with 650,000 people, among them at least 30,000 girls in 270 community groups in 9 Local Government Areas (LGAs) in Kano, Kaduna and Jigawa. As a result of this support, these people will make faster progress towards the MDGs. Citizens will be more able to plan and control their development. They will be more aware of the responsibilities of government to deliver services more effectively and local government will be more responsive. The 30,000 girls will have their awareness and self-confidence raised, go to school for longer and marry and have children later. The expected outcome is “Policy Makers and Service Providers are more responsive and accountable to citizens’ better articulated demands and entitlements, especially adolescent girls and people with disabilities”. / To achieve this outcome the programme will deliver the following outputs and results: / Communities better organized, engaged and demanding equitable service provision and development outcomes – by 2018, 54 CBOs, representing 650,000 people will have become better organised, engaged and will be demanding services. / Marginalised groups, particularly girls and people with disabilities better organised, engaging and demanding services and development outcomes – both from within the community but also acting directly with policy makers and service providers across all 45 wards and in nine LGAs – at least 30,000 girls will be directly impacted. / Increased knowledge/awareness of policy makers and service providers to design, innovate and implement appropriate and responsive approaches to selected service delivery issues – 540 individuals will benefit, registering 65 demands and producing 65 action plans over the life of the programme. / Innovative and better-fit approaches to service delivery and accountability mechanisms on targeted issues identified, developed and tested - 18 innovative service delivery approaches and 6 accountability approaches will be tested; at least 10 successful better fit approaches will be documented / Scalable models and better fit approaches promoted and shared with targeted stakeholders – 550 people will take part in learning events, 10 scalable approaches will be subject to advocacy initiatives and media coverage.
What is the context in which UK support is provided?
More than 100 million Nigerians (64% of Nigeria’s 158 million people[1]) live in poverty. Nigeria has a quarter of Africa’s extreme poor, 10% of the world’s children out of school, 10% of child and maternal deaths and 25% of global malarial cases. Nigeria’s human development indicators are worse than comparable lower middle-income countries[2]. In northern Nigeria, poverty rates are 77% and the current context is one of poor service delivery and little progress towards the Millennium Development Goals. Women and girls are further disadvantaged by gender politics and gender-biased interpretations of religion. / Although oil provides Nigeria with disposable income, poor governance is a major challenge and contributes to these poor development statistics. Thirty years of military rule and dependence on oil revenues has weakened the social contract in which government is accountable and responsive to citizens. Government underperformance is caused by political and bureaucratic patronage nourished by oil revenues, low expectations of government on the part of citizens and patterns of political allegiance and support determined by geography, ethnic identity, vested interests and personal connections. Together these have prevented the emergence of a broad-based political coalition of interests at a national level that could press for a change in government performance. In addition, control of local government resources by states through the Joint Account, and failure to make progress on LGA autonomy have stifled service deliver at the local level. / For government performance to improve the political culture must change. Government needs to be more accountable and responsive, and citizens more aware of the responsibilities of the state towards them, and more demanding of their rights. This programme will demonstrate that where communities and local government meet it is possible to reshape the relationship between the Nigerian state and its citizens whilst ensuring the delivery of services that matter to citizens are directly improved. The programme will also find new ways of delivering services and accountability in order to improve access, use of, and satisfaction with services.
[1] See UN Population Division’s World Population Prospects: 2010 revision and Nigerian Living Standard Survey (NLSS), NBS & World Bank, 2006.
[2] All figures are from the “Gender in Nigeria Report 2012”, British Council, May 2012.

## Section A: Detailed Output Scoring

Output 1: Communities better organised, engaged and demanding equitable service provision and development outcomes.
Output 1 score and performance description: A - Output met expectation / The spirit of the output is that communities are better organised. However the indicators all refer to the changes in CBOs. The expectation is that as the CBOs develop their capacity to influence and engage with local authorities, this will lead to development outcomes for communities. The CBOs are the primary unit of engagement and assessment for the project and in the first 8 months of implementation the CBOs have been mobilising communities and developing action plans. They report progress, although this has not been systematically assessed.
Progress against expected results: / 1.1. Progression of CBOs along a community organisation scale / Year 1 milestone 2014: 18 CBOs in 54 community groups (130,032 people (64,886 female/ 4114 girls)) / The year 1 milestone was exceeded. / M4D worked with 27 CBOS (18 community and 9 People With Disability (PWD) organisations) during this year. These CBOs have been identified by the project and are working at both Local Government Area (LGA- 9 community and 9 PWD) and ward level (9). The increase in totals is in part attributable to the inclusion of LGA level PWD groups and an earlier than anticipated start up in Kaduna state which was not planned for year 1. / The AR considers that to date, M4D’s figures have referred to the population in the areas communities supported by M4D operate in, rather than monitoring actual community engagement by the CBOs. This must be remedied in future years. / 1.2 Numbers of CBOs progressing along a community engagement scale / Year 1 milestone: 9 CBOs progress along CDA scale / Milestone was met / The project has administered the Community Dialogue Action Scale (CDAS) with 26 CBOs during the reporting period. They have supported CBOs to develop action plans for engagement, most of which focused on initial mobilisation and consultation meetings with the communities. Organisations report that they are engaging more in the meetings held, which are presented as proxy indicators of progress. / Given the project timescale and relatively short time since the first CDAS assessment and M4D capacity building inputs it was inappropriate to re-administer the CDAS. / The AR accepts that CBOs are undertaking community mobilisation for the project and making demands but does not attribute this to the M4D inputs alone. Some of the CBOs selected by M4D are already experienced in influencing strategies and making demands (e.g. Kader), whereas others are experienced in community mobilisation having worked with other DFID projects. KHADEV is already working in the community and worked in 16 LGA and in 30 communities before their contact with M4D. / The team acknowledges the progress made but is concerned about the quality of the data used for this indicator as it is not in line with the Logframe or the M&EL plan which indicates the sources as CDAS self-assessment, triangulated with focus groups and key informant interviews. / The team feels, given the limitations of the evidence that this milestone is at best just met and not over achieved as assessed by M4D. / 1.3 No. of demands made in a well-articulated way to service providers and policy makers by communities in M4D LGAs / Year 1 milestone: 10 demands / The milestone is not fully met. / Across the 3 states, 8 demands have been presented by CBOs (separately from those raised by organisations of PWD), based on needs of their communities. The quality of the demands is assessed with 4 criteria (Participatory, Evidenced based, SMART, Recorded and Retrievable). The evidence provided by the project assessed that 7/8 demands were average quality (meeting 2-3 of the criteria.) The progress on number of demands being well articulated on the basis of evidence available is 7. / Comments on milestones and progress: / Project implementation started in earnest in June 2013. The project is working with CBOs and has assessed their capacity to engage with the communities in all three states. Amongst the CBOs met during the AR there is a high level of enthusiasm for the progress they have made in working with communities on problem identification and channelling priorities to the local authorities. The project works with NGO partners to support the CBOs. / The wording of the output is that communities are better organised however the indicators all refer to the changes in CBOs. The project is working with CBOs on becoming more inclusive, in particular increasing female membership. / Given that the unit of engagement is CBOs not communities, it is questionable whether M4D can be seen to be directly benefitting the target populations as this is understood to be in the gift of CBOs not the project. In this instance, as the project does not have management control over the delivery of population numbers it would be more appropriate for these targets to be at outcome level. / The AR team is concerned that the population figures included in indicator 1.1 are based on a physical coverage (Ward and LGA populations) not actual coverage by the CBOs which given issues around exclusion (poverty, age, gender and disability) may not represent real numbers of communities being more organised. / The project does not currently report on the degree to which CBOs are able to develop: plans, demands mobilise communities etc. on their own. The project supports the CBOs and overtime it is anticipated that the level of help (support, mentoring etc.) will reduce. The CDAS assesses improvements in understanding and systems but does not fully address capability and confidence to use them without help which is important in terms of sustainability as well as the project management of inputs. Proxy indicators e.g. of CBOs taking up requests in other wards, might be seen as evidence of ownership and confidence with the new skills. Currently, neither the level of support given nor the CBO’s capacity to carry out its activity without project support, are reported on. / Two areas require further clarification and tracking by the project: / The degree to which CBOs are empowered i.e. able and confident to develop their demands with the project taking a reduced role over time, can be assessed by proxy indicators of CBOs using skills in other fora, or reports on reduced support provided by the Community Development Officers (CDOs) or support NGOs. / Indicator 1.3 needs more clarity on requirements for a well articulated demand. Does it need to cover all 4 criteria or is 3 out of 4 adequate? / A decision about indicator 1.3 is relatively straightforward, but more thinking is required by the project on how to assess empowerment and whether this can be incorporated into the CDAS. / Recommendations: / R1: The project should revisit population targets and ensure that its definition of beneficiaries: ‘counted as the number of people M4D’s partners (CBOs) directly reached at (a) Ward level and (b) LGA level can be verified objectively’. It is important that this terminology is understood and applied appropriately by partners and project staff. CBOs should be held accountable for the numbers and gender of the people who benefit from their work. / R2: Further clarification is required on the use of scales and criteria for making judgements on the indicators: training and guidance to all state teams is necessary to ensure consistent application across the programme. / R3: Monitoring change in the community is in the spirit of output 1. The logframe indicates the use of key informant interviews and it is important the project develops an approach through which self assessments can be triangulated. / Impact Weighting (15 %): / Revised since last Annual Review? No – this is the first Annual Review / Risk: Medium / Revised since last Annual Review? No – this is the first Annual Review

Output 2: Marginalised groups, particularly girls and PWD, better organised, engaged and demanding equitable service provision and development outcomes.
Output 2 score and performance description: A+ - Outputs moderately exceeded expectation / The purpose of this M4D output is to provide direct and focused support to marginalised groups to develop their capacity. At the outset the project works with PWD and Life Skills Clubs (LSC) separately. The expectation over time is that they will be able to use their increased skills and confidence to influence decisions which result in improved equitable outcomes either directly or through involvement in other community organisations. The project has initiated and contacted more groups than planned and capacity development has started, some demands have been made. / Progress against expected results: / Indicator 2.1 Establishment of Life Skills Clubs (LSCs) for Girls / Milestone Year 1: 27 clubs (675 girls) / Milestone exceeded / The project has established 52 LSCs (with 25 members per group) in the first year and this is significantly more than planned; in part attributable to the inclusion of Kaduna state in year 1. The clubs are facilitated by mentors who have been trained by the project. Each club has chosen a “peer champion” whose role is to speak out on behalf of the club in different fora. They have undertaken self-assessments. The LSC have done initial training. / Indicator 2.2 Number of marginalised group's CBOs that reach a capacity level, as determined by the community engagement scale, to enable them to articulate demands to service providers. / Milestone Year 1: 6 marginalised groups - 2 Adolescent Girls (AGs)/4 PWD / This milestone has been exceeded / The AR team met with several LSC and groups of PWD. The project has carried out initial capacity assessments. The girls generally rate themselves at a low level on all areas. The PWD, despite an existing structure recognise that they need to change their ways of working to make their demands to service providers. / As in 1.2 above, there has been no formal re-assessment of the capacity using the CDAS. However there are indications that the groups are willing to adopt project approaches. Since working with the project they have begun to develop the skills necessary to make their demands known to service providers; there is evidence of 10 demands being articulated. / For the PWD, the focus of their demands is on economic empowerment: accessing skills training etc. as the entry point. This is particularly appropriate as in some states there are new laws prohibiting begging which is a livelihood for many PWD. There is an established tradition that PWD make requests to local authorities, previously this is described as requests for welfare support. The project is supporting them to make requests on the basis of entitlement to services etc. the success of which will also depend on the extent to which rights of PWD are recognised in the state laws. / Girl’s peer champions are encouraged to bring the views of the group membership and work on articulating one voice for their demands. These loose groupings of peer champions to represent the clubs are called girls platforms. The project has recorded three girls’ platforms developing engagement with the Service Providers at ward level. The project narrative suggests platforms will focus efforts to LGAs but it has become clear that the existing clubs are better able to show representation at ward level. As the number of clubs expands, common interests can be presented to the LGA. / Indicator 2.3 No. of demands made in a well-articulated way to service providers and policy makers by marginalised group's CBOs in M4D LGAs. / Milestone Year 1: 3 Milestone exceeded. / This indicator is understood as showing the application of capacity developed as assessed in the indicator above (2.2) 14 demands made and assessed against the projects criteria as well-articulated. / In this category events took place on International PWD day in December and were presented across 7 LGAs. There was anecdotal evidence in the AR interviews that the Service Providers are planning to respond to the requests from PWD. Comments made by LGA staff indicate a shift from welfare and charity and a verbal willingness to address the issues raised. / The girls’ demands reinforce and reflect requests made by local CBOs based on community priorities. These demands are currently articulated in letters and mediated by the LSC mentors who attend community meetings as it is not seen as appropriate for the young girls to attend. / There are similar concerns here as in Output 1 that the project is not recording or monitoring the extent to which the marginalised groups are progressing towards feeling sufficiently empowered to work without project support. / Recommendations: / R1: The project needs to review logframe targets in particular for indicator 2.3 The target for 2018 is 18 demands which is almost met in the first year. / R2: Review the self assessment scales to incorporate empowerment into progressive levels of capacity. As above the use of proxy indicators such as AGs pursuing their own issues using different channels would be appropriate. As in output 1 it is important for the project to develop appropriate methods to triangulate self-assessment. (This is similar to the recommendation for output 1 indicators 1.3 above). / R3: The project should start to document the various pathways through which marginalised groups are able to access service providers and policy makers. This is critical for increasing understanding about pathways which lead to results. This can be applied in later stage of the project. / R4: This output should be included in the innovation trajectory, in particular the work with Girls Clubs and Platforms, as it is essential for the project to be able to showcase to policy makers how the inclusion of girls does not undermine social, cultural values and adds value to development. / R5 The project should monitor attrition in the LSC as the continued efforts of the AG , after the project has ceased engagement will have an influence on the inclusion targets and total number of AG benefitting from LSCs. / Impact Weighting (30 %): / Revised since last Annual Review? No - this is the first Annual Review / Risk: High / Revised since last Annual Review? No - this is the first Annual Review

Output 3: Improved capability of policy makers (PM) and service providers (SP) to design innovative and implement appropriate and responsive approaches to selected service delivery issues.
Output 3 score and performance description: A++ - Outputs substantially exceeded expectation / The project aims to work with supply side service provision and policy makers to help them work differently with their communities by responding, where feasible, to requests made by excluded groups and CBOs, and in terms of being more accountable. The project works with both traditional and formal leadership at state, LGA and ward level. The expectation is that with increased knowledge of needs, decisions will be taken to benefit the communities and marginalised. The two milestones set for year 1 have been overachieved.
Progress against expected results: / Indicator 3.1 Number of targeted individuals (from service provider and policy making bodies) whose awareness/knowledge has increased (on how to design, implement appropriate and responsive approaches to service delivery) in relation to the demands of communities and excluded groups. / Milestone Year 1: 120 / This milestone has been achieved. / The project has targeted 190 local governments (Service Providers - SPs - and Policy Makers - PMs). The anticipated changes are achieved through awareness raising meetings (understanding governance) and capacity-building with the local government leaders. The project has facilitated self assessments in target LGAs using a scale which assesses capacity using an adapted Capability, Accountability and Responsiveness framework (ARC). / The AR team met with several PMs and SPs at local government and noted an increased awareness of the needs of PWD and a willingness to try and address some of the issues. They were much less able to articulate issues related to girls’ inclusion. LGA knowledge is difficult to assess since the AR interviews showed that knowledge is held by individuals and their capacity to inform and inspire others in the LGA staff is also important, if the ideas are to have traction. The M4D ARC framework does not fully reflect the defined stages of accountability (effective accountability starts with setting standards and ends with sanctions if standards are not followed). The project is facilitating the development of performance standards, as these do not exist. / Indicator 3.2 Targeted service providers and policy makers who revise or develop action plans on standard based service provision or regulation with communities and Girls and PWDs. / Milestone Year 1: None / Although there is no milestone specified for year 1, the project has already worked with 4 LGAs on developing action plans for how to respond to community priorities which are within their authority. Provided the action plans are made public, they will be a useful tool to demand accountability. / Indicator 3.3 Number of service requests that are registered/logged by targeted service provider and policy makers. / Milestone Year 1: 10 requests / The milestone is exceeded / There are 15 requests which have been logged. This indicator tracks the “reception” of the requests made by CBOs, PWD and Girls Platform reported on under other outputs. The logging of a request allows it to be traced and followed-up. In most instances a letter (some supported with evidence) is logged by a clerk at local government offices. In most cases the letters had been delivered during January and as yet there were no formal responses. / Output 3 indicator milestones have been overachieved. However, the question remains whether the achieving the indicators will lead to achieving the output. The quality of change in PM/SP can be expected to progress over 5 years if this output is to be achieved. To understand what and why change is happening, it is necessary to track LGA (SP and PM) change individually not collectively. / Recommendations: / R1: The project should revise output 3 indicators to more closely reflect the output statement: e.g. LGA partners implementing not simply registering and planning. / Implementation is described in the project narrative as within the influence of the project, in particular when the project is willing to provide grants. If the project decides this is outside their influence then a rephrasing of the output 3 statement is recommended. / The project should likewise develop understanding about how best to attribute changes in LGAs which are subject to multiple influences, different projects and flows of funds / R2: The ARC assessments should be developed into a proper baseline as the current aggregation of data does not provide a foundation for assessing change across different LGAs. SAVI and SPARC who work with multiple actors may be able to help with how best to represent this. / R3: The project describes working with informal leaders but this is not explicitly mentioned in the indicators. The project needs to clarify what they expect from informal leaders and how they are expected to relate to both communities and formal authorities. / Impact Weighting (15 %): / Revised since last Annual Review? No – this is the first Annual Review / Risk: Medium / Revised since last Annual Review? No – this should be kept under review

Output 4: Innovative and ‘better-fit’ approaches to service delivery and accountability developed
Output 4 score and performance description: B – Outputs moderately did not meet expectation / This output was added into the project during inception and formal approval for a contract amendment was given by DFID in December 2013. The work done during year 1 so far has mainly been on developing a framework for generating and assessing “better fit approaches” (BFAs). There are 5 mechanisms in the process of being tested but none have completed the full testing cycle as yet and none of them have reached the stage of being fully documented.
Progress against expected results: / Indicator 4.1 No. of service delivery approaches /mechanisms tested / Milestone Year 1: 4 Milestone moderately not met / There are 4 service delivery approaches in the process of being tested. These relate to: / Public Private Partnerships on a participatory policy for provision of public-private toilets. / Basic education: Stimulation of demand for education by improving learning outcomes through the use of Jolly Phonics. This is being tested with State Universal Basic Education Board (SUBED). A 6 month pilot is being planned for 2014. / Mobile technologies for reporting on service delivery with data transferred to State level supervisors – early stage of software development; / Farm machinery leasing / These are all in a process of development: / Indicator 4.2 No. of accountability approaches / mechanisms tested / Milestone Year 1: 1 Milestone moderately not met / A process for integrated planning for LGA is being tested but not completed. This has the interest and support of Kaduna State government (Ministry of Local Government and Bureau for Public Sector Reform). / Indicator 4.3 No. of successful better-fit approaches / mechanisms with documented evidence base (accountability and service delivery methods). / Milestone Year 1: 2 Milestone moderately not met / There are two BFAs on accountability considered to be ready for documentation. The Sanitation and integrated planning BFAs mentioned under 4.1 and 4.2. The cycle is not complete. / Comments: This output started later than the others and is still in the early stages of development. The first round of testing has shown how the process and definitions need to be clarified. This is useful learning and adjustments can be easily made. / Overall the project needs to not only see BFA as the focus of project innovation, but once clarified the learning and testing approach can be used across the other project outputs. / Recommendations: The project should: / 1. Address the various definitional issues in relation to innovation and BFA output. This should be done as a team to ensure shared understanding. / When is a BFA considered to be fully tested? Does this include the costing of delivery? / Better distinction in relation to what a BFA will do: is it service delivery or accountability? The mobile reporting via tablets is arguably an accountability mechanism? / Clarity on how the different “gateways” or criteria should be applied. There appears to be good reason for initial assessment to focus on inclusion from the perspective of “who will benefit?” Particular reference to PWD, women and girls as well as poor people and a consideration of cost to user are important. / A further key entry question is whether the M4D support adds value. For example the Synthetic Phonics approach is being piloted in Akwa lbom State. It is therefore important to clarify at the outset what is the added value of a pilot in the M4D states? / Review and refine criteria for “tested”: / How should implementation costs be assessed in Better Fit products, as this is at least one of the factors which would be taken into account by policy makers / 2. Review the weighting of this output in relation to all the outputs it appears to be disproportionate at 30%. / Impact Weighting (30 %): / Revised since last Annual Review? No – this is the first Annual Review / This is the first Annual Review. It is suggested that the weighting for the current output is not appropriate for the current approach to Better Fit. In addition the current outcome is framed such that it can be achieved without any innovations being included. Thus the 30 % appears to be too high a weighting on the current framework. / Risk: Low/Medium / There is a disparity between the logframe and the projects own risk assessment. There is a good reason to consider this output medium rather than low risk. / Revised since last Annual Review? No – this is the first Annual Review

Output 5: Scalable models and approaches promoted and shared
Output 5 score and performance description: B – Outputs moderately did not meet expectation / In a project that is about developing and testing new approaches to improving accountability through behaviour change, the likelihood of being in a position to promote a scalable model by the end of Year 1 is understood to be low. The project is promoting awareness of the models which it is used but to a large extent this is more appropriately described as raising awareness of the issue and how the project is responding. There has been insufficient time to fully develop scalable models and there is a need to define more clearly what the terminology means.
Progress against expected results: / Scalable models and better fit approaches promoted and shared to target stakeholders / Indicator 5.1 Number of people from within and outside the M4D LGAs that take part in learning events / Milestone Year 1- 100 participants Milestone met / The project has both hosted and jointly collaborated in “learning events or skill share workshops” in all three states in 2014. There have been at least 130 participants at these events, mainly from relevant sector LGA level staff. / Indicator 5.2 Number of scalable and spreadable approaches that are associated with advocacy initiatives to targeted stakeholders (for example state government, federal government, and other DFID programmes). / Milestone Year 1: 3 advocacy initiatives related to scalable approaches. / Moderately not met. / The AR understands the advocacy which has taken place so far to be more about raising awareness than presentation of a scalable model. This is not to suggest that such awareness raising is not an important stage in gathering support and buy-in from decision makers. However, in relation to a scalable model, it is implicit that such a model should be proven to be likely to make a difference. / Indicator 5.3 Quantity and quality of media coverage on M4D approaches / Milestone Year 1: 8 media hits which is on target / The media coverage of approaches and models has appeared in different media, (e.g. radio and print). Evidence includes coverage of the PWD presenting their demands to LGAs on International day of PWD in December and other stories about the Life Skills Clubs. While these are both a starting point, the review team believes that the focus of this output is to disseminate successful tried and tested models and approaches. / While the coverage of PWD serves to show other PWD and LGAs that there is a new way of working being tried in their communities, as yet this cannot be seen as a scalable model. The same applies to the exposure and media coverage of LSCs which are as yet not fully tested by the project. / Although milestones were set for YR 1 of the programme which shows programme willingness to share and disseminate their approaches, the review team would argue that more time is required before the project has a fully developed product. It is difficult for them to show “what difference” these approaches make after only 8 months of implementation. / Recommendations: / R1: The project needs to distinguish more clearly between using the media to raise awareness about on-going project initiatives and the ambition of this output which is the promotion of scalable models. / R2: Further discussions and clarity on what constitutes a scalable model and innovative approaches are required. / Impact Weighting (%): 10% / Revised since last Annual Review? No - this is the first Annual Review / Risk: Low / Revised since last Annual Review? No - this is the first Annual Review

## Section B: Results and Value for Money.
1. Progress and results
1.1 Has the logframe been updated since last review? N/A this is the first Annual Review. / The logframe was changed to include output 4 on innovation and “better-fit” approaches. This was approved by DFID in 2013. The logframe requires adjustment in year 2. / 1.2 Overall Output Score and Description: A / The programme is meeting expectations overall. This is based on a mix of over-achievement, on target and, in some cases, moderately not meeting expectations. / 1.3 Direct feedback from beneficiaries / The Annual Review mission carried out visits to three states (Jigawa, Kaduna, Kano). The team met with LGA staff and councillors, CBOs, Life skills clubs and peer champions, PWD in all 6 of the 9 LGAs in 3 states. / In all cases the team found people to be enthusiastic about the programme. In the case of the Girls Clubs and PWD there was a high level of enthusiasm and good understanding of what they are doing with the project. The CBOs have undertaken community mobilisation and have a list of issues which they can relay to local government. The understanding amongst local government officials is less strong and there is an implicit assumption that the project will provide some “assistance” to delivering better services. The idea that the project is testing approaches which will hopefully be expanded by other actors is not fully understood. There is clearly good will amongst the project beneficiaries at this early stage. / These are, however, early days in a project that has only been on the ground for 8 months and it is anticipated that the project’s messages will be clearer to all once there are some successful cases to show case and learn from.
1.4 Summary of overall progress / This AR took place in the 3rd quarter of the first year of implementation. The output milestones based on quantity of engagement (outputs 1-3) were largely achieved and in some cases overachieved. It is considered to be early days in a 6 year programme to expect achievements in outputs 4 and 5 as these are dependent on learning outcomes from better fit ideas and innovations in programme approaches, which are essentially at an embryonic stage. / The programme has adopted a pro-active approach to generating support for innovation take up and has done well to communicate new ideas to potential decision makers in state and LGA governments. The second year needs to increase a focus on the quality of the achievements including developing clearer definitions and understanding and application of what constitutes quality in the indicators and how these relate to the actual outputs.
1.5 Key challenges / Changing social – cultural behaviours: This programme seeks innovative solutions to old problems and, as such, faces a range of challenges. Changing social attitudes and practice underpin many of the changes expected from the intervention, in particular in relation to excluded or marginalised groups and attitudes to them. Such behaviour change relies on repeated cycles to begin to be embedded as a change. There are good signs of changes in understanding of particular needs of PWD in some LGAs, but attitudes to women and girls in LGA and CBOs will take some time. Likewise the young girls in the LSC are observed to exercise self-exclusion in relation to community meetings and public speaking. The programme describes its approach as working with the grain to show how change can happen and has responded to requests from Jigawa state leadership on language being used. This is a pragmatic response. Overall, it is essential that a line of sight to the principles and concepts, such as equity and empowerment, included in the programme strategies are used as a benchmark when judging success. / Managing expectation in LGA and communities. Donor and government programmes tend to include significant investment in infrastructure as well as training etc. The programme communicated with local and state actors about the nature of M4D as a governance programme where the expectation is that spread and scale will be achieved through programme influence rather than direct implementation. At this early stage the beneficiaries continue to request the programme does more: more groups; more LGAs; more CBOs etc. While this is not surprising, the programme needs to monitor and respond to potential attrition during the life of the programme as it progresses on its implementation strategy. / In response to the challenges of behaviour change and risk of attrition, it is important for the programme to ensure foundations are strong before moving onto a new area. This may take slightly longer than anticipated but is essential for continuity and model building. Critical to success here and a current challenge in the programme is the need to document the processes and adaptation to methods and developing team capacity for the same. / Conflict and political change: The operating environment is likely to move from status quo to state of change due to the forthcoming elections and political manoeuvring that has already started. The sharing of intelligence and observations with other projects is integral to programme PEA.
1.6 Annual Outcome Assessment / During inception the outcome statement was simplified to: / Policy Makers and Service Providers are more responsive and accountable to citizens’ entitlements and better articulated demands, especially those of marginalised groups. / There are three indicators to measure progress here: / Improved influence of CBOs / Improved Responsiveness and Accountability of Policy Makers and Service Providers / Numbers of citizens demands incorporated into planning and service delivery / Comments on outcome statement: / In its current expression the outcome can be achieved without uptake of the innovations tested in Output 4 and shared in Output 5. As has been stated above the current focus of BFA and innovation is focused on introducing new ideas but it should endeavour to fully embrace the experimental nature of activities in outputs 1-3. As such 1-3 should be subjected to the same level of interrogation as innovative ideas in output 4. The project needs to continue taking into account the LSC, working with CBOs and LGA as innovative in the context. . / The idea that citizens may demand improved accountability, in addition to services and plans is missing in indicator 3. / The sources of data to measure indicators 1 and 2 are the same as for the outputs. It will be essential for the triangulation of self assessment to be done using inputs from a wider range of citizens that includes excluded groups: women; elderly; and poor in addition to PWD and AG. / Progress: / As this is the first year of implementation, it is too early to say with confidence that the outcome will be achieved. Achievements are reported against indicator 3. 1 LGA and 2 wards have committed to responding to demands from 8 PWD groups on International Disability day in December 2013. This includes: skill training and recruitment quotas for PWD. / The delay in finalising baselines for indicators 1 & 2 means that it is not possible to assess change. More work is required to convert data from self assessment of LGAs capacity (using the ARC tool) into a real baseline. It is currently presented as aggregated averages which disguises rather than illuminates changes. / An initial perception survey required for the first indicator is not complete due to delays in finalising the Independent Evaluation Manager scope of work. CBOs are already claiming an increased influence as a consequence of project interventions and approaches. It is for M4D and DFID to resolve the Independent Evaluation Manager (IEM) contract as soon as possible. / It is recommended that the programme revisits the indicators of success for the outcome and treats the development of baselines as urgent. / TOC assumptions : / A key assumption for the programme was that the Conditional Grant Scheme for MDGs and other sources of government funding would constitute a lever for the programme. At the outset the programme expected to be able to hook, planning processes and increased accountability onto a multi-annual CGS process. In practice CGS has become a one-off grant for MDG related infrastructures and, as such, does not provide an incentive to reform planning accountability and transparency. The project is still seeking a way to collaborate with CGS but this is less of a lever than hoped for. / As the programme was also redefined to take on issues broader than the MDGs, it is important for them to identify other entry points to support and increase performance at LGA level. The integrated planning BFA may be useful in this case but requires testing. / The assumption that social attitudes to girls, women and people with disabilities do not deteriorate is being monitored. In the states of operation there are positive signs at state and LGA level of a change of attitude to PWD. New legislation in relation to recognition of PWD is passing through the State House of Assembly in Jigawa. The conservative attitude to women and girls (particularly in Jigawa State) remains a challenge for a programme which is focusing on inclusion and equity. The programme needs to closely monitor inclusion in practice in Jigawa as a proxy for attitudes to women and girls and in all project deliverables. / The operating environment in northern Nigeria is understood as stable – instability. Monitoring of political and security is appropriate and shared with other DFID programmes so far changes in political and security climates have not seriously affected programme implementation, though some early LGA work was delayed. The programmes regular PEA updates indicate that the forthcoming election (2015) and actions by insurgents in north eastern states (and criminality reported as such) require a high level of alertness and a readiness to re- strategise if necessary in the programme. There is evidence that the team is already considering opportunities during election down time when access to communities may be reduced.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The approved DFID budget for the GRM component of M4D is now £17.5 million of which £2.7 million (15%) had been spent by the end of December 2013 (Q3 report). / Quarterly expenditure during the first three quarters of implementation has been an average of 26% below GRM’s latest forecast. / Forecast Actual Variance % / Q1 2013/4 702,943 463,339 -266,605 -38% / Q2 2013/4 461,706 408,442 -53,264 -12% / Q3 2013/4 704,494 540,892 -163,602 -23% / Total Q1-Q3 1,869,143 1,412,673 -483,471 -26% / GRM believes that the programme is now gaining momentum, and that its annual expenditure at the end of Q4 will be close to its October 2013 forecast of £2.26m, revised to £2.24m in January 2014. It anticipates that its quarterly expenditure will rise £0.86m in Q4, and an average of £0.95m per quarter in 2014/2015. / Delays in expenditure during the first year are common. M4D attributes some of this to a slightly extended inception period and delays in agreeing a contract revision. / If GRM continues to underspend, this would indicate that budget revision is required. However, this must be set in the context that implementation is broadly on track. / 2.2 Key cost drivers / The revised budget shows that 66% of the budget relates to fees, travel and living expenses of personnel. GRM correctly identifies that the principal cost driver is therefore human resource. This includes human resources used for delivering outputs, for development and for administration. GRM started to monitor the ratio of national to international TA in Q3, noting that 95% of TA was national in the quarter. / Other major cost components include programme activities (21% of budget), of which grants and capacity development are the largest parts; and the Independent Evaluation Manager (4% of budget). / All but Crown Agents expenditure on capital items (2% of budget), is contracted by DFID to GRM International. GRM’s subcontractors include consortium members and the Independent Evaluation Manager. / Since inception M4D has spent a total of £1.83 million on technical assistance of which £1.23 million (67.2%) has been on long-term technical assistance and £0.60 million (32.8%) on short-term technical assistance. Technical assistance is therefore a major cost driver, representing 68.4% of the total expenditure to date. Typically as in any programme start up there has been the need to use international TA for this stage of the programme, but M4D will ensure economy for the rest of the programme by limiting the use of short term international TA wherever it is possible to do so without undermining the value of the inputs. As most international TA is paired with a local counter-part, the programme over time will reduce the need to use international TA as capacity will be built up and transferred to local teams. / Since inception total security costs have amounted to £34,911. M4D has been able to share security resources with six other GRM managed programmes, (SAVI, GEMS1, PropCom, V4C, GRM, Futures Group). Some specific examples of cost sharing include; GRM Nigeria Security, Manager Defensive and Security Awareness Course run by David Bertie and in-country HEAT training for National Team Leaders. The costs that were shared include, international flights, in country accommodation and transport, per diems and daily fees / 2.3 Is the project on-track against original timescale: / Yes / Implementation is on track. Progress in the three outputs that relate to work at community level have moderately exceeded expectations. It is not surprising that the work (in output 4 and 5) that requires the project to develop and test models which are then shared is slightly behind on implementation milestones. Overall the pace of implementation in the last 6 months is impressive particularly in the light of the challenges of recruiting staff reported on each quarter.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / M4D’s Theory of Change is that by, working in a collaborative and solution-seeking way, with both the supply and demand side of governance, there are gains for both citizens and government. The project is to a great extent innovatory in the context and the programme is a testing ground for this theory in Nigeria. For the programme it is important to find the best way to ensure that such collaboration includes the marginalised (PWD and adolescent girls) and it will deliver improved and more inclusive services. The communication and sharing of proven models of intervention and better fit approaches to service delivery will be developed during the project. The spread of these new ways of doing things is understood to be done by other actors, the government, private sector and civil society: the projects role is to inform, explain and showcase successful models. The TOC does not show the inputs required for all these changes and the programme focus should be on increasing knowledge about what combination of inputs and context catalyse positive (and negative) change. / Overall, given the experiential and experimental foundations of this project, it is essential to set up a rigorous system of documentation that tracks inputs and changes. Documentation will provide a paper trace on adaptations and show adherence to M4Ds stated principles and values. This is the foundation of a robust evidence base. It is the basis for reviewing and learning from programme interventions and developing knowledge about what works, why and how. / The projects Monitoring Evaluation Learning (MEL) and Knowledge Management Strategies include a focus on learning and sharing, and team meetings include reflective practice. The MEL strategy refers to case study based evaluation but this is not being used nor is it mentioned as a source in the logframe. As yet the programme has not rooted this in the day to day work of the implementation teams; although the process for developing BFA s and the Girls strategy are both premised on the need to document processes. This must be developed in year 2. / 3.2 Where an evaluation is planned what progress has been made? / As this review took place in the first year of implementation there are no immediate plans for evaluation. The contract with an independent evaluation monitoring (IEM) agency is under discussion by the evaluation committee (DFID and M4D). The slow resolution of this sub-contract has meant that M4D has not completed the baselines against which the outcome and impact will be assessed in future. As the programme enters its second year baselines should be treated with urgency.

4. Risk
4.1 Output Risk Rating: Medium (to High) / The current output ratings in the logframe require adjusting as the programme did not effectively assess the rating on when a new Output 4 was included. As both output 4 and 5 are to a large extent the laboratory and dissemination of the project, it is felt that at output 4 should be reclassified as medium rather than low risk. Output 5 is classified as low risk and should be also be re-visited. Its success is dependent on the programme developing models and approaches that can be scaled or spread by others and might be better considered medium rather than low risk. / The M4D risk assessment template (below) rates both output 4 and 5 as being medium risk and this supports the suggestion above. / 4.2 Assessment of the risk level / M4D developed an assessment of risks during inception and these are reviewed in reports. These are generally well done, identifying both exogenous and endogenous risks. M4Ds risk assessment is included here as a framework for comments which mainly focus on mitigation strategies. / The AR team considers that in addition to the risks identified by M4D the pace of implementation and spread represents a risk to learning before spread and scale. The programme needs to show evidence of success and learning before spreading. This is particularly important on the approaches to inclusion: the project needs to be able to show that their inputs make a difference before scaling out. This is included in the final row of the risk table. / RISK Description LIKELIHOOD IMPACT MITIGATION AR comments / Exogenous / Political High 3 / low 1 High 3 / low 1 / Insecurity Proximity to conflict-affected states; / Violent crime (e.g. robbery); / Politically-motivated crime; Medium / 2 Medium-High / 2.5 Security management (GRM) & focal points; / Shared information with NSRP; / HEAT training; Agree / Elections Distraction from M4D programme aims; / Change of key government personnel according to shifting political landscape; / Shrinking space for controversial issues High / 3 Medium-High / 2.5 M4D maintain focus on key issues; / Maintain political neutrality; / Adapt discussion of controversial issues without compromise; / Maximise transparency about the programme. Develop and communicate simple key / Programme / messages / Endogenous / Girls Gender relations are central to the status quo; / Girls are considered assets for their families and communities; / Male family members fear girls and women becoming outspoken / Attrition: once intense support to LSC is complete the membership decreases. High / 3 High / 3 Include communities in development of girls’ clubs; / Adapt implementation to minimise apparent threat to status quo; / Ensure clubs are run in culturally-appropriate manner Mitigation strategies need to also address how CBOs and PWD are including women in their membership and target group / Work with mentors on skills to maintain groups and developing links to other “projects” / Innovation M4D emphasises innovation and nurturing Better-Fit Approaches. These present risks Medium / 2 Medium / 2 We have developed a BFA process to guide innovation development and also are keeping the value of each BFA low so as to mitigate risk The risk is not fully defined. Mitigation requires that / Resources required for “product” are assessed. / Brand/ / identity Prominent public profile can raise expectations; / Identity can be manipulated; / Communities or policy-makers can suspect that M4D threatens status-quo power relations; Medium – High / 2.5 Medium – High / 2.5 Maximise transparency through judicious use of different media; / Attract dialogue through use of social media; / Conduct learning events; / Coherence across programme team about M4D approach and objectives Comment: Medium to High / Development of simple project messages will also help here. / Suggest this is a medium risk / Scale and / spread Policy-makers expect M4D to move quickly to more LGAs – are reluctant to engage with a ‘small scale’ programme High / 3 Medium / 2.5 M4D personnel stress ‘pilot’ nature of programme and responsibility of communities and policy makers/ service providers to pick up good practice; / Consider extending reach in future. Be clear about spread and approach in communication messages. / Pace The coverage rate / (numbers and geography) works against learning from results of new approaches and innovations. Med-High / 2.5 High / 3 Improve process monitoring and documentation to ensure evidence based learning. / Focus team on qualitative change as well as quantity and take a flexible approach to pace
Risk of funds not being used as intended / The project manages its own funds according to DFID’s accounting and auditing standards. / The project has not provided grants directly to beneficiary groups (PWD, LSCs, CBOs). The implementation of grants will start during 2014 and at this stage the AR perceives a small risk that funds, in particular to some CBOs, may not be used as intended particularly when they are managing multiple projects/funding streams. There is a risk that funds are used for activities which already have funds from other sources. Although the size of funds being distributed is relatively small this is not seen to reduce risks per se. / Finalising grant procedures is an opportunity to include systems to reduce the risk of “double-dipping”. / 4.4 Climate and Environment Risk / No significant risks or impact on the environment resulting from the project activities are identified. / The AR team recognises the project desire to use optimal criteria for selecting innovation and BFA projects, however, it is suggested that when defining scale-ability it will be important to review environmental and climate risks.

5. Value for Money
5.1 Performance on VfM measures / Overall, M4D remains cost effective. However, it has yet to complete and implement a systematic framework of VFM measures linking financial reporting to the performance framework provided by the logframe. / Based on the economic appraisal reported in the Business Case, M4D still represents good value for money. / The Business Case proposed that the programme would deliver a 20.6% return within 4 years of its completion. Assuming a budget of £17.0m, this values the benefit at approximately £20.5m. The benefit is to be achieved by small economic gains from improvements in the use of local government services to the target population of 1.8 million. These in turn depend on successful interventions by M4D within communities of 650,000 people, and particularly with AG and PWD. / Changes in either the impact or the input cost of the programme affect cost effectiveness. If the expected benefit drops below the expected cost, the programme becomes poor value for money. For example, if the total number of people using, accessing or satisfied with services were to be 15% lower than planned, that might suggest a 15% drop in the benefit of the programme’s impact from £20.5 m to around £17.4 m, four years after completion – although this would need to be triangulated with other data. / Measuring changes in impact / A difficulty with the programme’s impact indicators is that they are only assessed on programme completion in 2018. Effective trigger points are needed sooner to prevent spending money on a programme that offers poor VFM. M4D’s VFM Strategy does not propose any of these as part of the VFM framework. The absence of clear baselines and intermediate measures of impact is a concern. The difficulty of estimating impact during the programme should not prevent M4D or reviewers from asking simple questions about how expected impact may have changed since the business case was approved. Both M4D and its reviewers need to look critically for material changes in the programme’s expected impact, and consider how these will affect its value. This is properly a matter for annual reviews. / Measuring changes in cost / Changes in cost are more easily measured than changes in benefit. In January 2014, the contract value was increased by £0.7m to 17.7 million (including Crown Agents). Unless the valuation of the benefit has been revised upward too, this will reduce the expected return on investment from 20.6% to approximately 16%[3]. However, if the value of benefit has been revised upwards, this would compensate for the additional cost. / Cost effectiveness trigger points / Further increases in cost or any reductions in expected benefits would reduce the value for money significantly. The economic appraisal comprises monetary and non-monetary benefits. No additional benefits have been indicated at this stage of the programme that would fall outside those envisaged in the economic appraisal. / Any indication that the economic benefit will be lower than expected should be a trigger for concern. If, as in the example above, it becomes likely that total programme impact will be 15% lower than originally planned, the programme may well be worth only £17.4 million and would therefore no longer be good value for money at the current cost of £17.7m. / This emphasises the importance of M4D and reviewers looking for changes in the value of expected benefits as part of each annual review. This can be done without resort to complex economic or financial calculations. Changes in the expected number or practical value of benefits to Adolescent Girls and other disadvantaged populations may have a high impact on the value of the programme. / M4D should use VFM measures, alongside its growing experience on the ground, to improve its cost effectiveness and impact. Grant mechanisms, BFAs and perhaps other mechanisms provide opportunities for innovation. / The framework for financial reporting and VFM still requires development, as follows. / Financial reporting / M4D should urgently implement reliable reporting of budgets, revised forecasts and expenditure by output, as well as input cost. These should be reflected in the Logframe and in quarterly reports. The multi-year programme budget should also be available in both summary and detail. / All budgets used for VFM purposes should reflect the full cost to DFID of the M4D programme. / VFM framework / Cost Effectiveness / M4D should address the lack of baselines for impact indicators and one outcome indicator urgently. Because Impact will only be assessed on programme completion, M4D needs to devise earlier means of anticipating changes in impact, as these are essential triggers for concern that value for money may be reducing. Changes in the numbers of beneficiaries, particularly among Girls and PWDs, or changes in the value of benefits to them are likely to have a high impact on value for money. / Effectiveness / M4D should confirm its VFM indicators. Provided that the three outcome measures in the logframe are appropriate for measuring programme outcome, they are equally suitable for measuring VFM. It may therefore be simplest and best to use the outcome indicators themselves as the best indicators of effectiveness. / Efficiency / M4D should urgently ensure that it has at least one indicator for each output, and monitors this against the cost the output quarterly. / M4D should urgently provide a clear definition of its administration costs and how it plans to control and preferably reduce cost over the life of the programme. / M4D should propose additional reporting for individual projects undertaken under BFA, and for grants. / Economy / M4D is developing an appropriate range of economy processes and indicators. / The quarterly report of input costs against budget should be the basis of VFM reporting on economy. / Presentation of VFM / As far as possible, VFM indicators should be integrated within the performance framework provided by the logframe. For instance, output costs and costs per output could be presented alongside outcome and output indicators. / The quarterly report should use a standard layout for VFM indicators, rather than extended narrative on occasional items. / Implementation of VFM framework / M4D should urgently design and implement a plan that prioritises and installs the urgent and essential components of its financial reporting and VFM framework. For Q4, it should focus on reporting by output, and establishing standard tabular reporting for efficiency and economy indicators. / 5.2 Commercial Improvement and Value for Money / No VFM trends have been identified at this early stage of implementation. Baselines and clear reporting cycles for its VFM indicators are required before these can be provided. / There is no strong evidence for commercial improvement at this stage. M4D should provide a clear definition of the baseline for its administrative cost as originally funded, and show progress against this. / 5.3 Role of project partners: / M4D has a range of partners directly involved in the programme. / The Lead partner, GRM has worked effectively with ITAD in the design of VFM indicators. This work needs to be concluded and implemented. / The Independent Evaluation Manager has not yet taken a clear role in relation to Value for Money, even though it is an integral component of any evaluation. The integration of VFM into the evaluation framework needs to be clarified. / 5.4 Does the project still represent Value for Money : Yes / Based on economic appraisal reported in the Business Case, M4D still represents good value for money. The increase in the total budget from £17.0m to £17.7m (including Crown Agents) reduces the rate of return on UK taxpayers’ investment from 20.6% to approximately 16%. / 5.5 If not, what action will you take? / n/a
[3] The revised return on investment is calculated as follows: (original cost)/(revised cost) X (100% + Return%) - 100%. Therefore 17.0m / 17.7m X 120.6% - 100% ≈ 15.8% (rounded to 16%) Alternatively: a return of 20.6% on £17m values the benefit at £20.5m. if the programme cost is revised to £17.7m, the new return is 20.5/17.7 -100% = 15.8% (rounded to 16%)

6. Conditionality
6.1 Update on specific conditions / There are no specific conditions attached to this programme.

7. Conclusions and actions
Despite a slightly prolonged inception period and an annual review in the third quarter, the first year of implementation has overall met its expectations. The AR finds that the project has worked intensely on establishing relationships with key actors at state and beneficiaries (LGA, CBOs, LSCs and PWD) on the ground. Implementation is largely on track. The project has focused on mobilisation, capacity needs assessments and some initial training. The groups (PWD, Life Skills Clubs, LGA level and Ward level CBOS) have responded with enthusiasm and show a willingness to engage with each other and the project. Progress on the three output indicators that relate to work at community level have moderately exceeded expectations. Given that programme has only been implementing for 8 months it is not surprising that the progress which depends on the project developing, testing and evaluating models which can be shared (outputs 4 and 5) is slightly behind in attaining their milestones. Overall, the pace of implementation in the last 8months is impressive, particularly in the light of the challenges of a high staff turnover reported on each quarter. Given the innovative and experiential nature of the entire programme, it is vital for the project to allow time for reflective practice on its approaches to inclusion of disadvantaged groups (PWD and adolescent girls). / The Review finds that the pace of implementation so far, is not fully matched by the need to prove that the approaches work. The Review recommends more investment in developing an evidence base. This means greater attention to learning and understanding what works and what doesn’t. This requires better evidence gathering and analysis; effective documentation of lessons learned. Reflective practice and documentation will provides a foundation for getting things right. This will, in turn, ensure programme models are on track to deliver results which can be scaled-up and spread. / ACTIONS / 1. Review and up-date the logframe: / There are several areas in which the logframe is not up to date with the actual programme. To maintain integrity with the management of implementation processes, it is recommended that the programme review the logframe in several ways: / Review all definitions in the outputs (well-articulated, tested etc.) and develop a check-list to support staff; / Revisit the output milestones and targets for subsequent years, given the high level of achievement in year 1. Ensure that milestones are still appropriate; / Review the outcome indicators; currently the contribution of output 4 to the outcome is minimal if not invisible. / Revisit the impact weightings and risk ratings. For example the impact weighting of 30% for output 4 is not fully aligned with its invisibility in the programme outcome. / Supporting VfM assessment by allocating budgets to outputs; / 2. Fully operationalise the Monitoring, Evaluation and Learning and Knowledge Management frameworks / The M4D project is a programme which aims to improve both development outcomes as well as contributing evidence of how collaborative working can lead to changes in service delivery and accountability relationships between marginalised citizens and the state at local government/community level. It is important for the programme not to focus too heavily on BFAs at the risk of missing the big picture of innovatory approaches. The programme must look at how it is developing an evidence base which shows when, why and how this collaboration succeeds or fails. In order to do this, it is recommended that the programme fully operationalises its MEL and Knowledge Management strategies and frameworks in a way that is inclusive, understood and functional for all levels of staff. Currently there is a risk that it becomes too centralised (and exclusive). This should prioritise: / Completing baselines for outcome level and the translation of the capacity assessments into meaningful baselines. / Develop a way of tracking the degree to which beneficiaries take responsibility and are capable of working on their own to achieve their goals. / Review the responsibilities in the M&EL framework, as currently the role of frontline staff is not specified and they are the important contact point with beneficiaries. Mainstream and produce guidance on adaptive and reflective learning approach and case study based evaluation for all staff. If necessary train frontline staff in basic documentation skills. / Creating an evidence base: by identifying key questions in the TOC that the programme wants to generate knowledge on for example: approaches to empowering marginalised citizens or effective collaboration between civil society and state for improved accountability. Defining the questions is seen as the starting point for implementing a process of increasing knowledge and ultimately knowledge management. / Staff training should include the qualitative base to the work and also concepts of attribution and contribution. / 3 Fully operationalise the Value for Money Framework / VfM is an integral part of the M&E framework. Although partners have given considerable thought to Value for Money, M4D has yet to complete and implement a systematic framework of VfM measures, linking financial reporting to the performance framework provided by the logframe. / Financial reporting: M4D should urgently implement reliable reporting of budgets, revised forecasts and expenditure by output, as well as input cost. These should be shown in the logframe and in quarterly reports. The multi-year programme budget should also be available in both summary and detail. / Cost Effectiveness: M4D should address the lack of baselines for impacts and outcomes urgently. Since Impact and Outcome will only be assessed on programme completion, M4D needs to devise earlier means of anticipating changes in impact, as these are essential triggers for concern that VfM may be reducing. / Effectiveness: M4D should confirm its VfM indicators. It should reconsider whether attaching costs to these indicators adds to their value, or whether the outcome indicators are sufficient indicators of effectiveness as they stand. / Efficiency: M4D should urgently ensure that it has at least one indicator for each output, and monitors this against the cost the output quarterly.M4D should urgently provide a clear definition of its administration costs and how it plans to control and preferably reduce cost over the life of the programme.M4D should propose additional reporting for individual projects undertaken under BFA, and for grants. / Presentation of VfM: as far as possible, VfM indicators should be integrated within the performance framework provided by the logframe. / Implementation: M4D should urgently design and implement a plan that prioritises and installs the urgent and essential components of its financial reporting and VfM framework. For Q4, it should focus on reporting by output, and establishing standard tabular reporting for efficiency and economy indicators. / The role of the Independent Evaluation Manager in relation to VfM should be clarified. / 4. Communication and Advocacy messages: / The project is concerned that their approach is not well understood by different stakeholders and that this may undermine their work as well as absorb time in re-explaining, remobilising and in some case distorting the programme. Communication and media strategies are well formed. A next step is for the programme to: / Identify potential advocacy messages found in the purpose, principles and values at the heart of the programme e.g. girls’ empowerment is critical to improving community development outcomes. Raw messages are not for immediate public consumption but are the basis for more strategic and focused for effective engagement in public arenas, advocacy and public relations work. / Given the number of other projects working with adolescent girls, it will be important to clarify M4D’s messages in collaboration with other programmes such as Girl Hub, V4C etc.

8. Review Process
The review took place from 29th Jan - 13th Feb 2014. The team comprised 3 external (to DFID) consultants and 1 DFID Social Development staff member. An initial approach paper was provided to DFID and M4D prior to arrival in country and plans were made on the basis of feedback provided. Given the security issues in the three M4D States the team met with M4D staff in Abuja for a presentation from the project; before proceeding to field visits in all 3 states. M4D provided an extensive range of documents via a drop-box during the first week of the review. Documents and up-dated evidence were provided throughout the mission. The field work visited LGAs and wards in all three states in the week 3 – 7 February. The team also met with a selection of state level officials in each State and attended a workshop promoted by the Ministry of Women Affairs and M4D in Kano. The VfM specialist on the team joined the field visit for 2 days, including 1 day in the M4D head office in Kano working with Finance and Management. / A validation and debrief meeting was held in Abuja with the M4D programme management team. Initial findings and recommendations were presented and discussed. DFID staff participated in this meeting as due to a VIP visit to DFID Nigeria it was not possible for the team to make a presentation in the DFID office.