Annual Review – post April 2018

Title: Preventing Violence against Women and Girls Scaling up Country Support
Programme Value £ (full life): 1,962,311.15		Review Date: 20 February 2019
Programme Code: 203245	Start Date: April 2013	End Date: July 2020

Summary of Programme Performance
Year	2014	2015	2016	2017	2018	2019
Programme Score	B	A	A	A	A	A+
Risk Rating	Minor	Minor	Moderate	Minor	Minor	Minor

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5300971.odt
DevTracker Link to Log frame:

A. Summary and Overview

Description of programme

The Preventing Violence against Women and Girls Scaling Up Country Support programme was approved in 2012 to support scale up of the quality and quantity of UK programming to prevent violence against women and girls (VAWG). The programme aims to achieve this through a combination of approaches:
- The VAWG Country Support Helpdesk (the Helpdesk), managed by Social Development Direct (SDD), provides demand-led services for teams working on this issue across HMG. The SDD team of experts respond to short-term queries or undertake more detailed country assignments. They also provide a series of Guidance Notes and Evidence Digests.
- A Community of Practice (CoP) to support VAWG programming and dissemination of best practice, managed by DFID’s Violence against Women and Girls policy team (VAWG team)
- A monitoring and evaluation resource, delivered by Oxford Policy Management, to capture the impact and lessons learned from VAWG programming and policy work within DFID – including beneficiaries at country level. This is now complete.
- Since March 2018 the programme has been extended to also provide specific safeguarding policy support.

The programme is part of a broader effort to scale up DFID’s work on ending VAWG and was designed to complement the Prevention of Violence against Women and Girls: Research and Innovation Fund (What Works), a programme that seeks to establish which approaches are most effective in preventing VAWG. Collectively, the programmes aim to provide the evidence and expertise to support VAWG programmes to be more effective and more cost-effective, and ultimately to expand their coverage to have greater impact on reducing VAWG.

In the year under review the programme timeframe has been extended and the VAWG Helpdesk will now continue operating until July 2020. This extension was agreed in recognition of the vital support that the Helpdesk continues to provide to HMG staff in designing, implementing and monitoring effective VAWG prevention and response programmes.

Summary supporting narrative for the overall score in this review

The overall score for this review is A+, outputs exceeding expectations. In the past year the Helpdesk has responded to a higher than anticipated number of queries, and despite this it has exceeded expectations in terms of satisfaction rates and continues to meet expected standards for response times.

An additional component was added to the programme in March 2018 to provide support to DFID’s newly formed Safeguarding Unit, and as a result the programme has provided expert advice to the development of DFID’s safeguarding approach as well as responding to safeguarding related queries from both policy teams and country offices.

The response to the increased focus on safeguarding demonstrated the strength of the Helpdesk in being able to rapidly respond to requests for specialist advice, to apply VAWG and safeguarding expertise to a wide range of sectors and provide practical, hand-on guidance to HMG staff in a relevant and accessible format.

A number of strategic initiatives undertaken this year have also demonstrated the added value of the country programme support, and in particular the Helpdesk, in identifying opportunities to integrate VAWG into new sectors and create synergies with other programmes and processes to increase overall impact and amplify VAWG messages. These include:
- Incorporating evidence on VAWG into DFID’s safeguarding response, providing rapid expertise whilst also situating safeguarding in the broader context of VAWG, power and gender equality to encourage a holistic response that recognises the key drivers of exploitation and abuse,
- Increasing engagement with other government departments through identifying linkages and providing tailored evidence on issues such as violent extremism and VAWG, VAWG in conflict and humanitarian settings and the links between international and domestic VAWG issues. This has led to the Helpdesk being used by the Foreign and Commonwealth Office (FCO) and Gender Equality Office (GEO) and emerging interest from the Ministry of Defence (MoD). Providing this expert advice and cutting-edge evidence has positioned the VAWG Helpdesk as a valuable resource across government, enabling DFID to influence the scale and effectiveness of a wider range of Official Development Assistance (ODA) programming,
- Leveraging the programme’s networks, both through the Helpdesk and CoP, to disseminate evidence from the What Works programme, translating this into programme specific advice to encourage the use of the emerging evidence base on VAWG prevention.

These activities, alongside the routine provision of VAWG advice and evidence mapping, are an extremely valuable addition to DFID’s efforts to end VAWG, helping to improve the effectiveness, value for money and ultimately impact of a wide range of HMG investments.

Recommendations for the year ahead
1. The VAWG team should proactively communicate the country assignments service and encourage DFID country offices to use this to integrate VAWG prevention and response into new and existing programmes. (VAWG Team at SDA cadre conference, March 2019, and ongoing)
2. As the Helpdesk enters its final full year, it will be important to consolidate the work done to date and ensure that key evidence products are appropriately packaged and signposted for maximum use. The SRO and Helpdesk team should work to identify thematic sets of queries that could be synthesised to generate a series of evidence products to disseminate to relevant partners. This should include incorporating evidence from the What Works programme where relevant. (SDD to propose by July 2019)
3. Review and summarise any lessons from the VAWG Helpdesk’s safeguarding support, particularly technical advice given on due diligence to DFID programmes, and feed this into any future policy, guidance or support service on safeguarding. (SDD with the Safeguarding Unit by end 2019)
4. In the final year of the Helpdesk the team should prioritise updating the VAWG and Economic Development guidance note, ensuring it reflects the latest evidence and learns from what has worked well in terms of different formats and interactive content to suit audience needs. (SDD, timing to be determined in consultation with DFID’s Economic Development Directorate)
5. The SRO should review the publication status of the guidance notes produced to date and, where possible, ensure these are readily available to as wide an audience as possible. (SRO, by June 2019)
6. The CoP should be made more effective by establishing a quarterly CoP meeting to disseminate evidence, including evidence products generated by the Helpdesk, and to increase the frequency of VAWG team engagement with country offices. The SRO should scope appetite for this amongst the existing CoP members and agree themes for meetings before the end of the programme in July 2020. (SRO with VAWG team policy adviser by July 2019)
7. SDD should identify queries that have a wider applicability or are of interest to more than one DFID team and hold learning meetings and discussions to broaden the audience for these queries. (SDD by December 2019)
8. The update of DFID VAWG programmes should be expanded to capture larger sectoral programmes which include a VAWG element and this should feed into decisions on what strategic engagement the Helpdesk prioritises in the remaining time on the programme. This will help to ensure resources are directed towards better integration of prevention into larger programmes and support a new, more ambitious phase of DFID VAWG programming. (SRO with Helpdesk by August 2019)
9. The programme logframe needs to be updated to set new milestones for February 2020 and final targets for July 2020. As the logframe is being updated the SRO should also: agree targets for beneficiary numbers and prevalence that can be appropriately measured in the time remaining on the programme; add an output indicator to capture the additional volume of work on safeguarding; explore options for an output indicator to measure knowledge and capability. (SRO by June 2019)

## B: DETAILED OUTPUT SCORING

Output Title	Guidance, tools and specialist support helping UK staff develop, monitor and evaluate their country and regional VAWG programmes
Output number per LF		1	Output Score	A+
Impact weighting (%):		100%	Impact weighting % revised since last AR?	No

Indicators	Milestones for this review	Progress
1.1 Call down contract in place for roster of experts to give ‘hands on’ help on VAWG programming and providing timely, high quality support to HMG offices	90% of COs that use the call-down contract report that they are satisfied with the quality and relevance of the support received for their VAWG or sectoral programmes	Exceeded: 100% of the country assignments (Zambia, Nepal) completed during this period received a satisfaction score of 4 out of 5 (or higher) in this review period.
1.2 Helpdesk on VAWG programming for UK staff is established, responsive and effective	90% of helpdesk queries are responded to within timeframes agreed in the SLA or as agreed with client on a case-by-case basis and receive a satisfaction score of 4 out of 5; actively encourage and respond to any requests from other government departments or DFID in-country partners	Exceeded: 100% of helpdesk queries were responded to within timeframes agreed in the SLA or as agreed with client on a case-by-case basis. / 100% received a satisfaction score of 4 out of 5 (or higher) in this review period. / Both Helpdesk staff and the DFID VAWG team have actively encouraged requests from other government departments, particularly the FCO.
1.3 New series of guidance notes on best practice in VAWG programming produced, disseminated and periodically updated	90% of targeted advisors say that specific guidance notes are relevant to their work and easy to use; at least 2 guidance notes updated in the last 18 months.	Met: the helpdesk produced two guidance notes (Humanitarian and Safeguarding in Education). See narrative below for feedback on these notes.
1.4 VAWG Community of Practice has large and diverse membership and is active in improving information sharing and best practice including through a quarterly Evidence Digest across UK and internationally on VAWG issues	2 learning events have taken place in the last 12 months	Met: the Community of Practice continues to be a mechanism for distributing evidence and sharing lessons across programmes. / 4 evidence digests have been produced and learning events have taken place, for example safeguarding mini clinics and an adolescence cross-programme learning event.
1.5 Dedicated resource for evaluation of DFID’s VAWG programming to capture impact and learn lessons on preventing VAWG.	Portfolio mapping and analysis of DFID's VAWG programming updated in the last 6 months before project close out.	Met: DFID updated its portfolio mapping of VAWG programmes in December 2018/January 2019.

Provide supporting narrative for the score

1.1 Call down contract in place for roster of experts to give ‘hands on’ help on VAWG programming and providing timely, high quality support to HMG offices
The Helpdesk has been commissioned to deliver 16 Country Assignments since inception. In the year under review the Helpdesk has completed two country assignments, one in Zambia to support the development of a cross programme VAWG theory of change and to identify opportunities to integrate VAWG prevention and response into other sectors, and one in Nepal to support a security and justice midterm review. Feedback was positive, with both offices recommending the service to others and stating that both the quality and approach of the teams was excellent.
Two country assignments are due to begin shortly in Nepal and Uganda. These will support DFID Nepal to scope options for a future security and justice programme and to integrate VAWG prevention into economic development programming, and support DFID Uganda to analyse their current model of VAWG response services with a view to improving the sustainability of the model in a new phase of programming.

Number of Country Assignments per year and Geographic Area Y1 - Y6
(at Feb 19)
There has been a drop off in country office assignments in the year under review, both the Nepal and Zambia assignments were completed in March 2018 and whilst there were initial conversations with Nigeria this did not lead to a full assignment. There are many reasons why this may have dropped off, but a lack of dedicated resource within the DFID VAWG team to champion the use of country assignments is likely to be a factor, along with delays in the Departmental spending review and the safeguarding crisis driving a different focus among DFID country and policy teams. With an extension to the programme now agreed, it will be important to ensure the country office assignment function of the Helpdesk is fully utilised to support DFID’s commitment to scale up effective VAWG prevention and response programming.
Recommendations:
The extension of the programme provides an opportunity for the SRO to reinvigorate the scaling up ambition and encourage more offices to consider use of the Helpdesk facility. The VAWG team should proactively communicate the country assignments service and encourage DFID country offices to use this to integrate VAWG prevention and response into new and existing programmes

1.2 Helpdesk on VAWG programming for UK staff is established, responsive and effective

Since the Helpdesk contract began 221 queries have been completed, 95.7% of which have received a satisfaction score of 4 out of 5 (or higher) with the average satisfaction rating of 4.5 out of 5.

In the year under review the Helpdesk has responded to 66 queries, more than double the number of requests in 2017 (28). This is the highest level of demand since the service began in 2013. Despite this significant increase in demand, there has been an improvement in satisfaction levels from the 2018 Annual Review, when there was a 90.6% satisfaction score of 4 out of 5 or higher and average satisfaction rating of 4.3 out of 5. This is a strong indication that the quality of the Helpdesk is improving and that the products are meeting the needs of a wide variety of users.

In 2018, the VAWG helpdesk has submitted responses to 66 queries, equivalent to 85 ‘query units’[1].
[1] The Helpdesk is budgeted in terms of query units of 3-day queries, with 1-day queries excluded to avoid skewing comparisons between years. The total number of queries for 2017 was 28 and for 2018 was 66. The total number of query units for 2017 was 43 and for 2018 was 85.
	Number (2018)	Query units (2018)	Query units (2017)
1 day queries	12	12	3
3 day queries	31	31	14
6 day queries	15	30	8
9 day queries	8	24	21
Total	66	85 (doesn’t include 1 day queries)	43 (doesn’t include 1 day queries)

In the year under review there has also been a shift in where queries are being generated from, with a considerable increase in Helpdesk requests from other DFID departments largely explained by the surge in queries from the new Safeguarding Unit and other departments requesting support to strengthen their programming on VAWG, sexual exploitation, abuse and harassment. The percentage of requests from country/regional offices has remained constant, and the increase from other government departments in 2017 has been sustained, while the VAWG team did not proactively commission as many requests. This is a positive sign that demand for the service is growing, with less need for proactive commissioning from the VAWG team.

Helpdesk requests by DFID organisational unit: change from Y1 to Y6

There is evidence that Helpdesk reports are being used to develop policy and country programming, as well as influence colleagues across DFID and HMG. For example, in the year under review:
- DFID Ethiopia used a report on reducing and preventing VAWG in rapidly urbanising cities/towns to inform policy and programming with UN Women to bring their safer cities programme to a city in Ethiopia that is rapidly urbanising. They also shared the report with DFID’s implementing partners working on gender issues;
- DFID’s Climate and Environment Department (CED) shared a report on VAWG, environmental degradation and climate internally with colleagues in CED, ISD and CHASE and are using it as a formative piece to potentially source further funding for broader research;
- DFID Nepal used a literature review on what works to influence social norms change in security and justice programming to inform the design and selection of implementing partners for a programme, and further used the Helpdesk to analyse the unintended impact that economic empowerment programming was having on VAWG outcomes;
- Government Equalities Office (GEO) used a report on engaging men and boys to develop policy options. The report was shared with colleagues in DFID and the Home Office with feedback stating: “5 out of 5. Thanks for this it is excellent … very satisfied with the outcome. This is very useful for improving our evidence base”.

There is also evidence that the reports are being shared widely outside of DFID and other government departments, increasing the potential that they will have broader policy impact with bilateral and multilateral partners. For example, a report on safeguarding risks for the skills and higher education sector was shared with DFID Country Offices and Economic Development Directorate, as well as other donors in the sector (e.g. Denmark, Germany) and actors such as the British Council. Another report and short factsheet on digital harassment of women politicians was shared with Parliamentarians who attended the ‘Women MPs of the World Conference’, DFID staff and other donors and organisations working on women’s political empowerment.
Some examples of the positive feedback on the quality of the service and responsiveness of the VAWG Helpdesk in 2018 include:
- “The service provided was amazingly helpful – swift, thorough, directly addressing the questions that we raised – just brilliant!” (GEO)
- “I’ve been very impressed with the speed and quality of the service. The report is clear and well written and provides valuable insights into the needs of beneficiaries.” (DFID Safeguarding Unit).
- “Really helpful and efficient, such a straightforward process. Excellent resource overall”. (DFID Sexual and Reproductive and Health Rights Team)
- “The entire team were very helpful, quick to respond to requests and provided great advice. The report itself was exactly what we needed to kick-start our understanding and discussions around VAWG. The extra support with a phone call to discuss the report was particularly appreciated” (North Africa Joint Unit).
The Safeguarding Unit has been one of the biggest customers of the programme in the last year, submitting a high number of queries and receiving bespoke support on safeguarding in the employment cycle. Feedback from the Unit confirmed that the Helpdesk provided a ‘fantastic service’, producing high quality products in a time of crisis. Support provided under this programme supported DFID staff to formulate their response with rapid, trusted assessments and information. The focus of much of this work focused on safeguarding in the employment cycle and the Unit also noted that 3 of the major initiatives launched at the 2018 Safeguarding Summit related to these issues, whilst the Helpdesk did not generate these initiatives, their support to early thinking and framing of the issue clearly played a role.
Recommendations:

- As the Helpdesk enters its final full year, it will be important to consolidate the work done to date and ensure that key evidence products are appropriately packaged and signposted for maximum use. The SRO and SDD should work to identify thematic sets of queries that could be synthesised to generate a series of evidence products to disseminate to relevant partners. This should include incorporating evidence from the What Works programme where relevant.
- Review and summarise any lessons from the VAWG Helpdesk’s safeguarding support, particularly technical advice given on due diligence to DFID programmes, and feed this into any future policy, guidance or support service on safeguarding.
  Safeguarding

  Since the safeguarding crisis began in February 2018, the Preventing Violence against Women and Girls Scaling Up Country Support programme has provided support to DFID’s Safeguarding Unit, policy teams and country offices to improve their understanding of and response to preventing and responding to sexual exploitation, abuse and harassment.

  The Helpdesk has provided rapid evidence mapping of best practice and effective policies from other sectors and organisations and quality assured safeguarding policies and procedures. In addition, the programme provided specific policy advice and recommendations to the Safeguarding Unit on potential international human resource responses and broader initiatives to address safeguarding across the sector.

  This experience has demonstrated the added value that a flexible and adaptive Helpdesk can provide, contributing to the rapid upskilling of DFID and partners in an area where a significant capability gap was identified.
1.3 New series of guidance notes on best practice in VAWG programming produced, disseminated and periodically updated
Since the beginning of the programme a series of 10 guidance notes on best practice in VAWG programming have been produced. In the year under review a guidance note on Gender Based Violence (GBV) in Emergencies was finalised in May 2018 and a note on Safeguarding in Education was finalised in January 2019.
The GBV in Emergencies note was well received, being launched at the Humanitarian Cadre Conference in September and shared widely through the Humanitarian Cadre monthly update, Humanitarian Response Group (HRG) and Humanitarian and Stabilisation Operations Team (HSOT). It has been formally requested for use by the Migration Team to inform their inclusion approach, by DFID South Sudan to inform their humanitarian protection work and business case development and by teams in Inclusive Societies Department.
The Safeguarding in Education Guidance Note was launched in January 2019 and therefore there is limited information on its uptake, but feedback from the commissioning team was positive, stating that the note is of high standards and meets their requirements. The commissioning team have confirmed that the note was well received across the education advisory network, the VAWG team SRO will continue to engage with the education policy team in the coming year to ensure opportunities for use are maximised.
Recommendation:
- In the final year of the Helpdesk the team should prioritise updating the VAWG and Economic Development guidance note, ensuring it reflects the latest evidence and learns from what has worked well in terms of different formats and interactive content to suit audience needs
- The SRO should review the publication status of the guidance notes produced to date and, where possible, ensure these are readily available to as wide an audience as possible

1.4 VAWG Community of Practice has large and diverse membership and is active in improving information sharing and best practice including through a quarterly Evidence Digest across UK and internationally on VAWG issues
The VAWG Community of Practice (CoP) continues to exist as a network of DFID staff across country and policy teams. The Helpdesk has continued to produce a quarterly evidence digest that is shared widely across DFID and other government departments. Whilst the widest circulation of the digest is by email, the reports are also hosted on the gov.uk website and have been viewed between 261 (April 2018 digest) and 1869 (January 2018 digest) times this year. The CoP receives the quarterly evidence digest along with invites to relevant events and learning opportunities.
In the year under review there has been a series of events which have targeted the CoP, including workshops focused on safeguarding in education, VAWG and social protection and dedicated events for the Children, Youth and Education Department and DFID Syria country office.
These sessions have received positive feedback from members of the CoP, both in relation to the meetings and the products generated as a result. Feedback from the safeguarding and social protection clinics stated that ‘This was an excellent and much needed piece of work. The support we received from the VAWG Helpdesk on safeguarding in cash transfer programmes was of high quality and well received by both country offices that were part of the deep dive and those that attended the broader dissemination. The checklist SDD produced has been shared with partners in a number of countries and have stimulated a conversation in DFID and between DFID and our partners on what more we can do. The checklist will also be used as part of bespoke guidance on risk management in cash transfers and we will seek to integrate this into the DFID smart guide if at all possible.’
A subsection of the CoP was engaged in an adolescence cross programme learning, during which the Helpdesk presented analysis from DFID’s adolescent focused programmes, along with recommendations on how to strengthen cross-programme learning.

Recommendations:

- The CoP should be made more effective by establishing a quarterly CoP meeting to disseminate evidence, including evidence products generated by the Helpdesk, and to increase the frequency of VAWG team engagement with country offices. The SRO should scope appetite for this amongst the existing CoP members and agree themes for four meetings before the end of the programme in July 2020.
- SDD should identify queries that have a wider applicability or are of interest to more than one DFID team and hold learning meetings and discussions to broaden the audience for these queries.

1.5. Dedicated resource for evaluation of DFID’s VAWG programming to capture impact and learn lessons on preventing VAWG

The dedicated resource for evaluation provided by the VAWG Helpdesk Knowledge and Learning Advisor finished in May 2017. Since then, DFID has been delivering these activities internally, with the VAWG Helpdesk contributing with ad-hoc inputs such as the completion of a Portfolio review during 2017.

In the year under review, DFID’s VAWG team has completed a portfolio mapping update to capture the current scale of programming on preventing VAWG. This has identified several new, ambitious programmes that are seeking to take evidence-based prevention approaches to scale and has enabled the VAWG team to create linkages to share evidence and programme experience between different offices.

The updated mapping of VAWG programming has created additional opportunities to scale up evidence-based prevention approaches, but it has also confirmed that several countries are not planning to continue with standalone VAWG programming. This creates a need and an opportunity to use the country programme expertise and latest evidence to better integrate prevention into larger sectoral programmes with the potential to scale (e.g. education, health), but this will require greater engagement in design and potentially a range of different evidence products targeting a new audience. The recommendations above on synthesising evidence products, promoting the use of country assignments and updating the economic development guidance note should assist this process.

With the Country Programme now extended until July 2020, there is a need to continue to keep this mapping and analysis updated and ensure that the Helpdesk service is responding to the shape and future direction of the DFID VAWG programme footprint. This extension also provides an opportunity to further increase linkages to the future What Works scaling up programme, identifying potential geographies or sectors that could partner to test violence prevention at scale.

Recommendations:

The update of DFID VAWG programmes should be expanded to capture larger sectoral programmes which include a VAWG element and this should feed into decisions on what strategic engagement the Helpdesk prioritises in the remaining time on the programme. This will help to ensure resources are directed towards better integration of prevention into larger programmes and support a new, more ambitious phase of DFID VAWG programming. SRO with Helpdesk by August 2019.

Lessons identified this year, and recommendations for the year ahead linked to this output

The last year has demonstrated that the Helpdesk is able to respond well to pressure and support DFID to rapidly upskill and apply evidence in response to events and emergent priorities. The inbuilt flexibility of the programme has enabled it to adapt to meet a wide range of needs across DFID and other government departments, and this strength has been particularly apparent in the programme’s response to the safeguarding crisis whilst maintaining a core programme of VAWG prevention and response work.

Feedback from both the Safeguarding in Education guidance note and the safeguarding training sessions have also generated lessons for how the programme can more effectively respond to DFID staff needs. Whilst the shorter written analysis and advice has been incredibly well received, there was mixed feedback on the training sessions, particularly concerns over whether the training was practical enough to support staff to improve attention to safeguarding across the programme cycle. Similarly, feedback from the education team noted that additional work was needed to get the guidance note suitably tailored to its intended audience. This is partially due to a pressure to mobilise resources quickly, with insufficient time for the Helpdesk and commissioning teams to agree a common understanding of the intended audience for different pieces of work. SDD have welcomed this feedback and agreed action to improve the service in future, specifically ensuring adequate time at the beginning of all assignments to fully understand the users’ needs and clarify a shared vision for the work. This will help SDD to assign the best staff, allocate an appropriate amount of time and to pitch both written and in-person guidance at the right level.

A further lesson from the last year has been that, when both the Helpdesk service and VAWG team are stretched or operating under full capacity, their ability to identify new opportunities, including new programming to influence or new policy areas to support, is constrained. The VAWG and Helpdesk teams should agree a suitable level of ambition in relation to supporting new or scaled up country programming and prioritise engagement accordingly.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The programme’s theory of change is that a lack of knowledge and evidence globally on how to successfully tackle VAWG in developing countries means that new programmes are particularly in need of strong technical support, coordination and substantial learning components. The lack of technical and programmatic support to DFID country offices, coupled with limited opportunities to learn and share lessons across DFID programmes, hampers progress in making women and girls safer and achieving UK ambitions and the global goals.

Therefore, increased programme support, lesson sharing and rigorous monitoring and evaluation is required to enable DFID country offices to do more and better programming on preventing violence against women and girls, and to contribute to increasing the global knowledge base on effective programme approaches through documenting success.

The theory of change assumes that DFID country offices and other UK government departments working on VAWG are not currently very well networked to share information, expertise and advice and are not using the most up to date evidence and best practice. It also assumes that VAWG programming must be tailored to specific contexts and therefore advice and support on individual programmes is often needed, Overall the theory of change assumes that increased and improved DFID programming will lead to a reduction in incidence of violence against women and girls.

This theory of change still holds, with the programme providing the only dedicated networking and information sharing platform for DFID teams and offices engaged in VAWG work, and the high level of demand for the Helpdesk demonstrates that there is still a lack of knowledge on the subject that requires technical support.

One area in which there are changes to the original theory is the limited evidence globally on how to successfully tackle VAWG in developing countries. In the last year a significant amount of evidence has been generated from the What Works programme and more evidence will be available in the coming year. The Helpdesk and What Works are already well integrated to ensure that this emerging evidence is integrated into Helpdesk services. The country programme theory of change is therefore shifting more towards the need to disseminate and support the application of this evidence in a broad range of contexts.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Outcome:

The anticipated outcome of the programme is effective, relevant and coordinated VAWG programming in UK priority countries. The outcome indicator measures the increase in beneficiaries reached through DFID programmes on VAWG. It is difficult to aggregate beneficiary numbers from VAWG programming because programmes often measure different things – some track the number of survivors receiving services, others monitor the number of people receiving comprehensive interventions to prevent GBV and some track wider community members who have been exposed to anti-VAWG messages.

With that caveat, this year the Helpdesk has contributed to new or improved programming through: strengthening the attention to social norms change for VAWG in Nepal’s security and justice sector; supporting a large new education programme in Tanzania to incorporate a component on preventing violence in schools; developing a cross-office VAWG prevention approach in Zambia to maximise opportunities across sectors; and, supporting the design of an ambition new VAWG prevention and response programme in Malawi.

Overall the Helpdesk is contributing to increasing the scale and effectiveness of our VAWG programming, which is meeting the outcome targets set in the logframe. In the next year the programme will continue to support this scale up, providing both reactive, demand-led support to strengthen VAWG and safeguarding in HMG programming and focusing more strategic support to sectors and countries where scaling up effective approaches to preventing violence against women and girls is most feasible.

Explain major changes to the logframe in the past year

The logframe was amended to extend the output indicators with a final target set for April 2019 – the date at which the programme was set to end. At this point the outcome and impact targets remained the same, with a target date of September 2017.

Describe any planned changes to the logframe as a result of this review

The programme has been extended to July 2020 and as such a new set of milestones and final logframe targets will need to be set.

The outcome and impact targets have not been extended past 2017 and this should be rectified in a light touch logframe review following completion of this annual review. In setting revised outcome and impact targets the VAWG team should liaise with the Helpdesk to identify targets for beneficiary numbers and prevalence rates that can be appropriately measured in the time remaining on the contract, and consider an output indicator to measure knowledge and capability rather than generating evidence products.

Given the volume of safeguarding queries, and the specific support provided to the Safeguarding Unit, the logframe should be amended to reflect safeguarding as a core part of the programme.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

Total spend under this programme from February 2018 – January 2019 has been £290,465.46. This is broken down as £284,446.86 spent on the Helpdesk and £6,018.60 in surge support to the Safeguarding Unit. This total does not include the country assignment in Zambia that was funded directly by the country office. The key cost driver remains the fee rates for personnel engaged in the Helpdesk.

The business case stated that the programme represented value for money on the grounds that it is:
- relevant (based on the needs of DFID country offices and staff working across UK government that are engaged with violence against women and girls in their programmes and policy engagement),
- strategic (based on overarching violence against women and Pillar strategy),
- will contribute to the efficiency by better collaboration, learning and coordination, drawing on expertise on the specific areas of interest to DFID and UK government, and
- economical (costs of the helpdesk, call down contract and evaluation will be benchmarked against similar initiatives to ensure it is being economical)

This assessment remains accurate. The increase in demand for the Helpdesk has confirmed that it provides a highly relevant service, it remains firmly embedded as part of DFID’s Strategic Vision for gender equality and broader ambition on reducing violence against women and girls, it continues to drive efficiency through identifying and sharing lessons, and all fees are benchmarked.

Economy
The fee rates are the key cost driver for this programme. In 2017 SDD committed to a reduction in fee rates for all SDD employees deployed to support the delivery of the Helpdesk, and this is now in line with the fee rates for the ‘What Works to end Violence’ programme. These rates will be held for the duration of the contract extension, this represents a real term cut in rates when inflation is considered. The VAWG team convened the first meeting of an internal Helpdesk learning group within DFID to share information on costs and drive greater economy across a range of similar services.

Efficiency
The Helpdesk continues to exceed the service level agreement standards in relation to response time for queries. In the last year the Helpdesk team has met regularly with the SRO to plan the Helpdesk pipeline and improve systems to refine, sequence and combine queries, select the most appropriate consultants and ensure a full pipeline to maximise efficiency.

Effectiveness
The Helpdesk consistently exceeds its target of ensuring that 90% of respondents are satisfied with the support received. In the year under review the Helpdesk average satisfaction rate has improved to 4.5 out of 5. This is particularly notable given the context of an increased number of queries, that the Helpdesk was able to not only maintain standards but improve them.

Equity
The Helpdesk helps to ensure that DFID programmes on VAWG understand who the most vulnerable and excluded people are and how to reach them. In the past year the Helpdesk has produced a rapid evidence review of violence and widows, linkages between VAWG and VAC. This complements previous work on links between VAWG and excluded groups such as sexual minorities and women and girls with disabilities.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The programme should continue as it remains a highly relevant service, with demand growing across DFID and other government departments. Despite a significant increase in the query service, the Helpdesk has managed to improve the its satisfaction rate, demonstrating improved efficiency.

The Helpdesk monthly retainer was calculated based on handling 4 queries per month. Between February 2018 and January 2019 there were only 2 months when 4 queries were handled, 1 month when the Helpdesk fell below 4 queries and 9 months when the Helpdesk was operating above this threshold. This includes 7 months where the Helpdesk handled more than 8 queries.

In January 2019 a costed extension was approved to extend the Helpdesk service until July 2020, on the basis that the contract continues to provide good value for money, delivering strong performance against the logframe and service standards. As part of this extension the Helpdesk will maintain the same monthly retainer despite the sustained increase in demand, again a real term reduction when taking inflation into account. This demonstrates that the Helpdesk is continuing to provide a valuable, timely service albeit with a lower administration cost per query, and therefore is delivering better value for money than during previous review periods.

In the context of the wider portfolio, the Helpdesk continues to improve the value for money of other programmes both within DFID and in other government departments. By sharing the latest evidence on effective VAWG prevention and response, the Helpdesk helps to improve the effectiveness and equity of other programmes, and in providing flexible support to safeguarding the Helpdesk has ensured that the best international and other sector evidence is used to shape an emerging policy area.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The overall programme risk rating is minor: 7 risks are actively monitored – one of these is a moderate risk and the remaining 6 are minor. The moderate risk is a reputational risk that DFID’s use of contractors to support policy and programming on VAWG generates media criticism.

Reputational Risk
The use of contractors to support policy and programming on VAWG and/or their fee rates could lead to criticism. However, the need for technical expertise to support the scale up of VAWG programming was recognised by ICAI and the safeguarding crisis further highlighted the need for additional expertise in this area. The continual benchmarking of Helpdesk fees helps to mitigate this risk. The Independent Commission for Aid Impact (ICAI) noted that the Helpdesk has provided a useful source of additional VAWG expertise, including on specific countries and themes. This independent review also helps to mitigate any potential reputational risk.

Operational Risk
This is a combination of risks related to low demand for the helpdesk from DFID staff, lack of engagement from other government departments and a proliferation of Helpdesk-type vehicles creating duplication. In relation to the first two, the last year has demonstrated that this risk is reducing as the programme progresses, with higher level of awareness and demand from both within and outside of DFID. There is a risk of a decline in the next year as people are unaware of the extension of the service. This will continue to be mitigated by communication from the VAWG team and support to country offices and other government departments to use the service. Reinvigorating the CoP, including with members from other government departments, should also help to mitigate this risk.

Helpdesk-type vehicles continue to be created, in the last year additional facilities providing support on social protection and disability have become operational, but enhanced coordination and clarity on scope is helping to reduce this risk. The VAWG team has mitigated this by establishing an internal Helpdesk learning group to share information between SROs and programme managers and ensure lessons are learnt across different facilities.

An additional operational risk has materialised during the last year, related to the VAWG team capacity to effectively manage the Helpdesk. Due to a range of competing priorities, the team managing the Helpdesk has not been able to fully engage to maximise the potential for the Helpdesk and to proactively generate interest and strategic queries. The risk is that, if capacity gaps remain, then the Helpdesk may not be as effective as it could be in proactively shaping the portfolio and generating demand in strategic partner countries, with the potential capacity to scale up effective approaches.

Delivery Risk
This is a combination of two risks – that materials produced by the programme do not meet staff needs and that there continues to be demand for the Helpdesk beyond the end of the current contract. The risk that materials produced do not meet their needs is decreasing over time as the Helpdesk and VAWG team continually improve the processes for responding to requests and systematically gather feedback to improve future performance. A good example of this is the Tanzania country assignment, where learning from what did not work fed into a different selection process for any similar work in future.

The risk that there is demand beyond the contract end date increased during the year under review. The planned mitigation was to review on-going capacity and capability gaps on VAWG and consider how best to address, including provision of longer-term technical assistance as part of a new What Works programme. This mitigation measure was successful, with DFID recognising that there would be a capacity gap between the planned end of the Helpdesk and the mobilisation of the new What Works programme. The response was to extend the programme to July 2020 to ensure support for VAWG and safeguarding can be sustained. This risk will continue in the next year and the frequency of monitoring should increase to ensure a more sustainable capability offer is in place before the end of the contract.

Fiduciary risk
The overall risk of misuse of funds is low. Checks and balances are in place to prevent misuse of funds and all invoices are cross checked to ensure that each query has been approved by the VAWG team, and feedback has been received by the commissioning departments, before payment is made. The specific fiduciary risk that is tracked by the programme is the risk that DFID country offices using the Helpdesk call down contract service issue contracts above the OJEU threshold and breach procurement procedures. This is mitigated by close engagement between the commissioning country office, SRO and Helpdesk teams, use of standard contracting templates and separation of duties at contracting stage.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

Delivery against planned timeframe
The Helpdesk has responded well to the high level of demand experienced since February 2018, managing some very busy periods whilst still sticking to timelines and delivering quality products. This increase was caused partly by the high demand for Safeguarding queries (more than half of the queries during the period from February to November 2018 were from Safeguarding Unit or related to safeguarding issues), and the period from February to December 2018 has seen 8 months out of 10 when the number of queries exceeded the average of 4 per month, on which the Helpdesk is budgeted. DFID staff time to engage properly with this service continues to be essential if it is to achieve maximum impact and value for money, especially if demand continues at current levels.

The only other component active during the year under review was the contract to deliver rapid analysis of policy response options for the Safeguarding Unit. This contract did provide rapid response in a time of crisis, and the main users of the service (Safeguarding Unit) praised the rapid response and clarity from partners on timelines. At the start of the crisis rapid estimates were made of the potential demand for such support, and the contract was designed to be able to respond to this. In practice, demand was met in other ways and ultimately this contract was not used to the extent originally envisaged. Out of a budgeted £100,000, this element of the programme only spent £6,018.80.

Performance of partnership
The relationship between DFID VAWG team and SDD has continued to be positive, with regular meetings and discussions to identify strategic priorities, to plan for the remainder of the programme and to learn from what has and has not worked well, in both content and format of Helpdesk products.

The Helpdesk’s Strategic Oversight Committee (SOC) meets quarterly to review progress and plan for the next quarter. The SOC consists of representatives from each consortium organisation and DFID’s programme management team. Alliance partners also meet quarterly before each SOC meeting. Written feedback on the quality of the Helpdesk service and reports is also received from DFID staff upon completion of all helpdesk queries, country assignments and guidance notes before payment of invoices, with any negative feedback followed up with partners. Feedback received over the period of this Annual Review has been largely positive, and the Helpdesk has been proactive at addressing any criticism, and actively learning lessons to improve.

For example, feedback on the Safeguarding in Education Guidance Note was positive, but with some suggestions for future large pieces of work: “the final product from the VAWG helpdesk is of high standard and meets the requirements well. I am confident it will be useful across DFID and it supports an important work stream. The process was sometimes challenging however, and DFID did have to be quite interventionalist at points, providing substantial comments/track changes, and for one section of the drafting securing the time of a Senior Adviser to be more directly involved in the writing process. This is partly due to DFID having an ever-increasingly clear idea of what it was we needed, and it is to the VAWG Helpdesk’s credit that they accepted this hands-on approach to get the product to completion. The final product is exactly what we need.” Following this feedback, the Helpdesk team, SRO and commissioner of the guidance note have had further discussions to identify concrete lessons to improve the service in future, demonstrating the quality of the partnership and ability to learn together from constructive feedback.

Quality of financial management
The VAWG Helpdesk is demand driven, which leads to monthly fluctuations in forecasting. During the early years of the Helpdesk, there were quite large fluctuations where several months in a row saw demand of less than the average of 4 queries per month. Levels of demand have been consistently higher over the period since February 2018, and monthly costs have fallen mainly within the £17,000 to £27,000 per month bracket. The SRO continues to review past performance of the Helpdesk to help forecast monthly costs more accurately. Regular forecasting updates from partners and better pipeline planning of larger, supply-side products such as guidance notes and policy and strategy tools have also continued to assist with planning and delivery of these larger-spend products.

With the Helpdesk now extended to July 2020, the need for excellent financial management will become increasingly important to ensure sufficient resources for both the smaller, reactive pieces of work and larger more strategic interventions. To achieve this the Helpdesk team and SRO have committed to increase the frequency of communication with relation to work scheduling and forward planning of larger Helpdesk assignments.

Asset monitoring and control
The assets of the programme relate to the information generated by the partners. Knowledge products and reports are saved on DFID’s internal document management platform and shared through networks. Where appropriate, they are made available to wider HMG and DFID audiences on the gov.uk website. SDD have also donated space on their own website and opened a twitter account for dissemination of Helpdesk products at no charge to DFID. We are currently in discussions with Research for Development (R4D) around which Helpdesk reports can be shared on that platform and have asked SDD to add a question to the feedback form around sharing reports in the public domain. We remain committed to sharing Helpdesk learning with as wide an audience as possible.

Date of last narrative financial report
Date of last audited annual statement	27 June 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

The formal monitoring arrangements for the programme is a quarterly SOC, chaired by the DFID SRO and consisting of the DFID programme team and all Helpdesk consortia partners. These meetings look back at the work done by the Helpdesk in the last quarter and look ahead at the pipeline for the larger, more strategic plans for the next quarter. In addition, the meetings address programme management issues such as updates on the annual review recommendation, logframe, risk and budget. DFID receives monthly and quarterly query logs from the Helpdesk.

The DFID SRO approves all Helpdesk requests, to ensure that these are in line with the programme objectives and within budget, and the team also receives feedback from each query commissioner on their satisfaction with the service and any ideas for future improvement. These are fed back to the VAWG Helpdesk to improve the quality of the service in future.

Internally, the DFID programme team meet monthly to discuss progress on the programme, identify any emerging issues or action needed and plan for coming months.

Evidence

Most Helpdesk products are evidence reviews or syntheses and as such the core objective of the programme is to generate, disseminate and facilitate the use of evidence. To date the Helpdesk has responded to a total of 221 queries, generating and applying evidence across a wide range of subject area such as harmful cultural practices, women peace and security, links between climate change and VAWG digital harassment, and safeguarding against sexual exploitation, abuse and harassment.

In addition to this service, the Helpdesk also produces a quarterly evidence digest summarising developments in the sector and drawing on both Helpdesk reports and other evidence. The 2018 digests have been viewed a total of 2,796 times, and this does not include the number of people who receive the digest through the CoP mailing list.

The volume of evidence produced by the programme since 2013 is substantial and not all is publicly available. During the remainder of the programme, the VAWG team should work with the Helpdesk to attempt to synthesis similar sets of queries into resources packs and ensure that, where possible, these are published and proactively disseminated to a wide range of partners working across a range of sectors.

Learning

The increasing use of the Helpdesk is evidence that there is still demand and need for this type of service, and the increase in satisfaction rates is a signal that the Helpdesk is learning from experience to improve the quality of this service. In the year under review the programme has demonstrated a strong ability to learn about the best format and approach for engaging DFID staff and building their capability. This has led to a move away from long written guidance notes in favour of more interactive content and bespoke advice through mini-clinics and learning events.

In 2018 the DFID VAWG team established a learning network across the different helpdesks run by DFID. This has been useful in sharing experience about the operations of helpdesks as they relate to costs and measurement, and will continue to be a useful platform for cross-DFID learning.

Beyond the operations and management of the Helpdesk, the programme has generated broader learning on DFID’s approach to safeguarding, including learning from other organisational approaches and different mechanisms that could be adopted by both DFID and our partner organisations. This fed into the Safeguarding Summit in October 2018 and the subsequent actions to which many multilateral, bilateral and civil society partners agreed.

Progress on recommendations from previous reviews

The SRO and the VAWG Helpdesk manager should guide country offices on what is the best and most appropriate use of the VAWG Helpdesk Country Assignment Service to ensure maximum value for money	Done: This recommendation arose due to a country assignment in Tanzania that did not fully meet the needs of the requestors. Feedback from country assignments completed this year has been positive, and the SRO has proactively engaged with the new country assignments (Uganda and Nepal) to restructure requests and sequence work to ensure maximum value for money
The SRO will work with the Helpdesk manager to provide advice where country assignments are required to provide support to a third party rather than DFID directly, or where the DFID country office is not able to give adequate time to engaging with the work	Not applicable: This recommendation arose from the Tanzania assignment and a similar situation has not arisen in the year under review. We will action this recommendation if the situation arises again.
Social Development Direct will introduce additional steps to verify consultants they have not worked with before. As well as interviewing them and taking up references, they will also require samples of written work	Done: This practice was followed with selection of consultants for country assignments in Nepal.
Social Development Direct will continue to explore opportunities to increase user-friendliness of helpdesk products with visuals (infographics), accompanying factsheets, talking points and checklists	Done: The format of Helpdesk products has been discussed with SDD during SOC meetings and has featured heavily in discussions on updating or replacing guidance notes. In the year under review the Helpdesk has provided clinics rather than written reports or guidance (safeguarding), summarised evidence into infographics (prevalence of SEAH) and used checklists to support programme teams (safeguarding in social protection programmes)
DFID to review the impact of the strategic MENA CSSF engagement, and look at whether this might provide a model for similar engagement in other regions on CSSF programming	Ongoing: The Helpdesk support for MENA CSSF is ongoing, with the gender review due to be presented to the regional board shortly. The SRO and Helpdesk team have discussed the potential to use this as an entry point for broader FCO engagement, including on PSVI and integrating VAWG into broader security framework thinking. They should continue to follow up after the CSSF board discussion.
The SRO will form a learning group across DFID with those managing similar ‘helpdesk’ programmes, to ensure we share lessons about what works, maximise synergies and avoid duplication	Done: The first meeting of the learning group took place in September 2018 and focused on costs. The second meeting took place in February 2019 and focused on measurement.