REVISE LOGFRAME (v.022014)

PROJECT NAME	SUPPORT FOR THE IMPLEMENTATION AND PREPARATORY ARRANGEMENTS OF THE ICCTF
GOAL	Indicator	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011	Target (Dec. 2013)			Target (Dec. 2014)
To ensure the GoI can provide more effective leadership and management of climate change programming to deliver emissions reduction and poverty reduction outcomes	Development of comprehensive transition plan from interim trustee into the ICCTF	Transition plan doesn't exist.	Implementation of transition plan (deferred to 2013)	Transition plan is fully implemented (deferred to 2013)	Transition plan is fully implemented (i.e SOP of ICCTF finalized and implemented, Ministrial regulation on LWA ICCTF issued, Fund Raising Strategy developed; Ministrial decree on MWA issued)			ICCTF Secretariat and LWA is fully operational
		Source

	Indicator	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011	Target (2013)			Target (2014)
	Existence of a fully functional ICCTF	ICCTF lacks of institutional, legal and organisational arrangements/capacities	N/A	ICCTF has governance, management and administrative capacity required to fully operationalised (deferred to 2013)	National Fund Manager is appointed; ICCTF has governance, management and administrative capacity required to be fully operationalised			National Fund Manager and Satker are fully operational to support ICCTF governance, management and administrative functions
		Source

PURPOSE	Indicator	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011	Target (2013)			Target (2014)		Assumptions
ICCTF efficiently and effectively serves as a National Trust Manager and is fully capacitated to do so	Establishment of ICCTF as Indonesia National Trustee through development of SOP and National Trustee selection Guidance	N/A	N/A (new purpose after AR in March 2011)	SOPs and National Trustee selection guidance available (deferred to 2013)	SOPs and National Trustee selection guidance available			The SOPs fully implemented by LWA as a National Trustee
		Source

	Indicator	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011	Target (2013)			Target (2014)
	ICCTF window investment guideline and project selection mechanism	N/A	N/A (new purpose after AR in March 2011)	ICCTF window investment guideline and project selection mechanism available (deferred to 2013)	ICCTF revised business plan, funding strategy; window investment guideline and project selection mechanism available			Investment & Fundraising Strategy fully facilitated and managed by ICCTF (MWA and its Sec.)
		Source

INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)			DFID SHARE (%)
	6,200,000
INPUTS (HR)	DFID (FTEs)

OUTPUT 1	Indicator 1.1	Baseline March 2010	Milestone Aug 2010	Milestone Jun 2011		Milestone Jan 2012	Target (2013)		Target (2014)	Assumption
Priority climate change projects (Land Based Mitigation, Energy and Resilience and Adaptation) selected, supported, monitored and evaluated	Number of proposals received.	Nil	2 proposals received for 2010	3 proposals received for 2011		3 proposals received for 2012	Call for small grant proposals conducted; 6 proposals received under Small Grant Program for 2014		Nil
		Source

	Indicator 1.2	Baseline March 2010	Milestone Aug 2010	Milestone Jun 2011		Milestone Jan 2012	Target (2013)		Target (2014)
	Number and type of activities conducted or supported by ICCTF secretariat for the project selection	Nil	Land Based Mitigation, Energy and Resilience and Adaptation projects targetted	2 workshops/meetings on project assessment/selection and 3 coachings/trainings for proposal development conducted		2 workshops/meetings for project assessment/selection and 3 workshops for proposal development conducted	2 workshops/meetings for project assessment/selection; 3 trainings for proposal development conducted		6 capacity building programs on project proposal strengthening conducted for line ministries and CSO's (eg pipeline projects)
		Source

IMPACT WEIGHTING	Indicator 1.3	Baseline March 2010	Milestone Aug 2010	Milestone Jun 2011		Milestone Jan 2012	Target (2013)		Target (2014)
35%	Number of Climate Change Project selected, monitored and evaluated	Nil	2 projects monitored and evaluated	3 projects monitoried and evaluated		programmatic monitoring and financial spot check conducted 4 times (quarterly)	3 climate change project monitored and evaluated; Each project will have quarterly programmatic monitoring and financial spot check conducted, in total 12 times		Impact Evaluation conducted at the end of projects (Health, Agriculture and Forestry) and shared with donors
		Source					RISK RATING
						Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)			DFID SHARE (%)
	5,800,000
INPUTS (HR)	DFID (FTEs)

OUTPUT 2	Indicator 2.1	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011		Milestone Jan 2012	Target (2013)		Target (2014)	Assumptions
Functioning policy dialogue and increased awareness of ICCTF nationally and internationally	Number and type of policy dialogue conducted	Nil	4 Quarterly Policy Dialogues	4 Quarterly Policy Dialogues		4 Quarterly Policy Dialogues	10 National Policy dialogues conducted		6 National policy dialogues conducted	Policy dialogue encompasses a broader spectrum of climate change and development issues, aimed to improve coordination and information sharing among ICCTF, GOI, development partners, CSO and private sector. It may include SC meetings; policy cordination forum; workshops/discussions.
		Source

	Indicator 2.2	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011		Milestone Jan 2012	Target (2013)		Target (2014)
	Number and type of awareness raising activities conducted	Nil	2 awareness activities for potential audience conducted	Public Relation and Communication for ICCTF		Public Relation and Communication for ICCTF	3 major events of awareness raising including: - Regular quarterly newsletters. - Participation in COP and media campaign		Implementation of awareness raising including: - Reguler quarterly newsletter - Participation in COP - Media/journalist award/fellowship

IMPACT WEIGHTING
20%
		Source:					RISK RATING
						Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)			DFID SHARE (%)
	100,000
INPUTS (HR)

OUTPUT 3	Indicator 3.1	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011		Milestone Jan 2012	Target (2013)		Target (2014)	Assumptions
Capacity of ICCTF governance, and related stakeholder (Government of Indonesia and CSO's ) developed	Number and type of capacity development programmes for ICCTF and related stakeholder (GoI and CSOs)	Nil	4	A rapid capacity assesment conducted		Capacity Building for ICCTF Governance and potential beneficiaries	10 capacity building activities on thematic climate change issues for related stakeholders for annual reporting on GHG emissions reduction and resilience increase		10 Capacity building activities conducted for ICCTF governance and related stakeholder (GoI and CSO's);	Certification (Indicator 3.2 Target 2014) is aimed at assessing and certifying robust ICCTF fiduciary management and finance sytem and performance in compliance with national and international standards and regulations
		Source

	Indicator 3.2	Baseline March 2010	Milestone Aug 2010	Milestone Jan 2011		Milestone Jan 2012	Target (2013)		Target (2014)
	Number and type of activities conducted to establish a fully staffed and functioning ICCTF national trust fund	Nil	4	Design capacity development programs for selected entities		Implement capacity development program for selected entities	National Fund Manager appointed; an institutional set up required for a nationally managed trust fund established (Kepmen/Permen); data base system (finance, HR, project management) established; conversion of contract from UNDP to GOI ; - Review of Fund Raising Strategy and Endorsement of Business Plan		- MWA ICCTF as Satker under BAPPENAS established and operational; - Executive Director mobilised; HR strategy revised; - ERP System operational; - 6 workshops and 3 conferences/seminars participated; - 3 training conducted; - Certification by an international audit firm conducted
		Source

IMPACT WEIGHTING
45%						High
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)			DFID SHARE (%)
	300,000
INPUTS (HR)		o