Project Completion Review

Title: South Sudan Health Pooled Fund – Phases 1 and 2
Final Programme Value: / £256m total, including: £108m (DFID); £148m (other donors)		Review Date: January 2018
Programme Code: 203109	Start Date: / October 2012	Final End Date: 15 October 2018 (end of implementation)

Summary of Programme Performance

Year	2013	2014	2015	2016	2017	2018
Programme Score	A	A	A	A	A	A
Risk Rating	Medium	High	High	Major[1]	Major	Major
[1] DFID changed its risk categories in 2016 (see page 12)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3769141.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/34449787.xlsx

A. Summary and Overview

Description of programme and what it has achieved

The Health Pooled Fund (HPF) was the largest primary healthcare programme in South Sudan. Implemented over 2012-2018 by a consortium led by Crown Agents and contracted NGO implementing partners at state and county levels, HPF was a £256m multi-donor fund led by DFID as the largest donor (58%), and received funds from Australia, the EU, Canada, Sweden and the USA. The programme supported the Government of South Sudan to deliver primary health care services through its network of primary health care facilities, county and state hospitals. The programme’s focus was to increase the utilisation and quality of health services, with an emphasis on maternal and child health. The programme achieved this through direct support to health facilities including equipment, staffing and supportive supervision. The programme also provided a supply chain of essential medicines, in addition to supporting humanitarian health interventions and strengthening the public health systems.

The intended impact of the programme was to develop a government-led health system that saves lives. The overall outcome was increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. The original business case for HPF1 covered the period 2012 - 2016. Under this phase, the programme worked in 6 of the former 10 states (Eastern Equatoria, Warrap, Lakes, Unity, Northern Bahr El Ghazal and Western Bahr El Ghazal) in South Sudan. The outputs were:
1. Strengthened delivery of health services, particularly responsive to the needs of women and children;
2. Increased ownership, governance and demand of communities for health services; and
3. Strengthened health systems at state and county level.

DFID agreed a costed extension with the incumbent supplier in 2016, which extended the programme until 2018. At this extension point, USAID became a co-donor of the HPF, combining their two states (Central Equatoria and Western Equatoria) into the HPF model. This expanded the HPF to cover 8 of the former 10 states. The focus of the programme also expanded to include nutrition. This widened scope of the programme was reflected in the amended outputs:
1. Strengthened delivery of health services, particularly responsive to the needs of women and children;
2. Strengthened health systems at State and County level with detailed focus on: policy; human resources for health; health financing; health information; leadership and governance; and
3. Increased access to nutrition services particularly for pregnant women and young children.

Throughout the programme period, the operating context in South Sudan proved extremely challenging. The outbreak of national-level conflict in December 2013, and the deeper conflicts in July 2016, made operating in South Sudan precarious. The widespread conflict resulted in increased insecurity, internal displacement of citizens, and exacerbating a humanitarian crisis. Donors and implementing partners were evacuated following the outbreak of violence in Juba in 2016, impacting on the delivery of the programme although it was able to continue. At the same time, a worsening economy with very high levels of inflation and drastically reduced government revenues reduced the government’s ability and willingness to contribute to health, leading to an almost non-existent national health budget.

Despite the challenges, the programme has continued to meet its overall objective of delivering primary health services to the population of South Sudan. It has effectively met Outputs 1 and 3 (from the second phase). Output 2 has been more challenging due to the limited government resources and lack of spending on the health sector including salaries, drugs and commodities. Given this context, the ambition under this output was reduced over time, with increased emphasis instead put onto stabilisation of existing systems and services.

Key achievements across the 8 states include:
- Supporting the delivery of more than 9 million consultations to children under-five.
- Almost 28% of all pregnant women attended four or more antenatal care sessions
- Supporting 29 Comprehensive Emergency Obstetric care centres and 44 Basic Emergency Obstetric care centres
- The Human Resources Information System (HRIS) was established in all 54 counties
- The percentage of facilities reporting stockouts of key tracer drugs reduced from 35% to 18%
- Over 1.7 million children were weighed and measured as part of routine nutritional assessments
- More than 3,000 health workers were trained on management of acute malnutrition

Overall, the programme has met expectation across programme output, indicators. All three outputs of the programme have been assessed as achieving a score of “A”. The project also broadly achieved its outcomes, particularly exceeding the percentage of children who were fully immunised, although still low. It was more difficult to assess the impact of the project. There has not been a national estimation of the maternal mortality ratio or the infant mortality rate since 2008. Nevertheless, internal estimates show that the project contributed to averting more than 2.7 million Disability Adjusted Life Years (DALYs), which is comparable to other large scale health programmes.

Key lessons and recommendations from HPF1 and HPF2 are summarised as below for implementation under the third phase of HPF in 2018-2023:
- An increased focus on community interventions to improve the delivery of family planning and maternal and child health services.
- Further improving the availability of drugs and medical supplies by ensuring “last mile” delivery of items and an annual procurement cycle of essential items.
- Utilising resources more efficiently through allocation of primary health care facilities and increasing the focus on delivery of quality services
- Supporting the stabilisation of the health system where it exists, and not build more structures or larger scale health system strengthening activities
- Streamlining the number of indicators to cover the most pertinent programmatic ones, and striving to have data disaggregated by gender and disability
- Maintain up to date strategies that cover: conflict, gender, mental health and disability
- Ensure that safeguarding policies are in place and operationalised
- Conduct a review of conflict sensitivity for future HPF partners and consider direct support to some partners.

There are still some remaining follow up actions that will be required after completion of this review:
- Final HPF2 invoices to be paid alongside internal financial closure
- Finalisation of disposal of assets transferred to HPF3, ensuring maximum VfM, and reclaiming of any lost assets, primarily due to insecurity.

## B: DETAILED OUTPUT SCORING
Output Title	Strengthened delivery of health services, particularly responsive to the needs of women and children
Output number per LF		1	Output Score	A
Impact weighting (%)?		50%	Impact weighting % revised since last AR?	N

Indicator	Target: September 2018	Progress
Output indicator 1.1: / Under five years outpatient consultations (total): 1. Curative consultations 2. Preventive/ promotive services	Cumulative / 8,252,350 (total) / 5,607,015 (curative) / 2,645,335 (preventive)	Score: A (114%) / 9,425,612 (total) / 6,219,974 (curative) / 3,205,638 (preventive)
Output indicator 1.2. / Percentage of children under five years with diarrhoea who receive ORT	Average / 91%	Score: A (100%) / 91%
Output indicator 1.3. / Percentage of women who attended at least four times or more for antenatal care during pregnancy	Average / 27% (290,065)	Score: A (104%) / 28% (314,987)
Output indicator 1.4. / Number of facilities with capacity to offer Emergency Obstetric care (disaggregate BEmONC[2] and CEmONC[3])	CEmONC: 26 / BEmONC: 44	Score: A (104%) / CEmONC: 29 / BEmONC: 44
Output indicator 1.5. / Percentage of ANC attendees who received IPT2 and more	Average / 52.0%	Score: A (105%) / 54.4%
Output indicator 1.6. / Proportion of women 15-49 years using any modern family planning method	6.0%	n/a (no data due to lack of survey)
Output indicator 1.7. / Percentage of counties where bulk consignments of medical drugs are distributed at Hospital and CHD level	98%	Score: A (100%) / 98%
Output indicator 1.8. / Number of health facilities offering family planning services, with a minimum of three modern methods including male condoms	200	Score: B (83%) / 165
Output indicator 1.9. / Number of Antenatal client given Ferrous Sulphate + Folic Acid supplementation	489,031	Score: A+ (125%) / 611,931
[2] Basic Emergency Obstetric and Newborn Care
[3] Comprehensive Emergency Obstetric and Newborn Care

Supporting narrative for the score

The service delivery component of the Health Pooled Fund maintained steady performance throughout the implementation of the programme. This was particularly bolstered by a more consistent supply of drugs to the facilities, supportive supervision and the filling of key health worker vacancies. There was a strong consistency in delivery of basic health services since the programme inception in 2012. Attribution of results remains challenging in a context where humanitarian implementing partners are also operational although it is still felt that using data from the national health information system is the best way to support it and the trends across the programme remain valid.

The availability of drugs, use of outreach services and availability of health workers led to an increased demand in services, which increased outpatient consultations and children under five who received Oral Rehydration Therapy (ORT) (Indicator 1.1 and 1.2). Even though the targets were met for indicator 1.3, there was a very limited increase in numbers of women who attended four ANC visits. This remained a challenge throughout the programme, as it was perceived there were no added incentives for women to attend ANC four times during the pregnancy. It will be useful to explore how community based interventions can be used to increase the acceptability of ANC in future programmes.

There were issues with the data on Indicator 1.4, the number of BEmONC and CEmONC centres. Even with the modest targets, the data was not felt to be robust and reliable enough. This was particularly true of the number of facilities that were able to offer CEmONC, as some of the facilities were not able to perform Caesearean sections; thus were erroneously labelled as CEmONC facilities. It will be useful in future programmes to set the parameters for health facility functionality very clearly.

On indicator 1.5, the percentage of women who received the second dose of intermittent presumptive treatment for malaria (IPT2), the targets were consistently missed throughout most of the life of the programme. The targets were thus set very low, but were finally met in one quarter at the end of the programme. Part of the reason for the inconsistent achievement of this target was the stockouts of ANC specific drugs which are procured through a separate supply chain, outside of the direct control of the programme.

Indicator 1.6 has not been tracked by the programme. Due to insecurity there have not been any systematic national health surveys conducted since the start of the programme, and this will need to be carefully considered in future designs. Overall however, there were some achievements in improving family planning, including increased training to facilities, outreach services and supportive supervision to implementing partners. There was also a regular supply of contraceptives provided by UNFPA, but delivered using the HPF supply chain. Several challenges still existed, including the lack of dedicated budget for family planning activities, the lack of a family planning strategy and poor community acceptance.

Indicator 1.7 shows a consistent supply of drugs to Hospital and County Health Department (CHDs). This was one of the key successes of the programme in ensuring that essential drugs are delivered on time to counties across the country. Commodity supplies were also key to the success of indicator 1.9, where more women were given ferrous and folate supplementation. However the focus must now be on ensuring last mile delivery and the reliable availability of medicines at the facility level.

Indicator 1.8 was not met due to challenges with community awareness of family planning as described under indicator 1.6 above. Future programmes will need to have an enhanced focus on family planning particularly increasing the options available, and reaching the community to try and counter negative perceptions of family planning in South Sudan and increase demand.

Lessons identified this year

- A strong supply chain of essential drugs and commodities is vital to primary health care in South Sudan. Future programmes must maintain a keen focus on further improving the supply chain down to the facility level, and then to the end user through last mile distributions, but also focus on increasing the variety of drugs that are available. The current essential drugs list under the HPF is very narrow and could be revised.
- Achievement in family planning was poor. Future programmes need to fully consider how they will involve both the community level, but also national strategies and policies in order to increase family planning. Tracking the uptake of family planning methods through surveys did not occur. Either, surveys will need to be inbuilt to the programme design or other alternative ways of tracking results need to be identified and included.
- The programme was tracking a large number of indicators, and it would have been useful to streamline the indicators to make a more focused monitoring plan. Future programmes need to as far as possible use standard indicators, to enable comparison with other programmes. This can then be bolstered with fewer programme-specific indicators.

Output Title	Strengthened health systems at State and County level with detailed focus on: Policy; HR for health; health financing; health information; leadership and governance
Output number per LF		2	Output Score	A
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Target (September 2018)	Progress
Output indicator 2.1. / Number of HPF Steering Committee meetings co-chaired by GOSS (cumulative)	19	Score: A (111%) / 21
Output indicator 2.2. / Number of State Oversight Committee meetings held (cumulative)	60	Score: A (108%) / 65
Output indicator 2.3. / Number of counties with one comprehensive health plan and budget (government and all partners combined)	100% (March 2018 target)	Score: A (100%) / 100% (March 2018; no annual plans during extension)
Output indicator 2.4. / Number of counties in which HRIS is implemented	94% (50/53)	Score: A (106%) / 100% (53/53)
Output indicator 2.5. / Percentage of functional facilities with quarterly integrated supportive supervision visits conducted by county health department using the Quality Service Check (QSC )tool	60%	Score: B (80%) / 48%
Output indicator 2.6. / Percentage of functional health facilities submitting HMIS reports through the DHIS timely (according to the data flow policy)	83%	Score: A (99%) / 82%
Output indicator 2.7. / Number and percentage of health facilities with a health committee in place for communities to give feedback regarding health services	95%	Score: A (101%) / 96%
Output indicator 2.8. / Percentage of functional health facilities which have documented joint meetings held with the health committee and health facility and either CHD or IP (i.e. a quorum of 3 with the health committee and health facility being the main parties. CHD and/or IP will be present)	50%	Score: C (62%) / 31%
Output indicator 2.9. / Percentage of health committee representatives that are women	33%	Score: A (94%) / 31%
Output indicator 2.10. / Percentage of health facilities with reported stock outs of all 4 tracer drugs supplied through HPF	35%	Score: A++ (194%) / 18% (April-Jun 2018 average stock out)

Supporting narrative for the score

The health systems strengthening component of the HPF showed variable areas of achievement. Of notable significance are the roll-out of the Human Resources Information System (HRIS) in all facilities and the implementation of District Health Information System (DHIS), which will lay the foundation for stronger health systems. Progress on other areas was more limited. Nevertheless, by continuing to work mostly through national systems the programme has contributed to stabilising the health systems in the eight states where it was operating, albeit not as strongly as would have been desired, given resource and capacity constraints within the states and counties themselves.
Subdivision of the 10 states into 28 states in 2015 and then 32 states in 2016 and ongoing subdivision of counties has created additional burdens on an already weak and under resourced state subnational structure. New boundaries are often closely aligned to ethnic divisions, thus strengthening a narrative of ethnic ownership of states and counties by certain groups and stoking conflict with contests around exact borders and control of resources. This has created new pressures on the governance structure of health facilities and has provided additional pressure for resourcing and service delivery decisions not primarily based on need and balanced coverage.

Indicator 2.1: This was a cumulative indicator with most steering committees held during the beginning of the programme. There was inconsistent holding of the steering committees in the later years of the programme, which needs to be a focus of future support.

Indicator 2.2: This indicator was also cumulative from the beginning of the programme, and did not have subsequent revisions. There were discrepancies in how the state level meetings were held, and thus the data was not able to be verified. However, there is a strong likelihood that this indicator was met.

Indicator 2.3: All the counties had developed comprehensive budgets, which considered partner contributions. This indicator contributed to enhancing the central role of county health departments (CHDs) in the delivery of health services in the states. However the lack of government funding continues to limit their capacity.

Indicator 2.4: Establishment of the HRIS in all states is a notable positive achievement of HPF. This makes it possible to have a more in-depth view of the health workforce across the country and should be maintained.

Indicator 2.5: There was an incomplete coverage of supportive supervision visits conducted under the programme in the later stages. This was compounded by insecurity, but also due to the absorption of two states previously supported by USAID, which had different systems. Future programmes need to be cognisant of differing reporting and monitoring systems, and how adopting new systems can reduce the overall impact of the programming.

Indicator 2.6: The DHIS was adequately strengthened during the life of the HPF. The indicator was only narrowly missed due to stockout of DHIS tools, and the addition of new states to the HPF.

Indicator 2.7: Community health committees were set up at several facilities in the each of the states, Even though these have been set up, there is often poor publicity, and it is possible to increase the utility of the health committees to promote more positive community engagement, which should be a focus of future support.

Indicator 2.8: Meetings between the IP, CHD and facilities were sporadically held, and this indicator was grossly underachieved. There were often bilateral meetings between different parties; but it was very rare for all parties to meet. A more pragmatic governance structure at local level needs to be developed for future programmes.

Indicator 2.9: This was met; there are more than one third of health committees that have women representatives. Even though the number might seem modest, this was remarkable achievement in South Sudan. Future programmes should focus on ensuring women take up leadership roles on the health committees.

Indicator 2.10: As noted under indicator 1.7, a key success under HPF was the delivery of essential medicines across the country, minimising stock-outs and increasing the impact of the programme. A more ambitious target should have been set for this indicator given good progress. Looking ahead, accountability of IPs in rotating stock and ensuring last mile delivery will be of great importance, in order to prevent stock-outs completely.

Lessons identified

- It is possible to strengthen health systems even in fragile contexts, including through capturing programme data through HMIS. Human Resources information is more difficult to strengthen, but a functional system can be developed even in the context of weak health systems.
- Expanding the programme by adding other states had reduced the ability of the programme to fully meet some of the targets. Future programmes should ensure that these changes are factored into the design when expanding the programme.
- The programme has so far navigated well the pressures of state and county subdivision, and has resisted allocating resources in suboptimal ways. The programme has also tracked many of the conflict risks that are emerging in relation to the subdivision of states and counties along ethnic lines. In HPF3 a more structured approach to identifying conflict dynamics at subnational levels would help the programme identify and manage conflict sensitivity risks.
- In order to reduce stock-outs, and ensure essential medicines reach those requiring treatment, IPs should be increasingly held to account for ensuring last mile delivery and stock rotation, which will further prevent drug expiration.

Output Title	Increased access to nutrition services particularly for pregnant women and young children
Output number per LF		3	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Progress
Output indicator 3.1. / Number of children under five weighed and measured as part of preventative or curative consultations (total)	1,449,656	Score: A (119%) / 1,729,408
Output indicator 3.2. / Number of health workers trained on CMAM[4] and MIYCN[5] (disaggregated by sex)	2,847	Score: A (110%) / 3,137 (39% female)
Output indicator 3.3. / Number of children nutrition outpatient discharged cured six to 59 months (total)	116,557	Score: A (116%) / 135,391
[4] Community Management of Acute Malnutrition
[5] Maternal, Infant and Young Child Nutrition

Provide supporting narrative for the score

The programme fully started to support nutrition from the second phase of HPF in 2016. Despite the late addition of nutrition as an output, there were some significant successes. Through HPF, the national nutrition strategy was updated twice; and the government was supported to utilise data from smart surveys and Integrated Food Security Phase Classification (IPC) surveys in their planning. The increased focus on nutrition through the HPF led to the introduction of 9 nutrition-specific indicators in the national DHIS.

The programme carried out several training sessions of health workers at national and county level. This included finalising and printing the CMAM guidelines, and rolling out the training for health workers at state level. Additionally the programme supported the establishment of working groups at the national level, which guided the delivery of nutrition in South Sudan.

The indicators were largely met, but with significant challenges. A challenge was that there were a lot of activities that needed to be carried out in a short period of time, since nutrition was only added in the second phase of programme. The reliance on UN agencies for supplies and commodities raised some challenges in the implementation of some activities, including the availability of Ready-to-Eat Food rations for children experiencing malnutrition, which could only be provided by UNICEF.

Indicator 3.1: This was met but was very difficult to achieve due to lack of weighing scales.

Indicator 3.2: The programme successfully trained more than 3000 trainers in nutrition including trainers of trainers at state level. The training was also successfully cascaded to all HPF health centres.

Indicator 3.3: This indicator was met, but the HPF was not directly providing any supplies or commodities for treatment of malnutrition. The attainment of this output was therefore not solely due to HPF activities.

Lessons identified this year

- More linkages are required between HPF and UN agencies providing nutrition supplies. It was difficult to link HPF outputs to direct service delivery in nutrition, thus clearer supply chain channels of the nutrition commodities need to be established in future programmes.
- The nutrition strategy could be clearer in subsequent programmes. Ultimately, the HPF focused primarily on system strengthening activities, and did not support the implementing partners to directly provide nutrition services.
## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The programme’s target impact was: ‘Government led health systems that save lives’. In general, the programme’s theory of change anticipated that the Government of South Sudan (GOSS) would develop capacity over the programme period to be more involved in leading the health system. Unfortunately government capacity weakened over the life of the programme, leaving most health services reliant on international support.

The programme attempted to work as far as possible through government structures and systems, rather than supplanting them, and has undoubtedly saved lives. It was not possible to assess the impact of the programme on the reduction of maternal or infant mortality, as the national surveys of these data have not been done since 2008. However, considering the increase in the number of skilled birth deliveries and immunisation, the programme can be expected to have had a significant impact at reducing the number of women and children dying from preventable deaths. The programme’s internal calculation of statistical data further collaborates this. The statistics suggests that 2.9 million disability adjusted life years (DALY) and 37,500 deaths were averted in part due to interventions implemented in HPF2 (Nov 2016 – Sept 2018). Although attribution to HPF is very difficult in a context where there are also humanitarian health actors operating.

However, the evidence that the health system is ‘government-led’ is weaker. Government capacity to run the health system remains very limited due to the overstretched capacity in the central and local ministries of health, a greatly reduced health budget and general constraints in human resources for health. The inability of the government to consistently pay health workers has greatly impacted on the ability to run the health system. Nevertheless, HPF has improved the government’s capacity to conduct supportive supervision, conduct annual planning and the use of evidence; despite the existing constraints. DFID (and other donors) have had to adjust their expectations about the extent to which a truly government-led health service could be achieved over the lifetime of the programme, returning the focus to health service delivery, improving community governance and working on basic stabilisation activities. HPF has been able to adapt to some of these challenges and future programmes will have to consider how to support services most effectively and better track conflict sensitivity risks given the likely continued weakness in government capacity.

Summarise the programme’s theory of change and major changes to it in the past year

The programme’s theory of change focused on supporting essential health services, on the basis that improved access to good quality health services (including removal of financial, social and cultural barriers to access) has major impacts on health outcomes in particular in low and mid income countries.

During phase 1 (2012-2015) of the programme, a focus on service delivery and health systems strengthening was appropriate to strengthen the newly formed government and transition towards a national government-led health sector. However, by 2017, continued conflict and reduced government budget and expenditure on the health sector, made the transition to a government led health sector unlikely. There was therefore an increased focus on service delivery, with the programme stabilising health systems as opposed to wider systems strengthening. This led to less ambitious targets in these areas. The majority of these shifts happened prior to the last year of the programme, and as such there have no been major changes to the theory of change since the last annual review.

Explain major changes to the logframe in the past year

Changes were made to the logframe in July 2018 to reflect the recommendations of the previous annual review, to amend the end-date of the programme to September 2018 (following an agreed no-cost extension) and to ensure that all targets were clear and reflected the level of ambition DFID wanted to see.

The output changes broadly were as follows:
- Extension of all targets to September 2018
- Revisions of wording on several output 2 indicators to clarify what was needed
- Slight up-lifts of targets where previous targets were felt to be under-ambitious
- Movement of indicators to more logical outputs:
  - Output 1.8 to output 2.10 (on tracer drugs stock-outs)
  - Output 3.4 to 1.9 (antenatal clients given ferrous sulphate and folic acid)

Changes were also made to the logframe in the last year to reflect the lack of anticipated household survey data across many of the impact and outcome indicators. New impact indicators were therefore added retrospectively to best use existing data to approximate outcomes and impact across the life of the programme. The following impact indicators were therefore added:
- Couple Years Protection (CYP) - impact indicator 4
- Disability Adjusted Life Years (DALY) – impact indicator 5

Various assumptions and statistical inferences are necessary for calculating this data. Therefore they cannot accurately measure the impact of the programme, but can be used as useful proxies given the current lack of data.

## D: VALUE FOR MONEY

The programme performed positively well during its implementation consistently meeting output expectations as evidenced by good performance during the annual reviews. The VfM measures implemented during the lifetime of the programme are similar to those identified at the start. By meeting targets for the provision of health services, despite the on-going conflict, the programme can be viewed as delivering VfM in this challenging context where other programmes have been unable to continue. The conflict has made delivery more challenging and the continued reduction in government expenditure has further limited sustainability. Other donors have also invested significant amounts, especially in the last two years of the programme, recognising HPF as an efficient route to supporting health services. This has ensured that continued support was provided in 8 out of the 10 states in South Sudan, and improved efficiencies through pooling resources together for maximum impact.

An extensive VfM strategy was developed for the programme at the start of HPF2 in 2016, this was reviewed and further updated in March 2018. VfM performance was measured against available indicators in the VfM framework during the HPF2 phase. However, HPF2 finance data did not seamlessly link to the monitoring and evaluation (M&E) data that reported outputs and outcomes. It was observed that a sizable amount of outcome data was not collected directly as part of routine HPF2 M&E but relied on surveys meant to be conducted by the Ministry of Health (MoH). It was not possible to redo the economic appraisal to compare cost benefit analysis for HPF1 and 2 due to a lack of health outcomes data, which should be considered under future programmes.

Key cost drivers
The key cost drivers throughout the HPF2 programme have been staff salaries and incentives (comprising about 62% of IPs’ spend); procurement of commodities; HPF and IPs overheads (23% for Juba IP office running costs and up to 7% for IP HQs); and warehousing and distribution costs. Prior to HPF2, VfM analysis was only consisted of budgetary analysis around fund utilisation rates and direct/indirect costs.

Key cost drivers affecting input costs (economy). There have been no significant changes to the cost drivers. Health commodities (i.e. medical supplies) were procured at competitive unit costs, and supplier fees and expenses remained within approved financial limits. Overall costs were monitored monthly and any costs in excess of limits were discussed in monthly review meetings between HPF and IPs. A positive trend in VfM performance is that implementing partner support costs reduced over the lifespan of the programme by approximately 15%, allowing more funding to be directed to front-line activities.

However, the on-going conflict and deteriorating economic situation have increased costs of delivering health services over the life of the programme, particularly regarding health worker incentives. HPF2’s expansion from six to eight of the ten former States increased the number of health workers HPF supported and increased costs. Also, the costs for distributing commodities to county-level were nearly 18% of HPF2’s total procurement budget due to the need to transport freight by air into harder to reach locations (due to insecurity or poor road/weather conditions).

Cost of converting inputs to project outputs (efficiency). While it has not been possible to link expenditure directly to outputs in HPF2, the programme has been efficient in terms of maintaining coverage. The fund utilisation rate by implementing partners was on average 96% and costs only marginally increased as the conflict spread. The number of children under-5 treated rose from 1.8m per year under HPF1 to 2.3m per year under HPF2, and the amount spent by implementing partners rose from about £30m to £40m a year. The average costs per client visit varied significantly across locations, indicating the variable operational costs and contexts in the area.

Cost of converting outputs to outcomes (effectiveness). The Disability Adjusted Life Years (DALYs) averted were estimated for some of the interventions that are provided as part of HPF. A total of 2,909,648 DALYs were averted due in part to HPF interventions. The cost per DALY averted of approximately $1, 030 during HPF2 is less than the estimated $ 1,440 GNI for South Sudan in 2016. An intervention that costs less than once the annual national income is considered to be highly cost effective. In future programmes, there should be more efforts to show attribution to HPF, which was very challenging in the HPF 1 and 2[6].
[6] Threshold values of cost-effectiveness are presented in GDP per capita, international dollars for the year 2005

A calculation of deaths averted was also used to assess effectiveness. An estimated 37,497 deaths were averted due to interventions implemented in HPF. Treatment of malaria contributed the most to deaths averted, followed by oral rehydration therapy for diarrhoea, and provision of skilled deliveries .

The HPF model has also proved effective, working closely with other partners to deliver a basic package of health services. For example, family planning commodities were not directly procured by the programme, but the HPF supply chain was used to distribute UNFPA procured commodities to the health facilities in HPF supported states. Similarly, for the immunisation programme, UNICEF provides the cold chain equipment and vaccines, whilst HPF complements the delivery through providing health worker training and incentives, and supporting outreach; thus contributing to an effective and coordinated intervention.

On equity, the project targets vulnerable sections of the population, and provides free health care services which benefits the most disadvantaged in society. HPF has aimed to bring an equitable level of support in all 8 former states, through its support to hospital and peripheral health centres. There were in excess of 12 million outpatient visits from all clients to facilites supported by HPF2, in both government and opposition-held areas. The data is however not disaggregated by age or gender and therefore unable to definitively highlight the increased access of services by women and children. This will be of key focus under a new programme. The programme did however increase the number of women that are on facility health committees, therefore contributing to improving gender relations

Key Recommendations:
For future programming (in HPF3), it is imperative that the following VfM recommendations are implemented:
1. Selection of appropriate VfM indicators from the outset, including identifying appropriate surveys and sources.
2. Implementing outcome data collection tools for use across all locations which can be aggregated and disaggregated depending on the VfM analysis required. Seek to disaggregate data at the next possible opportunity.
3. Regularly monitoring VfM indicators including cost, cost per output and cost per outcome while capturing qualitative narrative on cross-cutting themes including equity.
4. For a comprehensive VfM assessment, cross-cutting themes such as sustainability, scalability and cultural acceptability also need to be assessed, as they provide critical contextual information for interpreting VfM assessments.

E: RISK

Overview of programme risk during the past year and over the life of the programme

The programme has been exposed to substantial risks due the prevailing security context in South Sudan. At the start of the programme, the risk was “medium”, but this increased to “high” following the outbreak of conflict in December 2013. The risk level has remained at “high” since then, with a change in the DFID scale, it was re-rated to ‘major’ in 2016. The level of risk in the programme still currently stands as major. The majority of the programme risks stemmed from the inherent insecurity and instability of the environment in South Sudan. The programme adapted well to mitigate the impacts of these risks, which were outside of the control of the programme. However, it inevitably had an impact on the ability of the programme to fully deliver the ‘government-led health system’ that was envisaged at the outset (see Section C).

Since the outbreak of conflict in late 2013, delivery risks related to insecurity have been high, presenting a threat to the safety of staff and facilities, assets and programme results. As a consequence, up to 20% of health facilities were non-operational at any one time. Implementing partners on the ground managed this risk as effectively as possible by operating flexibly, using mobile clinics where necessary and returning to areas once fighting ended.

Over the course of the programme, the economy was also highly unstable. High levels of inflation impacted upon health worker salaries, leading to increased absenteeism. Furthermore, the lack of resources allocated to the health sector by the government has impacted on the Ministry of Health’s engagement in the programme and ultimately meant reductions in capacity-building ambitions. This has also at times led to more difficult relationships between donors and government, further reducing government engagement in the programme.

The 2016 Presidential Decree and formation of 22 states out of the former 8, alongside increased counties and bomas to coordinate across, has also further stretched limited resources and government engagements at local level. The programme worked flexibly to ensure continued delivery without offering to fund the newly created structures given the UK and other donors do not support the new structure.

Conflict Sensitivity
Conflict presents various risks for HPF, with the programme adopting a “do no harm” approach to delivery. The programme therefore worked in both government and opposition held areas across the country and also focused on involving the community in health facility governance. While HPF has developed a system to identify, monitor, and manage conflict-related risks to delivery, and a mechanism and security network to timely track and respond to developments in the conflict environment, their approach to monitoring conflict sensitivity has remained an implicit, rather than explicit, part of HPF’s ongoing delivery and contextual analysis at all local levels.

HPF has no formal strategy to address conflict-sensitivity and has not undertaken specific conflict analyses either at national or subnational levels. Despite this, HPF has implemented a number of measures that have the effect of improving conflict sensitivity, such as using a controlled process of asset disposal that prioritises disposal to implementing partners – thus reducing the risk of subsequent use by conflict actors.

HPF’s ability to continue to deliver during periods of formal and inter-communal conflicts, without instances of protest by beneficiary communities has been evidence of the success of this approach. However the lack of a systematised approach to identifying and mitigating conflict-sensitivity risks (as opposed to just tracking formal conflict events) is a strategic weakness that increases the risk of inadvertently doing harm. Key issues to mitigate are: co-option of aid inputs, perceived or real illegitimacy of service delivery and distribution (particularly in the context of subdivision of states and counties), emerging hyper localisation demands around staffing, ‘pull’ factors of development investments, and inadequate consultation/ communication/ participation that reinforces senses of exclusion. A key recommendation is to build greater formal conflict sensitivity analysis into the programme and particularly around the selection of facilities to support under the future programme and the monitoring of non-functional facilities.

Update on partnership principles

There were no specific conditionality requirements linked to this programme, as it did not channel any funds directly to or through the partner government.

Throughout the period, the relationship between international development partners and government remained difficult in the light of the ongoing conflict and human rights concerns. There was however agreement amongst donors that basic service delivery remains an important goal and activity for donor support. Pressure on the government to allocate more resources to the health sector has not been successful, necessitating practical measures to ensure the programme can function independently should government support to the health sector decrease further.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

HPF was implemented through a fund manager- Crown Agents, who in turn engaged 16 Implementing Partners (IPs) to deliver across the 8 states. HPF also benefitted from contributions from other donors: US, Canada, Sweden, Australia and EU (see below). DFID was the lead donor as well as the administrative and technical lead for this programme.

Proportion of Donor Contribution
Donor	Amount	%Contribution
Sweden	£27,360,278.68	10.7
Australia	£16,116,866.65	6.3
Canada	£47,702,557.71	18.7
EU	£15,727,400	6.2
US	£40,407,000	15.8
DFID	£108,126,327.69	42.3
TOTAL	£255,440,430.73	100

Generally, the overall performance of Crown Agents was satisfactory, with a performance improvement plan successfully completed in 2016. While there are various areas of weakness noted below, this has to be considered in the context of inadequate resourcing of teams and acute security concerns. The key challenges in the commercial and financial delivery are outlined below.

DFID: The DFID team was under-resourced for the majority of the programme, sharing the health advisor with various other responsibilities and had only one full-time member of the programme team. In the final year of the programme, the decision was taken to recruit an additional programme manager as well as advisory staff focused on HPF. With the successor programme, there is an increased focus on staff capacity ensuring that advisory and programme management roles are properly staffed as well as pushing for increased capacity within the fund manager as well as capability to deliver such an ambitious and complex programme in a fragile state.

Reporting: A key area of weakness was that the Key Performance Indicators (KPIs) drafted in 2012 were never implemented under the programme. This limited DFID’s ability to hold Crown Agents to account on areas of underperformance. Under HPF3, clear KPIs with performance-related retentions will be of priority.

Financial Management: was raised as an area of concern in the February 2015 mid-term review. Improvements were made since then, to an acceptable level. There were errors in the forecasting and reporting that required significant input from both the donor and the fund manager before the reports reached an acceptable standard. The overall management of finances by the Fund Manager was never fully comprehensive, due to the challenges of managing this process between London and Juba; and this required continued input to ensure uninterrupted disbursements and utilisation of funds.

Narrative reporting: under the programme was generally timely, however the reports lacked in-depth analyses of pertinent issues. This will need to be of key focus under future programmes to ensure key trends are understood and to help the programme respond flexibly and allocate resources efficiently.

Risk Management: In the final years of the programme, HPF developed a risk management and monitoring framework which was reviewed monthly. HPF was able to report incidents quickly to DFID, although concerns remain in Crown Agents’ proactive identification of risks and mitigation. As noted in Section B, a focus on Last Mile Distribution and accountabilities of IPs in this regard will be of greatest focus going forward.

Asset Management: Monitoring of assets was initially under-resourced and therefore a weakness of the supplier, with irregular updates to the asset register throughout the programme. However, asset losses were reported and followed up responsibly, and by the end of the programme a full reconciliation exercise was carried out for the implementing partner assets. Given the challenges with managing the high number of assets under the programme, it was recognised that more staff time was needed and is a recommendation for successor programme- HPF3.

Date of last narrative financial report	December 2018
Date of last audited annual statement	January 2019

G: MONITORING, EVIDENCE & LEARNING

Monitoring

In addition to annual reviews, DFID also contracted an external mid-term review in February 2015 to reflect on achievements and challenges, and increase depth and independence of analyses.

Given the conflict environment, the frequency and scope of DFID field monitoring visits was more limited than desired across the programme period. The ability of the DFID team to travel fluctuated over the programme period, but reduced severely during and after the July 2016 evacuation. Visits increased in the later part of 2018. When visits were conducted, they were mainly limited to urban areas in relatively stable parts of the country, thus not fully representative of the programme.

DFID contracted REACH, an external agency, to conduct short-term third party monitoring in 2017. This evidence was used to inform programme discussions with the partner, particularly around the issues of health worker salaries variations across the country, and also in the design of the successor programme (HPF3). Other donors (such as Canada and USAID) and partners (such as the WHO, MSF) also shared feedback directly with the HPF team and with DFID following visits. Under HPF3, a dedicated Third Party Monitoring (TPM) facility will be established to verify data, map development and humanitarian health services across donors, and provide a technical review of health service functionality data with.

Evidence

The programme largely relied upon the nationwide health management information system (HMIS) for evidence against outputs. The use of routinely collected HMIS data reduced the efforts of duplication of sources, and was therefore considered the most efficient way of measuring the progress of the programme. However, this did at times compromise the quality of evidence, as it relied on health facility workers to input data correctly. The HMIS is also not disaggregated by gender, further limiting the analysis on inclusiveness. DFID will continue to lobby for the re-introduction of disaggregation in future to improve the evidence generated. Finally the use of the national HMIS system does not allow precise attribution to the HPF specifically, but shows improvements in the wider health system that HPF supports. Partners do also monitor and report service availability directly on a quarterly basis.

Nationwide surveys were expected to be conducted that would have generated useful evidence, particularly relating to outcomes and impacts of the programme. However, these were not conducted due to security and other concerns, thus making it difficult to assess the programme’s impact.

Given some of these challenges, DFID contracted a process evaluation to be conducted in 2018. This looked at the whole 5 year HPF1 and 2 programme, and was conducted through a desk review, interviews and a field-based research segment. This used the data that was available to provide more evidence and assurance to DFID that the programme was performing well, and additionally generated recommendations to inform the implementation of the successor programme HPF3.

Learning

A key learning from the programme has been the acceptance that efforts to build a government-led health system has only been marginally successful despite efforts, particularly in HPF1, to support this. This has been due to the decision of the Government not to prioritise support for the sector along with the economic crisis. Until the Government starts to allocate significantly more resources to the sector (the 2017/18 budget was just $7m), future interventions should focus on ensuring services are delivered to the population as effectively as possible, rather than attempting to build government capacity.

DFID has been investing resources over the past year to try and capture lessons from this programme to ensure that the design and implementation of the successor programme takes these into account. Examples include:
- Commissioning internal analysis from HPF regarding incentive payments to health worker staff. This has been used to commission wider external research about incentives across the whole South Sudanese health sector to inform harmonised HPF3 rates.
- HPF looking into variances in consultation rates across the country to identify areas for prioritisation under HPF3.
- Integration of community-level health service delivery, subsuming DFID’s Integrated Community Case Management (ICCM) programme and the government’s Boma Health Initiative under HPF3 for maximum impact.

A key lesson identified from these processes has been the vital importance of using and refreshing evidence to drive programme design. A mixture of analysis and strategic direction from the fund manager, added to local knowledge of implementing partners, will create a better designed programme.

Progress on recommendations from annual reviews for this programme

Previous recommendations have been taken forwards on an annual basis. The programme adapted to recommendations over time, with the re-design under the HPF2 extension representing the biggest change. The below focuses primarily on the recommendations from the 2017 Annual Review.

- Last mile delivery was strengthened under HPF2, but much more stringent controls have been built into contracts with the fund manager and implementing partners under the HPF3 bridging period to ensure increasingly robust management.
- New outcome/ impact indicators were developed and used retrospectively to measure impact of HPF2, and options are still being discussed to improve this measurement under HPF3.
- The UNFPA supply chain has been merged into HPF distribution as far as possible; with UNFPA commodities being included in the HPF distribution chain if they are able to provide stock within timelines.
- DFID is funding research into incentive payments as part of HPF3 inception to inform decision making in this area.
- The HPF team has implemented new tools and guidance to strengthen noted weaknesses (including under pharmaceutical utilisation data, social mobilisation training, and VfM strategy).