Type of Review: Project Completion Review

Project Title: Bihar Governance and Administrative Reforms Programme

Date started: September 2008	Date review undertaken: 6-8 May 2014

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
DFID provided £13 million in financial aid to the Government of Bihar to design and implement governance and administrative reforms in two phases of three years each (2008-2014), and £5 million in technical cooperation to procure Technical Assistance to support reforms prioritised by the Government of Bihar.

What were the expected results?
As a result of the programme interventions, the quality of governance was expected to improve in Bihar. This was anticipated to reflect in the improved capacity of the government to deliver public services, mobilise more revenue and build institutional capacity. This assessment was to be based on an independent citizen feedback and other independent sources. / The main programme outputs expected were: / Quality of human resource management viz. recruitment, training, performance management to be more efficient and effective / Performance of focal Departments made more effective, efficient and accountable / Strengthened district level administration and service delivery

What was the context in which UK support was provided?
Bihar is one of the poorest states in India, accounting for over 13% of the country’s poor. In 2005, it ranked at the bottom of Indian States for a range of governance indicators including law and order, corruption, legal structure and security of property rights, revenue collection, and investment climate. There were systemic weaknesses such as out-dated administrative functions, poorly managed, demotivated and low skilled workforce with large number of unfilled posts; and weak accountability at all levels. Since 2006, the government of Bihar demonstrated a real intent to improve governance and there were significant improvements in law and order, financial management, accountability of public institutions, and delivery of public services. Through this programme, DFID supported the Bihar Government to undertake governance reforms for improving its capability to deliver better quality services to all its citizens, particularly the poorest and most excluded. / DFID provided financial assistance to the Government of Bihar through a dedicated Mission set up for undertaking administrative reforms in the state. This was likely to enable the government to improve its human resource management, develop stronger institutional capacity and enhance quality of public service delivery, particularly at the frontline level. / The technical cooperation funds were to contract a technical support team that provided technical assistance to the Government of Bihar on prioritised reform areas

## Section A: Detailed Output Scoring
Output 1: Quality of human resource management viz. recruitment, training, performance management is more efficient and effective.
Output 1: Final score and performance description: A+ (Outcome substantially exceeded expectation) / Indicator Score / Indicator: Proportion of vacancies against currently sanctioned strength for Bihar Administrative Service (BAS), Bihar Financial Service (BFS) and Bihar Registration Service (BRS) cadres A+ / Milestone (EoP 2014): Less than 25% (Baseline ~ 50%) / Milestone status: The table below presents the sanctioned strength and the posts filled for the three cadres. The overall vacancy is around 18% as on May 2014. / Related Interventions / A number of interventions can be linked towards directly influencing the milestone under this indicator. These interventions are as below: / The restructuring study of BAS under BGARP recommended raising the entry level of a BAS officer. General Administration Department (GAD) agreed to the recommendations and issued a resolution (Annexure 1) for restructuring the cadre. Based on the same the following actions were taken by GAD / The entry level of a BAS officer be upgraded from that of a Block Development Officer (BDO)/ Circle Officer (CO) to Sub-Divisional Officer (SDO), leading to a decrease in the sanctioned strength from 2878 (pre-restructuring) to 851 (Post-restructuring). Therefore, in terms of actual strength, the pre-restructuring vacancy of over 50% against the sanctioned positions disappeared resulting in surplus officers. To accommodate the existing surplus strength, GAD sanctioned creation of 262 temporary positions vide the circular no. 3983; dated 3rd May, 2010 for a period of three years. / In addition to the surplus, 167 new BAS probationers were recruited based on the 48th to 52nd combined examinations by Bihar Public Service Commission (BPSC). These examinations were under process prior to the restructuring. To accommodate these probationers, GAD sanctioned additional 170 temporary positions vide circulars no. 8487 dated 30th August, 2010 for three years. / The duration of the total 432 (262+170) temporary positions, renamed as floating posts, were further extended for a period of another 3 years vide the circular No. 14187 dated 30th August, 2013 (Annexure 2) / The Functional Review of Registration Department (cadre controlling department for BRS) recommended filling up the vacancies in the cadre. Hence for the BRS cadre, with the selection of 56 probationers by BPSC in August 2013, the final vacancies have reduced to 3%. / The Functional Review of Commercial Tax Department (cadre controlling department for BFS) recommended filling up the vacancy in the sanctioned position of the BFS. Based on the same the department: / Sanctioned additional 258 positions over and above the existing 525 position, vide gazette notification no. 470 dated 19th June, 2013, (Annexure 3) resulting in total 783 numbers of sanctioned positions. Of these 313 positions were filled (40% posts filled). / Indicator Score / Indicator: Training of BAS, BFS and BRS Officers A / Milestone: All BAS probationers and 80% in-service BAS, BFS and BRS officers given training as per new training plan. / Milestone status: / Induction Training: All the 170 BAS probationers (48th to 52nd batch) have been provided induction training as per the new plan / In-service training: / As on May, 2014 of the actual strength (1235), about 570 BAS officers are eligible for in-service training (officers who are above the age of 55 years and those who have completed less than 6 years of service are not considered for the training). Of these, till date 200 BAS have received in-service training from reputed institutions (such as Administrative Training Institute, Gurgaon and Administrative Staff College of India, Hyderabad) in the country as per the new training plan. This forms about 35% of the total target (570). The details of the BAS batches sent/ planned to be sent for training are given as follows. / There are around 220 BFS officers who are eligible for in-service training. About 119 personnel have already been trained and the process is underway to send another 20 to be sent to be trained as master trainers to be trained on GST by end of June. / Around 74 BRS officer are eligible for in-service training. Till date, all the officers of the department have undergone in-service training in BIPARD or in reputed training institutions outside Bihar. / The table below gives the total personnel trained from the BAS, BFS and the BRS cadre as per the new in-service training plan: / Table 1: Sanctioned and filled positions for BAS, BRS and BFS (as on May 2014) / Cadre Total number of officers eligible for in-service training Number of officer actually trained or proposed to be trained % of target trained / BAS 570 235 41% / BRS 74 74 100% / BFS 220 139 63% / Total 864 438 51% / Thus in terms of induction training the milestone has been achieved. In terms of in-service training about 51% of the eligible officers have been trained or a proposed to be trained within end of project. / Related Interventions / New Induction Training for BAS Probationers: / The BAS restructuring note emphasised on the need to revise the induction training plan for the probationary BAS officers. The recommendation comprised increasing the training period, contemporizing the training syllabus to reflect the modern administrative priorities and inclusion of a best practice visit to other states. Based on the recommendation, GoB issued the new Induction training vide circular dated 6th October 2009 (Annexure 5.5) whereby the period of training has been increased to 80 weeks (24 weeks institutional + 6 weeks Bharat Darshan + 50 weeks field training) from the existing 70 weeks (18 weeks institutional + 1 year field). / Inputs and development of Training Plan: / The need for phase wise in-service training has been recognised in the BAS restructuring note. As a precursor to the preparation of the in-service training plan, a Training Need Assessment (TNA) exercise was carried out for all BAS officers. Based on the input in-service training plan was proposed. The Plan proposed three modules of training based on no. of years in service viz., M1 (for those with 6-10 years of experience), M2 (for those officers with 11-15 years of experience) and M3 (for those with 16-20 years of experience). Training has now been mandatorily linked with promotion at each level. The Training plan was accepted vide GAD issued circular no. 8770 dated 8th August 2011 (Annexure 6). / Similarly a Training Need Assessment (TNA) was carried out for both the BFS and BRS cadre officers to identify training needs of the gazetted and non-gazetted officers of the department. Based on the findings a training plan was designed for both the cadre officers / Indicator Score / Indicator: Proportion of appraisal reports for BAS officers which are initiated and accepted every year A+ / Milestone (EoP 2014): 100% of the officers complete self-appraisal using the new Performance Appraisal Form (PAR). / Milestone status: The milestone has been achieved. As of date 100% of the officers complete self-appraisal using the new PAR form. However, with a manual system, 100% compliance of the timelines is difficult to be enforced. GAD has recently introduced an online PAR system for the IAS. A similar system may be envisaged for the BAS which might facilitate time-bound completion of PAR process. / Related Interventions / The BAS restructuring note recommended the transition of the existing process of appraisal for the BAS officers, from the existing single page Annual Confidential Report (ACR) to a more comprehensive PAR. / GAD accepted the recommendation and institutionalized the new PAR for BAS officers vide circular no. 12980 dated 3rd December, 2009 (Annexure 7). In addition the circular informed of the decision to develop similar PAR format for other premier services such as Bihar Police Service, Bihar Financial Service, Bihar Health Service, Bihar Engineering Service and Bihar Veterinary Service / As a further attempt to enforce the new PAR, GAD issued a circular no. 17121 dated December 14, 2012 (Annexure 8) with all the BAS officers required to fill their self-appraisal in PAR formats with the following timelines: / Completion of self-appraisal- By 30th April / Completion of review/ acceptance- By 30th September / Other interventions / An outcome of the interventions made under this output is the adoption of a comprehensive State Training Policy in 2011 (Annexure 9) for all government staff wherein training has been mandatorily linked to promotion and a specific fund equivalent of 1.5% of the salary budget was mandated for all the departments. / Governance Technical Assistance Support Team (GTAST) facilitated a pilot behavioural & technical training of 90 Group D staff in the secretariat. Based on the learnings, a concept note was developed and procurement support was provided by the project for conducting a behavioural & technical training of all the Group D staff (about 52,000 frontline staff estimated). Till April 2014, about 28,000 staff had been trained on basic communications relating to interacting with citizens, developing a positive attitude and technical training related to photocopying, filing records etc. Feedback revealed an increase in technical knowledge by over 50% and over 20% reporting positive change in behaviour. / New PAR forms recommended for BAS career appraisal has now been adopted for other state cadres like Bihar Police Service (BPS), Bihar Agricultural Services Officers, and Bihar Secretariat Services (BSS) as well. / A revised syllabus for the mandatory departmental level examination leading to service confirmation for the probationers of IAS & BAS cadres was proposed by the GTAST. The syllabus was last revised about 40 years ago and there was a need to contemporize it in line with modern administrative priority. The Central Examination Committee, Board of Revenue accepted the syllabus recommended vide letter no. 1363 dated September 30, 2013 (Annexure 9.5) / Technical inputs were provided for implementation of 2nd Administrative Reforms Commission (ARC) recommendations in Bihar. The support was provided for categorization of recommendations and for preparation of action taken reports. This also facilitated the meeting of State Committee on ARC recommendations leading to adoption of the categorizations and follow-up actions to be taken by the concerned departments. / Conducted functional/organisational review of Bihar Institute of Public Administration and Rural Development (BIPARD); development of training handbook and designing trainee’s manual. / Supported setting up of Centre for Good Governance (CGG),developing the initial concept note, drafting the Memorandum of Association, byelaws and developing the required manning levels; developed Vision/Mission, HR Plan, Procurement & Operation Manual for the operation. The CGG has been formed based on resolution no. 12670 dated 22nd November, 2011. Total 88 positions have been created with annual budget of Rs.3.81 crore has been approved by GAD vide the letter no. 11161 dated 8th August, 2012 to the Auditor General. / Final results: / The overall vacancies in the state reduced to 18% from the baseline of 50%. The achievement surpassed end of project milestone of halving the vacancies (25%). The cadre wise detail is tabulated as below. / Table 2: Sanctioned and filled positions for BAS, BRS and BFS (as on May 2014) / Cadre Sanctioned Strength Posts Filled Vacancies % vacancy / BAS 1283 1235 48 - / BRS 149 144 5 3% / BFS 783 411 372 48% / Total 2215 1790 403 18% / All BAS probationers underwent induction training. However, against the target of 80% coverage of staff from various cadres for in-service training, only 51% could be trained. / The new Performance Appraisal form has been made mandatory and 100% officers use the new form for their appraisal. / Impact Weighting (%):40% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 2: Performance of focal departments is made more effective, efficient and accountable.
Output 2: Final score and performance description: A (outcome met expectation) / Indicator Score / Indicator: Systems for enhancement of tax revenue A+ / Milestone (June 2014): No. of registered dealers (Commercial Tax Department) reaches 2,50,000 / Milestone status: This milestone has been achieved and the total number of Dealers registered has crossed the 2,50,000 figure as on April 30. As on March 2014 the number of registered dealers was 2,46,418 (growth of over 28% from last year when there were 1,91,967 dealers) The revenue of Commercial Taxes Department (CTD) during the same period grew at 21%. Table below summarises the revenue mobilised by CTD that can be directly attributed to BGARP interventions. / Revenue in FY14 in INR and Growth over FY12 (CTD) Impact due to interventions Related interventions Additional revenue generated (INR) in the review period Remarks / Rs. 13150.76 Crores (FY 14) / CAGR of 25% (Rs. 8,458 crores) over FY12 25.03% Enactment of “The Bihar Tax on Professions, Trades, Callings and Employments Act, 2011”. Rs. 126.79 Crores The impact was directly for BGARP intervention during the review period / Streamlining of check-post management practices. Rs. 1047.70 Crores This intervention also includes augmentation of infrastructure at the check-posts by the department and implementation of check-post management system. / Grand Total Rs. 1174.49 Crores (£ 117.44 million / Related Interventions / A number of recommendations were incorporated in the Departmental Functional Review for the CTD related to dealer facilitation and dealer registration & monitoring to widen tax base. Key recommendations such as introduction of e-registration services for dealers and citizen charter for department and time standards have been successfully implemented by the Department. Technical Support was also provided during introduction of e-services like e-payment, e-return, online issuance of statutory forms etc. which has helped in widening the tax base. / Other Interventions with Commercial Tax department / One of the key recommendations in the functional review of CTD was to set up checkposts at all the important exit/ entry points into the state of Bihar. The Department accepted the recommendation and initiated efforts to develop an integrated Checkpost, to not only house the CTD checkpost but also the checkposts related to the other departments who maintain their presence in these entry/ exit points such as CTD, Environment & Forest, Transport, Excise and Mining departments. With the functioning of CTD checkpost, there was an additional revenue generation of £ 46 million. / With the setting up of Integrated Checkposts, GoB decided to enable an apex institutional arrangement to ensure coordination between the various departments who would maintain their presence in the new integrated checkpost complex. GTAST provided technical inputs in the formulation of “The Bihar Integrated Checkpost Authority Act, 2011” and draft Rules “The Bihar Integrated Checkpost Authority Rules, 2011”. Both the Act and rules have been notified by GoB. The legislation has streamlining of management of the integrated checkposts. The integration of the different checkposts, which used to be located at separate locations in the prior arrangement, has resulted in a significant saving in time for the goods vehicles entering the state. Compared to the earlier arrangement where it took 7-8 hours for each vehicle to get the requisite clearances separately, the integrated checkpost enables the vehicles to get all the clearances from a single point within 1-2 hours. / Technical inputs were provided in the formulation of “The Bihar Tax on Professions, trades, callings and employments Act, 2011” to provide for the levy and collection of profession tax etc. in the state by CTD. The new tax head has generated £ 4 million till date. / A VAT Commodity Analysis study was conducted to compare VAT rates on all scheduled goods in Bihar with that of rates in select states i.e. Gujarat, West Bengal, Uttar Pradesh. Based on the findings of the study, CTD had revised the rates of few commodities to end the trade diversion and increase revenue / Reviewed central Sales Tax (Bihar) Rules, 1957 with recommendations for its modifications with focus on proposing enabling rule for online issuance of statutory forms. CST Return Forms used by dealers for reporting purposes were also revised reflecting the best practices from other states / A concept note on Tax Research Unit (TRU) was developed and handholding support was extended to establish TRU with the objective of supporting the department in conducting research on tax structure, tax collection methodology, changing trade practices, evasion and frauds etc. and on issues having impact on the collection and administration of the commercial taxes. Based on the recommendation, a TRU was set up and made functional / Developed a draft VAT Audit Manual with an objective to streamline audit processes of CTD and reflecting modern audit practices / Conducted a rapid cross-verification of sales and purchases declarations of the VAT taxpayers who have availed input VAT credit to identify areas of non-compliance/ tax evasion by dealers and identify scope for improvements / Submitted a report on Commodity Classification based on Harmonized System of Nomenclature (HSN) / Reviewed VATMIS Reports and suggestions for restructuring the same / Milestone (June 2014): Revenues generated by the transport department = £ 70 million / Milestone Status: With a revenue realisation of £ 83.5 million by the department in FY 2013-14, the milestone has been achieved. / Related Interventions / The main initiative for the department involved rationalising the tax structure as levied by Bihar Motor Vehicles Taxation Act. Most of the recommendations for personal vehicles and commercial vehicles were accepted, including rebates for battery operated vehicles and multi-axle vehicles, provision for green tax etc. vide amendment to the act as per gazette notifications No. 258 dated April 9, 2010, No. 119 dated April 1, 2011, No.129 dated March 31, 2012 and No. 261 dated April 1, 2013. / Transport Department recorded a total tax of £ 83.5 million in FY 14 (Budget Estimate) (source: Transport Department) which accounted for a year on year growth of 25% over FY 13. The revenue was growing at a CAGR of 5% per annum over the period 2005-06 till 2009-10. However from 2009-10 the revenue has been growing at a CAGR of 23% per annum over the period 2009-10 till 2013-14. Thus additional revenue of over £ 80 million over the period can be attributed to the interventions (shown in the figure below). There were no new intervention for the Transport Department for FY 12 and FY13 but the benefits of earlier reforms continue. / Milestone (May 2014): GoB funds digitisation process across all districts from its own sources / Milestone Status: Taking cue from the success of the DFID funded digitization initiative in Patna, the department initiated digitization of all registered documents across the state funded by GoB. Till date, out of an estimated 6.5 million documents in the rest of the districts in the state, about 28% (1.81 million) documents have been scanned. Overall about 32% of all registered documents in the state have been scanned and uploaded. Thus the milestone of GoB funding the registration in the state has been achieved / Related Intervention / Digitization of records is one of the key recommendations in Functional Review of Registration Department. The recommendation was accepted and it was decided to procure services of a vendor for a pilot initiative of digitization of all records in Patna District. GTAST supported the department by developing a concept note followed by support in drafting the documents to support the procurement of the vendor services. Thus the digitization of records initiative was initiated for Patna District initially from the Financial Assistance and till June 2013, £ 384,000 were spent from FA funds. For the Pilot project, out of a total of 0.413 million documents in Patna district, 100% have been scanned and uploaded. Of these over 75% of these records have been indexed / Other Interventions with Registration, Excise and Prohibition department / Registration Related Support:- / Comparative study of Registration duties and levies in select Indian states / Impact Assessment of revision of Registration and Stamp duties / Rationalize the process of fixing of Minimum Value Rates (MVR) / Assessment of differences between MVR for Registration and transaction price / Conducting a detailed functional review of the Department leading to: / Decentralization of Registration process for Societies / Amendments to Bihar Registration Service Rules allowing 100% recruitment through competitive examination / Organization realignment through filling up of key post such as AIG, IRO & SR/ Jt. SR / In-service training calendar for registration officers developed / Best Practices Study - Study tours by senior Registration Department officers to Maharashtra, Karnataka, Tamil Nadu and Andhra Pradesh / Recommendations for strengthening Audit & Inspection function submitted to the Registration Department / Concept note on ‘May I Help You’ booth for citizens at Registration offices / Excise related support:- / Comparative study of Excise duties and levies in select Indian states which led to the department revising the excise duties from January 2013. Based on the study on impact assessment of revision of Excise duties and levies, conducted separately for the department, it is estimated that the new duty/ fee structure contributes to about 19% more revenue over and above the revenue generated in FY13. Thus of the total increase in the revenue of £ 74.1 million, about £ 14 million (19%) can be attributed to the interventions under BGARP. / Indicator Score / Indicator: Delivery of social sector services A / Milestone: Online monitoring Systems in Monitoring of centrally-sponsored adult literacy programme for Education Department / Milestone Status: The milestone has been achieved. The PMU has successfully managed the mahapriksha (large scale literacy assessment drive by education department) related data on the online monitoring system for Saakshar Bharat sponsored by GoI. / Related interventions / Under BGARP, Education Department was provided technical assistance in creating a comprehensive database of about 34 lakh adult neo-literates under state sponsored adult literacy scheme, Mukhyamantri Akshar Anchal Yojana (MAAY). The data captured indicated significant achievement in cognitive abilities. About 66% of the neo-literates could read small sentences while 89% could write their names and 59% could perform simple additions. / Recognising the success of the MAAY, GoB requested Programme Monitoring Unit (PMU) support under the BGARP for Saakshar Bharat (centrally sponsored flagship adult literacy scheme). / Under Saakshar Bharat, as a prerequisite to actual learning activities it was mandated that literacy levels of the target population be assessed through an Examination (“Mahapariksha”) and properly recorded as baseline. The PMU team developed an in-house software “Saakshar Bharat Examination Process Monitoring and Management Information System” under Basic Literacy Examination for Government of Bihar to enable capturing of registration records of 41 lakh participants and test paper evaluation records of 36 lakh participants who actually appeared for the examination. The software has 2 modules for “Registration entry form” and “Marks entry form” along with MIS features in form of data tables and graphical representation (data entry status, examination results, gender profile and social profile). / Also, for accessing the central government fund under the programme, the household survey and other related records were to be uploaded on the central portal of Saakshar Bharat www.saaksharbharat.nic.in of GoI. The IT team prepared software patches for checking the data being entered & completing the data validation and provided troubleshooting support to all districts of Bihar. This led to successful uploading of the data on the central portal. Similarly, online authorizations had to be created at state, district, block and GP levels for accessing web-based fund flow in which PMU team lent technical assistance for facilitating the same. / Other interventions: Education / Documentation of inspirational experiences of gender empowerment of girls/ women in different walks of life belonging from disadvantaged sections was carried out and published in form of diary/ booklet. / This was inaugurated by Chief Minister on the centenary year celebration of the State in March 2012. / Developed an MIS for Kasturba Gandhi Balika Vidyalaya (KGBVs) and Residential Bridge Course under Sarva Shiksha Abhiyan. / Milestone: System for monitoring delivery of scholarships (SC/ST Welfare Dept) - Roll-out of Integrated monitoring system for scholarships / Milestone Status: The Honourable Chief Minister, during his review of the Education Department on December 17, 2010, (Minutes of the meeting provided under 2nd point, page 2 of the Annexure 10.5) decided to bring all scholarships under education department creating an uncertainty on the ultimate owner of the SC & ST scholarships. Hence the department is yet to take a final call on roll out of the MIS. / Related Interventions / Technical inputs were provided for developing a system for monitoring delivery of scholarships. A web portal to automate different processes related to receipt of scholarship application, verification, proposal preparation, sanction and its distribution for Bihar State was developed by Madhya Pradesh NIC with support under the programme and submitted to the department vide their letter dated October 12, 2012 (Annexure 10). / Indicator Score / Indicator: Quality of Police Administration B / Milestone: Sensitisation Training of police workforce imparted to 25% of the frontline police personnel and GoB institutionalises the training programme. / Milestone Status: The milestone has been partly achieved. 3500 police personnel have been trained (7% trained, universe of 50,000) so far. Based on a recent order from High court on a need for sensitization of the Police Force, the Police training has already initiated institutionalization of Maitri. However, the process of institutionalization which includes issuance of an appropriate government order and allocation of finances is yet to be completed. / Related intervention: An image sensitization training ‘Maitri’ targeted all the frontline Sub-Inspectors and constables. The training was to be carried out on a Training of trainer basis and a total 120 Master trainers have been trained from April to July 2012. / Maitri was being coordinated across the state by the Bihar Police Academy. Till date around 3500 police personnel were trained by the Master Trainers across the state / A feedback session was carried out of about 40 trainees trained under Maitri. The Feedback on Maitri training content revealed high level of Relevance and Implementability of ideas. Also appropriate speech and behavior had gone up by 30% as per the feedback indicating transfer of learning in to action on the field. / The Maitri roll out at the field was being coordinated and championed by Bihar Police Academy (BPA) under the leadership of the erstwhile Director. However the training in the districts has significantly slowed down mainly due to change in leadership of the BPA and the prioritization of ongoing and separately budgeted National Disaster management Training. / The State Police Board, has requested for a presentation from GTAST on Maitri vide letter no. 7 dated May 7, 2014, (Annexure 11, page 3, Agenda 2) to decide on the next course of action, including institutionalization of the training / Note: DFID support was to the extent of about £ 16,000 under TA under which Training of the Master Trainers under ToT mode was held. The rest of the training is being conducted by the Bihar police with the infrastructure and logistics support provided by the District SP office. / Other Interventions: / Police / Conducted a Gender Sensitization Training for about 300 probationers comprising Dy. SPs, Sub-Inspectors and Constable undergoing training at the Constable Training School (CTS), Nathnagar / Home Department / Categorization of records is an ongoing activity with about 40,000 files categorized till April 2013 (accounting for over 50% of total files in the department). Files marked as ‘A’ and ‘B’ being moved to the new Record Room. Totally 14,000 files from the category ‘C’ destroyed creating space in the department. / Developed a software application for indexing and locating of files in the compactor developed and deployed in the Record Storage Room. The Application has additional feature to track the movement of files from/into the record room. Ongoing entry of about 6000 file information classified as belonging to ‘A’ and ‘B’ category and subsequent storage into the Compactors ongoing with about 6000 file details entered and kept in the compactors / Application to support the digitization of ACRs for IPS and BPS officers / Application developed and deployed with the department and ACRs for the BPS officers being scanned and uploaded into the database by the department. / Supported State Police Board in Identification of Indicators for performance assessment of State Police / Conducted a diagnostic study of the process followed in both the above cases with analysis of cases of denial of request for character Certificate in Patna SSP office to identify and categorize the key reasons. / Developed a Human Rights Case Tracking software application to monitor and expedite Human rights cases. The application has been installed in Home Department, and is accessible over SECLAN. The application supports a Dashboard to flag cases pending beyond a certain period for the department to take corrective actions and expedite the same. / Indicator Score / Indicator: Prison reforms A / Milestone: Revision of the Bihar Jail Manual, seek cabinet approval and assist GoB in implementation of prison reforms across prisons in Bihar / Milestone Status: The Milestone has been successfully achieved. The new Jail Manual is enforced and various components of the revised manual are being implemented across the state. / Related Intervention / BGARP played a pivotal role in revising the Bihar Jail Manual which was last revised in 1914. The Bihar Prison Manual 2012 (http://home.bih.nic.in/Prison_index_english.htm) has been enforced across the state vide Notification dated December 12, 2012 (Annexure 12). As a next stage of support our GTAST facilitated the implementation of the provisions of the new manual. The figure below describes the select provisions introduced in the new manual, their status of implementation and the role of BGARP in the same. / Table 3: Select new provisions in the Revised manual and their implementation / Chapter Chapter heading and select New provisions Status of implementation BGARP Role in implementation / 1 Introduction / Jail inspectorate renamed as Prison and Correctional Services Inspectorate Implemented from the day the manual has been enforced Developed awareness on the provision through an orientation training on the provision of the new manual for all prison officials / 2 Definitions / Provisions of Open Jail in line with the existing Bihar Open Jail Rules 2008 Open Jails already operational in Buxar. Inclusion of the provision has facilitated their management / 5 Admission of prisoners / New Prisoner management information System PMIS implemented in Beur Prison, Patna on a pilot basis / 7 Maintenance of Prisoners / Revised Diet Scales, non- reusal of clothings, special diet for pregnant ladies and children below 6 years / Mess committees and monitoring of kitchen and food being cooked (Annexure 13) Implemented across all the prisons / Various committees formed in all the prisons. Close circuit cameras installed in strategic points in kitchen and dining room in Beur / 8 Medical Care / Provision of specialist doctors / Medical camp Implemented across all the prisons / 9 Welfare, Vocational Training & Work Programmes / Recreational Activities and other welfare activities Bandi darbar in all prisons (Annexure 13) / A Grievance Redressal mechanism for prisoners in all prison (Annexure 14) / Complaint boxes for Prisoners (Annexure 14) / Weekly meeting of the prisoners with the Superintendent (Annexure 14) / Recreational facilities in Beur such as Canteen, library, training for music, / Yoga, Gymnasium / Interactive prisoner information kiosk Kiosk started in Beur / Vocational Training & Work programme Bakery Plant operational in Beur / Textile industry operational in form of a textile manufacturing plant and as handloom units in almost all prison Procurement support for modernization of Bakery Plant / Developed a detailed project report for modernizing the textile industry in Bhagalpur using services of an expert / 20 Female Prisoners and Children / Creche system for children within prisons / Visit of children outside prison Initiated in Beur prison Awareness through training / 28 Chapter 29 (Part II): Staff Development Bihar Institute of Correctional Administration being constructed GTAST suggested the Organisational structure, courses and staffing based on a benchmarking study / Indicator Score / Indicator: Enhance efficiency of Industry Department A / Milestone (2014): IT enablement of investor interface with Industry Department and for Monitoring the Progress of Investor Applications / Milestone status: The Department proposes to receive all applications online. Presently on an average around 40 investment applications are received for SIPB clearance in a month. / Related interventions / Provided procurement support to the Industry Department for selection of a vendor for the development of the Integrated Web-Based Application for Online Filling and Tracking of SIPB Approved Investment Proposals. / Monitored the development of the “Integrated web-based application for online filling and tracking of SIPB approved investment proposals” and assisting the Industry Department in suggesting functional changes in the web application / The Web-Based Application was completed and launched in 30th December 2013 (http://182.18.160.245/registration). The figures below presents the screen shots of the login and a dashboard presenting the overall status of the applications filed / Figure 2: Screenshot of the login for the Online application for filing and tracking SIPB applications / Figure 3: Screen shot of the Dashboard for the Online application for filing and tracking SIPB applications / Other Interventions for Industries Dept.: / Identification of regulatory, institutional and process level interventions required including review of organization structure and manpower deployment for strengthening the Single Window Clearance Mechanism (SWCM) for investment facilitation in Bihar. / Conducted review of the current and proposed role for organization strengthening of the 38 District Industries Centres in the state involving assessment of availability of manpower and the capacity of the same for discharging mandated functions, key processes and related automation levels involved, availability of physical infrastructure, existing mechanism for monitoring the functioning of DICs etc. Based on recommendations from the review, significant improvement in the DIC office infrastructure & IT infrastructure has taken place by way of providing basic facilities like chairs, fans to all the DICs, ensuring the functionality of computers, photo copiers & printers, providing all the GMs of the DICs with laptops & data cards etc. Substantial progress has been witnessed in terms of process related efficiency across DICs and headquarters is currently receiving all the monthly reports in a timely manner. / Development of a Web Based MIS Application for Reporting from the DICs / The web based MIS application is functional from March 2014 and can be viewed at http://dicmis.bihar.gov.in/ / Extensive post implementation support in terms of capacity building of officials from the Industry Department has been undertaken / Detailed User Manuals for the head office users and for the district users have been provided / As on 23rd May 2013 there have been 19601 entries made into the system across 38 districts for the month of May 2014. / Time taken for reporting of monthly progress of various schemes and activities undertaken at the district level has been reduced by over 80% / Capacity Building of Staff from Industry Department / Conducted Training Need Assessment & developed Training Plan for officials from the four Directorates - Industry, Technical Development, Food Processing, Sericulture & Handloom / Developed a detailed Training Plan for the officers and staff at the District Industry Centers and facilitated coordination with national training institutions like NIMSME, Hyderabad, MCRHRD Hyderabad. In line with the recommendations, the Department has sent 8 General Managers / Project Managers from the DICs for Cluster Development Program at NIMSME, Hyderabad in May 2014. Additionally, the Department proposes to send around 77 IEOs/ JSAs for a month long orientation program to NIMSME Hyderabad in June-July-August 2014. / With a view to initiate double entry accrual based accounting system (DEAS) across DICs, Finance & Accounts training has been imparted to 40 accounts personnel from the District Industry centres, which has enabled the Industries Directorate to move from single entry based accounting to TALLY based DEAS / With a goal to move from paper based administration to computerized system and to increase the general computer awareness of the DIC staff, a training on Computer Basics was imparted to 105 UDCs/ LDCs/ Stenographers / Typists from the District Industry centres, between 19th – 28th May 2014. The average score attained by the trainees was around 80% & has resulted in significant improvement in computer literacy for DIC staff. / Figure 1: Trend of Revenue collection for Transport Department
Final results: / BGARP interventions with Commercial Tax; Transport and Registration, Excise and prohibition Departments of GoB resulted in enhanced revenues for the state. Revenue amounting to £ 214 million (Rs. 2149 crore) mobilised by the three departments in 2013-14 could be directly attributed to BGARP interventions. / Online monitoring systems for monitoring of centrally-sponsored adult literacy programme was developed for the Education Department and it is fully functional and institutionalized. / 3500 police personnel were trained using Maitri module (on citizen centric policing) developed through Technical Assistance under BGARP. An assessment of the interventions reveals that the attitude and behavior of those trained improved by 30%. / BGARP assisted GoB coming up with a new Prison Manual that was approved by Bihar Cabinet and is being implemented across the state. / IT enablement in Industries Department for reporting monthly progress of various schemes BU DICs reduced time lag by over 80% / Impact Weighting (%): 30 / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

Output 3: Strengthened district level administration and service delivery.
Output 3: Final score and performance description: A (output met expectation) / Indicator Score / Indicator: Effective implementation of Right to Public Services Act (RtPS) and its monitoring A+ / Milestone: RtPS roll out with on time disposal rate of 95% (of total applications). / Milestone Status: BGARP supported state wide roll out of RtPS in Bihar and the disposal rate of applications received is 98.8%. / Related Interventions: / BGARP supported technical inputs at all stages starting from development of Acts and Rules to implementation of the provision of the same / Simplification of the process of issuance of certificates / Drafting of the BRTPS Rules / Incorporating suggestions & Notification into the Final Act, Rules and Services / Training workshop of master trainers in state HQ & roll-out training in field / Mass Awareness Campaign launched through various media (Press ads, hoardings, radio jingles, audio-visual clips etc) / Periodic impact study reports based on field visits / Rohtas – Bihar RTPS implementation report (last week of November, 2011) / Bhagalpur – Report on RTPS implementation issues (16th & 17th December 2011) / Nalanda – Bihar RTPS implementation report (22nd & 23rd December, 2011) / Patna – Report on RTPS implementation issues (27th & 29th December, 2011) / Chapra - Bihar RTPS implementation report (2nd and 3rd February, 2012) / Nalanda – Report on RTPS, e-District and Vasudha Kendras (4th & 5th July 2012) (Letter no. 6147 by GAD dated April 27, 2012) (Annexure 15) / Nalanda – Report on Vasudha Kendras & e-District: Process Perspective (August 2012) / Analysis of RTPS data sourced through Adhikar software / Analysis report based on data from 15th August, 2011 to 4th July 2012 on applications received, disposed, delays and denials. User feedback survey on citizen satisfaction in some services in a block in Nalanda carried out in December 2011 with about 80% of respondents expressing their satisfaction. / A number of suggestions proposed in the above mentioned reports have been accepted by GoB in improving the implementation of the BRTPS, which are listed below / Issues Observation Suggestions Status / Time limits for services The feedback from citizens was to reduce the time limit for issuance of various certificates. / The due diligence required for Mutation cases meant that time limit provided under BRTPS Act was inadequate Reduce Time Limits / Introduce Tatkal System / Increase time limit for Mutation Reduced to 10 days (from 21 days) in the case of Caste, Income and Residence Certificates and select other services / Tatkal system introduced (Letter no. 19621 by GAD dated December 27, 2013 (Annexure 16) / Time limit for Contested Cases under Mutation increased / Information on status of applications Dissemination of information on status was patchy Display near the counters / Automatic SMS / Information of status on the Web / IVRS Automatic SMS system introduced / IVRS introduced / Timings of receiving & issuing counters Applications were being received only in the first half of the day and certificates issued only during the second half Full-day working of both receiving and issuing counters Full-day working of both Receiving and Issuing Counters introduced by Government of Bihar / Caste, Income and Residence certificates Need for repeated applications by citizens Issue multiple copies of the same certificate for a single application; make it fee-based / For those issued certificates after 16th August 2011, based on provision of prior Application Number, fast-track certificate issue as all relevant verification details will be on the data base of Adhikar Government of Bihar notified fast-track issue [3 days instead of 14 days] of certificates if applicants provide the number of the previously issued certificate. This was later replaced by tatkal. / Number of Applicants at Block/Circle Office counters In certain block/circle offices it was observed that the number of applicants was large affecting efficiency and orderliness Utilize Vasudha Kendras to reduce costs for applicants and increase their convenience; this will also reduce pressure at Block/Circle Offices / Introduce a PPP model at Block/Circle From the first week of May 2012 this has begun in Nalanda; reports on implementation and some preliminary issues highlighted by GTAST in July & August 2012 / E-District and RTPS The Block/Circle Offices were also levying fees under E-District Government to consider if it was legally valid to have no counter where the applicant can avail services without any application fee / To decide Where and How to have Fee and Non-Fee counters Abolition of Fee at Block/Circle offices announced end-July 2012 / Submission of Applications It was observed that a single person was submitting multiple applications; these could have been middle-men/brokers Ban multiple applications; Only 1 Application per Applicant Video-cams installed at all counters to check middlemen. / On-line Applications No notification had been issued by the GoB under the Act. It was observed that as no proof of any sorts was required to file on-line applications, there was a danger of the website being bombarded with fake, fraudulent and malicious applications. This could lead to server break downs. Notification under BRTPS Act of introduction of on-line services / Warning on the home page of On-line Services to prevent/reduce fake, fraudulent/malicious applications / Provision for uploading of documentary proof Online application being received for certificates since January 2011. / Public Conveniences GTAST teams observed that conveniences like chairs, drinking water were absent Provision of basic conveniences near the counters Chairs and sheds provided at all RTPS counters / Queuing in front of counters There is over-crowding and unruly behavior amongst applicants in front of counters, especially in offices where a large number of applicants are present A system of railing to ensure applicants are forced to stand in a single file Token system and chairs provided / Reporting data through Adhikar and E-District The reporting formats are different and so is data capture [Application ID No. structure is different] A system/patch to facilitate synchronization of reporting format/data under E-District and Adhikar e-district data now being synchronised / Appeals in the event of Delay or Denial of Service Very few Appeals have been observed in the case of Delay or Denial of Services Appellate Authority to be mandated under the Act to take suo moto action, instead of waiting for an Appeal from the Applicant / Increase Awareness through campaigns in print, Audio, Audio-Visual and electronic media Suo-motto cognizance being taken up by appellate authority / Campaign in media continuing / A number of citizen centric amenities have been introduced at the RTPS application counters. The shares of counters where these amenities have been actually installed are measured. The table below indicates that as on 15th May 2014, all the offices have counters, notice boards, sheds and waiting place constructed. / Table 4: Extent of citizen friendly amenities set up at RTPS application counters / %age of offices where counters have been constructed %age of offices where information regarding RTPS act written on the wall/ Board %age of offices where shed are available for queue people %age of offices where waiting place for Applicants are available. / As on 15th August, 2012 100% 100% 81% 64% / As on 15th May, 2014 100% 100% 100% 100% / Table 5: Status of Application received under RTPS and their disposal / Period Total Applications Received (Million) Total Disposal of Applications (Million) Percent of Applications disposed / 15 August, 2011 to 23 May 2014 71.1 70.3 98.8% / Indicator Score / Indicator: Citizen satisfaction with government services B / Milestone (EoP 2014): Final 3rd round of Citizen Report Card (CRC) carried out / Milestone Status: There was a delay in initiating the first round of CRC. The successful completion of survey and the subsequent processes of developing the reports and making a formal launch, extended well over 2012. With the review of the findings by GoB happening only in late 2013, there was a low possibility of conducting the second round. Hence instead of three rounds of CRC as envisaged in the logframe, only one round of CRC could be completed. / Related Intervention: / 1st round of CRC competed in 2012 covering about 32000 households from all districts and blocks of Bihar. For 7 out of the 8 services, more than 60% of the respondents expressed their satisfaction with the government services. / Key findings were publicly released in December 2012 in which representatives of research organizations, academic institutions, civil society and cross section of the local & national media participated and discussed the findings / A meeting of all the concerned head of departments was convened under the chairmanship of Chief Secretary in October 2013 to discuss the findings and the way forward. Consolidated State Report & Individual district reports along with dashboard have been shared with respective districts as well so that they could take appropriate actions on the basis of the findings. / Indicator Score / Indicator: Quality of Grievance Redressal B / Milestone (End of Term): Review of system undertaken and changes effected / Milestone Status: The review of the system has been completed; however, the recommended changes are yet to be implemented. / Related Interventions / Detailed assessment of public grievances received in Nalanda District Collectorate Janta Darbar in FY13 was undertaken for 3600 public grievances. A detailed typology of all the grievance lodged was conducted and findings have been presented as below / Table 6: Typology of Grievances received at Nalanda Collectorate in FY 13 / Seating arrangement and layout of the Public Grievance Cell in Collectorate has been reorganized. This has resulted in improvement in office hygiene and availability of more space for the staff. / Study on strengthening Public Grievances Redressal Mechanism in Ekangarsarai Block has been initiated. / Indicator Score / Indicator: Implementation of Reforms in District Collectorate A / Milestone (End of Term): Reforms Action plan implemented in one Collectorate, processes documented and replication model developed / Milestone Status: The reforms action plan for Nalanda Collectorate has been developed and its implementation is underway. Process documentation is also simultaneously being undertaken by the GTAST, but full replication model and plan is yet to be completed. / Related Interventions: / Report on key findings and suggestions/recommendations for Strengthening District Administration and Service Delivery Reforms was submitted in September 2013. / Implementation Plan was developed and finalized after detailed deliberations with the DM and senior district officials in October 2013. / The key interventions implemented in the Collectorate focused on – a) citizens as the ultimate stakeholders and included activities relating to removing inefficiency across the service value chain and improving citizen experience, and b) improving the internal office administration to enhance working environment and productivity of employees. / The key interventions undertaken include: / Migrated high volume, citizen-centric services to Samadhan Kendra for delivery from dedicated counters. The counters receive – a) scholarship applications from students and providing information on various welfare schemes (more than 100 queries entertained and applications received daily); b) applications for certified copies of records and issuance of the same (around 25 applications received daily); c letters/correspondences addressed to DM (more than 30 letters received daily) and d) applications for caste, income, and domicile certificate under RTPS and issuance of the same (more than 30 applications received daily). This initiative has provided ‘one-stop shop’ to the citizens and their needs are getting attended to without running from pillar to post as before. (Please refer to DM’s order in Annexure 17). / Reengineering of processes relating to character certificate verification - By reducing number of steps and people involved in service delivery, establishing timelines for delivering the services, and fixing accountability of officers within the system who would be held responsible, the time taken for verifying the character certificate has reduced significantly (from an average 90 days to 20-30 days). The table given below highlights the before and after intervention scenario. The revised process and timelines have been issued vide DM’s order dated 23rd January 2014. (Please refer to DM’s order in Annexure 18) / Average Time taken by Receipt office to dispatch the application to General Section in the Collectorate Average Time taken by General section to forward the request for verification to SP office Average Time taken by SP office for sending the verification report to Collectorate Average time taken by General Section for dispatching the verification certificate to the applicant Total Average time taken / Before 2 days 12 days 57 days 19 days 90 days / After 24 hours 2-4 days 15-20 days 2-5 days 20-30 days / Reengineering of processes relating to caste (SC/ST/OBC) certificate verification - By reducing number of steps and people involved in service delivery, establishing timelines for delivering the services, and fixing accountability of officers within the system who would be held responsible, the time taken for verifying the caste certificate has reduced significantly (from an average 120 days to 10-20 days). The table given below highlights the before and after intervention scenario. The revised process and timelines have been issued vide DM’s order dated 23rd December 2013. (Please refer to DM’s order in Annexure 19) / Average Time taken by Receipt office to dispatch the application to Welfare Section in the Collectorate Average Time taken by Welfare section to forward the request for verification to concerned block/circle office Average Time taken by Block/circle offices for sending the verification report to Collectorate Average time taken by Welfare Section for dispatching the verification certificate to the applicant Total Average time taken / Before 3 days 26 days 47 days 44 days 120 days / After 24 hours 2-4 days 5-10 days 2- 5 days 10-20 days / Record Management and weeding of records – The record management and weeding exercise was initiated in the Collectorate for the first time since its formation in 1970. Around 10000 files have been indexed for easy reference and shifted from the sections to a designated place which will be developed as new record room. This exercise has freed up valuable storage spaces and work spaces in Collectorate, enhanced information retrieval, with corresponding improvements in office efficiency and productivity. (Please refer to various DM’s order in this regard in Annexure 20) / Space management and layout re-design/re-plan of workspaces – Space management and layout redesign was implemented in all the sections of the Collectorate to provide efficient, hygienic, neat & tidy workspaces to improve work productivity and employee satisfaction. The new seating arrangements and layouts has opened up the floor plan to natural light and more space for most staff and promoted positive changes towards a more open and collaborative working culture. (Please refer to DM’s order in Annexure 21A and Annexure 21B) / Capacity building of staff – Around 100 clerks and Head clerks were trained on change management and around 50 clerks and Head clerks were trained on record management and weeding process. Furthermore, individual handholding support was provided to staff in operating the new applications (Please refer to DM’s order in Annexure 22) / Dak (letters & correspondences) Tracking & Monitoring System has been developed and being implemented – Dak (letters & correspondences) tracking & monitoring system aims to establish transparency and accountability, reduce processing delays and improve efficiency and effectiveness of Collectorate responses to 30000 odd letters/correspondences received in a year. Trial run has begun in May 2014 in Development Section. / Figure 5: Screen shot for Dak Tracking System / Court cases Monitoring System has been developed and being implemented – Currently, it is being implemented in DM’s court. For the 500 cases which have been entered in the system, it provides facilities for checking case status and generating automated cause list amongst others. / Figure 6: Screen shot for Court Case Monitoring System / Figure 7: Screen shot for Retirement Benefits Management System / Pension & Group Insurance Calculator has been developed and implemented – Currently, Pension & Group Insurance Calculator has been implemented under the Retirement Benefits Management System. This solution facilitates Establishment section to compute retirement benefits accurately in 5-10 minutes which used to take 3-4 days before. / Final results: / RtPS roll out has been one of the major success of BGARP. The programme supported full spectrum roll out of the act across all the 38 districts of the state. The system generated data reveals 98.8% disposal rate of applications received. / Further, the recommendations to shorten the time taken for delivery of several services such as caste, income and residence certificates has also been accepted by the GoB are notified. Moreover, the state Government also introduced tatkal services for speedy service delivery to citizens in dire need. / The CRC supported by Bihar to assess citizen satisfaction against various services revealed high satisfaction levels. GoB was appreciative of the initiative, but also apprehensive simultaneously considering its sensitivity for which the anticipated two more rounds could not be undertaken. / The collectorate reforms are being implemented in Nalanda district. Several interventions have been carried out such as one stop service centre, business process reengineering and IT enablement. These reforms have led to (1) reduction in time taken for character certificate verification from 90 days to 30 days (2) reduction in caste certificate verification from 120 days to 20 days (3) shifting from manual to IT based systems for court case monitoring, correspondence maintenance and management.
Impact Weighting (%):30% / Revised since last Annual Review? No. / Risk: Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Achievement and Results
1.1 Has the logframe been changed since the last review? Y/N / Yes. The logframe has been updated to reflect new initiatives and some revised milestones. It was updated twice during 6 years of project implementation. / 1.2 Final Output score and description: A / Overall, it is observed that the outputs have almost met the expectation. The major achievements have been roll out of RtPS for time bound delivery of public services, training of BAS cadre, and improvements in revenue collection. The outputs that have moderately underachieved include roll out of Maitri training across the state using the master trainers’, training of BRS and BFS cadre staff and strengthening grievance redressal system. / The list of indicators with their score is summarised in the table below. 9 out of 12 indicators have been rated as A+ or A whilst the remaining B. Therefore, the overall project has been rated as A implying that the project met the expectation. / Sl. Indicators Score / 1 Proportion of vacancies against currently sanctioned strength for Bihar Administrative Service (BAS), Bihar Financial Service (BFS) and Bihar Registration Service (BRS) cadres A+ / 2 Training of BAS, BFS and BRS Officers A / 3 Proportion of appraisal reports for BAS officers which are initiated and accepted every year A+ / 4 Systems for enhancement of tax revenue A / 5 Delivery of social sector services A / 6 Quality of Police Administration B / 7 Prison reforms A / 8 Enhance efficiency of Industry Department A / 9 Effective implementation of Right to Public Services Act (RtPS) and its monitoring A+ / 10 Citizen satisfaction with government services B / 11 Quality of Grievance Redressal B / 12 Implementation of Reforms in District Collectorate A
Strong connect between FA and TA / Further, the programme effectively made use of the resources under FA and TA. TC was creatively used for overcoming procurement and bureaucratic tangles and going ahead with speedy procurement of services and manpower. Whereas, FA was mostly used for accelerating service delivery across the state (IT platforms, initial HR and other operational costs), improving grievance redressal mechanisms, and capacity building of staff. / FA was primarily utilised for the following: / Setting up and operationalization of the Mission office (BPSM) and establishing Jigyasa call centre housed within the mission office / Conducting training of Group D employees across the state / Support from FA was the key reason for the successful and quick roll out of RTPS. The FA was the main source of fund used to bring onboard and pay the monthly honorarium during the initial roll out years to the contractual IT Managers, Executive assistants, Block IT managers. / FA fund was also utilized to cover the programming support - developing the Adhikar Software, the MIS for RTPS in Bihar / In-service training of Registration Department and Commercial Tax Department officials / Modernization of the offices of partner departments such as strengthening information management systems in General Administration, Education and Home Departments. / TA was used for the following: / TC funds were mainly utilized for conducting various training such as behavioral trainings (group D pilot training, Maitri Master trainer training), training on Management related subjects for BAS officers (by XIMB and XLRI), training on basic computing (BPSC employees, Industry Department employees), training on accounting (Industry department employees) / TC fund proved immensely helpful for quick procurement of services of communication experts during the state wide communication campaign for RtPS / Bringing onboard subject matter experts (such as Mr. Raju, Retd. IPS and John V George Retd. IPS) for police and prison reforms respectively / Manpower support to BPSM and PMU for Education department, programmers to assist in development of Adhikar and other IT related support to the mission and accounting support to BPSM / Fit between the interventions and need of the department / One of the major successes of BGARP was its fit with the needs and priorities of the GoB’s focal departments. BGARP was like an umbrella support to GoB and was flexible to accommodate emerging priorities of the GoB within the purview of the programme’s purpose and goal. Project interventions were planned based on two premises – (1) findings from departmental reform strategy study/ functional review during the inception phase, and (2) needs identified by Departments based on immediate ground level realities and long term priorities. In both the cases reform strategy were decided based on close consultation with the entire department. This resulted in high level of acceptance of the reform recommendation and their successful roll out as observed in case of RtPS and Commercial Tax and Transport tax. However, changes in leadership of some departments also resulted in slowing down of reforms agenda, such as Maitri training for police personnel. / Direct feedback from beneficiaries / A large scale citizen survey was undertaken in 2012 to assess citizen feedback on quality of service delivery for a range of services. This survey covered 31,556 households across all 534 blocks in rural Bihar. The findings of the survey indicate that more than three-fourth of the respondents were satisfied with 5 of the 8 public services viz., Pensions, Health Facilities, Certificates and Ration Shops. For two more services viz., Schools and Anganwadis, three quarters of the respondents were satisfied with the service delivered. / Direct feedback from citizens was also obtained during the annual reviews. Separately, feedback was also obtained from beneficiaries by the technical assistance team which undertook a study to assess implementation of RTPS. Furthermore, a feedback session was also organised by our TA team for the trainees of Maitri programme to gauge the shift in their attitudes and behaviours post training.
1.4 Overall Outcome score and description: A / The purpose of BGARP was better governance (improved government capability, accountability and responsiveness) enables better delivery of basic services to all its citizens, particularly the poorest and most excluded. The logframe had two outcome level indicators (1) Quality of service delivery and citizen satisfaction (2) Bihar achieving Own Tax: GSDP ratio of 6% by end of project. The indicator wise description of project achievements is summarised in table below and overall outcome score is assessed to be A. / Outcome Indicator Progress Score / Quality of service BGARP had strong influence on the quality of service in the state. / The programme supported drafting of the RtPS Act, its roll out and high quality implementation with staggering 98.8% disposal rate of application indicating that implementation of RtPS is highly successful. / About 70% of services availed by citizen are pertaining to caste, income and domicile. Such certificates are generally issued to the poorest and the most vulnerable. It can also be inferred that delivery of services has also touched the poorest and the most disadvantaged in the state. / Further, the pilot in Nalanda collectorate towards implementation of decentralisation reforms and its modernisation has led to steep decline in time taken for verification of caste and income certificates (from about 120 days to 20 days). Besides, the one-stop centre developed in collectorate premise has significantly improved government and citizen interface. / Moreover, the IT based solutions implemented at district level for the industries centre has reduced the reporting time for updating monthly progress report against key investment related schemes. A / Citizen satisfaction As envisaged earlier, three rounds of CRC could not be undertaken in the state. However, one round of CRC that was undertaken revealed very high satisfaction among citizen (on an average 80%) against 8 major programmes of the government. A / Own Tax:GSDP ratio The end of project milestone was to help the state achieve own tax: GSDP ratio of 6% (from baseline of 4.8% in 2009). In absolute terms the revenue collection of the state improved dramatically (from Rs. 6173 Crore in 2009 to Rs. 20963 Crore in 2014[1]). The own tax:GSDP ratio also strengthened from 4.8% in 2009 (beginning of the project) to 5.3% in 2014[2]. A / Overall outcome level score A / Impact and Sustainability / Impact / Impact level indicator of BGARP was reduction in percent of households below poverty line from 54% (in 2009) to 49% by the end of the project. The recent release from Planning Commission (in 2013) suggests that poverty level in Bihar fell from 54% to 33%. Several factors have led to this steep decline in poverty numbers, primarily a series of home grown reforms undertaken by GoB. Though BGARP supported GoB in several such reforms across 9 departments, but direct attribution to reduction in poverty figures is difficult to be computed. / BGARP strongly supported GoB in enactment and effective roll out of RtPs across the state. Bihar’s RtPS is widely regarded as immensely successful initiative. Several other states (Karnataka, Rajasthan and Odisha) and some South Asian countries (Pakistan and Nepal) studied the implementation mechanism of RtPs for its replication in their respective geographies. / Sustainability / It is assessed that most of the interventions supported through BGARP stand high in terms of their sustainability. Below are highlights of some interventions that have been institutionalised by GoB to exemplify the sustainability efforts. / RtPS is an example of a legally justiciable entitlement to the citizen, for which the state government is accountable. / Several initiatives have been institutionalised by GoB through appropriate instrument such as Government Order, Cabinet Approval and Departmental Orders. For instance, the revised Prison Manual of Bihar was approved by the state cabinet. Similarly, the training plan developed by our TA team was institutionalised by GoB vide circular from General Administration Department. / Further, the new institutional mechanisms set up under BGARP have also been formalised by the state government. GoB has decided to continue with Bihar Prashshnik Sudhar Mission Society (BPSMS) after BGARP comes to an end. / However, there are certain areas where the interventions within BGARP supported a part of larger reforms agenda and discontinuity of support might result in slowing down of the momentum created. For instance, the support to Commercial Tax Department was very focused and precise around check post management and commodity coding. These definitely helped the department improve its revenues, but owing to inadequate capacity and limitations in technical advisory inputs the department may not realise full tax potential in the state. Similarly, in industries department the nut and bolt level reforms at DIC level did strengthen reporting mechanisms but gap in technical assistance at state level will have limited impact on state attracting private sector investments.
[1] Economic Survey, 2013-14, Government of Bihar
[2] Economic Survey, 2013-14, Government of Bihar

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y/N / The overall budget of the programme is £18.00 million (£12.00 million FA and £6.00 million TA) over a period of 6 years. By January 2014, the programme had spent £15.46 million (FA £10.02 million and TA £5.5 million, including £0.6 million for Bihar Language Initiative for Secondary Schools). The balance budget of £2.1 million is committed against forecast expenditure (FA £1.6 million and TA £0.5 million) for the period from February till end June 2014. Both FA and TA commitments will be fully spent and GoB will be submitting the final claim within the 6 months post-completion grace period for financial closure of the project. / 2.2 Key cost drivers / The Governance and Administration Department (GAD), Government of Bihar (GoB) is the key cost driver of the programme. The Governing Council, chaired by the Chief Secretary, along with representation by DFID and other spending departments approves all expenditure at the beginning of the financial year and disburse allocation to various departments. DFID’s contribution is reimbursed on submission of expenditure statement and claimed bi-annually. The details of the FA spending is presented as follows: / Sr. No. Department FA Allotment in INR Lakhs Forecast Expenditure till end June 2014 in INR Lakhs / FY10 FY11 FY12 FY13 FY14 Total / 1. GAD, BPSMS & Capacity Building 571.90 1,517.14 1,555.90 2700.00 1830.00 8,178.55 5,358.10 / 2. BIPARD - - 111.60 111.6 109.80 / 3. BPSC - 17.00 30.00 47 38.95 / 4. F&CP - - 52.50 52.5 52.50 / 5. Registration 448.00 - - 448 384.43 / 6. CTD 75.10 - - 73.2# 73.72 / 7. Transport 180.00 - - 180 180.00 / 8. Education 300.00 600.00 - 900 684.25 / 9. IT - 138.00 - 138 138.00 / 10. SC ST Welfare - 2.86 - 0.63@ 0.63 / 11. Home - 25.00 - 25 22.75 / Grand Total 1,575.00 2,300.00 1,750.00 2700.00 1830.00 10,155.00 7043.13 / TC funds are spent directly by DFID. These funds are used to procure staff/consultants, provision of training and contribute to running costs of the GTAST. DFID reimburses GTAST expenditure following the submission of quarterly invoices using standard agreed procedures. / 2.3 Was the project completed within the expected timescale: Y/N / The programme will complete 6 years of DFID support on 30 June 2014 and has achieved significant results. The Project Completion mission has done an assessment of overall performance of DFID supported interventions against all three outputs and identified areas that need more focused engagement from GoB and GTAST to achieve targeted results by end of the project.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / Though no formal evaluation of evidence was carried out during the project cycle, but no changes in evidence is observed. The evidence used while designing of the programme is found to be valid towards end of the project. / 3.2 Set out what plans are in place for an evaluation. / Since the programme design did not contain formal evaluation, such a plan was not pursued. However, project performance and attribution to results could be assessed using secondary sources and are described below: / By the end of BGARP a total of 71.1 million applications were received under RtPS. Of the total application about 75% applications were related to services which were mainly availed by poor and marginalized citizens such as Certificates (Caste, Residential and domicile) and Pensions (old age, widow and handicapped). Evidence are available to support the improvement in the services and reduced instances of corruption in delivery of the services due to the onset of RTPS as follows: / About 76% of the respondents, as reported in Citizen Report Card (CRC), found the services related to issuance of certificates and pensions had improved over last four years. The CRC was based on a survey conducted in 2012 and covering 32,000 households across the state / A separate survey at select district found that use of middlemen for certificates has reduced from 65% to 14% with only 9% and 12% of the respondents reported to having paid bribe for certificates and pensions. / Interventions under BGARP, direct or indirect, resulted in about 446,000 person days of training. In addition, due to regularization of recruitment the vacancies of administrative cadres reduced from over 50% to 18%. Further, because of the restructuring the 50% vacancies for the combined positions of Block Development Officers and Circle Officers reduced to nil, having a direct impact in terms of implementation of development related schemes at the block level. This can be directly correlated to improvement in implementation of several schemes affecting the poor citizens. As per the CRC, about 74% of the respondents reported an improvement in 8 key services provided at block level (such as MGNREGA, Primary and Middle Schools, Anganwadi, PDS etc.) over last 3-4 years. / Under BGARP, Education Department was provided technical assistance in creating a comprehensive database of about 34 lakh adult neo-literates under state sponsored adult literacy scheme, Mukhyamantri Akshar Anchal Yojana (MAAY). The data captured indicated significant achievement in cognitive abilities. About 66% of the neo-literates could read small sentences while 89% could write their names and 59% could perform simple additions. Buoyed by the success of the MAAY, GoB requested Programme Monitoring Unit (PMU) support under the BGARP for Sakshar Bharat (centrally sponsored flagship adult literacy scheme).

4. Risk
4.1 Risk Rating (overall project risk): Low to Medium / Did the Risk Rating change over the life of the project? No / 4.2 Risk funds not used for purposes intended / The risk of funds not being used as intended was assessed to be low for the programme and remained the same. Approval for each spending proposal was accorded by the Governing Council, which used to be chaired by the Chief Secretary and its members included Principal Secretaries of all focal departments. DFID used to be a special invitee at the Governing Council meetings and has been party to approval of each spending proposal. / DFID financial assistance was provided to BPSM on a reimbursable basis. Departments and districts submited utilisation certificates before the release of next tranche of funds. Annual audit of funds by chartered accountants was received for all the financial years. / 4.3 Climate and Environment Impact / The climate and environmental risk is judged to be low for the programme.

5. Value for Money
5.1 Performance on VfM measures / 5.1.1 Interventions in improving implementation of Right to Public Services Act, 2011 / A cost-benefit analysis of RtPS was done by GTAST in the month of May 2014. The benefits that were monetised include / Time & labour savings for beneficiaries as s/he no longer needs to make multiple trips. / Travel & other expenses saving by beneficiaries. / Savings from reduction in rent-seeking avenues due to ease of and transparent application process. / The costs that were taken into account include / HR costs for staff deployed in districts & blocks. / Cost of providing uninterrupted power supply through Diesel Generator back up. / Contingency expenses on stationery, print cartridges, etc in field offices (RTPS counters in Block/ Circle) for which specific provision have been made. / Two different calculations were done – (a) costs & benefits for the last year and (b) potential benefits of delivery through Vasudha Kendras. / Against a cost of estimated Rs. 454 million (£ 4.6 m), actual benefits are monetised to be Rs. 7.15 billion (£ 72 m) for the period August 2010 to May 2014 (including savings due to not paying of bribes). / Vasudha Kendra Potential: If the issuance of caste, income and residential certificates could be done through Vasudha Kendras (village level common service centres), the benefits could potentially be Rs. 8.53 billion (£ 86.5 m) every year, assuming all the certificates are issued from Vasudha Kendras, translating into further saving in time and money for the applicant, who have to travel up to one such Kendra located in his/her panchayat. / There have been significant efficiency improvements in the service delivery process in the last year. These include: / Provision of tatkal in certificates / Further reduction in time period for services such as Certificates, which constitute the bulk of the demand for services. / Further improvement in amenities for citizens at the RTPS counters in terms of sheds, seating arrangements (coverage of 100% of RTPS). / Inclusion of two more services namely 1) National Family Benefit Plan, 2) Mukhyamantri Kanya Vivah yojana vide notification on January, 2013. / 5.1.2 Interventions for Commercial Tax Department / The two key intervention carried out for the Commercial tax department in the current review period were / Technical inputs leading to the enactment and implementation of “The Bihar Tax on Professions, Trades, Callings and Employments Act, 2011” / Head Amount Remarks / Benefit to state in terms of additional revenue / (Details provided by Commercial Tax Department) £ 10 Million (INR 105 Crores) Collection of professional tax in the Review period / Cost equivalent of Efforts £ 9,500 Total 40 Man-days / Streamlining of check-post management practices through inputs in: / Formulation of Integrated Check-post Authority Act & Rules / Strengthening the check-post management system / Head Amount Remarks / Cumulative benefit to state due to reduction of leakage at checkposts owing to improved integrated infrastructure and increase in collection due to streamlining of the check-post management practices / (Details provided by Commercial Tax Department) £ 46 Million (INR 460 Crores Growth in checkpost collection in FY 13 over and above the CAGR of 23.5% (for period FY08 to FY12) has been attributed to the efficient check-post management practices. / Cost equivalent of Efforts £ 53,500 Includes about 5 Man-months effort and expenses due to study visits to Andhra Pradesh and Karnataka / 5.1.3 Interventions for Department for Registration, Excise and Prohibition / A. Registration: / The Stamp Duties in the state were revised based on the findings and recommendations by GTAST of a comparative study of registration fees and Stamp duties in select Indian states. The revised stamp duties were brought into effect from February 2013. The direct benefit was in terms of increase in revenue. The method of arriving at the quantum of increase in revenue due to the increase in stamp duty is given below: / The average revenue/ deed for the FY12, FY13 and FY14 (April, May, June & July) is given in the table below: / Period Average Revenue/ deed registered (INR) Growth Remarks / 2011-2012 13,645 - / 2012-2013 14,612 7% Natural growth of 7% / 2013-2014 22,642 55% Additional Increase in average revenue/ deed of around Rs. 6,995 in FY14 over that in FY13 attributed to the revised stamp duty rates / It is observed that at a regular growth of 7% (realized in FY13 over FY12), the Department would have realized revenue/ deed of around Rs. 15,647. / Benefit: Considering the total number of deeds registered over the period April till July 2013, the increase in revenue/ deed amounts to Rs. 284 crores (£ 33.41 m). / Effort: Total 4 Man-month of effort translating into cost of GBP 13,500. / B. Excise / The excise duty structures in the state were revised based on the initiatives of (i) Comparative study of excise duties and levies in select Indian states and (ii) Impact Assessment of revision of excise duties and levies. The new rates were brought into force since the 23rd January 2013. The direct benefit was in terms of increase in revenue. / The average revenue/ LPL (London proof Litre) of consumption for the last 3 years for the period of April till July are given below: / Period Revenue/ LPL of consumption in INR Growth / 2011-2012 339.84 / 2012-2013 426.72 26% / 2013-2014 569.93 33% / As is observed from the above table, considering a growth of 26% Y-o-Y in revenue/ consumption in FY14, the Department would have realized a revenue/ LPL consumption of Rs. 535. / Due to the revision of the excise duties in the state, the Department was able to increase its revenue realization by around Rs. 33.82 per LPL of consumption (accounting for a spurt in growth by about 7%) / Benefit: Considering the consumption for the period of April 2013 till July 2013, the increase in revenue of INR 51.32 crores (£ 6 m) due to additional increase in growth. / Effort: Total 5 Man-month of effort translating into cost of GBP 16,700 / 5.2 Commercial Improvement and Value for Money / To ensure commercial improvement and better value for money, DFID programme team regularly reviewed performance of the GTAST, whom DFID had directly procured through OJEU process at the start of the programme in 2009. GTAST’s contract was also reviewed and extended twice after ensuring satisfactory performance for the previous periods. PrG team conducted an audit of third party procurement done by GTAST and ensured that they followed DFID agreed procurement procedures and made recommendations for further improvement. DFID programme team visited the interventions frequently and ensured the resources deployed are with right skills and as per the contractual agreement. GTAST fees and expenditures were reimbursed on a quarterly basis on receipt of satisfactory performance reports and detailed expenditure statement. DFID programme team maintained spread-sheet to monitor input days and agreed fee rates of GTAST team. / All expenditures under FA were managed by the Bihar Prashasnik Sudhar Mission (BPSM) under the leadership of the Principal Secretary, Governance and Administration Department (GAD), Government of Bihar. FA allocation to other departments was based on annual work plan approved by the Governing Council. The governing council chaired by the Chief Secretary, Government of Bihar reviewed all request for FA funds and disallows expenditure items which were not covered within the scope of BGARP. BPSM had carried out audit of FA expenditure for the financial year 2009-10, 2010-11, and 2011-12 and reports were submitted to DFID. The audit for the current fiscal year is underway. / 5.3 Role of project partners / DFID has been the sole donor for the BGARP interventions. Principal partners were the Mission Directorate for coordination and leading government-wide reform, the General Administration Department (GAD), and line Departments identified for service delivery improvements. The Mission Directorate (MD), led by the Principal Secretary, GAD, was responsible for implementation of the programme and eventually overseeing other governance reforms to ensure coherence and co-ordination. / The Technical Support Agency (GTAST) provided consultancy support to the MD and help identify and procure specific expertise needed to achieve outputs and goals / 5.4 Did the project represent Value for Money : Yes

6. Conditionality
6.1 Update on specific conditions / There are no conditions.

7. Conclusions
BGARP has been on track in achieving its goal and purpose. The programme has contributed to the positive governance agenda of the State Government. It has delivered effectively against strengthening systems and service delivery in partner departments and improving delivery of services at the frontline level; but could have done better in the areas of citizen friendly policing, strengthening grievance redressal mechanisms and development of replicable model on district reforms. / In our interaction with GoB officials during the last year and at the time of project completion review we understood that there is reduced interest in financial assistance (owing to increase in financial resource availability) but very high demand for Technical Assistance. Therefore, DFID will be working on aTA support in the areas of growth and governance as its commitment to GoB’s priority of fostering inclusive economic development.

8. Review Process
The project completion review of BGARP was carried out during 6-8 May 2014 by three member team from DFID India (Padma Kumar, Head State Partnerships; Raghwesh Ranjan, Governance Adviser and TTL and R.K. Pillai, Project Officer). On the first day the team held meetings with Principal Secretaries of various departments responsible for the implementation and monitoring of the programme. On the second day, DFID team along with the TA team visited Nalanda district of Bihar, reviewed progress of the RTPS service delivery functions, progress of district reform initiatives and held meeting with the District Collector. On the last day, the team reviewed the project progress with GTAST members. The findings of the review and recommendations were discussed with the Mission Director of BPSM.