Project Completion Review – post April 2018

Title: Mining Sector Reform Programme
Final Programme Value £ (full life): £10,837,020.38	Review Date:	February 2019
Programme Code: 105844	Start Date: 19 October 2011	Final End Date: 30 November 2018

Summary of Programme Performance

Year	2012	2013	2014	2015	2016	2017	2018	2019
Programme Score	C	B	B	A	A+	A+	A+	A+
Risk Rating	High	High	High	Low	Minor	Minor	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-105844/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-105844/documents

A. Summary and Overview (1-2 pages)

Description of programme and what it has achieved

Between 2011 and 2014, the UK provided £9 million (out of an originally allocated programme budget of £27 million) to a World Bank-managed single donor trust fund for the ‘Growth with Governance in the Minerals Sector’ (ProMines) Technical Assistance programme in the Democratic Republic of Congo (DRC). In addition, a further £0.5 million was allocated for the sharing of costs of a senior mining specialist within the Bank’s Kinshasa office for Project management and sector coordination. The World Bank contributed $50 million (£33 million) to ProMines.

The intended impact of the ProMines project was to improve governance of the mining sector and increase its contribution to economic growth, sustainable development and poverty reduction. At the outcome level, ProMines intended to strengthen the capacity of key institutions to manage the minerals sector, improve the conditions for increased investments and revenues from mining, and help increase the socio-economic benefits from artisanal and industrial mining.

During its implementation, ProMines had some tangible successes. For example, ProMines’ support with respect to the revision of the Mining Code was widely praised by NGOs, the Mining Industry and other stakeholders, including the Government of the DRC (GoDRC). There was also some progress made on several analytical studies such as the strategic environmental and social assessment of the mining sector (SESA) and the institutional audit of mining sector institutions – both were considered useful by other donors, the GoDRC and civil society organisations (CSOs).

The ProMines component was closed in 2014 due to underperformance against the results framework. From the £9 million already disbursed to the World Bank, unspent funds amounting to £4,786,913 were returned to DFID. The budget was also subsequently reduced from £27m to £10.2m. A lessons learnt document was produced following the closure of ProMines were a number of key lessons learnt were identified and shared.

Following closure of ProMines, and with the importance of having improved transparency and governance in the DRC’s mining sector, part of the funding (£1,319,559) from the programme was re-allocated to TCC’s extractives programme, “Advancing Transparency and Accountability in the Democratic Republic of Congo’s Extractive Industries”. The aim of the TCC programme is to work with Congolese civil society organisations (CSOs) to advocate for fiscal reform, analyse revenue data, and improve the DRC’s Extractive Industries Transparency Initiative (EITI) process and reporting. With empowered Congolese CSOs utilising enhanced skills, the CSOs are better able to influence reforms at both Government and Private Sector level to ensure improved accountability of mining sector revenues.

DFID funded TCC through three Accountable Grants - the first grant (£136,927) ran from October 2013 to January 2015, the second grant (£643,632) ran from September 2015 to February 2017 and the final grant (£539,000) ran from August 2017 to November 2018. The TCC component comprises three outputs:

1. Congolese civil society better understands EITI implementation in the DRC and is able produce contributions on EITI reporting and processes in the DRC.
2. Congolese civil society partner develops mining sector revenue analysis skills
3. Congolese civil society partners develop skills to use EITI data and other data for advocacy and produce interim deliverables for the implementation of evidence-based advocacy.

Over the life of the grants, TCC has performed very well against the logframe milestones and targets in most cases exceeding the identified targets. The overall score awarded to the programme following this review is an “A+”. Some notable achievements include:

- CSO partners and TCC have increased their profile as the ‘go-to’ organisations in their areas with respect to understanding the EITI process. They are increasingly invited to EITI workshops and meetings, including EITI executive committee meetings chaired by the Minister of Portfolio with the Minister of Mines as the Vice Chair).
- In Feburary 2019, Fredrik Reinfeldt, Chair of the EITI International Secretariat in Oslo, Norway wrote to former US President Jimmy Carter to acknowledge the Carter Center’s contribution in advancing transparency and accountability in the management of natural resources in the DRC and to thank him for TCC’s leadership in advancing democracy, human rights and economic opportunity around the world. The International EITI acknowledged that through TCC’s work, a wide network of local CSOs in the DRC are empowered to demand information about their natural resources and to use this information to hold companies and their government accountable.
- The payment of royalties from the DRC’s largest gold project, Kibali Gold Mine, to the province of Haut-Uele due to advocacy efforts of Cadre de Concertation de la société civile de l’Ituri sur les resources naturelles (CdC).
- CSOs increasing number of contributions to help shape the local and national EITI process, including recommendations on improvements needed to move towards the 2016 international EITI Standard. All the contributions made are publicly accessible on the TCC-run www.CongoMines.org online mining sector document library and information portal.
- Increased engagement of women on the programme through the inclusion of two women-led CSOs (DYFREN[1] and DYFEM[2]) as partners on the programme. Both CSOs have successfully completed eight revenue modules and developed case studies on Alphamin’s Bisie tin mine and Tenke Fungurume Mining (TFM). The collaboration and participation of these two CSOs has stimulated engagement from women civil society activists and developed their capacity to contribute to the normally male-dominated debate on extractive governance in the DRC.
  [1] Dynamique des Femmes des Mines
  [2] Dynamique des Femmes sur les Ressources Naturelles
- Successfully influenced EITI to ensure social expenditure analysis was a key part of the EITI process – this included developing a social expenditure framework which has been adopted and approved by the EITI executive committee. Furthermore, the CSOs have worked with the Government of the DRC (GoDRC) to include a standardised measure of social expenditure contributions in the new Mining Code
- Improved capacity of CSOs resulting in the production of advocacy strategies, draft governmental decrees for the publication of financial statements and the creation of sustainable development plans, advocacy memos, presentations to multi-stakeholder groups, etc.
- Collaboration between CSOs (IBGDH[3] and ACIDH[4]) on the publication of a joint report based on their research and analysis of provincial tax issues in Haut Katanga and Lualaba provinces.
  [3] Initiative Bonne Gouvernance et Droits Humains
  [4] Action Contre L'Impunité des Droits Humains
- 45 recommendations made by the CSOs to improve EITI-DRC reporting have been adopted by the EITI, significantly exceeding the target of 12.

Following this project completion review, a follow-up action will be to check on progress of the Alphamin Bisie Case Study which is due to be published over the course of the next few months. With the publication of the case study, which relates to the analysis of revenues from the Bisie Mine, local authorities and the community can use this information to ensure that funds identified for local development are allocated and used accordingly. In addition, the design of a new business case for the mining sector should be commenced over the course of 2019. Recommendations and findings from this and previous reviews, including lessons learnt, should be considered and reflected in the new business case.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Congolese civil society better understands EITI implementation in the DRC and is able produce contributions on EITI reporting and processes in the DRC.
Output number per LF		1.1	Output Score	A+
Impact weighting (%)?		33%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1a - Percentage of men and women of civil society organizations that have increased their knowledge on the EITI process and reporting by at least 20%.	72%	81% - moderately exceeded target
1.1b - Overall level of satisfaction among men and women of civil society organizations participating in TCC-led workshops held on monitoring and advocating for improvements to EITI-DRC processes and reporting.	87%	88% - slightly exceeded target
1.1c - Cumulative number of contributions by members of civil society developed for use in advocacy with key targets of the EITI-DRC process.	10	12 – slightly exceeded target

Provide supporting narrative for the score

All the targets under this output have been exceeded, therefore warranting an A+ score. The main aim this output is to improve the implementation of the EITI in the DRC through improved, well-informed and inclusive engagement between civil society and the EITI process. With an informed civil society, they are better able to support the EITI in ensuring it becomes a useful vehicle for driving forward better transparency and improved governance in the extractives sector. Over the grant periods, TCC has trained and mentored 11 CSO partners to more effectively contribute to the EITI process and to push for improvements in number of areas, including beneficial ownership, social expenditure, etc. Furthermore, TCC and its partners have positively engaged in the EITI process, providing recommendations to ensure that EITI-DRC conforms to the international EITI standards and produces data and information that is useful to stakeholders.

Whilst the activities related to the third TCC grant experienced delays at the start due to the delayed publication of the 2015 EITI report, there have generally been several successes reported on the programme. The knowledge of the CSOs has increased (as measured through pre and post-training evaluations on the various subjects that the CSOs were trained on). DFID verified this increased knowledge through interviews held with various CSO partners as well as the EITI. In addition, the CSO partners have positively contributed to the EITI process by producing 12 pieces of work which included analysis and recommendations related to several key EITI documents including the 2015 EITI report, 2016 EITI scoping report, the social expenditure framework, EITI work plan and annual progress reports.

 Lessons identified this year linked to this output and recommendations for future programmes

Over the life of the TCC component, several lessons have been learnt as outlined below:

- Identify contingencies in the event of delays that occur outside of the programme team’s control - this may entail early planning to better manage and anticipate such eventualities.
- Consider the inclusion of government officials in the training on the EITI process rather than just limiting the training to the CSOs on the programme.
- The need to be flexible and adaptive by maintaining a fluid timeline as well as supplementary activities / interventions to accommodate changes to EITI activities (e.g. the delayed publication of the 2015 EITI report had a direct impact on TCC’s ability to undertake activities on this component).

Output Title	Congolese civil society partner develops mining sector revenue analysis skills.
Output number per LF		2.1	Output Score	A+
Impact weighting (%)?		33%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1a - Percentage of men and women of civil society organisations that have increased their knowledge on mining sector revenue analysis by at least 20%.	66%	82% - significantly exceeded target
2.1b - Overall level of satisfaction with TCC-led workshops held on mining sector revenue analysis.	88%	86% - slightly below target
2.1c - Cumulative number of interim deliverables completed toward the final revenues impact analysis case study.	16	21 – exceeded target

Provide supporting narrative for the score

Outputs 2.1a and 2.1c have been substantially exceeded, with Output 2.1a achieving a final score of 82% against a target of 66% and Output 2.1c achieving a final score of 21 against a target of 16. Output 2.1b has come in slightly below the target of 88% by 2%.

TCC has over the period, provided hands-on training to the CSO partners, including two new women-led CSOs (DYFEM and DYFREN) who were introduced onto the programme during the last grant agreement. Interviews with DYFREN and others solidified the view that the CSOs had indeed increased their knowledge, including increased understanding of revenue analysis. As evidenced by the above average scores received through the training evaluations, the CSOs have positively gained from the trainings received. The CSOs also indicated that they valued the training and support received from TCC and had significantly more confidence in their abilities to analyse revenues and challenge mining companies and other stakeholders. They also indicated that they have valued the methodology and approach used by TCC in building their capacity.

To play an effective monitoring role, the CSOs need to be equipped with the skills needed to review and analyse revenues as well as developments taking shape in the sector. Through learning by doing, the CSOs have been able to produce high-quality outputs including two case studies on Alphamine’s Bisie Mine and Tenke Fungurume Mine which will help raise public awareness on the revenues due and collected from mining companies.

DYFEM and DYFREN have produced a combined total of 21 deliverables above the proposed target of 16. These deliverables, which include memos, recommendations, reports, analysis, etc., are continuously reviewed and scored by TCC, and have attained an average quality score of 82%.

Lessons identified this year linked to this output and recommendations for future programmes

TCC found that working with new and inexperienced organisations such as DYFREN and DYFEM presented unique challenges given the highly technical nature of the activities required. As such, TCC learnt that exercising patience and allocating additional resources is sometimes needed when working with CSOs. Whilst TCC had to put in extra effort, they felt it was a worthwhile investment given the importance of engaging women-led organisations.

With the DYFREN case study on Alphamine’s Bisie Mine, some delays were experienced in the publication of the case study. This was due to Alphamin indicating that they had not been sufficiently engaged in the production of the case study and that they required additional time to review the outputs and accuracy of the content. A key lesson here for both TCC and DFID is to ensure that the subjects of any case studies should, where practically possible, be informed at the outset to avoid any misunderstandings or delays down the line.

Output Title	Congolese civil society partners develop skills to use EITI data and other data for advocacy and produce interim deliverables for the implementation of evidence-based advocacy.
Output number per LF		3.1	Output Score	A+
Impact weighting (%)?		34%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1a - Percentage of men and women of civil society organizations that have increased their knowledge on data utilization and advocacy by at least 20%.	69%	88% - significantly exceeded target
3.1b - Overall level of satisfaction with TCC-led workshops held on data utilization and advocacy.	88%	83% - slightly below target
3.1c - Cumulative number of deliverables developed for using EITI-DRC data analysis in the implementation of the advocacy strategy.	12	26 – significantly exceeded target

Provide supporting narrative for the score

The aim of this output has been to ensure that the data that the EITI produce can be used to act as a lever for improving extractives sector governance and transparency as a way of reforming the sector. TCC has been providing tailor-made analytical and advocacy-focused training and ongoing technical support to their CSO partners on issues relating to provincial taxes and social expenditure.

In August 2018, DFID met with all three partners involved in the delivery of this output (OCEAN[5], ACIDH and IBDGH). Outputs 3.1a and 3.1c have been significantly exceeded with actual scores of 88% and 26 deliverables against targets of 69% and 12 deliverables respectively. Output 3.1b come in slightly below the 88% target, achieving a score of 83% which is still a relatively good score. The underachievement against Output 3.1b is mainly because of delays experienced in the first quarter of 2018 relating to the delayed grant disbursement (following a delay in the publication of the 2015 EITI report by the EITI) and a low score in the second quarter of 2018 by one of the participants which brought down the average score for the rest of the participants.
[5] Organisation Congolaise des Ecologistes et Amis de la Nature

TCC has worked with ACIDH and IBGDH and helped them to collaborate on a study of provincial tax issues in Lualabla and Haut-Katanga provinces. The training provided to the partners has improved their understanding of provincial taxes and reinforced their ability to collect and analyse provincial tax data, leading to increased advocacy on the use of tax revenues. The collaborative efforts of IBGDH and ACIDH in producing the provincial taxes report culminated in a workshop that was well-attended by several stakeholders including representatives from local government (including the Finance Ministry Cabinet Director, the Director of the Lualaba Province Tax Revenue Directorate, the Division Chief of the Mining Ministry, the Division Chief of SAESCAM (Service d’Assistance et d’Encadrement du Small Scale Mining), provincial deputies, the Division Chief of DGRAD (Direction Générale des Recettes Administratives, Judiciaires, Domaniales et de Participations), representatives from mining companies, and members of Lualaba civil society. This is a testament to the advocacy efforts by TCC and the CSOs which has generated interest from various stakeholders in the findings of the report. A key result from the report, the presentation and follow-up advocacy is that the taxes identified from the report are once again collected by the Lualaba Province Tax Directorate for the benefit of the province.

With OCEAN, TCC has been supporting them on work related to social expenditure. A requirement from the EITI is for companies to include social expenditure information but does not provide a definition of what this includes / entails. Given that some companies report certain payments, including specific taxes, as social expenditure, it is important to have a clear definition to ensure that the social expenditure payments truly benefit communities. A key result on with work is that OCEAN developed the first-ever social expenditure framework to better understand these social investments. Because of this work, OCEAN was appointed to the EITI-DRC sub-committee on social expenditures and TCC was asked to provide technical support to the sub-committee.

OCEAN also proposed to the Ministry of Mines, the standardisation of levels of social expenditure paid by companies, resulting in this recommendation being adopted under the revised Mining Code (0.3% of annual turnover to be spent on community development, etc.). Furthermore, OCEAN have developed a guidance note related to social expenditure and obligations which will be used to raise awareness amongst mining companies.

Lessons identified this year linked to this output and recommendations for future programmes

Given the actual scores for the satisfaction levels of partners came in below the expected target, a lesson has been to ensure better communication with partners prior to workshops and trainings so that expectations are better managed.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

Impact targets:
Overall, against the logframe targets, the TCC component of the programme has met and in numerous cases, exceeded expectations. At impact level, there were two indicators identified as follows:

  1. The DRC is compliant with the EITI.
  2. Cumulative number of sector-wide changes to fiscal governance of the DRC extractives sector influenced by civil society advocacy.

With the first impact indicator, the target has been achieved - the DRC is an EITI compliant country. It is expected that an ongoing validation exercise (underway at the time of this review) will reveal if DRC will remain compliant, but early indications are that DRC will remain compliant. With respect to the second impact indicator, again, this has been met. In 2018, President Kabila signed a new mining code, which reflects several reforms recommended by CSOs under the supervision of TCC through the programme. Such reforms included in the revised code relate to the allocation of 0.3% of mining revenues towards community development / social expenditure. Whilst there remains an opportunity to exceed the target (e.g. requirement to publish provincial tax data in EITI reports and strengthened obligations on social expenditure reporting), the total number of reforms achieved at the time of the review, had met the logframe target of 4 as follows:

1. Requirement of for companies to pay royalties directly to provincial authorities;
2. Requirement for companies to use linear depreciation as opposed to accelerated depreciation;
3. Requirement for all contracts to be published in French on the Ministry of Mines website; and
4. The mandatory publication of financial statements.

Outcome targets:
At outcome level, all the target indicators have been exceeded as follows:

Outcome Objective	Indicator	Target	Achieved
Outcome 1: Congolese civil society partners are able to effectively monitor, and advocate for improvements to, EITI-DRC processes and reporting	1a. - Number of partner civil society recommendations taken into account in final EITI-DRC reports and improved EITI-DRC process.	12	45
	1b. - Cumulative number of EITI contributions from civil society teams receiving TCC’s technical support that achieve a quality of at least 60%.	9	15
Outcome 2: Congolese civil society partners are able to effectively research and analyse revenue impacts and use their analysis to advocate for improved fiscal governance of key mining projects/companies	2a. Quality of civil society team’s case study interim deliverables.	Average of 68%	Average of 70%
Outcome 3: Congolese civil society partners are able to effectively utilize EITI-DRC data and other sources for advocacy to address sector-wide fiscal governance challenges	3a. Cumulative number of interim deliverables on using the data and associated advocacy from civil society teams receiving TCC’s technical support that achieve a quality of at least 60%.	6	22
	3b. Number of meetings with targeted stakeholders.	8	21

With such significant achievements, a degree of confidence can be had with respect to the level of influence this programme has had on the extractives landscape of the DRC. The voice of the CSOs is being heard and acted upon by the EITI-DRC and CSOs have succeeded in commanding a wide range of stakeholder audiences including government and mining companies in their advocacy campaigns.

Summarise the programme’s theory of change and major changes to it in the past year (1/2 page)

The original programme business case did not have a theory of change. The main objective of the TCC programme has been to improve the governance of the DRC extractives sector through increased access to data, improving revenues management and ensuring more responsive, sustainable and equitable extractives investment.

Given the early closure of the ProMines component, the current programme (comprising just the TCC component) is a considerable scale down of the original business case (both in monetary and results terms). However, despite this, the programme has still managed to deliver its overall objectives.

Explain major changes to the logframe in the past year (1/2 page)

The last Annual Review in August 2018 highlighted the major changes that have taken place on the logframe as follows:

LOGFRAME INDICATOR	ORIGINAL TARGET	FINAL TARGET
Outcome Indicator 1a - Number of partner civil society recommendations taken into account in final EITI-DRC reports and improved EITI-DRC process.	8	12
Outcome indicator 2a - Quality of civil society team’s case study interim deliverables.	60%	68%
Output indicator 1.1a - Percentage of men and women of civil society organizations that have increased their knowledge on the EITI process and reporting by at least 20%.	60%	72%
Output indicator 1.1b - Overall level of satisfaction among men and women of civil society organizations participating in TCC-led workshops held on monitoring and advocating for improvements to EITI-DRC processes and reporting.	60%	87%
Output indicator 1.1c - Cumulative number of contributions by members of civil society developed for use in advocacy with key targets of the EITI-DRC process	9	10
Output indicator 2.1a - Percentage of men and women of civil society organization that have increased their knowledge on mining sector revenue analysis by at least 20%.	60%	66%

These changes were a result of recommendations from the 2017 Annual Review as well as an assessment of the achievements made on the programme in the previous year. Following a challenge from DFID to TCC to increase the targets of the programme, a revised, more ambitious set of targets was agreed as outlined above.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

In August 2014, recommendation was made to exit from ProMines and to maintain oversight of the component “Advancing Transparency and Accountability in the DRC’s Extractive Industries” through TCC’s Accountable Grant. Through this grant, a recommendation was made to continue engaging bilaterally with the extractives sector, exploring possible areas of support including the Extractives Industry Transparency Initiative (EITI), the Katanga Extractives Industry Development Initiative (KEIDI), and conflict minerals.

It was assessed that to achieve Value for Money (VfM), ProMines’ objectives were to a) strengthen the government’s capacity to manage the mining sector, thus increasing the sector’s contribution to revenues; and, b) help make the mining sector in DRC more attractive to investors, thus further increasing the revenues generated by the sector. Given the underperformance on ProMines, it was deemed not to be achieving VfM and therefore offered no reasonable justification to continue.

The new phase of the programme stemming from the TCC Accountable Grant sought to improve governance of the DRC’s extractive sector by increasing data accessibility, improving revenues management, and supporting more responsible, sustainable, and equitable investment. This required extensive work in terms of technical support to civil society partners on key (and at times sensitive) extractives sector issues. The focus of the work was in stakeholder’s engagement as well as supporting the expansion and capacity building of Civil Society Organisations (CSOs), particularly in the mineral rich province of Lualaba and more specifically in the Kolwezi area.

As a result, the substantial resources were associated with staff salaries, consultant fees, travel, and meetings. In effect, these costs are the most significant drivers of project performance and contributors to achieving VfM.

To achieve VfM, TCC focused on the 4E criterium outlined by DFID: economy, efficiency, effectiveness, and equity. This meant rigorous management and monitoring of project activities spent through benchmarking, cost reduction; regular oversight of spending by civil society partners; limiting administrative overhead; women inclusion in all levels of project activities; building skills and an environment that ensures the project achieves sustainability.

Particularly, TCC had increased its level of scrutiny on mission costs (travel and meetings) which has led to savings on travel costs. For example, TCC reduced some of the costs by combining meetings which reduced the number of travel while lengthening the mission duration – thus saving on travel and possible terminal expenses.

Additionally, TCC put in a place a rigorous partner selection process which included technical and organisational capacity assessment tools and support to develop practical and efficient project budgets. Also, they used previously used but actual training modules to save time and resources and ensure timely delivery of activities.

Moreover, on benchmarking, staff salaries were in line with the market and competitive enough to deduce that TCC had recruited strong technicians to instil confidence and credibility in engaging with or supporting stakeholders. This benchmarking exercise was facilitated through participation in the Birches Group NGO Local Pay review of national staff in the DRC which DFID partakes in as well. On training spend, TCC has trained participants at a total training cost of approximately £145 per participant which is within the national and local (Province of Lualaba) average.

The strengthening of CSOs should be considered determinant in assessing sustainability which is evidenced by key outcomes achieved by the Dynamique des Femmes des Mines (DYFEM), Dynamique des Femmes pour les Ressources Naturelles (DYFREN), Action pour la Défense des Droits Humains (ADDH), the Organisation Congolaise des Ecologistes et Amis de la Nature (OCEAN) and Initiative Bonne Gouvernance et Droits Humains (IBGDH). These organisations have contributed to the EITI validation of crucial reports and action plans, to producing a comprehensive framework on social expenditures reporting, to promoting women’s inclusion in the extractive governance issues debate and to producing reports on provincial tax issues. These outcomes have durably cemented CSOs’ role as an official and recognised partner of the government (national and provincial) and mining companies.

Finally, considering the time lag between the Business Case addendum approval in June 2017 and the Accountable Grant finalisation and signature in August 2017 as well as the delays in the finalisation and publication of the EITI report which inherently caused delays in the activities of TCC, the Accountable Grant received a five-month no-cost time extension. This extension took the programme end date to 30 November 2018. The extension was instrumental in ensuring the TCC component was able to meet and, in several cases, exceed its targets.

E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

At the onset, the overall risk for this programme was originally assessed as severe. After the closure of the ProMines component, the programme risk was reviewed and downgraded to minor from 2015 to 2017.

This is because the programme was reduced to one live component managed through an Accountable Grant to TCC who worked with local CSOs. TCC undertook due diligence and put in place some contingencies prior to entering into funding agreements and prior to disbursing funding to the various CSOs which provided further risk mitigation on the programme. In addition to the Due Diligence Assessments that TCC undertook, TCC provided the CSOs continued support and mentoring throughout the duration of the Accountable grants.

However, during the last Annual Review conducted in August 2018, there were some concerns around the political economy of the extractives sector, the outbreak of Ebola in the eastern part of the DRC, and the tension and violence around the December elections. Although, all these risks were external, their impact deemed to be major and could have negatively affected the implementation of TCC and their partner’s work. As result, the overall risk was therefore reviewed and assessed as moderate. It is viewed that at the time of the programme closing, the risk was still assessed to be moderate.

No major issues arose since the last review. However, an outstanding issue yet to be resolved is the publication of the DYFEM case study on the Alphamin Bisie mine. Whilst DYFEM have completed the case study, its publication is delayed following a request from Alphamin to be awarded additional time to sufficiently review and address any inaccuracies within the case study prior to publication. As such, consensus is yet to be agreed between TCC and Alphamin on the content and timing of the publication of the case study. Discussions around this and agreement on the case study development and publication process, including the development of an MOU between the three parties (Alphamin, TCC and DYFEM) are ongoing. DFID is confident that a resolution will be found and that the case study will be published during 2019.

As part of the Accountable grant management, TCC submitted an updated risk register on a quarterly basis and any changes to the risks were raised and discussed during monthly meetings between TCC and DFID.

Update on partnership principles (1/2 page)

No funds were channelled directly through the DRC government. However, ProMines provided technical assistance to the DRC Ministry of Mines to support a proposed revision of the Mining Code; to conduct a strategic environmental and social assessment of the mining sector; to undertake an institutional audit of mining sector institutions (which has been useful to other donors, the government and civil society); and to draft a new strategy for SAESSCAM (an agency that aims to support small scale artisanal miners).

TCC’s support was essentially to CSOs so that they are empowered to contribute to the improvement of the DRC’s mining sector governance. Interaction with government was mainly through the EITI’s Executive Committee meetings, which was chaired by government.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The largest component of this programme was ProMines, originally designed as a £27 million World Bank-managed single donor trust fund for the “Growth with Governance in the Minerals Sector work” programme which provided technical assistance to the Government of DRC (GoDRC)’s Ministry of Mines.

The ProMines component ran from 2011 to 2014 and closed due to underperformance which included limited achievement of logframe targets and poor programme management capacity within the Project Implementing Unit (PIU). The programme also suffered from insufficient engagement from the World Bank in-country, in particular, their failure to provide a senior mining expert based full time in Kinshasa.

The funds committed at the time of DFID’s exit from the World Bank trust fund was £9 million out of which £4.8 million remained unspent. The World Bank refunded this remaining balance to DFID on 9 November 2016.

The financial performance of the ProMines is shown in the table below:

Promines Budget	Disbursement	Spend as of August 2014	Refund from World Bank	Total budget remaining at close of ProMines
£27,000,000	£9,000,000	£4,213,087	£4,786,913	£22,786,913

Given the total remaining budget available on the programme, a budget reduction was made in March 2016 (reducing the budget to £10.2m). TCC received three grants totalling approximately £1.32m, from DFID over a period of almost 4 years. For each grant, TCC submitted to DFID a proposal accompanied with a breakdown of their budget. At the end of each grant period and by the end of the programme, TCC had spent and accounted for all the grant funding received as outlined as follows:

Funding	Start date	End date	Amount (£)
Accountable Grant 1	October 2013	January 2015	136,927
Accountable Grant 2	September 2015	February 2017	643,632
Accountable Grant 3	August 2017	November 2018	539,000

As part of the programme reporting requirements, the accountable grants had provision for quarterly reporting. This included (1) a narrative of progress made during the quarter including a report on the progress made against the log frame targets; (2) a financial narrative, providing details of the expenditure made and costs incurred during the quarter; (3) an updated risk register and (4) an expenditure profile. For the final grant, DFID requested that TCC also provides an updated delivery chain map. All the deliverables were generally delivered on time and their quality met DFID’s expectations.

With respect to their final grant, TCC encountered some unpredicted difficulties to the start of their activities in relation to Objective 1. The work carried out as part of this objective related to the EITI implementation in the DRC. Given the delay in the publication of the DRC 2015 EITI report by the EITI-DRC, TCC were unable to start their activities with CSOs as planned. As such, the programme of activities had to be delayed until the 2015 EITI was published. This resulted in a significant underspend in Q4 2017 and lower spending as well in the subsequent quarters as compared to the original forecasts.

Grant disbursements are done quarterly upon submission of a detailed financial report and statement of expenditures. Forecasts were continually adjusted to reflect any lag in the programme workplan.

DFID recognised that more regular and direct communication with TCC was more effective than multiple email exchanges. As such, during the final grant agreement, monthly conference calls were arranged between DFID and the TCC team to go through progress in the month, any key issues and risks and to provide TCC and DFID to give each other any key updates on activities.

Date of last narrative financial report	31 January 2019
Date of last audited annual statement	28 September 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

Over the life of the grant, TCC have been actively monitoring and reporting the performance of their partners. Monitoring of the partners has included having regular ‘check-ins’ with partners through face-to-face meetings, telephone meetings and interactions during workshops – during the interviews with partners, DFID established that these have been taking place. The partners also confirmed that TCC visited them on average at least every 2 months (one partner, DYFREN, they indicated that ‘TCC has been with us all along the journey rather than just handing over the money and walking away’). Not only were TCC following up with their partner CSOs, but also with the EITI, with whom TCC have no partnership agreement, but are a key stakeholder in the delivery of the programme.

Due diligence assessments were undertaken on partners prior to disbursement of funding. With regards to training, TCC ensured that pre and post-evaluations of the training and workshops conducted were undertaken. The CSO partners also have an opportunity to evaluate TCC’s performance, something which is captured through the logframe as well.

The monitoring by DFID of the programme has been proportionate. However, given the strategic importance of the work being undertaken, and potential for the work of TCC and their partner CSOs to cause unease, DFID introduced, monthly progress calls in the last year to discuss monthly progress, key issues and risks, updates, finances and proposed activities for the upcoming month. This monthly call was attended by the DFID SRO, the DFID Programme Manager, TCC’s senior finance and administration team in Atlanta, USA, the TCC Country Director in Kinshasa and the lead Programme Manager in Lubumbashi. This regular forum helped DFID to keep on top of progress on the programme and any potential issues that may have arose. In addition to the monthly calls, adhoc meetings have taken place between DFID and TCC whenever the TCC team are visiting Kinshasa from Lubumbashi. Furthermore, DFID have visited partners in Kinshasa, Lubumbashi and Kolwezi as part of the field monitoring and review process.

Whilst this Project Completion Review has been primarily desk-based, it has largely utilised information gathered from field visits undertaken in August and November 2018 to Lubumbashi where DFID met with TCC and its partners based in Kolwezi and Lubumbashi, as well as the EITI both in Lubumbashi and Kinshasa. Furthermore, the review has drawn upon the final report received from TCC as well as previous progress reports received.

Evidence (1/2 page)

The impact of the programme has been evident through the changes in approaches and behaviours by the CSOs and key stakeholders as observed during the programme. At impact and outcome level, the targets set at the outset have been exceeded, demonstrating that the programme has already been making an impact on the ground. From the signing of the revised Mining Code (which incorporates recommendations from the CSOs that the programme supported), to visibly increasing advocacy efforts by the CSOs, the work of TCC has had a positive impact on the CSOs.

Additional sources of evidence of impact has been through interviews with the CSO partners, EITI and TCC staff. Some notable evidence of impact of TCC’s work has been:

- The payment of royalties by Kibali Gold, following the work on provincial taxes by the CSO partners
- The willingness of EITI to seek inputs from TCC and their partners during the process of developing their report and data, but more importantly, incorporating recommendations received into their work-plan.
- Participation of TCC and their partners at national-level EITI meetings.
- Incorporation of OCEAN’s proposal regarding the standardisation of social expenditure contributions from mining companies into the new Mining Code.
- Inclusion of TCC-trained CSO partners on the EITI-DRC Executive Committee
- The Feburary 2019, letter from Fredrik Reinfeldt, Chair of the EITI International Secretariat to President Carter acknowledging the Center’s work in the DRC and the transparency improvements observed.

Learning (1/2 page)

Several lessons have been learned over the life of the programme. The previous annual reviews have comprehensively captured the lessons learnt on the programme. In addition, following closure of the ProMines component, a lessons learnt report was produced, capturing the key lessons from the programme. Some key lessons include:

- Be clear and upfront about expectations, including on roles and responsibilities
- The need for close in-country engagement by the implementing partner.
- The need for flexibility to be built into projects from the outset to respond to changing situations on the ground.
- Have commonly agreed logframes and milestones.
- Having a common approach on fiduciary risk, with open information sharing.
- Improved financial management of Trust Funds, specifically disbursement schedules and liability relating to commitments upon exit.

During each quarterly report, TCC were required to report on lessons learnt during the quarter – a practice that was useful in keeping the continuous cycle of learning lessons at the top of everyone’s mind.

A key follow-up would be to ensure that future programming takes into consideration all the lessons that have been learnt on this programme. Some notable lessons learnt include:

- The value of relationships, visibility and organisational profile within the DRC extractives sector should never be under-estimated as these are all key to gaining influence and buy-in from the government and other key stakeholders.
- Working with CSOs is key element to unlocking improvements in the governance the DRC mining sector, including improved transparency and accountability. This is because unlike other countries, there is a high-level of engagement from CSOs with respect to matters concerning the extractives sector.
- If one is to be successful in advocating for change in the extractives sector in the DRC, they need to have a detailed understanding of the DRC mining sector, the mining companies’ operational models, reporting structures and political economy.
- Given the different levels of competencies amongst the partners, implementing partners need to ensure that they categorise partners / training recipients in terms of their level of experience and capabilities - a one-size-fits-all approach doesn’t always work.
- The sensitiveness around tax-related matters makes research work challenging, especially when dealing with the provincial authorities, as they are normally reluctant to discuss revenues, etc. it is therefore important to gain their trust and confidence to ensure they are engaged in discussions around finances, tax, etc.

Progress on recommendations from annual reviews for this programme (1/2 page)

Progress against the recommendations from previous annual reviews has generally been good and recommendations have been followed upon and progress captured and reported. The progress made on addressing recommendations from the 2018 annual review is outlined in the table below:

2018 Annual Review Recommendation	Progress made
TCC to leverage funding to maintain momentum and continue building CSO capacity	TCC are pursuing other avenues of funding. Residual work on the Alphamin case study for example will be funded from TCC’s resources.
TCC to work closer with the EITI-DRC to build their capacity and ensure long-term improvements in transparency and governance of extractives	TCC continued to work alongside EITI-DRC in finalising the programme work. TCC remain engaged with the EITI and relationships with the EITI are being maintained.
TCC to ensure public dissemination of the key findings from the revenue analysis work on TFM and Alphamin Bisie projects and to use the data for advocacy for economic reform	The case studies have been completed and awaiting input / comments from TFM and Alphamin. Once this process is complete, the case studies will be published.
DFID DRC to use evidence and the results achieved from this programme to inform wider policy and programming decisions with respect to the extractives / mining sector of the DRC.	Evidence and results to be used in the design of the new extractives business case which is due to be underway.