### Annex 1: Logical Framework DFID Uganda HIV Prevention Programme

PROJECT TITLE (max. 50 characters)			DFID AIDS Programme
GOAL	Indicator		Baseline + year	Milestone 2011	Milestone 2013	Target 2014
To reduce the number of new HIV infections occurring annually in Uganda	Annual number of new HIV infections in Uganda	Planned	120 000 (2009)			72000
		Achieved	Source
			UNAIDS, MoH Spectrum

PURPOSE (max characters 250)	Indicator 1		Baseline + year	Milestone 2011	Milestone 2013	Target 2014		Assumptions
	NPS operational guidelines developed and utilised at District levels to implement combination HIV prevention (CHP)	Planned	NPS developed but districts lack operational guidelines (2011)			Districts effectively implementing CHP		Successful programme interventions are scaled up and lessons learned effectively influence national policy
Improved effectiveness of the prevention response		Acheived
			Source

	Indicator 2		Baseline + year	Milestone 2011	Milestone 2013	Target 2014
	Proportion of adults aged 15 to 49 who have ever taken and HIV test and received their results	Planned	366% F; 45% M (2011)			xx F; xx% M
		Achieved
			Source: AIS
	Indicator 3		Baseline + year	Milestone 2011	Milestone 2013	Target 2014
	National gap on HIV test kits reduced	Planned	$15 (2013)			50% reduction in HIV test kits gap
		Achieved	Source
			MoH Lab costing
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£16m		£	£	£
INPUTS (HR)	DFID (FTEs)		M&E DFID (FTEs): / 0.04 Results Adviser
	0.25 Health Adviser / 0.25 SDA / 0.10 Economic adviser / 0.25 Administrative personnel / 0.5 DFID Project Officer / 1 FT Programme Staff

OUTPUT 1	Indicator 1		Baseline + year	Milestone 2011			Milestone 2013			Target 2014			Assumptions
Completion, implementation and monitoring of a national HIV prevention strategy and action plan	National HIV Prevention Strategy & Action Plan addressing socio-cultural and structural drivers of the epidemic	Planned	NPS under development	Approved NPS and Action Plan reflects understanding of socio-cultural and structural drivers & consensus on the response			NPS Action Plan updated for the period 2013 - 2015			NPS and Action Plan effectively implemented and updated in light of evidence emerging from M&E			The MoH will collaborate with UAC to build consensus and stakeholder buy in to the National Prevention Strategy, and stakeholders strive to implement the NPS
		Achieved
			Source
IMPACT WEIGHTING	Indicator 2		Baseline + year	Milestone 2011				Milestone 2013			Target 2014
15%	Effective intervention packages identified through the NPS	Planned	NPS under development	Effective intervention packages designed, costed and guidelines produced.				NPS implementation guidelines developed			Intervention packages implemented & delivering results
		Achieved						Operational Manual to guide implementation of the NPS 2011-2015 has been developed. / A report on the Costing of the NPS 2011-2015 including the Costing tool for HIV planning has been developed
			Source: WB EFO 421 progress
	Indicator 3		Baseline + year		Milestone 2011			Milestone 2013			Target 2014
	NPS monitoring and evaluation including evaluation of complex combination prevention	Planned	No M&E framework for the new NPS		Tender awarded for NPS monitoring and impact evaluation and baseline underway			NPS M&E guidelines developed / Impact evaluation of combination prevention in Rakai carried out and lessons replicated			Effective routine monitoring + impact evaluation of NPS carried out
		Acheived						Routine Monitoring Systems improvement Framework (data collection, management and use Systems) and Capacity Building Plan was delivered. Source: WB EFO 421 Progress note					RISK RATING
													Medium
INPUTS (£)	DFID (£)		Govt (£)	Other (£)			Total (£)			DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 2	Indicator 1		Baseline + year	Milestone 2011		Milestone 2013		Target 2014	Assumptions
Improved capacity of MoH and UAC to coordinate the implementation of the National HIV Prevention strategy	A functional M&E system for combination HIV prevention	Planned				M&E guidelines and system established		M&E system providing timely and accurate data for use in the JAR and other processes	M&E systems in the country get harmonised by MoH and UAC / UAC agrees to collaborate with KMCC towards capacity building of NADIC
		Achieved
			Source
	Indicator 2		Baseline + year	Milestone 2011		Milestone 2013		Target 2014
	Improved HIV strategic planning at district level	Planned				District HIV planning guidelines developed		At least 30 districts having and implementing HIV strategic plans
		Achieved
IMPACT WEIGHTING	Indicator 3		Baseline + year	Milestone 2011		Milestone 2013		Target 2014
25%	The National Aids Documentation & Information Centre able to synthesise, store and disseminate HIV information	Planned				A functional e-mapping system established at UAC		A revitalised and functional NADIC website
		Achieved			A web-based database for mapping of service organizations working in HIV sector at district level, what services they are providing and where they are providing these services was established including development of an Operations manual for the electronic data base;				RISK RATING
			Source WB EFO 421 progress note						Medium
INPUTS (£)	DFID (£)		Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)
	0.02 Results Adviser / 0Recovery Adviser / 0.20 Social Adviser

OUTPUT 4	Indicator 1		Baseline + year		Milestone 2011		Milestone 2013	Target 2014		Assumptions
Improved policy and practice through effective dissemination and uptake of HIV-related research, evidence and lessons learned from experience	Effectively functioning KMCC	Planned	No centre		KMCC created and costed work plan developed		Thematic knowledge presented to at least 2 major national events in 2013	Costed work plan has been implemented		Capacity exists and can be mobilised in Uganda to establish an effective KMCC / Stakeholders are willing to participate in review and debate of research disseminated by KMCC and to participate in its events
		Achieved				EMTCT Synthesis findings presented at not only 2, but 3 major national events (MoH national stakeholder conference, 2012, Uganda Society for Health Scientists (USHS) 14th Annual Scientific Conference May 2013 (along with a BCC knowledge synthesis poster presentation), and the Research, Academia and Science (RAS) Annual Experts’ Meeting in October 2013, (Approximately 300+ stakeholders combined) / Source: KMCC revised Log-frame Progress 2013
			Source KMCC reports, DFID reviews and evaluation
	Indicator 2		Baseline + year		Milestone 2011		Milestone 2013	Target 2014
	No of dissemination events and quality reports from HIV related bio-medical and social science research & analysis produced by KMCC	Planned	0					Regular events being held and analytical reports regularly published including in journals
		Achieved
IMPACT WEIGHTING	Indicator 3		Baseline + year		Milestone 2011		Milestone 2013	Target 2014
25%	HIV policy and programmes informed by quality operational and academic research including social science	Planned						National policy reflects research and analysis disseminated by KMCC
		Achieved								RISK RATING
			Source: KMCC reports, DFID reviews and evaluation							Medium
INPUTS (£)	DFID (£)		Govt (£)		Other (£)		Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)
	0.02 Results Adviser / 0 Recovery Adviser / 0.20 Social Adviser