Annual Review - Summary Sheet
Title: Support to the Public Procurement System in Mozambique
Programme Value: £3.9m		Review Date: September 2014
Programme Code: 202463	Start Date: November 2012	End Date: November 2016

Summary of Programme Performance
Year	2013	2014
Programme Score	B	A
Risk Rating	High	High

Summary of progress and lessons learnt since last review
The previous AR for this project was carried out nine months ago, when it scored a B mostly due to a slow start. Given our concerns, it was recommended that the next AR be brought forward to review progress over the second 6 months of implementation and coincide with the completion of the Inception Phase of the Technical Assistance (TA) component which had not yet started at the time of the last AR.

This AR incorporates key findings from the inception report and sets out an approach to respond to issues identified. The TA component started with an unexpected one-month delay (in February 2014); the inception report was delivered in August and an Inception Review took place in September. The next AR will be submitted in May 2015, so as to align annual milestones with government reporting cycles.

Overall, progress over this reporting period has been positive and the pace of implementation has picked-up with the successful integration of the TA component. Institutional relationships and ways of working have been consolidated and expectations of different stakeholders clarified.

An inception report for the TA component was submitted in August 2014. Detailed analytical reports on specific dimensions of public procurement operations and oversight are also available. These technical inputs have provided useful lessons and feedback on the current approach and validated some of the initial assumptions and risk assessments. The additional analysis has also provided a useful steer as to the areas of focus of the project (reflected in the revised logframe).

Following the completion of the TA inception phase, a number of follow-up actions have been identified, including a light restructuring of the project that will require a contract amendment. These are summarised below. Detailed commentary and analysis is provided in sections B and C.

Summary of recommendations for the next year
Based on the analysis in this annual review, drawing largely on the inception report, below is a list of actions to be completed before the next AR.

N	Recommendation	Timeframe	Responsible
1	Design additional indicators to meaningfully capture progress at the outcome and impact levels	December 2014	Lead Adviser with support from Statistics Adviser and CA
2	Review the TA contract to take into account the experience to date (as set out in Output 1 section)	October 2014	Lead Adviser with support from Programme Officer and Commercial Adviser
3	Appraise the timeframe and management arrangements for the Procurement Management Information System feasibility study and review outer milestones in the logframe	December 2014	Lead Adviser, CA, UFSA
4	Agree with UFSA which recommendations it intends to take forward with respect to its monitoring and compliance framework and support implementation	Ongoing	CA, UFSA
5	Be ready to be adaptable and flexible to exploit potential windows of opportunities that may open after the elections, for tackling some of the more difficult reforms including through use of short term TA resources.	Throughout 2015	Lead Adviser, CA, UFSA
6	Prioritise capacity-building activities over the next three months and monitor closely	December 2014	CA
7	Encourage UFSA to consider alternative models for undertaking training of UGEA staff and support implementation	Ongoing	CA, UFSA
8	Increase the visibility of the programme and strengthen links with other actors interested in procurement reform; use procurement working group meetings to provide regular updates on the programme to other development cooperation agencies	Continuous	Lead Adviser
9	Review and streamline management arrangements for the pilot sector component (as set out in section D)	November 2014	Lead Adviser, UFSA, MINED
10	Work with UFSA to improve financial and performance reporting	Continuous	Lead Adviser with support from Programme Officer

For completeness below is an update on each of the recommendations from last year’s AR.

Recommendation	Update
Clarify working arrangements with UFSA, and MINED and the TA support	Done, but these will need to be further refined to take into account lessons from the inception phase.
Revised the logical framework to review the timeframes for milestones, across all outputs and identify interim milestones for end June 2014	Done. The logframe was updated in March, with QA and signoff by Results Adviser.
Monitor the quality of the reports extracted from e-SISTAFE and based on the available sample define a baseline for indicator 1 (Output 1)	Ongoing. However, this is now less relevant as in the revised logframe different indicators have been identified to capture progress around the MIS dimension. This continues to be an area of focus of GBS PAF monitoring.
Use TA to appraise the extent to which the changes to the statutes of UFSA and DPPFs mitigate some of the institutional issues in the way procurement oversight is enacted, and the implications for the activities and milestones envisaged under output 2	Done. A comprehensive analysis on the legal and institutional environment for procurement monitoring and compliance is now available, with detailed recommendations for UFSA to consider.
Hold an early kick-off meeting with the TA when in country in order to agree priorities for their initial work plan including a plan to catch up on delayed output areas (particularly 3, 4 and 6). Once TA work plan agreed at technical level with TA and UFSA, organise high level meeting (Head of Office and Vice Minister)	Done. Successful kick-off of inception phase held. High level meeting was deprioritised in light of gradual progress shown. Meeting between the Vice-minister and High Commissioner was used as an opportunity to stress the importance of this project.
Explore synergies in the planned programme of support to CEDSIF to facilitate and accelerate the implementation of activities focussed on procurement-related information systems and private sector communications and interactions	Ongoing, with progress (see section on MIS for detail).
Use the TA to facilitate dialogue between UFSA and MINED and generate more traction for this programme within the sector.	Ongoing. Communication issues persist and role of facilitator has in part been played by DFID.
Undertake an additional Annual Review in July 2014 to check progress over second 6 months of implementation and review TA inception report	Done, but submitted with a one-month delay due to a postponement of the start date of the TA contract.
Agree on a revised reporting calendar for the programme which aligns with Government financial and performance reporting timeframes whilst also meeting DFID requirements and make changes in DFID internal systems	Done.
Continue working with education sector colleagues in Human Development Team to facilitate engagement with MINED and other education sector donors, and to input to TA work plan for education sector.	Ongoing. It is recommended that approach to MINED component is reviewed to facilitate management and oversight and take into account lessons learnt to date.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3743498.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4586030.xlsx

Outline of the programme
The UK is providing £3.9m over the period 2013-16 for strengthening public procurement operations and oversight in Mozambique. Of this amount, £2.6m is financial aid to the GoM and £1.6m is for a Technical Assistance (TA) package managed directly by DFID and delivered by Crown Agents (CA).

Mozambique has made significant progress in updating the legal and institutional framework for public procurement, with the approval of modern regulations in 2010 (which updated and improved a decree from 2005), and the establishment of a Procurement Oversight and Regulatory Agency (UFSA in its Portuguese acronym) in 2005. Other key functions of UFSA are managing a procurement information system, for monitoring overall trends and implementing evidence-based policies, and providing guidance and capacity building to public procurement practitioners.

However, in terms of implementation, procurement reforms have been lagging behind relative to other core areas of PFM, as evidenced by: lagging procurement-related PEFA sub-indicators; analysis contained in the 2008 update to the Country Procurement Assessment Report (CPAR); and procurement-related recommendations emerging from annual Auditor General reports on State Accounts and external audits commissioned for donor-funded programmes (e.g. large basket-funds in health and education).[1]
[1] See background material used in appraising and designing the project for detailed information on the most common procurement issues and weaknesses.

Weaknesses have been identified both at the operational level i.e. capacity and practices of decentralised procurement units (UGEAs) especially at the provincial and district layers of administration, and at the supervisory level. UFSA currently has limited capability to adequately perform its core functions.

Donor funding targeted at procurement strengthening and reform has, in recent years, been scarce. It has focused more at the operational/UGEA level (especially in the context of support to particular sectors and/or selected provinces and districts), rather than at strengthening overall policies, processes and oversight of the national public procurement system as a whole.

This DFID comprehensive programme of support to UFSA, complemented by a pilot component focused on facilitating dialogue and interactions with the Education sector was designed to fill an important gap in support to key aspects of the procurement function in Mozambique’s public sector. The inclusion of the sector pilot is to ensure that reforms are not tackled and supported only by central institutions (e.g. Ministry of Finance) and from the top downwards (by national level ministries) but also from a sectoral level and at deconcentrated operational levels. This multi-pronged approach for supporting coordinated reforms at a national and sectoral level was expected to increase the pace of reform by generating ownership outside of the central ministry responsible for regulations and policy setting.

DFID is providing financial aid and a comprehensive package of TA to support reforms in the following five output areas:

1. Strengthened UFSA's performance through the provision of high quality strategic support
2. UFSA's strategies plans and operations are informed by evidence on procurement
3. An effective monitoring and compliance framework supports UFSA's oversight function
4. Enhanced capability of UGEAs to undertake more effective, efficient and transparent procurement
5. Improved public access to public procurement information

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The outcome statement is “Public institutions at the national and provincial levels run transparent and open procurement competitions”. The indicators chosen to track progress focus on compliance with procurement regulations i.e. the number and percentage of public sector contracts that are granted prior approval by the Administrative Court or the extent of follow-up to procurement recommendations made by the internal and external audit institutions. At present, under a third of contracts are granted prior approval by the Administrative Court, while the rest are either rejected or returned for clarifications, additional supporting documents etc. A baseline on procurement-related recommendations emerging from audits is still being firmed-up.

It is expected that the programme will contribute towards an improving situation over the medium to long term. A limitation of the selected indicators is that a negative trend might in fact be a function of stronger frequency, coverage and depth of audits, rather than a worsening compliance environment. They also focus on procedural compliance, rather than the quality i.e. “value for money” (VfM) of procurement for the Mozambican public sector. As a result, complementary indicators should be used to monitor progress. For example, the indicator selected for impact level (i.e. “extent to which independent assessments such as the World Bank's Country Procurement Assessment Review - CPAR or the Public Expenditure and Financial Accountability - PEFA framework provide evidence of improving public procurement”) could also be used to track progress against the outcome indicator. Going forward, additional indicators that can be meaningfully used to capture progress at the outcome level will be included in the logframe (recommendation).

The impact statement is “The public procurement system ensures more efficient public spending”. The assumption is that all of the output areas supported through this programme would contribute towards improved assessments on the quality of systems and processes through which goods, services and works are procured. In turn, these can be used as a proxy indicator for assessing whether the system is enabling greater VfM from public spending in Mozambique. Ultimately, the end-result that this programme strives to achieve is more/better public service delivery for Mozambicans.

Overall output score and description
Despite some persisting challenges with the education component, the direction of travel since the last annual review has been sufficiently positive to conclude that overall outputs have met expectations (i.e. projects scores an A)

Key lessons
Experience with this programme so far, confirms that institutional reforms are complex, unpredictable and require a long-term horizon for implementation. Similarly, it is important that a programme designed to address them can be sufficiently flexible to adapt in response to emerging challenges and opportunities that come with a dynamic operational environment and fluid incentives (as a result of e.g. elections, high profile cases of corruption etc.) Additionally, assumptions underpinning programme design have to be constantly revisited, on the basis of what is/is not working in practice and may/may not be feasible following findings that may only emerge as a result of more detailed assessments carried out during implementation. Linked to the latter, is the fact that TA can have a significant impact and act in some cases as a catalyst for the programme, if the right person is involved.

On reflection, the experience with the pilot sector component is a reminder about the value of undertaking a proper institutional appraisal before agreeing a programme, and investing an adequate amount of time to carefully set-out management arrangements. Taking the lessons above into account, the education sector pilot component requires a critical review. This component was always expected to be complicated, but after a year of implementation the institutional buy-in from MINED remains weak, and the financial and management arrangements between UFSA and MINED do not properly function to ensure effective use of the Financial Aid component resources available for the sector. Combined with the fact that the TA engaged for the sector has also been unable to support progress – in stark contrast to the TA working with UFSA – this review (see Output One below) sets out a set of changes to project design based on these lessons.

Looking ahead, it is recommended that the approach to the education sector component is reviewed to take into account lessons from the TA inception phase, and practical difficulties experienced from a programme management and coordination perspective (see commentary and analysis under outputs 1 and 4 and section D).

Key actions
Already covered in summary sheet - under “summary of recommendations”.

Has the logframe been updated since the last review?
Yes, reviewed in March, to streamline the number of indicators and increase the overall coherence of the TA and pilot sector component with the overall objectives of the programme. This was to mitigate the risk of MINED activities being treated as if belonging to a separate project, and better reflect the role of the substantial TA package. There was also an effort to recalibrate indicators at a level in which performance is directly linked to responsibility and accountability for delivery by the implementing actors, and less affected by factors outside programme’s control.

The revised logframe is much more qualitative, to account for the fact that institutional reform processes are usually very dynamic, uncertain and difficult to capture through quantitative yardsticks. Proposed indicators are also reflective of the current state of procurement management information systems (PMIS), which do not offer a reliable basis on which to craft meaningful performed indicators on the overall quality of the system (in terms of driving VfM for the public sector). The programme will try to change this and in the future it might become possible to establish reliable baselines (see output 2 for a detailed discussion).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened UFSA's performance through the provision of high quality strategic support
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Planning and management of UFSA's operations reflect strategic priorities	High quality medium-term strategy developed and owned by UFSA	Met. A strategic planning process was facilitated by the resident TA and a Strategic Plan aligned to the next government cycle (2015-19) has been drafted. Formal approval will have to await the formation of a new government.
Targeted TA outputs delivered to strengthen UFSA and MINED operational and organisational performance	Urgent TA needs jointly identified with UFSA, MINED and CA / Scope defined for the delivery of TA support in specifying business requirements for the development of e-Procurement modules	Met. Four work-streams for short-term technical assistance have been identified. Of these two are already underway. Some mentoring of UFSA’s management has also been undertaken. The resident TA is also helping with the redefinition of internal work processes and staff allocation to enhance UFSA’s effectiveness. / Met. Officials from UFSA and CEDSIF have agreed that any plans for introducing e-Procurement modules require careful appraisal and planning. The project will provide support in this area (See discussion under output 2)

Key Points
On the whole, in light of the initial difficulties and sensitivities around agreeing an approach for TA to this programme, in procuring a supplier and negotiating a TA contract[2], this output area is now on track. After a long procurement process and a slow start in getting the TA component up-and-running, the choice of modality and supplier for the delivery of this component seems to have paid off. The senior international TA, posted to UFSA, is held in high regard and has had an immediate impact. Some short-term TA (STTA) outputs have actually been brought forward to the inception phase, showing good ownership of the TA by UFSA, and willingness to fully exploit the opportunities offered by the DFID contracted supplier. It has also become clear that the short-term TA needs are higher than anticipated.
[2] The current contract with CA comprises of a package of long and short term TA. The long-term TA component (LTTA) consists of a senior resident adviser for UFSA and a resident adviser for MINED. The short-term TA (STTA) comprises of 100 days of international-level TA and 100 days of national-level TA to be mobilised on a call-down basis over the duration of the contract.

On the other hand, the six-months inception period has shown that whilst the international adviser has met expectations, is well respected and integrated within UFSA, the long-term adviser allocated to MINED has not had the same impact and limited progress has been made in the pilot sector. STTA has not yet been requested by MINED. It is clear that the Long-term TA (LTTA) in MINED is not operating at the right level and not playing the envisaged role within the project. This partly reflects MINED’s lesser commitment to the programme as a result of limited technical engagement, evident constraints on our key senior counterpart’s time, inadequate coordination and communication with UFSA, and a general sense of diverging expectations as to what MINED’s role within the project ought to be (i.e. pilot sector for a whole-of-government reform process rather than a separate project within a multipronged programme).
Following recent discussions with programme stakeholders, it has been agreed that the structure of the TA package ought to be reviewed, to reflect lessons coming out of the inception phase.
To make the TA package more effective it is proposed that the LTTA to MINED element is removed, and that the STTA resources available across the project are increased. The latter builds on the fact that there has been a good level of demand for these to date. The sector would still benefit from STTA resources by submitting proposals through UFSA and CA. This should make support to the education sector under this programme far more demand-led. The proposed review of the TA component would be complementary to changes proposed to management arrangements (see recommendation under section D “VfM and Financial Performance”).These proposed changes have been raised with MINED, and careful handling of communications will be required, to ensure a smooth transition of the TA project from inception to implementation.

Summary of responses to issues raised in previous annual reviews (where relevant)
NA

Recommendations
Use the end of the inception phase to review the programme’s TA component, to take into account the experience to date. Ensure that the necessary steps are taken to agree with CA a light-touch amendment of the contract (with support from CPD as required).

Output Title	UFSA's strategies plans and operations are informed by evidence on procurement
Output number per LF		2	Output Score	A
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
A reliable and user-friendly MIS is introduced to generate relevant, accurate and timely information on procurement operations (with a focus on MINED)	MIS concept and strategy developed and approved	A diagnostic of current situation and MIS concept is available and a way forward has been agreed. A strategy as such has not yet been prepared as more appraisal work is required.

Key Points
This is a critical area to achieving efficient public procurement and value for money but where substantial progress might only be possible in the long-run due to the complexities involved in implementing any chosen solution.
A diagnostic of the current situation undertaken in the context of the programme, concluded that the lack of an established Procurement Management Information System (PMIS) means that at present, the availability of accurate procurement data is weak, as are the tools to efficiently produce reports for both the UGEAs and UFSA. At present, almost all procurement information is collected manually due to the lack of a government-wide PMIS or an e-procurement system. Some PMIS needs can be fulfilled by a good public procurement portal, but this is not the case in Mozambique (see discussion under output 5) where a portal exists but has limited functionality.
A functionality was also developed in the context of the programme to capture the value of expenditure going through GoM's IFMIS (e-SISTAFE) for each procurement regime and modality before payments are processed. Since becoming operational in mid-2013, the functionality has made it possible to disaggregate, for the first time, approximately MZN 21.6 billion (roughly £450 million) of public expenditure on goods, services and investments executed through e-SISTAFE into different procurement modalities. The new data generated by the functionality highlights that, in the second half of 2013, 45% of expenditure was made against contracts that were non-competitively awarded. Some of this may be well justified, but overall this is high. Data for a full year will be available early in 2014 and will provide a good basis for monitoring trends going forward. It is also expected the data to be more reliable, given that a reasonable testing period was allowed and that and that users have now been trained in its usage. Even if the functionality represents a useful interim tool, for raising awareness of the scale of direct awarding, its coverage and potential as a PMIS and system’s performance tracking tool are very limited. Data extracted from the functionality will be uploaded on UFSA’s portal as of next year (an important first step towards increasing the public availability of public procurement statistics).
A single and more comprehensive PMIS would make it possible to have all procurement related information in one place to facilitate access by the private sector and monitoring by UFSA. The report recommends that the collection of procurement data and reporting should be strengthened by the phased implementation of e‐procurement. It also recommends that the Government undertake a feasibility study and develop and implement a long term strategy for the phased introduction of e‐procurement with initial emphasis on PMIS requirements. Concretely, CA advise is that UFSA should appraise the viability of acquiring an “off-the-shelf” e-procurement system, and initially use its portal, PMIS and reporting components, before, over a number of years, introducing automated procurement transaction e.g. publications of tenders by UGEAs on a single, government-wide procurement portal, and electronic submission of bids by suppliers (e-tendering).
While this appears to be the trend globally, and potential efficiency gains from the successful introduction of such a system are significant (estimate is at least 5%), so are the risks, especially in a low capacity environment such as Mozambique. A high degree of caution and extensive preliminary analysis is warranted, to avoid potentially high waste of resources invested. Additionally, to be sustainable, any strategy and programme in this area should be led by, and fit the needs of UFSA i.e. the business side, rather than being driven by than IT (as has tended to happen in Mozambique due to the capacity mismatch between public institutions and CEDSIF, the agency responsible for introducing and managing IT systems in the public sector).

These findings and proposals were discussed in a recent meeting held by all interested parties (DNP, UFSA, CEDSIF, CA, MINED and DFID), which was useful to harmonise concepts and terminology, and served to agree a way forward. Key points that emerged were that:
- A comprehensive solution tailored to Mozambique’s needs and capacity has to be sought. Parallel systems developed at sector level should be avoided as they fragment the data into different systems, and can pose obstacles to the private sector. Any reform in this area should be led by UFSA.
- The implementation of a single government-wide PMIS, selecting MINED as one of the pilots, is preferable (Discussion around MIS appears to be the only area with some traction within MINED, and where some productive technical discussion has taken place. This positive engagement should continue so as not to lose momentum).
- Although the potential benefits in terms of VfM are huge, so are the risks of implementing any comprehensive PMIS and strategic decisions in this area need to be preceded by detailed scoping and appraisal work, to carefully weigh the different options available.
- A feasibility study, which would include an e-readiness review, should be undertaken to ensure that any plans are implemented at a pace appropriate for the conditions of Mozambique (including the private sector). An offer by CA to undertake a viability assessment was taken up. This would lay the groundwork for a strategic (and costed) roadmap to be implemented in the long-term.

Summary of responses to issues raised in previous annual reviews (where relevant)
NA
Recommendations
Appraise the timeframe and management arrangements for the feasibility study and review outer milestones in the logframe.

Output Title	An effective monitoring and compliance framework support UFSA's oversight function
Output number per LF		3	Output Score	B
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Effective tools and methodologies for monitoring UGEAs compliance in a systematic way are developed, tested and mainstreamed (with a focus on MINED)	Monitoring and compliance framework (and implementing tools) developed and agreed with UFSA and MINED	Partly met as activities are still ongoing. A review of the current situation with strategic options for improving this key UFSA function was presented. The revision of supervision tools and methodologies has been agreed and options are under discussion.
Evidence of improved coordination, data sharing and strategic collaboration with the internal and external audit institutions (Inspector General of Finance and Administrative Tribunal)	Diagnostic of current efforts and proposals for streamlining and improving activities and information sharing presented	Partly met as activities are still ongoing. This was undertaken in the context of the same report. There is evidence that UFSA is already collaborating more closely with IGF and TA. / Strengthened interaction and information sharing with other control bodies is also one of strategic objectives identified in UFSA’s Strategic Plan for the next governmental cycle (see output 1).

Key Points
The TA report on the procurement M&C framework concludes that the legal landscape in Mozambique is an issue, as existing legislation is complex and not always coherent. For example, there is a need to clarify and simplify concepts and responsibilities around the broader control and supervision functions within the public sector. Compliance also appears to be hampered by the absence of secondary legislation, detailing the “how” in addition to the “what” contained in the public procurement regulations. The assessment also points out that the institutional architecture is equally complex and that UFSA’s existing position is problematic. Best practice is that oversight bodies should be autonomous with enhanced powers of enforcement relating to compliance and supervision. UFSA is currently not in a position to take action against procurement units that it finds to be in breach of legal provisions.

The same report is also critical of UFSA current model for procurement oversight/supervision, which is overly centralised and inefficient (as base on field missions by centrally-based staff and not sufficiently analytical and strategic). The external communication and dissemination of findings could also be much improved and the visibility of UFSA’s supervisory role enhanced (this could be supported through the revamped procurement website - see output 5). The report suggests that UFSA supervisory role should be much more intelligence-focused to reflect trends of increased decentralisation and enhance cost-effectiveness.

It is clear that implementing the resulting recommendations around high-level and politically-charged issues such as harmonising/streamlining legislation and institutional architecture, introducing secondary legislation on procurement, and elevating UFSA’s position, are outside of the project’s control. Appetite for PFM reform by the new government will determine the programme’s room for manoeuvre in supporting sensitive reforms around rethinking the legal and institutional framework.

At the same time, the programme can contribute to enhancing UFSA’s oversight role, by improving the quality of day-to-day operations. Resident and STTA can be used to help clarifying concepts around types of monitoring and supervision activities (e.g. to differentiate between compliance/audit and supervisory/advisory functions); introducing tools and methodologies that are more fit for purpose; and strengthen capacity for analysis and follow-up to findings.

Summary of responses to issues raised in previous annual reviews (where relevant)
NA

Recommendations
- CA to agree with UFSA which recommendations it intends to take forward with respect to the M&C framework and support implementation.
- Be ready to be adaptable and flexible to exploit potential windows of opportunities that may open after the elections, for tackling some of the more difficult reforms including through use of short term TA resources.

Output Title	Enhanced capability of UGEAs to undertake more effective, efficient and transparent procurement
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Evidence of strengthened UGEA capacity, with a focus on MINED	Training Needs Assessment (TNA) tool developed and approved / Operational guidelines and manuals reviewed and improvements suggested (with a focus on MINED) / Options for professionalising the procurement function presented	Some TNA undertaken at the level of MINED central and Maputo Province district UGEAs / Review of MINED procurement manual undertaken / Delayed. However, STTA identified and mobilised, work is currently underway

Key Points
On the whole, progress against this indicator has been limited. Envisaged provincial and district-level TNA of a sample of UGEAs was constrained by logistical problems and were not undertaken to their planned extent.

Finding ways that can ensure a greater professionalization of the procurement function within the public sector is an UFSA priority. International STTA has been mobilised and is underway to help establish minimum requirements for UGEAs in terms of staff skills and composition, structure and governance. This input is expected to contribute towards a MF directive (diploma ministerial) aimed at standardising UGEAs characteristics and composition, which at the moment is left at the discretion of each of the more than 1000 spending units in the public sector. The directive is planned to be submitted for approval within this year. This regulatory initiative is seen as a first step towards the mandatory certification of procurement skills and, potentially, a procurement career stream. The latter is, however, beyond UFSA’s control and requires coordination and agreement with other institutional actors inside and outside MF (e.g. the Civil Service Ministry) before reform proposals can be submitted to Parliament.
Further STTA has been requested to follow-up on the aforementioned activity and prepare a TNA of UGEAs, that will feed into a comprehensive technical training programme to attend the needs of UGEA staff. ToRs have been drafted for the mobilisation of support for appraising capacity-gaps within UFSA and designing a training programme to improve UFSA’s staff technical knowledge (e.g. information management, planning, supervision) as well as behavioural/soft skills (e.g. leadership and communication). The resulting action plan for the implementation of both training programmes (including the identification of a service provider) will include proposals for future certification of skills.

An option for enhancing UFSA’s capacity-building function, is to outsource to a private service provider, at least the basic-level training currently given to UGEA staff. This would enable UFSA to focus on developing and structuring training programmes rather than giving them. This recommendation was given by CA following an assessment of the quality of UFSA’s trainings, and is currently under consideration by UFSA, as would entail a radical departure in the approach to training from the one followed to date.

Summary of responses to issues raised in previous annual reviews (where relevant)
NA
Recommendations
- Prioritise this activity over the next three months and monitor closely, to ensure that trainings are delivered to a high standard and add value to both UGEAs’ procurement management, and UFSA’s strategic oversight.
- Encourage UFSA to consider alternative models for undertaking training of UGEA staff and support implementation.

Output Title	Improved public access to public procurement information
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Evidence of gradually improving UFSA internet portal (in terms of publishing relevant and timely procurement information to bidders and the public)	Analysis of the quality of UFSA's internet portal and benchmark against minimum quality standards. Agree plan for implementation of short-term improvements. / Support ongoing efforts to clean and integrate the suppliers databases into a single registry to be made available online / Design process for gathering private sector and public demand for procurement info to inform medium/long term improvements to portal	Met. Redevelopment of the procurement portal is well advanced. / Ongoing. Current engagement is limited as this work-stream is being led by CEDSIF, but likely to increase in the future (linked also to developments under outputs 2) / Ongoing. Many of the shortcomings in public access to procurement information will be addressed by the upgraded website (planned to be launched before year-end)

Key Points
An analysis of UFSA’s website was carried out by CA’s resident TA, and a proposal for upgrading has been agreed by UFSA. This has involved analysing the current information maps and functionalities and benchmarking against other portals internationally to identify gaps in meeting the information requirements, for suppliers and other stakeholders, as laid out in the procurement regulations. Following the submission of a detailed report identifying needs and proposing a phased development of a new layout and additional functionalities, UFSA has given the go-ahead for implementation. CA is supporting the project design and management in collaboration with UFSA’s IT department.

A potential quick win that could be facilitated by the upgraded portal, is the publication of bidding announcements and contract awards online, which is limited at present. Making it compulsory, would require a revision of the procedures for the mandatory procurement-related advertising, which currently has to be done through the daily newspaper with the highest circulation, at a significant cost for UGEAs (that need to factor this cost in their budgets). The portal upgrade could also provide opportunities to support some PMIS function (as an interim solution)
In UFSA’s next Strategic Plan, the objective of creating an official forum on procurement was introduced. This is intended to bring together interested parties from the public sector, the business community and civil society to openly discuss public procurement-related issues and agreeing remedial actions. The project will support this activity. Potential stakeholders have been mapped and initial meetings have been held, or are planned, with actors from the private and non-profit sector (such as Mozambique’s Procurement Professionals Association – APPROCUR).

Summary of responses to issues raised in previous annual reviews (where relevant)
NA
Recommendations
- Use the work-stream on the procurement forum to increase the visibility of the programme and strengthen links with other actors interested in procurement reform (from private sector, civil society and donors/multilaterals).
- Use procurement working group meetings (in the context of Budget Support M&E framework) to provide regular updates on the programme to other development cooperation agencies and explore potential for complementarities and linkages with other ongoing/planned interventions in this area.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The programme has a financial aid component and a TA component managed by DFID. A disbursement of £400,000 was made to UFSA in late June 2013. Of this amount, just 55% had been executed up to August 2014 (of which 20% in 2013 and 35% in 2014). Another disbursement is planned for this year, pending the satisfactory closure of the audit of 2013 project accounts (currently underway).
14 months after funding was made available, these evidence points towards weak absorptive capacity at UFSA; this will be monitored closely alongside future disbursement planning.

Activities funded with the financial aid component in 2013 include: expenses associated with the development of a functionality for capturing procurement data in Mozambique’s financial management system; training of UGEA staff in the use of the system and how to input data; training of UFSA in data analysis and presentation; a study tour of peer oversight agencies abroad; production and dissemination of procurement procedures manuals; training of provincial-level focal points; field supervision of UGEAs and activities around the development of a goods and services catalogue with standard specifications and new single suppliers registry (requirement specification and IT development) in collaboration with CEDSIF.

Implementation of these activities continued in 2014, where they benefitted from and were complement by the TA package commissioned by DFID and operational since February. In June 2014, UFSA organised a high-level seminar in Maputo focused on issues of public procurement and asset management, with participation of international speakers from peer agencies.
In economic classification terms, the breakdown of expenditure in the two years, translates as follows.

Economic classification	2013 / (million MZM)	Share (%)	2014 – up to August / (million MZM)	Share (%)
Expenses w/ personnel	0.7	18%	0.2	3%
Goods & services	3.2	82%	6.2	97%
Capital goods	0	0	0	0
Total	3.9	100%	6.4	100%

Of the DFID-managed TA component, £194,905 has been spent to date, amounting to 13% of the overall value of the contract with CA (£1,492,675). The contract is fully output based but, based on the agreed budget, key cost drivers are consultancy fees and associated expenses (travel, accommodation etc.)

VfM performance compared to the original VfM proposition in the business case
Project realities have changed since 2012. The approach to measuring VfM will also change to align with changes to project design and to the logframe and to ensure that VfM reporting effectively captures both the VfM of UK spending, and the increased VfM of Mozambican public expenditure that we are trying to induce. For example, support that TA has already provided for limited cost, to introduce new approaches and methodologies for procurement oversight, is likely to lead to reduced non-compliance with procurement regulations and significant efficiency savings for public spending across the board. A concrete example of a likely VfM gain, has been CEDSIF’s buy-in with regards to the need for Mozambique to undergo a thorough feasibility study, before rushing into investing in the development and roll-out of ICT solutions for procurement MIS and transactions’ automation (the cost of which can run into tens of millions of dollars over the duration of the project). Experience elsewhere suggests that solutions designed without taking into account capacity and technological constraints have a high risk of failure, which is why the move towards a more cautious approach by the MF in this area is a welcome development. Support to improve the quality of UFSA’s strategic and operational planning processes, and early steps towards the accompanying organisational restructuring, is also conducive to greater VfM, as a result of more prioritised, and thus more effective, procurement oversight activities.

On a more general level, given the very issues that this programme is trying to tackle, any progress against logframe indicators will, in and of itself, drive greater VfM for public spending (including that financed by DFID support channelled through government). The planned review of the TA contract will also drive greater value for money for the programme.

At the same time, this AR has identified additional opportunities for driving VfM at a more strategic level, which will be tracked going forward. These are listed below. This approach to VfM monitoring will be agreed with UFSA and CA alongside the proposed changes to the project design upon approval of this AR.

Table 1: Proposed VfM indicators
Indicator / VfM element	Rationale	Target / Timeframe
Progress against PMIS Strategy (also see logframe output 2) / economy, efficiency, effectiveness, cost-effectiveness	Reliable procurement system baselines would only be available with the introduction and mainstreaming of a PMIS that can enable recording data on transactions across all stages of the procurement cycle (such as procurement plans, notices, tenders, contracts and payments). This will enable the establishment of reliable baselines for tracking performance of the procurement system by UFSA (e.g. to spot bottlenecks in the cycle and large variations in unit-costs)	To be set-out in PMIS Strategy. Annual Reviews to qualitatively describe progress and how this is yielding VfM. / 2015/16
Improvements in UFSA model for procurement supervision (also see logframe output 3) / efficiency, effectiveness	Current model is overly centralised and inefficient (as base on field missions by centrally-based staff and not sufficiently analytical and strategic).	Evidence of different model being adopted (with support of TA) and estimates of efficiency gains / 2015/16
Improvements in UFSA model for training UGEA staff / (also see logframe output 4) / effectiveness, cost-effectiveness	Current model means UFSA staff-undertake all procurement training of thousands of UGEA staff. Recommendations have been provided to encourage outsourcing at least basic training to a service provider, so as to improve quality and free-up UFSA staff for more analytical and strategic oversight roles	Extent of take-up of advice on reviewing the training model, and evidence of implementation / 2015
Cost savings by UGEAs from the online publication of bidding announcements and contract awards rather than in newspapers (at least 500USD per procurement-related insertion per day) / Economy	The procurement portal upgrade offers an opportunity to consider mainstreaming the availability of bids/awards notices online	TBD as significant efficiency gains contingent on changes to legislation / TBD

Assessment of whether the programme continues to represent value for money
The proposed changes to programme design will help deliver improved VfM for the programme as a whole. At a more strategic level, important VfM gains are also likely to be driven by this intervention. More than half public expenditure on in Mozambique goes through the procurement system: even a marginal improvement in the system’s overall effectiveness, efficiency, transparency and integrity can generate huge economic gains for both the public and private sectors. These are hard to quantify, as would be the project’s attributable contribution. Strengthening the public procurement environment in Mozambique should be seen as a gradual and long-term process that will also require improvements in areas that go beyond the scope of this project.

At the same time, in light of the positive initial steps in a number of crucial areas of institutional reform, and of the encouraging signs in terms of stronger ownership of the programme by UFSA, the assessment is that the programme represents VfM.

Quality of financial management
For the financial aid component of the programme, we rely on UFSA’s reporting against activities and budgets. Evidence to date confirms weak internal capacity for planning, budgeting, budget management and financial reporting. Various iterations for incorporating comments and suggestions are usually required before reports are of acceptable quality. This has been gradually improving and is linked to the previous lack of experience by UFSA in managing external resources (this being the first programme that is channelling significant funding directly to the institution using national PFM systems and processes).

Due to the bureaucratic complexity involved in setting up the necessary financial arrangements and authorisations for the transfer of part of the project’s resources from UFSA to MINED, the latter has only recently been able to drawn down on projects funds channelled via UFSA. This has contributed to a slower than desired implementation of the education component and complicates overall programme management arrangements.

Going forward, it is recommended that UFSA becomes the sole Government managing institution and that management responsibility of all financial aid is centralised in UFSA (rather than split between UFSA and MINED). This would complement the proposed changes on the TA side, and will contribute to reduced fragmentation and transaction costs for all stakeholders, whilst facilitating financial oversight by DFID and by UFSA itself. These proposals have been raised with MINED, and careful handling of communications will be required going forward, to ensure a smooth transition in the way the financial aid component of this project is managed. An amendment to the Exchange of Notes will also be required, to confirm this with the GoM (recommendation).

Date of last narrative financial report	August 2014 (six-monthly report)
Date of last audited annual statement	NA (but audit underway)

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk
The overall risk environment for this programme remains high, but we assess the direction of travel as being a positive one.
The original risk matrix prepared in the context of the Business Case has been substantially reviewed to better reflect the programme and country circumstances, and ensure that the risks to the successful implementation of the programme are not confused, in the way they are worded, with the underlying issues that the programme is trying to tackle. Table 2 presents the revised set of risks, with an indication of new risks that have been identified and reassessment of impact/probability of existing risks where relevant.

Follow-up to actions recommended throughout this AR will ensure a degree of mitigation against other programme and fiduciary risks that have been identified.

Table 2: Reviewed Risk Matrix
Risk description / type	Impact / Probability	Update / mitigation
New administration shows little appetite for procurement reform / [country risk]	H / M	To be monitored closely / [new risk]
Senior staff reshuffle following appointment of new administration / [partnership risk]	M / M	Mitigate through active engagement and quick establishment of personal and institutional relationships (involve HoO as required) / [new risk]
Insufficient commitment to, and ownership of reforms from MF/UFSA and MINED / [programme risk]	H / M	At least formally, high level commitment appears to be there. However, whilst UFSA have shown an increasing level of ownership and commitment to the programme, the same cannot be said about MINED. Mitigate through active dialogue and collaboration. Involve HoO as required.
Lack of coherence between DFID programme and other interventions limits potential for overall impact / [programme risk]	M / L	DFID is currently the only donor with significant engagement in central/strategic level procurement reform. We will continue regular communication and coordination in the context of the procurement WG to mitigate. / [probability downgraded to low]
Weak coordination and collaboration between the many project stakeholders undermine programme coherence and impact / [programme risk]	H / M	Coordination and communication between DFID, CA and UFSA are good. Coordination with, and buy-in from, education sector is weaker. Will use re-design to address. DFID to also play facilitator role if and when necessary.
Weak technical/managerial capacity and motivation to implement reforms effectively (exacerbated by high staff rotation) / [programme risk]	H / H	Gaps in capacity are evident both at central and decentralised/UGEA level, and will widen with the trend towards increasing deconcentration of procurement operations to provincial/district levels. See discussion under outputs 1, 3 and 4 for analysis of issues (the implementation of actions under output 4 will help mitigate). / [probability upgraded to high]
Weak financial management and reporting capacity increases fiduciary risk / [financial risk]	M / M	Mitigate through close engagement during planning and reporting periods. Ensure audit findings are acted upon. Consider additional TA to build FM capacity. [new risk]

On the whole, risks around UFSA’s commitment have been reassessed on the upside, and the successful integration of the TA component has helped mitigate risks around output delivery.
In the coming months, careful monitoring will be required to assess the impact of the evolving political landscape on the overall risk level and possible mitigation strategies. Specifically, a new administration will likely have an impact on the general appetite for reform in procurement/PFM and more widely, and on the composition of senior MF personnel (including, potentially, at UFSA). Given DFID’s significant efforts in establishing and maintaining a positive relationship with the heads of UFSA, DNP, CEDSIF and MINED-DAF, the latter is a major risk.

The interaction of these two factors has the potential to either add to the risk level or diminish it, depending on the outcomes. Fresh impetus to reform is likely, but the opposite is also possible. A reshuffle of senior managers within and outside MF would likely bring opportunities as well as threats, which are difficult to anticipate. For example, greater drive for reform in areas where engagement has traditionally been weak can have a direct bearing on elements of procurement reforms supported through the programme (e.g. anticorruption and broader public sector management reforms such as decentralisation and civil service reform).

Outstanding actions from risk assessment
Fiduciary risk is still assessed as significant and stable, largely due to the poor quality of financial reporting to date; low financial management capacity within UFSA; and lack of any experience in managing donor-funded programmes.
Findings from an external audit of project accounts for 2013, which was commissioned by DFID and is currently underway, will provide further evidence to inform our assessment of fiduciary risk and provide an opportunity to agree remedial/follow-up actions with UFSA. The implementation of actions recommended under section D, relative to the sector component, will also contribute to mitigating fiduciary risk.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Although broadly on-track against the output targets and milestones in the revised logframe, the project is off-track against the original timescales set out in the BC. This is due to the lengthy delays in getting the programme up-and-running, which are documented in the last AR. It is anticipated that the programme will require an extension to 2017, to account for the initial delays.

Performance of partnership (s)
The commercial partnership with CA has to date worked well. Productive meetings are held at regular intervals with the Team Leader; KPIs have been agreed for the implementation phase (subject to quarterly monitoring), and outstanding contractual issues have been resolved.
Whilst the overall assessment of contract implementation was positive, issues were raised about the Education sector component. As a result, it is recommended that the contract with CA be reviewed to take into account feedback and lessons learnt in the inception phase (see discussion under output 1).
Asset monitoring and control
NA

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
This programme does provide a small amount of Financial Aid to government. As such the partnership principles are relevant to overall programme monitoring, though we would not expect to use this programme to respond to deteriorations in the partnership principle assessment unless the deteriorations were directly related to this project.

DFID assesses the GoM commitment to the UK Partnership Principles on a regular basis in line with the UK Conditionality Policy. Box 2 below provides a summary of the latest assessment, which was cleared by the Secretary of State in April 2014.

Box 1: Summary of Latest Assessment of GoM commitment to UK Partnership Principles
In respect of the commitment to poverty reduction, DFID continues to be concerned that despite increasing investments and improvements in access to key social services, poverty levels are stagnating. Challenges around quality and equity of service provision are also of concern. Results from the next household survey will be available in 2015 and will provide a more up to date analysis of progress in the past four years. / There have been some positive developments regarding the commitments to public financial management (PFM) and to domestic accountability. For example, the GoM remains compliant with the EITI initiative and, in January 2014, published all existing minerals and petroleum contracts. GoM management of the investigation into the education fraud reported last year has continued, in a timely way, to follow due process. / However, the assessment highlights some deterioration in security with consequences for our assessment of the commitments to human rights and to domestic accountability. These appear to be largely linked to the electoral cycle (municipal elections last November and presidential elections scheduled for October 2014) and not an indication of a permanent deterioration. At the same time, there have been positive developments including the recent agreement between the two main political parties on electoral reform. It remains likely that in the run up to the presidential elections there will be further problems; we will keep the situation under close review.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The theory of change for this programme and the evidence and assumptions underpinning it are still regarded as valid.

Monitoring progress throughout the review period
Regular meetings have been held with project partners and stakeholders, namely with technical and senior officials at UFSA, MINED and CEDSIF and with CA Team Leader and Project Director (during his three visits to Mozambique).
For this review, the key sources of information were UFSA’s reports (both internal and project-specific); and TA mobilisation report, progress update reports and inception phase report.

CA’s analytical inputs used in this AR include the PMIS diagnostic report and powerpoint presentation; the report on the Monitoring and Compliance Framework and the Training Needs Assessments.