Type of Review: Annual Review

Project Title: Creating Opportunities for Poor and Excluded (COPE)
Date started: August 2013
Date review undertaken: May – June 2014

## Introduction and Context

What support is the UK providing?
The UK is providing £24 million over 3.5 years (August 2013 to 31 December 2016) to the Manusher Jonno Foundation (MJF), a leading Bangladeshi human rights organisation, to implement the Creating Opportunities for the Poor and Excluded People in Bangladesh (COPE) programme. COPE follows the DFID-funded Rights and Governance Challenge Fund (RGCF) programme (2008-13), also implemented by MJF, in providing funding, technical and organisational support, and access to national policy influence for NGOs and civil society organisations selected through a competitive process. The 122 partners in COPE are implementing projects designed to / Advance the rights of marginalised people (including excluded and minority groups); / Combat violence against women; / Protect the rights of vulnerable workers and working children; and / Ensure the responsiveness of public institutions. / Australia has also contributed AUD 2.5m to COPE up to 30 June 2014, and committed a further AUD 3.5m (£3.3 million) for the period July 2014-June 2015.

What are the expected results?
COPE will enable Bangladeshi NGOs to work with some of the most poor and marginalised people in Bangladesh to improve their economic, social, political, and legal entitlements, including access to quality public goods and services. Over the 3.5 years of the programme an additional 129,000 poor and vulnerable households will newly benefit from social transfers and pensions; 37,000 women victims of violence will get medical and legal services; an additional 9,000 acres of land and water bodies will be leased to poor and vulnerable households; and 51,000 more workers will have decent working conditions. / Up to 150,000 people per year will be involved in activities to claim their rights through their involvement in COPE, including applications to service providers, peaceful protests and demonstrations, or the use of the Right to Information (RTI) law and fact finding meetings to access information from government offices. 15,000 people from marginalised groups (70% of them women) who are involved in these activities will participate in local government bodies and forums such as clinic or school management committees; 6,600 potential labour migrants will receive training in safe migration; and 22,300 people will monitor the quality of public health, education, agricultural extension and social protection services. / The programme will complement and reinforce the impact of other DFID programmes in Bangladesh that support basic social services such as health and education, promote economic development and job creation, and improve access to credit, markets and opportunities to make a living. Other outputs will include capacity development of small partner organisations, and advocacy campaigns on human rights and good governance issues on which MJF and partners have a comparative advantage.

What is the context in which UK support is provided?
Despite rapid poverty reduction and improvements in health and education, over 30% of Bangladesh’s people live in poverty, and the basic needs of 50 million people have yet to be met. Women and girls have won access to education and work but are still more than likely to experience physical or sexual violence in their lifetime. Many people are excluded from the gains of growth and public services because they are marginalised from social and political life. Women and girls, dalits (low caste Hindus), religious and ethnic minorities, working children, and people with disabilities are inadequately represented by decision makers, and excluded from forums where decisions are made. Changing this situation means ensuring they can voice their concerns, be heard by decision makers, and have the knowledge and means to hold those decision makers to account. / There is evidence that NGOs and civil society organisations have made major contributions to poverty reduction in Bangladesh. This includes getting benefits to people who would otherwise be excluded from them, as well as longer-term activities to build their organisations so that they are equipped to make and enforce their claims to public services. It also includes other NGO and civil society activities working to promote human rights and good governance on behalf of poor and marginalised groups. Through COPE, UK support is providing technical and organisational capacity as well as financing to a wider social movement about rights and inclusion within the development process. COPE builds on the achievements of the work supported by MJF under DFID’s Rights & Governance Challenge Fund (2008-13). / This is taking place within a political context which offers mixed support to the changes COPE aims to contribute to. The current government (since January 2014) is generally supportive of the objectives of COPE, as can be seen in the number of new laws and policies to protect and promote the rights of minorities, socially disadvantaged groups and women and workers that are in process. However, the context has also included extensive political turmoil around election times, high-profile instances of politically-motivated clampdowns on human rights defenders and political activists of all political stripes, and a decline in law and order and the overall conditions of public sector governance.

Section A: Detailed Output Scoring
Output 1: Increased use of services (education, health, and social protection) by poor, marginalised, and vulnerable people
Output 1 score and performance description: A++ - substantially exceeded expectations
Progress against expected results: / Indicator 1.1: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of people supported by the project to practise their citizen rights and tradition (People supported to have choice and control over their own development and to hold decision-makers to account - DFID Results Framework indicator). 40,000 61,489 (42,448 (69%) women, 19,041 men) / Score: A++ / This indicator measures participation in planned collective action as part of the programme strategy of citizen empowerment. NGO partners in the programme mobilise men and women to take part in primary groups and awareness-raising activities. This indicator measures the number of these men and women who have participated in the following types of project activities to claim rights: / Submitting applications for access to safety nets, wage increases, education quotas for dalits, khas land and water bodies to service providers / filing cases / Peaceful protests, rallies or human chain (protest) / fact finding meetings / Submission of memoranda on rights issues, for example the incidence of VAW, inclusion of adivasis on lists for public services, land commission for plainland adivasi people, wage increases in formal sector / Press conferences on particular issues, rallies, applications submitted under the RTI law. / The indicator only measures activities the NGO has itself organised and/or facilitated: it does not count participation in spontaneous or community-initiated rights-claiming activities, nor in wider social movement actions (e.g. mass rallies celebrating International Women’s Day). Participants are only counted once, even if they participate in more than one rights-claiming activity. MJF provides guidelines to partners on how to avoid double-counting, and check on lists of participants in their routine project monitoring visits to follow this up. / Indicator 1.2: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of people from marginalised groups actively taking part in local government bodies and local forums / (70% women, 30% men) 2,000 2,685 (women: 1,825 (68%), men: 860 (32%)) / Score: A++ / This indicator measures membership of local public institutions by marginalised groups, including standing committees of union councils (the lowest elected administrative tier of local government), school management and health user committees, and other official committees. This indicator excludes participation in non-governmental groups such as community-based organisations or mosque committees. The target was substantially exceeded this year in numerical terms. / MJF and partners only measure people’s membership of such groups, not the quality of their participation, so in the interests of precision, the word “actively” should be removed from the indicator for routine monitoring. The quality of participation will need to be assessed through research and evaluation. Partners and field visits highlight cases where the participation of marginalised people has brought about real change in public services and some have been encouraged to stand for local election. How widespread such cases are cannot be known from this indicator. / Indicator 1.3: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of children in project areas learning in mother tongue in their schools 1,000 4,130 (boys: 1,816 (44%); girls: 2,314 (56%)) / Score: A++ / This indicator counts the numbers of girls and boys from adivasi or indigenous communities who have been learning in their mother tongue in schools supported by project partners in the past year. This includes children from the Chakma, Marma, Pankhua, Khumi, Bawm, Khiyang, Mro communities of the Chittagong Hill Tracts and children from the Oraon, Mahali, Santal communities of the plains. / The achievement is more than four times over target because the government recently decided it will introduce mother tongue language up to class three and bridging in class four in adivasi areas, and MJF partners have decided to start to implement this policy in the schools they support. / The Government plans to introduce mother tongue education as part of its primary education policy. Once that policy is implemented, this indicator will not be a relevant measure of achievement by the COPE programme. An alternative indicator may need to be developed. / Indicator 1.4: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of children enrolled in primary schools 17,500 24,798 (boys: 10,267(41%); girls: 14,531 (59%)) / Score: A+ / Children from the marginalised poor groups targeted by partner projects often do not enrol their children because they do not have information or access to schools. Partners adopt one of two strategies here: 1) activating school management committees to identify and encourage dropouts and unenrolled children to attend; 2) building and supporting schools that enrol listed beneficiary children in the Chittagong HiIl Tracts and adivasi plain land communities. / Indicator 1.5: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of men and women received skill development training and entrepreneur assistance 8,000 14,578(women: 9,476 (65%); men: 5,102 (35%)). / Score: A++ / These are people from marginalised and minority groups, the Chittagong Hill Tracts and women and girls at risk of violence who have received training for income generation or enterprise support, including linkages to microfinance, product markets or asset transfers. / Despite over-achievement on this output, achievement on the related outcome indicator 4.3 (numbers of women and men in paid work or self-employment) was substantially lower than targeted. This seems to reflect the economic slowdown of the three months of intense political turmoil during the 8 month project period. Training and other support can be given, but they may not translate into new jobs or businesses if the entire economy slows or new activities look risky. / Indicator 1.6: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Cumulative numbers of poor and marginalised people improve their monthly income BDT 1000 in the targeted area (CHT). 20,000 beneficiaries, assuming 4,000 direct beneficiaries earning additional income, and 5 people per household benefiting. 7,111 (direct beneficiaries women 3,361 (47%); men 3,750(53%)) / Score: A++ / In the Chittagong Hill Tracts, partners are working to raise incomes through additional earnings of at least Tk 12,000 per year, by organising and supporting producer groups through market linkages, training etc. The indicator measures additional earnings from the partner-supported activity, measured as profits net of input costs based on partners’ monitoring data. Technically these are ‘additional earnings’ and not income because there is no assessment of total household income the standard manner, nor does this take into account opportunity costs of involvement in IGAs. / The original target was set at 20,000 beneficiaries, but this intended to refer to the total number of people benefiting from each additional earnings, assuming 5 people in each household. For clarity, the target should have been set at 4,000 to refer to the numbers of people who will be making additional earnings. This was the figure used for the initial cost-benefit analysis of the programme. Assuming a target of 4,000, the achievement was well above target. Tk 1,000 (£7.70) per month may seem a low target given recent inflation, but many producer group activities still fail because of distance to markets, crop failures, lack of experience etc. / Recommendations: / 1. The full and true impact of participation in rights-claiming activities and official bodies and forums cannot be adequately measured using quantitative indicators alone. Questions to consider in plans for evaluation include how and how much participation in rights-claiming activities a) increases the organisational strength of marginalised groups; b) influences how responsive public institutions are; and c) makes a difference in terms of public services actually received. DFID Bangladesh should commission a ‘Monitoring & Evaluation TA’ to assist MJF to redesign quantitative and qualitative methods and tools for evaluative research by November 2014. / 2. Projects supporting mother tongue learning may consider new areas of work or develop new measures of their value-addition, if government changes its policy to provide mother tongue learning. MJF has already commissioned a study in this regard that is expected to be completed by February 2015. In addition, MJF programme leads should trace their and their partners’ contribution to the policy changes around mother tongue education. / 3. CHT partners should review the Tk 1,000 level for their ‘additional earnings’ target. Having over-achieved it significantly despite some group activities failing suggest that it may be set too low. The forthcoming M&E TA review will complete this review by February 2015. / Log-frame recommendations: / 1. Output 1.2 specifies ‘actively’ but the data collected do not consistently track the quality of participation in these bodies. To avoid claiming participation is ‘active’ without evidence, the word ‘actively’ should be removed from the indicator. / 2. To ensure a suitable indicator is in place throughout the lifetime of COPE, we recommend that partners and MJF should consider replacing Indicator 1.3 with an indicator that tracks their direct contribution to the learning of adivasi children, if government policy changes to include mother tongue education in government schooling. Indicators that could be used include: % of children in supported schools who participate in / pass the primary school leaving examination, with targets set at the national average for completion of primary school / pass the primary school leaving examination (depending on which is seen as the best measure of COPE partner strategy and activities). MJF notes, however, that the Government plans for mother tongue learning will take time, and they include only four CHT languages (COPE covers more). The forthcoming M&E TA review will assess the status in February 2015. / 3. The indicator for Output 1.6 should be reworded: ‘Cumulative number of poor and marginalised people in target communities in CHT who increase their monthly income by BDT 1000 through income generating activities”. The milestone and target measures should specify that this measures the number of beneficiaries involved in the IGAs, not the total beneficiaries within each household of which they are members. Milestone 1 for Output 1.6 should therefore be amended from 20,000 to 4,000, and similar adjustments should be made to subsequent milestones. / Impact Weighting (%): 30% / Revised since last Annual Review? Increased from 25% in the original logframe, to reflect the removal of Output 7, which was not relevant to the smaller programme that was approved. / Risk: Medium / Revised since last Annual Review? Revised upwards since business case. A repeat of the political turbulence experienced during 2013 would constrain people’s mobility, make planning impossible, and increase the risk that mass meetings and any critical engagement with power-holders may be considered confrontational and clamped down on. Extended episodes of strikes or hartals and political unrest also tend to impact on some sectors of the economy, so some livelihoods activities may be particularly vulnerable.

Output 2: Women's groups equipped to challenge violence against women and girls.
Output 2 score and performance description: A++ - substantially exceeded expectations
MJF’s Combating Violence Against Women(VAW) programme is contributing towards reduction of violence against women and girls by changing institutional norms and practices, and reducing impunity for perpetrators. It works at individual, household, community, sub-national and national levels, through 21 partners and 12 sub-partners in 29 districts, working in 3008 villages, with 35 police stations, 10 hospitals, and 13 courts with 140,701 direct beneficiaries. Activities focus on prevention, protection and provision. There are currently 242 Nari Nirjaton Nirodh (Protection Against Repression of Women) Committees working in 70 sub-districts. / Progress against expected results: / Indicator 2.1: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of dowry-less marriages in programme areas 1,750 1,969 / Score: A+ / The exchange of dowry (from brides’ to grooms’ families) is understood to be closely linked to violence against women (VAW). Demands can continue throughout a marriage, and women can be pressured or abused to force their parents to make payments to their son-in-law’s families. Dowry is also highly prevalent and can even said to be a normal transaction during weddings and well into the lifetime of a marriage. / Partners working on VAW organise and train beneficiary groups to take action to raise awareness to prevent local people from giving or taking dowry (1,192 marriages were arranged without dowry during this period). They also actively intervene to stop marriages with dowry from happening (777 during reporting period). The target was over-achieved. / Indicator 2.2: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Numbers of women victims of violence in project areas have access to medical and /or legal assistance 6,800 12,474 / Medical support: 6,994 / Legal support (legal aid etc): 2,020 / Access to justice including alternative dispute resolution (ADR): 2,220 / Village courts: 1,240 / Score: A++ / Projects to combat VAW provide access or linkages to medical care (including forensic evidence collection), legal aid and support, access to non-formal justice, and to village courts (where relevant – they do not have a mandate to adjudicate on criminal matters but can make judgements about return of women’s property or maintenance payments etc.). / The achievement was almost twice the target, which could reflect a) a low target, b) improved awareness of services due to the wider social movement and government multi stakeholder programme, c) increased levels of VAW or d) increased reporting of VAW. / Among the project participants 885 acid survivors got medical treatment, shelter support and counselling to reduce trauma, 164 acid survivors received education support and 4 received support for income generating activities. During the legal or shalish process 6,112 survivors of VAW got counselling, recreation to reduce trauma, skills training for rehabilitation, education support. / Indicator 2.3: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of early marriages (i.e. girls under 18 years) prevented in project areas 1,750 2,378 / Score: A++ / Child marriage is a form of violence against girls, and it is also associated with VAW in later life and is highly prevalent in the project areas. Partners working on VAW raise awareness locally of the bad effects and illegal status of child marriage. They also organise and train beneficiary groups to take action to prevent local people from marrying off their girls before age 18. / This indicator counts the number of child marriages that the groups claim they have prevented through their awareness-raising and direct action. This is based on their assessment of the population in their local area that vulnerable to early marriage and their knowledge of child marriages that were planned but stopped. / Recommendations: / 1. With increased social mobility, some people give ‘gifts’ rather than ‘dowry’, but the pressures on women and their families may be similar. Dowry and early marriage are also connected, because parents usually have to pay less to marry off younger girls. The programme needs to be alert to changing meanings and practices, and address the link between practices like dowry and early marriage and violence against women and girls. Programme staff recognise that the fear of sexual violence or premarital sex is a major factor behind early marriage, but it is not clear what partners are doing to improve the sense of safety and security or to reduce worries about girls’ sexual purity. MJF VAW team should hold discussions with partner project staff during their monitoring visits to a) alert them to these possibilities and b) gather their own knowledge about local meanings and practices. These can then be c) documented in a report about project partners’ reflections about how marital practices and perceptions are changing in project areas, with a focus on what this means for the overall problem of VAWG. This should be checked by the next Annual Review. MJF will: i) prepare a fact sheet/ analytical report highlighting the partners’ concerns; ii) revise the reporting format for process documentation by October 2014, to enable it to follow up and monitor the updates during field visits. / 2. The impact of this work can be wider if VAW partners can share their lessons about what is working well with other NGOs and civil society groups, and in particular the women’s movement and government agencies involved in the multi-stakeholder platform against VAW. To address this, MJF will document on lessons learned by November 2014. During the same period, MJF will also form a national network for experience sharing and discussion on strategic direction on VAW. / Log-frame recommendations: / The review has identified a number of possible improvements to the indicators for this Output, but the benefits from better indicators need to be set against the feasibility of collecting data (including year 1 and baseline data) for indicators that MJF and its partners are not currently collecting data for. With that caveat in mind, the following changes should be considered: / 1. Outputs 2.1 and 2.3 both rely on partner-organised groups’ assessments of the potential damage they have helped avoid through their work. The ‘dowryless marriage’ works as an indicator as long as a) other forms of exchange likely to produce violence are not being used instead, and b) there is confidence that raising awareness and collective action to stop dowry exchange in planned marriages does work. MJF programme staff need to investigate and report on partner project staff knowledge of how perceptions and practices relating to marriage are changing, particularly in relation to dowry. The assumptions and risks underpinning the logframe outputs can then be revised, if necessary. The forthcoming M&E review will undertake this revision by December 2014. / 2. The ‘child marriages avoided’ indicator is more problematic as it is only when the child reaches age 18 that this can be said to have been achieved. A recommendation is to adopt a new indicator such as ‘the number / % of girls in project areas remaining unmarried till 18’. The source will be data the project beneficiary groups already collect on teenaged girls in the locality. This is feasible because the programme plans to develop lists of unmarried girls aged 14-17 in project locations, which will make it possible for MJF to track results. This should be considered in the forthcoming M&E review by February 2015. / 3. The programme should try to establish why their target was so low/achievement so high for access to health and legal services. Given this high achievement in Y1 (183%), targets should be revised for forthcoming years. The forthcoming M&E review will undertake this revision by February 2015. / 4. The milestones and target for output 2.1 were set based on past programme experience. However, it is not clear on what basis (calculations or population size) these figures were arrived at so it is not clear whether or not they are reasonable or realistic milestones or targets for these activities. The formula (e.g. X % of the average # of all marriages that take place in targeted areas per year) should be clarified. / 5. The use of numerical rather than % targets could be problematic because success in raising awareness could mean fewer cases to tackle. Ideally, the indicator should measure the % of marriages without dowry (compared to national or divisional average etc.) and % of girls staying unmarried till 18. This is feasible because project partners track marriages in their communities, and data can be gathered to calculate non-dowry weddings as a % of all weddings in and among the local community. As the programme also plans to develop lists of unmarried girls aged 14-17 in project locations, this will make it possible for MJF to calculate percentages. MJF should confirm whether % indicators are possible based on the data partners already collect or which MJF plans to ask them to collect, and revise the indicator and targets appropriately. / Impact Weighting (%):20% / Revised since last Annual Review? Increased from 15% in the original logframe, to reflect the removal of Output 7, which was not relevant to the smaller programme that was approved. / Risk: Low / Revised since last Annual Review? We considered revising this upwards in line with with Output 1. VAW frequently rises during political violence, and in late 2013, many union council chairmen, who dispense justice through ADR and village courts, were jailed or on the run due to political violence. This is believed to have affected women victims of violence access to justice in specific instances. However, as the output indicator includes a range of different types of justice and legal and medical services, less access to one set of services does not seem likely to affect the overall likelihood of achieving the output, as people seek other kinds of help over time, and MJF partner NGOs are able to help them explore alternative options.

Output 3: Rights of working children and vulnerable workers protected and strengthened.
Output 3 score and performance description: A+ - Exceeded expectations
Progress against expected results: / Indicator 3.1: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of students received non-formal education (NFE) from child centre 6,000 7,484(boys: 2,994 (40%); girls: 4,490 (60%)) / Score: A+ / Partners working on the rights of working children provide non-formal education in dedicated child centres attended by working children and children at risk of working (because they are poor, their siblings work, or they do not attend school). Some of these are single year preparatory education programmes that ‘feed’ children into the formal education system, and others involve learning alongside working. Often this works as early childhood development for children who have had no organised learning or safe play spaces. / These preparatory education programmes are a type of non-formal education (NFE), but unlike the NFE provision commonly found in Bangladesh. MJF partners have developed their own curriculum based on their practical experience, but no widely recognised curriculum for such activity is currently available. The impact of this preparatory education provision on uptake of government education services by hard-to-reach groups is likely to be good, but is not measured here. This target was over-achieved. / Indicator 3.2: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of workers in decent working conditions supported by the programme (30% men, 70% women) 6,800 8,767(men: 1,578 (18%); women: 7,189 (82%)) / Score: A+ / COPE partners are working with 32 factories employing around 45,000 workers in the readymade garments (RMG) and frozen food industries. Their main activity is to teach workers about their rights, organise them into associations and support their efforts to negotiate for decent working conditions (specifically, receiving wages on time, able to use leave entitlements and have standard working hours). / During the reporting period about 6,558 workers claimed BDT17,470,241 (£135,000) due to them for termination, resignation, retrenchment and maternity benefits. An additional 1,967 workers benefited from improved working conditions in the form of standard working hours. / These direct benefits to targeted workers are less significant than the impact of MJF on the legal framework and implementation of labour laws. In addition to direct benefits to specific workers, MJF has also advocated minimum wage reforms through research and drafting, and RMG wages were raised in November 2013, benefiting 4 million workers, around 80% women. MJF is also coordinating and drafting amendments to reform the Labour Law on behalf of the Government. / Indicator 3.3: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of migrant workers in project areas receiving training and support for safe and legal migration (70% men, 30% women) 800 825(men: 698 (85%); women: 127 (15%) / Score: A / Potential migrant workers are receiving services such as information and training, visa checking, online registration, opening bank accounts, complaints handling, support for death compensation, and local mediation. The data are from the 16 centres run by 4 of MJF's partners. The proportion of women receiving support is half that targeted. / MJF staff and partners are now members of the Core Technical Group (CTG) under the ‘Standardisation of the Pre-departure Orientation Services (PDOS) Training Program for Potential Migrants’, a major project of the Ministry of Expatriate Welfare and Overseas Employment. / Recommendations: / 1. Bangladesh has numerous examples of world-class excellence in NFE service provision. Small partners need not produce their own preparatory education materials from scratch, and should build on what is already available. MJF partners should take advantage of the offer from CAMPE (the Campaign for Popular Education) to provide free training on NFE for partners over the next year. The next Review should also assess the quality of preparatory education inputs to ensure maximum value for money is being achieved. This will be reviewed as part of the upcoming M&E review by February 2015[1]. 2. MJF should explore whether potential women migrants are being excluded from support services. It is possible that this under-achievement reflects low numbers of potential women migrants. But that may in turn reflect the lack of information and support for safe migration that women have access to. An effort specifically targeted to reach potential women migrant workers should be considered. By October 2014, MJF will conduct a workshop with its project partners on migration to explore gaps/exclusion issues in support services and accordingly, strategies will be revised to reach potential women migrant workers. Based on the workshop findings, the percentage of women and men migrant workers will be recalculated. / Log-frame recommendations: / 1. Revise gender breakdowns for targets if they are unrealistic in their estimates of how many potential women migrants seek support by October 2014. / Impact Weighting (%):20% / Revised since last Annual Review? Increased from 15% in the original logframe, to reflect the removal of Output 7, which was not relevant to the smaller programme that was approved. / Risk: Medium / Revised since last Annual Review? No. RMG workers have won higher minimum wages and compensation for the Rana Plaza building collapse, as well as some other basic rights. But workers’ rights in general remain a very challenging and sensitive area of work. The risk for COPE, that decent work conditions cannot be achieved, even though these are within the law, remains moderate to high. Risks with respect to child and migrant workers are lower, and so the overall risk level for this output area remains medium.
[1] Instead of ‘Non formal Education (NFE)’, MJF proposes to replace the wording with ‘Preparatory Education Session’, because MJF partners are preparing children for the next year’s school enrolment which is not the same as NFE.

Output 4: Capacity of citizens in project areas to monitor activities of government service delivery institutions
Output 4 score and performance description: A - met expectations / Activities and strategies under output 4 are designed to bring about systemic change by building demand for good governance. This means a) getting citizens to see how they can contribute to monitoring public services and what practical benefits that can bring, and b) persuading service providers that their performance will improve by being monitored with citizen involvement, particularly by the most marginalised and hard-to-reach groups.
Progress against expected results: / Indicator 4.1: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of people involved in project areas to monitor health, agricultural extension, education, social protection, nutrition services available to the poor 6000 6257 (104%) / Score: A / Marginalised, excluded and poor people are organised into groups and trained and equipped to monitor local public services that matter to them. Participation in this monitoring of public services aims to raise their standard and make it difficult for government officials to fail to deliver the services or to turn up for work, or for corruption to occur. This indicator counts how many people are involved in these activities, not the quality or impact of their monitoring, nor the impacts on people’s experience of civic activism and engaging with state officials. The target was achieved. / Indicator 4.2: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of Government institutions monitored by partner organisations using social accountability tools 106 124 / a) Agricultural Extension Offices 20 25 (125%) / b) Health Facilities 40 49 (123%) / c) Social safety net programmes 16 15 (94%) / d) Schools 30 35 (117%) / Score: A+ / Partner organisations use social accountability tools such as social audits and scorecards (mainly) to involve beneficiaries and stakeholder groups in monitoring public services, including provision (e.g. whether health facility staff and teachers show up; numbers of visits by extension officers etc.) and quality (e.g. whether a beneficiary list is prepared for safety nets). This indicator measures how many services or government offices are being monitored using these tools. / Recommendations: / 1. Grievance and feedback mechanisms for service users seem weak, and continue to rely on under-used ‘complaints boxes’ based on unrealistic assumptions of literacy and action. MJF could usefully invest in exploring good practice in the use of grievance/feedback mechanisms and helping partners develop stronger practice in this area (e.g. SMS complaints in BISP in Pakistan; use of oral complaints mechanisms, local ombudsmen etc.). MJF will conduct consultation with its partners to identify effective grievance mechanisms and accordingly, the new grievance mechanism will be in place by September 2015. / 2. The impacts on beneficiaries, public services and service-providers, and the wider impacts on relationships and mechanisms of accountability of these monitoring activities cannot be measured with these quantitative indicators. Plans for evaluation should consider how monitoring contributes to better-performing public services, and how much. This may include an assessment of how service-providers’ behaviour and attitudes have changed or the immediate effects of social audits or report cards on the level and quality of services provided. The forthcoming M&E review will consider how feasible it is to do this assessment, by September 2015. / Log-frame recommendations: / 1. The logframe needs to be reviewed to explore whether indicators can be included that capture performance of monitored services. The impacts on accountability mechanisms and relationships between participants and service-providers will need to be evaluated for their contributions to outcome and impact level. The forthcoming M&E TA review will assess this by February 2015. / Impact Weighting (%):10% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No.

Output 5: More sustainable civil society organisations
Output 5 score and performance description: A+ - Exceeded expectations
Progress against expected results: / Indicator 5.1: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of small partners receiving financial support other than from MJF 2 5 / Score: A++ / One of MJF’s goals is to build the capacity of small organisations to stand on their own feet. Most of the MJF’s larger and more established partners already receive funds from more than one source. This indicator measures the progress of smaller organisations towards accessing more diversified funding sources (other than MJF). MJF and COPE contribute to this by providing capacity development support - organisational and technical capacity development, financial management training, M&E support. The achievement was more than double the target. / Indicator 5.2: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Percentage of MJF budget coming from sources other than DFID. 21 23 (110%) / Score: A / This indicator is a measure of MJF’s progress towards sustainability and independence through more diversified funding sources. In the reporting period, MJF has won some competitive bids (Comic Relief, GPSA, EU) and is involved in the institutionalisation of third party monitoring of World Bank projects in Bangladesh, as well as being part of a new DFID programme (SGSP). / Excluding the DFID contribution to MJF’s budget through the SGSP programme, this target was achieved, as more than 23% of MJF’s budget was from sources other than DFID as of March 2014, and 28% of the budget is from sources other than the COPE programming funding. The training centre is chiefly used to control in-house training costs and quality, but has also provided a small income for MJF of around Tk 900,000 (c. GBP 7,000) in the past year. / Recommendations: / The sustainability of civil society organisations is not only about its funding, but also about rooted they are in the context in which they work. The strength and density of the interactions of partner civil society organisations could be assessed in terms of the quality of the long-term relationships being built with communities; the nature and achievements of coalitions and networks between civil society groups, and the density and quality of interaction with Government at different levels. It should be stressed that civil society organisations will not always have positive relationships with government or donors, and their sustainability will need to be assessed in terms of their achievement of their own goals. This should be built into forthcoming work on measurement of COPE’s contribution to qualitative change. In this regard, the M&E review will make recommendations by September 2015. / Impact Weighting (%):10% / Revised since last Annual Review? NA / Risk: Medium / Revised since last Annual Review? No.

Output 6: Output Indicators 6: Evidence generated, synthesised, and used to advocate for changes in various social development policies
Output 6 score and performance description: A- met expectations
Progress against expected results: / Indicator 6.1: / Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / Number of policy advocacy campaigns on rights and governance 2 2 (100%) / Score: A / MJF with its partners and in coalition with non-partner organisations and with some government agencies conducts policy advocacy campaigns on selected issues. In the reporting period, these have included campaigns on equal respect for women’s contributions (Morjada Gori Shomota) and for an anti-discriminatory law. These campaigns are about raising popular awareness of human rights and exclusion issues, and about pressing the Government for action, through enacting laws or implementing policies. / Recommendations: / 1. MJF’s campaigns are currently somewhat low-key, partly out of respect for the more direct contribution made by their partners to social change in Bangladesh. However, MJF could invest more effectively in a knowledge broker role, to enable cross-learning from and sharing the lessons and achievements of its partners’ advocacy campaigns more widely. MJF could also invest in social media to influence the better off and more educated sections of Bangladeshi society, as these groups tend to have more impact on policy. As a first step, MJF has planned to invest in social media and is in discussion with young experts, especially to initiate campaign on issues like women’s contribution, child rights, and workers’ rights, issues where MJF has a comparative advantage. The campaign will start in September 2014. / 2. This indicator neither measures the generation and use of evidence, as the output name suggests, nor does it provide an adequate measure of MJF's upstream policy influencing, advocacy and campaigning work. In the present context, an alternative quantitative indicator may include: '#s of laws advancing human rights and good governance drafted, amended or contributed to by MJF and partners'. If the aim is to measure the use of evidence generated by MJF, then indicators should count 'numbers of policymaker, civil society or researcher mentions, dissemination events and media coverage' for particular evidence outputs. / 3. More appropriately, qualitative indicators can also be considered, such as 'direct influence over human rights and good governance legislative, policymaking or policy implementation [in COPE programme sectoral areas]'; 'acts of resistance against repressive or regressive laws, policies or actions by policymakers and powerful groups affecting groups reached by COPE'. This Output should be a focus of forthcoming work on measurement of qualitative change. The M&E Review Team on Quality will review this and accordingly, revision will be proposed against this indicator by February 2015. / Impact Weighting (%):10% / Revised since last Annual Review? NA / Risk: low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? / This is the first Annual Review since the programme was approved. COPE’s budget and timetable were cut from the original business case plan. The logframe has already been adjusted once to reflect this reduced budget, and targets were reduced on a case-by-case basis. The budget received by MJF was 66% of the original plan (£38m) and the timetable reduced from 5 to 3.5 years (60%). One of the main objectives of this review was to obtain clarity on whether the indicators (a) accurately reflected the data that MJF and partners are collecting; and (b) are being reported on a consistent basis. The review has clarified indicator definitions (reflected in greater detail in the “Source” section of the logframe and made several recommendations for refinement of the logframe to ensure consistent interpretation of results in the future. / 1.2 Overall Output Score and Description: Overall COPE has moderately exceeded expectations, substantially exceeding expectations on most outputs and at least meeting all. / Output No. Output Description Impact Weight (%) Output Performance Risk / 1 Increased use of services (education, health, and social protection) by poor, marginalised, and vulnerable people. 30% Outputs substantially exceeded expectation (A++) Medium / 2 Women's groups equipped to challenge violence against women and girls. 20% Outputs substantially exceeded expectation (A++) Low / 3 Rights of working children & vulnerable workers protected and strengthened. 20% Outputs exceeded expectation (A+) Medium / 4 Capacity of citizens in project areas to monitor activities of government service delivery institutions. 10% Outputs met expectation (A) Medium / 5 More sustainable civil society organisations. 10% Outputs exceeded expectation (A+) Medium / 6 Evidence generated, synthesised, and used to advocate for changes in various social development policies 10% Outputs met expectation (A) Low / Annual Output Scoring / Annual Output Score A+ / Annual Output Performance Outputs exceeded expectation / 1.3 Direct feedback from beneficiaries / Direct feedback from COPE beneficiaries is gathered through routine field visits by MJF programme and M&E staff. Beneficiaries also have a range of levels of contact with project partners and their staff through which complaints or feedback could conceivably be aired. / Direct feedback given to the review team by beneficiaries of COPE was positive in a range of different ways. For instance: / women and men benefiting from permanent or leased access to khas land or waterbodies in Khulna described how they were able to invest in their children’s education, to eat well and to live better lives through their involvement in the work of Uttaran; also in Khulna, fisherfolk and farmers were beginning the process of getting their official leasehold papers (Mukti Foundation) and spoke optimistically of what they would cultivate and earn / a new group of landless women in remote Koyra, near where cyclone Aila struck, described how after only a month of meetings they were already feeling more optimistic about their future, and identifying ways their group could be put to good use to access resources or help each other (Mukti Foundation) / Members of the dalit community in Satkhira (Bhumijo) and people with disabilities in Cox’s Bazaar (SARPV) spoke of how they were more accepted by other members of the community than in the past; disabled young people spoke of how their parents would take them out when they had been left at home before, and they were being called by their own names rather than labelled ‘lame’ or ‘the deaf one’ as in the past / members of a ‘mother’s club’ in Khulna city proudly showed us the clean streets and waste disposal areas they helped to monitor, and spoke of how they phone the Ward Councillor directly when problems arise / In the Chittagong Hill Tracts, members of income generating activity groups reported enjoying great success with goat-rearing, and were learning from their mistakes with the natural cold storage unit, which they had not been able to profit from in the past year / members of Protection against Repression of Women Committees in Jessore spoke proudly of the dowries and child marriages they had stopped, of their success in tackling violence and their plans to declare their villages ‘violence-free zones’(Mukti Nari o Shishu) / small children and older boys in Paltan in Dhaka described their pleasure in visiting the VAFWSD children’s centre. Older boys said they were beginning to make a good alternative living with the training they were receiving in mobile phone repair, and the mothers of younger children explained that they felt their children were safe at the centre, and that they had a chance to enter the formal schooling system, which without VAFWSD support they would not have done / RMG workers in Chittagong described their continued struggles with factory management to achieve basic rights (working hours, pay, benefits, respect) that were theirs by law, and explained how their workers’ associations helped them push for those rights (Mamata). / Other changes reported by beneficiaries included plans to stand for local office, which they would not have considered before being part of COPE. Ability to engage with officials and educated people and greater overall confidence and respect were also important changes in people’s lives. Officials and local elite groups were engaging directly with excluded groups and finding this useful in their professional and social work capacities, and showing signs of changing how they work and the efforts they make to reach excluded groups. / However, the Review team could not identify any other means through which participants could give their feedback without being specifically asked for it. This means it is possible that the beneficiary feedback being received is highly selective. It is not clear that suggestions or grievances about the programme or how it is implemented would reach MJF. / Recommendation: The M&E Review should explicitly consider how MJF’s programme team should improve the beneficiary feedback mechanism, by September 2015.
1.4 Summary of overall progress / Overall, progress on the outputs in the first 8 months of COPE was at or more usually above target. This was possible, despite the political disruption in the period, because in many parts of its programme, COPE extended or continued work with partners on issues or using strategies that had already been tried and tested during the RGCF programme that went before COPE. / In programming terms, there are relatively few and minor recommendations. In terms of measuring progress, and capturing the impacts, outcomes and even the outputs of COPE, however, there is work to be done.
1.5 Key challenges / Political context / The reporting period was one of the most turbulent and violent in Bangladesh’s recent history. This posed severe challenges for around three months (one-third of the programme period), during which daytime travel was in effect stopped, particularly in the insecure southern regions of the country where MJF has many programmes, and a number of activities involving local elected and administrative officials were delayed or stopped. / Partners appear to have adapted very effectively, with the support of MJF in flexibly adapting quarterly targets so that workplans could be adjusted to fit the circumstances. Quantitative targets that were in partners’ control at a local level (training, group formation, action to prevent early or dowry marriages; NFE provision) were unaffected. However, where the external environment mattered more (e.g. access to employment or enterprises, khas land transfers, union council-administered shalishes or informal courts for justice for victims of violence) partners reported signs of adverse impact. / Measuring results; M&E system / A second key challenge is that success with respect to the objectives of COPE is difficult to measure and to demonstrate. The theory of change indicates deep-seated changes in power relations, transforming the capabilities of marginalised and excluded people and qualitative changes in how public institutions respond to groups that have usually been left behind. The quantitative output and outcome measures provide an overall sketch, but not an adequate sense of progress towards the aggregate social change that COPE is likely to bring about. These imply the need for impact evaluation and research on the aggregate and qualitative changes COPE contributes to. / Recommendation: The M&E Review should make recommendations to MJF on how to collect and analyse stories of change, to feed into an impact evaluation. A plan for doing this will be drafted by September 2015. / MJF staff and partners do not uniformly display clarity and a sense of ownership of the current logframe. In some instances, indicators appear to work better to quantify and monetise results than to capture COPE’s achievements. Several areas of work are not included in the logframe (e.g. contribution to health outcomes) because of the challenge of measuring results attributable to the programme’s work. / The M&E unit appears to be under-staffed, in particular in relation to impact evaluation expertise. The Review process found the data verification process to be generally sound, and the monitoring data on the whole of good quality, once gathered. Yet how targets had been set, some indicator definitions, and knowledge of which activities/programmes contribute to which targets need to be revised. / Management arrangements / MJF’s staff, particularly its senior programme team, are a major asset both to partner support and to influencing policy and advocacy work. However, the need for more qualitative evaluation and research, for more targeted communications around advocacy campaigns and for a stronger M&E unit all suggest the need for dedicated senior management oversight of communications, research and M&E type functions, possibly in a joint programme/unit. The Executive Director of MJF will take necessary actions in this regard by November 2014.
1.6 Annual Outcome Assessment / The Outcome COPE aims for is that marginalised and vulnerable people have better access to public goods, resources and services. / Annual achievements were more uneven at Outcome than at Output level in year 1 of COPE, yet milestones were achieved for all but three of the 11 indicators, signalling overall strong progress. There was no change measured in the incidence of VAW (2.1), reflecting problems with the indicator. / Some programmes were hit by political turmoil in 2013. The number of women victims who received justice (2.2) may have been met had alternative dispute resolution activities continued in the last quarter of 2013. Many livelihoods, particularly in the conflict-ridden south, were hit hard by the political turmoil; this helps explain why the numbers of people in paid work and self-employment (4.3) was below target. It may be necessary to revise the milestones and targets to reflect this period of uncertainty, and the possibility that it may recur. / Five logframe indicators at outcome level (20 sub-indicators) have milestones for March 2014. / Indicators Stated in the Logical Framework of COPE Targeted Milestone 1 (2014) Progress of March 2014 (Milestone Status 1) / COPE OUTCOME: Marginalised and vulnerable men, women and children have better access to public goods, resources and services / Outcome Indicator 1: Increased use of services (education, health, and social protection) by poor, marginalised, and vulnerable people / 1.1 Number of poor, marginalised, and vulnerable households supported from government safety net services 17,500 19,292 (110%) / men-1,963 / women-17,329 / 1.2 Total amount (in £million) of social safety net support received by programme beneficiaries 0.84 0.92 (110%) / 1.3 Number of boys and girls who were able to complete primary schools 12,000 11,622 (97%) / boys-4,882 / girls-6,740 / Outcome Indicator 2: Women and girls protected against violence / 2.1 Incidence of violence against women and girls in the project area 33% 34% (0%; no change against baseline) / 2.2 Number of women victims received justice 9000 5480 (61%) / if we assume 3 months out of 8 the union council was closed, so no shalish took place, 5/8s of 9,000 = 5,670 should be the target 5670 5480 (97%) / Outcome Indicator 3: Vulnerable and marginalised groups' participation and representation at the national and local political structures / 3.1 Number of marginalised men and women elected to local bodies (union parishad) No target / Outcome Indicator 4: Legal rights and access to resources realised in programme areas / 4.1 Number of workers having annual pay increase through collective bargaining. (25% men 75% women.) 8,000 12,000 (150%) / men-2520 / women-9480 / 4.2 Number of acres of additional khas land and water bodies leased to poor and marginalised people. 600 630 (105%) / men- 283 acres / women-347 acres / 4.3 Number of women and men in programme areas having paid work and self-employment. 6,400 5,305 (83%) / men-1,750 / women-3,555 / 4.4 Total value (in million £) of government khas land and water bodies accessed by beneficiaries. 0.48 0.5 (104%) / Outcome Indicator 5: Children protected from hazardous labour / 5.1 Number of working children (aged 14-17) withdrawn and reassigned from non-hazardous work. 75% boys, 25% girls) / Withdrawn 1500 2036(134%) / boys: 1588; girls: 448 / Reassigned 1000 677 (68%) / boys: 556; girls: 121 / Outcome milestones not achieved within a 5% range included: / 2.1 Incidence of violence against women and girls in the project area / The field visits and discussions with project and MJF staff indicate this reflects a problem with the indicator, the target and the methodology for collecting the data rather than the approach to combating violence of against women and girls. The methodology used here is problematic because / a) it relies on baseline data from sites in which some MJF partners have been working for years, so the prevalence rates are low / b) the 1% milestone decline is too small to be statistically significant (small household sample) and also it will be sensitive to other kinds of changes, e.g., the prevalence of political violence / c) according to DFID’s own advice on indicators for VAWG, incidence of violence is an impact rather than an outcome indicator, so this should not have been selected as an outcome indicator. / 2.2 Number of women victims received justice / This low achievement may reflect a specific effect of the three month period of intense political turbulence, which was that in a substantial number of union councils, chairman, who convene the shalishes or informal local courts in which many VAWG cases are resolved, were absent (jailed or absconding). This was reported as a specific problem among VAW partners. If we assume that around 3 months’ worth of shalishes did not take place and adjust the target accordingly, it was almost achieved. / 4.3 Number of women and men in programme areas having paid work and self-employment / This counts numbers of men and women in programme areas who start jobs or enterprises after receiving some training or other support. This may be low because of the general slowdown in economic activity resulting from the political crisis, but there is no specific evidence of this. / 5.1 Number of working children (aged 14-17) withdrawn and reassigned from non-hazardous work. 75% boys, 25% girls) / On this indicator, it should be clarified that to withdraw children from work in hazardous sectors altogether is preferable to reassigning them to new jobs within them. So this achievement reflects an over-achievement, because more children have been withdrawn than reassigned. / Recommendations: / 1. MJF staff need to clarify why the victims of violence receiving justice indicators was so low below target. If the absence of union chairmen is the main explanation, then the target should be adjusted and the risk of this recurring should be noted and built into the programme design. MJF’s programme team will review this and come up with a solution by September 2014. / Log-frame recommendations: / 1.1 Number of poor, marginalised, and vulnerable households supported from government safety net services / This measures how many poor and excluded households are supported, but is also supposed to take into account how they come to be included in safety net services, because the programme activity includes making beneficiary lists and selection processes transparent and rule-bound. This should be specified in the logframe ‘Source’. MJF agrees with the recommendation and accordingly, the indicator has already been revised. / 1.2 Total amount (in £million) of social safety net support received by programme beneficiaries / Exchange rate fluctuations over which COPE has no influence will affect target achievement. This should either be specified as BDT, or the target should be adjusted in line with the exchange rate for each year. This indicator will be reviewed as part of the upcoming M&E review by February 2015. / 1.3 Number of boys and girls who were able to complete primary schools / This currently implies that the programme supported children through the (5 year) primary school cycle, but as COPE is 3.5 years, no children will be supported from start to finish of primary school through COPE. However, the completion of primary school/ class V is a credential or qualification which matters qualitatively more than merely having attended school for nearly five years. So this indicator can be reworded as ‘'# of boys and girls who were supported & completed primary school' in a given reporting period. MJF agrees with the recommendation and accordingly, the indicator has already been revised. / Outcome Indicator 2: Women and girls protected against violence / 2.1 Incidence of violence against women and girls in the project area / According to DFID’s own advice on indicators for VAWG (HTN 2013), incidence of violence is an impact rather than an outcome indicator, so this should not have been selected as an outcome indicator. There are also problems with both the target and the methodology for collecting the data. The target is likely to have been set too low (that is, set too high a level of achievement) because it is based on the incidence of VAW in communities after many years of interventions. An alternative outcome indicator could be ‘the number / % of girls in project areas who remain unmarried up to age 18’ [also sugged as an alternative output indicator]. This is feasible because the beneficiary profiles will make it possible to monitor the right age cohorts, and then also to trace girls who leave the village (as girls/women typically leave their villages when they marry and go to their husbands’). Alternatively, indicators of the acceptability of violence such as ‘% of men who think physical violence against women is acceptable’ can be used. MJF will remove the indicator from the logframe, because the programme doesn’t have the M&E tools to collect data against it. A new indicator will be developed as part of the M&E TA Review by February 2015. / 2.2 Number of women victims received justice / It is not clear that women are always receiving ‘justice’; ‘resolution or compensation’ may be better terms. This target was probably too high. If it were set on the basis of experience in sites where partners were working for several years, it should be revised downwards. If political turmoil affected the achievement, this needs to be programmed. MJF agrees with the recommendation and accordingly, the indicator has already been revised. / Outcome Indicator 4: Legal rights and access to resources realised in programme areas / 4.1 Number of workers having annual pay increase through collective bargaining. (25% men 75% women.) / This needs some clarification. An annual pay increase is a legal requirement but it tends to need negotiation to realise. This indicator measures the number of workers being empowered to build a legal platform on which to claim annual pay increase through collective bargaining. This depends on them entering unions, officially. Informally, they are bargaining through workers' associations at the unit level. MJF is working to both support workers' associations and unions. These activities are not actually ‘collective bargaining’ by the legal definition. ‘Collective action’ is a more accurate term and it better reflects the range of processes through which organised workers bargain, negotiate, struggle for and claim their entitlement to an annual pay increase as set out under labour law. MJF agrees with the recommendation and accordingly, the indicator has already been revised. / 4.4 Total value (in million £) of government khas land and water bodies accessed by beneficiaries. / A number of distinctions could be drawn here to better reflect the contribution of COPE. First, khas land can be permanently settled on landless people or temporarily leased; water bodies are only ever temporarily leased, and at a rental cost. The costs and benefits of these leases are therefore not all the same. This indicator will be reviewed as part of the upcoming M&E review by February 2015.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts? / Yes. Financial forecasts had to be revised downwards during the year once it became clear how much the political disruption towards the end of 2013 was going to curtail partner activities. Actual expenditure was 68% of the original forecast, but in line with revised forecasts. Funds received from DFID were all programmed in line with the annual forecast. / 2.2 Key cost drivers / The key cost drivers are the grants MJF makes its partner NGOs. The business case identified MJF’s identification and selection of its partners as an important value for money issue. In COPE, MJF has maintained its previous rigorous procurement process for selecting partners, based not only on project design, but also on experience, track record, integrity and organisational capacity. / Under COPE, MJF has also established unit costs to guide its partners, from salary to office and operational costs. This has brought partners costs in line with each other and ensured greater parity. However, partners have shown concern that some partner salary scales may have been set too low, and MJF is looking into the outliers to ensure performance is appropriately remunerated and staff skills can be retained. / 2.3 Is the project on-track against original timescale? / Yes. Activities slowed down for 2-3 months at the end of 2013 and beginning of 2014 as a result of political unrest, but despite this disruption, outputs are in line with, or ahead of, the milestones agreed for the first 8 months. This is a remarkable achievement given the upset of 2013 and its direct impacts on some regions and types of work. Some flexibility to adjust targets within a year, support from MJF staff, and other coping strategies appear to have helped partners manage through this period.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / A few changes are suggested above. Overall, the indicators used for monitoring and how they should be monitored in the field appear robust and well understood by partners. How log frame targets are set, data uploaded, cleaned and checked, and their translation into monitoring reports appear less clear and effective. There is room to strengthen the overall data management system to be speedier and more responsive to management and funder evidence needs. The RAT or real-time activity tracking system being piloted in the CHT programme is a promising option for real time monitoring, although problems with internet and even electricity access may mean a technologically simpler model (e.g., emailed / dropbox spreadsheets) would also speed up and improve the accuracy of monitoring data. These are some of the issues the M&E Review need to look closely into. This review will be completed by February 2015. The MJF proposal and the COPE business case both assumed a larger budget, and a significantly greater investment in research and evaluation than is currently being actively planned for. The business case plan to invest in more systematic qualitative monitoring through a ‘Qualitative Assessment Scorecard similar to the one developed by DFID Girl Hub’ has not been implemented. MJF’s own plans for a dedicated Policy research, Communications and Documentation unit have also not been implemented. The evidence base for the qualitative impacts that COPE will no doubt contribute is not currently being put in place. As part of the suggested M&E review, evaluation and research plans will need to be put into place more or less immediately if partners and contractors are to be in place to support the research and evaluation plan before the end of COPE. / 3.2 Where an evaluation is planned what progress has been made? / A review of monitoring and evaluation in the programme is planned in the next 2-3 months. This review will include the development of a strategy for evaluation, including measurement of qualitative change that the programme is contributing to.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The risk rating for one output was increased from low to medium. This raised level of risk reflects the political turbulence of 2013 and the likelihood that this will impact on a) the overall environment for livelihoods and civic activism; and / b) the scope for excluded or vulnerable groups to organise to challenge powerful groups. / Discussions with an MJF governing board member and other stakeholders indicates that this risk is less likely to be felt at the national than at the local level. The increase in risk rating for one output does not affect the overall risk rating, which remains at Medium. / Risk of funds not being used as intended / 100% of MJF partner projects are audited, and DFID commissions an audit of a further 25%. Recommendations are followed up in the next financial monitoring visit, but are mostly minor in nature. MJF’s financial management system is highly regarded, and close financial monitoring of partners is given a high priority. MJF has a zero tolerance policy for financial misuse. The risk of funds being diverted for other purposes is low.
4.4 Climate and Environment Risk / The project did not have an explicit climate and/or environment focus, and the logframe made no direct reference to relevant indicators or activities. However many of the projects carried out by partners involved individuals, household and communities regularly exposed to negative climate/environmental negative impacts. Pressure on land is already intense in Bangladesh and as a result many local disputes revolve around land. Climate change may make this pressure greater because one effect of rising sea levels and more frequent and intense storms could be to make some agricultural land unusable. Communities living in certain vulnerable areas are given information on the implications of climate change and possible avenues of adaptation by partners working in the area. Partners are encouraged to carry out participatory environmental assessments and to work towards establishing appropriate dispute resolution mechanisms to resolve disputes over access to natural resources (e.g. khas lands and water-bodies in char areas or areas which are most at risk from floods and tidal surge in the south). / MJF works with a large number of partners operating throughout the country. Supporting the different projects requires a significant amount of travel, which had an impact on transport emissions. In considering travel options, staff were asked to look carefully at costs and environmental impact. MJF developed an Environmental Emission Control Plan which was used to inform decisions about travel. / MJF’s current premises offer more opportunity to use natural light and to reduce the use of electricity (although this has not been costed), a source of energy which in Bangladesh is scarce. MJF reporting format will be automated to reduce use of paper and paperless working is encouraged.

5. Value for Money
5.1 Performance on VfM measures / On the main VfM measures in the logical framework, within the reporting year, achievements included: / An over-achievement of 5% on the transfer of khas land and water bodies to landless people / Value of safety nets received: these were almost 10% over-achieved, at £920,000 instead of £840,000 / BDT43,305,542/ £ 333,400 was recovered in terms of dower, marital entitlements and victim compensation. / On all these and other VfM measures in the logframe, COPE has performed at or above the original targets, and should generate the same or higher returns for unit cost (proportionally, or adjusted for lower budget and shorter timeframe) as estimated in the business case. / Other value for money measures in the business case included: / The cost-benefit analysis, which was done on the basis of a programme with twice the cost. This has not been fully updated in the light of the revised results framework – a full update will be done once the revised logframe is agreed at the end of this review. However, as the MJF component was the only part of the original programme for which economic benefits were calculated, these benefits have only been reduced by 30-40%, whereas the cost of the programme was reduced by 50%, it is very unlikely that a recalculated benefit-cost ratio will be lower than the one calculated for the Business Case. / Unit cost measures of some of MJF’s interventions (para 128 of the Programme’s Business Case). / Comparison unit costs for similar activities between different partners. This was covered in the previous section. Unit costs were established and enforced across all partner activities. Project costs are monitored through regular financial monitoring, and partners’ proposals were required to budget with these costs. Partners complain that these are low, and some seem on the stringent side, but the review did not conclude that they are unreasonably low, or that partners are unable to perform. Variations in staff-beneficiary contact time, one of the main programme costs, were discussed with different partners. In all cases, a justification for the level of contact was given. It seems clear that resources are being spent thoughtfully and with caution. / Management of MJF’s administrative overheads, and balancing management of internal costs against the need for effective management of programme risks and impact. Management overheads have been controlled in line with the original budgets. / One area where further work is planned in the next few months is to develop a better way to measure the most important qualitative changes it is working towards with its partners – another value for money measure identified in the business case. / 5.2 Commercial Improvement and Value for Money / MJF’s Finance Team has developed a full set of unit costs and harmonised partner project costs through its ‘Budget Guidelines’ (August 2013). These estimated and set ranges for staff salaries, staff numbers, office rent, maintenance and equipment, communications, travel, subsistence, meeting costs, grant size, overheads, audit fees, capacity development, information and communications materials and sub-partnerships. / The Review team explored partners’ views on these efforts to increase VfM. There are some concerns that experienced senior staff may have been driven out by caps on salary increments (5% instead of 10%) and low salaries; this suggests that tighter costs may not always have produced better VfM and may merely have contained costs. Others felt that they were unable to compete with UN and international NGOs in terms of attracting public officials to their events, as they could only pay low levels of ‘compensation’ or ‘travel costs’ and offer meagre lunches etc. The Review team also visited the offices of 10 partners (8% of the total) and so knows that these are basic facilities with no excess expenditure. / Recommendation / MJF has done very well to standardise costs across partners. But cost considerations should not be allowed to push out considerations of effectiveness. Unit cost comparisons might best be used for purposes of benchmarking – where outliers need to be justified – rather than as strict controls. The measurement of unit costs needs to be reviewed in the light of forthcoming work on measures of qualitative change, to ensure that control of unit costs does not come at the expense of qualitative measures. MJF will complete this review by December 2014. / 5.3 Role of project partners / 5.4 Does the project still represent Value for Money / Yes. The project is over-achieving against the milestones for the first year, despite spending less than was budgeted in Year 1 (as a result of the political unrest and the consequent slow-down in activity). / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on Partnership Principles and specific conditions / The funding in this programme is all channelled through non-government organisations. Partnership principles do not apply.

7. Conclusions and actions
The key conclusion of this Annual Review is that COPE is working well, despite the challenges of the political environment, and of adjusting budgets and workplans to the smaller budget and shorter timeframe. On all its outputs, COPE is delivering at or more usually considerably above the expected level. / Other than a few minor adjustments (reviews of the training and NFE inputs, ‘problem-solving’ explorations of why COPE under-performed on some outcome indicators) the key issues that need action are to do with how the results are captured. This means both the process and tools for monitoring, and even more importantly, the process and approach to evaluation and research. / The key recommended actions are to do with improving the ways in which MJF and its partners capture, aggregate and share the results of their work, including its outcomes and its processes. The best means of doing this seems to be to assist MJF with an M&E expert in citizenship, human rights, good governance and participation programming to support MJF and COPE to: / Finalise the logframe to strengthen monitoring; ensuring there is clear agreement on what is being measured, and the basis of reporting. This annual review has highlighted a few indicators which may need to be amended in the light of external changes (potential changes in national education policy) or DFID guidance (on prevention of violence against women), to ensure they continue to be relevant measures of the work the programme is doing. However, as noted, changes to indicators need to consider the feasibility of changing partners’ systems for data collection. Monitoring tools need to be amended to speed up data uploading and ensure monitoring reports meet the information needs of programme staff (in terms of timeliness and relevance). The M&E TA Review Team will finalise the logframe by February 2015. / Improve MJF and partners’ systems for documenting and reporting their contribution to qualitative changes. The logframe is now primarily quantitative, but with some clarification of definitions and sources, the qualitative elements of some of these quantitative indicators can be uncovered. MJF is also well aware of qualitative changes they and their partners contribute to which are not measured in the existing logframe at all. This is particularly relevant to Output 6, on policy influencing, which with better qualitative indicators could be given a higher impact weighting. ). With assistance from the M&E Review Team, MJF and its partners will revise their reporting system by September 2015. / Develop an evaluation plan; this may need to target particular areas of the programme in which understanding of the linkages between output and outcome are particularly unclear or are inadequately documented in the available evidence (e.g., Combating VAWG). The evaluation plan should also set out which qualitative outcomes / impacts are most valuable and which contribute most to the sustainability of the results, so that the evaluations in the remaining 2.5 years target the priority topics. With support from the M&E TA Review Team, MJF will complete the Evaluation Plan by September 2015. / Develop a research plan to assess the impact of COPE at the aggregate level, including in terms of its qualitative achievements. A fuller set of suggestions is provided in the accompanying Aide Memoire. With assistance from the M& E Review, a plan for the impact evaluation will be drafted by September 2015 / Identify workable management arrangements to support a stronger M&E, communications and research unit within MJF. To address this, MJF has targeted to appoint senior professionals to lead its Research, M&E, MIS and Communication Units by December 2014.

8. Review Process
A two person team, comprising Shyamal Barman (from Dhaka consulting firm Sustainable Development Associates) and Dr Naomi Hossain (from the UK Institute of Development Studies) undertook the Review between May 5 and June 15th 2014. The team were supported by the MJFM&E team who helped prepare the itinerary for partner visits, partners meetings and stakeholder and staff interviews, presentations and follow-up data requests. The review process involved the following: / Meetings with MJF staff, including programmes, M&E, finance staff and senior management / Meetings with 42 partner staff including head and field office staff / Meetings during the review with COPE funders, including the DFID core team responsible for COPE on three occasions and other DFID B staff with relevant interests/ expertise; also DFAT/Australian High Commission staff; DFID staff also accompanied the team on one field trip during which we visited projects of two partners / Project visits or contact with 10 partners (8% of the total portfolio) including one new partner; projects visited or beneficiaries met were in Dhaka (child rights project by VAWFSD); / Meetings with partner project staff, including in most instances the Executive Director, programme leads, field and M&E staff / Group discussions, meetings and activity observation with primary beneficiaries; this includes people who benefit directly from COPE activities through access to safety nets, legal, health or education services, participation in groups or service monitoring etc; on average around 30 primary beneficiaries were met with at each project (in some instances considerably more, but with less contact time), giving a total of around 300 beneficiaries from whom feedback was gathered / Discussions with secondary beneficiaries / stakeholders including local elites and stakeholders (such as the Nagorik or Citizen Forum in Khulna) / Discussions with local officials and other local stakeholders including elected union councillors and chairmen, upazila (sub-district) officials, doctors, teachers, employers etc / Meetings and discussions with other stakeholders including high ranking Government officials and prominent civil society activists, including one on the Governing Board of MJF. / Programme and M&E staff made annual performance presentations and also gave more detailed information about indicators and data collection methodologies. The Review team prepared checklists to use with different stakeholder groups, based on the logframe indicators and Review TORs. Preliminary findings including initial output (and outcome) achievements and scores were presented to MJF and to funders for corrections and feedback.