ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA) - Phase 1 & 2
Country or region targeted	Cote D’Ivoire, Democratic Republic of Congo, Ethiopia, Liberia, Malawi, Mozambique, Niger, Tanzania (including Zanzibar), Uganda and Zambia
Type of cost extension (if applicable)	Time extension
Original project budget	£50,000,000
Original project start and end dates	Start: 30 October 2010 / End: 31 December 2016
Cost extension value (if applicable)	N/A
New project end date (if applicable)	31 March 2019
Business Case Vault Document No.	7922740

INFORMATION
What is the project’s purpose?
The Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA) programme aim is to reduce morbidity and mortality in ten African countries by delivering a total of 203.5 million treatments for SCH and Soil-Transmitted Helminths (STH). For the countries in sub-Saharan Africa included in this programme, the aim is to control rather than eliminate SCH and this is in line with the WHO NTD (neglected tropical diseases) roadmap to 2020. Frequency of treatment is determined by prevalence of infection in school-aged children and mass drug administration (MDA) may have to be repeated as often as every year.
What is the objective of the cost extension or other changes?
This addendum is to extend the programme’s Business Case from January 2017 until March 2019 and to reflect the budget realignment between the two components within the ICOSA programme. / Historical Changes and Context / In October 2010, DFID provided £25 million for Phase I of the ICOSA programme to deliver treatment in eight countries (Cote D’Ivoire, Liberia, Malawi, Mozambique, Niger, Tanzania (including Zanzibar), Uganda and Zambia). Of the £25 million, £14.5 million was allocated to Crown Agents for procurement of the drug praziquantel (PZQ) and £10.5 million was allocated to the Schistosomiasis Control Initiative (SCI – part of Imperial College, London) to implement the programme and provide technical support. / In June 2014, DFID approved a costed contract extension to the ICOSA programme for an additional £25 million (Phase II) to expand the scope of the programme and to include two further countries (DRC and Ethiopia) until December 2018. Of the £25 million, SCI received an award of £16.6 million with the remaining £8.4 million being allocated to Crown Agents for procurement. / The SCI contract was for the delivery of 203.5 million treatments. However, the implementation component of the programme has overspent due to costs being higher than anticipated. The procurement budget, however, has made a saving of £2.4 million due to an increase in drug donation from Merck meaning that Crown Agents no longer need to purchase as much PZQ as originally budgeted for. The business case for Phase II of the programme indicated that “there should be some flexibility in the exact allocations to the selected countries and in the PZQ/implementation split, to accommodate some of the programme risks, primarily related to country uptake and speed of scale up”. / This led to a subsequent amendment to the implementation contract in December 2018, to realign the budgets between the two components (without a change to the overall programme budget) and to extend the programme’s end date until March 2019. / This change meant that the programme could continue activities until March 2019 in order to meet its original treatment targets plus follow-up activity.
What is the additional and total support the UK will provide?
There is no change to the overall programme budget. / The additional time extension for implementation would allow for continuation of the ICOSA activities including drug supply management, drug treatments, surveys, training and technical assistance to national NTD programmes in seven countries (DRC, Liberia, Malawi, Niger, Tanzania (including Zanzibar), Uganda and Zambia). These activities are critical both in terms of treating people and maintaining progress on control, and for timely follow-up to assess effectiveness.
What are the expected results?
The extension to 31 March 2019 will enable the programme to meet the original target number of both people treated (~64 million) and tablets distributed (~203.5 million). It will also mean that a potential gap in treatment and other programme activities prior to the next DFID NTD programme commencing (ASCEND) will be covered. Therefore, the programme will be able to achieve its outcomes and objectives.
What is the approach to implementation?
The ICOSA programme is compliant with the Gender Equality Act (2014). DFID will ensure that any activity supported considers the impact on gender equality, including disaggregation of data by gender and the inclusion of gender-based targets in results measurement. / Terrorism and financing: The overall risk of programme funds being diverted for terrorist related activities is considered low. / Risk and Safeguarding / The programme’s risk register was previously updated as part of the original contract amendment. There are no major notable changes in risk given that activity is continuing in the same contexts and with the same implementing organisations. / SCI had previously provided a detailed response to DFID with Imperial College’s policies on safeguarding (SCI is part of Imperial College). Further to this, safeguarding risks have been monitored via regular updates to the programme’s risk register and through monthly discussions with SCI.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The original business case covered Phase I and Phase II of the programme from October 2010 to December 2016. The key change under this addendum is to the end date and to reflect the budget realignment between the programme’s components. This is primarily to allow the programme to meet its original targets and prevent a gap in treatments and other programme activities.