Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Improving the Quality of General Education in Ethiopia
Programme Value: £130 million		Review Date: 21 September 2014 / (Review Period: 18 October 2013 – 17 September 2014)
Programme Code: 203396	Start Date: 18 October 2013	End Date: July 2018

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating	Medium

Main Acronyms Used
GEQIP	General Education Quality Improvement Programme
GoE	Government of Ethiopia
MoE	Ministry of Education
MoFED	Ministry of Finance and Economic Development
QESSP	Quality Education Strategic Support Programme

Summary of progress and lessons learnt since last review

The “Improving the Quality of General Education Programme in Ethiopia” was approved by DFID in October 2013 to support the Government of Ethiopia’s (GoE’s) general education sector. It is a four year (January 2014 – July 2018) £130 million programme with two components:

Component 1:- £120 million to the GoE through a World Bank Multi Donor Trust Fund to support GoE’s General Education Quality Improvement Programme phase two (GEQIP II). GEQIP II is being implemented by the federal Ministry of Education (MoE) through decentralized modalities including 11 regions, 900 districts, 10 universities, 36 Colleges of Teachers Education and approximately 40,000 schools and Alternative and Basic Education centres ; and,

Component 2:- £10 million to GoE’s Quality Education Strategic Support Programme phase two (QESSP II) through a DFID contracted Fund Manager. QESSP II is designed to maximise the impact of GEQIP II by providing support for research and evidence building, capacity building and technical assistance to the MoE.

GEQIP II is expected to contribute to improved learning conditions and institutional capacity for enhanced learning outcomes for 21.6 million children (of which 10.54 million will be girls). Some of the results anticipated are:
- All 40,000 plus government primary and secondary schools and Alternative and Basic Education Centres receiving a per capita grant of on average of £1.90 per pupil enrolled to focus on improving learning achievement (35% of the grant attributable to DFID);
- 1,600 principals and supervisors trained to ensure better managed, more accountable, primary and secondary schools and Alternative and Basic Education Centres (training for 560 principals and supervisors attributable to DFID);
- approximately 140,000 more qualified teachers and Alternative Basic Education Facilitators trained to use more participatory and inclusive teaching approaches in classrooms (46,000 teachers and facilitators attributable to DFID);
- 83 million more textbooks and supplementary materials effectively utilised by teachers and students to promote learning for all students, including the provision of braille books for the blind (29 million attributable to DFID);
- 200 secondary schools use new Information and Communication Technology equipment to enhance learning outcomes of students (equipment for 70 schools attributable to DFID);
- Skills and capacity of education officials in all 900 plus districts enhanced to monitor and support schools and Alternative and Basic Education Centres performance and help them to improve learning (training for staff in 315 districts attributable to DFID); and
- A national monitoring and evaluation system that builds on the existing infrastructure to provide more comprehensive feedback on progress and helps identify bottlenecks.
In addition to this by using a mix of instruments and working closely with government and partners, the education sector development plan is expected to produce the following outcomes:
- An increase in overall primary enrolment to 21.6 million (of which 10.54 million will be girls), from 17 million in 2012/13;
- Improved enrolment in the developing regional states, especially in pastoralist communities;
- A million more students completing grade 8 of primary school and 500,000 more completing lower secondary school (grade 10);
- Improvements in the gender parity index, especially at secondary level, by making schools more conducive to girls’ participation and learning;
- Better access to education for students with special needs; and,
- Improved learning outcomes for students with a minimum of 10 million students scoring above the basic level in the National Learning Assessment for language and mathematics at grades 4, 8, 10 and 12.
This is the first annual review of DFID’s ‘Improving the Quality of General Education Programme in Ethiopia’ for the period from October 2013 to September 2014. All crucial preparatory activities have been completed during the first year of the programme to establish a firm foundation to operationalize DFID’s support. These activities include:

- A launch event in January 2014 where key messages on the purpose and processes of GEQIP II were delivered by the Prime Minister of Ethiopia, DFID Ethiopia Head of Office and other development partners;
- A due diligence assessment conducted on the World Bank and an administrative agreement signed to channel resources through a Multi Donor Trust Fund (MDTF) for GEQIP II;
- The signing of a Memorandum of Understanding between the GEQIP II partners and the GoE;
- The signing of a financial agreement between the World Bank and Ministry of Finance and Economic Development (MoFED);
- The disbursement of $55 million from the World Bank to the MoFED in April 2014;
- The disbursement of £30 million from DFID to the World Bank’s Multi Donor Trust Fund (MDTF) for GEQIP II in June 2014;
- The development of a work plan for the GEQIP II for the fourth quarter of the 2013/14 Ethiopian financial year (April-June 2014), and for the period of July 2014 to June 2015;
- The initiation of a procurement process by DFID to hire a Fund Manager for QESSP II; and
- A review of how DFID will measure value for money (VfM) of this project and recommendations made for a shorter but SMARTER list of VfM indicators linked to regional benchmarks.

Summary of recommendations for the next year

Consider supporting the GoE to conduct an analysis of the different sources of funding for primary and secondary schools, including school grants, private contributions from parents/communities (in kind as well as monetary) and support from NGOs and how this varies from one region to another, and from one school to another. This will enable the government and partners to better understand the resources available in the sector;

Use of a standard template for preparing School Improvement Plans should be considered by the MoE to improve consistency in planning and budgeting at school level, and to provide simpler guidelines for less experienced school committees and Parent Teacher Associations. The template should be prepared in triplicate for sharing with districts, regions and federal level;

After the approval of the School Improvement Plan, the MoE needs to work hard in creating more awareness at district level on the importance of timely disbursement of school grant to schools to implement School Improvement Plan. The MoE also needs to share the audit finding with Regional Education Bureaus on a timely basis for strengthening the school grant disbursement mechanisms at district level;

Once contracted, the QESSP Fund Manager should prioritize procurement capacity building support to ensure that the key areas of institutional weaknesses, particularly at district level, are addressed as quickly as possible;

Training of teachers and Alternative and Basic Education facilitators as well as improvement in the Education Management Information System (EMIS) need to be prioritised to accelerate progress towards the 2015 milestone;

The design of the teacher licensing process should be finalised and rolled out to ensure better progress towards the 2015 milestone;

For the Teachers Development Programme impact evaluation and annual GEQIP progress reports should measure the logframe’s outcome indicator pertaining to the proportion of teachers using student centred approach; and

To conduct the next Annual Review by March 2015 to incorporate data from the 2014 Education Abstract, GEQIP II’s first progress report and audit and costing data from the procurement processes – all of which are not currently available. This will allow us to review progress against all of the logframe milestones and conduct a Value for Money analysis using the revised metrics.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203396/documents/

Outline of the programme

Increasing equitable access to quality general education has been a high priority of the GoE, especially since the launch of the Education Sector Development Programme (ESDP) III in 2006. Over the past ten years, impressive progress has been made in Ethiopia including enrolling 86% of primary school age children into schools. Other key accomplishments include:

- Increased Net Enrolment Ratio (NER) for primary education (grades1-8). The NER has increased from a low base of 24.9% in 1996/97 to 86% in 2012/13. Number of children enrolled in primary enrolment has reached 17 million, and the number of out of school children has dropped from 6.5 million to around 3 million between 1999 and 2008;
- Improved enrolment of girls. The gender parity index (girls to boys ratio) in primary education has increased to 0.94 in 2012/13 in comparison to 0.7 in 2001/02; and,
- Increased secondary enrolment. The Gross Enrolment Ratio (GER) has increased from 17.1% in 2001/02 to 38.4% in 2012/13 (36% for girls up from 13.7% in 2001/02). Despite improvement, only two out of five eligible children are in secondary schools.

Ethiopia has also put in place most of the building blocks for improving quality of education, including:

- Strong government commitment and clear policy direction;
- Expanded and well managed teaching force;
- Equitable provision of education services;
- A decentralized implementation structure;
- Accountability of schools to communities; and,
- A relatively robust Education Management Information System (EMIS).

Despite these accomplishments in expanding equitable access to schooling, and putting in place the foundations for quality improvements, levels of learning achievement are still very low. The 2011 National Learning Assessment has shown very low levels of learning outcomes: the average score of sampled students in grade 4 and grade 8 was below basic proficiency; the average score of majority (57%) of the students in grade 4 in four subjects was below basic level; and, the average score of majority (56%) of the students in grade 8 in five subjects was below basic level.

Recognising the urgent need to improve the quality of primary and secondary education, the GoE launched GEQIP as an eight year (2009 – 2017) programme. The UK contributed £95 million to the first phase (2009 – 2013) of GEQIP I. The first phase of DFID support, along with government and other donor’s contribution, achieved the following results:

- Over 88 million high quality textbooks and teachers guides were developed, printed and distributed to primary and secondary schools;
- The proportion of qualified primary teachers (grades 1 to 8) increased from 38% in 2009 to 56% in 2012; and,
- More than 98% of the schools received grants and used them to fund their school improvement plans that were developed and agreed with school communities.

However, at the end of the first phase, there remain many challenges pertaining to quality of primary and secondary education. Also, there was a strong need to consolidate the work done in GEQIP I and sustain its gains. To respond to these needs, in October 2013, DFID approved the Improving the Quality of General Education Programme to contribute to delivering DFID Ethiopia’s Operational Plan commitment to support 1.94 million children in primary and 240,000 children in lower secondary by 2015, of which at least half will be girls. This will be achieved by providing:

£120 million to the GoE through a World Bank Multi Donor Trust Fund (MDTF) to help improve the curriculum and availability of textbooks, to undertake teacher training; to continue to provide grants to schools to implement school improvement plans, to improve the capacity and management of educational leaders, and to develop the information and communication technology system to improve the quality of teaching and learning; and,

£10 million for QESSP II to improve evidence based programming, programme coordination, Monitoring and Evaluation. This support will be provided through a Fund Manager engaged by DFID.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

This Annual Review has not assessed annual outcome at this stage of the programme. However based on the discussions with stakeholders and the successful outcome of GEQIP I, it seems likely that good progress can be made on all 4 indicators in the next year. However, outcome indicator pertaining to assessment of teachers using student-centred teaching requires careful consideration as it is likely to be a difficult indicator to measure accurately.

Overall output score and description

A: Outputs meet expectation – Important and extensive preparatory work has been carried out to operationalize the programme. Despite the slow start of the programme and late disbursement of funds (the World Bank disbursed $55 million in April 2014 and DFID disbursed £30 million in June 2014), a good start has been made for most of the activities that had been planned for the fourth quarter of the year 2013/14 (April – June 2014). Farther, a firm foundation for the programme has been established and there is a good opportunity to catch up with progress in Year 2 (2014/15).

Key lessons

1. There are always likely to be delays between the implementation of different phases of a major programme (such as GEQIP I and GEQIP II), in terms of planning, procurement, communication structures, and finance. In future, it might be worth considering an inception or bridging phase of 3-6 months linking the first phase and second phases of a large nationwide programme.

2. Although the co-ordination and communication structures in GEQIP II are quite well defined, and build on already well-established relationships, it is always worth reviewing them and improving where necessary. In the case of GEQIP II, it would be valuable to have initial monthly co-ordination meetings, not least to clarify disbursement schedules from partners, and key capacity building actions with the GoE.

3. Experience from GEQIP I influenced the decision to increase the capacity of procurement, financial management and monitoring and evaluation of the MoE at national and regional levels in the very early stages of GEQIP II. This should enable the programme to reach its targets more successfully if the capacity development activities remain on track.

Key actions

1. Follow up on selection of printing companies for regional language textbooks in October 2014.
2. Check on progress in finalising the teacher licensing system by January 2015.
3. Confirm that the revised school grant guidelines have been approved.
4. Establish that national/regional personnel have been recruited for procurement and FM capacity building.
5. Check on the progress with the development of MoE’s Information and Communication Technology (ICT) policy and costed strategy.
6. Set up more regular (monthly) meetings, between GEQIP partners, and establish timing for future disbursement to GEQIP II and commitment to regular communication to all partners by the World Bank.
7. Follow up by DFID on the World Bank’s enhanced supervision of GEQIP’s social safeguards to ensure it is conducted per the agreed schedule.
8. Conduct the next Annual review by March 2015 to allow the use of data from the 2014 Education Abstract (due in October), the first GEQIP audit report (due in November) and costing date from the procurement processes. This will also allow a preliminary Value for Money analysis using the newly revised Value for Money metrics.

Has the logframe been updated since the last review?
Not Applicable since this is the first review.

However, the logframe has been updated since the indicative logframe submitted with the Business Case to improve the relevance and objectivity of number of indicators. For future Annual Reviews, it will be helpful to align milestone dates more closely to the Annual Reviews date so that it can utilise the most recent reporting.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved curriculum, textbooks and inspection
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
% of schools using the full set of printed curriculum documents in the regional language	Selecting a printing company to produce the full set of curriculum documents in mother tongue	The MoE has developed bidding documents for textbooks and teachers guides for Grades 1 to 4 in 7 regional languages. The technical and financial evaluation has been carried out by the GEQIP procurement team in collaboration with experts from curriculum directorate. The bid evaluation team has selected two printing companies and the evaluation report has also been approved by the MoE’s bid endorsing committee. / Also, the bid evaluation report has been shared with the World Bank for their review and no objection. / However, the MoE has learnt that the review and approval of the bids by the World Bank may involve a lengthy process; that will cause a significant delay in the printing and distribution of the above mentioned textbooks. Hence, the MoE has come up with a practical solution to use the left-over resources from the Teacher Development Programme for this activity. All Teacher Development Programme partners, including DFID, have agreed to this. / (Indicator Score: A)
Number of textbooks and teacher's guides (based on new curriculum) distributed to schools (cumulative)	0	This will be reviewed in 2015.

Key Points

All Teacher Development Programme partners have agreed for MoE to use the project’s left-over funds for the printing and distribution of textbooks and teachers’ guides. The GoE has selected two agencies for printing textbooks and teachers’ guides. Therefore, we assess that the milestone for this Output has been achieved.

The Teacher Development Programme left over fund of USD $ 2,178,794 (excluding the Netherlands share which was returned) has been transferred to the GEQIP II account.

Increasing procurement capacity of the MoE is one of the GEQIP II targets. Given the large procurement requirements of this programme, the Directorate of Planning and Resource Mobilisation has emphasized the need to ensure no delays in procurement which might impact negatively on programme indicators and milestones. As a result, the MoE has established a GEQIP II procurement unit under the procurement directorate of the MoE and a procurement specialist has been hired who will be working together with the MoE procurement experts.

The World Bank is of the view that procurement at national level is reasonably good. However, more capacity is needed for GEQIP II procurement at regional levels.

Printing company capacities vary across the regions, so it would not be practicable or cost-effective for each region to procure a company to print its own textbooks. In general, there are likely to be only a very few companies with the technical capacity to print the required materials, and also from the VfM point of view, the larger the print run, the cheaper the production of materials.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable as it is the first AR

Recommendations

- Ensure that recruitment and training of procurement staff is prioritised in the coming financial year.
- Monitoring of textbook costs for Value for Money purposes should include not only printing of books but transportation and distribution to schools to provide a comprehensive understanding of the true costs of providing textbooks.
- The MoE needs to push for swift printing of textbooks in mother tongue so that books will be available for schools on time.

Output Title	Strengthened teacher training programme
Output number per LF		2	Output Score	C
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Number of teacher trainees completing programmes with updated curricula (% female) including Alternative and Basic Education (ABE) facilitators upgraded each year	28,000 (40% female) teachers and 1,000 ABE facilitators	The annual education abstract from the MoE EMIS is yet not finalised, therefore, we are not in a position to fully assess this indicator at this stage. However, 1,161 ABE facilitators have been upgraded in Somali region in 2013/14. / (Indicator score: C)
No. of teachers licensed (cumulative)	100,000	A written evaluation, comprising of content and pedagogy, has been carried out for 46,000 teachers from all regions. There is also a plan to conduct written evaluation for additional 12,000 teachers in October 2014. However, the licencing activity has not yet started as the directorate of Teachers Licencing and Relicensing (TLRD) is finalizing the modalities to issue licences. / (Indicator score: C)

Key Points

Although the GEQIP II was originally scheduled to begin in January 2014, it was delayed by a mixture of slow DP disbursement, as well as capacity issues in the MoE. This has meant that the first milestone for Output 2 has not been achieved.

MoE Teachers Licencing and Relicensing Directorate (TLRD) is seeking technical assistance to improve the validity of the assessment instruments and to benchmark teachers’ performance with the professional development career structure. By October 31, 2014, Teachers Licencing and Relicensing Directorate (TLRD) will prepare the Terms of References for the hiring of consultancy for: (i) licensing and relicensing organizational capacity building; (ii) assessment and result analysis; and (iii) Teacher Licensing Information system. Thus, the second milestone for Output 2 has not been achieved.

Certification/licensing will be given to teachers and leaders who score above the cut-off point (combined scores of written tests and performance assessment).Those that score below the cut-off point will be given two chances to re-take both tests. In the short term, the aim of the licensing system is to certify teachers and school leaders who meet the standards and encourage others to improve their competencies. In the long term, however, the system will determine individual’s entry and continuation in the teaching profession.

Government and DP’s funding to the Promotion of Basic Services (PBS) programme is complementing GEQIP by supporting payment of teacher salaries.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable as it is the first AR

Recommendations
The training of teachers and upgrading of ABEs facilitators in GEQIP’s work plan needs to be prioritised along with improved Education Management Information System (EMIS) data to ensure better progress towards the 2015 milestone.

The modalities of the teacher licensing process should be finalised and rolled out by January 2015 to ensure better progress towards the 2015 milestone.

Output Title	Improved school improvement programme including Provision of school grant
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
% of schools receiving school grants. (Academic year begins on September)	October -10% / November - 60% / December -30%	Not in a position to score at this point of time. However, the annual work plan for the year 2014/15 has been developed and the World Bank is likely to disburse funds to MoFED by mid-October. All modalities are in place to transfer funds to schools from MoFED through the districts. It is expected that all schools will receive their grants by December 2014. / (Indicator Score: NA)
% of rural, isolated area schools, ABEs, and schools with less than 200 students using revised, simple and pictorial School Improvement Plan (SIP) guidelines that are judged to be satisfactory	School grant allocation revised, SIP guidelines revised and agreed	The School improvement Plan (SIP) guidelines have been updated to include small, disadvantaged, remote schools, schools with special needs pupils and ABEs and are ready for approval. / (Indicator score: A)

Key Points

The first indicator could only be objectively assessed by the end of December. The second indicator has been achieved.

The focus in GEQIP II is on using school grants for improving learning achievement through additional learning materials such as textbooks, supplementary readers, and charts, laboratory equipment, teachers’ reference books, educational media etc.

The grants are disbursed by the MoFED to regional finance departments, then to districts and finally to schools. Schools without bank accounts have to travel to districts to collect their grant. This means that although it may only take about a month for grants to reach districts, it may take another month or two to reach schools.

Although the grant is not meant to be used for major infrastructure improvements, it is worth bearing in mind that small-scale improvements such as additional latrines for girls, school gardens, solar energy, water supplies, mending leaking roofs can contribute to a better learning environment. The latest school grant guidelines of the MoE appear to support this.

Although there is a standard process for school development planning involving a school management committee consisting of principals, teachers, parents, and students, there does not appear to be a development plan format or template which might guide schools to plan, prioritise and cost better, as well as making it easier for districts/Regional Education Bureaus to assess plans for funding.

A strong feature of the school grants guidelines are the accountability mechanisms. Each school is required to erect and maintain a School Grants Notice Board and display, details of the date each School Grants was received, and how the School Grants have been spent. Income from other sources, and the details of major expenditures made by the school with those financial resources, are also required to be included on the School Grants Notice Board. The School Grants Cash Book is retained by the school or Alternative Basic Education Centers, along with all receipts, invoices and quotations, and is always open for examination by members of the Parent Teachers Associations, the school community at large, school inspectors, and auditors.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable as it is the first AR

Recommendations

It would be useful to carry out research on the different sources of funding for primary and secondary schools including school grants, private contributions from parents/communities (in kind as well as monetary) and support from NGOs and how this varies from one region to another, and from one school to another.

A school improvement plan format or template ( in triplicate for sharing with districts/regions) should be considered to improve consistency in planning and budgeting at school level, and provide simpler guidelines for less experienced school committees and Parent Teachers Associations.

Monitoring & Evaluation should include checks on how well schools are adhering to the accountability mechanisms laid down in the school grant guidelines.

After the approval of the revised School Improvement Plan guideline, the MoE has to work hard in creating more awareness at district level on the importance of timely disbursement of school grants to schools. The MoE has to feed in audit findings to Regional Education Bureaus to strengthen the school grant disbursement mechanisms at district level.

The Annual Review timing needs to be changed to allow it to measure whether school grants have been fully disbursed by December.

Output Title	Strengthened education management and administration
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
No. of capacity building proposals supported by QESSP II	QESSP Fund Manager selected and contract signed.	The Fund Manager has been identified and post-tender clarification is currently underway. It is expected that contract will be signed by end of October 2014. / (Indicator score: B)
No. of supervisors and directors exposed to quality and relevant short term leadership training annually (%female)	0	This milestone will be assessed in 2015.

Key Points

This output has been slightly under-achieved as we are waiting for approval for the contract to be signed.

Two areas (procurement and financial management) is being targeted in GEQIP II and the World Bank is of the view that procurement capacity has been improving throughout GEQIP I but that financial management is more of a challenge, especially at decentralised levels in districts, colleges and schools.

Annual work plan and budgets also vary considerably in quality and relevance by institution/implementing agency, and there seems have little grasp of unit costs and GEQIP II priorities. This could impact negatively on deliverables.

Strengthening Education Management Information System and National Learning Assessment tools will be an important link with the quality focus of GEQIP II, and contribute to improve Monitoring & Evaluation.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable as it is the first AR

Recommendation

Once the Fund Manager for QESSP II is contracted, procurement of capacity building support should be carried out in a timely and carefully targeted manner to ensure that the key areas of institutional weaknesses identified are addressed as quickly as possible.

Output Title	Improved use of ICT to enhance the quality of education
Output number per LF		5	Output Score	B
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
Information and Communication Technology in Education Policy formulated, approved and used by all stakeholders to guide initiatives.	Terms of Reference (TOR) / developed and agreed	The Terms of Reference has been drafted by the MoE and is being reviewed by the World Bank. They are likely to be finalised by the end of October 2014. / (Indicator score: B)
Schools equipped with energy efficient Information and Communication Technology labs	Sample schools selected	The MoE has identified 300 secondary schools based on the following criteria: access to internet; availability of power; availability of suitable and furnished computer labs; and distance from main road. / (Indicator Score: A)

Key Points

Milestone for the first indicator has only been partially achieved but good progress has been made, the second indicator has been achieved.

As this is an entirely new component compared to the GEQIP I, procurement will be critical in ensuring Value for Money and suitability in terms of equipment.

A key factor will be the development of both a realistic Information and Communication Technology (ICT) policy and costed implementation strategy.

Information and Communication Technology training and capacity building for teachers will also be a key factor to ensure sustainability of the infrastructure as well as effective learning by students.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable as it is the first AR

Recommendations

The consultant together with the MoE needs to identify lessons learnt of good practice (and failures) from other African countries and factor these into the Information and Communication Technology policy and implementation strategy.

The MoE Information and Communication Technology directorate will need to build maintenance contracts into costs of this component.

Output Title	Improved co-ordination, monitoring and evaluation
Output number per LF		6	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		NA	Impact weighting % revised since last AR?	NA

Indicator(s)	Milestones	Progress
% Implementing Agencies providing timely inputs to GEQIP annual planning exercise and GEQIP six monthly reports	80%	All implementing agencies contributed to the Annual Work planning Exercise. Implementing agencies include 11 MoE directorates, 11 REBs, 10 universities and 36 Colleges of Teachers Education. MoE has also received the six monthly reports from all implementing agencies. This ensured 100% involvement from all relevant implementing agencies. / (Indicator score: A+)
Evidence base on impact of reforms aimed at improving the quality of education	No milestone	To be assessed in 2015

Key Points

This output milestone moderately exceeded expectation. However, although participation in the annual work plan exercise was high, the actual quality and consistency of different institutional plans and reports varied considerably. The World Bank has developed a useful template to simplify the complexity of many institutions contributing to the GEQIP results and outputs which could be helpful to MoE’s annual planning process.

Given the huge coverage of the GEQIP II, it is a challenge for all levels of the system to be fully conversant with the programme’s key targets and priorities.

Monitoring & Evaluation has already been identified as a challenge, and in particular access to accurate data. However, the impact and management of school grants for GEQIP I has been independently evaluated and captured in the evaluation report. In addition GEQIP I school grant audit has been conducted by the audit service under the Office of the Federal Auditor General (OFAG). This process will be maintained for GEQIP II.

Co-ordination, joint government and partner reviews, are carried out every 6 months along with Annual Reviews. The involvement of funding partners seems to vary. For example only two DPs commented on the annual work plan.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable as it is the first AR

Recommendations

Given the length of time between 6 monthly reviews, there should be monthly co-ordination meetings between the GEQIP funding partners, monthly meetings between the World Bank and State Minister of Education, and regular e-mail updates on key processes or documents from the World Bank during the initial stages of the programme. The frequency of these meetings can reduce as the programme becomes more established.

Future planning exercises should include guidelines that could assist the understanding of the GEQIP’s key targets and priorities and how they can be achieved at the different levels and institutions.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers for GEQIP II, as set out in the Business Case are:

- Cost of school grants
- Unit costs of textbooks
- Unit cost of enhanced pre-service training for primary and secondary teachers
- Unit cost of upgrading teachers
- Cost of Information and Communication Technology (ICT) infrastructure in secondary schools

The table below describes how much of the financing will be directed to the cost drivers in the life time of the project.

Cost driver	Estimated cost	% from the total project cost
School grant	USD $248,950,000	45%
Teaching and learning materials	USD $ 104, 264,814	19%
Pre-service teacher training	USD $ 19,700,000	3.6%
In-service teachers training	USD $ 29,800,000	5.4%
A national ICT infrastructure Improvement	USD $ 28,430,000	5.2%

DFID Ethiopia has recently undertaken a study to strengthen the Value for Money (VfM) measures in its Human Development Programmes. This study suggests that only a few of the cost drivers in the business case lend themselves to be a valid Value for Money indicator for the Improving the Quality of General Education in Ethiopia Programme. Therefore, the following additional Value for Money measures have been suggested for the programme:

Average cost per textbook (a measure of Economy): Average cost calculation needs to include not only cost of printing of books but transportation and distribution costs to schools, and this measure needs to be compared with the unit costs in sub-Saharan African countries;

Total cost per primary teacher trained (a measure of Economy): This measure needs to take account of both initial teacher education and continuing professional development costs – for example of upgrading primary teachers from certificate to diploma. This will need to assess the extent to which student-centred strategies are in use and needs to look the data from comprehensive evaluation;

Average price of computer labs installed and operational in secondary schools (a measure of Economy): This measure should include both purchase and installation. Maintenance might also have to be included if there is a standard maintenance contract. This measure needs to be compared with the cost in other African countries;

Cost per primary pupil educated (a measure of Cost-Effectiveness): The ultimate measure of this cost driver will rest with learning outcomes of students and needs to look at the data from the National Learning Assessment ;

Procurement processes completed on time (a measure of Efficiency): The theory behind including this is that key deliverables such as textbooks, computer labs, training delivered early are more likely to lead to achievement of programme objectives and milestones; and,

Receipt of school grants - speed of delivery by system (a measure of Efficiency): The timely receipt of school grants means more immediate impact on provision of necessary inputs that can impact on the quality of education.

VfM performance compared to the original VfM proposition in the business case

Given that this review covered the preparatory phase of the GEQIP II and that procurement of many of its components are still underway, there was not enough data and information on costs to be able to make a valid assessment at this time. It is recommended to conduct the next Annual Review by March 2015 so that a VfM analysis can be conducted using these revised metrics. This will allow us to use the costing data coming from the procurement processes, the most up to date expenditure data from the Interim Financial Reports and information from Education Abstract that will be published in October/November 2014.

Assessment of whether the programme continues to represent value for money

This cannot be assessed at this stage of the programme as actual implementation of GEQIP II is in its early stages. However, as it builds on what has been assessed as a successful first phase (GEQIP I), there are opportunities to increase VfM in this second phase based on lessons learnt from the previous phase.

Quality of financial management

It was agreed that the project will be staffed with finance officers at the MoE, MoFED and regional offices. Accordingly, the MoE has already recruited three personnel (a financial management expert, a financial management analyst and an accountant). The recruitment of an additional financial management expert is still under way. At the MoFED, one finance officer and coordinator have been made responsible for the GEQIP II. Also, accountants have been assigned to all regional offices except for Dire Dawa, Addis Ababa and Tigray regions which are in the process of assigning accountants.

The project funds were only disbursed in late April 2014 to the MoFED, and from the MoFED funds were released to the MoE, regions and other implementing agencies such as Universities in May 2014. Hence, there was little time for implementing agencies to implement the proposed activities for the fourth quarter of the 2013/14 fiscal year (April-June 2014). As a result most of the activities planned by the implementing agencies for the Ethiopian financial year (EFY) were not implemented and hence activities are transferred to the next EFY. The main reason for the late disbursement of the fund was the slow start of the project as a result of a major delay in the preparation of an evidence-based annual work plan. This delay occurred primarily due to the slow process of recruiting contracted staff to support the GEQIP Coordination Office and the technical directorates in the MoE.

Of the $54 million disbursed by the MoFED to the MoE, Regional Educational Bureaus and other implementing agencies in April 2014, only $8 million was recorded as actual expenditure between May and June 2014 in the Interim Financial Report (IFR). The main reasons for this low spend was late disbursement of funds to implementing agencies and to schools.

District finance offices and regional finance Bureaus submitted the first GEQIP II financial reports for the period April to June 2014. Also, an Interim (un-audited) Financial Report has been prepared by the MoFED and is being approved by the World Bank audit. GEQIP II’s first financial audit report is expected to be available in November 2014.

Summary of Disbursement

Year	Budget	Disbursement	Expenditure	Variance
2013/14	$55 Million	$54 Million- April 2014	$8 million from May - June 2014	$46 Million

The financial management challenges have been discussed in the first implementation support mission of the project and key action points have been identified including organising a financial management taskforce meeting in October 2014 conducting and continuous Financial Management training. The first Financial Management training will take place before end of October 2014 and the World Bank will provide technical support for delivering the trainings and reviewing the training materials. We will continue to monitor levels of expenditure through the quarterly Interim Financial Reports.

Date of last narrative financial report	Not yet available. Draft Interim Financial Report (IFR)sent for the World Bank and should be available in beginning of October 2014.
Date of last audited annual statement	The first audit is underway and the draft report will be available in 31st October 2014.

E: RISK

Overall risk rating: Medium

The solid foundation developed under the GEQIP I is a good justification for retaining this assessment in the BC. The strengthening of financial management, procurement and Monitoring & Evaluation, particularly at decentralised levels, will be a key factor in ensuring that the risk level remains at medium throughout the life of the programme.

Overview of programme risk

There may be some possible risks in relation to supporting government to improve the quality of general education and their resettlement programmes. Since GEQIP II is a nationwide programme it will support schools in Commune Development Programme areas. The World Bank’s Indigenous People’s Safeguard (OP4.10) was triggered during the project appraisal and an enhanced social assessment was conducted. The entire GEQIP II MDTF, including DFID’s funds, is subject to this safeguard, known in Ethiopia as the policy for Vulnerable and Marginalised Groups. DFID has worked closely with the World Bank, the GoE and other donors to ensure that safeguards are well incorporated throughout the key guiding documents of the GEQIP II and are applied to all donor funds. These include the memorandum of understanding signed between pooled partners and the GoE and the financial agreement signed between the World Bank and MoFED. The World Bank is responsible for monitoring government’s implementation of the safeguard issues and will report on them to the partners every 6 months. The first implementation support mission that was carried out in June 2014 did not look at the government’s adherence to the safeguards since not much has been implemented as part of the project activity. The next implementation support mission that will take place in December 2014 will look closely this issue and a report will be delivered on the government’s adherence to the safeguards as part of the Aide Memoire by beginning of January 2015.

There are some risks related to procurement capacity at all levels of the GoE and limited understanding of the World Bank procurement procedures. The agreed institutional arrangement for the implementation of the procurement aspect of the project is partially in place and a procurement team has been established for the GEQIP II under the procurement directorate of MoE. It has been noticed that there is an improvement in the procurement process of textbooks and as a result 5 National Competitive Bids (NCBs) and 3 International Competitive Bids (ICBs) totalling of $40 million have been launched. But this needs to be monitored closely to make sure that other procurement processes for goods and consultancy services are in place on time.
The coordination of partners appears average and there is a need to set up more regular (monthly) meetings, between the GEQIP partners, and establish timing for future disbursement to the GEQIP II and commitment to regular communication to all partners by the World Bank.

Outstanding actions from risk assessment

How the monitoring of social safeguards is being undertaken needs to be assessed during the next annual review. DFID need to follow up with the World Bank and ensure it is going to be done as it is planned.

Need to make sure that full procurement staff are in place and have a good understanding of the World Bank procurement procedures.

The World Bank has to arrange more regular coordination meetings and demonstrate their commitment to regularly communicate with all the Development Partners.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The Business Case was approved in October 2013 and administrative agreement and due diligence assessment with the World Bank was agreed and signed in April 2014 and May 2014 respectively. There was some slippage in the programme due a combination of slow initial implementation of key actions by the MoE, and slow disbursement of initial funds by partners. After the disbursement of $55 million by the World Bank in April 2014, DFID transferred £30 million to the Multi Donor Trust Fund (MDTF) account on June 2014. Even if it is has been explained in the financial management section of this review that expenditure of funds are low, it is important to note that important and extensive preparatory work has been carried out to operationalize the programme and a firm foundation for the programme has been established. There is a good opportunity for the programme to get back on track soon and to catch up with progress in Year 2 (2014/15).

Regarding the establishment of QESSP II; a winning Fund Manager has been identified and is in the process of being contracted. As a result no funds have been transferred to the fund manager to date. It is expected that the winning supplier/fund manager will be contracted by end of October 2014 and start the preparatory work soon after. There is a need for DFID, the fund manager and the MoE to ensure that the QESSP moves swiftly so that Technical Assistance (TA) to the MoE is in place in time to give the support that is required to maximize the impact of the programme.

Fund disbursement table

Programme	Forecasted	Disbursed
GEQIP II	£30 million - May 2014	£ 30 million- June 2014

Performance of partnership (s)

Overall the performance of partnerships appears to be satisfactory. The GoE through the MoFED and MoE have maintained their political commitment to the GEQIP II, in particular its Planning and Resource Mobilisation Directorate with the support of GEQIP Coordination Office , have managed to act on several of the initial processes (such as the annual work plan). Progress on identifying additional staff for capacity building in financial management and procurement has also been made.

The World Bank has to reconsider its lengthy processes in reviewing and approving of bids that will cause a significant delay in delivering results as in the case of the printing and distribution of the mother tongue textbooks.

Contributions by financing partners have been good. The Embassy of Finland, Italian Development Cooperation, the World Bank and Global Partnership for Education (GPE) have maintained their commitments and all, with the exception of Italy, have disbursed funds to the MDTF. Italy has finalised its administrative agreement with the World Bank and is preparing to disburse. USAID is in the process of reviewing the administrative agreement.

Comments from partners on the annual work plan came from the World Bank, DFID and Finland. DFID Ethiopia will need to continue being an active partner, and its role in ensuring links between programmes such as the Promoting Basic Services is an important one.

Asset monitoring and control
N/A

G: CONDITIONALITY

Update on partnership principles (if relevant)

Ahead of our £30m GEQIP II disbursement to the MoFED in June 2014, DFID carried out a programme specific partnership principles assessment. This assessment built on the country level Partnership Principle Assessment (PPA) conducted in November 2013, but included new information that had become available since November 2013 and which was relevant to GEQIP II. Taking account of all previous and new information available to us, we judge that the Government of Ethiopia’s commitment to the partnership principles remains sufficient for disbursement of £30 million to GEQIP II.

The preparatory work on the GEQIP II has established a strong foundation for upholding our partnership principles and a clear structure delineating how the funds will be used. Looking forward the main onus is on ensuring sound monitoring of these shared commitments so that any concerns regarding adherence during implementation are detected and addressed at an early stage.

The next programme and country level Partnership Principle Assessments (PPA) will be conducted and approved before our next disbursement is made in May 2015.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The GoE and development partners have agreed on a Results Framework to conduct timely assessment of results generated by the GEQIP II, including its impacts on institutional strengthening and improving learning outcomes of students. The key indicators of the Results Framework are: student textbook ratio, use of active teaching approaches by teachers, utilization of the school grants for improving teaching and learning at the school level; completion of school report cards at the district level; and, reduction in dropout rates at grade 1 and improvement in the ratings of schools. The MoE has agreed to prepare six-monthly and annual national consolidated GEQIP II performance reports by activities and by implementing agencies, and quarterly financial reports. These reports will be discussed by all GEQIP II partners during the Joint Review Mission (JRM) and Annual Review Meetings (ARM). These meetings will also identify specific thematic areas to undertake more in-depth studies including evaluation of the Teacher’s Development Programme (TDP), school grants, and the overall impact of the GEQIP II by undertaking mid-term and end-term reviews. A draft Terms of Reference has been developed by the MoE, in consultation with development partners, to recruit an independent consulting firm to support the GEQIP II mid-term and end-term reviews/evaluations and also to undertake annual school audit, independent procurement evaluation, evaluation of school grants that will inform VfM assessments.

DFID will provide capacity building support to all GEQIP II Monitoring & Evaluation activities through QESSP II.
The GoE and GEQIP II pooled funding partners carried out a joint implementation support mission in June 2014. This mission reviewed GEQIP II progress by component and provided support to resolve key technical issues; discussed the 2014/15 work plans and budget forecast; and, carry out a procurement and financial management review. The GEQIP II project coordination office is currently preparing the first semi-annual national consolidated report for sharing in November 2014.
Monitoring progress throughout the review period
The core review team included Richard Arden (DFID South Sudan, Essential Services Team Leader, and Senior Education Adviser) and Rahel Yergashewa (DFID-E Education Adviser). The review team carried out interviews with key stakeholders from the GoE at federal level including MoE (Director, Planning and Resource Mobilisation, GEQIP Operation Manager, MoFED (GEQIP II accountant), and a primary school head teacher. Meetings and discussions were also held with the World Bank, Finland, and DFID Ethiopia Human Development team members and economists.

A number of key documents were also consulted as part of this review including:

1. GEQIP BC and Logframe
2. Report on Strengthening DFID Ethiopia’s Tracking of Value for Money in its Human Development Programmes
3. Ethiopia GEQIP II World Bank Implementation Support Mission – Aide Memoire – July 31st 2014
4. MoE School Grant Guidelines
5. MoE Work Plan Template
6. World Bank Results/Outputs Template

This annual review has been Quality Assured within DFID Ethiopia by Jyoti Shankar Tewari (Senior Human Development Adviser) and Angela Spilsbury (Human Development Team Leader) and OPEX. Their comments have been incorporated.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How are the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process