Annual Review – post April 2018

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / Green Climate Fund (GCF): Long-Term Support to Multilateral Climate Funds
Programme Value £ (full life): £720m of which DFID £380m; BEIS £340m		Review Date: 24/3/2019
Programme Code: / 202737	Start Date: 01/04/2015	End Date: 31/07/2023

Summary of Programme Performance
Year	2016	2017	2018	2019
Programme Score	B	A	A	A
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4735004.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/7927444.xlsx

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Green Climate Fund (GCF) is a multilateral international climate finance fund, established under the UN Framework Convention on Climate Change (UNFCCC) in 2010 as the principal dedicated multilateral vehicle to support low carbon and climate-resilient development in developing countries. The UK is contributing £720 million to the GCF in its initial resource mobilisation period (2015-18), with DFID contributing £380m, and BEIS providing £340m.

The purpose of the GCF is to promote paradigm shifts towards low-emission and climate-resilient development pathways by providing support to developing countries to limit or reduce their greenhouse gas emissions and to adapt to the impacts of climate change. This will help vulnerable people to cope with the impacts of climate change and, through reducing emissions, will help to slow down the rate of climate change and reduce the severity of future impacts.

The GCF is central to delivering a significant portion of the $100bn pledge per year that developed countries have committed to mobilising for developing countries by 2020. The GCF is recognised globally as the main multilateral vehicle for mobilising increased climate finance, as part of the effort to reach the $100bn commitment and meet the ambitions of the Paris Agreement.

The GCF received overall pledges of $10.3bn for its ‘initial resource mobilisation period’ of 2015-2018, receiving funding from 43 countries (including 9 developing countries). The UK is in the top three contributors.

The GCF is structured into 3 ‘windows’ covering: low carbon growth (mitigation); building climate resilience (adaptation); and a dedicated Private Sector Facility to promote private sector partnerships and lever private finance (for both low carbon and climate resilient development). GCF aim to allocate half of its funding to resilience and half to mitigation, with at least half of the resources for resilience allocated to particularly vulnerable countries including Least Developed Countries (LDCs), Small Island Developing States (SIDS) and African States.

Through the UK support to the GCF we expect to achieve the following:

Outputs:
GCF makes successful transition from design phase to full functioning, demonstrated through continuing progress on key operational aspects
 GCF makes progress on key priority areas including private sector finance, a balanced approach to mitigation and adaptation, and facilitation of a country driven approach
 GCF demonstrates an innovative approach to providing climate finance through focus on learning, building national capacity and capability, and gender sensitive programming

Outcome:
GCF demonstrates the ability to deliver results at scale, measured through the indicators of:
 Tonnes of carbon dioxide equivalent (CO2e) emissions (cumulative) mitigated through improved GCF projects, attributable to the UK contribution
 Number of direct and indirect beneficiaries (cumulative) of GCF support through approved projects, attributable to the UK contribution, to build resilience.

Impact:
GCF demonstrates its unique position in the climate finance architecture, transforming the volume and access to climate finance.

Summary supporting narrative for the overall score in this review (1/2 page)
We judge that GCF made good progress overall in 2018, meeting expectations and demonstrating it is a maturing institution capable of programming climate change investments at scale (over $2bn of investment approved in 2018). The Fund consolidated its institutional capabilities in 2018: it now has a Secretariat staff of over 210; fully functioning independent units (covering evaluation, integrity, and redress[1]); and has appointed the World Bank as permanent Trustee. Its portfolio of approved projects stood at $4.6bn at the end of 2018, balanced, balanced between mitigation and adaptation investments and with almost three quarters of adaptation funding directed to the most vulnerable countries, including LDCs, SIDS and African States (exceeding its 50% target). Furthermore, 40% of programming is through the GCF’s Private Sector Facility, maintaining the Fund’s successful engagement with private sector partners. GCF’s network of accredited implementing agencies rose to 75 in 2018, and significant progress was made on finalising legal agreements with project partners to enable project implementation to accelerate, including with the World Bank. Demand for GCF financing continues to grow in developing countries, and the project pipeline now stands at around $15bn. 2018 also saw the launch of GCF’s first formal replenishment process, scheduled to conclude in October 2019 with a pledging conference to achieve greater resuts through provision of new funds for the coming years .The ICAI report on UK aid for low carbon development reflected positively on the UK’s influencing agenda as it relates to the GCF. In particular, the report recognised the UK’s key role in using its influence to affect significant progress on raising project quality, strengthening results orientation, a proactive private sector and strengthening capacity.
[1] The Independent Evaluation Unit (IEU) ensures GCF is accountable and is open to continuous learning. It conducts independent evaluations of GCF's activities to guarantee its accountability and synthesises learnings from high quality and rigorous evaluations to support GCF's effectiveness and efficiency. The Independent Integrity Unit (IIU) ensures all GCF staff, in addition to external stakeholders, implementing entities and intermediaries relating to GCF adhere to the highest standards of integrity. The IIU investigates allegations of fraud, corruption, misconduct and other prohibited practices. The Independent Redress Mechanism (IRM) responds to complaints by people who feel they have been adversely affected by GCF projects or programmes failing to implement GCF operational policies and procedures. This includes allegations of a failure to follow adequate environmental and social safeguards.

Despite this progress, 2018 was not without setbacks and there remain areas where improvements are needed. In particular, stalemate at the Board meeting in July 2018 slowed progress on a number of important matters, illustrating the need for a voting procedure to allow progress to be made where consensus can not be reached. Lessons becoming evident as the fund matures indicate the need and the opportunity to refine policies and procedures to enhance the quality and value of GCF programming, including in relation to more strategic programming, benchmarking projects against best practice, and the financial terms of GCF support. Now that key legal agreements have been finalised with project partners, notably the multilateral development banks (MDBs), there needs to be a strong focus on project implementation, so that the expected benefits from approved programming can be realised. iImprovements on how results are managed and monitored are also needed, so that it is clear what impact GCF investments are having, and to promote learning and results-based management.

Recommendations for the year ahead (1/2 page)

Seek to increase the effectiveness of GCF programming, including by increasing the use of strategic programmatic approaches.

Promote improved functioning of the Board, including by adopting a procedure for the Board to take decisions when consensus cannot be reached

Push for improvements to Fund standards and transparency, including on safeguarding.

Push for increased value for money from GCF’s investments, including through targeting of GCF grants and concessional resources to increase the Fund’s impact (in accordance with project type and country needs and capabilities), and increased leverage of other climate finance investments, notably from MDBs and the private sector through the Fund’s Private Sector Facility.

With the growth in GCF secretariat’s capacity, and progress in finalising legal agreements with project partners, push for an acceleration in project implementation.

In line with GCF’s objective to be a continuously learning institution, continue supporting GCF’s Independent Evaluation Unit (IEU), including through adequate resourcing to deliver its ambitious 2019 workplan and by promoting adoption of the Evaluation Policy by the GCF Board.

Promote an enhanced approach to results collection and management, in line with findings from the UK visit to the GCF Secretariat and IEU in September 2018. Push for improvements to GCF’s Results Management Framework (RMF), in line with recommendations from the IEU’s recent evaluation of the RMF.

Explore opportunities to promote high quality investments of GCF funds in poorer countries by direct access entities.

Progress towards these objectives will support the UK’s objectives to improve the effectiveness and efficiency of the GCF through the GCF’s first replenishment process, which may be summarised as to:

Increase:

Value for Money relative to the GCF’s Initial Resource Mobilisation, through setting more demanding results targets in all areas;

Effectiveness of Programming in achieving transformational change, by increasing the use of strategic programmatic approaches; and

Leverage of multilateral development banks, the private sector (through the GCF’s private sector facility) and other forms of co-financing.

Improve the:

Functioning of the Board and Fund, including through the adoption of a voting procedure and other improvements to standards and transparency, including on safeguarding; and

Targeting of GCF grants and concessional resources to increase the Fund’s impact by provision of support in accordance with country needs and capabilities.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)
Output Title	GCF makes successful transition from design phase to full functioning, demonstrated through continuing progress on key operational aspects
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1. Cumulative number of implementing entities accredited, providing sufficient geographical coverage, scale, and access to private sector finance	65	As of Jan 2019, 75 implementing entities have been accredited, substantially exceeding expectations. This includes 26 international organisations, 37 national/regional organisations, and 12 private sector entities. / 14 Accreditation Master Agreements (AMAs – the legal framework agreement between GCF and implementing partners) were signed during 2018, taking the total now signed to 55 (out of a total of 75 organisations approved for accreditation by the GCF Board). AMAs have now been signed with all major Multilateral Development Bank (MDB) partners, meaning project implementation can begin on projects being undertaken by those key partners. / A review of GCF’s accreditation framework was carried out in 2018 by an independent consulting firm (Moore Stephens). This review is due to be considered by Board in 2019 and will be an opportunity to focus on making sure the right organisations are accredited to GCF to help deliver its mandate. This would support the decision taken by the Board also in 2018 to bring forward entities for accreditation that fill the GCF’s mandate on balance, diversity, coverage and ability to advance the Fund’s objectives.
1.2. Cumulative volume of pipeline of proposals (including concept notes), allowing funding at sufficient scale	Pipeline volume >$10bn	As of Jan 2019, the pipeline is c.$15bn (comprising around 80 full project proposals for a total of $4bn, and over 100 concept notes for a total of $10.7bn), substantially exceeding expectations against this milestone. The pipeline continues to grow rapidly as demand for GCF finance exceeds supply. The GCF has now reached the point where demand will always exceed available resources, implying the need and opportunity to improve resource targeting for better impact.
1.3. Cumulative volume of quality proposals approved to achieve replenishment target	$6bn	As of Jan 2019, $4.6bn of projects have been approved, up from $2.6bn a year ago. This did not meet the $6m milestone but did meet the replenishment target (owing to the US not meeting its pledge) and therefore triggered GCF’s first formal replenishment.
1.4 Current permanent staff numbers within the GCF secretariat, to deliver transition out of design phase and progress each key operation aspect.	250	As of Jan 2019, 219 staff are in post, up from 161 a year ago. This did not meet expectations, but is a significant rise over the year and we assess the secretariat’s capacity has grown in quality as well as quantity as the organisation matures. The target of 250 staff by the end of 2018 was ambitious and we would expect staff numbers to stabilise at around that number in the next year or so, in line with GCF’s growing portfolio of investments and other operations.
1.5 GCF adherence to UK and international best practice for transparency in aid delivery, including membership of the International Aid Transparency Initiative (IATI)	Formal decision to join IATI taken by the Board	Not met. We have held further discussions with GCF Secretariat on IATI, but given other competing priorities this has not yet been discussed by the GCF Board. However, GCF continues to display good standards of transparency (e.g. live webcasting Board meetings; publishing Board papers ahead of meetings). Also, of the $4.6bn approved for GCF projects to date, over 75% is being channelled through implementing partners that are members of IATI and publish to IATI standards (MDBs and UNDP).

Provide supporting narrative for the score

GCF approved over $2bn of projects in 2018, a greater volume than in any previous year. The project pipeline also continued to grow significantly and at around $15bn, marks the point at which demand for GCF resources will likely always exceed available funds. During 2018 the cumulative volume of projects approved reached the 60% target (of overall funds mobilised for 2015-18), thereby triggering GCF’s first formal replenishment process[2]. This process will run throughout 2019, with a pledging conference scheduled for October. There is a good geographic balance in the GCF portfolio, with projects now covering 34 African countries, 30 countries in Asia-Pacific region, 27 countries in Latin America and the Caribbean, and 5 countries in Eastern Europe.
[2] Decision GCF/B.21/30/Rev.01 outlines how the board came to the decision to trigger replenishment taking into account a number of factors including total contributions, B.21 funding proposals and U.S. ceased funding.

The number of accredited implementing entities also continues to grow, further expanding the reach of the GCF and the coverage and choice of implementing partners available to countries in need. The GCF Board agreed in 2018 that organisations should be brought forward for accreditation that fill the GCF’s mandate on balance, diversity, coverage and ability to advance the Fund’s objectives. This was in line with our recommendation from last year’s AR to prioritise entities that address gaps in coverage and add value to the Fund in meeting its objectives. There will be a further opportunity to strengthen the accreditation framework in 2019, when the review of the accreditation framework will be discussed by the Board. A further significant milestone reached since the last AR is the completion of Accreditation Master Agreements (AMAs) notably with MDB partners, following long negotiations over legal arrangements (especially with the World Bank). Having AMAs agreed with these key implementing partners means implementation can progress on their projects that have been approved by the GCF Board (NB. some 67% of GCF projects approved are to be implemented through MDBs). These milestones largely conclude the major institutional limitations to project implementation, which allow for faster rates of implementation from now on. By value $2bn of the $4.6bn of projects approved overall are now under implementation, with $442m of funds disbursed.

While our logframe target for GCF staff numbers was not met, the secretariat grew in size by over a third in 2018, to 219 staff. This represents a significant rate of growth, commensurate with the growth in GCF’s portfiolio and operations. The target on transparency (IATI) was also not met, although with hindsight the milestone of IATI membership by Jan 2019 was unrealistic given the number of competing priorities for the Board’s attention in 2018, and the fact that GCF has already adopted an Information Disclosure Policy requiring high levels of transparency. We also note that the majority of GCF funds approved (over 75%) are being channelled through organisations publishing to IATI (in particular UNDP and the MDBs). On safeguards, progress was made in a number of areas in 2018 – including the adoption of a whistleblowers policy – but there are still policies under development which must be a priority for 2019, including on Sexual Exploitation Abuse and Harassment.

While not all milestones under this output were met in 2018, we judge that the overall growth in GCF’s portfolio and pipeline, coupled with continued growth in the number of accredited implementing partners, legal agreements signed, and sufficient resources now committed to trigger GCF’s replenishment, supports an ‘A’ for this output.

Lessons identified this year, and recommendations for the year ahead linked to this output

Sufficient secretariat capability, effective functioning of the Board, and a pipeline and portfolio of quality projects are all necessary for GCF to fulfil its role. To this end, recommendations for 2019 are:

Seek to increase the effectiveness of GCF programming, including by increasing the use of strategic programmatic approaches.
  - This is one of our key objectives for the replenishment. The Board is also due to consider its approach to programmatic approaches as part of the review of the initial Investment Framework in 2019, an agenda item that the UK has pushed to have included.

- Promote improved functioning of the Board, including by adopting a procedure for the Board to take decisions when consensus cannot be reached.
  - Decision-making in the absence of consensus is another of the UK’s replenishment objectives, and, in our role as Co-Chair of the Board in 2019, we have also ensured that this is on the Board agenda for 2019.

- Push for improvements to Fund standards and transparency, including on safeguarding (notably adoption of a Fund policy on Sexual Exploitation Abuse and Harassment that applies to GCF counter-parties).
  - Improvements to standards and transparency are included in the UK’s replenishment objective and, in our role as Co-Chair of the Board in 2019, we have ensured this is on the Board agenda for 2019.

- Push for increased value for money from GCF’s investments, including through targeting of GCF grants and concessional resources to increase the Fund’s impact (in accordance with project type and country needs and capabilities).
  - Further guidance on concessionality for GCF projects will be considered by the Board in 2019, as part of the review of the initial Investment Framework. This is another agenda item that the UK has pushed to have considered this year.

As part of the Board’s review of GCF’s Accreditation Framework, press for a streamlined approach to accreditation that attracts the right organisations to deliver GCF’s mandate, including private sector institutions, while maintaining the Fund’s robust fiduciary, environmental and social standards.

Push for an acceleration in project implementation.

Output Title	GCF makes progress on key priority areas including private sector finance, a balanced approach to mitigation and adaptation, and facilitation of a country-driven approach
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1. Of total value of projects approved, % of funding through the Private Sector Facility	>35%	9 private sector projects were approved in 2018, taking the total value of projects approved through the Private Sector Facility to 40%, substantially exceeding expectations.
2.2. Of total value of projects approved, % of funding for adaptation activities	>45%	In ‘grant equivalence’ terms, 56% of the overall value of projects approved is for adaptation activities, exceeding expectations (NB. in assessing performance against GCF’s aim to allocate 50% of funding to adaptation, the GCF Board agreed grant equivalence terms should be used).
2.3. Cumulative number of direct access programmes approved (more pilot enhanced direct access programmes are expected to be approved over time)	25	9 ‘direct access’ projects were approved in 2018, taking the total to 22 overall to date (including two ‘enhanced direct access’ projects), moderately not meeting expectations.

Briefly describe the output and provide supporting narrative for the score

As in the last Annual Review, progress with engaging the private sector continued to exceed expectations in 2018, whereas the number of ‘direct access’ projects was marginally off-track. Taken together with the result for the indicator on adaptation support, this leads us to judge that progress against this output has met expectations, supporting the score of ‘A’.

GCF continued to engage successfully with the private sector in 2018, approving a further 9 private sector projects and channelling an overall total of 40% of the Fund’s investment this year through private sector channels. The private sector projects approved in 2018 included the first private sector adaption project (Acumen Agriculture Resilient Adaptation Fund – ARAF).

The UK’s ongoing close engagement with the GCF’s external Private Sector Advisory Group (PSAG) and Private Sector Facility (PSF) within the secretariat continues to bear fruit. We have continued to work with the PSF and Accredited Entities to support higher quality private sector proposals being submitted to the Board, and the recent ICAI report indicates there is evidence that the UK has pursued an active influencing agenda in advocating for and developing the PSF. The UK has also encouraged more direct engagement between the PSAG and the Board, supporting a more strategic approach to private sector engagement.

The PSF held the first GCF Private Investment for Climate Conference in October 2018, alongside the Global National Designated Authority (NDA) Conference (NDAs are countries’ points of contact for engagement with GCF). This was a direct response to PSAG recommendations on a private sector outreach plan in early 2018, and helped promote private sector engagement with GCF and understanding in developing countries of how the private sector can help achieve their national climate goals. The conference itself was very well attended and is anticipated to become an annual event. PSAG recommendations on outreach and engagement with LDCs and SIDS have also been included on the Board’s workplan for 2019 and in the strategic documents that will inform GCF’s replenishment and support improving efficiency and effectiveness of the GCF.

GCF is making good progress against its aim of allocating half of its funding to adaptation / resilience activities. As per the GCF Board decision on this measure, progress is measured in ‘grant equivalence’ terms, with 56% currently committed to adaptation activities (NB. this is significantly above the global average of climate finance flowing to adaptation of around 23%[3]). However, as GCF’s pipeline contains more requests for mitigation funds than adaptation, this will continue to require active management to keep on track to meet the 50% adaptation target.
[3] OECD (2018) - Climate finance from developed to developing countries Public flows in 2013-17

Lessons identified this year, and recommendations for the year ahead linked to this output

Although UK is not formally a member of PSAG, our advisory input and engagement has helped to improve the strategic direction of, as well as strengthen links between PSAG and both the Board and the Secretariat. We should continue to engage with PSAG and seek to maintain improved uptake by GCF Board of PSAG recommendations.

Challenges to private sector engagement in adaptation activities remain, but following the approval of GCF’s first private sector adaptation project in 2018 we should continue to explore opportunities for - and push for - greater private sector engagement in adaptation.
  - The Board is due to consider modalities to support the private sector to engage in adaptation activities as part of the review of the initial modalities of the Private Sector Facility in 2019.

We should support a strategic approach by the PSF, likely to include improved access for the private sector to GCF, and promote a greater range of financial instruments and flexibility in potential investments. This will be important in achieving greater impact with the private sector, both through private finance flows and working with businesses in developing countries to achieve higher leverage and greater scale-up, thereby supporting the paradigm shift objective of the GCF.
  - The Board is due to consider a private sector strategy in 2019, as part of the review of the initial modalities of the Private Sector Facility.

- As part of discussions on GCF’s Strategic Plan (due to be updated in 2019) and any review of the Fund’s allocation parameters, we should seek to maintain 50% of GCF’s resources being channelled to adaptation activities. We should also push for identification of areas where GCF’s adaptation activities can have highest impact.
  - The Board is due to consider guidance for providing support to adaptation activities as part of its review of the initial Investment Framework in 2019.

Progress on ‘direct access’ remains slow, despite GCF’s introduction of measures to support it (for example through the Simplified Approvals Process – SAP). We should continue to explore opportunities to promote high quality investments of GCF funds in poorer countries by direct access entities.
  - The Board is due to review the SAP in 2019 and this will provide learnings and an opportunity to consider whether and how its operations can be further simplified.

Output Title	GCF demonstrates an innovative approach to providing climate finance through focus on learning, building national capacity and capability, and gender sensitive programming
Output number per LF	3	Output Score	A
Impact weighting (%):	30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1. A programme of work to enable evaluation and to facilitate learning that informs proposal and decisions made by the GCF	Completion of the first independent evaluation by IEU (e.g. Readiness evaluation); publication of independent evaluation policy; unit is fully staffed	Moderately did not meet expectations / The Independent Evaluation Unite (IEU) completed two independent evaluations in 2018: a review of the GCF’s Results Management Framework; and an evaluation of the Readiness and Preparatory Support Programme. It also started a Learning-Oriented Real-Time Impact Assessment (LORTA). / The IEU has developed an evaluation policy to be considered by the Board in 2019. / At the end of 2018 the IEU had 6 permanent members of staff, having recruited five new staff members over the year, and was supported by long- and short-term consultants based in Songdo. The IEU recruited a Communications and Uptake Associate in January 2019 and will soon add two researchers (data and qualitative), one GIS analyst and an Evaluation Specialist. The ambitious workplan of the Unit requires further staff resources and aims to be fully staffed with 12 staff by the end of 2019. This will include the Unit Head, 8 international staff members, 2 researchers and 1 administrative team assistant. / The IEU will conduct 4 evaluations in 2019: a Forward-looking Performance Review of the GCF; an assessment of the GCF’s success in ensuring country ownership; an assessment of the GCF’s environmental and social safeguards; and will complete the LORTA.
3.2. Cumulative number of countries benefiting from GCF readiness funding and/or preparatory support, including LDCs, SIDS and Africa	50, 25 of which are LDCs, SIDS, Africa	Substantially exceeded expectations / 122 countries total, of which 80 LDCs, SIDS, and Africa / If factoring in Project Preparation Funding (PPF) this number rises to 124. Fiji and Solomon Islands have received PPF only, not readiness grants. / For National Adaptation Plans (NAPs): 23 countries total, of which 14 are for LDCs, SIDS and African countries. The official approved amount for NAPs is USD 62.3m. / For Project Preparation Facility: 19 countries total, of which 13 are for LDCS, SIDS and African countries. The total amount for PPF is USD 10.8m, of which USD 7.2m is for LDCs, SIDs, and Africa. / As of December 2018, of the 204 Readiness requests that have been approved, 178 have been disbursed and are under implementation and managed by PMU. The IEU has completed an independent evaluation of the Readiness Programme, which credited the good work the programme had completed to date, but provided recommendations for a more targeted approach. The Secretariat broadly agreed with the recommendations in the evaluation, and developed a strategy for 2019-2021, and a workplan for 2019, both of which were approved by the Board at its 22nd meeting.
3.3. % of projects/programmes that have collected gender-disaggregated (or other social inclusion) baseline data against one or more indicators	80%	Substantially exceeded expectations / 94% of the 93 approved projects/programmes have gender assessments. 86% contain project level gender action plans, and 49% of approved projects have baseline data collected for targets in the gender action plan or logframe.

Provide supporting narrative for the score

Overall progress has continued to be strong, with indicators 3.2 and 3.3 exceeding expectations, while 3.1 was narrowly missed in respect of the IEU’s staff strength, despite meeting evaluation report issuance expectations. Taken together, we assess that this output has met expectations.

The delays in 2017 to the approval of the IEU’s 2018 workplan and budget have resulted in delays to the IEU’s planned workplan, and despite the Evaluation Policy having been written and introductory webinars with stakeholders taken place, it will not be considered by the Board until B23. Despite this, the IEU has prioritised the delivery of key and timely evaluations, two of which have been finalised and published. This also includes the forward-looking performance review of the Fund, which will be an integral evidence-based resource to inform replenishment.

The IEU increased its staff in 2018 to equip itself for the ambitious workplan, however this was also affected by the delayed approval of the budget. The Unit was also supported by short-term consultants on its evaluations in 2018 to mitigate the effect of these delays, and will have increased the staff numbers to 12 by the end of 2019. Plans for the overall staffing will be presented to the Board in 2020, at which time the IEU will have been operational for three years. This will also mark the end of its first three-year work plan.

Lessons identified this year, and recommendations for the year ahead linked to this output

Delays to the approval of the IEU’s workplan and budget have had a knock-on effect to it’s productivity in 2018. A budget for the IEU has now been approved and we will need to continue supporting the IEU to ensure that the Evaluation Policy is adopted in 2019, a priority for the UK, and that it has the resources to deliver it’s ambitious 2019 workplan.

Following the visit of ICF analysts to the Office of Portfolio Management of the Secretariat and the IEU in September 2018, a number of areas for improvement, particularly in the results collection and management process were identified. These improvements are reflected in the IEU’s evaluation of the Results Management Framework, and progress on the Fund’s approach to results collection will be a key deliverable for the UK in 2019. An updated Results Management Framework is due to be presented to the Board in October 2019.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The theory of change (ToC) diagram below sets out how the GCF is expected to lead to a transformational shift towards low carbon, climate resilient development.

There have been no changes to the ToC in the past year, and the steps to achieving the outcomes are still considered to be relevant.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Improving the rate of moving projects and programmes from approval to implementation continues to be a priority for the GCF. This is to be expected of a new institution, where new legal and other operational agreements are required with implementing agencies. However, as these largely one-off agreements are concluded we expect disbursement rates to continue to improve and have joined other Board members in making this clear to the GCF Secretariat and agencies. Despite these delays the Fund has demonstrated an improved capacity for moving to implementation in 2018. At the end of 2016 one project had started implementation, as of the end of 2018 this had increased to 40 (41 countries), accounting for 43% of the 93 approved projects. These projects under implementation are worth USD 1.8 billion in GCF funding and account for 39 per cent of total GCF approved funding.

We expect to see progress continue in 2019, with the GCF having finalised its first Funded Activity Agreement (FAA) with the World Bank, which soon should allow the implementation of all nine WB projects (10 countries) for a total of USD 577m.

The GCF will use its updated Results Management Framework from late 2019, once it is approved by the Board (it is scheduled for B.24 in October). The update will take into account the Independent Evaluation Units report and associated management response approved at B.22. The UK team will press to see that the recommendations of the IEU’s evaluation are implemented, whilst continuing to push for improvements in its enhanced approach to results collection and management. Alongside the evaluations completed by the IEU in 2018, and the unit’s workplan in 2019, these developments will improve the evidence base, enabling the fund to better understand what works and why in climate change programming.

Describe any planned changes to the logframe as a result of this review (1/2 page)

The UK is planning to revisit the theory of change as part of the business case, which will be finalised in 2019, for its second pledge to the GCF, and will subsequently revise the logframe accordingly.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The GCF performed well on both the efficiency and economy criteria and particularly strongly on the effectiveness criteria. This was due to the Fund being designed to promote climate resilient, low carbon development by concentrating donor finance into one body, to achieve results at scale. The potential of the Fund to offer a range of instruments and terms to recipient countries and its ‘direct access’ modality were also assessed as strong indicators of potential effectiveness.
## Value for money is achieved by optimising the effect of each pound spent and is analysed through assessment of the ‘three E’s’: economy, efficiency, and effectiveness.

Effectiveness
Approved projects give an indication of the GCF’s potential to achieve results and good value for money, in particular the ability of the GCF to lever the resources of others and incentivise private sector investments at scale. The 93 proposals approved so far, for a total GCF funding of USD 4.6 billion, have enabled co-financing of USD 11.7 billion from other contributors, both public and private. The programme is still considered to represent value for money as set out in the Business Case.
We will be able to provide further assessments of the efficiency and effectiveness of the GCF based on the expected results of further new proposals and, subsequently, based on actual results as more projects progress to implementation.
The UK is a strong proponent of achieving good value for money in the GCF. At the Board we seek to maximise value for money through our positions on a range of issues relating to economy, efficiency and effectiveness. For example, on funding proposals we pay particular attention to the terms of the financial support requested, to see that this is appropriate to the country context and to the specific activity, following the principle of using the minimum level of concessionality required.

Efficiency
The GCF has had an upward trend in funding approvals in 2018. 19 proposals were approved in 2017 across two Board meetings, in 2018 this increased to 42 also across two Board meetings. Whilst we anticipate a slower rate in 2019 due to the GCF managing its remaining resources from the IRM prior to replenishment, this represents increased capacity and efficiency of the Fund to prepare, present and and approve funding proposals.

A key area of improvement for the GCF is increasing the efficiency of fund disbursement for approved projects. At the end of 2016 one project had started implementation, as of the end of 2018 this had increased to 40 (41 countries), accounting for 43% of the 93 approved projects. These projects under implementation are worth USD 1.8 billion in GCF funding and account for 39 per cent of total GCF funding. Conclusion of the legal and operational arrangements with the Fund’s agencies will speed up implementation. The UK will continue identify and seek to resolve any constraints that delay moving from approval to implementation in 2019.

Other GCF processes that have improved their efficiency in 2018 include: The Readiness and Preparatory Support Programme (RPSP), which Independent Evaluation Unit review showed has reduced its average processing times of readiness grants (from approval to effectiveness[4]) from 293 days in 2015 to 10 days in 2017, and from effectiveness to first disbursement by more than 50%[5].
[4] Includes the time taken between frome the proposal being approved to letter of authorization and takes in legal agreement being finalized, legal arrangements being concluded in the form of a grant agreement and the grants becoming effective.
[5] The time, in days, from the date the grant is considered effective to the date it is disbursed. The first tranche of funding is released upon the grant becoming effective, the last preceding the closure of the grant itself. This temporal step will include both disbursement dates when applicable

Economy
In 2018 the Secretariat had an approved total budget of USD 69m. This included an administrative budget of USD 63.6m, and approved budgets for each of the three independent units of approximately USD 5.5m in total. This included costs for Board meetings, the Interim Trustee and all Secretariat costs.
In 2018, the total expenditures on the Board, independent units and the Secretariat as well as estimated costs for the services of the Trustee amounted to USD 61.8 million – approximately 3% of overall approvals in the period. The Board had an underspend of 23%, the independent units 15%, and the Secretariat 10%.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

We anticipate the key costs for the GCF to continue to be:
- staff costs for the GCF Secretariat
- the costs of Board meetings, including support to developing country Board members as per the UNFCCC
- the cost of Trustee services, provided by the World Bank
- costs in relation to project implementation (fees); and
- costs for the three independent accountability units.
The Appraisal Case of the Business Case assessed that of the three options presented (bilateral funding, medium to long term funding to the Climate Investment Funds (CIFs), and funding through multilateral climate funds), support to the GCF was the best option overall given its potential to perform well and its stated objectives and action to date to learn from existing funds, even taking into account the inherent risks and uncertainty of setting up a new fund.
As stated above we assess VfM against economy, efficiency and effectiveness. The GCF performs favourably against all three of these, and we remain confident that the GCF continues to represent value for money as outlined in the business case.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

We judge the overall risk of the GCF to be Major. Some of the risks from the last annual review have now been resolved and, therefore, removed for the risk register. Notably, compared to last year, the GCF secretariat has become significantly better resourced (removing risk 2 from last year’s annual review). However, delivery and reputational risks related to the efficiency of the board (risks 1 and 3) remain significant. In addition, while GCF has built up a much larger pipeline (removing risk 3 from last year’s annual review) the quality of that pipeline remains uncertain so has been introduced as a risk for this year (risk 2 below).

The Board has agreed the Co-Chairs proposal to consider with a view to approving policies on decision-making in the absence of consensus and strategic programming which may reduce some of these risks during 2019. HMG staff and the GCF programme team will continue to monitor these changes and will review the risk register on a regular basis.

Risk Description	Mitigation Strategy	Comments
Risk 1: The GCF Board does not become sufficiently more efficient in decision-making, leading to delays in finalisation of operational elements, approval of proposals and/or disbursement of GCF funds	(Treat) Press through UK Co-Chair role to see that decision making in the absence of consensus (voting) remains on the Board agenda during 2019 until it is resolved. / Nominate and coordinate a dedicated negotiation team, comprising developed and developing country representatives, to work on options to improve decision making, between and during Board meetings. / Use diplomatic channels (FCO) to make the case for change in key developing countries; and lobby for change through the UNFCCC negotiations (BEIS).	We judge this risk to be major. Board operations were improving over last two year, but gaps remain and the failure of Board decision making at B.20 (July 2018) meant we could not reduce this risk during 2018. We continue to apply mitigation actions as set out in the business case and subsequent ARs, with the addition of our cross-Whitehall influencing strategy as agreed by Directors in June 2018. Positive outcomes from most recent Board meeting (B.21, Oct 2018), including approval of over $1bn of projects and agreement to launch GCF replenishment, indicate mitigating actions are bearing fruit.
Risk 2: Accredited Entities, in particular national entities from developing countries, are unable to develop a pipeline of sufficient quality programmes that can be financed through the GCF	(Treat) Press through UK Co-Chair role to propose a schedule of policy/ procedural proposals for the Board during 2019 to improve national entity performance. / UK proactively engages in Board discussions on accreditation and pipeline development /management and in strengthening policies/guidelines to promote project quality/VFM.	We assess this risk to be major. The GCF pipeline continues to grow as AEs submit more projects (over $15bn now in pipeline when concept notes included). Delays in programming and concerns over quality are mainly due to outstanding operational and policy issues, which require Board decisions for progress to be made. The focus of our mitigating actions has therefore shifted to the Board, as set out above. Whilst pipeline volume risk has receded (demand for GCF funding now well outstrips supply), there is still a risk in respect of quality of projects, which we are tackling through proposals to tighten relevant policies (e.g. concessionality guidelines) and improve GCF’s overall efficiency.
Risk 3: Reputational risk to the UK from adverse publicity that occurs as a result of failure of the GCF Board to function effectively or to make progress, especially in the context of the upcoming replenishment.	(treat) Press through UK Co-Chair role to propose an agenda for the whole of 2019, to be dealt with in sequence through the Board meetings; and in tandem through the replenishment process. / Nominate and coordinate dedicated negotiation teams, comprising developed and developing country representatives, to work on options to improve policies and procedures. / Work with Press Office to ensure UK has robust lines ahead of Board Meetings to explain controversial or unproductive outcomes and measures for improvement.	We judge this risk to be major. We have estimated that our mitigation steps can reduce the likelihood of this risk down from likely to possible. The impact level also depends on the context: individual failures are of lower risk than repeated failures which would have a compounding effect.
Risk 4: Private Sector Facility (PSF) does not sufficiently attract private sector finance and agencies across mitigation and adaptation work.	(Treat) UK team to continue to engage with Accredited Entities and DFID country offices/ FCO to maintain engagement of other HMG departments and raise awareness of GCF as a financing mechanism. / UK team to push GCF Board on programming and accreditation progress.	We assess this risk to be moderate. Evidence from the funding proposals to date, accreditation applications, and the developing pipeline indicates that interest in the GCF amongst private sector entities is high and resilient. However residual risk remains in terms of quality. Long timelines and high transaction costs for accreditation could lower the quality of proposals from private sector entities. The recent Request for Proposals was successful in terms of response but approval of project proposals has been slower than expected
Risk 5: Reputational risk to the UK from adverse publicity that occurs as a result of potential fraud and corruption, and failure of the GCF Secretariat to exercise effectively its fiduciary duty related to the operations of the Fund.	Treat. Ensure the accreditation process identifies risks of fraud and corruption associated with Accredited Entities (AEs); establish internal controls and regular assessment of compliance with fiduciary standards; ensure robust risk management framework is in effect; ensure the Secretariat carry out ad-hoc checks, as well as annual reviews on the GCF’s portfolio of projects	We assess this risk to be moderate.
Risk 6: Risk arising from potential fraud and corruption, or failure of the GCF Secretariat to exercise effectively its fiduciary duty related to the operations of the Fund	(treat) Assess the risk further as part of planned Central Assurance Assessment of the GCF. Ensure the accreditation process identifies risks of fraud and corruption associated with Accredited Entities (AEs), and that they establish internal controls and regular assessment of compliance with fiduciary standards; ensure robust risk management framework is in effect; ensure the Secretariat carry out ad-hoc checks. Press for adoption of full suite of updated integrity policies, including whistleblower protection	We assess this risk to be moderate. The UK has invested a sizeable sum in the GCF – a high profile and relatively new institution. While the GCF has policies and controls in effect to mitigate this risk, their operational performance has yet to be tested. We should remain vigilant in tracking performance as these systems are tested and bed down.
Risk 7: UK taking on co-chairing role of GCF has reputational and implementation risks. Reputational, in that the UK could become associated with poor Board performance and/or replenishment outcome; operational in that the UK could find it harder to achieve its reform agenda, both due to resource constraints (from managing additional responsibilities) and as our national influence in the negotiation process may be constrained by the need to maintain the conciliatory stance expected of Board chairs.	(Treat) Press through UK Co-Chair role to propose Board and replenishment objectives for the developed country group during 2019. / Clearly distinguish UK Co-Chairing and national positions and representation Clear comms lines about our role as co-chair - to a range of audiences (other board members, external press). Make sure team is adequately resourced.	We assess this risk to be moderate. Most mitigation measures are already in effect.
Risk 8: The GCF lacks credibility with external stakeholders, in particular developing countries.	(Treat) UK team to continue to engage with Accredited Entities and DFID country offices/ FCO to maintain engagement of other HMG departments and raise awareness of GCF as a financing mechanism. / UK team to push GCF Board on programming and accreditation progress.	This risk remains minor. Demand from developing countries for access to the GCF remains high. However, it is vital that programming and accreditation continue to progress in order to build the credibility of the GCF with all stakeholders, including in support of a successful replenishment process.
Risk 9: The UK and other donors lacking sufficient evidence of impact and lesson learning, owing to an inadequate and/or poorly implemented results management framework it not having a credible and adequate process	(treat) Press through UK Co-Chair role to propose improvements to the RMF and its application in 2019. / UK press for sufficient monitoring arrangements and budget for the IEU to promote continuous evaluation and learning.	We assess this risk to be moderate. / Achieving, recording and learning from results is essential to demonstrating that the GCF has positive impact and gives good value for money – particularly during a replenishment year.

Outstanding actions from risk assessment

A review of the due diligence assessment remains an outstanding action from the last Annual Review. Taking account of the fact HMG’s sizeable core contribution to the GCF and the forthcoming replenishment of the fund, it has been decided that due diligence will be conducted through a Central Assurance Assessment. This is scheduled to take place over the summer of 2019.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The GCF Board approved the Fund’s first eight projects at the 11th Board meeting (B.11) in November 2015, shortly before the UN Framework Convention on Climate Change (UNFCCC) negotiations took place in Paris (COP21). This was in line with our expectations in terms of timing, although the number and the value of the proposals were lower than anticipated. Despite the failed B.20 meeting in July 2018 where no projects were approved, by the end of 2018, a total of 93 projects had been approved, for a total of US$4.6bn of GCF funding, demonstrating further evidence of GCF’s ability to programme at scale. As expected in the last annual review, the replenishment process was triggered at the B.21 meeting in October 2018 and is expected to conclude at a pledging meeting in October 2019.
Our Promissory Note (PN) payments and encashments are managed against the Fund’s ‘commitment authority’ (i.e. funds available against which to approve projects), liquidity position and anticipated disbursements. Due to this increase in programming and a strong pipeline, DFID and BEIS were able to deposit the last PN of our £720M commitment authority the UK in November 2018, as scheduled in the last Annual Review.

Narrative reporting and audited financial statements

Within the GCF Secretariat an Office of the Internal Auditor (OIA) has been established, and during 2017 developed a three-year risk-based internal audit plan for 2017-19. The audited accounts for 2017 were approved at the second meeting of 2018 (B20). The external auditors, Grant Thornton, were of the opinion that the financial statements present fairly, in all material respects, and that the financial position of the Fund as of 31 December 2017 and of its financial performance and its cash flows for the year ended in accordance with International Financial Reporting Standards.

Risks and delivery chain maps;

The GCF has a strong framework for financial management, including the fiduciary standards adopted for Accredited Entities; the Financial Risk Management Framework; internal controls including an internal audit department; and the World Bank operating as the Trustee.
At B22 in 2019, the GCF adopted a Policy on Prohibited Practices to replace their interim policies. These are in line with international best practice. GCF’s policy on anti-money laundering and countering the financing of terrorism was adopted at B.18 (Oct 2017). At B22 in 2019, the GCF board adopted an interim policy on protection from sexual exploitation, sexual abuse and sexual harassment along with guidelines and procedures for the Independent Redress Mechanism which strengthen GCF’s existing safeguards and standards.

The GCF Secretariat publishes risk and portfolio dashboards which highlight the key risks and delivery chains for the programme.

The GCF agreed a revised policy on fees for grants for public sector projects/programmes (fees paid to the accredited entities and delivery partners of the GCF to cover their costs for implementing projects) at the first meeting of 2018 (B19). The policy on fees will only apply to the projects/programmes, PPFs and the Readiness Programme, including NAPs or other adaptation planning processes, approved by GCF after B19, and were adopted as the following:

Size	Fee cap % of GCF funding (on grant)
Micro (< USD 10 million)	Up to 8.5%
Small (USD 10 – 50 million)	Up to 7%
Medium (USD 50 – 250 million)	Up to 5%
Large (> USD 250 million)	Up to 4%

An outstanding issue was concluded at the third meeting of 2018 (B21) with the appointment of the World Bank as the Trustee, which was a priority for the UK in 2018. The Trustee plays an important role for the GCF; receiving financial contributions, holding and investing them, and transferring them upon the instruction of the GCF.

Asset monitoring and control

GCF’s cash and promissory notes are held/managed by the World Bank, GCF’s Trustee. The internal controls and audit of the World Bank are applied to the GCF trust fund resources.

The internal auditors monitor compliance of GCF’s operations with the Fund’s policies and decisions, and safeguarding of Fund assets, as well as investigating the effectiveness of resource use and performance against Fund priorities. Work carried out in 2018 included finalising two audits (Private Sector Facility Division and Correspondence Management) and worked towards finalizing three audits (Finance, ICT and Procurement Units). It conducted one more audit (Relationship Management) from the 2018 audit plan during the reporting period. Furthermore, OIA conducted 8 ad-hoc reviews, 3 of which have been finalized. OIA (Office of the Internal Auditor) is also currently finalizing its audit manual.

OIA, together with Office of Risk Management and Compliance and human resources, arranged for a second training course on the Committee of Sponsoring Organizations (COSO) framework for internal control. (The first COSO training was held in 2017.) A trainer from the Institute of Internal Auditors delivered a three-day training course to 20 staff within the Secretariat and a presentation to the SMT. The Secretariat is currently exploring options to provide the COSO training to more staff members of the Secretariat as well as Board members.

Quality of Financial management in the programme

The GCF Secretariat’s work programme and administrative budget for 2018 was approved at B.18 in October 2018 and the Secretariat’s report to the board on its execution at B.22 in February 2019. This report notes an under-spend of USD 7.2 million comprising USD 0.8 million for the Board; USD 0.8 million for the independent accountability units; and USD 5.6 million for the Secretariat.

To provide guidance on the different accounting procedures, standard operating procedures were developed for 11 processes. Accounting staff were trained in the procedures, which are accessible to all staff for reference. Staff roles and responsibilities in the accounting department were also reorganized to align with the approved procedures. Development of standard operating procedures for three more processes is at the 2nd level review stage and will be presented for OIA and senior management team review in the first half of 2019.

Date of last narrative financial report(s)	Feb 2019
Date of last audited annual statement (s)	May 2018 (for calendar year ending 31 December 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

We monitor progress on all aspects of GCF operations through constant engagement with the Co-Chairs, other Board members, the Secretariat, Accredited Entities, and with developing countries through our country office network. 40 of the approved projects have now begun disbursing funds, and will be monitored from implementation, with the first batch of monitoring data expected in March 2019.

This Annual Review has been carried out as a desk-based review, drawing on the knowledge of the GCF advisory teams in DFID and BEIS, and using the existing policies, frameworks, and decisions of the GCF as evidence. This includes reporting on KPI15 (transformational change), which will be completed in March 2019 for the second time.

Evidence (1/2 page)

The GCF has a sound approach to evaluation, with all projects expected to include a mid-term evaluation and an evaluation on completion. In addition, the Independent Evaluation Unit (IEU) of the GCF is also mandated to carry out evaluations at project, programme, and fund-level. The IEU is developing the Fund’s Evaluation Policy, which is due to be adopted in 2019, and build on the Fund’s ambitious mandate. The IEU’s 2018 workplan was approved at the first meeting of 2018 (B19), and its 2019 workplan (also ambitious), including budget, and updated three year rolling workplan was approved at the third meeting of 2018 (B21). The IEU delivered two evaluations in 2018: an evaluation of the Readiness and Preparatory Support Programme, and a review of the Results Management Framework. It also commended he Learning-Oriented Real-Time Impact Assessment (LORTA) programme, which will be completed in 2019. While working on these, the IEU continues to focus on internal learning and development, regularly scheduling internal learning sessions that are focused on staff and peer learning and include discussions on important subjects related to climate change and evaluation, while learning from other disciplines.

The quality and effect of the IEU’s reviews and recommendations presented and approved at B22 clearly demonstrated a virtuous circle between evaluation fby the IEU and the corresponding management response form the Secretariat. We assess this augers well for the future.

The workplan for 2019 sets out activities that the IEU will undertake to inform proposals and decisions made by the Board and guide the Board in a strategic way. In 2018 the IEU has been able to increase its staff numbers, from 2 full time staff in September 2017 to 12 (including long-term consultants) based in Songdo by the end of 2018.

Learning (1/2 page)

Analysts from the UK GCF team visited the IEU and the Office of Portfolio Management in the Secretariat in September 2018 to develop the relationship further; influence the standards used to assess future project proposals; understand the opportunities for learning across portfolios; and to influence results collection processes and procedures to see they meet UK needs for annual results reporting (in particular on credibility, consistency and transparency). The team were able to identify a number of areas for improvement, particularly in the results collection and management process, which are reflected in the IEU’s evaluation of the Results Management Framework.

The UK are working closely with the Secretariat, and the IEU, having made it a priority for 2019, to ensure the improvements are implemented in 2019 to allow for improved collection of actual results, and enable the revisiting of the expected results from the business case.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided