Business Case

Summary Sheet

Title: Humanitarian Response to the 2018 Earthquake and Tsunami in Sulawesi, Indonesia
Programme Summary: An effective humanitarian response providing immediate assistance to the most affected people and households in Central Sulawesi, Indonesia.
Programme Value: up to £3,000,000		Country/ Region: Indonesia
Programme Code: 300741	Start Date: 28 September 2018	End Date: 30 April 2019
Overall programme risk rating:	Moderate
Vault Number:	38284482

Intervention Summary (2 pages max)

Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver (1/2 page max)
A 7.5 magnitude earthquake struck Central Sulawesi, Indonesia, on 28 September 2018, triggering a tsunami which hit Dongala and Palu and massive, localised liquefaction and mudslides, most notably in Balaroa, Petobo and Jono Oge. This all had devastating impacts across many areas and resulted in an official death toll of over 2,100 deaths. 130,000 people remain displaced two months on.

DFID’s response funding of up to £3 million to various affected areas in Central Sulawesi over 6 months prioritises meeting urgent humanitarian needs. This includes UK direct support (expertise, relief supplies, monitoring), as well as programme support to bilateral partners (including common logistics; water, sanitation and hygiene (WASH); child protection; gender-based violence (GBV); and cash-based assistance). This funding complements and is in addition to the £2 million in aid match funding provided to the Disasters Emergency Committee (DEC) which is covered under a different business case

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
- Humanitarian response is a priority of the UK Aid Strategy November 2015, Single Departmental Plan 2015-2020, and the International Development Act 2002.
- The response fits within the current CHASE HRG humanitarian intervention criteria as was approved in submissions to the Secretary of State on 1st and 2nd October 2018.

What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
This programme delivers results under objective 2: ‘Strengthening resilience and response to crises’. No specific target on humanitarian assistance is provided, so it is not possible to give a percentage here.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
- DFID is closely coordinating its response in the region with the Indonesian government. All partners supported in this programme have secured prior approval from the government to implement DFID funded projects.
- DFID is working closely with other bilateral and multilateral donors in the region to ensure complementary approaches, including with the EU’s humanitarian aid office (ECHO), Australia’s DFAT and New Zealand.
- Our advisers have been actively involved in sectoral coordination groups; the allocations set out here are in line with priorities identified in them.

Has the programme considered working with HMG Departments and accessing cross-HMG funds?
- This is a DFID led response, but DFID has been working closely with other Government departments including the Foreign and Commonwealth Office (FCO).
- DFID has also been working closely with the Ministry of Defence (MoD) during the immediate response, including utilising an RAF cargo plane to carry vital UK aid supplies from the UAE to Indonesia. This plane has also assisted the Indonesian Government with moving vital supplies between Jakarta and Balikpapan, the main hub for relief items.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
- In addition to this direct UK aid, the UK is providing support to the humanitarian response through core contributions to the UN’s Central Emergency Response Fund (CERF), UN agencies, the Red Cross, the EU’s Civil Protection and Humanitarian Operations and the Education Cannot Wait Fund. The support in this business case is closely aligned with these partners and we worked with them during the design to ensure complementarity of approaches.
- This programme does not directly relate to the existing bilateral UK aid programme in Indonesia which focuses on forests and climate change.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
- Although this programme is only 6 months in length, DFID has been monitoring progress of partners’ work closely both from London and from relevant colleagues based in the region. A Humanitarian Adviser was present in Indonesia until end October to ensure funds were programmed effectively according to needs in the fast-changing early weeks.
- In line with our Grand Bargain commitments, DFID has supported programmes which gather feedback from beneficiaries and communities, and to use this to inform both the UK programming and to support partners to adjust their commitments.
- DFID will undertake a monitoring mission to the region mid-programme (Jan 2019), which will be used to assess and discuss course correction with partners.

Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
Yes. This is a moderate risk programme. DFID will examine and continuously assess the risk level of this intervention through ongoing monitoring and through a monitoring mission mid-programming.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
- Yes, the programme will be branded with the UK aid logo wherever possible.
- Partners will also be informed to acknowledge UK aid in organisational outputs.
- DFID’s communications team has been closely engaged on this programme and working to improve visibility of UK Aid in the media.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
- This business case has been designed based on recommendations from the CHASE field team. It was approved by the CHASE Humanitarian Response Group management.
- There are several factors that could affect the programme and/or mean adjustments are necessary. These include the capability of local authorities and the staffing levels of partners, as well as the political situation in country. However, we remain confident that the programme can be delivered and has the support of the national government.

Does the SRO and team have the capability and resources to deliver this programme?
The SRO for this programme was identified at the outset of the response and has been working closely with colleagues in CHASE HRG to deliver this programme. The Humanitarian and Stabilisation Operations Team (HSOT) has also been supporting this programme with humanitarian and logistical advisory capacity. Together the team has the capability and resources required to ensure adequate management and oversight of the programme.
Strategic Case

Context
On 28 September 2018, a series of strong earthquakes struck Indonesia’s Central Sulawesi province, the strongest a 7.5 magnitude earthquake only 10 km deep and with its epicentre close to the provincial capital, Palu. The earthquake triggered a tsunami with waves reaching up to three metres in some areas, striking Palu and Donggala. Massive, localised liquefaction and mudslides were also triggered, most notably in Balaroa, Petobo and Jono Oge. The earthquakes, tsunami and resulting liquefaction and landslides caused significant damage and loss of life in affected areas as shown in figure 1 below.

Over 2.4 million people were affected and at least 210,000 people displaced, although many left the province or found refuge with host families. As of 10 December, 133,631 people remain internally displaced and the official death toll is 2,101 with 4,438 people seriously injured and 1,373 people missing. Given the extent of damage in some communities and suspected under-reporting, actual figures may be higher than this. An estimated 15,000 houses and land have been totally devastated and some 17,000 houses heavily destroyed but the sites may allow for reconstruction. Around 35,000 families whose houses were damaged required emergency shelter support. The Indonesian National Agency for Disaster Management (BNPB) has put the total cost of material damages at $910 million USD.

Fig.1: Areas affected by the tsunami and liquefaction (sources: REACH, Shelter cluster, BMKG, BIG).

The Government of Indonesia (GoI) has exerted strong leadership and control over the response effort. Immediately after the earthquake and tsunami, local communities and responders on the ground began efforts to rescue people trapped in the rubble of collapsed buildings and provided urgent assistance to survivors. Search, rescue and retrieval efforts were undertaken by thousands of people from affected communities, Indonesian Red Cross (PMI), the National Search and Rescue Agency (BASARNAS), Indonesian National Armed Forces (TNI) and local government agencies.

The GoI, through BNPB and Ministry of Foreign Affairs, began accepting offers of international assistance on 1 October 2018. The Indonesian Government outlined its priority needs as: basic relief items for disaster-affected people and logistics to bring them to Palu, particularly clean water, sanitation and hygiene; and immediate repair of infrastructure and public services including schools and health centres. Other priority needs included child protection and prevention of GBV, and education.

The Red Cross launched an appeal for CHF 22 million which is expected to deliver assistance to 160,000 people for 20 months. The Indonesian Red Cross mobilised volunteers to support search and rescue, first aid and delivery of immediate assistance. The UN Central Emergency Relief Fund (CERF) allocated $15 million to rapidly scale up support to the Government-led response in the areas of logistics, shelter, safe water and sanitation, health care, camp coordination and camp management, emergency livelihoods and protection services. UNICEF is working to reunite unaccompanied children with their families and provide drinking water. OCHA has deployed staff into the AHA Centre (ASEAN Coordinating Centre for Humanitarian Assistance) to assist with coordination.

Rationale and overall strategy for UK support
The UK government’s 2017 Humanitarian Reform Policy commits to a bigger, better and faster response capability to rapid-onset emergencies. This includes appropriate use of expertise, funding and emergency relief supplies. It also commits to building the capacity of our partners (UN, Red Cross, NGOs and governments) in emergency responses. The 2016 World Humanitarian Summit outlined the Grand Bargain, of which the UK has been a key supporter. The Grand Bargain outlines ten commitments to improve efficiency of the humanitarian system. This includes more participation from affected communities, less earmarked funding and more collaboration between development and humanitarian actors.

A range of factors, or ‘intervention criteria’, inform DFID decisions on humanitarian response, including the estimated humanitarian impact of events, the capacity of the affected country, the reaction of other donors and the UK’s interests. Indonesia, the world's largest island country located between the Indian and the Pacific Ocean, sits along a volatile seismic strip called the ‘Ring of Fire’ in the Pacific. Volcanic eruptions and earthquakes occur regularly, which can present a potential threat of tsunamis. A number of significant disasters have occurred in Indonesia since the 2004 tsunami, including earthquakes, tsunamis, volcanic eruptions and events caused by climate change.

Indonesia has extensive risk governance and management arrangements, (with a reported budget of up to $500 million USD) and significant capacity at national, local and regional scales to respond to emergencies. They are however one of the highest ranked countries for disaster risk, and as such do not have the capacity to respond to all emergencies above a certain size, or when the system is already stressed, as may have been the case dealing with Lombok and Sulawesi crises simultaneously.

The nature of the events in Sulawesi, which comprised four hazards (earthquake, tsunami and resulting liquefaction and landslides), meant that, along with an already stressed system, the severity and scale of the impact of the event was assessed as medium. Interest from the UK media and public was significant which can influence decisions around engagement. With a Red Cross appeal and CERF activation, it was also clear that there would be a strong donor response to the situation to meet immediate needs.

This business case is therefore consistent with UK priorities and also the priorities outlined by the Indonesian Government above. DFID’s funding will initially focus on delivering immediate life-saving supplies to the Indonesian authorities for distribution to affected communities and also on supporting logistics capability through air cargo handling equipment and support to a common logistics service. Our support will also ensure immediate WASH, child protection and GBV protection needs are met whilst enabling a focus on cash transfers to meet the needs of affected families. Within the programme, community participation and feedback will be encouraged.

Expected Outcomes and Desired Impact
This programme seeks to achieve the overall impact of saving lives and alleviating suffering by supporting the GoI in meeting the immediate relief and protection needs of the affected population to contribute to improved emergency public health (shelter, WASH and health) and protection (child protection and GBV) outcomes. It will do this through the immediate outcome of ensuring an effective, well-functioning humanitarian response that delivers immediate support to vulnerable households in the affected areas.

At the time of writing this business case, it is expected that DFID will deliver the following directly attributable results in contribution to this outcome. Final results may change due to the nature of rapid humanitarian response and results will be closely monitored through a monitoring visit and a logframe:

- Delivery of non-food items (NFIs) to Balikpapan, the main hub for relief items:
  - 47.5 tonnes of NFIs including 1768 shelter kits, 1008 solar lanterns and 288 hygiene kits for affected beneficiaries and air cargo handling equipment including 2 rough terrain forklift trucks and a conveyor belt loader for the efforts to get Palu airport working again and ensure delivery of relief items.
- WASH:
  - 30,000 people benefitting from improved hygiene practices
  - 500,000 people reached by hygiene messages on water treatment, handwashing with soap and use of latrines
  - 100 local schools engaged with menstrual hygiene management messaging
  - 5,000 hygiene kits distributed for menstrual hygiene management
  - 1,000 volunteers trained in hygiene promotion
- Child protection:
  - All affected children benefiting from protection services for improved wellbeing
  - Coordination services for child protection, GBV and Mental Health and Psychosocial Support (MHPSS) including assessment of protection and mental health and psychosocial needs
  - 60 social workers trained on child protection minimum standards
  - 20,000 children provided with psycho-social support
  - All children referred for support with birth registration, legal identity and family tracing are provided with services
- Gender-based violence (GBV):
  - Preventing sexual exploitation and abuse (PSEA) complaint mechanism established with link to GBV referral services
  - 1,060 frontline workers trained on GBV and PSEA
  - 3 sectoral participatory safety audits conducted (WASH, education, health)
  - 25 child friendly spaces linked to the GBV and PSEA referral system
- Cash-based assistance (CBA):
  - Feasibility assessment undertaken of cash transfer modalities
  - 2,400 children aged 0-6 benefitting from CBA being received by the family
- Logistics coordination and information management:
  - 20 organisations assisted, weekly meetings held, and weekly situational reports and access constraint maps published
- Common logistics services:
  - 90% of common service requests addressed
  - 20 organisations provided with logistics support equipment
  - 2000m2 of storage space available across the affected areas

Gender Equality
Indonesia has an active female population in both public and private life. UNFPA estimates that 352,000 women of reproductive age have been impacted by the earthquake and tsunami, including 45,300 women who are pregnant. With community support networks weakened, high levels of displacement, disrupted livelihoods and limited access to basic services, in addition to pre-existing gender inequalities, women and girls are particularly vulnerable, including to threats such as gender-based violence and the effect of displacement on their sexual and reproductive health. This programme will ensure that partners can work closely with the government and others to protect women and girls in the aftermath of the earthquake and tsunami, including through the provision of safe spaces for women and children and technical support to ensure sexual and reproductive health provision.

Partners have been requested to disaggregate data by age and gender as part of their reporting commitments wherever possible and make efforts to ensure a holistic approach to protection issues by integrating concerns for people with disabilities, as well as women, children and the elderly. We judge this Business Case is fully compliant with the International Development (Gender Equality) Act, and that gender has been considered throughout the design and will be central to implementation.

Terrorism and financing
HRG operates in compliance with strict departmental protocols of due diligence and procurement, as well as UK Counter Terrorism legislation. DFID’s primary risk mitigation is working through partners whose financial risk management systems have been assessed by DFID to be of a high standard. We will ensure that partners are briefed on their obligation to report fraud incidents, as well as their responsibilities under the UK Counter Terrorism legislation to manage the risk of diversion of aid to terrorist organisations.

Appraisal Case

Option 1: do nothing

The counterfactual of doing nothing was not considered a feasible option, given the scale of destruction and humanitarian needs emerging. The Indonesian response mechanisms are overwhelmed, particularly with earthquakes in Lombok a month earlier. Doing nothing would not meet DFID’s humanitarian objectives as set out in its humanitarian reform policy, or allow DFID to push the international system on the World Humanitarian Summit Grand Bargain commitments

In this option, the UK contribution would be limited to its indirect contribution through core funding to the UN Central Emergency Response Fund, the International Red Cross and the EU’s Civil Protection and Humanitarian Operations.

Option 2: Up to £3 million delivered through a range of partners and mechanisms providing life-saving assistance and improving the effectiveness of the overall humanitarian response

Building on experience and lessons learned from previous recent responses (e.g. Hurricane Irma and Maria, Hurricane Matthew, Nepal earthquake, Typhoon Haiyan), the preferred approach is to respond in a comprehensive manner to meet immediate humanitarian needs over a six-month period. This includes supporting the wider humanitarian system; using our influence with the UN and other donors to galvanise additional support, and to use this more effectively and efficiently. The use of military assets were considered as appropriate in line with the UK’s Humanitarian Reform Policy..

Selection of partners depended on their in-country capacity, their ability to meet DFID’s strategy and priorities for the response, and their ability to deliver programmes to those most in need while meeting DFID’s value for money expectations (on appropriate quality, cost and speed – more detail below). Selection of partners also took into account their ability to deliver programming across the priority sectors (WASH, child protection etc), and also considered support to the enabling environment of the response (logistics, co-ordination etc) as well as direct programme delivery.

In light of the medium scale of the disaster, the access challenges for international personnel and the desire to ensure this is a nationally-managed response, the response strategy focussed on three pillars: 1) provide immediate relief through logistics support and NFIs, to be distributed by PMI and World Vision; 2) bolster national and local response capacity through funding to international humanitarian partners: UK Aid Match of the DEC Appeal and funding to UNICEF and WFP; and 3) support the enabling environment through HMG advocacy and the provision of expertise to improve the operational planning and management of the response, and thus the timeliness, relevance, impact, accountability and VfM of assistance.

Disasters Emergency Committee Aid Match Funding

The Disasters Emergency Committee (DEC) is an umbrella organisation that brings together 14 leading UK humanitarian relief organisations. It channels the funds it raises through these organisations to help those most in need. Through broadcasts on mainstream media (BBC and ITV) the DEC can bring greater public attention to humanitarian emergencies around the world and raise significant amounts of money to support responses through its member agencies. DFID has provided UK AID Match funding to the DEC for 6 previous appeals including most recently in 2017 for the East Africa Crisis Appeal.

DEC launched a public appeal for the earthquake and tsunami in Sulawesi on 4 October. DFID committed to match pound-for-pound the funds raised by the DEC up to £2 million for the immediate emergency phase (first six months), encouraging further donations. The contribution is not covered in this business case but is instead covered under the UK Aid Match business case. As of December 2018, the appeal has raised £25 million. In the immediate emergency response phase, DEC partners will work with national NGOs in Sulawesi to provide support to the affected population including food distribution, meeting WASH needs and ensuring access to shelter. At the end of this phase, DEC agencies will move to longer-term recovery activities to support the population.

Theory of Change

Up to £3 million and CHASE staff time and £2 million in aid match to DEC:
DFID support to UNICEF and WFP;
relief items and air cargo equipment; technical specialists

INPUTS

Vital support to NGOs to ensure a LOCALLY LED response that meets needs in the short and medium term
ENABLING ACTIVITIES
on logistics coordination, information services and technical expertise to the humanitarian community
LIFE SAVING ASSISTANCE, including cash, to meet shelter and immediate needs, particularly of the most vulnerable including women and children

OUTPUTS

Local NGOs lead the response on the ground and respond effectively to affected people, taking on board feedback
Humanitarian system more effective, targeted and timely at delivering assistance and protection to vulnerable people

Communities, households and vulnerable people in affected areas have access to shelter and essential non-food items to meet basic needs, particularly WASH and protection

OUTCOMES

IMPACT
Lives saved, suffering alleviated and early recovery promoted through the provision of multi-sectoral assistance and protection to the most affected and vulnerable

Strength of the evidence base: medium / high

Following a rapid onset disaster, people quickly start to rebuild houses to meet immediate shelter needs and secure against further damage. However, these ‘repaired’ structures at best will replicate previous vulnerabilities. Rapid humanitarian assistance in this early stage will not only help to better secure homes and meet immediate shelter needs but can also ensure that repairs incorporate the use of improved materials and build back better techniques that can help withstand against future external shocks.

The UK’s 2017 Humanitarian Reform Policy makes explicit that extreme weather events are likely to disrupt populations and livelihoods, making political instability and migration more likely (p.6). Early humanitarian assistance to households and communities will encourage more people to remain and join reconstruction efforts.

Costs and benefits
Value for money (VfM) in DFID humanitarian work is judged by cost, quality, appropriateness, speed and timeliness. Therefore, VfM best practice points to the use of pre-existing arrangements with trusted and experienced partners, and an agreed costing framework. This allows DFID to transform funds into high quality and appropriate cost-effective aid, directly delivered into communities within a short timeframe. This basic principle underpinned the up to £3 million allocation.

DFID and its partners have put in place a number of measures to reduce setup, operational and administrative costs:
- Using cash early and as soon as markets allow to avoid costly in-kind assistance. This also allows households to prioritise their own needs and supports the local economy with cash injections.
- DFID will work through and strengthen existing response mechanisms in country where possible. This will include working closely with the Indonesian Red Cross Society (PMI) and the Indonesian military.
- The use of the Standby Partnership to deploy specialised skills into key cluster groups or agencies in affected countries.
- An understanding with MoD that DFID is only charged marginal costs for use of its assets in a humanitarian response.
- As part of the proposal review process, all partner project budgets undergo detailed review against VfM criteria.
- Where possible, DFID claims partial rebates on transport costs through the EU Civil Protection mechanism.

In addition, with regards to quality, all UK AID relief items (e.g. emergency shelter items, water filters) comply with the international humanitarian SPHERE standards.

In terms of appropriateness and timeliness of delivery, as well as quality, everything from hygiene kits to cash disbursements will be reviewed through a number of different mechanisms. This will include partner post-distribution and other monitoring reports, use of beneficiary feedback processes, a DFID monitoring visit to the region. Close co-ordination with key partners (including Australia, the EU and the USA) through the course of the response should ensure there is no duplication of effort or overlapping programming.

DFID’s own internal procedures also ensured speed and timeliness. Two Humanitarian Advisers were deployed to Indonesia immediately following the GoI’s indication that they were open to receiving offers of international assistance. Other personnel (additional advisers, logisticians, Humanitarian Affairs Officers) were identified and put on standby for immediate deployment whilst initial scoping took place.
Commercial Case

Funding mechanism and partners

The up to £3 million allocation involves no direct commercial procurement under OJEU (EU procurement) procedures. Given the urgency of the humanitarian response, the timescales associated with a full procurement procedure would be impractical and the procurement of in-kind assistance is already covered by an existing DFID framework contract. However, commercial considerations are a core part of the partner identification process. All partner proposals are scrutinised to identify pre-established presence in the region with the capability to intervene rapidly in the affected areas. Partners all show a strong understanding of the situation and also any constraints that are likely to affect their ability to respond and deliver relief items. DFID continues to monitor partner performance from London and via colleagues in Indonesia.

Partner proposals and budgets are scrutinised and the cost of core relief items are benchmarked against the cost of similar goods procured during previous humanitarian responses in the region. This ensures that only partners with proposals that reflect value for money are selected.

Direct partners proposed for this response are UNICEF and WFP. A Contribution Arrangement will be signed with each partner and these will be subject to the terms of the Framework Arrangements already in place between DFID and each partner, drawing upon pre-agreements and vetting processes.

Financial Case

Funds will be drawn from CHASE’s humanitarian contingency budget and all allocations will be ODA-eligible.

Funds will only be provided through pre-approved, tried and tested partners; none will be channelled directly through government at local or national level. They also have robust tracking systems at all stages of the supply chain from procurement to distribution. Based on the above, financial risk and fraud is assessed as low. Funded partners will provide appropriate financial reports, as set out in the Management Case. Annual Audited Statements will also be provided by all partners. Management costs associated with providing funds through these partners are within normal ranges agreed by DFID.

On receipt of appropriate justification from both UNICEF and WFP payments will be made in a single tranche. These justifications will be in the form of proposals including thorough needs assessments, detail on proposed activities and timelines, logical framework, risk matrix and budget. UNICEF and WFP will be required to provide financial reports after the short-term projects have concluded. These will set out and account for the funding provided as per standard agreements with DFID. Standby Partnership secondments will be invoiced in arrears.

NFI and staffing costs will be invoiced to DFID by Palladium. The majority of payments are expected to be made before 31 March 2019.

Overview of costs

Partner	Amount	Sectors	Timeframe
UNICEF	£950,000	WASH, child protection, gender-based violence protection and cash-based assistance	16 October 2018 – 16 April 2019
WFP	£300,000	Common logistics and information management	3 October 2018 – 31 December 2018
DFID relief supplies (47.5 tonnes)	£473,000	Shelter kits, solar lanterns, hygiene kits and air cargo handling equipment	October 2018
Essential air operations	£848,500	Air operations to deliver relief supplies	October 2018
Staffing/Expertise	£150,000	Humanitarian Advisers, Informational Management Officers, Logisticians	1 October 2018 – 15 January 2019
Standby Partnership secondment into UNFPA	£72,000	Sexual and reproductive health and rights	12 October 2018 – 29 April 2019
Monitoring	£30,000	Monitoring visit	January 2019
Unallocated	£176,500
TOTAL	£3,000,000

These figures are accurate at time of completion of this business case but may not reflect final spend as further changes or reallocations may occur. All projects are expected to be completed by end April 2019.

Management Case

Reporting and monitoring

The Humanitarian Response Group in CHASE will be responsible for the programme and will ensure that it delivers the expected results on time and on budget. The core team will consist of the Senior Responsible Officer (SRO) and Programme Manager. The SRO will have oversight of the entire programme, ensuring compliance with DFID’s ‘smart’ rules. The Programme Manager will be responsible for the day to day running and management of the programme. Humanitarian advisers, along with the Programme Manager, will prepare the Project Completion Report (PCR) in line with DFID/CHASE guidelines.

A monitoring visit will be conducted in January 2019, predominantly looking at the direct funding to UNICEF and WFP. The visit will include some engagement with UNFPA and the DEC to understand their work to date on the response.

All partners will be required to provide detailed end of project narrative and financial reports, with UNICEF also providing mid-term monitoring reports, and further ad hoc updates as required. These will be scrutinised in the region and in London, and further validated by the monitoring visit to the field. Overall responsibility for monitoring and reporting will be held by the SRO, with substantial support provided by the programme manager. This will ensure a continued and responsive focus on programme activities and results achieved by all partners.

Risk management

Risk	Probability	Impact	Overall	Mitigation
DFID staff injury due to damage to infrastructure	Unlikely	Moderate	Moderate	Adherence to TRA procedures, and embassy security advice. All deployed staff have completed HEAT training and know First Aid and deploy with first aid kit and trauma kit. Limit the number of people in the field.
Funding not used for intended purposes because of fraud, lack of partner capacity, poor management or diversion of goods resulting in less effective and efficient response, and aid not reaching those most in need	Possible	Minor	Moderate	Due diligence of partners, informal monitoring of distributions of NFIs, monitoring visit at mid-point of programme.
Critical media because of real or imagined inefficient or ineffective response leading to reduction in public buy-in for DFID humanitarian aid	Possible	Minor	Moderate	Strong programme management and local stakeholder engagement to ensure effective and efficient response. Robust communications engagement to ensure the positive stories are amplified, and that negative stories are refuted.
Misalignment with the Indonesian authorities’ response plans	Unlikely	Moderate	Moderate	Close work with the Ambassador and Embassy to ensure that DFID plans and actions align to Government edicts. Ensure partners work with line ministries.
Delays to NFI distribution which could result in the affected population not receiving what they need quickly enough, or UK goods not be distributed at all	Likely	Moderate	Major	Donors have agreed to blanket distribution of NFIs to ensure items can reach those in need quickly. We will therefore not formally monitor the distribution and there is a limited amount of mitigating action we can take. Some informal monitoring and conversations with PMI can take place. We have had discussions in advance with GoI about what they need and will align our goods with that
Further disasters (Indonesia or otherwise) demanding the attention of the international community, which could result in lack of attention or resources (funding or expertise) being drawn away	Possible	Moderate	Major	DFID and partners would ensure resource in place to continue to focus on addressing existing emergency needs in Central Sulawesi and meeting current obligations and needs to our best standard while expanding response through additional funding to address newer emergency situations
Safeguarding concerns due to inadequate training of response workers or lack of knowledge from affected people about their rights which could result in harm to the affected population	Unlikely	Severe	Major	Our support to UNICEF will ensure that MoSA social workers and other partners will be trained on GBV safe identification and referral and PSEA and will deliver messages about PSEA in order to ensure women and girls at risk are aware of their rights and are able to access appropriate services safely.