 Annual Review

Title: Strengthening Evaluation in Governance and Politics
Programme Value £ (full life): £4,990,237.00		Review Date: 31st March 2019
Programme Code: 205133	Start Date: 31st March 2016	End Date: 31st April 2020

Summary of Programme Performance
Year	2016/17	2017/18	2018/19
Programme Score	A	A+	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-205133/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-205133/documents

A. Summary and Overview

The Evidence in Governance and Politics (EGAP) research network is a cross-disciplinary network of researchers and practitioners which is united by a focus on experimental research and is dedicated to generating and disseminating rigorous evidence on topics of governance, politics, and institutions. EGAP’s members use rigorous impact evaluations (i.e. randomised control trials and quasi-experimental methods) to accurately measure the effect of governance interventions on outcomes of interest. EGAP’s network consists of nearly 200 members from over 100 leading universities, research institutes and development organisations worldwide. This network is supported by a small secretariat, who manage and lead activities.

EGAP was founded in 2009 and was initially funded by agencies other than DFID. EGAP’s early work focused on improving standards and working practices in academia, including through building networks, defining evaluation technical standards, and providing training, including to researchers based in the Global South. In 2013, EGAP launched a highly innovative research project (titled the “Metaketa Initiative”). EGAP researchers undertook seven impact evaluations on the effects of information on voter behaviour (now called ‘Metaketa 1’). Each evaluation tested a similar intervention, but in a different context. Once completed, the studies’ findings were brought together into a meta-analysis, to examine the intervention’s effect across contexts. This innovative method developed a rigorous way to learn about where and why a development intervention works, and to better predict where and why it will work in the future.

In April 2016, DFID entered into an Accountable Grant agreement with EGAP, to expand the “Metaketa Initiative.” The program was initially planned for three years, and has since been extended to four years, at no extra cost. DFID funding is supporting three new “Metaketa” clusters of impact evaluations. Each Metaketa consists of a group of 5-6 impact evaluations. The topics have been chosen to provide high-quality evidence on important DFID policy areas: taxation (Metaketa II), natural resource management (Metaketa III), and community policing (Metaketa IV). Studies have been selected for funding on a competitive basis, with 17 different research teams delivering them. The aim is to deliver robust evidence on where and why interventions in these areas work, to improve the effectiveness and value for money of future governance programming in DFID and other agencies. In addition, the program will foster the development of the innovative “Metaketa” evaluation method. The aim is to build a robust, reliable method for accumulating knowledge about where and why different development interventions work. If proven, this has the potential to be widely applied to evaluate aid interventions, and to improve their value for money. Finally, by funding studies in developing countries with local implementing partners, the programme will improve capacity of researchers in developing countries and support increased use of evidence in policy making.

DFID’s funding to EGAP has supported a major scale up in EGAP’s activities. To deliver this scale up, DFID funds supported EGAP to expand its secretariat, and establish new permanent offices at University of California, Berkeley (UC Berkeley) in 2016. EGAP continues to receive funding from non-DFID sources for its other activities i.e. training and research standards improvement, for a fifth Metaketa. EGAP’s DFID and non-DFID funded activities are highly complementary of each other. The combination of DFID funding for new evaluations, and non-DFID funding for academic, training and standards improvement work, jointly help to maintain a strong network of collaborators delivering innovative and high-quality impact evaluations. The EGAP secretariat supports all activities and builds links across them where appropriate.

Summary supporting narrative for the overall score in this review

The programme has exceeded three of its four outcome indicators. It has made substantial progress against the remaining outcome indicator and the impact indicator but has not fully met expectations on these two indicators. Overall, the progress against the indicators proves that EGAP is able to influence policy decisions and promote better evaluation methods in low income countries (LICs) or middle income countries (MICs). For example, an EGAP evaluation in Uganda has influenced the Uganda Police Force to move forward with a standardised rollout of community policing strategies with potential for better police services for citizens.

At the output level, EGAP has met or exceeded all its indicators and is making good progress against its four objectives of improving linkages between EGAP researchers and policy makers and practitioners; generating knowledge on priority governance questions (the Metaketas); defining evaluation technical standards; and providing training, including to researchers based in the Global South.

Achievements include.
- High numbers of views of EGAP’s policy briefs, exceeding the target by over 500%
- More engagement with potential users of metaketa results than planned
- High quality management of the 17 Metaketa impact evaluations, and great preparations in place for the meta-analysis
- Promotion of better transparency in research, with many more analysis plans being preregistered than expected.
- Good progress in increasing the capacity and representation of Southern based researchers. High quality training delivered and the number of southern based researchers presenting at EGAP conferences has exceeded expectations.
- Higher number of EGAP consultations on practitioner led research designs than expected.

Recommendations for the year ahead (1/2 page)

EGAP, with DFID and donor support, should conduct a stakeholder mapping exercise that identifies key audiences for EGAP expertise and research. EGAP to use the mapping to identify changes in plans for outreach activities, the optimum routes and products tailored to each of these audiences (stakeholder mapping to be completed by May 2019, action plan to adjust routes to reach key stakeholders and products by July 2019).

DFID to work with EGAP to identify and facilitate opportunities for engagement with relevant individuals in DFID and HMG, who are working in areas which overlap with EGAP’s research interests. Possibilities being considered to date include:

- A UK launch of the EGAP Metaketa findings for DFID and relevant HMG colleagues.
- EGAP researchers’ participation in learning seminars for DFID’s Governance Cadre.
- Evaluation learning events with UK-based EGAP researchers.
- EGAP researchers will visit the UK to hold a series of events and meetings with DFID/HMG individuals in advance of the EGAP meeting in Geneva in October 2019.
- Improved articulation of EGAP’s offer to DFID.

DFID should also transfer a small amount of funds from the EGAP monitoring component to facilitate DFID events. (Agreement on priority events between EGAP and DFID by June 2019)

DFID to work with EGAP to develop research products and dissemination channels for the Metaketa results, which are designed to reach a range of non-academic audiences (by July 2019).

EGAP to explore options for disseminating results from baseline and midline data, particularly to practitioners in the countries where the studies are taking place, where this will not compromise the integrity of the research (by July 2019).

EGAP firm up the timelines for the completion of the standards grants, providing these timelines to DFID by April 2019.

There are number of recommendations to improve the logframe. These are detailed in section C.

DFID ensures regular catch up meetings with the other funders, commencing by June 2019.

## B: DETAILED OUTPUT SCORING

Output Title	EGAP researchers and evaluators build strong networks of linkages with interested policymakers and practitioners and share evidence and knowledge effectively.
Output number per LF		1	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
> Number of organizations in policy influence study on institutional members, policy event hosts, and organizations working in the space of governance and institutions conducted by EGAP / > Number of institutional stories of change/case studies to explore impact on policy/program decision making prepared	20 / 4	Policy influence survey begins in March 19. Target number of organisations is expected to be met[1] / 7
> Number of policy briefs about Metaketa projects written / > Number of views of all EGAP policy briefs per annum / > Number of meetings with government agencies/policymaking institutions on results of Metaketas	6 / 360 / 6	6 / 2168 / 17
> Number of DFID-funded EGAP studies which have been discussed or profiled with relevant government and civil society organisations in country of study (including by gaining required government sign-offs for research)	16	17
> % of Principal Investigators on DFID-funded EGAP studies signed up to EGAP ethics framework	100%	100%
[1] This expectation is based on the response rate of the pilot survey and the large range of organisations EGAP are approaching, which should lead to the target being exceeded.

Provide supporting narrative for the score

This output is concerned with expanding the use and influence of EGAP research, ensuring that EGAP continues to build a strong network and demand for its evaluations, through publications, events and other outreach activities. DFID funds contribute to these targets through outreach activities and products associated with the Metaketas. Non-DFID funded outreach activities, which often cover DFID-funded work, also contribute. EGAP has met expectations for this output, and in some cases exceeded expectations. Achievements include:

- EGAP met with 17 government agencies or policy-making institutions to promote both the methods and results of EGAP’s metaketa research, exceeding the target of six. Research by EGAP institutional members was furthermore instrumental in creating the U.S. Government’s Global Fragility and Violence Reduction Act in 2018.
- EGAP have produced seven ‘stories of change’ that track the policy influence of DFID-funded studies, exceeding the planned target of four. End line data collection for the Metaketas remains ongoing, so these stories of change will be supplemented over the next year as EGAP achieve more policy impact through the Metaketa studies.
- EGAP met its target to deliver six Metaketa briefs.
- EGAP policy briefs (including the Metaketa ones) have received over 2,000 views online, exceeding the target by over 563%.
- All 17 DFID-funded EGAP studies have been discussed with actors in the country of study, versus a target of 16. These discussions have furthermore resulted in early policy uptake of the Metaketa studies by policy actors. For example, the Community Policing Metaketa in Uganda has influenced the Uganda Police Force to move forward with a standardised rollout of community policing strategies. In DRC, the EGAP taxation Metaketa team, who are working with the provincial government of Kasai Central to promote access to formal property titles in Kananga, convinced the government to randomise access to the programme and discounts in the price of land titles, leading to more equitable programme participation and distribution of discounts.

Over the last year, EGAP have started consistently holding policy events before each of the EGAP meetings. These are a great initiative and capitalise on the EGAP members attending the core EGAP meeting. They are aimed at a wider audience than researchers. Examples of topics covered are immigration, countering violent extremism and the effect on voters’ choices and turnout from supplying information about candidates’ background and performance. EGAP are still refining their approach to make these as effective as possible; for instance, at the event in The Hague in October, the Dutch Foreign Ministry suggested preferred policy relevant topics and EGAP presented recent research on these areas. EGAP are also bringing in expertise to guide the academics on their presentation style for a non- academic audience.

EGAP are improving their strategic approach to facilitating interactions with policy makers and seeking opportunities to strengthen linkages. For instance, future American based EGAP meetings will be held in Washington DC where there is a large policy community, rather than regional universities. EGAP are also actively cultivating their institutional members, to improve linkages with policy institutions.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lesson: As highlighted above, there continues to be a clear demand across both donor countries and the Global South for the rigorous evidence being produced from the Metaketas, other EGAP member research, and the research methods being developed through the Metaketa studies. As identified in the previous Annual Review, the programme needs to be strategic in consolidating outputs to those that deliver the greatest impact; understanding which audiences can be reached by which outputs; and how outputs individually contribute towards broader EGAP and donor objectives. EGAP has produced a dissemination calendar as recommended in last year’s annual review; however, further work is needed to identify the key target audiences and the optimum routes and products for reaching these audiences to maximise the programme’s impact.

Recommendation EGAP, with DFID and donor support, should conduct a stakeholder mapping exercise that identifies key audiences for EGAP expertise and research. EGAP to use the mapping to identify changes in plans for outreach activities, the optimum routes and products tailored to each of these audiences (stakeholder mapping to be completed by May 2019, action plan to adjust routes to reach key stakeholders and products by July 2019).

The indicator for online views is not appropriately set and will continue to be exceeded with minimal effort. Additionally, the indicator “Number of DFID-funded EGAP studies which have been discussed or profiled with relevant government and civil society organisations in the country of study (including by gaining required government sign-offs for research)” is an important indicator but does not contain a measure of quality. Recommendations: Review the indicator target for online views to make it more stretching. Add an indicator “Positive feedback on EGAP studies from relevant government and civil society organisations interviewed for the Annual Reviews.” (by June 2019)

Lesson: EGAP produces high-quality evidence in a range of areas that are relevant to programming and learning inside DFID. For example, a key consideration in DFID’s investment in EGAP was that a relatively small £4.9m evaluation fund could potentially inform nearly £700m of governance programming in DFID. This year, EGAP and DFID collaborated on a series of activities during the EGAP Nairobi meeting in June 2018, including a methods training event for East African evaluation and program staff. In addition, during the October 2018 EGAP policy event in The Hague, the Netherlands, DFID colleagues met with EGAP researchers to gain EGAP’s advice on shaping a proposed research programme. The feedback received was much appreciated by the DFID staff, and improved the focus of the proposed research. Nevertheless, in order to maximise the impact of DFID’s investment in EGAP, more should be done to facilitate engagements between EGAP members, DFID, and other UK policy makers.

Recommendation: DFID to work with EGAP to identify and facilitate opportunities for engagement with relevant individuals in DFID and HMG, who are working in areas which overlap with EGAP’s research interests. Possibilities being considered to date include:

  - A UK launch of the EGAP Metaketa findings for DFID and relevant HMG colleagues.
  - EGAP researchers’ participation in learning seminars for DFID’s Governance Cadre.
  - Evaluation learning events with UK-based EGAP researchers.
  - EGAP researchers will visit the UK to hold a series of events and meetings with DFID/HMG individuals in advance of the EGAP meeting in Geneva in October 2019.
  - Improved articulation of EGAP’s offer to DFID.

DFID should also transfer a small amount of funds from the EGAP monitoring component to facilitate DFID events. (Agreement on priority events between EGAP and DFID by June 2019)

Output Title	Knowledge is generated and accumulated on priority governance questions in the areas of domestic revenue mobilisation, natural resource management, and conflict prevention / resolution (now community policing)
Output number per LF		2	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
> Number of (Metaketa) thematic evaluation grant portfolios funded / > Number of Metaketas funded / > Number of impact evaluations funded / > Number of pre-registered Metaketa meta-analyses (1 for each Metaketa)	3 / 3 / 17 / 3	3 / 3 / 17 / 3
> Number of articles on research projects submitted by Metaketa grantees to academic journals / > Number of webpages on Metaketa projects for dissemination to policymakers / > Number of policy briefs written at end of projects / > Number of working papers on Metaketa studies written (to be posted on EGAP website after publication)	0 / 0 / 0 / 0	0 / 0 / 0 / 0
> Number of Metaketa book/journal issues, 1 per Metaketa. To provide meta-analysis of RCT results, describe how they improves external validity of answers to research question, and how Metaketa contributes to improving external validity of RCTs in general.	0	0
> EGAP establish and maintain functioning headquarters at UC Berkeley / > EGAP fill all headquarters staff positions / > EGAP financial management system maintains forecast errors within 5% / > EGAP addresses outstanding action points from Due Diligence Assessment	1 / 6 / 1 / 1	1 / 6 / 1 / 1

Briefly describe the output and provide supporting narrative for the score

This output relates to the management of the EGAP secretariat, as well as the production of academic publications and resources for non-academic audiences based on the findings of the Metaketas 2, 3 and 4. The programme has met expectations for this output.

Key achievements include:
- EGAP is managing the Metaketa impact evaluations well. There are clear, demanding timetables for the impact evaluations and high-quality oversight of delivery. EGAP secretariat conducts monthly check-ins with research teams. Strong, positive feedback was received from the research teams about the EGAP secretariat’s management of the process. The committee structure for managing the technical content of the impact evaluations and ensuring consistency between research teams (crucial for the meta-analysis) is working well. Again, strong positive feedback was received during the review about the Metaketa committees, particularly the helpfulness of the trouble shooting advice received by research teams to address technical issues. Interviewees noted that being the chair of each Metaketa was a time-consuming job; some suggested that a co-chair would be a useful innovation for future Metaketas.
- The stage of the impact evaluations varies; some are currently collecting their end line data, others will begin end line data collection shortly. EGAP are clearly using the learning from Metaketa 1 to improve the processes and the speed of producing results. The studies have completed pre-analysis plans and have produced most of the coding for completing the individual and meta-analysis. Draft articles have been produced based on simulated data to ensure that publications can be completed and submitted to journals rapidly once end line data analysis is finished.
- The Metaketa studies have a lot of potential for policy impact. As well as the evidence on effectiveness of the studied interventions, the data collected, such as crime victimisation surveys and information on tax formalisation, has clear policy relevance to the countries they are working on and internationally, and for which little data currently exists.
- EGAP is already in discussions with some journals to publish the results of Metaketas 2,3 and 4 once complete. For example, EGAP is in talks with a high-profile journal to do a special issue on the natural resource Metaketa studies.

While not included in the targets for this indicator, EGAP are continuing to ensure the dissemination of the non-DFID funded Metaketa 1. Their article titled ““Voter information campaigns and political accountability: Cumulative findings from a preregistered meta-analysis of coordinated trials” is under review at the journal “Science Advances” with a potential publication date in April. They are also publishing a book “Information, Accountability, and Cumulative Learning”; this is tentatively expected to be published in June 2019.

At this point, there is only one Metaketa completed, so it is still early days for the model. Nonetheless EGAP are discussing with other funders the advantages of the Metaketa model and are gaining interest. A fifth Metaketa is already funded; the World Bank, USAID, Swedish International Development Cooperation Agency (SIDA) and German Development Cooperation are considering the model. EGAP have significant expertise in conducting a Metaketa and have produced an internal field guide on Metaketa processes. They are sharing this expertise more widely through the 30 page chapter of the book, which describes the model and articulates practical and technical considerations for conducting a Metaketa. It would be worth considering what guidance on running Metaketas could be added to the methods resources on the EGAP website.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lesson: While plans for academic publication are progressing, it is essential that the programme also continues to consider the production of research products and outreach for non-academic audiences, and (where possible) disseminates findings from baseline and midline data, to ensure that the full value of the Metaketa evidence is realised within the programme’s lifetime.

Recommendation: DFID to work with EGAP to develop research products and dissemination channels for the Metaketa results, which are designed to reach a range of non-academic audiences (by July 2019).

Recommendation: EGAP to explore options for disseminating results from baseline and midline data, particularly to practitioners in the countries where the studies are taking place, where this will not compromise the integrity of the research (opportunities for dissemination identified by July 2019).

The targets for next year have not been adjusted to allow for earlier DFID caused delays in signing the accountable grant. Additionally, the wording of the indicator “Number of articles on research projects submitted by Metaketa grantees to academic journals” is likely not to incentivise maximum dissemination, when research teams prioritise submission over dissemination activities. A possible alternative wording is ““Number of citable research papers on research projects by Metaketa grantees”.

Recommendation: EGAP and DFID revise the logframe indicators to allow for earlier delays in signing accountable grant and to incentivise maximum dissemination (by June 2019).

Output Title	Innovative, rigorous methods are applied to answering a broader set of governance questions
Output number per LF		3	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
> Number of new studies preregistered with EGAP / > Number of standards grants to improve impact evaluation methods & practices funded / > Number of EGAP-authored methods guides	825 / 5 / 14	1149[2] / 5 / 14
[2] At 11 March 2019.

Provide supporting narrative for the score

This output concerns the processes that develop and publicise new research methodologies. DFID directly funds EGAP’s standards grants. DFID does not fund the pre-registration database or methods guides, but these are complementary to the Metaketa Initiative. Targets have been exceeded for this output:

- The number of new studies that have been preregistered exceeds the milestone. Pre-registration improves the academic rigour and validity of studies by ensuring that data analysis methodologies are set ahead of data collection, avoiding situations where data are manipulated with new analysis until they show favourable findings.
- Five standards grants have been awarded; one is completed. These grants support the study and development of advanced methods and practices in experimental research, and improved methods are disseminated to improve rigour and standards across the wider research community. The indicator relates to awarding of the grants; The review team recommend that the EGAP firm up the timelines for the completion of the grants.
- The target of publishing fourteen methods guides has been met. These cover a range of topics from survey design and implementation, to internal and external validity, to more advanced methodologies to support quasi-experimental research. There have been 168,192 views of methods guides since the beginning of the DFID grant in March 2016.

The large expansion in the membership of EGAP is important for advancing this objective. EGAP membership has doubled over the last 5 years. The demand from suitably qualified candidates exceeds the number of places given funds available. This expansion is promoting improvements in rigorous research across the community of social science researchers. It is the norm among EGAP members to preregister research designs, and this change in behaviour will help promote preregistration amongst other social scientists. Better methods are also being promoted through the consultations on research run by EGAP researchers; in these consultations EGAP researchers receive feedback on their research designs or draft papers from a large group of other researchers. The review team got strong positive comments from interviewees about the research consultations’ effectiveness in raising expectations and standards in research produced by EGAP.

Recommendation: EGAP firm up the timelines for the completion of the standards grants, providing these timelines to DFID by April 2019.

Output Title	Increased capacity and representation of developing country researchers and evaluators generating rigorous governance evidence
Output number per LF		4	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
> Number of trainings delivered for principal investigators from developing countries	7	7
> Number of Global South-based researchers present research at EGAP events	18	28
> EGAP identify demand for mentorship through member survey / > Percentage of EGAP members in Southern institutions engaged in mentorship / > Number of feedbacks given to mentees (at least one project per year)	Yes / 80% / 20	Yes / 79% / 34
> Number of consultations on research designs	30	49

This output covers EGAP’s work to engage and improve the capacity of researchers in the Global South, with a dual purpose to improve the research quality, relevance and dissemination by including researchers with rich contextual knowledge, and to improve research methods and standards used by Global South-based researchers. DFID contributes to EGAP’s capacity building of researchers based in the Global South, through training and research activities on Metaketa evaluations. Non-DFID funds also contribute, supporting EGAP’s week-long “Learning Days” training events, various EGAP seminars, and other activities.

Achievements against targets include:

- EGAP has conducted seven trainings for developing country researchers during the period of the grant[3].
  [3] The seventh will be conducted in Bogota in early April 2019.
- Twenty-eight Global South-based researchers presented research at EGAP events, exceeding the cumulative target of 18.
- EGAP has significantly exceeded targets for consultations on practitioner-led research designs, with implications for improving the quality of research. This year the designs were for National Democratic Institute (NDI), the Swedish International Development Cooperation Agency (SIDA), the World Bank, a grouping of Kenyan NGOs and DFID. The DFID consultation was on the research agenda for a proposed £15m research programme on conflict and economic growth. The feedback received was much appreciated by the DFID staff. During the annual review, the DFID team attended two EGAP meetings with policy actors; one with the World Bank, where EGAP members brought in the latest evidence base on improving revenue collection, to improve a World Bank project and the initial design for the research for the project; the second with USAID on their desire to establish a rolling Metaketa for their democracy programming. To note, this indicator includes research designs that are led by Global North-based researchers, and so more speaks to output 3 and output 1.

Feedback received during the annual review from Southern based researchers valued the access to EGAP’s methodological debates and methodological resources, as well as access to finished research. For instance, a Ghanaian researcher working in a Ghanaian advocacy organisation said that “the EGAP policy briefs are one of the best resources for finding ideas for policy solutions and he uses the research results in his policy advocacy in Ghana”.

There is strong demand for the Learning Days, enabling EGAP to be selective towards high quality, motivated candidates with a promising research idea. The Learning Days are an intensive week long training, which improves participants understanding of impact evaluation and helps them develop a robust research design. In some cases, the Learning Day events have been a stepping stone that has also helped the participants to enter EGAP. But the Learning Days are not designed to provide the methodological training to be a Principal Investigator. Instead, EGAP have secured funding from another donor to put in place a more intensive mentorship scheme, including sponsoring fellowships for southern based researchers at highly regarded EGAP related institutions.

The Southern based EGAP membership has been increasing now stands at 14% of EGAP membership. The new intensive scheme to build capacity of southern based researchers will continue this positive progress.

Lessons identified this year, and recommendations for the year ahead linked to this output

EGAP’s network of academics are available to offer consultation and support to aid agencies on the design of impact evaluations and research programmes. There is potential for DFID to promote this further internally and across relevant areas of the UK government, for example Stabilisation Unit are interested in closer links. Recommendation: As with output 1, DFID to work with EGAP to further identify and facilitate opportunities for engagement with relevant individuals in DFID and HMG, who are working in areas which overlap with EGAP’s research interests.
## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The existing theory of change is premised on four interventions that roughly align with the outputs in Section B above: 1) making evaluation policy relevant by organising a network and engaging policymakers; 2) generating valid evidence by funding portfolios to create higher external validity of evidence; 3) improving evaluation standards and methods; and 4) developing capacity in the Global South. Outcome statements reflect – to some degree – the two outcome statements in the logframe (policymakers and practitioners use rigorous, externally valid evidence to inform governance interventions, and a larger and more globally representative pool of researchers generate better evidence). There is a mismatch between the breadth of the impact statement in the theory of change in the business case and the narrower one in the logframe. The programme theory of change being implemented has changed since the initial business case. EGAP’s plans about how to reach out to practitioners and increase membership from the Global South has developed since the original business case, particularly as some of the plans articulated in the business case are being funded by other funders, and so specific plans depends on agreements between EGAP and the other funders. The recommendations contained within this review will further develop the theory of change.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Impact	Indicator	Target	Progress
Governance in developing countries is strengthened through improved policies and programmes on domestic revenue mobilisation, natural resource management, conflict prevention/ resolution and governance evaluation	> Number of policy or programme decisions taken by LIC/LMIC national governments or civil society organisations which are influenced by EGAP.	8	7
Outcome	Indicator	Target	Progress
1. increased availability of rigorous and relevant evidence informs policies and governance interventions	> Number of LIC/LMIC developing countries whose government agencies or civil society organisations attend EGAP thematic meetings, plenary meetings, or presentations of Metaketa results. / > Number of requests from LIC/LMIC country governments or civil society organisations for substantive policy or programme advice from EGAP.	14 / 15	16 / 11
2. a larger and more globally representative pool of researchers and evaluators use improved methods to generate relevant, externally valid evidence for governance interventions and policies	> Number of LIC/LMIC government agencies or civil society organisations which are influenced to improve their evaluation methods or policy by EGAP. / > Number of dissemination events on Metaketa RCTs convened in LIC/LMIC countries by LIC/LMIC based EGAP members or grantees.	3 / 7	11 / 9

The programme has exceeded 3 of its 4 outcome indicators. It has made substantial progress against the remaining outcome indicator and the impact indicator but has not fully met expectations on these two indicators. There are a couple of reasons for this; Firstly, outcome and impact indicators are more out of the control of the implementer and thus it is harder to predict in advance what a reasonable performance would be. Secondly, several of the DFID-funded Metaketas impact evaluations chose not to disseminate the baseline data of the impact evaluations, as this had potential to affect the integrity of research. The latter limited the potential of EGAP to influence country governments to date. Nonetheless the progress against the indicators proves that EGAP is able to influence policy decisions and promote better evaluation methods in low income countries (LICs) or middle income countries (MICs). One caveat to this statement: The timing of DFID Metaketa data collection means that in many cases, developing country governments will not have had time to make policy changes based on DFID Metaketa impact evaluations before the end of the project. However, we would expect solid progress against the outcome level indicator “Number of requests from LIC/LMIC (lower middle income countries) country governments or civil society organisations for substantive policy or programme advice from EGAP” by the end of the project.

Recommendation: Target for the impact level is adjusted to allow for realistic timescales.

Given the stage in the project and that DFID is the largest donor for EGAP, the review also considered EGAP’s sustainability. EGAP have secured increased funding from the other two donors to keep the network going for the next couple of years. This enables continuation of EGAP meetings and the EGAP review of research designs. EGAP will be able to further expand the network, but at the end of the DFID grant there will be some constraints on the extent of this expansion. At the end of the DFID grant, if no additional funds are secured the EGAP network will be managing less research than currently. EGAP are addressing the situation appropriately, talking to a range of possible funders. One of the existing funders is paying for a consultancy to explore future funding opportunities further. Building the right links between EGAP and DFID’s governance research, policy and programming areas will help EGAP to be positioned appropriately, where their capabilities match DFID’s needs. They are also an appropriate organisation to implement key areas of DFID’s evaluation strategy as they have a comparative advantage in thematic evaluation and expertise in trialling.

Explain major changes to the logframe in the past year

The logframe has not been changed in the past year.

Describe any planned changes to the logframe as a result of this review

There are a number of recommendations to improve the logframe as follows:
- Output 1: Review the indicator target for online views to make it more stretching.
- Output 1: Add an indicator “Positive feedback on EGAP studies from relevant government and civil society organisations interviewed for the Annual Reviews.”
- Output 2: EGAP and DFID revise the logframe indicators to allow for earlier delays in signing the accountable grant and to incentivise maximum dissemination.
- Impact: Target for impact level is adjusted to allow for realistic timescales.

Additionally, both EGAP and DFID agree that it would be worth improving the clarity of the definitions of some of the indicators. This will all be completed by June 2019.

## D: VALUE FOR MONEY

Assess value for money (VfM) compared to the proposition in the Business Case, based on the past year

Overall, EGAP continues to deliver value for money. Operating on a small budget, EGAP is able to deliver a substantial body of work by leveraging its network of academic members, who contribute to EGAP’s objectives at low or no cost, motivated by their professional incentives to advance evidence and methods. The EGAP training and research activities, which are funded by donors other than DFID, are highly complementary to the DFID-funded impact evaluations and serve to increase the potential for DFID-funded studies to have a broad impact.

As identified in previous annual reviews, the summary VfM model from the original business case has been extended to include specific indicators. The output and outcome indicators below largely relate to efficiency and economy. The impact indicators reflect the effectiveness of the intervention. EGAP has also sought to maximise the equity of its use of resources over the last year. Key achievements in this area include:
- In the Democratic Republic of the Congo (DRC), the EGAP taxation Metaketa team, who are working with the provincial government of Kasai Central to promote access to formal property titles in Kananga, convinced the government to randomise access to the programme and discounts in the price of land titles, leading to more equitable programme participation and distribution of discounts.
- EGAP has conducted two learning events (one in Africa and one in Latin America) for Southern researchers to workshop their research designs. These events are provided free of charge to the researchers, with all the researchers’ costs of attending being met by EGAP.
- EGAP has reviewed the membership of its board of directors to increase the representation of women and southern researchers. Under the new rules, three of the seven seats are reserved for women, and two seats are reserved for members from the Global South. Because of these changes, EGAP’s board now has a female majority membership for the first time since EGAP’s inception.

Roughly 68% of DFID funds (£3.4m) pay for the costs of Metaketa impact evaluations. 24% (£1.2m) contributes to the salaries and expenses of the executive secretariat. The secretariat oversees contracting, project management, financial management, compliance, monitoring and dissemination. 8% of DFID funding (£0.4m) pays for use of University of California, Berkeley (UC Berkeley) offices, facilities and administrative systems.

Indicator	Status
Output: efficient and timely delivery of high-quality evaluation, methods and policy influencing
Study Costs: Average cost per impact evaluation < $275,000.	The total cost of the 17 DFID-funded studies is $3,688,355, with an average cost of $216,961. This includes a relatively small number of asset purchases ($89,805 or £63,243 across all studies).
Management Costs: Funding multiple thematic impact evaluation portfolios using a single agency distributes costs of overheads associated with each portfolio/study.	DFID funds 60% of secretariat costs. This is roughly 24% of total DFID spend.
Indirect Costs: Indirect costs are waived for all subgrants, except where they add to capacity building goals.	Achieved on 13 of 17 studies
Travel Costs: EGAP maximises travel budget and hold sub-grantees to agreed travel budgets.	EGAP comply with UC Berkeley travel and accommodation policies, keeping costs to a minimum.
No Cost Inputs: Inputs supplied at no cost by EGAP members, including selection of studies, support to southern researchers, drafting of materials, dissemination.	At least $160,500 of time supplied at no cost by EGAP steering committee members in 2018/19 on workshops, writing drafts, discussions, troubleshooting issues, overseeing interventions and meta- analysis publications. This represents over 1000 hours of work.
Outcome: Uptake of operationally useful evidence so that DFID and partners can invest in effective interventions and withdraw from interventions that are ineffective.
Research Production: EGAP delivers on logframe targets for publications and research. Funding academic sub-grantees allows EGAP to leverage their data management, publication and other infrastructures, and frees space for meta-analysis and other research activities.	EGAP is delivering on all logframe targets for publications and research.
Management costs: Working via UC Berkeley allows EGAP to use UC Berkeley financial systems, procedures, policies, facilities and infrastructure at 8% indirect cost to DFID.	Aggregated UC Berkeley overhead rate is 57%. A waiver is used to accept the lower rate of 8% for EGAP (£369,593).
Use of other funds: DFID provided financing provides leverage to bring in other, external sources of funds, which upscale EGAP's ability to deliver training, research and methodological innovation	EGAP secured increase in its non- DFID funding, this allowed them to launch a new Metaketa. Whilst DFID does not fund any of this Metaketa they do directly benefit from it.
Impact: Evidence produced should contribute to improved poverty reduction and peace and justice globally. The associated cost savings and efficiency gains will deliver improved value for money for development investments by DFID and partners.
Relevance of outputs: EGAP selects studies with clear demand side links, continues to build these, and targets training and outreach to potential users of studies and/or meta-analysis.	EGAP have selected studies where there is demand for evidence both globally and in-country. Policy engagement and outreach has been targeted at relevant users (i.e. in-country users or Global South researchers).
Quality of outputs: EGAP hires a highly-skilled research team and selection panels, funds studies with good quality teams and research designs, and final studies are considered for publication in peer-reviewed journals.	EGAP have an experienced secretariat based at UC Berkeley, and highly qualified academics leading each individual study and sitting on each of the three steering committees. A book has been written on the original Metaketa, this is in production and is due to be published June 2019.
Innovation of outputs: EGAP has put in place the foundation for innovative meta-analyses of their studies.	All three of the overall Metaketa studies have had their methodologies pre-registered, as has all the individual studies.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The programme continues to deliver good value for money for DFID and the global development community. Many of the indicators in the logframe have not only been met but greatly exceeded. Many of the deliverables in the logframe and EGAP outputs overall, are not incentivised by financial reward but by academic reputation and advancement of research methods, as well as the intrinsic motivation of many members of EGAP to producing impactful research. The programme relies on these incentives to achieve good value for money. The analysis in the previous section shows that EGAP performs strongly against a range of VFM indicators covering economy, efficiency, effectiveness and equity.

In future years the EGAP programme should continue to deliver value for money for DFID and the global development community. There is evidence of uptake from the first Metaketa study and from EGAP’s tracking of early policy engagement on the DFID-funded Metaketas that indicates that if the 3 DFID-funded Metaketas are successful, they will lead to more effective and efficient governance programming, through the use of improved evidence generated in this programme.

The outputs and impacts from EGAP will demonstrate DFID’s commitment to become a world-class commissioner and user of evidence to drive improved value for money and development impact.
E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The programme is considered to be a major risk before mitigation. With the mitigation in place it is a moderate risk. The mitigated results are shown in the table below.

External Context	Major
Delivery	Major
Operational	Moderate
Safeguards	Moderate
Fiduciary	Moderate
Reputational	Moderate
Residual Risk Score	Moderate

Key risks and mitigations are as follows:

- Context: EGAP is conducting research on sensitive topics in developing countries and often in fragile and conflict affected states. The risk that external events and security issues prevent studies being delivered as planned remains major. EGAP sub-awardees have mitigated this partially by building relationships with local authorities, and with in-country DFID and UK government staff to facilitate the smooth running of the interventions.
- Delivery: The key risk is that the Metaketa studies do not complete in time to allow for good quality analysis and dissemination. From discussions with the Metaketa chairs, the majority of studies are on track to complete on time, with two exceptions where contextual issues have delayed data collection. EGAP has provided DFID with delivery plans and mitigation strategies for all delayed studies. EGAP has furthermore drafted full pre-analysis plans and is working on coding for all studies. The chairs have also drafted articles using simulated data to ensure that publications can be completed and submitted rapidly once data collection and analysis is complete. Nevertheless, major risks remain to all sub-grantees implementing their research as per plan. As EGAP plan co-ordinated analysis across groups of studies, delays on one study will delay the entire group. This risk is concentrated in the policing Metaketa, which has riskier studies, many of which have tight timelines.
- Operational: The six month no-cost extension granted to EGAP in 2017 required extending the time for which the EGAP secretariat is funded. This has cut funds available to manage exchange rate risk or other unforeseen circumstances. Mitigating this, 70% of funds are now disbursed. Staffing challenges in DFID’s Evaluation Unit have resulted in a high turnover of Senior Responsible Owners (SROs) and programme management for the programme in the last year and insufficient SRO time to maximise the full potential of the EGAP network. DFID staffing levels have now increased, and the SRO is working with the DFID team leader to ensure the team’s workforce plans provide sufficient staffing capacity to ensure EGAPs needs are met. The risk level remains moderate.
- Safeguards: All studies have been approved by relevant University and country ethics boards, and EGAP holds copies of these approvals. DFID and EGAP have agreed a standardised and clear process for reporting ethical breaches and issues and written this into sub-awards. DFID has completed Overseas Security & Justice Assessments (OSJA) on all studies for which these were required, which examined safeguards against human rights violations of persons involved in EGAP evaluations. Studies employ additional safeguards as required. Given, however, the fragile contexts in which many of the studies operate, and sensitive nature of the topics being researched, the risk level remains moderate.
- Fiduciary: EGAP utilises UC Berkeley systems which have been assessed through DFID’s due diligence assessment and recommendations followed up. EGAP does disperse funds through sub-grantees in countries where there is a high risk of corruption and fraud, which creates both VfM and fraud risks. To mitigate this, EGAP complete field monitoring visits and make payments in arrears on the basis of cost-checked invoices. Assets are listed and tracked, and downstream partner mapping is complete. The risk level remains moderate.
- Reputational: The Metaketa initiative uses advanced and non-tested research techniques - there is a risk that it fails to fully consolidate learning across studies or advance the external validity of knowledge within fields of study. The research studies being undertaken by Metaketas have been chosen to be of intrinsic interest, with the intention that they have good prospects for uptake individually. EGAP have past experience of consolidation of studies from their first Metaketa, and a range of policy actors have already expressed interest in the results of the studies. The risk level remains moderate.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

Delivery

The performance of EGAP has been good through the review period. To supplement DFID’s views, feedback was solicited from EGAP members about the performance of the EGAP secretariat. This was universally positive. EGAP regularly conduct membership surveys, asking for feedback and making changes based on this feedback.

Staffing challenges in DFID’s Evaluation Unit have resulted in a high turnover of SROs and programme management for the programme in the last year and insufficient SRO time. This has constrained DFID’s ability to maximise the full potential of the EGAP network and to work with EGAP to implement all the Annual Review recommendations. This was reflected in the feedback received during the Annual Review from EGAP, where the management gap was described as “loosening the connections between EGAP and DFID”. Now the staffing challenges have mostly been addressed, EGAP and DFID are rebuilding the connections.

The other current EGAP funders were contacted as part of the review. Both expressed a desire to have regular contact, every 2-3 months.

Recommendation: DFID ensures regular catch up meetings with the other funders, commencing by June 2019.

Financial reporting & management

EGAP have submitted quarterly narrative financial reports, and an annual report as part of this review process. Narrative updates are of good quality. EGAP have shared their Gannt chart of studies with DFID, with this alongside the monthly communication means that forecasting is improving. There are still small errors in the requests. These are transcript errors from the detailed excel sheet that EGAP are now using.

EGAP have compiled asset registers and hold spot checks, they have also started to think about the disposal of assets come the end of the studies. EGAP have sought advice from DFID in relation to this. EGAP have also completed a full delivery chain mapping for each study and submitted to DFID.

EGAP complies with UC Berkeley financial management and anti-fraud procedures, in addition to DFID requirements laid out in the Accountable Grant agreement. DFID due diligence before the programme began judged that UC Berkeley has appropriate governance structures and policies in place for managing, reporting and investigating fraud, bribery and corruption. As recorded in the due diligence assessment, this programme does not have its own set of audited financial statements. EGAP’s finances are included in the audited accounts of UC Berkeley.

Date of last narrative financial report(s)	January 2019
Date of last audited annual statement (s)	UC Berkeley Annual Financial Report 2017/18

G: MONITORING, EVIDENCE & LEARNING

Monitoring

EGAP secretariat have maintained an overview of progress this year through regular conversations with sub-awardee research teams and a number of site visits. Reporting on output level logframe targets is gathered through documentation generated by researchers, records and databases kept by the EGAP secretariat, and monitoring activity on EGAP’s website. Reporting on outcome and impact level logframe targets is based on information gathered from research teams. They are asked to report details of meetings held and policy processes in which they are involved. EGAP maintain a repository of this information, and have been drafting “stories of change”, based on policy influence observed so far.

DFID monitors progress through quarterly management meetings, with additional meetings as required. EGAP submit narrative progress and financial reports ahead of management meetings, allowing for active discussion of progress. For this Annual Review, DFID conducted a document review, interviews with EGAP’s Directors and Secretariat, the committee chair for each Metaketa, the lead researchers on three randomly selected impact evaluations (one per Metaketa), stakeholders involved with EGAP impact evaluations and other EGAP events, potential users of EGAP expertise in DFID and other UK government departments and with representatives for other EGAP funders. Two members of the review team attended the Washington DC EGAP event, the new SRO had also attended part of an EGAP event in The Hague. Attendance enabled many further informal discussions with a range of EGAP members. The review was conducted by the new DFID Senior Responsible Owner, Evaluation Unit’s Influence and Use Manager and DFID’s programme manager. It was quality assured by the Head of Evaluation Unit and Head of Evidence Department

Evidence

EGAP are actively learning from experience to date on Metaketa 1 and from their experience of building a network and practitioner relationships, as shown by the changes they have been implementing (for example more preplanning for the meta-analysis, adding the policy day to EGAP events and more strategic thinking about the location of EGAP events).

EGAP have conducted a study of the effectiveness of social science evidence to change policy makers beliefs about the impact of a policy or intervention. This study used a robust, experimental design. EGAP researchers presented to a group of Washington D.C.-based policy practitioners at an EGAP organised Evidence Summit. The participants were presented with the findings of (i) a single study from Metaketa 1, (ii) a meta-analysis from Metaketa 1, (iii) an observational study focused on the same theoretical question and (iv) a placebo. Taking repeated survey measurements, the study estimated how this changed policy makers’ ability to predict the results of a similar intervention and how it affected their views on a hypothetical spending decision to put money into a similar intervention. Policy makers proved responsive to evidence, according weight to the meta-analysis results. Moreover, the extent of changes in policy makers’ views proved by the experiment is a positive indicator that exposure to Metaketa findings can have downstream consequences on practitioners’ decisions. This supports EGAP’s theory of change that evidence can improve decisions made by development practitioners.

Learning

EGAP have significant expertise on conducting a Metaketa; some of this expertise is being collated and published as part of a book. It would also be worth considering what could be added to the methods resources on the EGAP website.

EGAP are conducting a policy influence study, aiming to better understand how policymakers use research in their work. This work is one of the deliverables in output 1. Once the survey is analysed, both DFID and EGAP can use the results to refine their approach to promoting the use of evidence in policy making.

A key learning aim for the programme for the coming year is to ensure that DFID and many stakeholders are gaining the most from the results of the Metaketa 2-4. The recommendations in the review are aimed at maximising this.

Progress on recommendations from previous reviews

EGAP to continue to focus on project management, timelines, and prioritise pre-analysis throughout the year to avoid delays. EGAP produced a comprehensive workplan detailing all project activities planned through to Metaketa publication. Clear evidence was seen through quarterly discussions, regular updates from the EGAP secretariat and through the review that EGAP are managing the Metaketa timelines well and prioritising pre-analysis.

Update the overall EGAP theory of change and revise the logframe to better reflect DFID-funded activities, outputs, and intended outcomes, by July 2018. This work was not completed due to the DFID staffing shortages. Key changes to the logframe are articulated in this Annual Review.

The theory of change being implemented has changed since the business case. EGAP’s plans about how to reach out to practitioners and increase membership from the Global South has developed. In particular, some of the plans articulated in the business case are being funded by other funders, and so plans depend on agreements between EGAP and the other funders. The changes in the theory of change have not been codified in a document.

EGAP to conduct a review of activities to produce a holistic plan that combines the revised theory of change (above), with the influence and usage strategy, by October 2018. EGAP have produced a dissemination calendar that outlines planned dates for the publication of reports, and dates of seminars, Learning Days, and other outreach or external events; They have not conducted a) stakeholder mapping that identifies EGAP audiences and attributes EGAP activities to their intended audiences (e.g. EGAP members, policymakers in countries or institutions, donors, development partners, or researchers in the Global South), b) an analysis of alignment between EGAP and DFID (and other donor) objectives to identify common areas or gaps; and c) success criteria that identify intended outcomes or impacts of activities and how they will be assessed. The recommendation is that EGAP does this across its broader portfolio rather than for DFID-funded activities only. Key areas to be addressed are included in the recommendations of this years’ annual review.

DFID to consider ways to improve evidence and knowledge sharing with EGAP by end July 2018. This work was not completed to deadline due the DFID staffing shortages. Initial ideas have been collected through this annual review as articulated in Output 1 and 4.

EGAP to define objectives and strategy for engaging with Global South, by October 2018. Progress on this is addressed under recommendation 3 above and in output 4.

EGAP and DFID should develop equity VfM measures by July 2018. EGAP has not developed formal equity VFM measures but has taken a range of steps to ensure better equity both within EGAP itself or promoting equity through its research.