Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA) – Phase 1 & 2
Programme Value: £50m		Review Date: October 2014
Programme Code: 200706	Start Date: 01/10/2010	End Date: 31/12/2018

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	A	A	A
Risk Rating	Low	Low	Medium

Summary of progress and lessons learnt since last review
The project has delivered 29.1 million treatments by September 2014 across the eight Phase 1 countries. Mapping has been completed in all Phase 1 countries with the exception of Liberia due to the Ebola outbreak which has resulted in temporary curtailment of Neglected Tropical Diseases (NTD) activities. There has been progress in collecting baseline data for the new indicators in Phase 2.
Following the previous annual review which made recommendations on strengthening management there has been a strong focus on improving management including financial management. New more robust processes have been designed and have started to be implemented. There has also been a needs assessment done with each of the countries to better understand their requirements, this was also a recommendation of the last annual review. These new processes are being used across both the Schistosomiasis Control Initiative (SCI) based at Imperial College and the Centre for Neglected Tropical Diseases (CNTD) based at Liverpool School of Tropical Medicine who manage the programme in three countries (Liberia, Mozambique and Zambia). Phase 2 is costed extension which started in June 2014 and treatments are scheduled to start in both DRC and Ethiopia (Phase 2 countries) this year. In Phase 2 there is stronger emphasis on monitoring with additional indicators. This programme is also making a significant contribution to developing new knowledge on how best to reach elimination of schistosomiasis as a public health problem. Key lessons learnt over the last year include the importance of ensuring programmes reach the most marginalised, the programme is doing some analytic work to understand the reasons for the very low coverage in out of school children and will develop plans to improve access by this vulnerable group. Another lesson has been the importance of measuring validated coverage in addition to reported coverage.

Summary of recommendations for the next year

The project will need to ensure compliance with the new financial systems being rolled out. There is a need to continue to strengthen management and to expedite the recruitment of a senior financial manager.

Developing and piloting approaches on increasing access by out of school children must be a priority given the very low coverage in out of school children.

There needs to be stronger progress on VFM including recruitment of VFM lead who will be supported by a health economist.

In general the programme should follow WHO technical guidance where this is available. Where the evidence base for the guidance is weak, the programme needs to have a process for resolving differences with WHO in a timely manner.

There should be an external review in 2015 with a particular focus on management including financial management and value for money. This will allow sufficient time for any recommendations from the review to be implmented by the programme.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-200706/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-200706/

Outline of the programme

DFID is providing £50 million from FY 2010/11- FY 18/19 to deliver treatments for Schistosomiasis (SCH) and Intestinal Helminths in 10 countries in sub Saharan Africa. Of the £50 million, £22.9 million is allocated to Crown Agents largely for the procurement of praziquantel (PZQ) but also some other commodities which include vehicles and laboratory testing equipment. Phase 1 was for £25m with a further £25m agreed for Phase 2. Phase 2 will add 127 million treatments to the 76 million supported by Phase 1 funding, giving a total of 203 million treatments over the total period of DFID support. This increased number of treatments delivered under Phase 2 is largely due to the increased donation of praziquantel (PZQ) resulting in the programme having to purchase less PZQ and some economies of scale. The contract for Phase 2 was signed in June 2014. The funds to the Schistosomiasis Control Initiative (SCI) at Imperial College include funds for disease mapping, developing annual work plans, training staff at different levels of the health system, delivering mass drug administration (MDA) in countries and monitoring process, performance and health impact.
Schistosomiasis is a debilitating parasitic disease caused by flukes of the genus Schistosoma. It is a chronic illness that damages internal organs, with morbidity directly related to worm burden, affecting over 200 million people in developing countries. According to the World Health Organization (WHO), Africa accounts for nearly 90% of the global burden of disease. Soil transmitted Helminths (STH), commonly known as intestinal worms, affect a large number of people, perhaps over 2 billion worldwide, and have an insidious effect on health. Schistosomiasis along with other neglected tropical diseases (NTDs) disproportionately affects the poorest people living in rural areas, and perpetuates their poverty through the disability they cause. The control and elimination of Schistosomiasis in the long term requires an improvement in environmental conditions especially water and sanitation. However in the short to medium term, WHO recommends chemotherapy with praziquantel as the most cost-effective means of control. A child can be given praziquantel, a safe and effective drug, at a cost of between US$ 0.20–0.30. WHO recommends that school aged children receive a total of 2 treatments in low risk areas, 5 treatments in moderate risk areas and 10 treatments in high risk areas. Ideally treatments should be given annually in high risk areas but less often in lower risk areas. Treatment for schistosomiasis at regular intervals benefits the individuals treated and also, once adequate coverage is achieved, reduces the transmissibility of the disease so that new cases are reduced. Because STH commonly occur alongside Schistosomiasis, it is more efficient to treat both together. STH are normally treated annually with albendazole, which is donated.
The UK support focuses on mass administration (MDA) of drugs to children of school age and high risk adults (whose work involves contact with fresh water or who reside in highly endemic areas). Key factors in national success for achieving schistosomiasis reduction include political commitment, strong planning and execution of plans for mass drug administration, the availability of adequate financial resources, technical capacity and monitoring and evaluation. MDA is when the entire at risk population is treated rather than diagnosing and treating individual patients.

SCI has subcontracted the Centre for Neglected Tropical Diseases (CNTD) to deliver the programme in 3 countries. SCI and CNTD work with the governments of ten sub-Saharan African countries to support implementation of their drug distribution programmes and the collection of essential monitoring and evaluation data. Each of the countries falls into one of three groups which encompass their position with respect to NTD control prior to the commencement of the programme:
Group 1: Cote D’Ivoire, Liberia, DRC, Ethiopia and Malawi had little, if any, history of treatment of NTDs. The project is supporting the governments to develop a control programme, map the distribution of infection and commence implementing MDA. DRC and Ethiopia are Phase 2 countries.
Group 2: Mozambique, Tanzania and Zambia had existing NTD control programmes but require scale up of treatment across the country into previously untargeted areas.
Group 3: Niger and Uganda have had an NTD control programme implementing MDA for several years and their strategy is now focussed on sustaining the control of schistosomiasis morbidity and, in certain areas, to move towards elimination of SCH as a public health problem. This will provide lessons for other African countries as Schistosomiasis control moves forward. Zanzibar also falls into this category.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The impact will be a reduction in morbidity and mortality. In particular treating children has a longer term impact - reducing their susceptibility to re-infection and morbidity in later years. The programme will also develop robust evidence of appropriate strategies to move towards elimination of schistosomiasis contributing to the global goal to eliminate schistosomiasis as a public health problem by 2025.

Indicator 1: Mean intensity of infection will be reduced by at least 65% thereby reducing illness due to infection and preventing future illness. There will also be a 25% reduction of infection in untreated children due to reduction in transmission.

Indicator 2: Validated treatment coverage in school aged children (disagregated by gender) by country. Target for December 2014: At least 70%

Validated coverage is a new phase 2 indicator and results are still not available for all countries. The target of 70% has been met in Cote d’Ivoire, Malawi and Zanzibar but not in Uganda where validated coverage is very low at only 36%. Validated coverage levels in both males and females is similar in all countries.

The outcome is to contribute to the global strategic plan for SCH (2012-2020) by providing a total of 203.5m treatments over Phase 1 and 2. The main programme activities (mapping to determine the geographic spread of the disease, training, logistic support, drugs and equipment procured) are all necessary intermediate steps to ensure treatment uptake, which is the main programme outcome.

Indicator : Number of treatment delivered in millions (cumulative). Target for December 2014: 44m treaments. 29.1 million treatments have been delivered by September 2014.

The programme estimate that the target of 44m treatments by December 2014 will only be met by March 2015. There were considerable delays in procurement of PZQ initially due to the need to go through the WHO Expert Review Panel to ensure the procurement of quality PZQ. The programme has overcome initial procurement difficulties and treatments are now picking up. However there will need to be a rapid scale up of treatments to meet the target of 203.5m treatments by 2018. The programme are optimistic that they can meet the target now that the mapping is largely complete and treatment will be starting in the two new Phase 2 countries.

Overall output score and description
A
Mapping which was a major focus of previous years has largely been completed in all Phase 1 countries except Liberia due to the outbreak of Ebola. Quality drugs are being delivered to countries in a timely manner. Treatments are continuing to increase though the programme remains heavily reliant on two Phase 1 countries (Mozambique and Malawi ) and on Ethiopia in Phase 2 for reaching the target. Strong monitoring and evaluation (M and E) sytems have been put in place including to measure impact. Baseline data for Phase 2 indicators are being collected. Treatment coverage levels in out of school children which is a new Phase 2 indicator remains very low and strategies will need to be developed to address this. Analytic work is planned to better understand the reasons for the low coverage which can then be addressed. There is also work ongoing on increasing the evidence base for achieving elimination as a public health problem in some areas.

Key lessons

Programmatic

The expectation in Phase 1 that treatments would increase sharply in all countries was not realistic. There was a slow start up in many countries and there were initial delays in procurement largely due to the the time taken by suppliers to submit data required by the WHO Expert Review Panel which assesses the quality of medicines.

Need to focus on the most vulnerable. Coverage in out of school children is extremely low and there is a need to increase the evidence base on how best to improve this. This is a new Phase 2 Indicator.

Need for lesson learning around elimination where the evidence base remains poor. This includes issues such as the frequency of treatment needed in different settings and the benefit of additional interventions.

Need to measure validated coverage and not just reported coverage, this is a new Phase 2 indicator.

Management including financial management

Need to strengthen financial and management systems and skills where small programmes are expanding rapidly and to ensure all partners use same systems

Countries requiring different level of support and support in different areas e.g. planning and financial management. Programmes must have the capacity to meet country needs in management and finance.

Key actions

	By when	Whom
Ensure compliance with the new financial systems and audits.	Jan 2014	ICOSA
Spot checks on financial systems	Dec 2014	DFID
Develop and pilot approaches to increase access for out of school children	2014/15	ICOSA
Recrutiment of senior financial manager and Value for Money staff member. The latter to be overseen by a health economist.	Jan 2015	SCI
Dissemination of lessons in a timely manner	Throughout	ICOSA
Agree way forward on market shaping activities. At present there is a lack of consensus on the level of risk and therefore what market shaping activities are needed. This is because the programme is buying less and less PZQ as the donation from Merck Serono scales up.	Dec 2014	SCI, CA, DFID
External review next year along with the review of our lymphatic filariasis project	Nov 2015	DFID and SCI

Has the logframe been updated since the last review?

The logframe has been strengthened and updated for Phase 2. This includes:
- An impact indicator on reduction in the intensity of infection, this is used as a proxy measure for ill health as it takes many years before people get ill from schistosomiasis
- Using validated coverage in addition to reported coverge as the outcome indicator.
- Disagregating some data by gender and by whether the children are in school or not.
- Inclusion of an indicator on progress towards elimination. (This is only applicable for Uganda, Niger and Zanzibar.)

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Priority areas identified through mapping of the infected populations
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y. It was 10% in Phase 1 and reduced for Phase 2 as the mapping has now largely been done.

Indicator(s)	Milestones (December 2014)	Progress
Number of country specifc mapping protocols available	8	8. All countries have mapping protocols
Targeted areas mapped for disease by country (cumulative)	100% at risk areas mapped in Phase 1 countries	98% of at risk areas mapped. / Mapping has been completed in all countries that needed it except Liberia.
Studies commissioned on impacts of climate change and on where additional interventions required	0 (Phase 2 indicator)	0

Key Points
A substantial amount of effort in the first few years of this programme was devoted to mapping. Mapping has now been completed in all Phase 1 countries except Liberia where 5 out of 15 counties have yet to be mapped. The delay is due to the Ebola outbreak and mapping will be completed once the Ministry of Health has reinstated NTD activities. Of the Phase 2 countries, Ethiopia has completed mapping and DRC is scheduled to complete integrated NTD mapping including for schistosomiasis by December 2014 (not through this programme).

Summary of responses to issues raised in previous annual reviews (where relevant)
Since the ICOSA programme has been following a slightly different protocol for mapping from that recommended by WHO, the last annual review recommended that the ICOSA programme resolve outstanding issues on mapping protocols with WHO. This has been partially resolved. There will be no further mapping through this programme apart from completing the mapping in Liberia.

The programme will however need to assess progress in the reduction in intensity of infection in each country to measure the impact of the MDA. In addition reassessment is needed to evaluate the impact of treatment in Uganda, Niger and Zanzibar to inform decisions on future treatment frequency to reach elimination. Reassessment differs from mapping because baseline mapping data already exists, usually from at least 5 years prior to reassessment and due to the focal nature of schistosomiasis reassessment can be conducted at a smaller spatial scale i.e. a subdivision of a district/province which will become the more focused implementation unit on which to base MDA. The evidence base for the most appropriate timing of reassessment and protocols for this is not well established so this programme will increase the evidence base.

Recommendations
Complete mapping in Liberia once the situation allows.
The ICOSA programme should follow WHO guidance and protocols so as to avoid countries receiving conflicting advice. Where there are sound reasons not to do this or where there are evidence gaps, there should be prompt discussion with WHO. Effort should be made to resolve any differences or where there are evidence gaps to fill these in a timely manner.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Drugs procured and delivered and market monitored
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	70%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y. Increased for Phase 2 Business case as it was felt this indicator was the strongest reflection of the outcome.

Indicator(s)	Milestones (Dec 2014)	Progress
No. of tablets delivered to countries (includes both procured wth DFID funds and donated).	143m / (including both Phase 2 and Phase 1)	127.2m procured and delivered to countries by Crown Agents to date with a further 12.4m scheduled for delivery by Dec 2014. / 17.5m donated tablets delivered to countries. / Total 157m delivered by Dec 2014.
Number of countries implementing Mass Drug Administrations according to National Strategic Plans	8	8 All Phase 1 countries are implementing mass drug administration according to National strategic plans. Treatment has started in Liberia but it now on hold.
DFID (along with other partners) will monitor and contribute to the effective management of the market for PZQ. New indicator for Phase 2 which will be more clearly defined following initial work	New indicator for Phase 2.	Discussions on how best to take this forward are ongoing. Initial work is planned.

Key Points
Crown Agents continue to procure and deliver PZQ to countries as requested by SCI/CNTD. Only two sources of PZQ were technically acceptable to the WHO Expert Review Panel. One manufacturers costs had been substiantially lower than the other so the programme has largely purchased PZQ from a single source. The price of PZQ has increased by 25% since the start of the programme. The difference in price of PZQ between the two manufacturers is now smaller which could allow for more competition in future. There remain different opinions on what level of market risk ICOSA is facing in terms of quality, price and supply security for PZQ given the context of a reducing commercial market as the Merck Serono donation increases and therefore what type of risk management/market-shaping mechanism needs to be put in place. ICOSA is reducing the procurement of PZQ and will increasingly use donated PZQ as the Merck Serono donation increases.
There was some overordering of PZQ. In Tanzania 10m tablets were delivered in April 2014 anticipating treatment during 2014, the MDA was then postponed and these tablets will now be used in 2015. A total of 48m tablets have been delivered to Mozambique through the ICOSA programme. Of this 25m have been used and the remaining 23m will be used in 2015. This was a result of Mozambique originally planning to treat both school aged children and high risk adults and later changing plans to only treat school aged children at this stage.

Summary of responses to issues raised in previous annual reviews (where relevant)
There was a recommendation that Crown Agents (CA) inform suppliers of the new opportunities under Phase 2. CA have contacted 25 potential suppliers of PZQ informing them of the increased market for PZQ under Phase 2 of this programme. They have informed potential suppliers that WHO will now carry out prequalification (PQ) for PZQ and have explained the process and the requirements for this. The process of full assessment for PQ is expected to take about 20 months. The earliest PQ approval is not expected until mid 2015. (There has only been one submission for PQ status with full documentation to date).

Recommendations
Programme managers need to ensure rigour in estimating the PZQ requirements and to be in close contact with NTD managers over plans for MDA. The programme has made arrangements to ensure that drugs are appropriately stored and used prior to their expiry and that there is no further excess ordering.

The Schistosomiasis Control Initiative (SCI), Crown Agents and DFID including the Access to Medicines team will determine how best to take forward market shaping activities. An initial assessment is planned.
C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	National programmes using monitoring and evaluation results to refine strategies
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (December 2014)	Progress
Percentage of targeted districts submitting reports 90 days after MDA by country	Baseline:Cote d’Ivoire (2014): 100% / Liberia (2014): 100% / Malawi (2014): 50% / Mozambique (2014): 100% / Niger (2014): 16% / Tanzania (2014): 70% / Uganda (2014): 80% / Zambia pending	Phase 2 indicator
Validated coverage of children not in school, by gender	BaselineMalawi: M 15.5% F 14.8% / Uganda: M 1% F 5.5%	Phase 2 indicator
Percentage of population with heavy infections	Baseline / Cote d’Ivoire: Sh 2.0% Sm 2.0% / Liberia: Sh 9.3 Sm 0.2% / Malawi: Sh 1% Sm 0.1% / Tanzania: Sh 7% Sm 4.1% / Zambia: Sh 2% S m.1% / (Sm- Schistosoma mansoni, / Sh- Schistosoma haematobium)	Phase 2 indicator

Key Points
Timely reporting: Reporting has been very delayed in Niger. To address this the MOH plan to hold meetings in each district to discuss and validate the data following the next MDA. A USAID funded programme is also working with the ministry to identify problems and strengthen reporting.

Coverage in out of school children is extremely low. ICOSA is conducting qualitiative surveys to better understand the barriers to uptake by out of school children. Examples of this include: Malawi: strengthened Information, Education and Communication campaigns in collaboration with Save the Children. Cote d’Ivoire: In-depth interviews with the Community Health Workers conducted in September 2014. Uganda: A combination of in-depth interviews with school teachers and community drug distributors and focus group discussions with families and out of school children. Validated coverage surveys will be conducted every 2-3 years depending on frequency of treatment.

Percentage of the population with heavy infections: Those with heavy infections are most likely to suffer from morbidity, WHO guidance is that where less than 5% of the population have heavy intensity infections, control of morbidity will have been achieved in the target population.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A as these are Phase 2 indicators.

Recommendations
The data indicates that coverage in out of school children is extremely low. Building on the planned qualitiative surveys, ICOSA needs to support countries to develop their approach to reach these vulnerable children. This will include expanding links with other organisations working with communities and out of school children. The programme needs to finish collecting baseline data on children not in school. The logframe indicators will need to be revised as the expectation was that the baseline would be about 50%

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Development of strategies for the elimination of SCH as a public health problem in Zanzibar, Niger and Uganda
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Dec 2014)	Progress
Transmission hotspots (areas with persisitent tranmission) treated with adjusted preventive chemotherapy (PCT)	70% hotspots treated by Preventive Chemotherapy (PCT)	Niger 100% / Uganda 54% / Zanzibar 100%
Percentage of population with heavy infection	Post 1 round of PCT 25% reduction for both S.h and S.m.	Baseline: Uganda (2013): Sm 0.8% / (There is no significant Sh in Uganda) / Baseline: Zanzibar (2012): / Sh Pemba 3.65%; Unguja 0.68% / (There is no Sm in Zanzibar) / % reduction from baseline (2014): / Unguja island– 13.2% / Pemba island – 52.9%

Key Points
Transmission hotspots: This indicator was selected for Phase 2 as it will indicate progress towards elimination. As there are still evidence gaps in this area it will also help to determine optimal approaches to elimination. Niger, Uganda and Zanzibar have been doing MDA for a number of years and there is potential to reach elimination as a public health problem in some areas. WHO recommends that a prevalence of less than 1% of heavily infected individuals is required to achieve elimination as a public health problem.
Niger Though there is a substantial lag in reporting the programme is confident that there is 100% coverage of transmission hotspots as there is strong in-country supervision. In addition the ICOSA programme manager has recently visited Niger and visually inspected district treatment reports from the 2014 treatment campaign. A coverage survey will be conducted following the next round of MDA.
Uganda Coverage in Uganda is low, this is a mature programme that has been running for many years. Uganda previously had a high burden of disease with many deaths from schistosomiasis and this is now much reduced. We need to understand why coverage in Uganda is is so low. Reasons for this could include treatment fatigue in communities where people have had several rounds of treatment and are no longer seeing the symptoms of schistosomiasis as well as poor performance by the programme.

Heavily infections: Though Uganda has only just started following the elimination strategy the percentage of the population with heavy intensity infections in hotspots is very low and already within the WHO guidance on achieving elimination as a public health problem. ICOSA will continue to monitor the impact of treatment to determine if heavy intensity infections below 1% are being maintained and/or decreased with supplemental studies looking at impact on prevalence and intensity of infection with increased frequency of treatment. The programme in Zanzibar is part of a larger research programme funded by the BMGF to eliminate schistosomiasis as a public health problem. ICOSA is supporting treatment on a bi-annual basis, utilising donated PZQ. The research component is addressing whether other interventions, including mollusciciding, are having an additional impact on prevalence and intensity of disease beyond MDA alone. The review in June 2014 observed that the MDA is maintaining the prevalence of infection at low levels however it indicates little benefit of the additional interventions. This may be an indication of how difficult it is to drive prevalence to 0% and/or of the limits of our diagnostic tools to discern differences in low prevalence, low intensity infection areas. A coverage survey is planned after the next MDA round.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
To determine the reasons for the low coverage in Uganda ICOSA is conducting in-depth interviews with school teachers and community drug distributors and holding focus group discussions with families and children (both in school and out of school). They will also need to strengthen any weaknesses that are identified in the programme.

It is important for the ICOSA programme to share experience and dissesminate any lessons learnt on elimination as a public health problem to countries, WHO and other stakeholders.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Lower cost per treatment achieved
Output number per LF		5	Output Score	B
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones (Dec 2014)	Progress
Number of countries with financial cost per treatment determined	6	8. Costs determined in all Phase 1 countries. / Cote d’Ivoire: £0.28 / Liberia: £0.31 / Malawi: £0.12 / Mozambique: £0.04 / Niger: £0.17 / Tanzania: £0.45 / Uganda: £0.27 / Zambia: £0.27 / Zanzibar: £0.08
Direct financial cost per treatment by country (Indicator revised for Phase 2)	4 countries achieving reduced costs from baseline	Unable to compare costs due to lack of standardised processs

Key Points
The programme had not been using standardised templates to collect data on the cost per treatment for all countries, therefore, it has not been possible to compare costs per treatment. New systems to collect data on costs have now been put in place across all ICOSA countries so that costs over time and between countries can be compared in future. There is considerable variation in the costs per treatment by country, this is often related to the per diems paid during training of supervisors, teachers and community health workers.

The programme has now identified the indicators and started collecting data against economy, efficiency and effectiveness. Due the programmes difficulty in filling the health economist/value for money post progress has been slower than expected.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous review identified that the process for collecting costs was an intensive research approach, rather than to using less labour-intensive and more sustainable accounting and financial management procedures. ICOSA will now employ a person with accountancy skills who will be overseen by a health economist from within Imperial College.

Recommendations
These calculations on cost per treatment only refer to DFID costs. Working with others, ICOSA needs to establish the cost per treatment including all sources of funding, whether domestic or other donor costs.
There need to be plans to have discussions with countries to look at the costs and see where efficiences can be made. Recruitment of the value for money officer needs to be expedited.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
KEY COST DRIVERS	Expenditure Location	Budget Lines include:	Expenditure by March 2014
1. Commodities	UK-based / (by Crown Agents)	Procurement and delivery of Praziquantel (88% of budget)	£8,405,560
		Vehicles
		IT equipment (desktop computers, scanners, printers)
		Laboratory Equipment (Microscopes, HemoCue machines)
		Laboratory Consumables (urine filters, microcuvettes, Kato Katz supplies)
2. Programme Expenses / (all MDA and M&E activities)	Country-based / (by recipient governments)	Training (Staff, teacher, volunteer, supervisor) (>50% budget)*	£4,083,629
		Treatment delivery (>20% budget)*
		Information, Education and Communication (IEC) strategies
		Drug Logistics
		Supervision
		Social mobilisation
3. Management including financial	UK-based / (by SCI and CNTD)	Management Personnel	£734,849
		Management Travel and associated costs
4. Technical (includes support for mapping, MDA and / M and E)	UK and Country-based / (by SCI and CNTD)	Technical Personnel	£1,941,791
		Technical Travel and associated costs
		Short-term technical assistance

VfM performance compared to the original VfM proposition in the business case
The assumptions in the Phase 2 business case continue to be met. The key value for money measure in this programme is the cost per treatment delivered. The programme is monitoring cost per treatment and will compare costs of treatment between countries. Costs of delivery in the first year(s) are estimated 30% higher than in subsequent years, as a result of the initial investment required. As treatment is scaled up in Phase 1 countries, the programme should now benefit from economies of scale such that cost per person treated should reduce. Costs are being disaggregated to provide information on the key cost drivers within the programmes, these need to be analysed to look at where improvements can be made.

A matrix on indicators on VfM has been developed but has not really be used to inform the programme. The programme needs to start using the VfM information to improve performance. DFID funded NTD programmes that include mass drug administration are looking at how and where it may be possible to combine resources and integrate programmes to increase value for money.

VFM Criteria	VFM Metric
Economy	Cost of inputs (staff, per diems, fuel, raw materials etc.) as % of total MDA cost		Fuel & transport		Materials & services		Per Diems
		Liberia	19%		30%		51%
		Cote d’Ivoire	16%		47%		36%
		Mozambique	36%		3%		55%
Efficiency	Number of treatments – number of individuals being treated through ICOSA / (cumulative to date 29.15m)	FY2		FY3		FY4		FY5
		6,236,503		5,961,654		11,844,171		5,105,753* / *reported by end Sep 2014
	Geographic coverage percentage of endemic administrative units where Preventive Chemotherapy is implemented			FY2		FY3		FY4
		Cote d’Ivoire		18%		18%		28%
		Liberia		0		0		27%
		Malawi		64%		100%		100%
		Mozambique		48%		48%		100%
		Niger		100%		100%		100%
		Tanzania		0%		0%		5%
		Uganda		0%		0%		33%
		Zambia		0%		0%		60%
	Cost per person treated	Baseline / Cote d’Ivoire: £0.28 / Malawi: £0.12 / Mozambique: £0.04 / Niger: £0.17 / Tanzania: £0.45 / Uganda: £0.27 / Zambia: £0.27 / Zanzibar: £0.08
	Targeted areas mapped for disease by country / costs of activity	Liberia: £3,825/district mapped / Zambia: £3,579/district mapped / Malawi: £5,124/district mapped
Effectiveness	Disease prevalence reduction / costs of programme
	Validated coverage of targeted population (by age range, gender, in school, not in school) / costs of programme
	Total number of DALYs averted
	DALYs (by country) / costs of programme

The costs in this table refer only to DFID costs.

Assessment of whether the programme continues to represent value for money
Yes, the programme continues to represent good value for money at an average cost of £0.22 per treatment. The business case estimated the cost per DALY averted at £67 in economic terms and £35 in financial terms.[1] These figures are in line with, or better, than other health care interventions financed by DFID and well below well below the WHO cost-effectiveness bar of a cost/DALY at or below gross national income per capita.
[1] Financial costs include those costs funded by DFID, channelled through SCI and Crown Agents to cover programme delivery and management costs and procured goods and drugs respectively. For economic costs, the estimated government contribution of 18% is added as well as the cost of donated drugs

Quality of financial management
Following the last AR which identified the need to improve financial management the programme worked with Accenture Development Partners to redesign financial and management processes. Financial management tools have been developed for use across all ICOSA countries; this includes a standardised budget template. On a monthly basis, countries will report actual expenditure against the key budget lines with additional information on location of spend (to allow costs to be compared across districts) and a description of the cost (e.g. per diem, fuel, etc.). This expenditure will be reconciled and monitored centrally. This should also allow more accurate forecasting which has previously been weak.

The new processes are already being implemented in some countries with plans to roll out in all countries by 31st January 2015. All central staff have been trained in the new systems. Staff will routinely liaise with in-country finance managers on the reconciliation of expenditure reports and monthly finance meetings on every country are scheduled which will highlight when there is an issue or risk arising. Mitigation steps, which may include additional training or country visits, will then be planned.

The finance risks will be assessed and help guide the audit policy for each country whereby countries with a higher risk profile will require a higher percentage of their receipts to be audited by the ICOSA finance team. ICOSA is currently undertaking a programme of audits across all countries. Frequency of future audits will be depend on the results of the audit combined with the risk profile for each country.

SCI are in the process or recruiting a Senior Finance Manager.

Date of last narrative financial report	30/08/2014
Date of last audited annual statement	Not Applicable. Annual audit statement is not applicable for this type of programme.

E: RISK (½ page)

Overall risk rating: Medium. The risk has been increased due to the addition of DRC in Phase 2 and the outbreak of Ebola.

Overview of programme risk
Compliance is a risk in some areas; validated coverage has been low in Uganda which is surprising given that treatment in schools is supposed to be closely supervised by teachers who directly observe drugs being taken.
Out of school children: This indicator was added in Phase 2 to ensure that we are reaching the most vulnerable. The results indicate that the programme is not accessing these children.
Conflict affects implementation: ICOSA includes some high risk countries. There will be gradual expansion of implementation in DRC. SCI will work with the government, trusted community leaders and established NGOs to minimise disruption in case of insecurity. Within Niger, ICOSA works with an established NGO (RISEAL) to help ensure continuity of programmes.
Price and availability of quality PZQ: There is ongoing discussion on the level of risk this presents in light of the increasing donation from Merck Serono and how best to manage this risk. Initial analytic work is planned.
Delays in scaling up: Scaling up remains slow in some countries for a range of reasons. The last annual review identified the missed opportunities for advocacy and influencing. SCI support is intended to help build country capacity and overcome logistical difficulties but this is an area that requires constant monitoring.
Fraud: Financial management has been much strengthened. All large procurement is through Crown Agents who are a DFID procurement agent and have extensive experience of DFID procurement.
The Ebola outbreak in one programme countries (Liberia) represents a new risk. The possible impact of Ebola on the programme progress and mitigation measures have not been fully assessed so far.
Sustainability: There remains a risk to sustainability. The programme and DFID to continue exploring increased domestic resource contributions with beneficiary governments. The increased donation of PZQ will reduce the costs to countries.

Outstanding actions from risk assessment
A risk register for each country to identify risks and record mitigating actions is being set up. It includes both financial and programmatic risks and will be reviewed monthly.
Improving access for out of school children needs to be addressed as a priority. Qualitative surveys to better understand barriers to access are planned. In addition to community volunteers the programme will need to work with other groups/ programmes who may have better access to these children. There is a need for greater understanding on why coverage in Uganda remains so low and how best this can be improved.
Ebola Outbreak: CNTD who manage the programme in Liberia will undertake a full risk assessment of the effects of the Ebola outbreak on planned programme activities and consider mitigation measures which go beyond simply delaying activities – e.g. temporarily diverting resources into other areas.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Mass drug administration (MDA) Delivery of treatment is behind schedule and it will not be possible to meet the December 2014 target of 44m treatments. Mapping is now largely complete. ICOSA has made progress in collecting baseline data for the new Phase 2 indicators. There is ongoing work to determine the most appropriate approaches to reach elimination.

Performance of partnership (s)
The last annual review noted that the ICOSA project was not adequately meeting the different needs of countries. ICOSA has since had discussions with countries on their particular needs. In 2014, the programme supported the training of the NTD Programme and Finance managers from Malawi, Liberia and Zambia in the use of the Tool for Integrated Planning and Costing (TIPAC). There are ongoing discussions with partners on on how to support the training and use of the NTD database as a tool for planning and the Data Quality Assessment (DQA) as a tool for monitoring. Previously ICOSA had annual agreements with countries so countries were not aware of any future support which resulted in difficulties in planning. Countries are now provided with indicative funding numbers for future years. The relationship between SCI and CNTD has improved and they are now using the same systems for collecting data on progress as well as financial data. There is also increasing co-operation between ICOSA and USAID funded contractors. Following the initial delays in procurement which were outside the control of Crown Agents (CA) there has been a good relationship between CA and SCI.

Asset monitoring and control
A standardised asset register has also been created to allow ICOSA to track assets. All procurement items (excluding single use consumables) procured through Crown Agents or within country will be included in the register and regularly updated by the ICOSA finance team. In addition to providingknowledge of specific assets available for use in country this register will also assist with planning for replacement items in the future.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

There is no specific conditionality attaching to the business case.

The implementation of this programme involves close cooperation with country governments, particularly Ministries of Health and Education, who develop and implement national schistosomiasis control plans with assistance from partners. Of the 10 countries that benefit from the programme, eight are priority countires for DFID.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The theory of change and assumptions in the business case are still valid. ICOSA data should develop the evidence base on how and when to move towards elimination of schistosomiasis as a public health problem. The log frame has been strengthened for Phase 2 including indicators on impact as well as the disaggregation of data by gender.

A new indicator is the coverage of treatment in out of school children. Baseline results identify that this is currently extremely low. As a response ICOSA is undertaking qualitative work so as to increase the understanding of why coverage amongst this group is so poor and will be developing approaches to reach out of school children. Lessons on how best to reach out of school children will help to increase the very limited evidence base on this.

Another new Phase 2 indicator is monitoring of the percentage of the population with heavy intensity infections. The WHO guidelines are that control of morbidity has been achieved when ‘Prevalence of heavy-intensity infection is <5% across sentinel sites'. Cote d’Ivoire, Malawi and Zambia illustrate that the average baseline percentage of the population with heavy-intensity of infection is already below 5%. However several of the sites within these countries are not below 5%, and until they are we cannot assume that the country is ready to progress to elimination as a public health programme . ICOSA will continue to monitor these sites and will discuss treatment strategies with countries and WHO. This work will help to increase the knowledge on how and when countries can progress to the target of elimination as a public health problem as agreed at the World Health Assembly.

An indendent review will be carried out in 2015 and an independent programme evaluation is planned at the end of Phase 2 (2018).

Monitoring progress throughout the review period

Following the last annual review that identified shortcomings in management there have been regular discussions with the senior management of the project to discuss the findings of the review and the next steps in addressing the shortcomings. A joint visit by DFID and CNTD staff to Liberia was planned as part of this annual review process. This was postponed due to the Ebola outbreak in the region. The visit will be carried out after the end of the Ebola outbreak but will not be in time to inform this annual review. The Annual Review was conducted in August and September 2014 by DFID officials including: Delna Ghandhi, Tim Elwell-Sutton and Peter Clarke. SCI provided a report with the basic information and briefed the review team to discuss progress. The review process was coordinated with the review of the Lymphatic Filariasis Programme, which is a closely allied DFID-funded programme.

Beneficiary feedback: The programme is carrying out surveys of beneficiaries to understand how effectively the programme is being delivered to them and identifying any barriers. For example:
-Knowledge Attitudes and Practices study in Malawi pre and post treatment.
-Focus Group Discussions to be conducted in Uganda and rolled out subsequently in all countries simultaneously with treatment coverage validation surveys
-Studies to determine the locations and reasons for those not getting access to treatment.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process