Annual Review - Summary Sheet

Title: / Africa-Brazil Partnership on Climate-Smart Agriculture and Food Security – ClimAA
Programme Value: / £ 13.4 Million		Review Date: / September 2014 (review covers implementation period from January 2014 to October 2014)
Programme Code: / 203707	Start Date: / October 2012 (approved March 2012)	End Date: / March 2015

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	-	B	A
Risk Rating	-	Med	Med

Summary of progress and lessons learnt since last review

1. ClimAA builds on Brazil’s international reputation for sustainable agriculture development and progress on the fight against hunger. DFID provides small amounts of funding to programmes and partnerships between Brazil and African countries which aim to transfer technology, knowhow and experience to the benefit of the poorest in Africa. This is mainly achieved through joint research projects, pilots and learning events.
2. Across a number of the components, the ClimAA programme has moved substantively into a delivery phase over the last year. Key highlights:
  1. The field testing phase of the IFPRI pilot programme has moved from design and is now into implementing two pilot studies in Malawi and Senegal. The use of Random Control Trial (RCT) methodology will enable IFPRI to robustly test whether Brazil’s Fomento programme might work in Low Income Country (LIC) contexts.
  2. The Brazilian Research Corporation´s (EMBRAPA) Marketplace programme continues to fund a number of innovative research projects between Brazilian and African Researchers. Several people interviewed during the AR stated how they valued the role the UK is playing in assisting with the selection of projects to fund. It is extremely positive that discussions are now underway on a programme to complement Marketplace, which would enable the most successful pilots to be replicated at scale (M-BOSS).
  3. The Brazilian government-funded elements of the Purchase for Africa by African (PAA Africa) programme have undergone a period of transition from phase I to phase II including new management structures. The Brazilian Government has taken on more of the programme implementation costs while DFID will fund a new phase on Knowledge Management and Learning, including the production and implementation of a detailed Monitoring and Evaluation plan for the first time in PAA Africa’s implementation. This will contribute to learning across the countries of operation.
  4. The new CALBEE grant to the World Food Programme Centre of Excellence funds learning exchanges between LIC governments and Brazilian experts. This is a worthwhile complement to the PAA programme, as it focuses on the institutional and political reforms which are needed to implement local purchasing and school feeding programmes such as PAA effectively.
  5. There are still some issues with the EMBRAPA proposals on TRU and training. Although proposals have now been developed there are still issues regarding the quality of proposals and the time remaining for them to be completed.

The effective implementation and completion of the ClimAA Programme Improvement Plan (PIP) has improved programme management and delivery. Overall the review team feel confident that the programme is now on a solid footing and relationships and programme management structures are sound, which should allow for effective delivery.

One of the aims of DFID’s Global Development Partnerships Programme (GDPP) is to support policy dialogue between the UK and the Government of Brazil (GoB) on development issues. Although complex by nature, the range of components which make up the ClimAA programme have enabled DFID Brazil to establish and develop strong links and relationships with a number of important and influential development partners within Brazil.

From discussions with a number of programme participants, in particular CGFome[1] and ABC[2], it was clear that Brazilian partners value the UK’s approach to working with Brazil. A number of partners highlighted that beyond the (relatively) small amounts of funding which the UK brings to the table, the knowledge and expertise which programme implementers could draw on through working with the UK was of significant importance.
[1] The section of the Brazilian Ministry of Foreign Affairs (MRE) which leads international cooperation on food security and humanitarian relief
[2] the Brazilian Development Cooperation Agency in the MRE

There are a range of examples where the UK and Brazil are now cooperating more closely on development policy issues. A good example was the dialogue on food security issues around the ClimAA programme that led to the UK and Brazil agreeing to co-host the London 2012 Hunger Summit, and to deepen their joint work as global advocates for combatting hunger and under-nutrition up to the 2016 Rio Olympics. In the course of the discussions for this Annual Review, ABC suggested that the UK and Brazil should establish bi-annual strategic discussions on development.

Summary of recommendations for the next year
Creating Formal Bi-annual High Level Strategic Discussions Between Brazil and the UK. In order to ensure that the programmatic work through ClimAA forms part of a broader policy dialogue between the UK and Brazil, we recommend holding bi-annual high-level strategic discussions between ABC and DFID/FCO, as suggested by ABC during the review process. This could include humanitarian discussions between DFID’s Conflict, Humanitarian and Security Department (CHASE) and CGFome (as previously requested by CGFome).

Re-validating ClimAA’s assumptions on how Technical Assistance impacts on Poverty (Theory of Change). DFID’s contribution clearly allowed more African countries to be involved in R&D and has improved the uptake by LICs of Brazil’s agriculture and food security capacity and knowhow. However, it is important to recognise how ambitious it is for DFID to fund existing Brazilian expertise programmes on sustainable agriculture and food security without necessarily having a causal link between the way enhanced partnerships with such institutions can directly benefit the poorest. It is important at this stage to revise the ClimAA Theory of Change (ToC), engaging with partners and African recipient countries, as far as that is possible, so DFID can continuously demonstrate how the uptake of Proof of Concepts drives benefits to poor communities in Africa.

Ensuring DFID country offices in Africa are engaged in the Brazilian-DFID Brazil relationship. The impact of DFID’s contribution is related to the degree of influence that drives transformative action on policies, regulations and increased participation of civil society in African countries. The Annual Review noted how the work on PAA Africa had helped the Government of Malawi develop a national policy on school feeding for the first time. In addition, in Mozambique, the government is about to pilot the very first local procurement for the national school feeding programme in decentralised municipalities through PAA Africa. DFID in Brazil should ensure that DFID offices in countries where UK-Brazil cooperation projects are operating are fully engaged from project conception to implementation to evaluation to maximise their potential impact by ensuring that programmes are appropriate and linked in with existing DFID country work where appropriate.

Developing Mechanisms to Ensure Successful Projects Can be Scaled Up. EMBRAPA and IFPRI should discuss with DFID Brazil how successful projects and interventions will be supported in the future either through future support and/or dissemination of results. DFID should look to ensure that there is enough buy-in in those countries to take proof of concepts further beyond testing and validation.

IFPRI project should be extended for a minimum of one more cropping cycle. The current design of the IFPRI research trials covers only one cropping season, which is too short in order to be certain of the validity of any impacts observed. DFID Brazil should consider extending the project to be able to capture (at least) two, preferably three, agricultural seasons, if credible results are to be expected from the research.

PAA and CALBEE need to work closer together. There is significant overlap and complementarities between CALBEE, which works more at the policy-enabling level, and PAA Africa, which works more at implementation level, for linking local production with school feeding. As PAA Africa has now moved to WFP in Rome the links between the two programmes need to be maintained. The review team recommends that the programme team should ensure that links between the programme teams and interventions are maintained and that they continue to learn from each other.

EMBRAPA TRU/TRAINING proposals remain an area of concern. The team expressed a number of doubts regarding the quality of the proposal and the sufficiency of the time remaining in the programme (even with an extension) to complete the projects. On the quality of the proposal the team suggested that more time was needed to develop the proposal. Given the constraints on GDPP funding next year, DFID Brazil needs to make an early decision on whether to continue with this proposal.

Logframe needs updating. As acknowledged within the review, the logframe has been substantially improved. However, work is still needed to update the logframe in light of the recommendations made in this review. The impact and outcome statements remain relatively weak and should be improved in line with the suggested re-examination of the Theory of Change (ToC) in recommendation 2 above.

No-cost extension to March 2017. The extra funding given in July 2013 plus the delay to the start-up times for the programmes require that the ClimAA programme be extended until March 2017. Though the majority of the available funds will be distributed by the March 2016, the DFID Brazil team will need to continue monitoring the programme until 2017 to ensure the results are achieved.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4446020.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4446027.xls

Outline of the programme

DFID is supporting a set of integrated interventions with a total budget of £13.4million up to 2015, to boost agricultural productivity, food security and poverty reduction in Africa through stronger African-Brazil cooperation. The Business Case was initially approved in March 2012 for 3 years at £10.8M. An additional sum of £2.6M was agreed in July 2013 for two additional projects giving a total of £13.4M. The extra funding plus start up times for the programmes effectively require that the ClimAA programme be extended until March 2017.

The programme consists of a number of projects with different Brazilian Agencies, agencies working in cooperation with Brazilian Government Institutions and International Research Institutes. The main projects are:

The Africa-Brazil Agricultural Innovation MarketPlace
Through a competitive application process Marketplace supports small research projects between EMBRAPA and African Research Institutions. EMBRAPA is now developing a complementary programme with the Bill and Melinda Gates Foundation to take successful projects to scale (M-BOSS – MarketPlace Building on Successes). EMBRAPA has invited DFID to join this initiative.

Enabling Food Security Policy and Capacity in Africa: Leveraging Brazil’s Experience and Expertise - CALBEE (WFP Centre of Excellence on Hunger)
The WFP Centre of Excellence works with the Government of Brazil to meet the demand from other developing countries to learn from the Brazilian experience in food security and social protection. Through CALBEE DFID supports this objective by helping to fund up to six additional exchange visits. The Centre has funds from the Brazilian Government for four years. DFID funds will complement this, providing greater flexibility and additionality through: i) linking to a wider in-country networks through DFID offices; ii) bringing in expertise from outside of Brazil, GoB funding being restricted to Brazilian Nationals; iii) and consolidating engagement with stakeholders through setting up regional networks in Africa.

IFPRI – International Food Policy Research Institute
Through an initial scoping study IFPRI identified two potential Brazilian programmes which might be suitable for application in Africa. One, PAA, was already being tested through PAA Africa. The other programme, Fomento (a business support package for small farmers), is to be tested by IFPRI in two African countries. The research behind this choice, which is publicly available, is a useful output in itself. The Fomento model is being piloted in Senegal and Malawi through local implementing partners.

The Africa-Brazil Technical Reference Units (TRU) and Training
The TRU project looks to set up TRUs (similar to model farms where new farming practices can be tested at scale in a controlled environment and used to show farmers’ results) in up to four African Countries to test Brazilian Climate Smart Agricultural Technology within these contexts. Additionally EMBRAPA proposed a separate training project, which is looking to train approximately 180 African technicians on sustainable agriculture, to disseminate knowledge to smallholder farmers. This project has suffered substantial delays which were also noted in the last Annual Review.

Purchase from Africans in Africa project – PAA Africa
PAA Africa builds on two key components of Brazil’s Zero Hunger Strategy to increase food security through a local food purchasing programme (PAA)[3] and a school feeding programme (PNAE)[4]. PAA Africa combines the approaches and learnings from PAA and PNAE in five African countries (Senegal, Niger, Ethiopia, Malawi and Mozambique).
[3] PAA – Brazil’s local food purchasing programme
[4] PNAE – Brazil´s National Programme on School Feeding

The projects are structured around four complementary outputs, each project contributing to more than one output. The outputs are:

1. Capacity Building: Increased uptake of sustainable agriculture and food security practices (climate-smart) by African country institutions through formalised training and exchanges. These activities include policy makers and researchers;
2. Proof of Concepts: Generated principally through small and large scale research projects and pilots, with a proposal to look at funding some scaling-up of the smaller research projects at a later stage;
3. Generation of Evidence: Achieved through publications and events at national and international forums;
4. Fostering South-South Partnerships: Strengthened collaboration between Brazil and LICs, as contacts are through government bodies and/or through dedicated research and development institutions dealing with agriculture and food security.

The project is highly challenging in seeking to promote Brazilian cooperation using a mix of lessons from selected Brazilian partners, and working through complementary intervention approaches and partnerships. The programme combines the expertise of the Brazilian Agricultural Research Corporation (EMBRAPA)[5], World Food Programme’s (WFP) Centre of Excellence in partnership with the Humanitarian Office (CGFome) of the Brazilian Ministry of Foreign Affairs (MRE) and the Brazilian Government´s Education Fund (FNDE) and the International Food Policy Research Institute (IFPRI). The programme measures impact with a mix of indicators.
[5] EMBRAPA contributes with an array of results from the MarketPlace, M-Boss, Training and TRU programmes

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The UK ended its bilateral development programme in Brazil in March 2005 and its regional development programme in 2009. Since 2009 the focus of DFID’s work in Brazil has been to facilitate the wider application of Brazil’s experience to LICs, particularly in Africa. ClimAA has become an excellent example of how the UK can work with new partners to enhance global development impact by taking learning from countries which have experience of successful development, and testing it in other contexts. Despite delays ClimAA is now showing increased influence, and some preliminary visible results.

The main recommendations from the previous Annual Review were around delays to the various project components, the need to re-organise the logframe to provide greater clarity and reflect programme implementation, and the need to ensure the programme was compliant with latest DFID guidance (Annex 1). The Annual Review also flagged up some confusing coding information on ARIES, DFID’s internal programme management system, which had made it very difficult to manage the project in the past. The programme only achieved a B. In light of this, it was decided to produce a Programme Improvement Plan (PIP), despite the fact that it is normally only required after two consecutive Annual Reviews score a B. The PIP (Annex 2) set the following objectives:
1. To improve the programme clarity and accountability including resolving the confusion resulting from mixing of programme codes on the ARIES system;
2. To improve the programme implementation: DFID Brazil to increase their engagement with programme partners, and to review the log frame of the project improving the monitoring and evaluation capacity of the programme.

The PIP has been fully completed and signed off. Programme implementation has been accelerated and new programmes signed off and started. An additional programme (M-BOSS) is likely to be signed off in late 2014 as well as an additional injection of funds into MarketPlace.

Key observations from the AR interviews were:

- A number of interviewees stated that ClimAA was supporting a wider policy dialogue with Brazil. An example of this is Brazil’s engagement with Nutrition for Growth, which demonstrated how the programme work had translated into the UK and Brazil entering into joint political commitments.
- The Brazilian Development Cooperation Agency (ABC) stated that the UK-Brazil Memorandum of Understanding on Development formed the basis of the development relationship, and that it had signed similar MoUs with a number of other traditional donors. However, they were keen to keen to work with partners who were able to offer an operational element to cooperation, as well as a political dialogue. ABC also stated that they were keen to establish annual high-level strategic talks on development with the UK, which is a further indicator that working in this way with Brazil is building a closer relationship.
- Much of Brazil’s offer to recipients on development cooperation is based on technical expertise, which means that links with technical institutions, such as EMBRAPA, CGFome, WFP and IFPRI on the agricultural and food security sector are particularly important to promote positive change. Officials in recipient countries such as Malawi and Mozambique expressed a particular interest in Brazil’s blueprint for agricultural research, particularly in the case of Mozambique where both countries share the same official language.
- MarketPlace has won considerable recognition from donors and partners over the years. Since 2010 MarketPlace has received almost 500 applications from 28 countries in Africa and 21 in Latin American and Caribbean (LAC). Over a quarter of the participants were women, and more than $20M in funding from partners has been mobilised. DFID contributed 38% of those resources.
- At outcome level EMBRAPA MarketPlace has already had an impact with some proof of concepts been taken up by LICs: A good example is the MarketPlace pilot on cowpea inoculation techniques in Northern Ghana. This demonstrated the value of the technique, which enables plants to capture nitrogen from the air which fertilises the plant saving on inputs and increasing yields. Cowpeas are an important source of nutrition and a good source of income for poor farmers and families in many African countries. The project has already won additional resources from Alliance for a Green Revolution in Africa (AGRA) to enable it to scale-up.
- The review team was impressed with the WFP CALBEE team’s focus on ensuring that study visits to Brazil had sustainable impact. The team makes significant efforts to ensure action plans are endorsed by the right stakeholders. The centre is prepared to make tough decisions on the composition of the country delegations. This includes cancelling trips when delegations are not considered sufficiently broad to be able to push for change within their own countries .
- Despite some delays in the mobilisation phase, the IFPRI project is now making solid progress. The project is already providing significant contributions to ClimAA results. The model might be a useful element of Brazil’s horizontal cooperation ‘offer’. However in order to ensure that this contributes to GoB’s development cooperation policy it will be important that DFID Brazil and the IFPRI programme team create opportunities to feed the learning from the programme back to government partners and policy opinion-formers in Brazil.
- PAA Africa remains an excellent example of the Brazilian Government’s approach to south-south technical cooperation. Countries still face a great disconnect to ensure that subsistence family farmers break into local markets. PAA Africa provides a guaranteed market and guarantees a local source of food for schools. DFID’s support to PAA Africa has funded design work in previous financial years, and is now directed at the programme’s learning component, which is intended to ensure that lessons are shared between implementing countries.
- Over the last year programme management of PAA has moved from the WFP Centre of Excellence in Brasilia to WFP Rome. This should ensure that the programming is more integrated within WFP but it also reduces the opportunities for cross-fertilisation with the CALBEE programme, which supports reforms at the institutional end of the spectrum.
- During the review a number of interviewees confirmed that PAA Africa is well perceived and well known outside Brazil, at the level of officials and local government. A number of interviewees gave positive feedback on how participating in learning events with Brazilian government officials had provided a positive demonstration effect for how food insecurity could be reduced. This was contrasted favourably with experience of working with traditional donors who did not have direct experience of domestic reform. During the review in Malawi and Mozambique the review team saw evidence of clear links between PAA Africa and certain public policy reforms.
- The review team is concerned about the timeframe for the EMBRAPA TRU and Training proposals and how realistic it is to deliver the projected results in the remaining period covered by this business case. The review team were also concerned about the current project design. Further thought needs to be given as to whether the proposed transfer of technology is appropriate for the proposed country contexts – though a preliminary design phase is included within the project proposal to mitigate this. If this project does go ahead considerable revision to the original project design will be necessary, without creating further substantial delays.

Brazil strongly supports the wider extension of south-south cooperation, and ClimAA provides a good platform to enable the UK government to work alongside Brazil as it develops its own approach to development cooperation. Brazil at the same time has come to question its small, widely spread and financially constrained development footprint. Brazilian officials and commentators we spoke to suggested that after the Presidential elections it was likely that Brazil would review its institutional arrangements for development cooperation. DFID is now well positioned to share its own experience, thanks in many ways to ClimAA. Brazil clearly recognises the value of cooperation and collaboration with DFID because of DFID’s long experience, its policy capacity and its leading role in debates on international development.

Overall output score and description
The annual output score is A (Meets Expectation). The project is complex involving a variety of partners and testing a number of approaches – but good progress has been made in shortcutting delays, simplifying the complexity of the logframe and mobilising the scaling up of some project activities, while leveraging other donors to increase support at scale.

The PIP has been successfully completed with a number of actions taken by the team.

Key lessons
The original set up of the ClimAA programme had two main issues:

1. The programme was tied into certain pre-determined projects. Although this is not unusual, umbrella projects often need to be more flexible to be able to cope with changes in partners’ plans (as there is less control with programmes involving multiple partners and governments).
2. Individual projects were also considered as one output. This meant that if there were delays this affected the assessment of the whole project even if other parts were performing well and the desired outcomes were being achieved.

As the previous Annual Review showed this meant that although progress was good in some areas, delays in others brought down the score. The logframe also did not allow flexibility in terms of starting up new projects (as new outputs would need to be added). A revamp of the logframe as part of the recommendations from the previous Annual Review and the PIP has greatly increased flexibility and ensured all projects contribute to more than one output and to the wider outcomes around south-south cooperation.

Key actions
Key follow up actions are captured in the Summary Sheet and through detailed recommendations after each output.

Has the logframe been updated since the last review?
Yes. The last Annual Review and the follow-up PIP recommended considerable revision work to the log frame. This was to make it simpler, and align the respective outcomes, outputs and indicators with the overall scope of ClimAA. It also needed to take into account changes in individual projects, and the additional incremental resources allocated to the project.

The revised logframe is now organised to ensure that the various sub-projects (MarketPlace, PAA-Africa, WFP Centre of Excellence, IFPRI and TRU) as part of ClimAA contribute to all four outputs. The logframe was agreed and made public in May 2014. This Annual Review already reports results against the “revised” set of milestones and targets.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased capacity of LIC researchers, government institutions and extension staff through participation in LIC-Brazilian pilots, training and policy dialogue
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of researchers participating in joint research/pilot programmes and exchange visits disaggregated by gender/institutional affiliation and seniority	8 (3) researchers, 3 women researchers	Exceeded 100 %. Achieved: 156 (61 women)
Number of people trained in adaptive research, sustainable agriculture technologies, local food purchase systems and extension approaches to disaggregate by gender.	110 (25) people, 25 of which are women	Exceeded 100 % / Achievement (126 people, 28 females)
Number of training materials and capacity building events addressing gender issues	1	100 % / IFPRI

Key Points
Partnerships with credible Brazilian institutions are starting to show evidence of positive change in African country contexts. Significant progress has been achieved on Milestone 1 with both an increased number of researchers participating in joint programmes, and a wider variety of people that received training on sustainable agriculture and food security - from students, public officials, farmers, farmer associations and school teachers.
PAA Africa held a workshop in Ethiopia in June with 88 participants (35 women) contributing to indicator 1.1. They also conducted two technical support visits one to Malawi and one to Mozambique with two participants in each, a total of four (two women). From the interviews it was clear that some advances on national capacity have already been achieved, but that much work is still needed in African countries.
During the workshop in Ethiopia, delegates from the five PAA Africa countries along with Brazilian counterparts and the UN had the opportunity to compare how PAA Africa operates in different environments. They agreed that there is a need to increase the range of produce PAA Africa uses for local school menus to improve nutritional outcomes. They also agreed that there was a need for more efforts to increase the participation of the private sector and women and girls at all stages of the process. These learnings were re-enforced by a field trip to Hawassa, where delegates were able to see at first-hand how PAA Africa operates in Ethiopia.
CALBEE held an event during the Global Child Nutrition Conference at the end of September where 66 people (25 women) attended the event. Although no researchers were involved these were high level policy makers so this has been included in indicator 1.1. CALBEE will also host also a high-level visit from Malawi during early October which represents an incremental contribution to milestone 1.
IFPRI report that up until September IFPRI contributed with two researchers participating in the pilot programme, one being a woman (output 1.1). This IFPRI sub-project is also responsible for the total contribution to Output 1.2 with 126 people (28 women) being trained. Finally on output 1.3 IFPRI organised an event that specifically addressed gender issues.
The main contributions to output 1 this year are from CALBEE, IFPRI and PAA Africa, however, in subsequent years both EMBRAPA projects TRU and Training will have an increased influence especially on output indicator 1.2.

Summary of responses to issues raised in previous annual reviews (where relevant)
See Performance and Conclusions Section

Recommendations
None specifically for this section, see general recommendations. At the next Annual Review in 2015, this output will depend heavily on the TRU and training proposals. If the general recommendations regarding these are accepted, it will mean that the results for this output will need to be amended in the logframe.

Output Title	Proof of concepts tested and validated for LIC- specific context for potential outscaling
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of proof of concepts/pilots (PoC) initiated	1	Exceeded 100 % / Both (2) pilots have already been initiated (Senegal and Malawi)
Number of PoC tested and validated, with at least 40% showing potential positive impact on women and girls	0	100%
Number of PoC identified with the potential for upscaling (and number of projects with upscaling initiated and completed)	5	100%

Key Points
IFPRI has developed (Output 2.1) two site units that are up and running in Senegal and Malawi. Farmers clubs in Malawi have 40% women members.

PAA Africa has contributed to ClimAA (Output 2.3) under the current reporting period with the five countries in Africa that have initiated the upscale of PAA.

Eleven agricultural research projects were selected in 2014 in Tanzania, Ethiopia, Mali and Ghana and five in Latin America under MarketPlace. More than half of those proposals were directly dealing with smallholders and poverty-alleviation targeted technologies. The remaining proposals were mostly with a focus on policy development or productivity technology. Contracts for these proposals will be finalised before the end of 2014 so these projects will be counted in the next review. No DFID funded projects have as yet completed the two year implementation phase (indicator 2.2).Although ten MarketPlace projects have been tested and finalised these were funded by other partners (as opposed to directly from DFID resources).

EMBRAPA has taken clear steps to overcome delays on Technical Reference Units intended to cluster sustainable agriculture technology in key points in Africa.

The contributions to output 2 this year are from IFPRI and PAA Africa. However, in subsequent years the EMBRAPA projects MarketPlace, M-BOSS and TRU will have an increased influence.

Summary of responses to issues raised in previous annual reviews (where relevant)
See Performance and Conclusions Section

Recommendations
Whilst the Proof of Concepts which Marketplace generates are valuable, in order to effectively target improved livelihood systems it will be necessary to support successful Marketplace ideas at scale. EMBRAPA is partnering with Bill and Melinda Gates Foundation to design and fund a new programme, M-BOSS, to do this, and has requested DFID involvement. The review team recommends that DFID should consider this request seriously, to ensure that results from the projects are replicated at scale, and at the same time use it as an innovative way to monitor the uptake of the initial research evidence results .

The current design of the IFPRI research trials covers only one cropping season, which is unrealistic to capture any “real” transformation. DFID should consider extending the project to be able to capture (at least) two agricultural seasons, if credible results are to be expected from the research. DFID should make sure there is enough buy-in in those countries to take proof of concepts further beyond testing and validation.

DFID Brazil made significant efforts to accelerate the development and implementation of the TRU/Training Concept notes, however, the projects have still not started. Even if implementation of the TRUs starts soon it will be ambitious to expect effective results on the proposed time-frame. Additionally, during the review it was difficult to understand how EMBRAPA plans to place and target the Technical Reference Units in each country – how available to smallholder farmers in the “real world” will they be. More work needs to be done on the proposal.

EMBRAPA and IFPRI should discuss with DFID sustainable options for some of the research pieces. DFID should look to ensure that there is sufficient enough buy-in in those countries to take proof of concepts beyond testing and validation.

Output Title	Lessons learnt and robust evidence generated on adoption of Brazilian technologies and interventions relevant for policy and programme development in LIC
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of best practices, lessons learnt documents, internet discussions and policy briefs widely disseminated with at least 30% of papers/briefs addressing gender dimensions	3	Not achieved: 66% / Two reports finalised, one still being drafted.
Number of evaluation studies/action plans initiated and completed	3 (0)	Over-achieved / 4 studies initiated by PAA and IFPRI
Number of learning and policy events organised by ClimAA partners	2	100% / 2 one through CALBEE and one through MarketPlace
Number of presentations of lessons learnt from ClimAA at international and national events	2	Over-achieved / 4 presentations by PAA and MarketPlace

Key Points
PAA Africa has been the main contributor this year. Under indicator 3.1two technical notes have been produced and another one is in production. For indicator 3.2 two studies have been initiated with MoUs having been signed. For 3.3 workshop and trainings have been delayed. For 3.4 PAA Africa has presented in New York and at a workshop in Accra, Ghana.

IFPRI initiated two evaluation studies, one in Senegal and one in Malawi (Indicator 3.2).

CALBEE achieved one learning event as part of the Global Child Nutrition Forum at the end of September with a network meeting linking southern African policy makers on school feeding (indicator 3.3).

MarketPlace held a forum in early April for all existing and new MarketPlace projects where lessons learnt and experiences were shared as well as results from the first group of projects. During the forum delegates also visited one of EMBRAPA’s research centres – EMBRAPA Cerrado (indicator 3.3). MarketPlace also presented at two IFAD related forums one with the Brazilian Government and a south-south forum in Rome.

The contributions to output 3 this year are from PAA Africa, IFPRI, CALBEE and MarketPlace. In subsequent years the EMBRAPA projects Training, M-BOSS and TRU will also contribute.

Summary of responses to issues raised in previous annual reviews (where relevant)
See Performance and Conclusions Section

Recommendations
IFPRI is not a Brazilian institution and in order to build a “unique” Brazilian intervention that models independent research on agriculture technology adoption and social cash transfers for Africa the project needs to get buy-in from Brazilian institutions. The baseline study is an ideal opportunity to establish the degree of engagement with Brazilian authorities. In moving forward IFPRI should examine how it can engage more effectively with the Brazilian Government including the timely sharing of findings.

In order that project interventions are taken up robust evidence needs to be generated through evaluations and lesson learning.

Output Title	South-South collaboration strengthened between Brazil and LIC government, research and development institutions working on agriculture and food security
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		N/a	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress
Number of Brazilian and LIC institutions collaborating as part of ClimAA	2	100% / IFPRI signed two
Number of joint partnerships with signed MoU between LIC and Brazilian institutions working under ClimAA programme	0	100%
Number of presentations to Brazilian institutes to demonstrate relevance of Brazilian expertise to South-South cooperation and technology transfer	0	100%

Key Points
ClimAA clearly helps to influence the Brazilian government in relation to development cooperation with Africa. Many of the agreements were already signed at the beginning of the project and these form the baseline in the new ClimAA logframe. For this reporting period IFPRI contributed the milestones through the agreements with the project implementing partners.

FCO and DFID in Brazil were clear that the programme contributes greatly to the establishment of UK-Brazil dialogue in Africa. However, if the advantages of the trilateral relationship is to be promoted then UK missions in Africa need to be involved otherwise recipients countries will only see either the bilateral relationship with Brazil or the influence of the implementing party. As communication between African governments and Brazilian authorities is of paramount importance to drive delivery, FCO and DFID should strive to help build these bridges in-countries related to ClimAA, either with individual ABC offices in Africa, or through any Brazilian institution working in those countries under ClimAA (EMBRAPA).

The contributions to output 4 this year are from IFPRI. In subsequent years the EMBRAPA projects Training, MarketPlace, M-BOSS and TRU as well as PAA Africa will also contribute.

Summary of responses to issues raised in previous annual reviews (where relevant)
See Performance and Conclusions Section

Recommendations
DFID risks being overshadowed by UN agencies which have a strong presence in some countries and direct interaction with beneficiaries and the local authorities accountable to them. DFID country offices could in some instances reduce that risk by becoming more involved, and in some cases lead on some of the in-country discussions. This assumes Brazilian institutions would be comfortable to have a steer from national authorities under the oversight of DFID African offices.

Although CGFome is extraordinary fluent on the political economy that drove Food Security policies in Brazil, DFID must ensure it finds ways to promote political economy analysis to PAA African recipients. This is especially important for some of the ambitious, high risk reforms, such as decentralisation and effective inter-ministerial coordination, that only work under specific conditions. Experience up to now has been good with the project adapting to different contexts but as it scales up this needs to be carefully monitored.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

During nine months of project activities DFID disbursed £2,476,963, covering the period of January 2014 to September 2014.

ClimAA annual Programme costs	Year 3	9 months Financial Execution(2013/14)	Total to be Disbursed
1. PAA (CGFome, WFP, FAO) Phase I	£580,000	0	£580,000
2. PAA (CGFome, WFP, FAO) Phase II	£286,019	£286,019	£1,300,000
3. CALBEE (WFP)	£287,056	£287,056	£1,300,000
4. EMBRAPA (MarketPlace)	£1,720,000	£1,250,000	£2,200,000
5. EMBRAPA (TRU)	£0	£0	£580,000
6. EMBRAPA (Training)	£0	£0	£580,000
7. IFPRI	£789,915	£653,888	£1,170,000

It is likely in late 2014 that an additional funding of £900,000 will be given to MarketPlace for an additional round of proposals. If it is agreed to extend ClimAA to March 2017, as recommended, up to £1,200,000 for the new M-BOSS project will also be provided which will be split over 3 years.

DFID may propose a budget revision to accommodate certain project changes without detriment to the overall results in the logframe.

The largest share of expenditure under ClimAA is on fees/personnel and logistics. For some projects, such as with EMBRAPA, fees are low as EMBRAPA staff costs are part of their in-kind contribution. The costs for both are within reasonable limits for the nature and scope of interventions.

Spending has rapidly increased during this period and is close to that forecasted for the period. Problems with delays on the TRU and Training proposals had already been factored in in the forecasts but the lack of progress is still a concern as payments were due to start soon.

VfM performance compared to the original VfM proposition in the business case
No formal VfM assessment was carried out during this review, but the team was able to consider whether systems currently in place are adequate to ensure VfM. Measuring value-for-money in triangular cooperation programmes is difficult. The Organisation for Economic Cooperation and Development´s Development Assistance Committee (OECD-DAC) - member development agencies consulted by DFID acknowledge that this is rarely the “cheapest” means to deliver development results in recipient countries, as the transaction costs of working with a number of partners are high and complex. But there are wider benefits that make these interventions a worthwhile investment.

Although the project does not have an agreed, routinely reported against set of VfM metrics at output level, partners confirmed their commitment during the Annual Review to drive project costs down, and many good examples were provided. However, the team continues to consider that programme outputs will always be, by their nature, relatively more expensive when compared with DFID standard ‘bilateral’ models. However, it should be noted that in several of the projects Brazil supplies experts as an in-kind contribution. Thus projects with EMBRAPA do not include staff costs. Considering the world-leading expertise of the staff provided on agriculture in the tropics, and the institutional support behind this, these in-kind costs can be substantial. In the case of the original TRU and training proposals these costs would add an additional 60% to DFID’s contribution e.g. the original DFID contribution was £5 million and in-kind staff costs from EMBRAPA would add £3 million to the overall project resources).

A number of examples of VfM were provided:
- EMBRAPA were able to demonstrate that placing research funding for Marketplace projects directly into the hands of researchers encouraged them to find best-value options, such as finding cheaper accommodation during study visits for partners, to enable them to benefit from more time working with Brazilian researchers.
- WFP Centre of Excellence had a particular focus on ensuring that the only funded high-quality delegations for visits to Brazil. They explained that this meant they needed the right expertise and influence to be able to benefit from the time spent with GoB interlocutors, and implement the learning they had acquired once they had returned to home countries. This involved working closely with partners on delegation lists, and cancelling visits when they were not convinced by the calibre of the delegation.

Assessment of whether the programme continues to represent value for money
Yes. Although it is complicated to value the complexity of trilateral cooperation, in terms of relationship-building and sharing experiences with LICs, there is good evidence that shows that the project represents value-for-money. Programme cooperation is developing significant levels of goodwill and respect with Brazilian development partners and government officials. The programme is playing an important role in contributing to leveraging larger contributions from other partners including the Brazilian Government, Bill and Melinda Gates Foundation and the International Fund for Agricultural Development (IFAD).

For programmes such as PAA-Africa DFID only provides amounts that complement resources for M&E and lessons-learning.

Quality of financial management
Funds for projects are channelled to project partners from DFID’s Global Partnerships Department in Brazil in the following way:

ClimAA annual Programme costs	Recipient Institution
1. PAA (CGFome, WFP, FAO) Phase I	WFP Centre of Excellence
2. PAA (CGFome, WFP, FAO) Phase II	WFP P4P Unit in Rome
3. CALBEE (WFP)	WFP Centre of Excellence
4. EMBRAPA (MarketPlace)	FUNARBE[6]
5. EMBRAPA (TRU)	FUNARBE
6. EMBRAPA (Training)	FUNARBE
7. IFPRI	IFPRI (Washington)
[6] Due to the Brazilian Constitution EMBRAPA cannot spend funds outside of Brazil without congressional approval for each spend. FUNARBE, a charitable foundation, works with EMBRAPA on its overseas projects facilitating their implementation.

Recipient institutions have been working in Brazil and with DFID for a long time, with clean audits and no apparent issues. Due diligence was conducted by DFID in August 2014 for the relevant projects as part of finalising the PIP.

Date of last narrative financial report	Varies across partners 2014
Date of last audited annual statement	NA

E: RISK (½ page)

Overall risk rating: MEDIUM

The programme adopts a portfolio approach to risk in supporting components that are low risk (e.g. delays in approval and transfer of funds by DFID) through to medium and high risk (e.g. where Brazilian models may not be sufficiently adapted to context). This approach enables DFID Brazil to have a degree of confidence in a core set of results. The commitment to the programme by Brazilian partners seems to have matured, reducing the risk identified at the outset of the Business Case in 2012.

Overview of programme risk

Risks	Level		Mitigating factors
	Probability	Impact
Lack of commitment from partners by virtue of shifting political priorities;	Low	Medium	Continue to work with focal points in Government and forge partnerships with civil society;
Resistance of partner Governments and international agencies in reviewing national policies, procedures and programmes to apply lessons and take up new approaches;	Low	Medium	-Continue to engage local authorities (formal and/or traditional) in all project planning and evaluation stages. Work with focal points in Government and forge partnerships with civil society. / -Improve the Brazilian institutions knowledge and understanding of the political economy of the recipient African countries;
Brazilian models not sufficiently adapted to context;	High / (it was medium)	Medium	-Processes of lesson learning, testing and multi-stakeholder dialogue built into or the primary focus of recommended components. / -Better consultation with DFID African countries where and when suitable.
Insufficient ownership by African participants;	Low	Medium	-DFID Brazil to partners with African DFID country offices to seek for appropriate engagement avenues; / Lead partners build an effective multi-stakeholder network to build buy-in and capacity to engage in recipient countries; / -Seek for country specific road maps for the dissemination & adoption of technology or evidence from research;
Capacity of developing country partners insufficient to engage effectively with Brazilian actors;	Medium	High	-Capacity strengthening built into all main components of ClimAA.
Insufficient evidence base to measure results;	Medium (it was high)	High	-M&E must be part of the engagement with project partners, now that is built into each component, supported by analysis and decision support.
Financial mismanagement or fraud within project partners;	Low	Medium	1) EMBRAPA currently manages annual funds of US$1bn and FUNARBE’s fiduciary systems channel significant international funds, and meet DFID requirements. / 2) WFP has a good track record, DFID delivers more humanitarian assistance (36% of our 2008-09 spend) through WFP than any other agency. WFP meets all of DFID’s fiduciary risk requirements. 3)IFPRI: IFPRI has a track record of managing DFID funds, and meet CGIAR standards.
Delays in approval and transfer of funds by DFID;	Low (it was Medium)	Medium	This is a risk with large consequences. In particular rainfed agricultural programmes need to be implemented on time or a whole year of results can be lost. Implementing partners will demand timely action from DFID. Donor performance will be on the ToR of the evaluations.

Outstanding actions from risk assessment

Overall risks to the project are outlined in the updated risk matrix with the following highlighted as key risks:

During the review it was clear that the engagement with DFID country offices remains a challenge, but is an important piece. They could play an active part to make sure Brazilian models are fit-for-purpose and are sufficiently adapted to each recipient African country context;

MarketPlace: Projects are capped at US$80,000 which limits and spreads exposure to risk. Grantees will be informed of a zero tolerance policy towards fraud. Financial capacity and track record will be part of the assessment process. Funds will be released in against clear expected outputs and financial reporting requirements. Funding will be terminated if any evidence of financial mismanagement or fraudulent activities is identified or if performance targets are not met.

In Phase II of PAA Africa the governance structure is being changed as PAA Africa is now supported through WFP in Rome. As there are clear overlaps with the work by the WFP Centre of Excellence under CALBEE, DFID in Brazil need to ensure that there is effective cooperation between the two projects.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
On Track?	N

Given the nature of ClimAA implementation modality there are minimal commercial considerations when it comes to the delivery of ClimAA results and milestones. ClimAA initiatives are built on existing interventions and DFID Brazil has made all efforts to improve performance to reduce delays on the programme implementation. Overall the programme has significantly improved with increasing engagement with Brazilian partners on logframes, workplans and programme quality. A number of agreements have also been signed during this period. The engagement with Brazilian institutions seems to have improved, and also reduced transaction costs and political risks on the ongoing project implementation.

Performance of partnership (s)
ClimAA is an umbrella programme with decentralised management and a diversified set of partnerships.. DFID has established good clear relationships with the key implementing partners and has avoided a centralised programme management service provider, which would be costly and defeat the purpose of having ClimAA as an influential tool to strengthen the UK-Brazil relationship. The programme does not have a single Brazilian institutional lead, but uses a variety of institutions instead. This reduces risk and increases the flexibility of DFID support.

Asset monitoring and control

N/A

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)	N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The project is based on outputs related to formative research between research institutes in Brazil and Africa and on pilot programming. A significant number of programme results are associated with the publication of scientific research that provides strong evidence of the potential of Brazil’s agricultural development and food security programmes in African countries. Note that most of the implementation is conducted by project partners - Brazilian institutions with Brazilian expertise - subject to continuous evaluations and peer-reviews.
The project now benefits from an improved and simplified monitoring Logframe that is able to measure better the impact of the work of ClimAA on gender, and integrate gender dimensions into the different projects. It also captures successfully DFID in Brazil’s ability to foster south-south cooperation as part of the Global Development Partnership Programme. Indicators are now better distributed across the partners involved, being on the research/proof of concept part or the capacity building.

Monitoring progress throughout the review period
The Annual Review was innovative by having an integrated team with different perspectives on trilateral cooperation. The team was composed of three team members from 1) the Global Partnerships Department in London, 2) DFID Mozambique (one of the principal countries receiving Brazilian technical cooperation), and 3) DFID China (similar south-south programmes to DFID in Brazil). The team members provided a rich perspective that allowed a better grasp of the uptake of Brazil’s sustainable agriculture blueprint, but most notably to gauge on the extent to which ClimAA’s programmatic work is helping to establish a closer dialogue between the UK and the Government of Brazil on cooperation and development issues. Part of the team went on a field trip to Malawi, followed by a one-day stop-over in Maputo, Mozambique.
The annual review involved 14 meetings in Brasilia, together with four schools and three farmers’ organisations visited in Malawi, including a farmer mobilisation meeting with IFPRI. In Mozambique the team held a meeting with WFP regarding PAA Africa. Overall, the team had ample opportunities to meet stakeholders and to confirm that the programme supports policy dialogue, in particular with Nutrition for Growth as an example of joint political commitments.
The field visits offered direct feedback from the project and from a wide variety of beneficiaries. All provided a good deal of positive feedback, and contributed to some of the recommendations under this review. In addition to the visible evidence of the project implementation, it was possible to hear positive direct feedback from programme beneficiaries.

List of Acronyms:

ABC	-	Brazilian Government Cooperation Agency
AGRA	-	Alliance for a Green Revolution in Africa
AR	-	Annual Review
CALBEE	-	Enabling Food Security Policy and Capacity in Africa: Leveraging Brazil’s Experience and Expertise
CGFome	-	Brazilian Humanitarian Department in MRE
CHASE	-	Conflict and Humanitarian and Security Department
OECD-DAC	-	Organisation for Economic Cooperation and Development - Development Assistance Committee of the OECD
EMBRAPA	-	Brazilian Agricultural Research Corporation
FAO	-	Food and Agricultural Organisation of the United Nations
FCO	-	UK Government’s Foreign and Commonwealth Office
FNDE	-	Brazilian Government’s Education Fund
FUNARBE	-	Arthur Bernades Foundation
GDPP	-	Global Development Partnership Programme
GoB	-	Government of Brazil
IFPRI	-	International Food Policy Research Institute
LAC	-	Latin America and Caribbean
LIC	-	Low Income Country
M-BOSS	-	MarketPlace Building on Successes
M&E	-	Monitoring and Evaluation
MRE	-	Brazilian Ministry of Foreign Affairs
PAA Africa	-	Purchase from African for Africa
PCR	-	Project Completion Review
PoC	-	Proof of Concept
PIP	-	Programme Implementation Plan
PNAE	-	Brazilian National School Feeding Programme
RCT	-	Random Control Trial
R&D	-	Research and Development
ToC	-	Theory of Change
TRU	-	Technical Reference Unit
VfM	-	Value for Money
WFP	-	World Food Programme (United Nations)

Annex 1: Summary Sheet from 2013 Annual Review

As the previous Annual Review was done in the old format there is not a specific summary sheet. Instead included here is Section B.1 on progress and results which gives a summary of the score and key recommendations.

1. Progress and results

1.1	Has the logframe been updated since last review?
No. It is recommended that the log frames pertaining to both programme components are reviewed by the second quarter of 2014.

1.2	Overall Output Score and Description:
Outputs moderately did not meet expectation (B)

1.3 Direct feedback from beneficiaries
The information available so far and recent exchanges indicate the following early responses:

- Brazilian government: EMBRAPA (for the Marketplace activities), MDS and the Brazilian Ministry of Foreign Affairs - MRE/CGFome (for the PAA Africa activities) have reported to DFID that ClimAA activities provide important support to the Brazilian government’s efforts to help reduce poverty and hunger in Africa and that the African country governments and public institutions involved appreciate this south-south cooperation and would like it to be scaled up.
- UN and other multilaterals: regarding the PAA Africa, according to FAO and WFP: “The work in the schools is benefitting the whole community. The school children have diversified meals at school, including fruits, a variety of legumes and meat and fish. The schools’ staff and the parents of school children have been trained on management of funds, and how to maintain the school gardens and apply new agricultural techniques and plant new products. The farmers who are selling to the school now have a stable market and can plan their production in advance, while they receive training in production and commercialization and manage to increase the proceedings of their work”
(Source: http://www.fao.org/partnerships/news-article/en/c/195839/)

Stakeholders and beneficiaries in African countries:

- On the PAA Africa, Senegal’s PM opened the DFID-funded workshop held in April 2013 commending PAA Africa as “an exemplary model of South-South cooperation”.
- Also about PAA Africa, Malawi’s Ambassador to FAO, Brave R. Ndisale, stated that PAA created supply chains and promoted favourable market conditions in the southern region of the country, which is food-insecure. Furthermore, she reported that the increased income of local farmers (half of which are women), generated by the programme, also strengthens the local economy and that the programme also improved students’ learning through quality school feeding. (Source: http://brazilafrica.com/alimentos/modelo-brasileiro-no-combate-a-fome/).
- In Ghana, a woman farmer was one of the people who received support from a national research institution partnering with Embrapa on a Marketplace project to cultivate cowpea (an edible legume) using Rhizobium bacteria inoculants, which help the plant to get more nitrogen needed to make protein and thus more grain. After about two years, she said: “I had a very good yield in cowpea compared to what I used to have previously. I used to harvest only five bowls (15 kg) from that same piece of land but with the introduction of the Rhizobium inoculants given to me I harvested ten bowls (30 kg) this season; I am very happy and I have been telling my fellow women to join me because it is a good product” (source: case study provided by EMBRAPA to DFID).
- On the Africa-Brazil Marketplace, the Forum for Agricultural Research in Africa (FARA) observed at the Brazil-Africa leadership forum held in November 2013 that: “The on-going strategic alliance program between Brazil and Africa on agriculture named “Africa-Brazil Innovation Market Place” has fostered series of collaboration between Africa researchers and Brazilian researcher from EMBRAPA. This has led to exchange of germplasm, technologies and different production and processing techniques. The projects within this partnership have generated a handful of successes that could be scaled-up and out for the benefits of more farmers in Africa. However, Africa will benefits a lot better from this strategic alliance if it’s debilitating infrastructure deficit could find a solution within this strategic alliance, especially if it could draw the attention of the Brazilian investors in bridging the financing gap for infrastructure development in Africa. The role of Brazil-Africa collaboration is vital and a positive partner that is willing to aid the Africa agricultural development”
(Source: http://www.fara-africa.org/apps/news/item/283/ )
1.4 Summary of overall progress
- In terms of outcomes, the project is still in its early stages though some results specifically around demonstrating the value of local purchasing programmes is showing progress with interest from countries outside of the five countries in which the local purchasing programme, PAA, is operating. In terms of uptake of Brazilian approaches and climate smart agriculture the first projects from MarketPlace are approaching completion. The potential of these small scale projects has been recognised by the Gates Foundation which now, due to the MarketPlace programme, is looking to sponsor the most promising projects to enable them to scale-up.
- It takes time to achieve timely progress on programmes of this kind. The “south-south” and “government-to-government” partnership involves significant transaction costs. GoB, DFID and the recipient country need to plan and mutually agree upon the programme objectives, activities and implementation modalities. It has been necessary to balance the need to achieve and demonstrate tangible and visible results in a timely manner with the need to take actions that are fully planned, negotiated, agreed upon and co-implemented by DFID, the relevant Brazilian government parties, implementing partners (UN agencies, CSOs, etc.) and recipient governments, to avoid misunderstandings and mistakes that could threaten and damage the overall UK-Brazilian relationship, not only in terms of programme implementation, but also in terms of bilateral relationship on foreign policy issues.
- Considering the significant progress achieved in the bilateral relationship since 2011 (particularly through the signing of three high-level partnership agreements to cooperate on programmes and policies regarding global development, health and climate-smart agriculture), most progress has been achieved against “relationship indicators”, rather than indictors related to actual programme implementation. This has resulted in behavioural and transformational changes in the relationship with the Brazilian government and organisations. For instance, there are now a range of relevant government parties with whom we are developing work plans (e.g. Min of Social Development - MDS, Min of Foreign Affairs - MRE, Min of Agriculture - MFA, Embrapa, to name a few.). This is facilitating “greater collaboration on global public challenges” around social development, agriculture, food and nutrition security, “with UK being a partner of choice” – demonstrated by increased join working with DFID in important programme-relevant international events and initiatives – e.g. the two nutrition-related events in London and the roadmap agreed up to the Rio Olympics; the Global Child Nutrition Forum (held in Bahia on May 2013);and the PAA and PAA Africa events, in Brazil and in Africa.

1.5 Key challenges
The key challenge is to work effectively within a Brazilian international cooperation system which is constrained in terms of both financial and human resources and which is currently unable to expand its activities significantly. The ways in which this can be addressed include: to continue to engage with ABC and other Brazilian institutions to identify areas for cooperation consistent with Brazilian objectives but which are low or no cost to the institutions; to strengthen collaboration with other trusted partners, such as the UN (especially UNDP, WFP and UNICEF) to take forward programming; and try to advance progress by working more directly with Brazilian state governments already engaged in international cooperation activities (such as the state of Bahia, interested in supporting south-south cooperation with focus on social protection.
The overall trajectory of Brazil’s development cooperation and of its overall public and private sector footprint in LICs is still expected to be firmly upward over the next 10-15 years.

1.6 Annual Outcome Assessment
The available evidence from negotiations with partners and implementation at this stage suggest that:

- The programme has facilitated Brazilian government discussions around DFID’s role in supporting south-south cooperation, which will make an important contribution to thinking about a future UK-Brazil development relationship which increasingly looks beyond Brazil borders, with increasing focus on Africa;
- The programme is facilitating Brazilian civil society’s engagement in development cooperation issues (with focus on agriculture, food security and nutrition) in a way which will be both useful for the government and the civil society, and will increase awareness and understanding of these issues.
- The programme is supporting DFID Brazil´s policy work with the Brazilian Government on Nutrition for Growth (N4G).

With the slow start to implementation and the uplifting of the programme resources in 2013 it is expected that the programme will request a no-cost extension in March 2015 in order to enable the programme outcomes to be fully achieved. Considering the nature of the uplift of resources in 2013 it is likely that a no-cost extension will be needed. This will be reviewed in the next Annual Review due by the end of October 2014.

Annex 2: ClimAA Programme Improvement Plan

Introduction:
The ‘Africa-Brazil partnership on climate-smart agriculture and food security: new tools and new approaches (ClimAA)’ aims to build more effective, climate-smart approaches to boost agricultural productivity, food security and poverty reduction through stronger Africa-Brazil cooperation. The Business Case was approved in 2012 with an initial budget of UK£10.8 million to March 2015. The ClimAA Business Case listed a number of pre-defined outputs under three topics, the topics and associated outputs were:

Productivity and Food Security
1. At least 30 new joint research partnerships linking Brazil with partners in Africa and the LAC region, to generate and inform useful smallholder-targeted products for improving productivity and food security in Africa, supported by capacity strengthening and knowledge exchange processes.
2. Lesson learning and strategy development on Brazilian systems of local food production and procurement for feeding programmes informing piloting in Mozambique, Malawi, Ethiopia, Senegal and Niger.

Climate-smart development
1. Climate smart-approaches mainstreamed into 1 above and 3 below.
2. Climate-smart agriculture approaches being tested in dedicated units in Ghana, Mozambique and Tanzania.
3. Additional capacity building/training on climate-smart agriculture provided for at least 180 African professionals.

Knowledge management
1. Robust evidence and practical decision making tools generated to help Brazil’s prospective development partners assess the feasibility of Brazilian innovations in their own contexts.
2. Flexible support for convening debate and supporting knowledge generating products (e.g. seminars, workshops etc) upon demand.

Three organisations had been initially identified to work under these outputs: The Brazilian Agricultural Research Corporation (EMBRAPA), World Food Programme´s (WFP) Centre of Excellence in partnership with the humanitarian office (CGFome) of the Brazilian Ministry of Foreign Affairs (MFA) and the International Food Policy Research Institute (IFPRI).

Once ClimAA was approved only the WFP grant was immediately signed as there were delays with the other grants[7]. Even with the WFP grant the money was paid under the general office development budget 201399 “The Global Development partnership Programme” as no project code for ClimAA had been opened. In October 2012 a new ARIES code was opened for ClimAA - 203707 but only the IFPRI project was added to this. Three projects had been planned with Embrapa but only one (MarketPlace) is currently being implemented. The other two projects were delayed due to changes in management but are now close to being finalised.
[7] IFPRI November 2012, WFP April 2012, Embrapa MarketPlace July 2013

In June 2013 WFP proposed another two projects costing UK£2.6 million pounds and a submission for these was approved, taking the total for ClimAA to UK£13.4 million.

An Annual Review (AR) of 201399 was conducted in April 2013 but didn’t include the ClimAA components under it. In December 2013 a second AR was conducted of 201399 which included ClimAA activities and activities from a new Business Case (Development Effectiveness) which had also originally been included under 201399. According to ARIES an annual review was also required for ClimAA at the same time and this was completed using the information from the AR from 201399. This complicated structure is in the process of being simplified with the activities being migrated from 201399 to the respective codes for ClimAA and the Development Effectiveness programmes and 201399 being closed down.

The ClimAA annual review in February 2014 scored the programme as a B. During the review it was also noted that none of the projects in ClimAA had been subject to Due Diligence, a requirement since January 2013.

It was decided that ClimAA should be subject to a PIP. Normally under DFID´s programme management system a project has to score two Bs over successive ARs or a C to warrant a PIP. However, in this case as 201399 had also scored a B for both its previous reviews it was felt a light-touch PIP was appropriate for ClimAA.

Methodology:
The PIP was drawn up by the lead adviser and commented upon internally within DFID Brazil. The PIP includes a number of actions which have already been taken by the team. These actions were the result of the team, which is relatively new, identifying at an early stage that the confusion resulting from the use of the 201399 budget code was leading to difficulties in managing the project. We therefore started a number of activities to rectify this.

In order to ensure the success of this PIP, the livelihoods and Climate Change advisor in the DFID Brazil Office, has been nominated as the person responsible for its execution.

Plan:
In terms of the three outputs from ClimAA, in the annual review output 1 scored an A, output 2 a C and output 3 a B. The main reason for the low scores was the delays in implementation, particularly in terms of output 2 where Embrapa had failed to produce proposals for two planned interventions. In output 3 there were also delays in the IFPRI programme and the production of a monitoring and evaluation plan. In terms of the uplift components these are roughly on time but have yet to be included in the logframe.

Thus the main objective of this plan is twofold:

- Firstly, to improve the programme clarity and accountability by tackling the confusion resulting from the mixing of codes on the ARIES system ;
- Secondly to improve implementation, programme quality and speeding-up the process of reaching agreements through increased engagement with partners, by reviewing the logframe and better monitoring and evaluation.

Table 1 below details the Programme Improvement Plan. The completion of this plan will lay the foundations for ClimAA to achieve an A in the next Annual Review. The plan however, cannot guarantee this as this will depend on how the new programmes perform once they are being implemented. ClimAA is currently receiving a B in the AR because of delays in implementation not because of the performance of projects being currently implemented this plan tackles this. This plan will also help us track the projects once they start but cannot guarantee improved performance.

Progress against the PIP needs to be approved by the responsible officer in DFID[s International Relations Division after 6 months for the project to be able to continue. This is likely to coincide with the next Annual Review of ClimAA( due in October 2014 but due to Brazilian Elections in October will be conducted early in August 2014). This will also provide an opportunity to carry out an independent review of the success or failure of the PIP and thus the continuation or not of ClimAA.

Table 1. ClimAA Programme Improvement Plan

Objective	Action	By When	Progress
			End Of March	End of June
1. To improve programme clarity and accountability	1.1 Bring all the programme components under one programme code (203707)	Existing Projects End March
	1.2 Produce Project Completion Review (PCR) and Close programme code 201399	End March
	1.3 Define Annual Review Timetable for 203707	Completed
	1.4 Build team´s capacity in Due Diligence (DD) through shadowing from DD Team	Mid May
	1.5 Complete Due Diligence for all partners and projects	End July

2. To improve implementation, programme quality and speeding-up the process of reaching agreements	2.1 Engage partners (Embrapa, WFP and PAA Africa) to complete remaining proposals including logframes and workplans . This should include how the programmes fit with DFID priorities on Women and Girls, Climate Change and Environment and local economic development.	Mid April 2014
	2.2 Review ClimAA logframe within DFID Brazil and agree changes.	End May
	2.3 Review M&E system and produce an M&E plan for the remainder of the programme	End July
	2.4 Obtain and agree revised workplan and updated proposal from IFPRI for fieldwork component	End March

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process