Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Programme for Improving Mental Health Care (PRIME) – Research Programme Consortium (RPC)
Programme Value: £6,057,045		Review Date: September 2014
Programme Code: 201446	Start Date: July 2010	End Date: April 2017

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	A	A+	A+
Risk Rating	High	High	High

Summary of progress and lessons learnt since last review

Recommendations from last review
The RPC needs to maintain progress and help those countries where progress has been slightly slower than expected, so that the key research programmes are completed on time.

Financial forecasting needs to be improved and it is important that the RPC does not allow the substantial additional funding from other sources to displace planned DFID-funded expenditure.

It will be important to continue to prioritise key research activities which lead directly to the planned outcomes. The RPC is producing important findings already and these should continue to be shared, as appropriate, with WHO.

## The RPC is working hard and has a clear, coherent strategy for carrying forward research uptake activities. In the next and subsequent years it will be important to gauge the impact that the various products, programmes and meetings are having, particularly to document any changes in policy or legislation that directly result from the RPC’s activities. Liaison with WHO will continue to be important.

## There was good early progress with capacity development activities which has been further consolidated in the second year. The RPC must carefully prioritise activities, using the additional external funding to build and not divert from the RPC’s activities. Continued liaison with WHO is important.

Summary of recommendations for the next year
Continue to focus on timely budget spend against the agreed projections. This needs further improvement during the next year. Important to ensure that substantial multiplier funding, which is most welcome and impressive, does not result in any displacement of DFID-funded expenditure, as this could potentially increase the underspend problems. This has not happened so far but RPC Senior Managers will need to keep under review.

As the RPC starts on the final phase (Scaling-up of proven interventions), important to quickly finalise any outstanding research studies, so that effective dissemination and research uptake can take place before the end of the RPC. Important to move on from research dissemination into genuine scaling-up of proven methodologies and to develop an appropriate indicator for this in the logical framework

Continue to focus on establishing strong working relationships with key policy makers, not only in Ministries of Health but also in Ministries of Finance and Offices of President. The short tenure of key policy makers is an acknowledged problem and can only be overcome by the investment of time and effort to provide orientation to new staff.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/

Outline of the programme

The need for mental health services is extremely high. Life time prevalence for mental disorders is between 12.2% - 48.6 % globally and the one year prevalence is between 8.4% - 29.1%. More than 13% of the global burden of disease is due to neuropsychiatric disorders. Almost three quarters of this huge burden lies in low and middle-income countries (LMIC) and this burden is projected to grow dramatically in the next decade, in part due to the demographic and epidemiological transitions in LMIC. Mental disorders are a major contributor to economic hardships and are strongly associated with social and economic disadvantage.

Despite this enormous burden, a multi-country survey supported by the World Health Organization (WHO) showed that almost four out of five people with severe mental disorders in LMIC had received no treatment whatever in the previous year. "Treatment gaps" were especially large for depression and alcohol use disorders. Where treatments are accessed, they are often inappropriate and involve considerable out of pocket payments, leading to catastrophic health expenditure.

The UK is providing £6 million over the period 2011 – 2017 to generate world-class research evidence on the implementation and scaling up of treatment programmes for priority mental disorders in primary and maternal health care contexts in low resource settings

PRIME is based in Ethiopia, India, Nepal, South Africa and Uganda. Comparing experiences across these diverse settings, which include fragile settings, will enable PRIME to generate knowledge with local and international relevance. By the end of the RPC, the following key research questions will have been answered:

What are the feasible and acceptable components and packages of care for priority disorders and how can they be integrated into routine primary health care and maternal health care?
What is the feasibility, acceptability, costs and impact of various models for delivery of the packages of care in routine primary health care and maternal health care settings?
What are the health system requirements for scaling up: human resources; training and supervision needs; infrastructure; drugs; budgets; and the incremental cost of increasing coverage per new patient treated? / What are the specific barriers which influence access to services for people living in poverty with mental disorders, particularly women during the perinatal period? / What is the impact of scaling up of the integrated mental health care plan on coverage and utilisation of mental health care?

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The RPC continues to benefit from strong management and supervisory mechanisms, along with clear organisational structures. These enable the RPC to work effectively with other key players to achieve the planned outcomes. The RPC has made efforts this year to reduce the problem of under-disbursement, but this continues to be an issue and will need strong management in the next 12 months. It has been explained to the RPC that carrying over of unspent balances is unlikely in the future.

Overall output score and description
The outputs from the PRIME RPC have moderately exceeded expectations (A+) and the RPC has had another successful year, delivering strongly in all major areas of activity, with the exception of budget spend against projections. The RPC is well managed and is demonstrating success in involving and even integrating the various countries and lead institutions, as demonstrated by the User Satisfaction Survey conducted for the first time this year. The RPC is managing its research portfolio, dissemination and capacity building programmes well and has made substantial progress, particularly in disseminating research findings internationally and through WHO. Progress has accelerated in all countries, including those that were experiencing some delays during the last reporting period. In summary, another strong year, making significant progress at country level, with fully established research programmes and effective research uptake measures, that are starting to answer important policy questions in-country and beyond. Another impressive year.

Key lessons
Difficulties with RPC partner institutions in India, who were struggling to pre-finance activities, have been somewhat improved by changing the Lead Institution. The Public Health Foundation of India has taken over the lead role from Sangath. Despite the changes, all targets have been met and some substantially exceeded. Devaluations of local currencies in several of the countries have led to significant exchange windfalls for the overall budget, which has exacerbated the issue of under-disbursement.

While mental health remains neglected in almost all countries of the world, the RPC has managed to make a major contribution towards efforts to reverse this neglect, particularly from the research uptake work in South Africa and India. Arguably, the RPC has started to show success in changing the general trend in the other participating countries, based upon the progress outlined in the last two annual reports. Through the formative research, and by compiling the data on the proportion of the global burden of disease contributed from mental health conditions, the RPC is helping WHO and others to increase the profile of mental health and to solicit for additional funding in the future. RPC senior staff also made a substantial input at the Wish Foundation, World Innovation Summit for Health, held in Doha, which had a strong focus on mental health.

So far, the RPC has been successful in retaining highly qualified and experienced staff, something that is always a challenge in low income countries. By building up local capacity, the RPC is helping to enable participating countries to steadily build up their research capacity and mental health services, though this is a long-term effort as several participating countries started from a very low level of capacity.

Key actions

Continue to focus on timely budget spend against the agreed projections, informing all partners that there can be no guarantees that any unspent balances can be carried forward to subsequent financial years.

Has the logframe been updated since the last review?

No. The Logframe was last updated in September 2013 after discussions with the University of Cape Town. As previous targets had been significantly exceeded, it was felt that more challenging targets were required to ensure that the programme continued to meet the high expectations already set. The framework will be discussed/reviewed at the next meeting of the Consortium Advisory Group.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Establish and maintain an efficient and well managed RPC which draws on the strengths of each partner to deliver a high quality research programme that achieves the RPC’s goal and purpose.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		Y/N Yes	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Proportion of the following key RPC deliverables completed in consultation with all consortium partners: - Contracts between partners - PRIME country personnel recruited - M&E framework including logical framework refined - Detailed financial management plan for Phases 2 and 3 - Capacity Building Plan agreed – Research uptake Plan agreed	Key programme documents have been reviewed and revised as needed during project to improve progress towards achieving outputs, purpose and goal of RPC, by 2017 / Completion of PRIME Consortium Satisfaction Survey	Completed for most and ongoing, up to timetable for others. / Completed
Number of meetings held during inception and implementation phases of key governance groups (PMG; CAG; CMG)	At least two meetings, one of which is face to face in 2014	Completed – Annual meeting in Kathmandu in April 2014.
Draft mental health care plans for priority disorders in primary care and maternal care available.	Completion of a draft integrated mental health care plan comprising packages of care for mental disorders for delivery in primary care by 2013 and beyond	Completed

Key Points
Country Advisory Boards (CAB’s) have now been established in all countries. User Representatives are involved in the CAB’s only in India at present but there are plans to identify suitable users’ representatives for the CAB’s in the other countries.

Summary of responses to issues raised in previous annual reviews (where relevant)
There has been some improvement in the pace of disbursement against budget projections, though this remains a problem, in part because of significant exchange windfalls, due to the devaluation of local currencies in several countries.

Recommendations
As the RPC starts on the final phase (Scaling-up of proven interventions), it will be important to quickly finalise any outstanding research studies, so that effective dissemination and research uptake can take place before the end of the RPC.

Continued focus needed to improve disbursement against projected spend. This needs further improvement during the next year.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	A coherent body of high quality, peer-reviewed and policy relevant research that makes a significant contribution to understanding the implementation and scaling up of packages of care for mental disorders
Output number per LF		2	Output Score	A+
Risk:		High	Impact weighting (%):	50
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Research project is implemented in countries	Evaluation completed in 5 PRIME study districts by 2015	On track, baseline studies completed in 4 out of 5 countries and plans in place to complete in South Africa, on schedule.
# of high quality policy relevant primary research papers by RPC partners published in peer reviewed publications. # of conference presentations by RPC partners.	20 papers published, / 10 conference presentations by 2015	On track / 14 papers published, / 16 conference presentations and / 3 poster presentations
No of partner institutions who collaborate and publish with each other.	All partners have collaborated on publications between 2013 and March 2015	On track , 5 (out of the 9) partners have collaborated with other partners since March 2013

Key Points

Strong progress overall. A remarkable number of papers and presentations for this stage of the RPC, which highlights the strong progress being made.

Good progress so far on enabling collaborations between RPC partners and more progress expected in the next 12 months.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

Keep up the good work! It will be important to quickly finalise any outstanding research studies, so that effective dissemination and research uptake can take place before the end of the RPC.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective communication of relevant research findings and their uptake by national and international stakeholders to influence policy and practice in the study countries and other low and middle-income countries.
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
# of PRIME products disseminated to policy makers and donors across relevant sectors via multiple channels (conferences, high level briefings, workshops etc.) at the following levels: Local, National, International	At least 15 PRIME products disseminated to policy makers and donors by 2015	14 PRIME products disseminated to policy makers and donors
Participation of mental health service users and community groups in mental health care	MH service users represented on the Community Advisory Board in all Districts by 2015	Countries planning to include service users in CAB once services in place
# of PRIME citations in the media	At least 50 media citations of PRIME or PRIME outputs by 2015	Research has been cited 23 times over the past year by a / wide range of media, including websites (13 articles), print (14 articles), radio (1 radio show) / and television (3 TV/video productions). The total number of cumulative media citations / (Unduplicated) over the first 3 years are 52.
# of citations of PRIME outputs in research articles or other academic publications, curricula or training materials	150 citations of PRIME outputs by 2015	PRIME outputs cited 258 times in academic publications (Google Scholar), 118 (Scopus)

Key Points
Really strong progress and the overall profile for PRIME outputs has been very high. This has generated considerable debate, within the countries and internationally, as to why mental health issues have historically been neglected and the need to make substantial improvements. The combination of strong research findings and a high media profile has raised awareness among policy makers and, particularly in South Africa, resulted in significant change.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

Keep up the good work. Important to move on from research dissemination into genuine scaling-up of proven methodologies and to continue to focus on dissemination with/through WHO.
## 2C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Capacity exists in study countries to conduct and effectively disseminate research to improve access to mental health care
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Number of externally funded policy-relevant research grants successfully applied for; and level of funding achieved.	4 externally funded research grants successfully applied for. > £10,000,000 in value by 2017	Multiplier funding successfully applied for with value >£10,000,000
Number of researchers who complete higher training and/or successfully apply for fellowships	4:10 (M:F) PRIME researchers registered and PhD program started , 50 registered or completed master’s program started, 1 successfully applied for fellowship by 2015	5:10 (M:F) PRIME researchers registered or in the process of completing registration for a PhD; 68 registered and begun structured Masters programs; 3 researchers successfully applied for fellowships
Number of research publications and other research outputs by PRIME partner groups	Research publications by partner groups increase by 10% from 2012 by 2015	There has been an average 20% increase in 2013 compared to 2012 across partners.

Key Points

2 x 2 day research proposal writing workshops and 1 x 2 day gender mainstreaming workshop, were planned, conducted and evaluated.

A number of challenges exist regarding the uptake of PRIME research. As the results of the research from PRIME are now starting to be published more rapidly, the opportunities for research uptake are increasing. A challenge faced when engaging policy makers includes the high rate of turnover amongst government officials in some countries (particularly India and Nepal), as well as competing time pressures amongst PRIME Ministry of Health partners. Little can be done to address the high turnover amongst some policy making partners, except to ensure regular engagement amongst new policy partners assigned to work with PRIME.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations
Continue to focus on establishing strong working relationships with key policy makers, not only in Ministries of Health but also in Ministries of Finance and Offices of President. The short tenure of key policy makers is an acknowledged problem and can only be overcome by the investment of time and effort to provide orientation to new staff, as soon as possible after they come into post.

Important to ensure that substantial multiplier funding, which is most welcome and impressive, does not result in any displacement of DFID-funded expenditure, as this could potentially increase the underspend problems. This has not happened to date but will need continuing vigilance.

Risk rating for this output should be raised from low to medium to reflect the complexity of working in an area with high staff turnover.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The development and implementation of high quality research programmes, combined with adequate dissemination and building up of local research capacity, are costly processes. Key cost drivers are direct and indirect staff, travel costs, research consumables and related transport and supervision costs.

The RPC is fully aware of the need to work carefully within the planned budget. Costs have been contained and there has been some slippage in disbursement, though this has improved in the last 12 months – underspending is a general issue across all of our RPC interventions. Most of the participating countries have seen some slippage of exchange rates for the local currency, taken against international hard currencies, and in some countries there have been substantial devaluations. As the programme budget is denominated in Pounds sterling, and funds are only transferred into local currencies as the funds are directly required (to protect DFID funds against exchange fluctuations), the overall RPC budget has so far received significant exchange rate windfalls, thus potentially increasing the issue of under disbursement. DFID staff have discussed the issue with senior RPC staff and all RPC partners have been made aware of the problem. The RPC is currently implementing additional research and capacity building activities, in order to ensure the budget is on track as quickly as possible. DFID staff will continue to review the situation.

VfM performance compared to the original VfM proposition in the business case
Funding high quality research into neglected chronic diseases, such as mental health, provides value for money through: reducing the impact and burden of mental ill health; encouraging governments to provide essential services which are able to intervene early, before a lengthy and potentially costly mental breakdown or in-patient admission. This ensures that individuals with mental health conditions, and their direct families, are able to function in employment or farming, instead of becoming a burden on local communities or governments.

The macro-economic impact of mental ill health is very significant, with an estimated 13% of the global burden of disease being due to neuro-psychiatric disorders. Almost three quarters of this huge burden of disease falls on low and middle income countries. Most important of all, it is projected by WHO that this global burden is projected to grow dramatically in the next decade, in part due to demographic and epidemiological transitions. Mental disorders are a major contributor to economic hardships and are also strongly associated with social and economic disadvantage.

Assessment of whether the programme continues to represent value for money
The programme is delivering good value for money and it is likely that there will be substantial long-term impacts from the research, not just in the participating countries, but in additional countries through dissemination using WHO channels and through peer-reviewed publications and policy briefs. The RPC is paying careful attention to cost containment and is maximising the use of telephone and video conferencing, in order to reduce travel and subsistence costs.

Quality of financial management
The quality of financial management is high and senior staff of the RPC carefully calculate, monitor and manage the use of funds. The University of Cape Town, has a strong reputation for careful management and financial oversight. The PRIME Management Team has endorsed a new “Counter Fraud and Anti-Corruption” policy, on the advice of DFID. There have been no difficulties reported with misappropriation of funds. The RPC Prime Management Team is effectively overseeing all aspects of the programme and has performed well during the first three years. There has been a temporary staff change in the key coordination role (during the year), however this position has been filled seamlessly with no effect to the smooth running of the programme.
The RPC has established strong functioning mechanisms for management and oversight including the Prime Management Team and the Consortium Advisory Group (CAG). The Prime Management Team, which includes all participating lead institutions, meets periodically to oversee RPC activities. The CAG and Community Advisory Boards have also been established to feed-in external points of view.

Date of last narrative financial report	23/05/2014
Date of last audited annual statement	19/08/2014

E: RISK (½ page)

Overall risk rating: High
Overview of programme risk
Although performance has been strong, on balance, we continue to judge that the RPC should remain high risk overall. This has been reviewed by DFID staff, as recommended in last year’s annual review. The reasons for the high risk rating are because mental health services are under-resourced in many countries and there is a risk that high quality research findings will not result in changes to policy and practice, due to a lack of staff and other resources.

The RPC Prime Management Team and the Consortium Advisory Group regularly review the risks. As mental health is still a relatively low priority for many Ministries of Health, despite the considerable contribution to the overall burden of disease, it is difficult to guarantee that staff and financial resources will be forthcoming, as required, to step-up high quality mental health services. The RPC is operating across five countries, Ethiopia, India, Nepal, South Africa and Uganda, which includes fragile settings.

Risks related to the research portfolio and management are reducing and there is strong evidence of engagement by national and local authorities, but still relatively little funding being made available for mental health services, so sustainability concerns remain in the medium to long-term. Risks related to non-technical issues such as funding and organisational functioning, supervision and management are assessed by the Prime Management Team and the Consortium Advisory Group. The main risks this year have been related to delays in budget spend against projections and some exchange rate devaluations, but the earlier difficulties with pre-financing RPC activities in India have largely (but not completely) been resolved.

For DFID, the main risk remains that there will be insufficient uptake of the high quality research, as Ministries of Health struggle to provide essential services. Strong engagement with WHO and with participating governments does mitigate this risk, to some extent, but for now the overall programme remains high risk, high potential impact. DFID staff will discuss in more detail with the RPC staff, to strengthen the language on risks in the logical framework.

Outstanding actions from risk assessment
None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Substantial progress has been made on the research agenda, dissemination, publication and research uptake. This gives a high level of confidence that the activities can be completed within the planned timeframe. (There are difficulties regarding disbursement of finances against the planned budget timetable, which have been discussed earlier.)

Performance of partnership (s)

The Consortium is running very well and levels of satisfaction are high, based on the PRIME Consortium Satisfaction Survey, conducted for the first time during this reporting period. RPC Senior Managers are following up on the few areas of concern identified during the survey and will report back in the next narrative report, including efforts to achieve a higher rate of return of the survey questionnaire. Efforts will also be made to include Users in the Community Advisory Boards, as only India has these representatives at present.

Asset monitoring and control Effective systems are in place, including asset registers in each country programme, and these are monitored during routine supervision and country visits by the CEO.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
This is not applicable because the RPC model does not use partnership principles for management and monitoring of programmes. There are no other specific conditions to the core funding provided by DFID.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

All nine DFID-funded RPC’s are being externally evaluated during the second half of the financial year 2014-15. The findings for each RPC will be followed-up during the subsequent visits and details will be reflected in the next annual report.

Monitoring progress throughout the review period
This review was carried out by members of the Human Development Team in DFID’s Research and Evidence Division, with input from health advisors in Policy Division, the DFID South African Office, and members of the consortium. During the reporting period, members of the review team met with the consortium a number of times, along with regular engagement through email and telephone contact. Members of PRIME also presented at DFID’s internal educational events, including the continuing professional development conference in India in January 2014.

In December 2013, two members of the team visited PRIME field sites in South Africa and had face-to-face meetings with PRIME members to discuss progress and cross-consortium working.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogramme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process