Annual Review – post April 2018

Title: Improving the Management of Public Funds for the Benefit of People in Burma
Programme Value £ (full life): £20m		Review Date: February 2019
Programme Code: 203996	Start Date: 4 March 2014	End Date: 31 December 2019

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	A	A	A	B	A
Risk Rating	Severe	Severe	Severe	Severe	Major

DevTracker Link to Business Case:	Link 1
DevTracker Link to Log frame:	Link 2

A. Summary and Overview

Description of programme

DFID is providing £20m over five years (2014-2019) to improve the collection, management and use of public funds for the benefit of the people of Burma. The purpose of the programme is to support efficient, accountable and responsive delivery of public services through the modernisation of the Government’s PFM systems and strengthening institutional capacity. The programme was restructured in 2018 to end its financial support to the World Bank Recipient Executed Trust Fund (RETF) and to refocus activities on strengthening subnational authorities, increasing budget transparency and raising accountability over extractive industries. The three active components of this programme are:

PFM modernisation programme (corresponds to outputs 1-5) – £14.4m has been allocated to the World Bank Institutional Strengthening Window in support of the Government’s PFM modernisation strategy. This component has supported improved tax administration, budget planning and execution, and external oversight. Funding provided to the RETF ended in 2018, and DFID will maintain oversight until remaining activities are successfully concluded.

Social accountability (corresponds to outputs 6 and 8) – There have been two projects under this component. The first funded an advisor embedded in the MoPF to improve fiscal transparency between 2015 and 2016. The second provides a £2m grant to The Asia Foundation (TAF) to support subnational PFM through assistance to State & Region governments/parliaments, Development Affairs Organisations (DAOs) and Civil Society Organisations (CSOs).

EITI (corresponds to output 7) – Up to £3m is allocated to assist Burma’s participation in the Extractive Industries Transparency Initiative (EITI). There have been two phases under this component. The first funded the Myanmar Development Resource Institute’s Centre for Economic and Social Development to act as an interim secretariat until 2016. The second provides funding (£2.1m) through the World Bank to support the multi-stakeholder group’s work plan, including the independent country report, a mining cadastre and forestry work.

Summary supporting narrative for the overall score in this review

The overall programme score has increased to ‘A’ this year following a number of outputs relating to the PFM modernisation programme getting back on track following protracted delays. The contract for the Integrated Tax Administration System (ITAS) was signed in November and is now in development. Once completed, this system will be pivotal in fully implementing the self-assessment tax system which will raise revenue and reduce the scope for corruption in the tax authority. The contract for the Core Banking System (CBS) is also expected to be signed in February 2019. CBS will improve budget execution efficiency and financial reporting by electronically processing all government transactions. This will support more effective service delivery and raise accountability over government expenditure. A PFM curriculum has also been developed (awaiting final approval) for the PFM Academy which will systemise capacity development across the Ministry of Planning and Finance (MoPF) alongside other government departments in the future. There has been an improvement in budget transparency at the Union level and increased public participation in the budget process at the subnational level. Finally EITI reports covering 2014/15 and 2015/16 were published in March 2018, and activities around extractives reform including the mining cadastre and beneficial ownership have progressed over the review period.

However, a number of outputs have not yet been completed, including the application of electronic budget submissions by line ministries, the approval of the procurement law and the development of the mining cadastre. Furthermore, while the recent formation and expansion of extra-ministerial bodies, such as the National Economic Coordination Committee and apparatus around the project bank, provides opportunities to increase the pace of reform, they also create new challenges around improving inter-governmental co-ordination and institutional sustainability.

Recommendations for the year ahead

Having ended funding to the World Bank’s RETF for the PFM project in 2018, DFID will need to maintain oversight over the outstanding ITAS and CBS procurements to ensure they are successfully implemented and the project is responsibly closed. The MoPF has requested a 12 month extension to the World Bank grant agreement to ensure the successful execution of these major procurements. It is therefore recommended that the DFID PFM Programme receives a 12 month extension through to the end of 2020 so as to maintain oversight until project closure.

A number of other activities funded through the RETF are due to conclude by September 2019. DFID and the World Bank should conduct a sustainability assessment of these activities and utilise remaining project funds, including from the Bank Executed Trust Fund (BETF), to maintain support where there is risk that key results will not be sustained. Alternative funding sources should be considered where the project is unable to provide the appropriate level of assistance.

There has been a significant increase in the opportunities for public participation in budget processes at the subnational level. This should be consolidated, and where possible, formalised by continuing support in this area. However, opportunities for public participation in the budget at the Union level remain scant. DFID should build on the progress made at the subnational level to identify opportunities that improve public participation and citizen engagement at the Union level.

Subnational activities delivered through TAF are due to conclude in April 2019. Given strong progress made to date and alignment with new DFID Burma priorities around decentralisation and transparency, it is recommended that a one year cost extension is provided to sustain subnational PFM reforms and strengthen decentralisation through the proposed successor programme ‘Accountable and Inclusive States & Regions’.

Burma has made strong progress towards achieving validation as an EITI compliant country. However, there are both institutional and financial challenges to sustaining this progress. DFID should engage in the EITI Myanmar governance review process to engender a more efficient and sustainable multi-stakeholder led operating model than the current governance arrangements. Financial resources should also be identified to ensure a continuation of transparency activities and initiation of new reforms that build on the progress made to date. DFID should also create political impetus towards delivering beneficial ownership and mitigating the risk of fatigue.

Following the violence in Rakhine and continuation of conflict in Kachin and Shan states, DFID Burma will focus on addressing the underlying institutional issues that remain following 50 years of military dictatorship. Many of these issues relate to poor governance over the economy, weak accountability between the citizen and the state, and inequitable service delivery across the country. With the current programme due to start concluding activities from April 2019 onwards, there is an opportunity to develop a new business case which targets reforms that address these underlying issues while maintaining the core progress made in the current programme.
## B: DETAILED OUTPUT SCORING

Output Title	Increased tax revenue for delivery of public services
Output number per LF		1	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Number of large taxpayers completing self-assessment	250	Exceeded: 861 large taxpayers / Source: Internal Revenue Department

Provide supporting narrative for the score

Output 1 relates to Component A of the World Bank’s Modernisation of PFM programme, the strengthening of tax administration by providing support to the Internal Revenue Department (IRD).

Programme funded activities over the past year have included:
1. Three embedded tax advisers to support and build audit capacity in the large and medium taxpayer offices (LTO, MTO-1). One had also been engaged in the previous review period;
2. Integrated Tax Administration System (ITAS) contract signed in November 2018, vendor team have begun preparing implementation plan;
3. Engagement of international IT expert to support ITAS implementation;
4. Installation of data centres in Yangon and Naypyitaw.

The number of taxpayers completing self-assessments has continued to exceed the milestone indicator set out in the World Bank results framework. In addition to the 861 large taxpayers who completed self-assessments, 1,871 self-assessments were received from taxpayers to MTO-1. Reports indicate that all large taxpayers and 98% of medium taxpayers submitted their annual returns on time in 2018. The LTO collected 65% of all Corporate Income Tax in 2017/18, up from 27% in 2015/16. The programme can partially attribute these results as the International Monetary Fund (IMF), US Office of Treasury Assistance (USOTA) and Japan (JICA) have also provided support to IRD for the LTO and MTO-1.

International advisors have developed a basic audit case management system and are providing on-the-job training for the LTO and MTO staff (senior staff officers/audit team leaders) on conducting tax audits and applying the audit process manual. The advisors have also supported the audit teams in identifying areas of tax evasion, complex audits, and industry-specific issues related to audit and compliance management. This has helped increase the average tax collected per large taxpayer by 40% in 2017/18 compared against 2016/17. The move to self-assessment has shifted the burden of ensuring reporting compliance to the post-assessment stage, increasing the importance of effective audit, and reducing opportunities for corruption by front office tax collectors. The IRD view these advisors as essential to increasing the capacity and confidence of audit staff, as well as supporting the integrity of tax auditors.

After significant delays in developing the technical specifications for the Integrated Tax Administration System (ITAS), the procurement for ITAS has now been completed. The contract was signed in November 2018 and the vendor team has begun working with IRD to prepare an implementation plan. However, there is a risk that the vendor will be unable to fully install ITAS within the 12-month period as specified in their bid which may necessitate an extension to the contract. There is a further concern that some features of Burma’s existing tax law cannot easily be configured in the ITAS procured. If the unified Tax Administration and Procedures Law (TAPL), submitted to Parliament for approval passes soon this will not be a problem. However, in case this is delayed, IRD should work with the vendor to establish possible interim solutions as part of the implementation plan.

Data centres have been installed in Yangon and Naypyitaw. To date these have helped network the key IRD offices and provide e-mail, desktop applications and document sharing. They were also intended to support ITAS, however IRD have already identified a need for upgrades, which they plan to finance through government resources.

This output scores an A as the output indicator – number of large taxpayers completing self-assessments – has exceeded the target, and the second phase of procurement for the ITAS was completed and the contract signed in the review period. Despite significantly exceeding the milestone for large taxpayers, the output is not scored an A+ as the attribution is only partial and the related outcome indicator – tax to GDP – remains off track.

Lessons identified this year, and recommendations for the year ahead linked to this output

It is apparent that the changes to business processes and organisational structure needed to support implementation of ITAS will be significant. IRD has made it clear that they have limited capacity to implement any additional reforms and intend to work in line with their current reform strategy. There is support for the development of a Medium-Term Revenue Strategy (MTRS), but with the hope of shifting reform pressure and revenue demands to other revenue generating bodies, rather than reconceptualising IRD’s own strategy. At the working level, there is good coordination between staff and consultants of the World Bank, IMF, and USOTA, but it is not clear that there is effective coordination between development partners at the strategic level.

Recommendations:

The World Bank should prioritise supporting IRD to implement ITAS, including through BETF resources, to ensure implementation is complete by the time the programme closes. Technical assistance may be needed to support the shifts in business processes associated with the implementation of the ITAS.

The World Bank should identify options to continue funding tax advisers to provide audit support to IRD to support capacity development and a culture of integrity that mitigates the risks associated with the shift to self-assessment.

DFID should explore options for possible support to bridge any funding gap between the end of this programme and commencement of the next. Sustaining momentum is critical for the successful implementation and effective utilisation of ITAS to support compliance improvements and increased revenue collections.

The World Bank, DFID, and other relevant development partners should better coordinate support to IRD at the strategic level, with a focus on supporting IRD to achieve its current reform strategy, including implementation of ITAS.

DFID and the World Bank should engage with Government and the IMF if a decision is made to develop the next MTRS. DFID should steer any MTRS towards being developed through a genuinely cross-departmental and consultative process and encourage alignment with DFID’s own policies around MTRS good practice.

Output Title	Improved budgeting and planning
Output number per LF		2	Output Score	B
Impact weighting (%):		10	Impact weighting % revised since last AR?	No

Indicators	Milestones	Progress
Improve the information base for linking budgets to plans: Number of departments submitting forms: / recurrent budget; and / capital budget (both) forms electronically	40 / 40	0 (Not achieved) / 157 (Achieved)

Briefly describe the output and provide supporting narrative for the score

Programme funded activities over the past year have included:
1. Technical assistance and training provided to MOPF, ministries, 146 union departments and 32 SEEs in anticipation of the formal adoption of electronic submissions (including in-depth training mission by expert in December 2018);
2. Support provided to the Project Appraisal and Progress Reporting Department (PAPRD )to develop project appraisal guidelines, along with relevant forms (Project Proposal Form and Project Monitoring Form);
3. Support provided to PAPRD to compile capital projects database for key ministries;
4. Procurement of specialist tools for PAPRD to support site inspection; and
5. Training on macroeconomic forecasting and policy analysis provided to the Department of Planning.

At the time of the last annual review, implementation of electronic budget submissions was planned for the 2018/19 Budget. However, this was postponed due to the change of fiscal year and the need to prepare two budgets, the 6-month transitional budget (April – September 2018) followed by a full year budget (October 2018 – September 2019). The Budget Department now aims to commence the use of electronic submissions for the fiscal year commencing in October 2019 and intends to implement the change over a three-year transitional period during which both hard copies and electronic submissions are received. For the second year, the Planning Department received capital budgets submissions electronically from all 157 line ministries and state administration offices. The World Bank has provided technical assistance and training on electronic submissions, including supporting pilots within some select ministries.

The Planning Department has also received training in macro-economic analysis and forecasting in the review period from the World Bank macro-fiscal team. These needs had been identified through a mapping by Planning Department of their institutional and human resource capacity requirements. The Budget Department’s Medium-Term Fiscal Framework (MTFF) – which combines top down fiscal aggregates (revenue, expenditure, and financing) with bottom up prioritisation across ministries over the medium term to guide annual budget making decisions – was successfully maintained in the reporting period, ensuring a prudent fiscal deficit.

Project appraisal guidelines, developed by PAPRD with WB support in consultation with line ministries, were approved by the MOPF Minister in September 2018. The guidelines are intended to help to improve efficient and effective spending on public investments. However, the guidelines have not been issued to ministries due to ongoing internal consultations, though may apply for the 2020/21 budget period to assess projects screened and prioritised under the Project Bank[1]. PAPRD report that they intend to redraft the appraisal guidelines to re-submit to the Minister, with an expectation that they are approved within the year.
[1] The project Bank is a government mechanism launched in December 2018 which is intended to publically screen and appraise high value projects against delivery of the Myanmar Sustainable Development Plan

The World Bank has also supported MoPF, the Myanmar Development Institute (MDI) and the National Economic Coordination Committee to develop screening tools for feasibility studies and appraisals, and has helped develop a database of large capital investment projects across eight key ministries. Measurement tools for site inspection and monitoring are also being developed, and the necessary training is being provided.

This output scores a B as the shift to the submission of electronic budgets to Department of Budgets for recurrent expenditure has still not happened.

Lessons identified this year, and recommendations for the year ahead linked to this output

The lack of clarity and potential overlaps between work under this programme on project appraisal guidelines for PAPRD and development of the Project Bank suggest a need for greater engagement by the Bank team with government on reform efforts outside of the MoPF to ensure cross-government understanding and coherence.

Recommendations:

The World Bank should continue to support MOPF and line ministries in preparation for the submission of electronic budgets covering both capital and recurrent expenditure for FY 2019-20.

DFID and the Bank should ensure there is cross-government understanding around the application of the project appraisal guidelines and the processes for new Project Bank. Given DFID’s engagement with the Project Bank through the Cities and Infrastructure for Growth programme, DFID should support opportunities for increased coordination between PAPRD and MDI, the organisation responsible for the Project Bank.

DFID should revise its log frame in line with the amended World Bank results framework to better capture all activities undertaken with the Budgets, Planning and Project Appraisal departments by the project.

Output Title	Improved budget execution
Output number per LF		3	Output Score	B
Impact weighting (%):		10	Impact weighting % revised since last AR?	No

Indicators	Milestones	Progress
Timeliness of budget execution reports (number of months after end of period)	<3	Achieved: 2.5 - Treasury Department submits budget execution reports two and a half months after the accounting month. / Source: MoPF
Availability of information on public procurement outcomes	75%	Not achieved: Availability is not yet systematically recorded. Procurement Law has not yet passed and is with the Office of the Auditor General. / Source: MoPF
Budget holders empowered to execute budget within clearly defined procedures and regulations that are consistently enforced	Updated rules and regulation published (2017)	Achieved: The Financial Rules and Regulations were updated by the MOPF during FY 16-17 and approved by the Government in April 2017. They have since been put on the MOPF website. / Source: MoPF

Provide supporting narrative for the score

Output 3 relates to Component C of the World Bank’s Modernisation of PFM programme, supporting effective budget execution and financial reporting.

Programme funded activities over the review period have included:
1. Procurement of the financial reporting system for Treasury (FIRST) software is at the negotiations stage, with signing expected in February 2018;
2. Server room in Treasury set up to host applications (including FIRST);
3. Support to Myanmar Economic Bank (MEB) for procurement of Core Banking System;
4. Procurement of a remote location Recovery Data Centre for MEB, (installation by May 2019); and
5. Support provided to MoPF and Office of the Attorney General in preparing draft procurement law and a draft of the Implementing Rules for public procurement.

The Treasury Department has continued to use manual methods for its cash management and accounting & reporting functions over this review period. There is a delay of up to two months in receiving expenditure statements from the Myanmar Economic Bank through the Central Bank, which is unchanged from the previous review period. Treasury Department reconciles budget execution reports monthly within 10 days of receipt of financial reports from the Central Bank, and submits to Ministry of Planning and Finance, Cabinet, and Office of the Auditor General.

During the previous review period, the Treasury Department independently identified a local provider to develop a bespoke financial reporting system (FIRST) and requested this be funded under the programme. The system would allow Treasury to reduce the time it takes to produce budget execution reports from 10 days to 2 days. To establish the suitability of the system, the IMF – who had assessed the financial management information system requirements of Treasury Department in October 2017 – evaluated the proposed system and provider in 2018. IMF recommended that FIRST was a suitable interim solution given implementation of an integrated financial management system is several years off, and this was approved by the World Bank’s Regional Governance Practice Manager. A low value single source procurement compliant with World Bank rules is in progress. Treasury Department expect the contract to be signed in February 2019 and the system installation completed in June 2019.

Procurement of the Core Banking System (CBS) for the Myanmar Economic Bank (MEB) has made significant progress during the review period. All relevant World Bank approvals have been granted and Union Government approval is expected to be completed by February 2019. The MEB is the fiscal banking agent of the government and has commercial operations. The CBS will improve the connectivity of the MEB’s branch network; provide the government with quicker access to revenue and expenditure information; and deliver an easier and more secure real time payment system. However, funding will only support the rollout of CBS to the 86 largest branches of MEB’s 325 branch network. Until the entire network is covered, the financial statements required by Treasury Department to produce budget execution reports may not be produced significantly faster. Due to the earlier delays in the procurement process, there is a risk that implementation of this phase of the CBS will overrun the lifetime of the programme, even if the proposed extension is approved.

The development of the Procurement Law has progressed, albeit slowly. Comments from development partners, line ministries, and the private sector were incorporated in this review period, with support from the World Bank. The draft law is currently with the Attorney General’s office for finalisation, to be submitted to Parliament soon for consultation and approval. MOPF now expect the Procurement Law to be signed in September 2019, and the associated regulations finalised in 2020.

This output scores a B as although the timeliness of budget execution reports by Treasury Department meets expectations, progress on the procurement law has been slow.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendations:

The World Bank team should ensure that MEB stays on track to implement the Core Banking System by the December 2020 extended project completion date. The WB should ensure additional support is available during the contract negotiations if needed. Following this, momentum must be maintained for implementation. Close monitoring should ensure that WB become aware of any issues early and can support MEB to resolve them.

The World Bank and Development Partners should work with Government to establish a source of funding to roll CBS out to the remaining 239 branches not covered under this programme. Given that MEB is a commercial bank, albeit state-owned, opportunities for self-financing ought to be explored alongside external options.

The Bank should continue to engage on the Procurement Law as it undergoes consultation in parliament. It should continue to maintain the impetus for a law based on international best practice that provides flexibility for the Ministry of Planning and Finance to continue to enhance standards in the future.

The World Bank should ensure that the procurement of CBS and other activities undertaken with MEB is coordinated with the ongoing reform of State Owned Banks.

Output Title	Improvement in institutional PFM capacity for implementation
Output number per LF		4	Output Score	A
Impact weighting (%):		10	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
Number of beneficiaries of / (i) training courses and (ii) training module on revenue and expenditure incidence analysis (including by gender, income group and region)	(i) 300 / (ii) 60	7,900 (Exceeded) / 0 (Not achieved)

Provide supporting narrative for the score

Output 4 relates to Component E of the World Bank’s Modernisation of PFM programme, skills base and project management.

There has been considerable progress on the PFM Academy in this review period following earlier delays. A physical location for the Academy was agreed and facilities constructed using government funds. The Association of Chartered Certified Accountants (ACCA) has drafted a PFM curriculum, which has been reviewed by the WB team. MoPF expect to provide feedback in the coming month, and have the curriculum finalised in March 2019. Once the curriculum is finalised, procurement for a training provider will commence.

In the review period, a temporary Learning Centre was established within MoPF in which to run trainings until the PFM Academy is complete. Under individual project components training has been provided on topics including tax, budgeting, macro forecasting, planning, project management, accounting, reporting and auditing. The bulk of the training has been on IT and English training courses, however. This has led to the total number of beneficiaries far exceeding the expected milestone, despite the PFM academy not yet coming into operation. The programme has not yet conducted revenue and expenditure incidence analysis training as originally planned. However, given the low capacity and other more basic training and development needs, it is not clear that such training would be helpful.

The output scores an A because although no incidence analysis training has been conducted, the total number of beneficiaries of training courses has substantially exceeded expectations and meaningful progress has been made on the PFM academy and curriculum in this review period.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendations:

The World Bank should continue to support the Government to finalise the PFM curriculum so that procurement of training providers can commence.

The World Bank and DFID should consider possible funding sources for training providers to deliver the PFM curriculum given that this is not budgeted within the existing programme. Training providers would likely be a combination of locally and internationally based expatriate consultants (given the low PFM capacity in Burma), which would be difficult to fund through the Union budget.

DFID should amend the log frame output indicator to remove reference to incidence analysis training and replace with training modules linked to the new PFM curriculum. Results on capacity development should also be gender disaggregated.

Output Title	Improved transparency in the mobilisation and use of public funds in line with global good practice showing improvements in competency-based assessments
Output number per LF		5	Output Score	B
Impact weighting (%):		10	Impact weighting % revised since last AR?	No

Indicator	Milestone	Progress
Timeliness of submission of audit reports to parliament by the Office of the Auditor General	<10 months	10 months (Achieved) / Source: Office of the Auditor General

Provide supporting narrative for the score

Output 5 relates to Component D of the World Bank’s Modernisation of PFM programme, fostering external oversight and accountability.

Programme funded activities over the review year included:
- Data centre installed in Office of Auditor General (OAG) and networking completed;
- TORs for IT Audit strategy and procurement of IT consultant to develop strategy completed;
- Training for parliamentarians provided by WB-funded Budget, Audit and Economic consultants on budget oversight and audit report review;
- New ICT skills training (Dec – Jan 2019) provided to state and regional Joint Public Accounts Committee (JPAC) members

The Office of the Auditor General’s audit report for FY2017-18 was submitted to parliament within the target timeframe for this review period. Although they have not yet received the requisite financial statements from Treasury Department, OAG expect to complete the audit report for the 6-month Budget (April - September 2018) by April 2019. The Treasury Department’s adoption of FIRST could support further improvements in timeliness of audit reports as it should provide a more consistent and timely set of financial statements.

The installation of the data centre and networking for the OAG was completed in the review year, providing a platform to support future IT audits. Terms of reference for the IT audit strategy were completed in July 2018, but contracting delays have meant that an IT consultant has only commenced work in early February 2019. In addition to developing the IT audit strategy, the consultant will support data centre training and operation and develop an IT audit management system. OAG expect to commence pilot IT audits in late 2019. IT audits will reduce the demand on human resources, thus increasing efficiency, and enable OAG to effectively scrutinise government IT systems. OAG is also working to build capacity for environmental audits and performance audits with external support.

JPAC published their review of the Union audit report for FY 2016-17 in August 2018, within 6 months of receiving the report. The PFM programme has funded two locally-engaged technical advisers to help strengthen JPAC’s budget oversight function. Training was provided to parliamentarians on budgeting and planning, monitoring & oversight, debt management, macro- economic issues, governance and service delivery. These functions are important given the limited technical capacity within the JPAC despite their important oversight role. The JPAC has valued this support and has requested for it to continue.

The output scores a B as while the submission of audit reports to parliament by the Office of the Auditor General are timely, they are not made public.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendations:

The World Bank should engage with the Office of the Auditor General and IT consultant on the IT strategy as it develops to ensure it is fit for purpose and aligns with the terms of reference and International Standard of Supreme Audit Institution

Output Title	Improved citizen and civil society engagement
Output number per LF		6	Output Score	A+
Impact weighting (%):		10	Impact weighting % revised since last AR?	No

Indicator		Milestones	Progress
6.4	Publication of the eight key Union budget documents identified by IBP	Improvement over previous year (three documents published on time and made available to the public online.)	Achieved / Four budget documents were published on the MoPF website on time. / Source: MoPF Website
6.5	Number of States & Regions producing the following fiscal documents in the previous fiscal year: / i) Citizen's Budgets / ii) Reform Priority Documents / iii) Regional Economic Development Plan / iv) Budget Briefs	i) 8 / ii) 4 / iii) 2 / iv) 3	Exceeded / i) 14 (9 directly supported by TAF) / ii) 6 / iii) 2 / iv) 4 / Source: TAF
6.6	Number of States & Regions conducting events in the previous fiscal year: / i) Citizen Budget launch events / ii) Budget Transparency Regional Forums / iii) Budget Literacy Trainings / iv) Dialogue Sessions	i) 8 / ii) 6 / iii) 6 / iv) 5	Exceeded / i) 9 / ii) 6 / iii) 10 / iv) 5 / Source: TAF

Provide supporting narrative for the score

This output relates to the social accountability of government to its citizens through supply side factors (transparency, openness to public participation) and demand side factors (engagement and capacity of civil society in budgetary issues).

During the review year, the Union government published on its website four of the eight budget documents identified as key requirements by the Open Budget Survey (Executive’s Budget Proposal; Enacted Budget; Citizens Budget; and Year-End Report). This represents an improvement since 2017, where only the Enacted Budget and Year-End Report were published on its website on-time.

The Union Citizen’s Budget (which was originally supported by a directly engaged consultant and then subsumed by the national World Bank PFM programme) was well received across government and civil society, and has since influenced all of the State & Region governments to produce their own documents. TAF was well positioned to respond to demand from subnational governments, and has since assisted nine States & Regions (Mon, Magwe, Ayeyarwaddy, Kayah, Kayin, Kachin, Tanintharyi, Yangon, Bago) with the production of their own Citizen’s Budgets. Furthermore, the remaining five States & Regions have also produced their own Citizen’s Budgets, indicating horizontal uptake and sustainability. Initial hesitancy by some of these States and Regions to publish the final version of the budgets has now been resolved, with those supported by MSSP all publishing their documents.

During the review period, TAF increased the number of participatory budget events across States & Regions. This has involved Citizen’s Budget launch events and Budget Transparency Forums which fostered dialogue between government and civil society. Furthermore, TAF has delivered six budget literacy trainings to civil society organisations and supported five sub-grantees to implement activities that hold subnational governments accountable to local needs.

The output scores an A+ due to the significant improvement in budget transparency at both the Union and State & Region level, and the increased number of events that have fostered citizen dialogue with government and participation in the budget process, but only at the subnational level.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendations:

The programme has successfully raised citizen dialogue with government and participation in the budget process at the State & Region level. However, there remain scant opportunities for citizen participation in the Union level budget process. The programme should consider options to also support participatory mechanisms at the Union level.

Output Title	Increase transparency and accountability in Myanmar’s management of extractive industry data, revenue and impacts
Output number per LF		7	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	N

Indicator(s)		Milestones	Progress
7.3	Successful publication of annual EITI Reconciliation Reports and EITI Validation results that indicate steady progress towards to achievement 'Successful Progress'.	Publication of Fourth EITI Reconciliation Report	Achieved - It is highly likely that the fourth EITI report will be published by the March 2019 deadline and that the EITI validation result will find ‘meaningful progress’.
7.5	Improved management of the extractive industries through systematic registration and monitoring of gemstones, oil, gas and mining licenses	Public access to mineral cadastre system and hydrocarbons registry.	Partially achieved – Mining cadastre procurement ongoing. Expected cadastre completion date is December 2020.
7.6	Number of outreach activities	Three outreach events implemented / Male participants: 150 / Female participants: 90	Exceeded - Eight outreach events were held, including in Yangon, Naypyitaw and Mandalay. / 589 Male participants 238 female participants

Briefly describe the output and provide supporting narrative for the score

This output relates to the ‘EITI window’ of the World Bank managed MDTF, jointly funded by DFID and DFAT grants. EITI is a global standard to promote open and accountable management of natural resources.

Two EITI reports (FY2014-15 and FY2015-16) were published in March 2018, following an earlier hiatus due to the change of government in 2016. However, the official launch of these reports was delayed until November. Public dissemination has picked up from November to January with launch events held in Yangon and Nay Pyi Taw in late 2018, followed by four public debates. The events were attended by a range of stakeholders including the public and received some media attention. Reconciliation activities for the fourth EITI report are on track, and the report is expected to be published by the deadline of March 2019. Forestry reconciliation reports for FY2014-15 and FY2015-16 have been completed and are scheduled for publication in March 2019. Subnational EITI Units were established in five state and regions during the review period to support engagement at the subnational level and reach a broader audience.

Burma’s EITI validation assessment was conducted in August 2018 by the International Secretariat and the Validation Report is in draft, scheduled for finalisation in March 2019. The likely result is that Burma will achieve ‘Meaningful Progress’ and be given a number of corrective actions to be implemented before the next validation process to achieve ‘Satisfactory Progress’. The initial assessment indicates that government and civil society engagement in the EITI process is satisfactory while there is an opportunity to improve private sector participation. Overall the Multi Stakeholder Group (MSG) of EITI has been well-functioning to date.

A Beneficial Ownership (BO) Taskforce was formed in August 2018 with key MSG members and additional members from other relevant institutions. The taskforce has agreed on the scope of BO reporting and ran pilots with a small number of volunteer companies. The Directorate of Investment and Company Administration’s (DICA) company registry has been identified as the appropriate mechanism through which BO information should be reported. However, it’s not clear that this can be achieved by the 2020 disclosure deadline for EITI compliance. DICA are in the process of implementing a new company registry, and features enabling BO reporting are outside of the scope of work agreed with their supplier.

Development of the mining cadastre for the Ministry of Natural Resources and Environmental Conservation (MONREC) is behind schedule due to delays in the finalisation of scope of work and TOR. The scoping phase was completed in June 2018 and procurement for a consultant to develop the cadastre is underway, led by the cadastre evaluation committee. To ensure completion of the cadastre by end-2020, the procurement must be finalised and contract signed by June 2019 so that work can commence in July. To accelerate the procurement, MONREC and the MSG have agreed to streamline the decision-making process, as recommended by the Bank. Pre-Cadastre work that consolidates and verifies mineral and gemstone licenses is nearing completion. However, the Bank has suggested that it may be necessary to extend the scope of pre-cadastre activities to include re-mapping of all gemstone tracts due to the poor quality of the current maps used by the Myanmar Gems Enterprise. The Bank is coordinating with the Natural Resource Governance Institute (NRGI) which is supporting the Myanmar Gems Enterprise to digitise approximately 500 gems and jade licenses, with a view of incorporating this into the mining cadastre.

This component scores an A because despite excellent progress on the publication of EITI reports and the number of outreach events held, progress on the sector reforms and impacts of transparency has been slow, including mining cadastre, accountability of SOE expenses and beneficial ownership, and Burma is still far from achieving best practice.

Lessons identified this year, and recommendations for the year ahead linked to this output

It was initially foreseen that the data generated by EITI could be turned into reform activities through the PFM programme. However, it apparent now that it is too early to expect these results. Whether EITI translates to reform depends on the strength of other institutions that must enforce accountability, including the legal system, parliament, and government agencies. The placement of the EITI Secretariat (responsible for financial management and procurement in relation to the MEITI process) within the MoPF has continued to limit its ability to respond to the needs of the process and reinforces the need to explore options to change the governance of the project identified in the last annual review, which is ongoing.

Recommendations

DFID should actively participate in the independent review of the EITI implementation structure to ensure it identifies a sustainable model that is compatible with the programme’s transition. This review originated from recommendation 20 of the last annual review, which identified a need to explore options to change the governance of the project to ensure greater sustainability and institutionalisation beyond the term of the current government.

The World Bank should agree a no-cost extension until end-2020 to support completion of the mining cadastre.

DFID should ensure a managed transition between the current programme and future economic governance programming. This is important to sustain momentum, which has already stalled once since Burma became an EITI candidate country.

DFID should identify extractives reform opportunities beyond EITI for implementation through future economic governance programming.

Output Title	Improved planning, budgeting and revenue arising in targeted subnational government
Output number per LF		8	Output Score	A+
Impact weighting (%):		10	Impact weighting % revised since last AR?	N

Indicator(s)		Milestone for this review	Progress
8.1	Qualitative assessment of overall progress against programme outcomes and the MSSP results framework, Progress with State and Region governments (component 1.1) and Development Affairs Organisation (component 1.2) is assessed according to the extent to which the programme has contributed to improvements in the following: / Efficiency: revenue mobilization and budget management executed more efficiently and subnational government delivers better key social services in programme target areas / Accountability: improved transparency of budget process and PFM and space for public monitoring of policy management and public finances in programme target areas / Responsiveness: implementation of inclusive and evidence-based reforms in programme target areas. / Progress against component 1.3 (Subnational Governance Discussion Paper Series and public awareness raising) will be assessed according to the extent to which subnational governance policy discourses are strengthened and catalysed through the dissemination and uptake of high quality research on subnational governance processes, structures and dynamics. Progress against component 1.4 (CSO Engagement in Subnational Governance) will be assessed according to the capability of CSOs to hold subnational governments to account on budget issues.	To meet the programme’s expectations	Exceeded: The Asia Foundation (TAF) has continued to expand its activities throughout the year and has delivered a greater number of outputs than expected.
8.2	Qualitative assessment of the extent to which the programme demonstrates strong evidence of: (a) collaboration with, the influencing, other development actors (b) learning and adapting to new evidence and changes in political context.	To meet the programme’s expectations	Achieved: TAF continues to adapt to the context but needs to improve its collaboration and influence with other development actors.

Briefly describe the output and provide supporting narrative for the score

Delivery of this output has been measured against the support provided to the Asia Foundation’s ‘Myanmar Strategic Support Programme’ (MSSP). The MSSP has four subcomponents funded by DFID: (1.1) Strategic Support to State and Region Governments; (1.2) Strategic Support to Development Affairs Organizations; (1.3) Subnational Governance Discussion paper Series and Awareness Raising and (1.4) Social Accountability and Public Engagement.

Overall, good progress was made in each of these subcomponents during the reporting period which led to a number of outputs being delivered in 2018. Furthermore, TAF has continued to build relationships with subnational stakeholders, which has enabled them to expand and deepen its work with more State and Region governments and civil society actors.

On subcomponent 1.1, TAF worked with the Ayeyarwaddy and Mon governments to develop Regional Economic Development Plans (REDP) aligned with the MSDP. The REDPs were developed in consultation with government departments, Members of Parliament and business representatives, but could have engaged more citizens in the process. The project also supported six States and Regions to publish reform priorities reports, and Bago to produce Burma’s first subnational pre-budget statement. Eight States and Regions published subnational Citizen Budgets, and several have started sharing budget information with the media more openly.

Over 17 foundational and 21 technical trainings held in seven States and Regions have led to improvement in technical proficiency in annual planning and budgeting processes. This has been shown by improvements in pre and post tests for following trainings, as well as the production of new budget process documentation.

On subcomponent 1.2, Development Affairs Organizations (DAOs) in Hpa-An and Taunggyi have improved municipal waste management which has driven a demonstrable reduction in waste at illegal dumpsites. It is also evident that a number of MSSP supported tax reforms are taking place, with property tax in Taunggyi, Hpa-An and Mon state increasing significantly during the review year. The Myankhon tax application is now used widely in 11 DAOs within five states and regions. Communication training, DAO information campaign and the Myo Taw municipal communications app have also led to an improvement in citizen engagement as measured by app users.

On subcomponent 1.3, the new edition of the State and Region Governments in Myanmar report was launched successfully in Yangon and Naypyitaw. The report received significant interest from social media, national and international audiences, and every budget and planning department has requested copies to inform policymaking. On subcomponent 1.4, TAF has worked with Civil Society Organizations to build the awareness and capacity of the citizens on the government by organizing town hall meetings, people dialogues sessions and budget literacy trainings.

The output scores an A+ as it has exceeded expected progress against the MSSP results framework.

Lessons identified this year, and recommendations for the year ahead linked to this output

Overall the MSSP was able to exceed outputs around subnational reforms and policy-related changes in a complex and challenging context. Outcomes could also be seen in the areas of subnational tax reforms, innovative and improved resource allocation in local service delivery and the opening-up of subnational government to public scrutiny and accountability. The progress that the MSSP has made indicates the strong trust that TAF has built with the government and local organizations. However, with a greater number of development actors entering the subnational PFM and governance space, TAF will need to ensure it is able to collaborate and influence more effectively to ensure its evidence and learning is used effectively to deliver reform by other partners.

Recommendations

TAF should identify and mitigate programmatic risk related to the upcoming 2020 election to ensure activities and deliverables are not adversely affected.

TAF should increase its engagement with other partners active at the subnational level to ensure complementarity, knowledge sharing, and to foster a cohesive subnational development partner community.

DFID should consider support for TAF’s new programme proposal ‘Accountable and Inclusive States & Regions’ (AISR) through a one year cost extension to sustain subnational PFM reforms and strengthen decentralisation.

TAF should raise its own capacity in technical PFM areas to ensure it is able to provide the expertise necessary to deliver its future programme.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

During the review period, the programme adopted a modified theory of change proposed by the external evaluation report. The theory of change posits that technical assistance in PFM at the Union level, select State & Regions and through EITI, along with implementation support, capacity-building and learning (outputs) will result in strengthened PFM systems and institutions and improved policy formulation and implementation (outcome). This leads to the effective, efficient, accountable, and responsive delivery of public services for the benefit of the people of Burma (impact). Strengthened PFM systems will also support the three related long-term changes currently underway in the country: the transitions to democracy, peace, and a market economy.

A major change has been to incorporate important additional challenges within the government arising from the political and bureaucratic history and current context. These are: limited experiences of bureaucracy with good practices in PFM, the absence of cross-ministerial coordination, the vertical institutional structure of government, the dependence on success of building relationships, and the personal experience and capacity of ministers, deputy ministers and leaders of key parliamentary committees.

The World Bank has also updated its theory of change for the institutional strengthening window, through which the Bank-implemented components of this programme are funded, to better reflect activities and record attributable results. This has integrated BETF activities with those undertaken by the RETF and forms the theoretical basis for the ongoing results framework update.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The overall outcome assessment of the programme to date is mixed. On the positive side, the programme has helped the government to raise greater revenue from large taxpayers, sustain early improvements in its budgeting process, reduce the difference between budget approval and expenditure out-turn, and improve fiscal transparency through the publication of Citizen’s Budgets and other key documents. The change in fiscal year in the review period was implemented without significant disruption to business as usual, though delayed several programme activities. There has been further progress on PFM at the subnational level in several States & Regions – subnational budget transparency is increasing, new channels of Union level communication with States and Regions have been opened, and citizen engagement is strengthening - though fiscal relations between the Union and the subnational governments remain weak. The EITI process made significant progress, producing two reports in the last year, following a one-year hiatus, and is expected to publish Burma’s 4th report in March 2019, though extractives reform to date has been limited.

LF#	Outcome description	Progress
1	Contribute to enhancing the Tax to GDP ratio from 6.2% in FY2012/13 to over 10% by FY2018/19 increasing tax collections from large taxpayers by strengthening tax administration	Off track / Tax to GDP ratio is 8.49% for FY 2017-18 and is not on track to meet the 10% target for FY2018-19. This is due to increased tax exemptions and lower collections from SEEs. MOPF is now aiming to achieve the 10% target by FY 2019/20. / The programme supported LTO has however increased its share of corporate income tax collections to 65% in 2017/18 against 27% in 2015/16. Average CIT collected per taxpayer at the LTO increased by 40% in 2017/18.
2	Budget preparation process including (i) issuance of ceilings (ii) preparation of medium-term fiscal framework	On track / (i) Yes, completed for 6-month and annual (FY2018-19) budgets in the review period. / (ii) Yes. The MTFF was updated in the previous review period and has been sustained in this review period.
3	Composition of expenditure out-turn compared to original approved (deviation)	On track / The deviation between actual and approved expenditure has fallen to 3.84% from 4.87% in the previous year and is considerably lower than the 14% target.
4	Number of beneficiaries of (i) training courses, and (ii) training module on revenue and expenditure incidence analysis (including by gender, income group and region)	Partially on track / (i) 7,900 trainings provided on IT and English language / (ii) 0 trainings provided on incidence analysis / The PFM Curriculum has been developed by ACCA and is now awaiting feedback from government.
5	Government commitment to fiscal transparency in line with (i) global good practice, including (ii) report on revenues from natural resources	On track / (i) 6 of the 8 key budget documents published, 6 of which in a timely manner, versus a milestone target of 4 / (ii) EITI report published for the most recent period
6	Increased citizen engagement in budget processes measured by improvement to Burma's score in Open Budget Index	On track / In the last review period, Burma’s Open Budget Index score (7) exceeded the milestone (5). An Open Budget Index has not been produced for 2018, however

The upcoming PEFA assessment, now due in 2019, will provide a more thorough snapshot of core PFM indicators. As flagged in the last review, expectations with government and development partners will need to be managed given the limited progress to date on several key PFM reforms.

Explain major changes to the logframe in the past year

There have been the following significant updates to the logframe during the review period:

LF#	Change made	Rationale
Output indicator 6.4	"Publication of the eight key Union budget documents identified by IBP" is newly added in the logframe	Included to better reflect progress made on Union budget transparency
Output indicator 6.5	"Number of States & Regions producing the following fiscal documents in the previous fiscal year: i) Citizen's Budgets, Reform Priority Documents, Regional Economic Development Plan, Budget Briefs" is newly added in the logframe	Included to reflect progress made on S/R budget transparency
Output indicator 6.6	"Number of States & Regions conducting events in the previous fiscal year: i) Citizen Budget launch events ii) Budget Transparency Regional Forums iii) Budget Literacy Trainings iv) Dialogue Sessions" is newly added in the logframe	Included to reflect progress made on S/R public participation in the budget process
Output Indicator 7.3	Amended from ''Successful publication of annual EITI report and improvement in the validation process to become an EITI compliance country.'' To “Successful publication of annual EITI Reconciliation Reports and EITI Validation results that indicate steady progress towards to achievement 'Successful Progress”.	A slight edit to better match the terminology of the 2016 standard.
Output indicator 7.6	Newly added output indicator "Number of outreach activities"	To capture dissemination of EITI report findings as a proxy for engagement of public, civil society, etc.

Describe any planned changes to the logframe as a result of this review

Changes will be made to the log frame in line with upcoming amendments to the World Bank’s results framework for the institutional strengthening window. This will include an additional year of milestones to continue monitoring of extended activities, amendments to existing indicators to better reflect attributable progress, and inclusion of new indicators to track progress of key IT procurements.

Other changes proposed are:

LF Component	Change	Rationale
Outcome indicator 4	Remove indicator “Number of beneficiaries of (i) training courses, and (ii) training module on revenue and expenditure incidence analysis (including by gender, income group and region)”	This indicator does not represent an outcome and is also included in the logframe as an output indicator.
Output Indicator 7.3	Amend from “Successful publication of annual EITI Reconciliation Reports and EITI Validation results that indicate steady progress towards to achievement 'Successful Progress’”. To “Successful publication of annual EITI Reconciliation Reports and EITI Validation results that indicate steady progress towards to achievement 'Meaningful Progress’”.	Correction in terminology to align with EITI standard.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

The original VfM proposition in the business case identified delivery of the log frame indicators, financial management, procurement and World Bank fees to be the measures that should judge the performance of value-for-money for the programme.

Programme management costs (economy) have been reduced through the pooling of donor funds, both through the World Bank Multi-Donor Trust Fund and TAF’s MSSP. Overhead fees are set centrally by the respective organisations. The World Bank sets overheads at 5% for the RETF and 17% for the BETF, with the average overhead fee falling this year due to an increased share of expenditure being made through the RETF. TAF has reduced its overhead fee to average 13.6% for the entire grant period, a decrease from the 16.7% fee in the previous year.

The programme is on track to achieve six of its eight outputs (efficiency) and four of its five outcomes (effectiveness). Allocative efficiency increased this year following the decision to reallocate funding towards supporting the delivery of high priority revenue and budget execution components. Significant progress has been made in bringing the procurement of the Integrated Tax Administration System and Core Banking System to implementation following protracted delays in previous years. The programme has delivered demonstrable outcomes on tax administration, reporting, financial control, capacity, budget transparency and participation at both the national and subnational level. However, there remain challenges in terms of raising additional revenue despite improvements in tax administration, ensuring equitable budget preparation and efficient execution, and the timeliness of audit reports.

Although the tax-to-GDP ratio outcome indicator is currently off track, the Internal Revenue Department has collected an additional £661 million in revenue since the start of the project because of reform initiatives supported by the PFM Programme. Although this cannot all be attributed to the programme, it still indicates a high return on investment in this area (approximately £3 million from the programme has been allocated towards tax administration).

A number of outputs were achieved this year that have contributed towards improving the consideration of equity in economic policymaking. The World Bank, alongside government counterparts, launched the Myanmar Living Conditions Survey and the Multidimensional Welfare in Myanmar Report this year. These publications have provided detailed welfare and deprivation indicators at the subnational level to assist the government and development partners improve the equity of development planning and expenditure. TAF continues to track participation by gender at subnational governance events facilitated by the programme, and recorded that 66,103 of 132,503 event participants (49.9%) in 2018Q3 were women.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The programme continues to represent value-for-money based on its own merits and in the context of the wider portfolio through its integral part in delivering new DFID Burma priorities. Furthermore, the programme’s relevance towards delivering strategic objectives and the benefits of the World Bank’s MDTF and TAF’s MSSP modality were confirmed in the 2018 external evaluation of the DFID programme.

Based on its own merits, the programme has achieved or exceeded six of its eight outputs, and four of its five outcomes. The programme’s impact indicator will be assessed through the PEFA assessment to be conducted in 2019. Further to the formal results reporting, a range of intermediate outputs have also been delivered:

- Creation of the large taxpayers office and ongoing procurement of an ‘Integrated Tax Administration System’ that will reduce corruption in the tax authority and raise revenue for Burma to self-finance its own development;
- Established a Medium Term Fiscal Framework that has supported a sustainable fiscal deficit through setting medium term expenditure ceilings;
- Implemented a manual on ‘Public Investment Management’ and developed project appraisal guidelines to support the efficient delivery of large capital projects;
- Creation of a Public Accounts Committee office which has provided parliamentary committee members with technical support on the budget, auditing and economy that has enabled them to better hold the government to account over its economic policy;
- Developed a new PFM curriculum for public finance officials to systemise capacity development and embed sustainability in the programme’s results;
- Published detailed analysis on welfare, deprivation and exclusion at the subnational level for use in policymaking and development planning;
- Supported State and Region governments to more effectively budget and respond to local priorities through targeted technical assistance and capacity building.

Following the violence in Rakhine in August 2017, the programme was restructured to ensure continued value-for-money and alignment with DFID Burma’s revised priorities:

- The programme has ended its support to the World Bank Recipient Executed Trust Fund for national PFM reform, and existing funds within the trust fund have been reallocated to high priority procurements that will improve tax administration and budget execution;
- Remaining DFID programme funds have been reprioritised towards expanding the reach of subnational PFM activities to conflict affected areas. New analysis supporting this has been conducted by the World Bank through the Subnational Public Expenditure Review and Rakhine Economic Brief;
- The focus of the extractives component has shifted towards delivering reform opportunities that raise accountability over the sector, starting with the ongoing development of the mining cadastre and implementation of beneficial ownership reporting requirements.

Based on outcome attainment and the restructuring exercise, there is enough evidence from a value-for-money perspective that the programme should continue to until completion. A key priority for sustaining value-for-money in the future will be ensuring the sustainability of reforms and results, and the successful implementation of key IT procurements through to closure.
E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The programme’s risk rating was downgraded to ‘Major’ from ‘Severe’ during the review period. This is due to a number of high priority IT procurements advancing towards implementation, a renewed impetuous from government on economic reform, and the programme’s exit from the Recipient Executed Trust Fund to provide DFID with greater control over programme activities.

Partners manage risks at the project/component level, while DFID managed programme level risks. The DFID Burma programme team review and update the risk register every quarter to manage and mitigate programme level risks. This review has downgraded a number of these risks and identified two additional risks. The below table identifies the key risks for continued monitoring.

Risk	Mitigation	Likelihood	Impact	Residual Risk
Programme-wide
Peace process or democratic transition stalls, undermining reform momentum. This constrains the ability of the programme to improve PFM in all S/Rs.	DFID is working closely to support the peace process and democratic transition. Asia Foundation is working in ethnic areas to build the capacity of S/R governments and parliaments to increase the opportunities for different groups to engage on public finances.	Likely	Minor	Moderate
Upcoming elections in 2020 make government actors risk averse and unlikely to push forward with administrative or policy reforms. Risks of stagnating will for reform that slows the pace of outcome change. (New risk added)	World Bank PFM component will focus on finalising procurements, providing ad hoc support and conducting analysis. MSSP will focus on building competencies to provide a base for future reform. EITI will review the governance arrangements to ensure sustainability post 2020.	Possible	Moderate	Major
National (World Bank) component
Low capacity in MoPF leads to delays and weak implementation of reforms.	WB providing capacity building through BETF analytical processes such as the Public Expenditure Review. PFM academy curriculum complete.	Possible	Minor	Moderate
Subnational (Asia Foundation) component
Transfer of GAD from MOHA to Ministry of the Union Government leads to bureaucratic confusion that limits the programme’s ability to access or coordinate with government. (New risk added)	MSSP will tolerate this risk as a short term impediment and provide the GAD with space to reorganize. MSSP will consider this a relatively short term risk in relation to the longer term opportunities that this move to civilian government provides.	Unlikely	Moderate	Moderate
Extractives component
EITI process lacks political support from new government to implement the recommendations made by the report.	Continued lobbying by DFID and technical assistance for reform implementation.	Possible	Major	Major

Update on partnership principles

The PFM programme does not provide direct financial aid to the government. All procurements that benefit the government made through the Recipient Executed Trust Fund must be approved by the World Bank and follow all of its policies and procedures. The programme ended its support to national PFM reforms through the Recipient Executed Trust Fund in 2018, and will oversee remaining activities until project closure.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

Delivery against planned timeframe

A no cost extension for the programme until December 2019 was agreed this year. The no cost extension was provided to enable: 1) oversight over national component programme activities to ensure a responsible exit from the RETF; 2) to use uncommitted funding for subnational component to deliver revised strategic priorities around equity, inclusion and accountability; and 3) to refocus the extractives component towards implementing key reforms on the mining cadastre and beneficial ownership.

For the national component, the closing date for the project is currently 30 September 2019. Delays in the approvals of two major procurements, the Integrated Tax Administration System (ITAS) and Core Banking System (CBS), may necessitate a further no cost extension to ensure successful delivery and enable a responsible exit. The ITAS contract was signed in November 2018 and the CBS contract is expected to be signed in February 2019. This extension will enable the programme to provide continued oversight over the implementation of these systems given the lack of capacity within government.

For the subnational component, the project activities are on track following a delay in its initial stage. While DFID funding for this component will be ending in March 2019, there is an extensive work plan to continue and expand activities to other State and Regions. DFID will assess options to continue support to this component until the end of the current PFM programme through a costed extension.

For the EITI component, grant execution has been delayed and expenditure is at only 38% of the total budget. The closing date for this project is December 2019, though may be extended to December 2020. Although the EITI reports for three years have been published since 2015, there remain a significant number of activities still outstanding according to the Multi-Stakeholder Group work plan, which includes implementing the mining cadastre, delivering beneficial ownership, and publishing the 4th and 5th EITI reports. This may also necessitate a no-cost extension to ensure completion of all outputs.

Performance of partnerships

Partnership with government

DFID and the Ministry of Planning and Finance (MoPF) have a productive relationship despite issues in the external environment. The team met with the implementation Agencies from MoPF to discuss the progress of each project, challenges, and opportunities during this Annual Review and World Bank implementation support missions. The team also engaged in the Public Expenditure Review workshop, conducted separate missions to Naypyitaw to scope additional tax assistance opportunities and participated in the Macro Management Sector Working Group to guide the objectives and activities of new cross government reform teams. In these events, the government of Burma stated their appreciation of the support provided by DFID through both the PFM programme and in other areas.

Component 1 – National Public Financial Management (World Bank)

The partnership between the World Bank and DFID has improved, although there have been some challenges over review year. The Bank has recruited a new window manager who has increased oversight over the PFM related projects. The Bank has also recently developed a consolidated theory of change and results matrix for the Institutional Strengthening Window. These should be used as the basis to develop an overarching window level strategy which is responsive to the changing external context and identifies window level risks and mitigation strategies. There were two MDTF Steering Committee meetings during the review periods in May 2018 and January 2019. The quarterly meetings have been held regularly for the whole annual review year. The quarterly reporting template was developed in April 2018 for the Institutional Strengthening Window and has improved significantly over the period. However, there have been issues in the communication and risk mitigation around delays in procurement.

The disbursement rate of the RETF picked up during the review period, though there remains a positive committed balance in the last year of the project due to the delayed procurement of the last two major IT systems, ITAS and CBS. The project may be no cost extended for one year to ensure the successful implementation of these systems. While the level of oversight provided by the Bank over the RETF has been insufficient given the external context, there is a strengthened commitment to ensure the final IT procurements receive the appropriate level of support to ensure successful implementation.

BETF project activities, including ‘Implementation Support of the PFM project’, ‘Analysis for Better Spending project’, ‘Macro Fiscal project’, ‘Subnational Public Expenditure Review’ and ‘Local Government ICT’ have largely been delivered to a high standard. However, there is an opportunity to improve collaboration both within the Bank team and with other PFM development partners to share knowledge, deliver better results and reduce overlap.

Component 2 – Sub-National Public Financial Management (Asia Foundation)

The partnership between DFID and TAF has continued to strengthen, though there were changes this year in the Foundation’s senior country management. TAF has a strong relationship with their downstream partners, such as the Renaissance Institute, which has enabled them to reach a broad set of State & Region and Union government officials.

TAF met with partners every quarter to provide an update on the progress of the MSSP and discuss the MSSP’s future direction. The TAF team has developed a detailed work plan which enables better tracking of project activities and improved financial management.

The MSSP will be ending in April 2019 and TAF has discussed with partners about continuation through a new project. Given the strong alignment between TAF’s proposed work plan and DFID Burma’s new priorities, DFID is in discussion with TAF around continuing the partnership following the conclusion of this project to deliver priorities around decentralisation, citizen participation, transparency and accountability.

Component 3 – EITI component (World Bank + downstream partners)

For this component, World Bank is the first tier partner, Myanmar EITI Office, Budget Department (MoBD) under MoPF is the second tier, and National Co-ordination Secretariat (NCS) is the third tier and core implementer. The partnership between the World Bank and the NCS has improved due to better communication. However, there remains institutional and implementation challenges due to: vertical structures within government which limit coordination effectiveness; recruitment delays within the NCS; and unfamiliarity with the procurement guidelines set by the World Bank and the MoBD. The communication and coordination between World Bank, MoBD and NCS will need to improve further to successfully deliver outputs in the short term, and new arrangements should be considered through the ongoing governance review to ensure the longer term sustainability of the initiative.

The disbursement rate is slow due to delays in procurement activities and slow progress in work plan activities. There were three EITI missions in 2018 to review the implementation which met with various partners. The Bank should continue its engagement with MoBD and NCS during official missions and other stakeholder meetings to sustain the successful delivery of outputs.

Asset monitoring and control

Assets for the national and EITI components are procured according to World Bank procedures. The World Bank has strong procurement systems to monitor and control project assets. The EITI NCS follows both World Bank and MoBD procurement procedures. For the subnational components, TAF maintains a list of assets procured by the MSSP. DFID will continue to monitor each component to ensure appropriate asset disposal once the programme reaches its end date.

Component	1 & 3 (World Bank)	2 (TAF)
Date of last narrative financial report(s)	Sep 30th 2018	30 Nov 2019
Date of last audited annual statement (s)	FY 30 June 2018	30 Sep 2017

G: MONITORING, EVIDENCE & LEARNING

Monitoring

Monitoring of programme progress by DFID has been conducted throughout the review period. For component 1, DFID has met regularly with the World Bank task team leader and window manager, participated in both implementation support missions and the ‘Future Finance’ workshop, and conducted direct discussions with government. For component 2, DFID has participated in quarterly meetings with TAF to discuss MSSP progress, engaged in programme workshops and attended transparency forums. For component 3, DFID regularly meets with World Bank staff and consultants both directly and through the informal development partner meetings, and has attended many of the Multi-Stakeholder Group meetings. Formal reporting is provided by each first tier partner to DFID on a quarterly basis.

Evidence

DFID commissioned an external evaluation which took place between February and April of 2018. Overall, the evaluation concluded that the programme remains relevant to delivering policy priorities and that the modalities provided significant implementation benefits in the Burma context. However, the evaluation found challenges in procurement and disbursement, and identified a need to update the results framework and increase management support to implement reforms. The programme has since implemented a number of the recommendations of the evaluation, such as by making significant advances in bringing the final major procurements towards implementation with the appropriate level of support. The World Bank is also in the process of updating its results framework and is commencing a series of analytical notes to learn lessons from the programme. The findings of the evaluation are now being used to design future economic governance programming in this area.

Learning

The World Bank has continued to publish economy analysis to promote evidence based policies. During the review year, it published two Myanmar Economic Monitors and prepared a number of short policy notes for the government. The World Bank with the government also published new statistics on welfare, deprivation and living conditions at the subnational level. It is now commencing work on an analytical note series to consolidate programmatic learning, build sustainability into programme closure, and support future programme design. The external evaluation has provided important lessons around political economy of PFM in Burma, adapted the theory of change, identified issues around strategy and results, and proposed recommendations to improve operational management and programme governance.

TAF utilises an adaptive learning approach through its strategy testing workshops. During these sessions, the Foundation revisits activities, reviews successes, and challenges areas which require a change in approach or where new entry points have been identified. This has led the MSSP to adjust its activities throughout the review period, for example: by redesigning its social accountability component to focus more on building basic public finance management knowledge within local CSOs; by responding to municipal government demand to engage on improving garbage collection rather than road appraisals; and seeking new ways to increase the transparency of Citizen’s Budgets following initial government reluctance. The MSSP has also added to the evidence base by conducting a City Life Survey to inform programme design and set a results baseline, developing a new competency framework to measure improvements in government capacity over time, and publishing a flagship report on State and Region governments in Burma.

Progress on recommendations from previous reviews

Progress on recommendations from previous reviews is tracked by the DFID Burma programme team in the delivery plan. Progress made on general recommendations is shown in the table below. Furthermore, of the 24 output recommendations made in the previous annual review, 17 have been completed and the remaining 7, which relate primarily to updating the World Bank’s Results Framework, are ongoing.

General recommendations from 2018 Annual Review
Recommendation	Update (February 2019)
Improvements in the monitoring, adaptation and implementation of the national PFM component	Complete - The World Bank has improved their reporting template. Funding has been reallocated to support implementation of priority procurements.
Review of the log frame to better link activities with expected outputs and outcomes	Ongoing – The World Bank is updating their results framework. New indicators have been agreed with TAF and added to output 6 to reflect budget transparency outputs.
Support for reforms that increase public participation and drive greater economic inclusion	Ongoing – World Bank has published new subnational evidence on welfare and deprivation. TAF has increased the number of States and Regions where public forums on the budget take place. EITI continues to use a multi-stakeholder group to make decisions.
Greater co-ordination of subnational governance activities across DFID Burma	Complete – DFID has reviewed its subnational governance activities to aid co-ordination across different programmes and development partners.
Consideration of options for further support on extractives based on the upcoming EITI report	Ongoing – Reforms on the mining cadastre and beneficial ownership reporting are underway. Further reform opportunities will be considered for future programming.
Preparation of transitional arrangements and consideration of a successor programme in this area	Ongoing – the programme will be extended to enable a responsible exit. Future programming is under review.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided