ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	2013 Humanitarian Response in the Sahel
Country or region targeted	Sahel Region
Type of cost extension	Bridge funding
Original project budget	£83m
Original project start and end dates	January 2013 – March 2014
Cost extension value	£20m
New project end date	September 2014
Business Case Quest Document No.	4148387 – tranche 4 / 4263134 – tranche 5

INFORMATION
What is the project’s purpose?
The purpose of the Humanitarian Response in the Sahel is to focus on the preparedness, early action and response to the Mali crisis, and provide support to vulnerable populations for the on-going food insecurity across the Sahel.
What is the objective of the cost extension?
To provide bridge funding to NGOs and UN agencies delivering essential humanitarian assistance while finalising a multi-year business case for 2014-2017. This cost extension will provide continued support to key partners in the Sahel during the lean season, preventing any breaks in assistance to those who need it and allowing continuity of funding to partners.
What is the additional and total support the UK will provide?
Of the £83m already approved under this project, £12m currently supports five NGOs with the balance supporting multilateral agencies and enabling services (security, logistics). Multilateral agencies received additional support in November 2013 to support critical pipelines and preparation for the lean season, while the NGOs were already funded to end March 2014. This cost extension would support four of the five NGOs (we have opted not to continue to fund Handicap International), the UN agencies, ICRC and INSO up to end September, ie covering the period of the lean season. / The following allocations are indicative while awaiting cost extension proposals from implementing partners and submission of reports reflecting progress to date against logframes for the overall Sahel programme. They reflect continuation of current activities, with only minor adaptations. We have not yet received detailed proposals with results from the partners for this funding, and will need to revise results targets at that time and update the overall project logframe. / Agency Current DFID financing Sectors to be funded Proposed extension / WFP (203775-104) £27,500,000 Food security and nutrition (£5m) and UNHAS (£1m) £6,200,000 / UNHCR (203775-102 and 203775-105) £10,000,000 Refugee assistance and protection £2,000,000 / ICRC (203775-101) £15,500,000 IDP and refugee assistance and protection £2,000,000 / UNICEF (203775-103 and 203775-106) £18,100,000 Nutrition £3,100,000 / Action Against Hunger (203775-108) £2,803,000 Food security, nutrition, WASH, health / protection £1,550,000 / International Rescue Committee (203775-109) £2,396,000 Nutrition and health / protection £1,550,000 / Oxfam (203775-110) £3,100,000 Food security and nutrition £1,850,000 / Save the Children (203775-111) £2,000,000 Food security, nutrition, WASH, health £1,250,000 / CARE –INSO (203775-113) £301,000 Security focal point £200,000 / An additional £300,000 towards monitoring and surge staff support is also requested bringing the total to £20,000,000. / The multi-year business case is expected to start in October 2014.
What are the expected results?
Overall, 920,000 people will receive an additional package of assistance over the lean season focusing on food security, nutrition-related activities and basic needs for displaced people across the Sahel. This includes the following support through multilaterals: / 400,000 vulnerable people will receive food and cash assistance during the lean season in Chad, Mali, Niger, and Mauritania (WFP, £5m); / Over 1,500 aid workers will benefit through the provision of safe and reliable air transportation to deliver humanitarian assistance in Niger, Mali, Mauritania and Chad (UNHAS, £1m); / 138,000 children will receive essential nutrition products through the Ready-to-use therapeutic food pipeline in Burkina Faso, Chad, Mali, Mauritania and Niger (UNICEF, £3m); / 58,000 returning refugees and IDPs will receive a comprehensive package of support, including cash grants, support for a peaceful coexistence, quick impact projects and coordination with clusters in Mali as well as shelter, NFI (blankets, mats, jerry cans, soap, kitchen sets, mosquito nets, plastic tarpaulins) and registration/documentation (protection) in Niger (UNHCR, £2m); / 66,000 people (including refugees, IDPs and host communities) in conflict-affected areas of Chad, Mauritania and Niger will receive emergency health and medicine, food, water supply activities, seeds and tools, cash for work and livestock support (ICRC, £2m); / 64,000 people in food insecurity will receive cash, livelihood and WASH assistance in Chad, Niger, Mauritania, Burkina Faso and Mali (ACF, £1.5m); / 84,000 people suffering from malnutrition, refugees and flood-affected people will receive food assistance (through cash transfer), seeds and tools in preparation of the lean season in Chad, Mali, and Mauritania (Oxfam, £1.8m); / 48,000 people will receive a comprehensive nutrition package including health and WASH, as well as protection support in Mali, Chad and Niger (IRC, £1.5m); / 63,000 people will benefit from health, nutrition, WASH, cash transfer and livestock support activities in Niger and Burkina Faso (Save the Children, £1.2m); / At least 360 internationals and 3,500 national NGO staff will be provided with timely adequate safety and security advice in Mali (INSO/CARE £200,000). / We assessed through the recent Annual Review that results for these partners are broadly on track or able to be brought up to target in the coming months. However, given that full results information was not available for the Review, we will in some cases confirm these allocations with partners only once the next report has been submitted or further information on 2013 results provided (UNICEF and UNHCR reports are due on 31 March, and we will seek further information from WFP). This will help ensure that 2013 funding has been properly accounted for, and that these new targets are realistic.
What is the approach to implementation?
DFID’s approach to the Sahel in 2014 involves humanitarian preparedness, early action and response to on-going food insecurity and conflict-related crises across the Sahel, while also launching programmes to build resilience of vulnerable households in the longer-term. While resilience programmes are now beginning, humanitarian response is still needed. Our engagement is part of the wider HMG North and West Africa Strategy, and coordinated with the FCO and other Government Departments as well as with the UN integrated strategy and the AGIR framework. / This cost extension remains a proportionate response that meets urgent humanitarian need as the lean season gets underway, and as the predicted number of food insecure people across the Sahel rises to 20m. We will extend agreements with existing partners (with the exception of Handicap International) in our current focus countries in the key areas of food, nutrition and refugee response. There are minor adjustments to activities to reflect learning from implementation in 2013 (we have just completed an annual review of the project that has informed the recommendation for this extension), the fact that we are entering a different phase in the seasonal calendar, and the start of resilience activities under the BRACED programme (we will stop funding some activities that should be picked up by BRACED partners, for example those implemented in 2013 by Handicap International). / In parallel we will finalise a multi-year business case, incorporating findings from the annual review, and a Real Time Evaluation that is due to take place in April/May 2014. Subject to approval, the multi-year programme should start immediately upon completion of this extension.
Describe any key changes to the original business case?
Situation Update: / The main drivers of humanitarian needs in Sahel remain food insecurity and malnutrition compounded by epidemics, disasters associated with natural hazards, conflict and insecurity. / There has been an increase in projected need this year: around 20 million people are projected to be in need of humanitarian assistance in 2014, an increase from 11.3 million in 2013, reflecting the continued erosion of resilience following recurrent food security crises in 2010 and 2012. / The political crisis in Mali has improved since the start of this project, but conflict and insecurity continue to affect Northern Mali, with recent targeting of aid workers, and fragile access for agencies. Malian refugees are still present in Niger, Burkina Faso and Mauritania. / Chad has seen growing numbers of arrivals from the Central African Republic. Conflict in Northern Nigeria has displaced people to Niger, and affects the region through disruption of market dynamics. As of December 2013, the Sahel region hosts approximately 724,000 refugees and 495,000 internally displaced persons, who are particularly vulnerable to food insecurity, malnutrition, epidemics and disasters associated with natural hazards. / Partners and activities: With the exception of Handicap International (because we expect NGO-led resilience activities in future to be covered under the BRACED programme, not through humanitarian funding), all other partners funded in 2013 will receive continued or repeat funding under this extension. In most cases their activities will continue to be broadly the same as in 2013, though with minor changes that we will agree with the partners in each case. For instance, we agreed with IRC in 2013 that they should decrease some food security activities and increase health activities in Niger. We will also remove funds to one part of Oxfam’s programme in Niger, following discussions around coordination of agency activities with ECHO and Concern. Once partner proposals are received we may agree other similar minor changes, but do not expect to see a major shift in the focus of programmes or activities / Funding of the CAP across the region has also resulted in concerns about the food pipelines and stocks across the humanitarian community. / The only changes to the original BC are in the timeframe, financing and numbers of people that will be assisted as part of this Business Case.