Annual Review

Title: Ethiopia Productive Safety Net Programme Phase 4 (PSNP 4)
Programme Value: £276m (DFID contribution) £2.5bn (total value)		Review Date: 23 November-3 December 2018
Programme Code: 204290	Start Date: 07/07/15	End Date: July 2020

Summary of Programme Performance
Annual Review Year		2015	2016	2017	2018	2019	2020
Ethiopian Financial Year (EFY)		2007	2008	2009	2010	2011	2012
Programme Score		A	A	A	A
Risk Rating		Medium	Major	Major	Major
	DevTracker Link to Business Case:				Business case Vault# 3884274
	DevTracker Link to Log frame:				Revised log-frame Vault# 41649583

A. Summary and Overview

Description of programme
The Productive Safety Net Programme Phase 4 is DFID’s fourth phase of support to the Government of Ethiopia’s flagship programme for social protection, food security, resilience against drought and other shocks, and livelihood development for the poorest households. PSNP originated in a 2005 consensus between the Government and donors that successive annual emergency food aid appeals were not a suitable or effective way of dealing with chronic hunger. The programme provides a structured response to predictable food insecurity and shocks, reducing the need for expensive emergency response. The programme aims to support an impact of “Resilience to shocks and livelihoods enhanced and food security and nutrition improved for rural households vulnerable to food insecurity”.

The PSNP has a vital role to play in the country’s fragile context. Ethiopia is one of the poorest countries in the world (174th out of 188 countries in the human development index) with a Gross National Income (GNI) per capita of just $740 per head in 2017. A significant part of the population depends on subsistence agriculture and livestock rearing, and is exposed to high risk of drought and food insecurity. The effects of drought are worsened by climate change, degraded, unproductive land and dependence on rain fed agriculture. Impressive growth rates and pro-poor service delivery have led to significant poverty reduction, but challenges remain. In an average year in Ethiopia, between 10 and 11 million people need support to meet their basic food needs. Ethiopia is also home to a large number of internally displaced population and migrants from neighbouring countries.

The PSNP enables poor households with able bodied adult members to work on community-planned public works in exchange for cash or food transfers for six months of the year, timed to coincide with the lean season. Since the start of 2017/18 year, the transfer value is now equivalent in value to 15kg of cereals per household member per month (pegged at the price of wheat), or its cash equivalent. Public works activities are planned and designed to address vulnerabilities and contribute to the development of communities. Labour intensive activities include soil and water conservation measures, school room construction or rehabilitation, community water projects, community road construction and rehabilitation, small-scale irrigation, health post construction and renovation.
. The programme also responds to the needs of those who are poor but cannot work. Extremely vulnerable households without able-bodied adults receive direct support throughout the year without the requirement to participate in public works. Women who participate in community works are entitled to leave the work and get cash or food support from the fourth month of pregnancy.

The programme supports about 8 million chronically food insecure people in 350 chronically food insecure districts (known as woreda) and, within these woredas, to chronically food insecure communities (groups of villages known as kebele). Within these communities, targeting of the poor is managed through participatory processes. Taskforces comprised of community members and local officials use the PSNP targeting criteria to choose households that can take part in the programme. The process is verified in community meetings. To introduce independent scrutiny and accountability in the process, an appeals system was introduced in 2007.

Alongside cash or food transfers and public works, the programme is supporting a set of livelihoods interventions to allow poor households to save, develop business plans, access microcredit, diversify sources of income, and move out of poverty. PSNP also incorporates an emergency response mechanism for extraordinary years – this was deployed in 2017/18.

Under the current phase, DFID contributes £276m to a total programme cost estimated at £2.5bn. PSNP is supported by 11 donors, with an increasing GoE financial and in kind contribution. A Donor Coordination Team (DCT) supports coordination and programme management and leads liaison between the Government and development partners (DPs). Support to PSNP4 is central to DFID Ethiopia’s business plan and contributes to headline nutrition results. The current phase will end in 2020.

Actual and Indicative DFID,DPs and GoE Contribution in %
percent

Summary supporting narrative for the overall score in this review
Overall, performance against the outputs is scored an A (‘met expectations’). This score reflects the programme’s ability to continue its core operations (i.e. cash and food transfers) and an upward trajectory of progress on institutional reforms, capacity building and strengthening of the core systems within PSNP despite a challenging year. However, the pace of delivery has been slower than expected on some targets related to systems development, livelihood opportunities and management along with recurring issues of delays in transfers. However, this needs to be viewed in relation to the programme’s performance against outcomes and impact which is assessed as satisfactory. Preliminary results from the 2018 mid-line assessment indicate positive impacts on reducing food insecurity and enhanced resilience of households against distress and shocks. The findings give more credence to the recognition of PSNP as a successful programme which reduces extreme poverty.

Table 1:	Summary of output scoring
Output	Output Description	Impact Weight (%)	Output Performance	Risk
1	Prioritised instruments and tools in place to support an effective system for Social Protection and Disaster Risk Management	15	A	Moderate
2	Appropriate, timely and accessible transfers received by male and female clients	30	B	Moderate
3	Sustainable community assets built up and access to social services enhanced	25	A	Moderate
4	Clients’ livelihood opportunities facilitated through three pathways: crop and livestock, off-farm income generation, and employment	15	A	Major
5	Effective management and operational processes in place to manage the programme	15	B	Major

A challenging operating context: The PSNP is a large and complex programme which operates nationally across eight regions in food insecure woredas and kebeles. The delivery of cash and food transfers, public works, livelihood and social service linkages under the programme depends not only on political support and institutional capacity at the federal level but also on regional bureaus and local structures at the woreda and kebele level. Therefore, the wider socio-economic and political context directly affects the pace and quality of operations. Like the previous year, the programme coped with a difficult operating context. The knock-on effects of the El Nino drought in 2015/16 and the lowland drought in 2016/17, political unrest and enforcement of a state of emergency following the resignation of the Prime Minister in February 2018, ethnic tensions, and staff turnover in Somali and other regions posed serious delivery and coordination challenges.

Continuity of food and cash transfers: Despite another challenging year, PSNP continued to perform its core functions i.e. delivery of cash or food (or a mix) to almost 8 million chronically food insecure people in 350 chronically food insecure districts. This is a noteworthy achievement and a sign of flexible and resilient systems within the programme. The programme transferred Birr 8.83 billion in cash to beneficiaries in 2017/18. An amount of Birr 1.67 billion in cash was carried forward from the previous year and was also transferred to beneficiaries. 173,978Mt of food was transferred in this fiscal year which constituted 88% of the annual target. In addition, 95,632Mt of food was carried forward from the previous year and transferred to beneficiaries in 2018. Although delays in transfers occurred, the benefits are reaching poor people.

Key achievements in this year are summarised below:
- Continued government commitment: The programme has weathered serious political instability and constrained fiscal space which reflects the wider recognition of its importance for reducing food insecurity and extreme poverty. In 2018, the Government’s financial contribution was $73m (equivalent to approximately 12% burden share). The Government is committed to increase domestic financing gradually and end the need for donor financing by 2025. While it is an ambitious target, it represents an opening for dialogue and progress on financial sustainability of the programme.
- Cash and food transfers and coverage: The programme delivered cash and food (or a mix) to almost 8 million chronically food insecure people, and cleared the backlog of cash payments and food transfers from the previous year. The coverage has remained the same. However, the number of woredas has increased from 329 to 350 – an addition of 21 new woredas. This is due to split of some zones and woredas in the Somali and Amhara regions.
- System improvements: The Government has established the Commodity Management Unit (CMU) within the National Disaster Response Commission (NDMRC) in 2018 with 20 staff members. Focal persons are assigned at the woreda level. This is a significant achievement as it will improve the processes for food procurement, distribution and tracking, and reduce delays in transfers. Another key achievement is the completion of procurement for developing Management Information System (MIS) which was long overdue, following cancellation in 2017.
- Contingency budget and scalability: The programme also demonstrated its ability to flex and scale quickly to meet additional needs and reduce periods of food insecurity amongst households identified for humanitarian food assistance. 4,041,778 beneficiaries received transfers under the federal contingency budget in 2017/18. As of June 2018, PSNP 4 delivered Birr 2.4 billion in cash and 23,484Mt food in extended support payments to PSNP beneficiary households in woredas where emergency relief needs had been identified..

- E-payment system: The electronic payment system was rolled out to an additional 45 woredas. In total, cash resources are being transferred through this system in 112 woredas.
- Capacity building: A significant improvement is noted in utilising the budget for capacity building of regional bureaux on mainstreaming gender and social development and nutrition in the operations, and trainings of potential livelihood beneficiaries on financial literacy, crop-production, and income generating activities.

Progress has been mixed or slower than expectation in some areas:
Timeliness and predictability of transfers: There were significant delays in cash and food transfers. This is a recurrent issue in the programme. Delays in transfers from the Federal level to regions and woreda level, connectivity problems, delay in preparation of attendance sheets and payrolls for PW clients, delays in retargeting for PDS clients, turnover of payment agents in the e-payment system, and low cash liquidity at the payment points are some of the causes.
- The value of cash wage rate: In 2017/18, the real value of the transfer diminished by over 25 percent. Between March 2017 and March 2018, food prices soared by 19.9 percent; the price increase for bread and cereals was even higher at 24.9 percent. The Government increased the wage rate by 20% for 2011. There are still concerns at the Federal, regional and woreda level that this increase is not sufficient to mitigate the impact of inflation.
- Transition of the Permanent Direct Support (PDS) caseload: The Government and development partners agreed to transfer the Permanent Direct Support (PDS) component from the Food Security Coordination Directorate in the Ministry of Agriculture and Livestock to the Ministry of Labour and Social Welfare (MOLSA). This component supports those beneficiaries who cannot participate in public works and need social protection throughout the year to meet their basic needs. Progress has been slow on taking over the PDS component for rural safety net households. While a PSNP unit has been established within MOLSA and social workers recruited at woreda level, decisions on sharing administrative budget for delivery of this component are pending.
- Livelihood component: This component was scaled back last year from 30% of public works beneficiaries to 10% due to funding gap, but it is still struggling to meet annual targets. The volume of livelihood transfers remained below the target (in part due to an agreement to slow down implementation because of the impact evaluation and pilot activity). Similarly, progress on supporting households to engage in off-farm income generating activities and access gainful waged employment did not meet expectation, for reasons including limited (or no) availability of micro credit in some regions, and low availability of employers.

Recommendations for the year ahead
Looking ahead, DFID should work with the Government and other development partners to achieve progress on the following actions:

1. Reduce delays in cash and food transfers: The Government and donors should develop a “Timeliness and Predictability Action Plan ” by March 2019. The Action Plan should identify causes of delay, separately for cash and food transfers, at the Federal, regional, woreda and kebele level, and set targets for reducing the delay. A monitoring mechanism should be part of the Roadmap to define the roles and responsibilities at each level, and progress should be monitored on monthly basis. The Donor Coordination Team (DCT) should play a more proactive role to escalate the issues of delay to political leadership to remove strategic bottlenecks.
2. Protect the purchasing power of the cash wage rate: The Government should review the impact of inflation and local market conditions on the value of transfer periodically, at least on annual basis (this implies a lighter touch approach as used this year, than that envisaged in the PIM). Policy parameters for adjusting the cash wage rate should be clearly defined to protect the purchasing power of the transfers.
3. Increase investment and technical support for systems development: A key reason for underperformance in some areas is that the core systems cannot cope with the size and complexity of the programme. DFID should explore ways to enhance technical support, especially in automation and use of digital technology, to improve PSNP systems. Key priorities include:
- Digitisation of the beneficiary registry and communication across Federal, regional and woreda levels;
- Upgrading and digitisation of the payment roll and attendance sheet preparation;
- Completion of the MIS;
- Refinements in the e-payment system and building in fiduciary safeguards for beneficiaries; and
- Monitoring and evaluation processes, including monitoring the contingency budget line.
1. Reconsider the design of the livelihood component and its linkages with graduation: The goals of poverty reduction and graduation of households from PNSP are contingent on the wider enabling environment and the success of livelihood component. There are a number of design issues which warrant re-consideration: emerging evidence on low value for money of microcredit, lack of attention to the right institutional structures and partnerships needed for off-farm and employment pathways. The Government and development partners should review the design of the livelihood component by mid-2019 and learn from the on-going impact evaluation of the livelihood transfer and global body of evidence on livelihood and graduation.
2. Build in performance incentives in future support to PSNP: DFID should explore, along with the World Bank and other development partners, the use of funding modalities that would enhance collective influence on Government to resolve recurring issues (e.g. delays in transfers) and accelerate the pace of delivery. As discussions for the next phase of PNSP and financing model are beginning to take place, DFID should consider linking disbursements to achievement of time-bound, pre-agreed results in the Financial Aid component.
3. Full engagement of the newly established Commodity Management, Logistics and Finance Directorate; the use of CATS (Commodity Allocation and Tracking System) and CMPM (Commodity Management Procedures Manual). GoE and donors to follow JRIS agreed action plan to realize the previous commodity audit findings for EFY 2008 and EFY 2009 are addressed and report submitted to DPs by February, 2019

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Prioritised instruments and tools in place to support an effective system for Social Protection and Disaster Risk Management
Output number per LF		1	Output Score	A
Impact weighting (%):		15	Impact weighting % revised since last AR?	Y ↑

Indicator(s)	Milestone(s) for this review	Progress
1.1 Percentage of PSNP woredas where digital beneficiary registry is operational	0%	Met expectations: A / There has been satisfactory progress on this piece of work and procurement processes have begun. PASS operates as a basic beneficiary registry at present. An audit is planned to check data quality.
1.2 Development of national household registry	Initiate design with stakeholders	Met expectations: A / A procurement to identify firms able to carry out the large scale data collection is being initiated after Central Statistical Agency advised they had no capacity to do this work.
1.3 Percentage of clients and non-clients who are aware of programme objectives and entitlements (disaggregate by sex, and by permanent DS and other clients)	all clients -65%	Met expectations: A / There is no data this year to confirm the percentage of clients who are aware of programme objectives and entitlements (due to delayed midline evaluation). However, interviews, field visits and supervision missions show that this milestone is likely meeting expectations.
	MHH-67%
	FHH-63%
	Public works clients-70%
	Direct support clients-60%
	Non-clients-65%
1.4 Number of safety net kebeles implementing social accountability tools	120	Met expectations: A / 19 pilot woredas have a PSNP action plan (approx. 114 kebeles); the ESAP is set to expand significantly in its third phase, which is now under implementation. The vast majority of kebeles have a functioning kebele appeals committee(93% of highland and 83% of lowland)
1.5 Percentage of woredas where management information system is operational (MIS)	30	Moderately did not meet expectations: B / The MIS is not yet operational – however there has been significant progress on procurement (which is completed), and systems development is now underway

Provide supporting narrative for the score

Output 1 seeks to deliver improved tools to support the implementation of PSNP4 and to provide the operational underpinnings for the wider, emerging social protection system (which will be delivered across different implementing Ministries). The score reflects significant (if slow) progress this year, taking into account the challenging operating context. The MIS is not operational but development has been initiated; and steps towards better data collection have been taken. Milestones for 1.5 and future milestones for 1.1 may be over ambitious considering the historic rate of progress.

1.1/1.2 Data is a consistent issue for the programme (and one which is exacerbated for the scalable element), for a number of reasons including the highly devolved programme management (most data sits at woreda level)and the fact that the system is largely manual, due to infrastructure challenges. A digital beneficiary registry is crucial to building a stronger national system, alongside a new MIS to support improved reporting and monitoring. We expect the MIS development to be finalised during this phase (4) and the PSNP registry to be at around 80% completion by the end of PSNP4 (June 2020).

At the June 2018 JRIS, the Mission agreed that data collection for the beneficiary household registry would start in EFY 2011 and progress so far has been satisfactory: Terms of Reference (ToRs) for data collection procurement have been drafted and as of December 2018 the Central Statistics Authority has stepped out of consideration for the main data collection (due to resource constraints produced by the census) but will retain a position overseeing data quality and consistency. The procurement for the main data collection contract will begin at the end of 2018 extended to the private and NGO sectors. Training on monitoring and reporting has also taken place at regional level, and will be cascaded this year to woreda level.

The milestone for 1.1 for 2018/19 is 50%: the programme team should consider whether this is a realistic target, given progress to date.

1.3 There is as yet no data to confirm the percentage of clients who are aware of programme objectives and entitlements (this will be available in January with the impact evaluation midline). However, interviews and field visits suggest this is not a major concern: the maturity of the programme, annual retargeting processes at community level and clear communication, via client cards, of rights and responsibilities suggest that programme objectives are well known. However, comprehensive awareness of the GSD provisions (including transfer of pregnant clients to TDS) may require more communications and capacity building at woreda level (see indicator 1.4, and output 3). The full midline evaluation results, delayed but now due in early January 2019, will corroborate, or not, these assumptions. Some early results have been provided and inform this review.

1.4 PSNP continues to strengthen social accountability mechanisms year on year. The basis of any social accountability system is client knowledge of entitlements, which is good (see 1.3), and continues to be bolstered by built in continuous information provision and awareness raising – through (e.g.) posting of beneficiary lists. The social accountability pilot is part of a separate programme, ‘Ethiopian Social Accountability Programme’ (ESAP), which continues to expand provision across PSNP woredas, under phase 3 which has now begun.

Development Pathways, funded by DFID Policy Division, carried out a case study on social accountability in PSNP (published in April 2018), which showed largely positive results. It looked at two woredas in different regions operating under the ESAP II pilot, and found that the kebele appeals committee (the main grievance redress mechanism) succeeds in its aims to raise citizen awareness and confidence; promote direct dialogue between citizens and kebele officials; and enable citizens to bring local implementation issues to the attention of woreda officials. Kebele appeals committees have been established in 83% of kebeles in Afar and Somali, and93%in the highlands. It also showed that these mechanisms have strengthened local awareness of gendered public works provisions.

The study also suggests that social accountability mechanisms do not adequately meet the needs of the most vulnerable: (persons with disabilities and direct support beneficiaries are generally much less aware of programme provisions and of their rights than others and report lower levels of citizen action); and that processes and impacts are ‘locally-bounded’ (i.e. concerns and grievances are not escalated through the administrative hierarchy, even where issues are caused at higher levels). JRIS midline indicators show that on average only 35% of beneficiaries know about the functioning of the kebele appeals committee and appeals audits have shown that they do not always operate as intended.

The November 2018 JRIS field visits were encouraging, with participants clear on the role of the appeals committee and reporting having successfully accessed its support (though PDS clients noted being more comfortable reporting grievances informally, rather than formally).

1.5 Due to a previous failed procurement process there have been significant delays in delivering the new digital MIS but system procurement has been achieved as of 2018. The inception phase report has been submitted, and systems development has begun. Challenges for implementation at local level are significant, and donors will need to work closely with partners to ensure capacity is sufficient to properly implement a new system in a low infrastructure context.

Recommendations:

It is vital to push forward the procurement of primary data collection for the household registry and its implementation; and the development and roll out of a new MIS. DFID should explore ways to enhance technical support on automation and use of digital technology.

The team should also view next year’s milestones targets with realism, given the significant logistical challenges, and consider adjusting them.

Consider which of the recommendations from the April 2018 report can be taken forward as ESAP expands and enters its new phase, particularly: raising awareness among PDS about entitlements (the move to MOLSA should strengthen this – for example, newly-recruited social workers could, as per the PIM, play some oversight role in the KAC where possible); and strengthening linkages between local social accountability processes and the existing top-down PSNP monitoring and accountability mechanisms (in order to give beneficiaries a voice on those issues which are determined at regional and federal level).

Data on how social accountability mechanisms respond or could respond better to the needs of PDS clients (and to safeguarding concerns more broadly) could be considered in any future evaluation or spot checks.

Output Title	Appropriate, timely and accessible transfers received by male and female clients
Output number per LF		2	Output Score	B
Impact weighting (%):		30	Impact weighting % revised since last AR?	Yes ↓

Indicator(s)	Milestone(s) for this review	Progress
2.1 Percentage of clients paid within agreed timeframe (20 days for cash and 30 days for food)	90%	Substantially did not meet expectation (C) / Cash: 47% (July 2017-June 2018) and 26% (July-October 2018) / Food: 23% (January-June 2018)
2.2 Percentage of clients reporting that they receive cash or food transfers at a place less than 3 hours walking from their home - disaggregated by sex	Highland-90%	Met Expectations (A) / 88% of clients travel less than 3 hours to receive their payment. / Mean travel time to payment points: 1.6 hours (preliminary impact evaluation midline findings).This will be reduced when the e-payment impact is included in the study.
	Lowland-90%
2.3 % transfers received that have a value of at least 15 kg of cereals per person per month	65%	Moderately did not meet expectation (B) / Real value of cash transfers decreased by over 25% due to inflation / Cash Wage rate increased by 20% from July 2018 onwards
2.4 Percentage of clients receiving federal contingency budget resources within 60 days of identification of needs	65%	Exceeded expectation (A+) / 85%

Supporting narrative for the score
This output measures the adequacy, timeliness and accessibility of transfers received by male and female clients. Overall, progress against this output did not meet expectation. Overall, delays in transfers and deterioration of the transfer value due to high food inflation affected the objectives of this output but nonetheless, the annual entitlements were delivered to beneficiaries. In 2018, the programme benefitted almost 8 million beneficiaries in 350 woredas across the eight regions. The major proportion comprises of the PW and TDS clients (85%) followed by PDS clients (15%). The programme transferred Birr 8.83 billion in cash to beneficiaries. An amount of 1.67 billion in cash was carried forward from the previous year and was also transferred to the pending beneficiaries. 173,978 Mt of food was transferred in this fiscal year which constituted 87.77% of the annual target. In addition, the caseload of 95,632.13 Mt of food was carried forward from the previous year and transferred to beneficiaries in 2018. It is expected that delay in food transfer will be reduced in 2018/19 as contract has already been signed for procurement of 80,000 Mt and process initiated for remaining 75,000 Mt, pending security and access issues.

Indicator 2.1: This indicator monitors timeliness and predictability of transfers which are vital for enabling beneficiaries to meet their basic needs on time, and plan their household budget properly. The bulk of cash and food transfers remain non-predictable due to significant delays from the Federal level down to regional and woreda levels. This is an outstanding issue which has not been resolved for many years. The Annual Review noted a modest improvement in timeliness of cash transfers. In 2017/18, 47% of cash transfers were paid within the agreed timeframe i.e. 20 days. The performance deteriorated in the first quarter of 2018 as only 26% payments were made on time. Food transfers continue to suffer huge delays. Only 23% of clients received their food entitlement on time for the period of January-June 2018. This figure was even lower (17%) if the period of January-March is considered only. Food transfers in most of the regions began from January, except for Somali and lowland areas of Oromiya where transfers started from July, to time them better with the lean season there. This is partly due to instability in the region, along with staff turnover and security challenges.

Delays in transfers take place at several points: transfers from the Federal level to lower levels, transfers from MFIs to beneficiary accounts, preparation of attendance sheets and payrolls, procurement of food, etc. A systematic analysis has been undertaken to unpack the causes of delays at the Federal, regional and woreda level and along the delivery chain. This study has provided deeper insights into this issue which will require high political support and leadership for removing bottlenecks in smooth delivery of transfers. In addition, the Commodity Management Unit (CMU) has been established and staffed which is expected to reduce delays in food procurement and supply.

Indicator 2.2: This indicator looks at the accessibility of transfers and convenience of beneficiaries in receiving benefits. The early indicative results from the midline impact evaluation noted that 88% of beneficiaries travel less than 3 hours to receive their payment, compared to the milestone (90%). Although the target has been very modestly missed, this is still a remarkable achievement in view of the long distances and poor road infrastructure in some regions, especially in the Somali and Afar regions. The mean travel time to payment points is 1.6 hours. The introduction of e-payment system has also contributed to reducing the travel time due to greater accessibility of payment points managed by agents/retailers of the payment service providers (i.e. MFIs).

Indicator 2.3: This indicator monitors the adequacy of the transfer value by monitoring its purchasing power. In 2017/18, the real value of the transfer diminished by over 25 percent. Between March 2017 and March 2018, the food prices soared by 19.9 percent; the price increase for bread and cereals was even higher at 24.9 percent. Based on WB analysis of CSA Consumer Price Index 2018, the wage rate
could purchase only 11.5 kg of cereals on average. Therefore, no regions could purchase the full 15kg on the wage rate paid in 2017/18. However, the GoE acknowledged this issue and increased the wage rate by 20% for 2018/19. There are still concerns at the Federal, regional and woreda level that this increase is not sufficient to mitigate the impact of inflation. This issue needs resolution through a policy decision on updating the wage rate periodically based on inflation and zonal variations in market conditions.

Indicator 2.4: This indicator measures the scalability of the programme and its ability to respond to emergency and humanitarian assistance needs. The Annual Review notes a positive trajectory of contingency fund mobilisation, utilisation and consolidation of response to mitigate risks to food security arising from low rainfall and climatic conditions. In 2017/18, the percentage of clients who received federal contingency budget resources within 60 days of identification of needs was 85% ‑ in excess of the target set for this year i.e. 65%. The first-round budget was transferred to regions in September 2018.
The distribution started in October and was completed by November end. The first round covered 6,206,080 PSNP and HRD beneficiaries. In the same year DFID, UNICEF and WFP have all contributed additional finance to the contingency budget line. DFID’s contribution to the contingency budget line to reach emergency relief beneficiaries (and extended support to PSNP households in those areas) amounted to £25 million in 2017/18. While the utilisation of contingency budget is high, there are regional variations in assessing needs and priority woredas.

Lessons identified this year, and recommendations for the year ahead linked to this output
A key lesson related to this output is that peace and security, continuity of programme leadership, government’s own incentives for delivery at pace, and political support are vital for resolving recurring issues in the programme, especially delays in cash and food transfers, and for maintaining the value of the transfer to cope with negative impacts of inflation. It is important to monitor risks and developments related to these factors to improve performance of this output. Key recommendations for the year ahead are:

1. The GoE and donors should develop a “Timeliness and Predictability Action Plan” based on the analysis of the causes of delays in cash and food transfers by March 2019. The Roadmap should identify causes of delay, separately for cash and food, at the Federal, regional, woreda and kebele level, and set targets for reducing the delay. A monitoring mechanism should be part of the Roadmap to define the roles and responsibilities at each level, and progress should be monitored on monthly basis. The Donor Coordination Team (DCT) should play a more proactive role to escalate the issues of delay to higher political level to remove strategic bottlenecks and also in monitoring and working with government to ensure reliable and timely information to DPs.
2. The GoE should review the impact of inflation and local market conditions on the value of transfer periodically. Policy parameters for adjusting the cash wage rate should be clearly defined to protect the purchasing power of the transfers.
3. While the rollout of the e-payment system is expected to improve efficiency and beneficiary choice in terms of payment points, MoFEC should consider refining this payment model before further scale up to address strategic and operational issues: low commission for payment agent, delays in transfer of funds from MFIS to beneficiary account and risks associated with misuse of PIN.

Output Title	Sustainable community assets built up and access to social services enhanced
Output number per LF		3	Output Score	A
Impact weighting (%):		25	Impact weighting % revised since last AR?	Yes ↑

Indicator(s)	Milestone(s) for this review	Progress
3.1 Percentage of public works planned and implemented following the GoE's CBPWD Guidelines or Rangeland Management Guidelines integrated with DRR/Adaptation and mitigation plan – disaggregated by highland and lowland	Lowland-70% / Highland- 90%	Met expectation (A) / 77.5% / Breakdown for highlands and lowlands not yet available for this year.
3.2 Total closed area subject to enhanced management for climate adaptation	297,000ha	Exceeded expectation (A) / 301,640 ha land rehabilitated and treated in both Highland and Lowland regions.
3.3 Percentage of clients that feel PW sub-projects reflect their needs – disaggregated by sex	88%	Met expectation (A) / This indicator will be reported on in the full midline evaluation results (due Jan 2019) but qualitative evidence from missions, JRIS and MTR suggest that this indicator is meeting expectations. Disaggregation not yet available.
3.4 Percentage of female PSNP clients reporting that PW are implemented following GSD considerations disaggregated by highland/lowland.	Highland- 68%	Data will be available in the 2018 midline evaluation – delayed but due early January 2019. Other data from field visits and missions suggests this indicator is meeting expectations.
	Lowland- 31%
3.5 Percentage of adult public work HH members who have attended 6 BCC sessions during last public work season (disaggregated by sex)	20%	Moderately did not meet expectation (B) / Training materials updated and translated into local languages for Highland regions. 760 (85 females) master trainers trained. Progress slow on cascading training to household level. Further evidence will be included in midline evaluation results.
3.6 Percentage of pregnant women transitioning to temporary direct support before 4 months [amongst women who reach the 4th month of pregnancy during the public works period]	78%	Significantly did not meet expectation (C) / Overall: 35% of pregnant women / Field visits suggest socio-cultural issues with reporting pregnancy early.

Supporting narrative for the score
This output measures progress on development of community assets and enhancement of access to social services. Cash and food transfers are linked to building different types of assets (watershed management, community pond, roads, irrigation channels, etc.) for those households in which male or female members have the ability to work. The output is assessed as meeting expectations against the logframe targets. Improvements are noted in compliance of sub-projects with prescribed planning guidelines and technical standards, but variations exist across regions (notably the lowlands have poor compliance with Environmental and Social Safeguard Assessments). The programme has also demonstrated greater responsiveness to transition pregnant and lactating mothers from public works to Temporary Direct Support by or before the fourth month of pregnancy.

Indicator 3.1: This indictor tracks the compliance of PWs with government guidelines for planning and implementation. These guidelines differ for highland and lowland regions, and are meant to ensure consistency and quality standards in all projects. The available data indicates that 77.5% projects followed the guidelines. However, some PWs in pastoral areas fell short of expectation with only 56% of the projects meeting the required minimum standard. However, challenges remain in respect of maintaining a central repository of maps, maintenance, and reporting against implementation of mitigation plans to reduce negative environmental impacts. In 2017/18 the Government has completed procurement of a firm which will development a central database of PW map. The firm has submitted the final inception report.

Table 1: Community assets and social service projects completed (2018)
Non-pastoral areas
Rehabilitation of degraded lands	193,596 ha
Treatment of land	32,283 ha
Land covered by small irrigation projects	12,000 ha
Rehabilitation of irrigation schemes	14,816 ha
Construction of community roads	2,238 km
Social/community infrastructure projects	1,364 projects
Nutrition-based public works	1,510 activities
Pastoral areas
Treatment of land	75761 ha
Construction of water projects	252 projects
Community roads built	2,420 km
Social/community infrastructure	200 projects
Nutrition-based public works	449 activities

Indicator 3.2: This indicator tracks responsiveness of the programme to climate adaptation in PW sub-projects. There has been significant focus on rehabilitation and treatment of land. In 17/18, 301,640 ha land was rehabilitated and treated in both Highland and Lowland regions, exceeding the milestone of 297,000ha. The JRIS noted significant improvement in screening of projects against Environmental and Social Management Framework (ESFM) and implementation of mitigation actions, with the exception of Somali and Afar (based on evidence from the spot checks). However, there is further scope for building more capacity and monitoring and reporting mechanisms for tracking performance on implementation of the mitigation plans.

Indicator 3.3: This indicator assesses whether the PW projects reflect the needs of beneficiaries. There is no quantitative data for direct measurement of indicator. However the June JRIS noted that around 67% of the planned PW projects have potential linkages with livelihoods. Field visits during the November JRIS also confirmed this. The clients acknowledged the usefulness of community projects beyond the cash and food transfers as they helped their livestock and livelihoods. For example, watershed management supported moisture capture and steady growth of fodder for livestock.

Indicators 3.4 and 3.5: These two indicators track programme’s performance in mainstreaming of Gender and Social Development (GSD) aspects in the PW activities in highland and lowland regions and participation of households in related Behaviour Change Communication (BCC) sessions. The Annual Review noted that the PSNP is on a positive trajectory towards building capacity of the regional bureaus to plan and implement GSD and nutrition related provisions of the Programme Implementation Manual (PIM). In 2018, training materials were translated into Amharic, Oromiffa and Tigrigna languages followed by Training of Trainer (ToT) workshops and cascading GSD and nutrition training in 80 UNICEF-supported Comprehensive Integrated Nutrition Service (CINUS) woredas and their kebeles. Woreda level GSD experts are recruited in Oromia region. However, progress did not meet expectation in the pastoral regions due to unavailability of GSD and Nutrition mainstreaming training material as well as tailored Behavioural Change Communication (BCC) facilitation job-aid. In June, the adaptation process of the training manuals within the particular context of pastoral regions was completed. [

Indicator 3.6: The programme requires that pregnant women are transferred to temporary direct support (TDS) modality before 4th month of pregnancy during the public works period. This is meant to avoid any harm to women and the foetus and to ensure their wellbeing and adequate nutritional support. This indicator tracks whether this transition is happening as intended. No milestone was set for this year due to unavailability of a baseline and potential caseload. The 2018 mid-line report noted that 35% of pregnant women were transferred to TDS but this number also includes those women who were transferred after the fourth month. The percentage of pregnant women who reported they were moved to TDS by fourth month of pregnancy was 10%. This indicates that transition is happening but with a delay. This is partly attributed to cultural norms about late disclosure of pregnancy, and partly due to implementation challenges. There is scope for more awareness and capacity building within the communities as well as frontline implementers on this issue.
Lessons identified this year, and recommendations for the year ahead linked to this output

1. Monitoring system for PW projects should be strengthened and implemented fully. Training should be provided to regional bureaus and frontline implementers on using the reporting format.
2. Training on GSD and BCC should start to be cascaded down to beneficiary level in all regions and PSNP woredas during December 2018 before the commencement of next round of PW projects.
3. Messages on the programme requirement for transferring pregnant mothers to TDS before 4th month of pregnancy should be integrated into BCC sessions and training materials.
4. MoLSA should continue to increase its involvement in all aspects of PDS transition.

Output Title	Clients’ livelihood opportunities facilitated through three pathways: crop and livestock, off-farm income generation, and employment
Output number per LF		4	Output Score	A
Impact weighting (%):		15	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of safety net households who are members of RUSACCOs (disaggregated by sex of household head 50:50)	628,000	met expectation (A) / 650,266
4.2 Number of safety net households who received the complete livelihood training package (disaggregated by sex of household head)	281,000	Exceed expectation (A+) / Financial literacy: 390,655 / Livestock: 138,319 / Crop-production: 26,367 / Business and marketing skills: 153,119 / Off-farm pathways: 247,17 / Employment pathway: 19,179
4.3 Number of ultra-poor safety net households receiving livelihoods transfers [after completion of checklist] - disaggregated by sex	50,070	Substantially did not meet expectation (C) / 17,699 (Male: 9,282 / Female: 8387)
4.4 Number of clients with business plans developed - disaggregated by sex	157,000	Met expectations (A) / Total: 143,036 / (Off-farm: 25,506)
4.5 Number of PSNP clients linked to wage employment	42,000	Substantially did not meet expectation (C) / 27,534

Supporting narrative for the score
This output seeks to promote livelihood opportunities for PSNP beneficiary households through three pathways: crop and livestock, off-farm income generation, and employment. This component provides relevant trainings, one-off livelihood grants and links beneficiaries with microfinance and credit institutions so that they could build assets, increase income and strengthen resilience to shocks through interventions. Overall, this output moderately met expectation. The targets set for 2018 were ambitious despite the fact that this component was rolled back last year and faced implementation challenges. Although performance on mobilising savings, identification and targeting of livelihood clients, and provision of training has been considerably positive, the actual number of clients who receive livelihood transfer and those linked to employment remained low. Disaggregated data (by sex etc) will be available on publication of the midline evaluation.

Indicator 4.1: This indicator measures the number of safety net households who are members of Rural Savings and Credit Cooperative Organisations (RuSACCOs). The objective is to encourage households to save cash and food and re-invest the savings in productive activities. The 2018 Annual Report noted that there are 650,266 households are members of RuSACCOs, exceeding the milestone for this year i.e. 628,000. It was noted during discussions with beneficiaries during the November JRIS field visits that there was reasonable level of awareness about the importance of savings, however small.

Indicator 4.2: This indicator tracks progress on provision of livelihood training package to potential clients who are identified as having the ability to work. The Annual Review noted significant progress in this area, especially in addressing budget constraints for livelihood trainings. A high number of individuals received training on financial literacy, livestock, crop-production, business and marketing skills, off-farm income-generating activities, and employment pathways. The number of participants trained on crop production and employment pathways remained low. The performance of training component is assessed as satisfactory, but some issues need attention: (a) there is the need to develop metrics for monitoring the quality and effectiveness of trainings; (b) define “the complete” package of training or revise the indicator as training needs vary for different individuals, and (c) develop indicators for reporting information about participation with disaggregation by sex of household head.

Indicator 4.3: This indicator tracks the coverage of livelihoods transfers. The objective of this intervention is to provide additional support to PNSP beneficiaries to accumulate productive assets and generate income. The expectation is that this will enable them to graduate out of the programme over time. The programme provides $200 or ETB equivalent to eligible households. In 2017/18, 17,699 households received livelihood transfer – much below the milestone of 50,070 households. This sub-component of this output is being implemented as a pilot in 43 woredas of Amhara, Tigray, SNNPR and Oromia. A randomised controlled trial (RCT) is being undertaken to assess the impact of this intervention following which decisions for scaling up or otherwise will be taken. The primary source of delay was due to the design and implementation of the Livelihoods Grants Impact Evaluation (the RCTs needed more time to plan and prepare for fieldwork), which was a pre-condition to roll-out the entire intervention.

Indicator 4.4: This indicator measures progress on the development of business plans with support from the programme. This process enables poor households to identify the potential income generating activities they can undertake, and then access credit or grant according to the plan. In 2010, 143,036 individuals were supported to develop their business plans against the logframe target of 157000. This included 25,506 business plans for off-farm income generating activities.

Indicator 4.5: This indicator tracks performance of the third pathway under this output i.e. linkages with employment opportunities. In 2010, 27,534 PSNP beneficiaries were linked to wage employment against the logframe target of 42,000. This sub-component has consistently performed poorly because existing PSNP systems are not fit for this purpose. Information about employability and skills of beneficiaries, a database of employers and access to employment information, and a robust referral mechanism are needed to deliver this component. This is a design issue which needs discussion among development partners to take a view on (1) whether PSNP is the right place to deliver this sub-component; (2) or is it more appropriate to deliver it through MOLSA or any other government agency; and (3) institutional mechanisms needed for delivery. This is an unrealistic target given demand constraints and should be revised downwards.

Lessons identified this year, and recommendations for the year ahead linked to this output
Investment in delivery systems and institutional structures that are appropriate for different livelihood pathways is important to achieve this output’s objectives. The budget allocation and system strengthening have not corresponded to the ambitious targets set for this output. Key recommendations for the year ahead are:

1. The programme should set realistic targets for training, business plan development, and livelihood transfers, and allocate budget accordingly.
2. Decisions for livelihood transfer scale up should be made on the basis of evidence of impact and effectiveness from the RCT evaluation. As a significant proportion of this component focuses on business plan development and access to credit, evaluation of this modality should also be conducted in 2019.
3. The GoE and development partners should review the design of the livelihood component by mid-2019 especially in view of (a) the RCT findings of the livelihood transfer, (b) emerging evidence on low value for money of microcredit, and (c) new institutional structures and partnerships needed to deliver the results through employment pathway.

Output Title	Effective management and operational processes in place to manage the programme
Output number per LF		5	Output Score	B
Impact weighting (%):		15	Impact weighting % revised since last AR?	Y ↑

Indicator(s)	Milestone(s) for this review	Progress
5.1 Percentage of safety net woredas/regions meeting minimum safety net staffing standards –disaggregated by highland/lowland and new woredas	Highland- 88%	Met expectations A / Programme staffing is good, but with continuing turnover challenges. / Progress has been made in staffing, especially of social workers to facilitate the linkages to other services, and transition of PDS to MoLSA.
	Lowland- x
	new woredas- x
5.2 Incidence of recurrent audit findings (financial, commodity and procurement) on resources at woreda, regional and federal levels	financial management- x	No target set, but reports suggest continuous improvement in financial management; and a Commodity Management Unit has been established to address shortcomings in food management resulting in recurrent audit findings.
	Procurement- x
	Commodity- x
5.3 Percentage of permanent direct support caseload under MOLSA management	50%	Substantially did not meet expectations: C / 0% - but progress on structure and staffing is significant including at leadership levels. Agreement of division of admin budget is yet to be reached
5.4 Percentage of approved woreda regional CD training plans completed/implemented.	85%	Met expectations: A / 91%

Briefly describe the output and provide supporting narrative for the score

Output 5 seeks to measure capacity (including systems, processes and people) at woreda, regional and federal levels to manage PSNP. Progress across the output has been varied: capacity development and financial management have performed well; transfer of PDS clients to MOLSA has been slow but has progressed; and commodity management and staffing at all levels remain concerns.

Last year, the risk rating was revised to reflect weak management of food delivery systems for both PSNP and relief beneficiaries. The Commodity Management Unit is now live, and until it is functioning adequately and demonstrating significant, timely progress against the action plan, the risk rating should remain at Major.

5.1 Capacity development and adequate staffing of PSNP woredas remains a concern, but progress has been made in recruitment – in particular in more remote woredas. The principal issue is high turnover, largely attributed to low salaries (as compared to those for other flagship government programmes and across implementing partners within PSNP). Recommendations to adequately harmonise salaries and benefit packages need to be taken forward if this issue is to be resolved. Capacity concerns would be partially solved by this harmonised pay package – but ensuring transparent budget allocation for cascading training is also key.

5.2 Financial management is basically good in terms of both completeness and timeliness, though capacity differs depending on the region. Across the board, it is on a continuing trajectory of improvement. For the first time this year, all quarterly reports were submitted on time. There have been five consecutive unqualified financial audits. Where capacity is lower and risk higher (the Somali and Afar regions), verification and quarterly spot checks were implemented to increase oversight, and MoFEC has increased oversight of officials in Afar region.

Financial audit action plans are prepared in less than a month and financial audit findings are addressed in a timely manner. Adequate structure for internal audit exists, and MoFEC has recently reformed to allow internal auditors access – but there is a need to ensure PSNP is audited well at woreda level. Training for MoFEC auditors has recently been reformed to include the PSNP – DFID and the DCT should continue to drive system strengthening here to transform improvement into long term strength.

319 woredas (source IFR Q4) now use IBEX software (thereby aligning PSNP financial management with the wider government public financial management system); and 96% of the woredas (source June 2018 JRIS) use the PASS system for payroll. The new version of PASS upgrading is now complete and implementation has begun: at the time of this review, RPASS pilot testing has been conducted in eight woredas, and 314 operators in Oromia and Tigray have been trained.

Procurement: A significant amount of procurement has already taken place during the first quarter of EFY 2011, so far with satisfactory progress (as per the Nov 2018 JRIS report). Various procurements for federal level consultancies are ongoing – despite delay, two have recently been completed: for the MIS, and for the establishment of a public works mapping database. The STEP programme, an online planning and monitoring tool, needs to be used at both federal and woreda level with more consistency to ensure proper procedure and avoid these delays.

Commodity management: A key achievement for this year is the creation of the Commodity Management Unit, including agreement of its budgets, staffing and operations. This follows some years of poor performance and delay with both procurement and distribution of food, despite year on year audit – as at June 2018 there had been 8 consecutive qualified commodity audits. Recurrent audit findings relate to the internal control mechanisms and little or no improvement in the overall food management system.

A clear action plan to improve commodity management was put in place in February 2018, and progress has been made – including the operationalising of the joint Commodity Management Unit which is now staffed by NDRMC and FSCD staff. The June 2018 JRIS Mission noted that immediate significant improvements were required for DPs to continue to support food purchases for the program – this recommendation has been repeated in the December 2018 JRIS.

5.3 Transfer of the direct support caseload to MOLSA is an important step towards building a social protection system. MOLSA carry out this function for the urban PSNP, but it has so far proved a challenging administrative, logistical and political exercise to implement for the rural PSNP. None of the caseload is under MOLSA management as yet – this year the delay has been caused by difficulties at BOLSA level agreeing budget for administration; and due to changes in leadership at MOLSA. Good progress has been made though, in ensuring the human resources and logistics at federal and regional level are in place. Social workers have been hired at regional level to 95%+ capacity in all bar the Somali region.

5.4 There has been significant success in capacity development this year, despite a reduction in budget agreed last year in response to the financing gap. The DCT and the JRIS process identify the right actions as necessary and take steps to resolve issues and respond to key risks – this year including: recognising the need to strengthen institutional capacity, increasing awareness of the PIM and improving PSNP staff contract management guidance. Re-prioritising according to GoE federal priorities has also taken place – now focusing on continuation of provision of several federal Technical Advisors to key government counterparts.

An integrated annual CD plan for PSNP was prepared for the first time during EFY 2010. This included capacity development guidelines, which clarify the roles and responsibilities of stakeholders responsible for capacity development, and were disseminated to the regions. Plans for EFY 2011 are ambitious given challenges presented by continued high staff turnover.

Areas of support have included:

- Use of monitoring and reporting tools at woreda level (important as an interim solution, and in future if the MIS and programme registry are to function).
- E-payment; PIM awareness; contract staff management guidance.
- GSD and nutrition: materials have been revised and updated, including adapting materials for local contexts, and training for trainers in the highland regions has taken place. (It is noted that the same level of improvement is not seen in lowland regions.)
- Materials to support the livelihoods component, including on financial literacy, crop-production, and income generating activities.
- Capacity building for health extension workers and education experts.

The Technical Assistance to Strengthen Capacity Development is particularly important for these efforts.

The government has also committed to scaling up the UNICEF pilot next year to improve – among other things – capacity at local level for the linkages to services. If possible, donors should advocate for the implementation of any – particularly cost neutral – lessons which can be taken from the pilot and its government-funded expansion.

Recommendations:

Harmonise pay and benefits for local staff working on PSNP (as compared to other government programmes) – this is a challenge for federal ministries, but MoFEC has taken note of the implication for the programme and donors will continue to press the issue (including in the Aide Memoire of the most recent JRIS mission).

Donors’ approach to driving progress on financial management – requiring that funding depend on improvement – was successful: hard incentives like this should continue to be used to drive performance in commodity management.

It is important to take seriously and facilitate transparent discussion regarding the capacity questions raised by MOLSA, in terms of admin budget and staff on the ground to adequately deliver to PDS clients. If WOLSAs are to achieve their case management objectives, including linking clients to complementary services, they need to be adequately supported. (The lesson from the urban PSNP that BOLSA is given a proportionate share of the administrative costs for the percentage of PDS recipients relative to the whole programme should be considered as a possible solution to the difficulty agreeing budget at BOLSA level.)

Establish the cause of the bottleneck in using STEP and take action to address.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The Programme’s Theory of Change continues to be relevant and no major changes have been made to it this year – a summary (including assumptions) is outlined below.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Preliminary results from the 2018 mid-line impact evaluation, spot checks and direct feedback gathered from beneficiaries during field visits confirms that the programme is on track to contribute to the expected outcomes and impact. The PSNP4 has demonstrated a clear trajectory of positive change in the lives of beneficiaries despite the recurring of issue of delayed and unpredictable transfers and other delivery challenges, indicating that the design and theory of change continue to be relevant to the needs of Ethiopia’s poor population.

At the outcome level, the programme seeks “enhanced participation in improved rural safety net, livelihood and nutrition services by food insecure female/male headed households”. The programme has succeeded in expanding participation of extremely poor households across all regions of Ethiopia who are at risk of food insecurity, and loss of productive assets. In 2010, the total number of beneficiaries reached around 8 million of whom 4,113060 (51.4%) are females. A salient feature of the programme is its ability to respond to the needs of those poorest households who cannot indulge in public works due to age, disability, or others through Permanent Direct Support (PDS) and Temporary Direct Support (TDS) beneficiaries.

At the impact level, the programme envisages that “resilience to shocks and livelihoods enhanced and food security and nutrition improved for rural households vulnerable to food insecurity. The programme is on track to contribute to this objective through cash and food transfers and livelihood support to those most in need, and by evolving stronger mechanisms for scalability of the PNSP4 to provide extended support during drought and other humanitarian crises. While further analysis and triangulation is needed to understand the pathways of change, preliminary results from the 2018 mid-line indicate that:

- The percentage of beneficiaries reporting that they can provide adequate meal for their family for 12 months is 43% in highlands and 66% in lowlands. These figures suggest a huge improvement over the 2016 baseline which reported 35% of the beneficiaries could provide adequate meal for their family for 12 months (i.e. zero food gap). Currently, the number of months of self-reported food insecurity (mean food gap) is 1.83 for highlands and 1.50 for lowlands.
- Household dietary diversity is 4.39 for highlands and 4.87 for lowlands.
- Households have accumulated productive assets. The mean value of total livestock holdings is Birr 15,112. The mean number of livestock holdings in PSNP households is 2.90.
- 15 percent of PSNP households sold assets in distress for meeting the food needs in the last two years.

All but one of these results shows a marked improvement from the baseline (though these early midline results will be supported by the full analysis in January 2019). There is scope for improving the outcome and impact for female-headed households. The mid-line suggests that the mean value of the livestock holding was considerably lower for female-headed households (Birr 10,535) compared with those of male-headed households (Birr 19,221).This will require greater integration of gender and social development aspects in PW projects as well as livelihood component.

Explain major changes to the logframe in the past year (1/2 page)
There were no major changes made to the logframe this year, but output indicators and weightings were altered to align with the revised logframe that was a result of the 2017 Midterm Review. These changes were recommended in the last Annual Review in order better to reflect the programme outcomes and availability of data. The overall outcome and impact have not changed.

Describe any planned changes to the logframe as a result of this review (1/2 page)
The indicators in the logframe were updated this year. The milestones for next year will be reviewed and aligned with PSNP’s Annual Plan in view of recommendations of this Annual Review and the November JRIS.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

Key cost drivers and performance

The critical cost driver in PSNP is the transfers paid to beneficiaries, as cash or food transfers. In 2017/18 this amounts to 78% of the programme overall budget.

This is determined by (i) the number of recipients (caseload); (ii) the size of the transfers provided to households each month (wage rate revision will affect this); and (iii) the frequency of transfers paid per year( the extended support to PW beneficiaries will increase the amount of transfer value).

Cost Catagories -2017/18 in %

Increase in the number of cash transfer districts (beneficiaries) and rolling out of the e-payment woredas (now reaches 112 woredas) decreases overall delivery costs (in-kind food transfers incur greater implementation costs, including transport, storage etc).

Non transfer cost like capital expenditure for public works, government staff salaries, system establishment (MIS) and other overhead cost constitute 22% of the overall cost in 2017/18.
E- payment was introduced to the programme in 2015/16 and has the potential to contribute to reducing administrative and recipient costs as well as improving reliability, security and recipient choice.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

PSNP continues to represent good value for money, with independent evidence confirming a range of results on food security and household poverty. Last year’s review also presented evidence of wider economic impacts, both local and national.

Economy

Government of Ethiopia and PSNP donors made major programme cost reducing decisions in July 2017, to be applied from EFY2010 to EFY 2012 and this helped the programme to focus on core activities and programme sustainability. These changes were:

- Eliminating the federal contingency budget annual allocation of US$50 million equivalent;
- Reducing the transfer value from 15 kg of cereals and 4 kg of pulses per person per month (or the cash equivalent) to 15 kg of wheat per person per month;
- Scaling back the number of people to receive livelihood grants from 30 percent to 10 percent of the public works clients ; and,
- Reducing the range of system-building activities to those that are core to the objectives of the PSNP
Procurement under PSNP is carried out in accordance with the World Bank’s Procurement Regulations. The Regulations were guided by the core procurement principles of value for money. The procurement activities under this project included food grain, hand tools and construction materials for PW, and capacity-building items such as IT equipment, office furniture, vehicles, and motorcycles. The benefits from economies of scale is also continued.

Efficiency
The Total Cost to Transfer Ratio (TCTR) – ratio of total costs to value of transfers at delivery was also calculated for this annual review period (EFY 2010). The TCTR for EFY 2010 was 1.22. This means that it cost a total of 1.22 Birr, or 0.22 Birr in non-transfer costs, to deliver one Birr of transfers to a beneficiary household. The TCTR in EFY 2007 (PSNP3) was 1.30; in EFY2008 TCTR was estimated to be 1.29; and in EFY 2009 the TCTR amounts to 1.13. The cost of transfer has slightly risen because of.an increase in overhead cost resulting from increase in staff salary expenditures (because of split in Weredas) and a new budget line (Wereda capacity building expenditure). In general the cost of transfer is very good.
The delivery of assistance to Humanitarian Food Assistance beneficiaries through PSNP system with a common set of operational procedures is also helping to improve the efficiency and cost-effectiveness of the response.
Effectiveness

 E-payments have now reached to 112 woredas (Tigray: 18, Amhara: 30, Oromia 26, SNNP: 30 & Somali: 8) which is close to 2.4 million beneficiaries. Thus, more than 50% of cash only woredas are using E-Payment. This helps to deliver greater effectiveness in delivery, significant reduction in payment delays, lower client costs and greater client control over when and where to collect payments, better integration of MIS and M&E systems, and a potential for building financial inclusion amongst the poor. However, problems in operationalising e-payment related to network, low MFI capacity, limited capacity of agents, low commission fee, integration with PASS platform have to be countered.

Equity

Addressing issues of equity is a broader focus of the programme to reduce poverty and a significant focus on other equity dimensions such as tackling gender inequality and reaching vulnerable groups.
 Female-headed households and widows with permanent health and physical challenges were re- targeted for permanent direct support and furthermore PLW as well as women who served as caregiver for malnourished under 5 children were also being re-targeted for temporary direct support (TDS) (exemption from PW).

Initial analysis of HICES data suggests that there is scope for PSNP to reconsider its geographical targeting, based on consumption poverty distribution across zones. DFID is commissioning consultant expertise to further consider the programmatic implications of these findings, alongside others such as the household economy analysis of food security trends across livelihood zones.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation
PSNP4 is a large, complex and ambitious programme, which is expected to deliver large-scale benefits but also entails a number of risks. The programme is assessed overall as major risk with a number of moderate probability risks existing that hold the potential to impact the programme’s results if they materialise. The programme Risk Register reflects risks across six categories (delivery, context, operational, safeguarding, reputational, financial) and recent changes in the risk context. The programme is major risk, high development return and lies within DFID E’s risk appetite.

This year a number of risks have been realised including another State of Emergency, political unrest and instability and cash flow issues from GoE .The creation of an integrated cash and food response plan went some way to help realising the vision of a scalable safety net, but with some way still to go. Widespread localised protests in many areas of Ethiopia caused problems for programme delivery (in particular food transfers – as evidenced by lack of timeliness in those transfers reaching beneficiaries). However, risk mitigation measures appear to have worked well, and the programme has been resilient to the continued turbulent context. Actions have also been taken to address the performance gap in the lowland areas – including a contract for regular spot checks in Somali and Afar which provide semi-annual reports on performance and compliance.

The overall risk rating is expected to reduce over the next year as the new political context beds in and new staff improve their understanding of the programme. Contextual risk will reduce if drought and political instability subside (a relatively weak El Nino effect is expected in the Horn of Africa in the coming year). The MTR provided an opportunity to adapt the programme to the new budget and revision to the programme and its logframe (as reflected in this AR and logframe). IAD’s last review of PSNP4 (2017) indicates that the programme has adequate risk mitigation measures and a strong governance framework in place.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)

PSNP is a Government of Ethiopia-owned programme, and is delivered almost entirely through GoE systems (with the exception of micro-finance institutions that deliver e-payment transfers to beneficiaries). As such, the performance of GoE in delivering this programme has been largely addressed above through the indicators and associated narratives. The summary of the updated Fiduciary Risk Assessment Annual Statement of Progress and the Partnership Principles Assessment are given below. These annual assessments reflect the state of the relationship and fiduciary risks associated with programme. The overarching Public Expenditure Framework Assessment is due to be updated next year in full (2019).

Update on partnership principles
As aligned non-budget support financial aid, our engagement with PSNP is governed by the Partnership Principles directing DFID’s overall relationship with the GoE. These Principles cover (i) commitment to poverty reduction and the Sustainable Development Goals; (ii) respecting human rights and other international obligations; (iii) improving public financial management, promoting good governance and transparency and fighting corruption; and (iv) strengthening domestic accountability.

The updated Partnership Principles Assessment (PPA), September 2018 highlighted optimism in the wake of the recent political shifts (principally the election of PM Abiy Ahmed and his reform agenda, but also noted continued concerns about aspects of civil and political rights in Ethiopia following the State of Emergency. It also highlighted the Government’s continued commitment to reducing poverty.  “We therefore judge that it remains appropriate to use targeted financial aid to improve the life chances of poor people in Ethiopia. This is also the most effective way to provide value for money for the UK taxpayer.”
In addition to the DFID Ethiopia PPA, the programme-level PPA was updated in November 2018 to assess the application of the Principles specifically with regard to PSNP4. This concluded that “On the basis of this assessment we conclude that, at the programme level, there remains evidence of a credible commitment of GoE across the PPs and that aligned non budget support financial aid remains appropriate to deliver results for the poorest in Ethiopia through PSNP.”

Fiduciary Risk Assessment
The Annual Statement of Progress of the Fiduciary Risk Assessment was updated in October 2018 and assessed the public financial management system fiduciary risks, including corruption risks. This was followed by the programme level ASP dealing with specific programme-related fiduciary risks. The programme level ASP highlighted some new risks (such as the huge changes in government staffing and political leadership in Somali – mitigated by the doubling in coverage of the annual MoFEC audit and the spot checks in Somali), but also noted the satisfactory progress against others. The overall level of risk at the programme level was assessed as being moderate and stable.

One of the key risks associated with the financial and commercial elements of the programme last year was the weak procurement and commodity management. This year that weakness has started to be addressed via the establishment of the joint Commodity Management Unit which is now responsible for all elements of management of the food transfers in PSNP. This improvement should continue to mitigate the risks associated with commodity management, and should also allow donors to lift the restrictions imposed last year on the use of donor funding for food purchase in the programme.

The programme continues to receive unqualified financial audit reports, and the mechanism for drawing back funds for ineligible expenditures continues to function well. Additional support is being provided on FM and procurement through the continued provision of TAs embedded in federal ministries on these key areas, and regional support is also provided through the Capacity Development component of the programme to strengthen FM and procurement capabilities.

Date of last narrative financial report(s)	September 4, 2018
Date of last audited annual statement (s)	June 2,2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)
PSNP4 has a robust and multi-layered set of monitoring and evaluation processes. These include independent evaluations as well as government and donor review processes.

The Government of Ethiopia provide an annual report for the programme written by the Food Security Coordination Directorate (FSCD) within the Ministry of Agriculture and Livestock (MoAL). This summarises progress over the Ethiopian Financial year. The Ministry of Finance and Economic Cooperation (MoFEC), who manage finances for the programme, produce quarterly financial reports known as Interim Financial Reports (IFR). These record the flow of money from donors to the government and from federal to regional and woreda level and expenditures incurred.

Donor-led processes include the Joint Review and Implementation Support (JRIS) mission which occurs twice a year and produces a report, assessing progress against the outputs and outcomes of the logframe. This process involves a large number of government and donor counterparts working together in each region and at federal level and a set of field visits. DFID also produces an annual review. Last year, a Mid-Term Review (MTR) was also completed by technical working groups (TWGs) to produce working papers for each output and a synthesis.

The AR has been conducted by a DFID social development adviser from another DFID country office along with a social protection policy manager from DFID’s central social Protection Team based in London, the Programme Manager and the Programme Officer from DFID Ethiopia’s Livelihoods and Humanitarian Team (LHT). The review has been quality assured by the LHT Team Leader. The AR draws on programme documentation (described above); discussions with GoE staff, DCT technical staff and other development partners; a field visit to Tigray and SNNPR and Joint Review and Implementation Support mission attendance. During these visits, discussions took place with GoE staff responsible for programme implementation at regional, woreda and kebele level and with a small number of programme clients through focus group discussion and interviews. Direct feedback from stakeholders has been incorporated into the main body of this review.

Table 3:	Monitoring and evaluation processes and documents
Name	Purpose	Lead	Timing
Household Impact Survey (HIS)	To conduct rigorous, longitudinal impact evaluations.	International Food Policy Research Institute (IFPRI)	Biannual (January 2016, 2018, 2020).
PSNP Annual Report	To summarise annual progress and challenges	Government of Ethiopia. Food Security Coordination Directorate (FSCD)	Annual (covers July-June, comes out in September).
Joint Review and Implementation Support Mission (JRIS)	To assess progress towards achieving the outputs and outcome of the PSNP4.	Government with participation from donors and DCT.	Twice per year (June/July and November/December).
Mid Term Review (MTR)	To take stock of programme progress and strategic direction at mid-point.	DCT, external consultant, and technical working groups.	Once per programme cycle. Completed in 2017.
Interim Financial Reports (IFR)	To report on donor disbursements and programme budget execution	Government of Ethiopia. Ministry of Finance and Economic Cooperation (MOFEC)	Quarterly.
DFID Annual Review	To review progress of DFID’s investment against logframe.	DFID Senior Responsible Owner (SRO)	Annual (covers July-June, comes out in December).
Governance Retreat	To reflect on progress and discuss governance of the PSNP.	Development Partners (DPs)	Annually in PSNP 4.
Spot Checks	To review compliance with approved procedures	The World Bank	Need-based
Audit	To check financial and commodity flows, stocks and procedures in the programme	Government of Ethiopia. Ministry of Finance and Economic Cooperation (MOFEC)	Twice per year

Evidence (1/2 page)
PSNP awarded a 6 year contract to a consortium led by the International Food Policy Research Institute (IFPRI) to conduct an evaluation of performance and impact, with longitudinal survey rounds every two years. This is known as the Household Impact Survey (HIS). The surveys are representative at regional level and there is also qualitative research alongside the surveys. This evidence will allow disaggregation by region, programme instrument, sex and age. The baseline HIS was conducted in January 2016. Findings from that survey were covered in the 2016 annual review, so they have not been repeated here. The mid-line was completed in November 2018 and limited preliminary results shared with DFID and the development partners. As described in the Section C above, the results indicate that the theory of change holds and the programme is making positive contributions to reducing food insecurity and extreme poverty. Full results and analysis will be available in January 2019. The end-line evaluation for PNSP4 will be completed in 2020.

In addition to the above impact evaluation, a randomised controlled trial (RCT) is being undertaken to evaluate the livelihood transfer pilots. This study will provide evidence on income generation potential of the one-off grants provided to adult clients of the public works components. A tracer study is also being planned to gather evidence on the impact of linking individuals from PSNP beneficiary households to employment opportunities.

Learning (1/2 page)
PSNP has developed a number of learning processes within the programme cycle. A major platform is the JRIS Mission after every six months. The Mission brings together key government officials from all levels and implementing agencies, and representatives of the development partners to take stock of progress, and exchange views on performance issues. The Mission also provides an opportunity to the participants to visit community works in kebeles and gather direct feedback from beneficiaries. This process has been extremely useful in developing a shared understanding of the programme objectives, outputs and operational processes. In addition, the annual Governance Retreat of Development Partners also provides a platform for learning about best practices in areas related to PSNP.

In 2018, a number of special studies were also commissioned to develop a deeper understanding of performance issues. These included a spot checks study in the Somali and Afar region, and a study on the causes of delays in cash and food transfers. The findings of these studies have been shared with stakeholders. Key recommendations from these studies will be used for course corrections and improving systems as part of the JRIS Action Plan.

Progress on recommendations from previous reviews (1/2 page)

Summary of recommendations from 2016/17 AR
1. A solution needs to be found to complete the MIS procurement. In the meantime, discussions should focus on how to improve existing systems, following the woreda level monitoring and reporting assessment, currently underway. Procurement completed.
2. Improved cash flow management - GoE and DPs should ensure predictable resource flows with timely disbursements of resource commitments. In year cash flow impacts PSNP’s ability to make timely payments, as seen this year. All DFID funds disbursed in a timely manner but wider cash flow management requires further support, as GoE’s contribution increases.
3. Improve timeliness of payments, meeting the programme’s benchmarks for timeliness. Some progress made on cash timeliness, but food timeliness impacted by instability.
4. Continue to focus on delivering performance improvements in Afar and Somali regions, building on the efforts made over the course of 2016/17. Spot checks and additional capacity development in place for both Somali and Afar.
5. Donor partners to press GoE on longer term solution to timely food response ie single institutional structure to ensure timely availability of food resources and delivery to the woredas for both relief and PSNP beneficiaries. Joint Commodity Management Unit now operational Issues raised in Dec 2018 JRIS.
6. Monitoring and reporting systems should be strengthened, and should better describe gender and social development aspects of the programme. Gender disaggregation and reporting on disability are included in the design of the newly procured MIS.
7. DFID Ethiopia should update its VFM assessment of PSNP following the MTR. This should include the selection of a set of VFM metrics to track over the lifetime of the programme, working with other donors, the DCT and GoE to build support for the concepts within the programme. This piece of work will be commissioned in the new year 2019, informing the design of the next investment.
8. As recommended in the recent physical asset assessment, PSNP should introduce a comprehensive physical asset management programme to develop better asset management processes. A system to address this issue is in the process of being commissioned by the GoE.
9. The subset of logframe indicators that DFID uses to assess performance of the programme should be revised in line with the wider programme logframe revision that is part of the Midterm Review process currently underway. This should take into account those indicators that have annual availability of data, given DFID’s own requirement for annual review of progress. The logframe was revised in advance of this annual review in a workshop process.