PROJECT TITLE	Lablite: Optimising clinical care strategies and laboratory monitoring for cost-effective roll-out of ART in Africa
Impact	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
To improve efficiency of HIV programmes in Africa thus enabling more people to be on effective treatment	Impact and efficiency of HIV programmes in Africa improved by getting new knowledge and research into policy and practice more rapidly and effectively
		Source

outcome		Indicator		Baseline + year			Milestone 1	Milestone 2		Target + year	Assumption
To enable the use of effective approaches in the decentralisation of ART/HIV treatment programmes in Africa		Local: Sustainable approaches for decentralisation of ART initiation and follow-up implemented at lower level health centres in Malawi, Uganda and Zimbabwe									Planners and policy makers are not constrained by vested interests to develop new policy and practice that is sparing on technology
				Source
				Lablite publications, presentations and policy briefs / Lablite country reports
		Indicator		Baseline + year			Milestone 1	Milestone 2		Target + year
		National: Approaches developed in the Lablite project adopted to district- and national-level policy and practice in Malawi, Uganda and Zimbabwe
				Source
				National ART policy documents and reported practices in African countries
		Indicator		Baseline + year			Milestone 1	Milestone 2		Target + year
		International: Lablite provides an understanding of actual practice at lower level health centres in Malawi, Uganda and Zimbabwe which feeds into and encourages dialogue, internationally, around implementation of new WHO guidelines
				Source
				Lablite communications logs / Lablite publications, presentations and policy briefs / Annual meetings minutes
INPUTS (£)	DFID (£)		Govt (£)		Other (£)	Total (£)			DFID SHARE (%)
	£2,302,366
INPUTS (HR)	DFID (FTEs)

OUTPUT 1	Indicator	Baseline / May 2011	Milestone 1 / Nov 2011	Milestone 2 / Jul 2012	Target / Aug 2014	Assumptions
Effective ART service packages tested	Baseline survey completed	limited knowledge about service provision for ART	Survey designed	Survey carried out	Survey results analysed and reported	Possible to collect clinic outcome measurements without providing so much support and supervision to staff that data are distorted and not representative of the actual situation in each country
		Source
		Lablite publications, presentations and policy briefs / Annual meeting minutes
	Indicator	Baseline / Aug 2012	Milestone 1 / Dec 2012	Milestone 2 / Jul 2013	Target / Mar 2015
	Training materials and tools developed and evaluated	Training needs assessment	Development of training materials	Training designed and implemented	Training rolled-out and evaluated
		Source
		Lablite training manuals, job aides and video case-studies / Accreditation documentation / Lablite participation in PENTA courses / Case-study reports / Lablite publications, presentations and policy briefs
	Indicator	Baseline / Feb 2013	Milestone 1 / May 2013	Milestone 2 / Jan 2015	Target / Mar 2015
	Population survey designed and implemented	Survey designed and piloted	Phase 1 Survey carried-out and analysed	Phase 2 survey adapted, carried analysed	Comparative analysis
		Source
		Lablite data collection tools / Annual meetings minutes / Lablite publications, presentations and policy briefs
	Indicator	Baseline / Feb 2012	Milestone 1 / Mar 2013	Milestone 2 / Feb 2015	Target / Mar 2015
	Data from demonstration sites collected and analysed	Selection of demonstration sites	Design of bespoke data collection tools	Data collected	Data analysed and reported
		Source				RISK RATING
		Data sets / Lablite publications, presentations and policy briefs				Medium
						WEIGHTING
						50%

OUTPUT 2	Indicator	Baseline / Sep 2012	Milestone 1 / Jun 2013		Milestone 2 / Dec 2013		Target / Mar 2015		Assumptions
Economic and Qualitative results contribute to knowledge and inform debate around design of services	Qualitative study informs debate around design of services	Qualitative aspects identified as research priority	Study designed and implemented in 3 countries		Results from Malawi, Uganda and Zimbabwe analysed		Study findings reported and disseminated to national stakeholders		Patients and staff will actively engage in and be supportive of data collection. / District health officials and communities will actively engage in and be supportive of data collection / Planners and policy makers are receptive to findings and are not unduly influenced by some of the recommendations in the new WHO 2013 ART guidelines that are not at the moment implementable in Lablite sites and districts
		Source
		Meetings minutes and reports / Qualitative study report and dissemination activities / Communications log / Lablite publications, presentations and policy briefs
	Indicator	Baseline / Jan 2012	Milestone 1 / Dec 2012		Milestone 2 / Sep 2014		Target / Mar 2015
	Equity study adds to existing information on the socio-economic aspects of decentralisation	Equity identified as a priority aspect of the project	Literature review and development of methodologies		Data collected and analysed		Study findings reported
		Source
		Meetings minutes and reports / Lablite publications, presentations and policy briefs
	Indicator	Baseline / Sep 2013	Milestone 1 / Sep 2014		Milestone 2 / Sep 2014		Target / Mar 2015
	Young lives methods developed to estimate quality of life among young people in Africa.	Development of methodology and tool	QoL estimation in children in ARROW		QoL estimation in adults in Lablite		Analysis and reporting
		Source
		Meetings minutes and reports / Lablite publications presentations and policy briefs
	Indicator	Baseline / May 2012	Milestone 1 / Sep 2012		Milestone 2 / Nov 2014		Target / Mar 2015
	Informal Care and Productivity costing techniques developed and applied in study countries	Existing methodologies not suited to the African context	Development of methodologies and data collection tools		Data collection and analysis		Study findings reported
		Source
		Lablite publications, presentations and policy briefs
									RISK RATING
									low
	Indicator	Baseline / Jan 2012		Milestone 1 / Jul 2013		Milestone 2 / Nov 2014		Target / Nov 2015	WEIGHTING
	Effectiveness and cost-effectiveness modelling studies inform debates around national and international policy in HIV	Review of methodologies and literature		Contact with key stakeholders in policy and modellers involved with informing debates around HIV policy		Invitations to participate in key activities aimed at informing debates around HIV policy		Built collaborative relationships with key contributors to the debate around HIV policy which will last beyond the life of Lablite	20%
		Source
		Communications log / International collaborative publications

OUTPUT 3	Indicator	Baseline / Jan 2012	Milestone 1 / Jan 2013	Milestone 2 / Jan 2014	Target / Mar 2015	Assumptions
Build the capacity of African researchers to carry out research in Africa, participating in all steps including presentation of results and written outputs	The number of new and existing African researchers working on the programme. Capacity building of African researchers to carry out research in Africa	African researchers recruited to the Lablite Project	Involvement of Lablite researchers in training and professional development activities	Lablite researchers present Project data nationally and internationally	Lablite researchers are authors on Lablite publications	Trained African researchers remain committed to engaging in research in their countries after the end of the project.
		Source
		Conference abstracts, presentations and posters / Training and professional development activities / Annual meeting minutes
						RISK RATING
						Medium
						WEIGHTING
						10%

OUTPUT 4	Indicator	Baseline / Feb 2011		Milestone 1 / Nov 2013		Milestone 2 / Sep 2014		Target / Mar 2015	Assumptions
Communication of new knowledge and data to relevant stakeholders, planners and policy makers.	Number of a) papers b) policy briefs c) other publications produced	papers 0 (0); policy briefs 0(0), other 0(0)		2 x paper / 1 x policy briefs		1 x paper / 2 x policy briefs		12 x papers / 4 x policy briefs / 3 x other publications	Planners and policy makers are not constrained by vested interests to develop new policy and practice that draws on the project findings
		Source
		Lablite publications, presentations and policy briefs
	Indicator	Baseline / Feb 2011		Milestone 1 / Jan 2014		Milestone 2 / Jan 2015		Target / Mar 2015
	Policy Analysis Study informs debates around policy and guidelines processes nationally and internationally	Lack of knowledge of barriers to uptake of research into policy and guidelines		Design of policy analysis study		Policy analysis carried-out and analysed		Policy analysis study reported
		Source
		Policy Analysis study and outputs
	Indicator	Baseline / Feb 2011	Milestone 1 / Nov 2012		Milestone 2 / Sep 2014		Target + year / Mar 2015
	Lablite results feed into and encourage dialogue, internationally around decentralisation of ART and implementation of new WHO guidelines	Lablite not part of dialogue around decentralisation of ART and implementation of new guidelines	Participation by members of Lablite team in guidelines committees		Invitations to meetings with key stakeholders		Relationships built with key international stakeholders which will last beyond the life of Lablite
		Source
		Communications logs / Lablite Meetings minutes
									RISK RATING
									medium - high
	Indicator	Baseline / May 2011	Milestone 1 / Jan 2012		Milestone 2 / Feb 2013		Target / Mar 2015		WEIGHTING
	Local researchers and wider Lablite team engage with policy makers and influencers.	Minimal local engagement with policy makers and influencers	Contact made with key national stakeholders		Invitations to participate in national policy making activities and groups		Relationships built with key national stakeholders and policy makers which will last beyond the life of Lablite		20%
		Source
		Communications logs