Annual Review - Summary Sheet

Title: South African Partnership for Effective Development Co-operation (SAPEDC)
Programme Value: £5,000,000		Review Date: October 2014
Programme Code: 203622	Start Date: August 2012	End Date: March 2016

Summary of Programme Performance
Year	2013	2014
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review
SADEPC made positive progress in furthering its development partnerships with South African (SA) institutions in several areas, notably through its collaborative development approaches and in supporting SA thinktanks and civil society organisations (CSOs) to influence national and international debates on development. It struggled, however, to provide effective support to the SA Development Partnerships Agency (SADPA), whose establishment stalled over the year. Several key lessons were learned:

SAPEDC demonstrated some of the benefits of effective development partnerships with SA government bodies. However, improved monitoring and evaluation (M&E) is needed to develop higher quality evidence for the impact of this approach compared with traditional bilateral modalities.

SADPA will remain an important aspect of DFID’s development partnership with SA, though the timings of its establishment remain uncertain at the time of writing.

SA thinktanks and academic institutions are well placed to develop high quality products relating to SA’s development role and global development debates. However, outputs produced are most effective when they are demand-led.

The positive role played by SA civil society highlights the levels of influence and access that these groups can have, at multiple levels. Co-ordination and lessons sharing between CSOs working on the post-2015 development goals should be prioritised.

The high number of accountable grants under SAPEDC meant the programme management burden was high – a flexible model for pilot projects, but not likely to be cost effective in the longer-term.

Summary of recommendations for the next year
DFIDSA should start planning a follow on programme, which is multi-year, less management intensive and builds on successful development partnership pilots and CSO support.

The M&E approaches of the implementing partners should be reviewed and strengthened. Risk assessments with each implementing partner should also be confirmed and agreed.

Additional work should be done to consider development partnerships with the SA private sector.

SAPEDC should continue to prioritise flexible support to the establishment of SADPA.

The role of gender in SAPEDC should be addressed and key programme documents updated.

The organisations working on the post-2015 development goals should be encouraged to co-ordinate and share lessons between them on a more structured, regular basis.

Products delivered should reflect the needs of government and other target audiences.

Metrics should be developed in order to accurately measure the VfM of SAPEDC.

The Steering Committee for SAPEDC should meet on a six monthly, rather than quarterly, basis.

A. Introduction and Context

DevTracker Link to Business Case:	Iati.dfid.gov.uk/iati_documents/3770352.docx
DevTracker Link to Log frame:	Iati.dfid.gov.uk/iati_documents/3772221.xlsx

Outline of the programme
The South African Partnership for Effective Development Co-operation (SAPEDC) is a £5,000,000 programme running from August 2012 to March 2016, funded under DFID Southern Africa (DFIDSA)’s Global Development Partnerships Programme (GDPP). SAPEDC is designed to increase the transformational impact of South African development co-operation on poverty, under-development and marginalisation in Africa, as well as its contribution to national and global debates on development.

South Africa (SA) is an increasingly important development actor, both in the region and globally. In the region, SA brings unique expertise and experience to development challenges in Africa. It has engaged extensively in conflict mediation and peacebuilding work over the last 20 years. Its public institutions of budget management, revenue collection, public service planning and performance management, and statistical analysis are models for many of its neighbours. The establishment of a new SA Development Partnership Agency (SADPA) represents recognition of the value of a more formal, coherent approach to sharing this expertise and helping to address regional issues. The private sector has a presence across the continent. Infrastructure investment is driven by a range of public-private partnerships. SA’s civil society is engaged throughout the region on issues of transparency, pro-poor policy advocacy, the post-2015 agenda, peace and security, and health reform. SA academia plays a leading role, notably in driving developmental research.

Globally, SA exerts influence on international deals which are essential for development outcomes, both through its own voice and as an (informal or formal) representative of Africa. It is the only African member of the G20, emphasising the importance of outcomes across the agenda which support inclusive growth for the continent. The 2013 SA-hosted BRICS summit took African investment as its theme. SA will be a pivotal voice for the outcome of negotiations around the post-2015 development agenda at the UN.

This programme contributes to SA’s regional and global development role by working with SA partners to put in place the institutions, skills and knowledge needed to implement successful development programmes and policies. An indirect, but significant result of the intervention is intended to be a strengthened partnership between the UK and SA on international development issues. This is expected to increase the results which the UK and SA can achieve together through collaborative work on development policies and programmes in future.

The overall impact of SAPEDC is that SA regional development assistance and global policy influence have a transformational impact on poverty in Africa.

The programme outcome is that SA regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice.

The programme outputs are:

UK expertise and funding make a significant contribution to the organisational and policy requirements of SADPA.

SA-UK programmatic partnerships in Africa result in sharing and improving expertise on approaches to development co-operation on both sides

SA civil society, academia and think tanks increasingly able to contribute to and constructively shape national and international debate on development issues.

B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

Outcome Title	SA regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice

Indicators	Milestone September 2014	Progress
Status of progress towards establishment of SADPA as a functional organisation	Chief Executive and core staff recruited; management of Africa Renaissance Fund (ARF) transferred to SADPA team	Recruitment of these positions was not carried out, and the management of the ARF remains within the Department for International Relations and Co-operation (DIRCO).
Proportion of UK-funded research outputs (since previous review) which are judged relevant and influential by at least one Government department	50%	A survey to assess this indicator was not seen as reasonable in view of the time burden on officials required. However, in discussions with DIRCO, officials judged that the organisations supported by this programme were in general both relevant and influential, citing at least two publications as evidence of this.

Overall output score and description: A
Looking across the programme’s three outputs, SAPEDC failed to meet expectations on the first, met expectations on the second, and exceeded them on the third. Based on the equal weighting and scores of the three outputs (C, A and A+), the overall output score is assessed as an A.

SAPEDC’s weakest performance was on its support to SADPA, whose development stalled over the course of the year. Whilst DFID’s support to the emergence of SADPA had been well received in the previous year – and was still viewed positively by DIRCO officials – little progress on SADPA’s staffing and processes was made over the course of the year. The programme’s second output, focussing on SA-UK development partnerships, fared much better and achieved the intended targets. A collaboration with the SA Revenue Service (SARS) and the World Customs Organisation (WCO) was assessed to have been particularly effective, providing an effective model of development co-operation which can usefully inform future DFID programming in this area. SAPEDC’s last output, designed to strengthen SA civil society and thinktanks to inform national and international debates on development, was assessed as having exceeded expectations set. The organisations supported produced a larger number of papers and events than was originally intended (see Annex A), and there are some good indications of the impact achieved by some of these products, particularly around informing SADPA’s policy frameworks and the debate on the post-2015 development goals.

The programme’s progress against the outcome indicators reflects a similar picture. Whilst the progress against the milestone relating to SADPA was limited, DIRCO officials did indicate that some of the work of the organisations supported by DFID through SAPEDC was both relevant and influential.

Key lessons

SAPEDC demonstrated some of the benefits of effective SA-UK development partnerships – which were regarded as mutually beneficial by the partners involved and could have enhanced the development impact compared with traditional development approaches. However, further work on monitoring and evaluation (M&E) is required to develop higher quality evidence for this hypothesis.

SADPA will remain an important aspect of DFID’s development partnership with SA, though the timings of its establishment remain uncertain at the time of writing.

SA thinktanks and academic institutions are well placed to develop high quality products relating to SA’s development role in the region and globally, as well as to engage in development debates such as the post-2015 agenda. However, outputs produced are most effective when they are demand-led and risk having limited traction without buy-in from the intended recipient, e.g. the SA government.

The positive role played by SA civil society in this programme highlights the levels of influence and access that these groups can have, at both a national, regional and global level. Since the programme is supporting a number of organisations to engage in the debate on the post-2015 development goals, co-ordination and lessons sharing between them should be prioritised.

The high number of accountable grants under this programme meant that the management burden of this programme on the DFIDSA GDPP team was high. Whilst this model provided a high degree of flexibility and facilitated a number of effective pilot projects, it is likely not a cost effective approach for programming in the longer-term.

Key actions

The GDPP team should start planning a follow on programme for SAPEDC, which is multi-year, less management intensive for DFID and builds on successful pilots. This could focus on development partnerships with SA institutions, or on key themes such as extractives and customs, with partnership modalities embedded. It could also fund a new phase of support to SA civil society groups, facilitating further engagement in regional and global development issues.

The M&E approaches of the implementing partners should be reviewed and strengthened in the next year, to provide further evidence for the benefits of development partnership approaches. Risk assessments with each implementing partner should also be confirmed and agreed.

As recommended in last year’s Annual Review (AR), the programme should initiate work to consider whether partnerships in this area would have a regional development benefit.

Since SADPA remains important for DFID’s development partnership with SA, SAPEDC should continue to prioritise flexible support. Early meetings with the new Transition Team within DIRCO should be undertaken in order to identify potential areas of collaboration.

Though SAPEDC’s outcome is to maximise development results for both men and women, the programme does have clear requirements or targets relating to gender. This should be addressed in the next year, with the logframe, delivery plans and reporting templates updated accordingly.

The organisations supported by this programme working on the post-2015 development goals should be encouraged to co-ordinate and share lessons between them on a more structured, regular basis.

Products delivered should reflect the needs of government and other target audiences as far as possible.

Value for Money (VfM) metrics should be developed to accurately measure the programme’s VfM.

The Steering Committee for SAPEDC should meet on a six monthly basis which would be a more realistic tempo than the quarterly meetings previously envisaged in the Business Case.

Has the logframe been updated since the last review?

Yes. The logframe was revised in January 2014 in line with the recommendations from the last AR. New recommended changes to the logframe are as follows:

- Revise the SADPA output targets, following discussions with the DIRCO Transition Team.
- Revise the outcome indicators to provide a more realistic measure of success at outcome level.
- Update output level targets to reflect new project grants, including with the Council for Geosciences, NEPAD and the Department of Health Ebola response.
## C: DETAILED OUTPUT SCORING

Output Title	UK expertise and funding make a significant contribution to the organisational and policy requirements of the new South African Development Partnership Agency (SADPA)
Output number per LF		1	Output Score	C
Risk:		High	Impact weighting (%):	33%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Indicators	Milestones Sep 2014	Progress
1.1 Status of SADPA project office and management team	Chief Executive and core staff recruited; management of the ARF transferred to SADPA team	Recruitment of these positions was not carried out, and the management of the ARF remains within DIRCO.
1.2 Development of policy framework in areas including post-conflict development, based on consultation with national and international partners including the UK	Terms of reference (TOR) and inclusive process in place for formulation of post-conflict development (PCD) policy framework	TOR were drafted but not approved by DIRCO. Unclear at time of review when the PCD framework would be taken forward.
1.3 Status of UK-funded baseline study on outgoing South African development co-operation	TOR agreed, supplier identified	TOR were drafted but again not approved by DIRCO. Unclear at time of review when the study would be taken forward.

Key Points
After some positive progress was made on SADPA’s development in 2012-13 – including some well received support from DFID – the last year of the programme marked a significant slow-down. For much of this time, the SADPA position in DIRCO was effectively unfilled, meaning that there was no permanent interlocutor to take forward the collaboration with DFID. Consequently, a number of planned initiatives stalled. The recruitment process initiated in September 2013 was paused and had not yet resumed at the time of this review. DIRCO’s current intention is to set up a transition team to oversee the establishment of SADPA, which could be established by November 2014. Whilst the TORs mentioned above were drafted, these were not approved by DIRCO and neither projects were initiated.

Despite this, there were some positive developments. Parliament has taken an increased interest in SADPA over 2013-14, and DFID has initiated engagement with the International Relations Committee. The support provided by the Institute for Global Dialogue (IGD) was welcomed by DIRCO, particularly its contributions to the development of a trilateral policy framework for SADPA, in collaboration with support from GIZ.

Summary of responses to issues raised in previous annual reviews
Several of the recommendations in the last review related to providing support through the Technical Assistance Unit (TAU) in the National Treasury. Whilst an MOU was drafted between DFID and DIRCO to initiate this, and some initial work was undertaken, it was not approved by DIRCO and did not progress.

Recommendations
1. Despite recent slow progress, SADPA’s establishment is important for the UK’s development partnership with SA. SAPEDC should continue to prioritise flexible and demand-led support to SADPA, meeting with the new Transition Team as soon as possible to identify possible areas of collaboration.

2. The low score on this output was largely due to issues outside of DFID’s control. The indicators and milestones should be revised to ensure that they are realistic for the next year of the programme.

Output Title	South African - UK programmatic partnerships in Africa result in sharing and improving expertise on approaches to development cooperation on both sides
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	33%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicators	Milestones Sep 2014	Progress
2.1 Number of SA development cooperation initiatives achieving results in other countries with UK support through this programme	2	2 initiatives underway – SARS/WCO and Council for Geosciences.
2.2 Contribution of UK-SA partnerships to domestic resource mobilisation capacity and policies in other African countries	Case study evidence demonstrates improved regional coordination and cooperation on customs reform in at least 3 countries	The WCO/SARS project completed missions to 6 countries. A publication of 17 case studies from this project is forthcoming.
2.3 Contribution of UK-SA partnerships to global health challenges and national health sector policies in other African countries	Opportunities identified for SA expertise to inform regional health sector needs	A UNFPA led project is gathering lessons from SA’s experiences on maternal and neonatal health, to share with regional health departments.
2.4 Contribution of UK - SA partnerships to building more open and effective governance institutions in other African countries, through networks of expertise	At least two UK-supported, SA-led regional networks of expertise in place on issues of governance and open institutions	A regional research and outreach project led by UCT on began in April 2014. The ISS project included an international peacebuilding conference in January 2014.

Key Points
This output made positive progress in several areas, demonstrating the regional benefits of effective development partnerships. The co-operation with the SA Revenue Service (SARS) and World Customs Organisation (WCO) on customs reform was particularly successful, facilitating 7 capacity strengthening missions in 6 countries. SARS, WCO and the Malawi Customs Authority highlighted the strengths of this TDC approach and a second phase of the project will begin in late 2014. Other collaborations have only recently started, but show early signs of promise. The ‘Building Bridges’ project with the University of Cape Town (UCT) has recruited impressive political and policy research fellows, and initiated a young African leaders programme, with a focus on regional economic integration. An experts’ symposium will be held in November and the project was praised by the Minister for Africa when he visited in September 2014. The partnership with the Council for Geosciences on support to geological survey capacities in Zambia and Malawi started in September 2014, and was commended by DFID’s Senior Advisor on Extractives during a visit in October. UNFPA’s project on sharing SA’s lessons on maternal and neonatal health will culminate in a regional conference in November 2014.

Summary of responses to issues raised in previous annual reviews
As recommended in the last review, this output has been revised to focus on UK-SA development co-operation in third countries, with a number of new initiatives initiated over the past year. The review also recommended exploring ways of working with the SA private sector to enhance their development impact. Limited progress has been made in this area but this was also a recommendation of DFID’s Chief Economist following his visit in September 2014.

Recommendations
1. Scoping work should be considered on whether DFID could undertake any worthwhile collaborations with the SA private sector in the region, building on work undertaken by ISS in this area.

2. The GDPP team should develop a multi-year programme building on the success of these development partnership pilots, including in the areas of extractives and customs, and CSO support.
Output Title	South African civil society, academia and think tanks increasingly able to contribute to and constructively shape national and international debate on development issues.
Output number per LF		3	Output Score	A+
Risk:		Low	Impact weighting (%):	33%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicators	Milestone September 2014	Progress
3.1 Number of UK-funded, SA civil society-produced research papers or events on South African bilateral and trilateral development policies.	10	Over 10 papers or events delivered by ISS and IGD, focussing on SA’s global peacebuilding and bilateral/ multilateral development roles (see Annex A)
3.2 Number of UK-funded, SA-produced research papers or events on global development policy issues including the post-2015 development agenda and the Global Partnership for Effective Development Cooperation	10	Over 10 research papers or events were delivered by IGD, SALO and African Monitor, largely with a focus on the post-2015 development agenda (see Annex A)
3.3 Level of involvement and influence of South African civil society organisations in support of priority issues on the post-2015 development agenda	At least 2 supportive civil society voices on "golden thread" themes identified and strengthened. African Monitor providing recognised regional leadership.	Both SALO and AM now supported through this project, focussing on ‘golden thread’ themes including peace and security, LGBTI and good governance. AM providing regional leadership through its chair of the Africa CSO Working Group.

Key Points
The CSOs and thinktanks supported under this output – the Institute for Security Studies (ISS), Institute for Global Dialogue (IGD), African Monitor (AM) and the Southern Africa Liaison Office (SALO) – demonstrated high levels of productivity, exceeding most targets. High quality research papers and events on SA’s global role in peacebuilding were delivered by ISS, with a focus on the AU, UN, BRICS and private sector. IGD produced several papers on SA’s development role via multilateral and trilateral approaches. A paper on SA’s TDC role was published in the SA Journal of International Affairs and was recognised as valuable by DIRCO, leading to the support on SADPA’s trilateral framework. Between them, IGD, AM and SALO delivered a number of papers and events on the post-2015 development framework. Events were held in SA, the region and in New York in order to facilitate common positions amongst African civil society and to influence negotiations at the UN. The greatest traction seems to have been achieved by AM, which had a series of meetings with African representatives in New York and in the region, and engaged constructively in the Open Working Group process. Through chairing the Africa CSO Working Group, and collecting 23,000 signatures for a regional youth petition, AM is providing the regional leadership intended. See Annex A for a full list of products and events.

Summary of responses to issues raised in previous annual review
The last review recommended supporting a wider range of actors to engage on international development issues, including civil society. This has been addressed through the support to SALO and a forthcoming project with NEPAD to support African negotiators in the inter-governmental process.

Recommendations
1. Co-ordination and sharing of lessons between the CSOs working on the post-2015 development goals under this output should be prioritised, through more information sharing and regular meetings.

2. Whilst the organisations supported are clearly delivering to a high standard, their deliverables are not always demand led, particularly relating to DIRCO/SADPA. The programme should ensure that the products delivered reflect the needs of government and other target audiences as far as possible.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The key cost drivers remain those highlighted in the Business Case. These relate mainly to staffing costs (for advice, research and policy work), travel costs, events and related expenses. Additional drivers include the cost of producing and printing publications, other media publications, and training costs.

VfM performance compared to the original VfM proposition in the business case
The original business case did not include specific VfM metrics, but assessed VfM according to the
effectiveness, efficiency and economy of the interventions. The effectiveness of the programme was defined by the extent to which the activities funded achieved the intended outputs and then in turn the intended outcomes. In this regard, SAPEDC should be regarded as having achieved VfM overall, since where activities were undertaken they largely met or exceeded the intended outputs. The effectiveness at outcome level is more difficult to gauge due to the limitations of the indicators used.

The efficiency of the programme was measured by the programme’s ‘ability to respond flexibly to changing needs and to evidence on which components are performing well.’ In this regard SAPEDC is also assessed as having achieved VfM, since its funding mechanism has proved flexible enough to respond to emerging priorities, such as the rapid support provided to SA’s Ebola response in October 2014. However, SAPEDC’s efficiency in the business case was also predicated on a low management burden for DFID. In this area, the high number of components and implementing partners (at least 10 components at the time of writing and 14 implementing partners) has required a greater administration burden than was originally anticipated. Whilst this strengthened relationships between DFIDSA and a range of implementing partners in government and civil society, it also made it more challenging to actively manage the performance of the partners and their delivery against programme targets.

On its economy, SAPEDC’s VfM was based on a scrutiny of partners’ budgets and processes as part of the approval process, to ensure consistency with DFID guidance. Throughout the year, the budgets for each project were reviewed in this way before approval, and the due diligences of partners undertaken included a review of financial processes including procurement. This provides a degree of reassurance on SAPEDC’s VfM economy, but again this is difficult to measure accurately without specific metrics.

Assessment of whether the programme continues to represent value for money
The lack of VfM measures makes it difficult to assess whether SAPEDC continues to represent value for money. According to the 3E approach, the picture is mixed. Whilst the programme demonstrated the flexibility and responsiveness intended, and the activities undertaken largely achieved the intended outputs, this has come at the cost of a management burden which was higher than anticipated. It is recommended that some simple VfM metrics are developed when the logframe is revised in order to more accurately measure the VfM effectiveness, efficiency and economy of the programme.

Quality of financial management
DFIDSA’s Commercial Advisor reviewed a selection of quarterly financial reports submitted by implementing partners, concluding that a greater level of detail should be provided. The reports reviewed were at a high level (no units, quantities or their respective rates included), which makes it difficult for DFID to scrutinise expenditure and to undertake VfM assessments. The compliance of partners with the terms of the accountable grant agreements (AGAs) was varied. Some partners were fully compliant - in the case of WCO, for example, unspent funds and related interest amounting to 32,732.62 Euros is in the process of being returned to DFID. Nonetheless, whilst a number of partners have provided audited financial statements for review, at the time of this AR others were late in the submission of these.

To strengthen financial management of SAPEDC, it is recommended that in addition to reviewing the submitted audited statements, DFID undertake spot audits / checks on the project finances of the grant recipients, where DFIDSA staff resources allow this. As the management of the programme has been retained in-house, DFIDSA should also strengthen the financial management report and tracking tool to ensure consistency with the requirements of ARIES and the central GDP Team.

Date of last narrative financial report	Various. Last was October 2014
Date of last audited annual statement	Various. Last was September 2014.

E: RISK

Overall risk rating: Medium

Overview of programme risk
The main risks remain those outlined in the Business Case. In particular, the risk of ‘lack of commitment by the Government of SA to establish SADPA manifested itself over the last year, causing output 1 to score a C. Following conversations with the Transition Team in DIRCO, new programme activities should be designed to support SADPA which take into account this risk, and the logframe’s targets should be amended accordingly. A new risk that has emerged is that implementing partners are unable to fully spend their budgets within the period of the grant agreements due to the weakening of the SA Rand against the British Pound (see below for recommended mitigation).

Outstanding actions from risk assessment
At the time of this review, the risk assessment for SAPEDC was being reviewed as required by DFID’s new SmartRules. There are a number of actions which have been identified as outstanding through this review. For example, whilst some of the partners have identified key risks within their quarterly reporting, most do not appear to have risk registers and a formalised risk identification, mitigation and management process in place. This should be addressed as a priority by DFIDSA. The programme’s due diligences conducted are also in the process of being reviewed and updated to ensure that they comply with the SmartRules requirements, with payments currently being withheld until those requirements are met.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Funds spent from November 2013 to October 2014 was £623,512, with an additional £135,613.97 accrued, making the overall total to date £1,525,678, of a total allocated budget of £5,000,000. In addition, budget forecasts for most of the partners seem to have fallen behind schedule with actual expenditure significantly less than forecasts. This slower than anticipated rate of spend reflects several factors. Firstly, there were several activities under the SADPA output which did not take place despite being forecast. Secondly, a number of implementing partners have not spent their allocations as quickly as planned, in part due to the weakening of the SA Rand against the British Pound over the year, and in some cases due to overoptimistic planning or unforeseen delays. It is recommended that the budgets of all partners be reviewed and updated for accuracy, with no cost extensions agreed and forecasts updated as required. Following the meeting with DIRCO’s SADPA Transition Team, a quick decision should be made on the level of funds to allocate to this output over the next year.

Performance of partnerships
Overall, the partnerships in this programme are performing well, with strong, collaborative relationships having been built up with a range of SA partners in government and civil society. Partners have generally provided timely quarterly or six monthly reports over the period, and several of these have captured lessons learnt. In addition, this programme had a steering committee which met once over the year to review progress, identify lessons and make recommendations. Since this was intended to meet quarterly, it is recommended that the steering committee meet twice over the next year which would be a more realistic tempo given time restrictions. In August, a workshop between AM, SALO and other civil society groups working on the post-2015 development goals was held. This was an effective forum to share and learn lessons and it is recommended that these meetings are increased to encourage cross-partner learning and knowledge sharing. To be a more effective partner, DFIDSA should clarify reporting and risk management requirements for implementing partners to avoid ad hoc requests throughout the year. These could include risk registers, as well as financial and progress reports where helpful.

Asset monitoring and control
The due diligence assessments conducted of implementing partners have included verification of the existence of asset registers and the processes for maintaining them. However, SAPEDC does not have an asset management strategy in place for the overall programme or a centralised register of assets procured with its funds. It is recommended that DFIDSA develop this strategy and communicate the requirements to partners.

G: CONDITIONALITY

Update on partnership principles (PPs)
Neither the original business case nor the last AR considered whether to use the PPs for management and monitoring. This was because though SAPEDC was focussed in part on partnerships with government for effective development co-operation, it was not envisaged that any of the AGAs would be with government bodies or use their systems. At the time of this review, this was the case for all the AGAs, apart from the Council for Geosciences which is a parastatal organisation.

In this case, given the overall strong commitment of both the South Africa government and its National Science Councils (including the Council for Geosciences) to the PPs, and since the grant agreement is for programme costs and not general or sector budget support, it is not deemed necessary to conduce a separate PP assessment beyond the due diligence already conducted. This assessed that the Council had strong governance and control mechanisms and was deemed low risk as a recipient of DFID funds. In the event that the Council were to display any behaviours inconsistent with the PPs the programme has the ability to withhold payments given that these are paid based on the receipt of adequate mid-term and final reports. Any further accountable grants of this nature should also assess the relevance of a PP assessment on a case by case basis.

H: MONITORING & EVALUATION

Evidence and evaluation
Evidence which has emerged over the past year supports the rationale of this programme. A Institute of Development Studies policy briefing from May 2014, for example, concluded that ‘it is clear that South Africa’s role as a development actor is growing, and more needs to be done to understand the contribution it can make towards tackling poverty and promoting sustainable development at the regional and global levels.’ This conclusion has been reinforced by SA’s leading role in Africa in response to the West Africa Ebola crisis in October 2014. It has also been emphasised by SA’s appointment as Chair of the G77 in 2015, giving it a key role in the post-2015 development framework negotiations, and Co-Chair (and then Chair) of the Open Government Partnership in 2014-16.

Evidence on the role of trilateral development co-operation (TDC) from a South African perspective was developed in a peer reviewed paper written by Lesley Masters, published in the South African Journal of International Affairs with funding from this programme. This identified a number of advantages of TDC from a SA perspective, including ‘the opportunity to combine resources in order to scale up projects, capacity building and the potential for deepening political and economic relations’. However, evidence in other important areas remains scant, particularly: the impact of SA’s development interventions themselves; how neighbouring countries perceive SA development interventions; and whether TDC approaches are more effective or achieve better VfM than conventional bilateral programmes.
The SAPEDC business case argued that ‘given the moderate overall financial value of this programme, and the challenges of assessing the impact of UK-funded activities on broader SA policy issues, we do not judge that an external evaluation of this programme would be appropriate’. This was supported by the last AR and remains an appropriate judgement given the relatively short time remaining on this programme. However, a full evaluation to address some of these evidence gaps should be considered in the development of future programmes under GDP. In addition, whilst some useful results have been captured through programme reporting, the M&E approaches of the implementing partners should be reviewed to ensure that they systematically measure and record relevant evidence.

Monitoring progress throughout the review period
This AR was led by the incoming Head of GDP in DFIDSA, with support from the GDP Programme Manager and DFIDSA Commercial Advisor. It was quality assured by DFIDSA’s Deputy Head. Its findings were tested with an external panel made up of GIZ, CIDA, Embassy of Belgium and FCO, which provided feedback which was incorporated into this review. Feedback on the programme was provided by implementing partners, DIRCO and SARS officials, and by the Malawian Customs Authority. During the review period, monitoring was undertaken through quarterly and bi-annual reports from the implementing partners, regular project review meetings with implementing partners, review of papers produced by the programme, attendance of programme events, and an SAPEDC steering committee.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process