Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: : Humanitarian Emergency Procurement Programme
Programme Value: £12 Million		Review Date: 31st October 2014
Programme Code: 203416	Start Date: / 09/05/2012	End Date: / 31/06/2017

Summary of Programme Performance
Year	2013
Programme Score	A
Risk Rating	Medium

Summary of progress and lessons learnt since last review

This is a light touch DFID desk review based on reporting against the existing project logframe. Given the reviews over the last year and the decision to substantially raise the level of funding for the programme and extend the project timeframe a full review at this stage was judged to be inappropriate.

This uplift will enable the UK Government to meet the needs of 75,000 people, an increase of 57,500 over the original stockpile capability, and increase the range of non-food items that can be delivered during an emergency response.

The uplift has rendered the existing logframe and milestones inappropriate and a new logframe is in the process of being produced subject to a number of ongoing strategic discussions on how to operationalise the uplift to greatest effect. Both the logframe review and strategic decisions will draw heavily on learning from the Typhoon Haiyan and Iraq responses, currently being drawn together.

The next full annual review will be brought forward and completed in April 2015 and will take in to account both operational progress and the strategic decisions made to deliver the uplift. It will also allow for evidence on performance to be included from PCRs received from recent emergency responses as well as expected results over the full reporting year.
Progress against the initially expected outcomes for this project has been good, meeting the majority of the expectations plotted in the logframe by this period. This is particularly impressive in light of the unprecedented number of humanitarian emergencies that the CHASE OT Team have responded to in this reporting year. The primary function of the stockpile, to quickly, effectively and appropriately deliver humanitarian relief supplies, has been fulfilled following the successful deployment of a significant tranche of materials to support the responses to Typhoon Haiyan, Iraq and Ebola.
Additionally, considerable work has been undertaken to review the quality of the items currently held in stock, and the acquisition of additional goods to compliment or enhance what is already available. The completion of the refresh of framework agreements with the addition of 3 new suppliers has also been important both in terms of providing access to materials that the UK Government would not normally hold, and in providing information regarding what the market has to offer in respect of supplying humanitarian goods.

Work on influencing and improving the effectiveness of the humanitarian system is at a fairly nascent stage with a number of small initiatives having been undertaken with partners in the areas of WASH and vehicle procurement.

Summary of recommendations for the next year
The project has maintained the UK Government’s ability to provide essential humanitarian relief through the provision of life-saving equipment and non-food items (NFIs). The extent of this support will continue to grow as the financial uplifts in the project are fully implemented through both the increase in the volume of supplies available, and the greater range of goods which will be accessible..

Following the uplift decision further development and procurement work will be required on the NFI range in association with relevant partners. Strategic decisions on the content of the uplift will be taken by the head of HRG on the basis of recommendations by the HEPP team and based on lessons learned from recent large responses including Typhoon Haiyan, Iraq and ebola.

Further detailed recommendations and a logframe for the following year will be set out in the next Annual Review in April 2015. Recommended actions over the next six months are:

- Conduct a minimum of two HEPP strategy brainstorming and evidence review sessions which will inform a HEPP uplift strategic plan.
- Update the programme logframe to reflect the uplifts
- Move forward work on influencing and improving the effectiveness of the humanitarian system

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/sector/18/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/sector/18/

What Support will the UK be providing?

The UK will provide up to £12 million over a five year period to ensure non-food items (NFI) can be delivered to those in need rapidly in sudden onset emergencies. This is an uplift of £8.75m over the original programme budget of £3.25m. This scale up will also trigger the additional 2yrs of the programme set out in the original business case. The uplift is a result of reviews of UK government humanitarian stockholdings in March and May 2014 requested by the Minister of State. It was agreed that there should be an uplift to enhance the range of emergency supplies held in UK stocks and increase official deployment capability. This uplift will take place over the next three years and has triggered the additional two years of the programme set out in the original business case.

Complementary specialist logistics and supply chain management support will be provided through the on-going Humanitarian Emergency Operations Support Services programme.

What are the expected results?

The results of this investment will ensure the UK Government can respond quickly, effectively and appropriately to a broad range of humanitarian crises (including urban crises), drawing on equipment and materials that enable them to meet the needs of affected communities, and ensure they can support the field deployment of DFID and key partners for up to three simultaneous events. This investment will also inform current and future engagement with the wider international humanitarian procurement system.

Following the uplift the UK stockpile will be able to address the needs of more than 75,000 people (by April 2017) and this target has been included in DFID’s operational plan. The original stockpile was sufficient to meet the needs of only 17,500 people.

What is the context in which UK support is provided?

As part of the toolkit needed to ensure an effective direct bilateral response to a sudden onset or emerging slow onset emergency, it is vital that DFID holds or is able to rapidly access lifesaving and essential shelter materials and other specialist NFIs that can be quickly and effectively deployed to meet the immediate humanitarian needs of affected communities. It is equally important that the UK Government is able to access, and use, high quality and effective equipment and materials to support the deployment of DFID field teams and partners’ specialist teams.

In order to meet these needs DFID has established UK Government humanitarian stockpiles, currently mainly located in Dubai and Kemble, of materials and equipment that can be drawn on in a response. DFID has also developed a network of suppliers, including an awareness of their production capacities and stockholdings, who can supplement these resources as needed; which has been particularly important in enabling the UK Government to meet more specialist or less predictable needs. The humanitarian stockpile works in parallel with a similar Stabilisation Unit (SU) support package and shares warehousing, labour and maintenance services. To meet future challenges DFID needs to maintain these resources while undertaking an on-going process that reviews needs and the performance of the materials they hold or procure and the locations of stockpiles, and ensures the UK takes advantage of innovation and new technology.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Outcome performance is measured against the following indicators:
The expected results of this investment will be that we can respond quickly, effectively and appropriately to humanitarian crises by drawing on equipment and materials that enable us to meet the basic shelter and emergency survival needs for affected communities across a wider range of humanitarian crises. Equipment was provided in support of DFID’s response to the Syria crisis, Iraq, South Sudan, Sierra Leone and Serbia. The capacity to deliver an effective humanitarian response to up to 3 crises has also been maintained, although the concurrence of some emergencies has highlighted the challenges in restocking and will inform the discussion around placing of stocks with regard to the uplift. The on-going review and testing of items to complement the existing stockpile of materials will provide a greater breadth in terms of the type of response that the UK Government is able to commit to. Already, this process has involved the installation of new satellite communications and digital radio equipment, and armoured vehicle modifications designed in-house.

Effective systems are in place that ensure all members of the international community can quickly identify and access the shelter materials and NFIs (and complex and “hard to access” specialist equipment and materials) held by individual organisations in the international humanitarian community. A website has been launched enabling DFID partners to see DFID goods, stock levels and specifications as well as share the testing and development of products. This shared and collaborative approach is intended to be rolled out to other partners outside of the RRF, although progress on this has been limited due to the number of responses this year.

Overall output score and description
A – Outputs have met expectations. Items from the stockpile have been used in numerous responses over the course of the year with positive reports on quality and suitability of the goods. Mobilisation of the stockpile has been swift and effective.

Key lessons
Detailed lessons for the coming year will be set out in the full Annual Review in April 2015.This will take in to account both operational progress and strategic decisions made to deliver the uplift. It will also allow for evidence on performance to be included from PCRs received from recent emergency responses as well as expected results over the full reporting year.

Key actions

Key Actions will be detailed in the full Annual Review in April 2015.

Has the logframe been updated since the last review?

No. Due to the 2 uplifts, the logframe will be updated for the next review which will be brought forward to April 2015 to align with other internal reporting requirements and allow time for decisions around the uplift to be made based on evidence from recent responses.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output 1
Output Title	UK Government humanitarian stocks can meet the needs of affected communities across a wider range of humanitarian crises.
Output number per LF		Output 1	Output Score	A
Risk:		Medium	Impact weighting (%):	50 %
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Output Indicator 1.1: UK stockpile (quality, content, volume) is kept under review to ensure it is able to meet humanitarian needs on an on-going basis and respond to emerging needs.

Key Points
Progress against this output has been delivered as expected, with the stockpile composition having been reviewed for both Non Food Items (NFIs) and support equipment. The reviews have been undertaken by means of an assessment led by CHASE Operations Team (CHASE OT) logistics experts coupled with the benchmarking of the scale and type of holding of partners and other donors.

The reviews concluded that there should be an uplift of the project budget from £3.25 million to £12 million to enhance the range of UK emergency supplies held in stocks and increase official deployment capability.

The framework agreements that were in place for tents, shelter kits and blankets all expired between January and April 2014. Following an EU restricted procedure competition, CHASE OT issued 3 new framework agreements to replace existing ones. The new framework agreements are for a period of 4 years with a break point after 2 years to evaluate performance and any changes in circumstances in relation to policy and objectives. Only one of the suppliers appointed on these frameworks was new to working with DFID, and CHASE OT carried out full due diligence checks as part of the procurement process. All suppliers have agreed to sign the SoS Statement of Priorities.

The procurement process to deliver an uplift for some of the basic NFIs is on-going, with the first additional commodities expected by the end of the 2014. Support equipment reviews have thus far focused on specific country responses such as Syria with the tailoring of support equipment to specific environments, including the provision of appropriate vehicles to the UN. A specific study into the appropriateness of NFIs to address violence against women and girls in emergencies has also been undertaken.

The process for inspection and procedures for NFIs has been updated to improve quality assurance of stock.

In direct support to meet humanitarian needs the current UK stockpiles has made a significant achievements in the reporting period:

- Philippines- During the Philippines response both NFI and deployment equipment was provided in a large scale. NFIs came from production (using frameworks let under the HEPP) as well as from stock. The logistics response was reviewed favourably by ICAI subsequently.
- Gaza – logistics advice and information as provided as part of this response.
- Iraq – The Iraq response utilised the newly formed UK NFI stores for the first time including those goods stored airside at East Midlands Airport. NFIs were also delivered from Dubai.
- Ebola – The Ebola response (currently ongoing) has drawn heavily on the deployment equipment holding and the HEPP sponsored airfield equipment holding.
- Serbia – communications equipment was provided from stock in conjunction with the procurement of vehicles.
- South Sudan – the establishment of the Juba office has drawn heavily on armoured vehicle expertise and stock.

Recommendations
Following the uplift decision further development and procurement work will be required on the NFI range in association with relevant partners. Strategic decisions on the content of the uplift will be taken by the head of HRG on the basis of recommendations by the HEPP team and based on lessons learned from recent large responses including Typhoon Haiyan, Iraq and ebola.

Output 2
Output Title	Agreements in place to provide rapid access to essential materials and equipment held outside the stockpile.
Output number per LF		Output 2	Output Score	A
Risk:		Medium	Impact weighting (%):	10 %
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Output Indicator 2.1: Effective links made to agreements under the Rapid Response Facility that enables rapid access to goods, equipment, and materials not held in UK stockpile.
Output Indicator 2.2: Links made with potential private sector suppliers and innovators of international humanitarian products.

Key Points
In 2014, CHASE OT issued 3 new framework agreements to enable rapid access to goods in an emergency. The new framework agreements are for a period of 4 years with a break point after 2 years to evaluate performance and any changes in circumstances in relation to policy and objectives. Only one of the suppliers appointed on these frameworks was new to working with DFID, and CHASE OT carried out full due diligence checks as part of the procurement process. All suppliers have agreed to sign the Secretary of State’s Statement of Priorities. The range of products identified in this first tender complement existing holdings to form a family support package for beneficiaries with the following items: buckets, hygiene kits, water treatment and filtration, toilet bags, solar kits, kitchen sets, sleeping mats and hand tools.

Recent framework agreements allow for goods to be accessed in a range of ways including:

- ensuring DFID has the ability to access goods for stock;
- agreements to require the production of goods in a response and;
- for DFID to be able to access supplier held stocks in an emergency (such as part finished goods like solar lighting).

To meet output indicator 2.2, CHASE OT has developed an Innovations Filter to assess the products and services presented to DFID on behalf of manufacturers for their potential use in humanitarian emergencies. Products are assessed against criteria including whether they are fit for purpose, meet relevant international specifications, and if their procurement would represent good value for money. Subject to the outcome of this assessment, a recommendation is made on whether the UK Government should purchase products for the stockpile, whether they should add the supplier to those who may be approached on an “as needed” basis or whether the product is not appropriate for use.

In some cases the potential supplier is introduced to other organisations. The first field trial of goods which have successfully passed this filter was completed by Oxfam this year with the Lifesaver water purification jerry can. This trial was a success and we have since begun using the product.

Recommendations

The further development of framework agreements should remain under review, in particular with those that will allow for devolved stock responsibility. The expansion of the stockpile may necessitate additional or expanded frameworks and this will be a consideration in the discussions around implementation of the uplift and the stockpile’s overall fitness for purpose.

Output 3
Output Title	UK stockpile(s) appropriately located
Output number per LF		Output 3	Output Score	A
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Output Indicator 3.1: That the UK is assured that the location of the items in the stockpile programme are optimally located to reduce suffering and morbidity, offer value for money and are resilient.
Output Indicator 3.2: DFID held relief items linked effectively with DFID air service provider (Air Partners) operations and those of other logistics/transport providers to ensure a seamless supply/deployment process.

Key PointsA review of geographical locations is being undertaken linked to the on-going development of the stockpile holdings in terms of both their scale and the potential devolved nature of holdings to suppliers. The review is also considering the extent to which the UK Government should or could have more regional deployment holdings. Negotiations are ongoing to gain access to the International Humanitarian City (IHC) holding in Dubai.
CHASE OT are reviewing whether it would feasible to establish mini-hubs of immediately deployable kit that would be available in at risk priority countries including Ghana, Kenya, Nepal, and Pakistan.
A review of the current policy of holding stocks in the United Arab Emirates is underway and discussions continue with potential partners to undertake further reviews of the appropriateness of current locations to DFID’s anticipated areas of operation in the coming years.

Recommendations
1. Continued work will need to be undertaken on reviewing locations and appropriateness, in light of the decision to expand the HEPP programme. A target date of December 2014 is still anticipated for the delivery of this work, as per the business case.
2. The recommendations of these reviews will be factored into the work plan for next year, and progress reported on in next year’s annual review.

Output 4

Output Title	Implementation of agreed recommendations to support, improve and replace existing international systems
Output number per LF		Output 4	Output Score	B – output not met expectation
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Output Indicator 4.1: Effective system in place that ensures all members of the international humanitarian community can quickly identify and access NFIs and deployment equipment held by individual organisations in the community.
Output Indicator 4.2: Support to improve international stockpile monitoring systems.

Key Points
Not yet begun. DFID has been focusing on our own unprecedented number of bilateral responses this year. This output will be reviewed as part of our latest uplift.
Recommendations:

1. A workplan needs to be put in place to identify how DFID will address this output in the coming year of the programme, identifying who will lead each component and timescales for delivery.
2. A study is required to understand the current international capability in this area, its shortcomings and how improvements can be made. This is likely to form the basis of an outsourced research agenda which will take place over the next 12 months.

Output 5

Output Title	Implementation of agreed recommendations on standards and dissemination and compliance.
Output number per LF		Output 5	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Progress against expected results:
Output Indicator 5.1: Effective system in place to establish and monitor minimum acceptable standards for shelter materials and NFIs provided in response to emergencies.

Key PointsMeetings have been held with water, sanitation and hygiene (WASH) partners to better co-ordinate the contents and application of hygiene kits as well as household water treatment solutions.

Advice has been provided to humanitarian advisors regarding the specification of goods listed in partner proposals to highlight value for money (VFM) issues as well as the understanding of appropriate quality and specification.

DFID has amended its own inspection regime to better determine reliability of quality in production. DFID does not have a baseline for commodity specifications funded (nor the on-going quality and assessment of provided goods) which has made engagement with partners difficult.

Recommendations
A greater outreach from DFID is required to understand variation across partners, and to better co-ordinate DFID’s expectations on meeting international specifications and the needs of quality provision.

Output 6

Output Title	Innovations and emerging technology in essential humanitarian equipment and materials are properly assessed and, where appropriate, brought into standard stockholdings. Results of assessments shared with wider humanitarian community
Output number per LF		Output 6	Output Score	A
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Output Indicator 6.1: Effective system in place to enable innovation in NFIs to be properly assessed and, where appropriate, brought into standard practice for both DFID and the international community.
Output Indicator 6.2: Review undertaken to establish a range of NFIs/complex equipment/difficult to obtain materials that would not be appropriate for the UK stockpile (short expiry date, rapid innovation in sector, high value, high maintenance costs etc etc) but where we would want assured provision.

Key Points
Development work has been undertaken on the emergency shelter holdings of DFID, which have been re-tendered in 2014. This has been undertaken in conjunction with the Building Research Establishment (BRE) with a particular focus on defining more accurately the thermal capability of existing tent designs. DFID has procured (for delivery early 2015) a new tentage design as a result of this work

Through tender and as a result of the review of the appropriate of NFIgoods in addressing violence against women and girls, a more tailored approach to the provision of hygiene kits has been developed with contracts for such due to be placed late 2014. This approach allows both target population and culturally specific elements to be added late in the process as well as being steered toward meeting the requirements of women and girls

Recommendations

Continued development and refinement of commodities with further outreach to the private sector for engagement in the humanitarian sector. The HEPP team will enagage with the new Humanitarian Policy and Systems Group in order to fully explore the potential of aligning the HEPP with the humanitarian innovation agenda.

Output 7

Output Title	DFID held stocks support the deployment of DFID staff (and / or those of partners specialist teams) into a range of environments for up to three simultaneous deployments
Output number per LF		Output 7	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Output Indicator 7.1: DFID has the equipment and resources in place to enable the immediate deployment of up to twenty people to a range of environments and which can be scaled up in line with changing UK response capability.

Output Indicator 7.2: Instigate on-going review and testing of innovations and emerging technology in deployment platform holdings to ensure they are properly assessed and, where appropriate, brought into standard stock holdings - and referred to other relevant actors in the international humanitarian community and UKTI as appropriate.

Key Points

The equipment and the UK Government facility at Cotswold Airport has been used for pre-deployment training of staff as well as for enhancing the international system through initiatives such as the Armoured Vehicle Procurement Workshop run for various UN agencies.

CHASE OT continue to lead the review of innovations and emerging technology. Communications technologies regularly change. The short range VHF equipment has been migrated from analogue to digital as a result of technology reviews which necessitated a thorough refresh of the vehicle and deployment equipment holdings. New solar technology has been added to the module and investigations and development of water treatment products has occurred.

Recommendations

Further development work in key areas (communications, vehicles) as well as the benchmarking of equipment against like-minded organisations during TRIPLEX exercises. TRIPLEX is a regular, International Humanitarian Partnership-run, full-scale simulation exercise, enabling a range of humanitarian actors to practice their response mechanisms in a sudden-onset natural disaster scenario.

The HEPP team should engage with those planning the next TRIPLEX to ensure maximum gain from the exercise.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and Performance

The key cost elements that affect the overall cost of the programme are:

1. the cost of warehousing and maintaining the DFID stockpiles and
2. (ii) the indicative cost of the additional materials that will be added to the existing stocks following the reviews of needs and new and innovative products and technologies.

Both elements have been and, where a refresh is needed, will be subject to open competition that follows public procurement rules and best practice. Costs will be passed on to DFID without any additional procurement/management fees beyond those already included in the Humanitarian Emergency Operations Support Services (HEOSS) contract.

The project is on-track against financial forecasts. A budget increase was approved following interim reviews of the UK Government humanitarian stockpile in March 2014 and May 2014.

The proposed increase in the budget reflects the need to enhance the range of emergency supplies held in UK stocks and increase official deployment capability. The uplift in stocks will:

- Enable the UK Government to meet the needs of 75,000 people, an increase of 57,500 over the original stockpile capability, and increase the range of non-food items that can be delivered during an emergency response;
- Improve the quality of UK Government response by enabling it to provide support which meets the wider needs of disaster affected populations;
- Extend the ability of field teams to rapidly deploy by increasing the range of mission critical equipment at their disposal and by improving the logistical capability to move field teams and equipment at short notice.

VfM performance compared to the original VfM proposition in the business case

Value for money for this programme is assessed against the following two criteria: (i) Output Performance (ii) Flexibility Performance.

Output performance: time from date of request to delivery at first point of distribution.

Flexibility performance: number of different types of items held in stock or subject to a manufacturer framework agreement (precise indicator to be developed following the reviews of the NFI and deployment stockpiles and the establishment of the agreements for rapid access to goods, equipment and materials that we will not hold directly).

Additional quantitative indicators have been developed to measure the quality of the Central Register and Global Mapping of Emergency Stockpiles System as part of the review process and in the design of any programme to follow up agreed recommendations.

Additional outcomes metrics are also employed, which indicates the benefits received by the recipient (capturing appropriateness, quality and timeliness): Recipient satisfaction, measured by a survey 6 months after the intervention, is also an integral component of any evaluation process for individual humanitarian responses.

Assessment of whether the programme continues to represent value for money

The benefit of maintaining a stockpile of relief items is still relevant with the overriding necessity that the UK Government has to have the continued ability to make a large direct, bilateral, in-kind contribution if necessary. Holding stocks enables the UK to respond swiftly to humanitarian need without relying on market availability.

The project will also improve the quality and appropriateness of response due to greater breadth and depth in the stockpile, and drive higher standards and practice in humanitarian procurement stockpiling and coordination in the international system. The costs of the procurement work needed to increase the stockpile and provide on-going management support is met from within current resources within the CHASE OT logistics team. This support is covered by the CHASE OT contract, won by Crown Agents through a competitive tender process.

Quality of financial management
The programme is delivered by Crown Agents as part of the Humanitarian Emergency Operations Support Services contract. Their financial management and procurement and logistics capabilities were independently assessed as part of the contract review with no concerns raised.
 CHASE and Crown Agents work closely on this programme and regular updates and reports have revealed no issues with regard to performance, results or value for money of stockpile items.

3 Is the project on-track against original timescale: Y

Date of last narrative financial report
Date of last audited annual statement

E: RISK (½ page)

Overall risk rating: Medium

The overall risk level of medium remains unchanged.

Overview of programme risk

The current intervention follows a series of previous projects (Stockpile projects 1 through 5) which maintained the high quality stocks of UK Government NFIs and support equipment deployed into a range of humanitarian emergency operations using the CHASE OT supply management and logistics team.

The scale of ambition to drive up the quality of procurement in the overall humanitarian system necessitates a larger risk appetite. Success is contingent on the UK’s ability to influence other partners who may, possibly, not be committed to delivering real change. Anecdotal evidence suggests that there is scope and appetite for a well-designed intervention, with the risk needing to be mitigated by thorough investigation as part of the review process. For each of the low value reviews detailed Terms of Reference will be agreed in advance between CHASE HRG and CHASE OT. The recommendations of each review will be agreed by CHASE HRG before further resources are committed.

The overall risk for this is very low. Crown Agents are one of DFID’s three approved procurement agents and have in place stringent anti-corruption and anti-bribery policies and practices. The provision of the services being supplied under the Humanitarian Emergency Operations Support Services contract, which will provide the bulk of the resources needed to implement the Humanitarian Emergency Procurement Project were subject to competition. As part of the management arrangement for that contract a Partnership Board has been established to oversee the on-going management of the CHASE OT contract including the work of the supply chain management/logistics team. This Partnership Board meet on a quarterly basis to discuss progress, performance and any other issues arising. The Board comprises the Stabilisation Unit (SU) and CHASE Senior Responsible Owners (SROs) for the contract, the Crown Agents Commercial Director and Crown Agent’s Project Director.

Additionally, the Crown Agents Project Director convenes a leadership meeting with the CHASE SRO and SU SRO separately, on a monthly basis. The Crown Agents Commercial Director is available to attend these meetings on a regular basis as required. Weekly meeting of the Humanitarian Response Group and CHASE-OT leadership groups discuss and resolve any day to day issues.

F: COMMERCIAL CONSIDERATIONS (½ page)

Commercial Improvement and Value for Money

Commercial improvement for this intervention is driven through the establishment – of relationships with suppliers (following open competition as per public procurement rules and best practice). This is mediated by CHASE OT and through open procurement for materials and supplies that are held in the stockpile. Suppliers identified through the Rapid Response Facility process are also invited to participate in these procurement processes to formalise any agreements that need to extend beyond the EU Procurement Directive thresholds.

Performance of partnership (s)

Crown Agents are the sole implementing partner. They have arrangements with suppliers to ensure adequate supplies of non-food NFIs are maintained in storage, and maintain relations with suppliers to ensure delivery of NFIs in humanitarian responses.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The overall rationale established in the business case for the continued maintenance of a UK Government humanitarian stockpile remains valid. This is namely that this intervention will ensure that existing UK stocks, and our access to stocks held by others, will be maintained and refreshed and increased to meet the basic shelter and emergency survival needs (excluding food) for affected communities across a wider range of humanitarian crises. This will also ensure that innovations and emerging technology in essential humanitarian equipment and materials are properly assessed and, where appropriate, brought into standard stock holdings. It will also ensure the UK Government is able to effectively support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of emergency environments, including insecure/conflict affected environments, for up to three simultaneous deployments.

Given the strong evidence base for the existence of a UK stockpile the focus of evaluation will be on the success of the utilisation of the UK stocks. There will be an internal review of the programme, including the uplift, toward the end of 2016. Specific indicators for progress will be developed and agreed as part of the process refreshing the logframe.

The use and impact of stocks drawn down from the stockpile are reviewed as part of the Project Completion Review process for individual humanitarian responses. Ongoing monitoring will be undertaken through the existing CHASE-HRG and CHASE-OT partnership as defined in the contract for the Humanitarian Emergency Operations Support Services contract and in the monthly meetings of the combined management teams.

Direct feedback from beneficiaries
On-going monitoring of this project has been undertaken in line with the requirements as defined in the contract for the Humanitarian Emergency Operations Support Services and in the monthly meetings of the combined management teams. DFID has been satisfied with CHASE OT’s overall performance, particularly ability to initiate and manage change. Project completion reviews (PCRs) for the Philippines, Iraq, Gaza and Ebola will provide feedback for the April 2015 review. Initial anecdotal evidence from these responses is that beneficiaries were content with the quality of the goods provided.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process