Intervention Summary

## Title: Support to Girls’ Education in South Sudan

What support will the UK provide?

Why is UK support required?

What are the expected results?

Business Case for: Support to Girls’ Education in South Sudan

Strategic Case
Context and need for DFID intervention / Women and girls in South Sudan are more likely to die at childbirth than to complete primary education. Only one in four girls enrols in primary school and a mere one in ten completes primary education. Out of 377,085 girls of the secondary level age group only 2.6% (9,898) are in schools. These numbers are among the lowest in the world. / These average national figures conceal the wide disparity among the states in South Sudan. Primary level gross enrolment for girls is 93% in Western Bahr El Ghazal, but 34% in Northern Bahr El Ghazal. Unity, Lakes, Northern Bahr El Ghazal and Warrap States have 0% girls’ enrolment in secondary education while it is 12% in Central Equatoria and 16% in Western Bahr Al Ghazal States[1]. / A combination of supply and demand side constraints underlies this unusual gender disparity in education in South Sudan. Lack of schools, especially secondary schools; low numbers of female teachers; and inadequate water and sanitation facilities in schools are some of the supply side factors. Poverty, insecurity, early marriage and pregnancy have been identified across the States as key causes of drop out from schools[2]. Each percentage point increase in poverty reduces a girl’s chance of being enrolled at a primary school by 0.3 percentage point[3]. / Concerns over personal security impact negatively on girls’ enrolment and participation in education in the conflict zones. Additionally, gender roles have been geared to and adapted to conflict. Decades long civil war, resource conflict, cattle protection and raiding have created a male stereotype as a warrior in some communities. Women are viewed as a household resource, commonly valued by the number of cows they would bring as dowry; and as a tool for domestic chores. These social views result in further barriers for girls’ education. / Evidence Base / Benefits of Girls’ Education / Apart from rights based imperatives, arguments in favour of increasing girls’ access to and retention in education in fragile states can be made on the basis of evidence that: (a) it is fundamental to achieving other developmental objectives such as the poverty and health MDGs; (b) it is an effective and sustainable intervention for breaking the inter-generational poverty cycle; and (c) it is a way of achieving gender equity and so contributing to a just society. / Investments in girls, especially in adolescent girls, can provide long term benefits through intergenerational human capital improvements, as educated women with greater empowerment and awareness of reproductive health, family planning and broader choices, tend to have fewer children. In turn, smaller family size increases income and consumption per head of population, and reduces the dependent members of the population. Women with economic and decision-making power invest in their children and ensure that they receive high quality education and healthcare[4]. / The table below summarises the key evidence that girls’ education contributing towards other development objectives. / IMPACT SELECTED FINDINGS / 1 CHILD HEALTH AND SURVIVAL An additional year of female schooling reduces the probability of child mortality by 5 to 10%[5]. / 4 million lives of children under 5 years old were saved due to female education[6]. / 2 LOWERING OF FERTILITY RATES The fertility rate of a woman drops by almost one birth when she gains four additional years of education[7]. / 3 MATERNAL HEALTH AND MORTALITY An additional year of schooling for 1,000 women helps prevent two maternal deaths[8]. / 4 INCREASED FEMALE EARNINGS Girls with an extra year of schooling earn 10% to 20% more than their peers without that level of schooling[9]. / 5 PROMOTION OF ECONOMIC GROWTH Increasing the share of women with secondary education by 1 per cent boosts annual per capita income growth by 0.3 per cent on average[10]. / 6 POSTPONEMENT OF EARLY MARRIAGE Data from 40 countries shows that if a woman has attended secondary school she is considerably less likely to marry during her adolescent years[11]. / 7 INTERGENERATIONAL BENEFITS Each additional year of formal education completed by a mother translates into her children remaining in school for an additional one-third to one-half year[12] . / 8 ‘SOCIAL VACCINE’ AGAINST HIV AND AIDS Ugandan females with secondary education are three times less likely to be HIV positive than those with no education[13]. / 9 REDUCTION IN DOMESTIC VIOLENCE AND HARMFUL CULTURAL PRACTICES In Egypt, women with secondary education are four times more likely to oppose the practice of female genital cutting[14]. / 10 REDUCTION IN CARBON EMISSIONS Female education, leading to smaller family size is cheaper and provides larger impacts on carbon emissions abatement than direct low-carbon energy options[15]. / What works for promoting Girls’ Education / Cash transfers, both conditional and unconditional, have proved to be a powerful tool in increasing girls’ school attendance[16]. Increased income security enables households to pay fees or other costs associated with attending school. It also reduces the demand on children, particularly girls, to contribute to family income, enabling them to participate in school. At the same time, improved nutrition as a result of better income security helps children to learn better. Examples include: / In Pakistan, the Punjab Education Sector Reform Program increased enrolment rates for girls aged between 10-14 years by 11 percentage points from a baseline of 29%[17]. / In Bangladesh, the Female Secondary School Assistance Program increased attendance of 11-18 years old girls by 12 percentage points from a baseline of 44%[18]. / Malawi’s social cash transfer programme shows that targeting households with children led to an increase in school enrolment of five percentage points among children aged 6–17, while targeting households with orphans yielded an increase of 4.2 points[19]. / In Cambodia, the Japan Fund for Education Programme increased the attendance of girls in grades 7-9 by around 30 percentage points, from a baseline of 65 per cent[20]. / In Brazil, participants in the Bolsa Familia programme are 20% less likely than comparable children in non-participant households to have a one-day absence from school in any given month. They are 63% less likely to drop out of school, and 24% more likely to advance an additional year[21]. / One impact evaluation in Malawi has directly addressed the question of the value addition of conditionality in transfer. The evaluation compared a control group with i) a group that received the transfer with conditions and ii) a group that received the transfer without conditions and found that conditioned and unconditioned transfers resulted in the same gains (i.e. lower dropouts, higher enrolment), with no additional incremental gain due to conditionality[22]. Given the limited evidence with which to judge whether conditions add value, decisions on whether or not to use them need to reflect the influence of other contextual factors such as politics, costs, and the feasibility and desirability of setting conditions in low income countries with lower institutional capacity. / There is a growing body of evidence which suggests that safe environments are a significant factor in girls’ access and retention in schools and in particular parental choices in letting their daughters attend. According to one global report 60 million girls are sexually assaulted at or on their way to school every year[23]. Whilst the prevalence, frequency and intensity of violence in schools are not yet fully and systematically documented[24], evidence suggests that sexual harassment and other forms of violence may lead to increased rates of school drop out[25]. / Provision of adequate hygiene facilities and menstrual management techniques lead to improved educational outcomes, attendance and reduced attrition for girls[26], although more research is needed and there is mixed evidence. A study in Uganda found that 1 in 3 girls missed all or part of a school day during their menstrual cycle. A recent study undertaken in India found that "Inadequate menstrual protection makes adolescent girls (age group 12-18 years) miss 5 days of school in a month (50 days a year). Around 23% of these girls actually drop out of school after they start menstruating". / There is some evidence that non-formal education programmes providing accelerated literacy, numeracy and life skills education can bring positive results for adolescent girls. Examples of good practices are BRAC for Adolescents Clubs and the Developments in Literacy Programme in Pakistan[27]. These programmes are implemented through partnership arrangement with local NGOs. / The provision of female teachers, particularly in conservative communities, is a proven mechanism to increase the numbers of girls in schools. Recent education data[28] shows a correlation between the enrolment for females in secondary education and the proportion of women teachers in primary education. / This evidence base suggests that a combination of interventions (such as asset transfer, girl friendly safe school environment, and female teachers) would have a positive impact on education outcomes and bring broader social benefits. / Innovation and Knowledge Generation / The key innovative element of the programme to be considered in appraisal is a communication campaign in order to bring changes in social and individual behaviour towards girls’ education. The forms, reach and contents of the campaign would be determined during the design phase. The other innovative aspects to be appraised are school–Community Based Organisations (CBOs) partnerships for creating girl friendly and safe environments in schools and communities. / The programme will develop a Randomised Control and Trial (RCT) based evaluation framework to identify the most effective intervention. The evaluation framework will also generate knowledge and further evidence about return on investment for girls’ education in a post-conflict context. / Policy Context: DFID and Government of South Sudan / ‘Gender House’, DFID’s strategic vision for girls and women, is based on the premise that benefits of investing in girls and women are transformational. The vision commits DFID to work to getting more girls through the secondary schools, stating that DFID will increase the numbers of girls in primary and secondary schools in all 23 country programmes where we give support to education, and will assist girls to stay in school beyond primary level to ensure the full benefit from education, transforming their lives and opportunities. This programme will contribute to the target of the Strategic Vision. / DFID’s Structural Reform Plan (SRP) also puts investment in girls and women as a central theme. This programme will contribute towards the plan. / Through the Bilateral Aid Review and Operational Planning process DFID South Sudan has been tasked with delivering a substantial increase in enrolment and completion for both boys and girls in primary and secondary education. This Stage 1 Business Case is central to the achievement of DFID Sudan’s education results, which include supporting up to 200,000 girls in primary and secondary schools. / The programme will be complemented by existing non-formal education, school construction and textbooks printing programmes; and other planned programmes including an English language training programme; and support to expand the pool of capable teachers, including women teachers. / The programme is fully aligned to the Government of South Sudan’s (GoSS) declared priority of promoting girls’ education. The Multi-Donor Trust Fund (South) supports the Girls’ Education Initiative (GEI) implemented by the Ministry of Gender and Social Welfare with an objective to raise awareness about girls’ education. USAID implements a stipend programme called Gender Equity through Education (GEE) in order to assist girls in secondary schools to continue higher education. There have been initiatives by NGOs including the Save the Children and by the Episcopal Church of Sudan for promoting girls’ education. DFID will assess these programmes and initiatives in order to understand what lessons they provide and will build on those lessons. / The draft South Sudan Development Plan (SSDP) includes as a priority, a target of providing nation-wide and predictable cash transfers covering at least 20% of households in the first three years. The aim is to provide critical support to rural and urban families and to improve the health and nutritional status and educational opportunities of children. The education results of the SSDP include higher enrolment, reduced dropout and higher completion of girls at both primary and secondary levels. This proposed DFID-funded programme will contribute towards those objectives.
B. Impact and Outcome / The goal of the proposed programme is to transform a generation in South Sudan through education. The purpose of the programme is to expand girls’ access, retention and completion of primary and secondary education. Up to 200,000 girls in primary and secondary schools will supported by DFID to continue and complete their education. / The expected outputs of the programme are subject to appraisal of options, but are likely to include: / Household costs of girls’ education reduced through stipends; / Enhanced household and community awareness and empowerment for supporting girls’ education; / Girl friendly schools, lowered gender violence, teachers’ code of conduct, mentoring for adolescent girls; / Central and state level policies and resource allocations for girls’ education supported and improved; / Increased knowledge and evidence of what works for promoting girls’ education in fragile context. / The impact of the programme will be a generation of educated women and girls in South Sudan participating in economic, political and social activities and in turn boosting economic production, political stability and social cohesion.
[1] Same as above.
[2] Unicef, 2008. A Study on Socio-economic and Cultural Barriers to Schooling in South Sudan.
[3] Michael Morris, 2010. Analysis of Provincial Education Statistics of South Sudan. Unpublished. DFID Sudan 2010.
[4] Lindi Hlanze, 2010. Economic Returns to Investment in Girls: Making the case for DFID Ethiopia. The Girl Hub, DFID Ethiopia, DFID Chief Economist’s Office.
[5] Shultz, P. (1993) “Mortality Decline in the Low-Income World: Causes and Consequences” American Economic Review 83(2) 337-342.
[6] Gakidou E, Cowling K, Lozano R, Murray CJL. Increased educational attainment and its impact on child mortality in 175 countries between 1970 and 2009: a systematic analysis. Lancet 2010; 376: 959–74.
[7] Klasen, S. (1999) “Does Gender Inequality Reduce Growth and Development? Evidence from Cross-Country Regressions” Policy Research Report on Gender and Development Working Paper No. & Washington D.C. World Bank.
[8] UNICEF(2003) The State of the World’s Children 2004
[9] Psacharopoulos, G. and Patrinos, H.A. (2002) Returns to investment in education: a further update Workd Bank Policy Research working Paper Series 2882
[10] Dollar, David and Gatti, R. (1999) “Gender Inequality, Income and Growth: Are Good Times Good for Women” World Bank Policy Research Report on Gender and Development, Working Paper Series No.1, World Bank, Washington D.C.
[11] Kirin op cit
[12] Filmer, Deon (1999) “The Structure of Social Disparities in Education: Gender and Wealth” Policy Research Working Paper 2268, World Bank, Washington, DC
[13] DeWalque, Damien (2004) “How Does Educational Attainment Affect the Risk of Being Infected by HIV/AIDS” Evidence from a General Population Cohort in Rural Uganda”
[14] El-Gabaly (2006) “Female Genital Mutilation in Eygpt” Presentation at Global Forum for Helth Rsearch, Cairo.
[15] Wheeler, D. and Hammer, D. (2010) The Economics of Population Policy for Carbon Emissions Reduction in Developing Countries Working Paper 229 Center for Global Development November 2010
[16] Sarah Baird, Et al. 2010. Cash or Condition? Evidence from a Randomized Cash Transfer Program. The World Bank, Washington D. C.
[17] Chaudhury & Parajuli, 2008, cited in World Bank, 2009
[18] Khandker, Pitt, & Fuwa 2003, cited in World Bank, 2009
[19] Handa and Stewart, 2008.
[20] Filmer and Schady, 2008, cited in World Bank, 2009
[21] Veras, F., Ribas, R. and Osorio, R., 2007. ‘Evaluating the Impact of Brazil’s Bolsa Familia: Cash Transfer Programmes in Comparative Perspective’, International Poverty Centre (IPC), Brasilia
[22] Barid, S et al (2010) Cash or condition? Evidence from a randomized cash transfer program. World Bank Policy Research Paper No. 5259; March 2010. http://go.worldbank.org/LESSFGZKD0
[23] Action Aid 2010 Destined to Fail
[24] PLAN International, Save the Children Sweden, UNICEF, ActionAid, 2010, Too often in silence – a report on school based violence in Western and Central Africa
[25] Morrison, 2007
[26] Pearson, J. and K. McPhedran, A literature review of the non-health impacts of sanitation. Waterlines, 2008. 27(1): p. 48-61.
[27] EFA GMR 2011,UNESCO, 2011.
[28] UNESCO Institute of Statistics 2008

Appraisal Case

A. Determining Critical Success Criteria (CSC) / Each CSC is weighted 1 to 5, where 1 is least important and 5 is most important based on the relative importance of each criterion to the success of the intervention. / CSC Description Weighting (1-5) / Reduces economic barriers to girls’ education, including direct and indirect household costs. 5 / Reduces social barriers to girls’ education, such as parental perceptions about schooling of adolescent girls and community perception of benefit of girls’ education. 5 / Delivers at scale across the country and supports 200,000 girls in upper primary and secondary levels within programme timeframe. 5 / Reduces supply side barriers, like lack of girls’ hostels, inadequate water and sanitation facilities at schools, and gender based violence in schools. 4 / Works in collaboration with the GoSS and the State Governments to support and strengthen their policy and strategies on girls’ education. 4 / Promotes transparency and accountability in determining targeting strategies for programme activities. 3 / Generates knowledge and evidence on what works in promoting girls’ education in South Sudan. 3
B. Feasible options / In the table below: / the quality of evidence for each option as is rated either Strong, Medium or Limited, / the likely impact on climate change and environment is categorised as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Evidence rating Climate change and environment category / (A, B, C, D) / 1. Do assets transfer, behaviour change communications campaign and develop civil society partnerships for promoting local action and volunteerism for supporting girls’ education. Strong C-low risk/opportunity / 2. Build more schools, hostel facilities for girls and hire more women teachers to lower supply side barriers. Medium B-medium risk/ / opportunity / 3. Increase GoSS capacity to formulate and implement policies and programmes focussing girls’ education. This would cover all 10 States. Low C-low risk/opportunity / 4. Develop a combination of inputs of all the above options to lower both demand and supply side barriers, like construction of girls’ schools and hostel facilities, increased numbers of women teachers, along with a cash transfer/behaviour change communications campaign and policy support to government. Medium C-low risk/opportunity / Option 1 / Description: A combination of assets transfer, behaviour change communication campaigns and civil society partnerships promoting local action and volunteerism to lower economic, social and cultural barriers of girls’ education. This would cover all 10 States. / Costs: An indicative cost of the full package of interventions is £50 million. / Benefits: Additional 200,000 girls completing primary and secondary education. At the rate of £312 private benefit of completing primary education, the benefits will outrun costs in four years time after the completion of the programme. / Risks: The asset transfer is not well targeted and does not reach the priority population; upsurges of conflict makes it impossible for girls to attend schools; the GoSS policy on working with the civil society changes and makes it harder to develop effective partnerships with CSOs. Supply side barriers would be addressed to some extent, though not through construction of new girls schools or hostels, nor through large scale provision of women teachers. However, other programmes funded by DFID, USAID and other donors are or will start to address these through school construction and teacher development. / Option 2 / Description: Build more schools, hostel facilities for girls and hire more women teachers to lower supply side barriers. This would be in up to 5 States. / Costs: Construction of 60 new secondary schools with boarding facilities would cost around £50 million. / Benefits: Additional 12,000 girls enrolled every year. / Risks: Social and economic barriers still prevent girls from enrolling in secondary schools; insecurity arising from conflict adds to the barriers to schooling. / Option 3 / Description: Increase GoSS capacity to formulate and implement policies and programmes focussing girls’ education. This would cover all 10 States. / Costs: There is little evidence and cost data for policy formulation and programme implementation through the GoSS. Costing for this intervention could be done during the appraisal phase. / Benefits: GoSS capacity increased. The exact number of girls benefitting due to the enhanced capacity can not determined as this stage due to lack of evidence. / Risks: There is high fiduciary risk of channelling resources though GoSS, although this option could be implemented without channelling funds in this way, or with special controls to reduce fiduciary risk. Programme and policy implementation could be delayed due to limited capacity in government. / Option 4 / Description: Develop a combination of inputs of all the above options to lower both demand and supply side barriers, like construction of girls’ schools and hostel facilities, increased numbers of women teachers, along with a cash transfer/behaviour change communications campaign and policy support to government. / Costs: Costs for this option would only be affordable with DFID Sudan financial allocations if elements of the programme had a much narrower geographical focus. The number of girls supported in school would be much lower than what might be achieved under Option 1. However, this option will be appraised further during the Stage 2 Business Case. / Benefits: The details of benefits will depend on the combination of inputs and will be determined during Stage 2. / Risks: This is a high risk option as it may not achieve a transformational impact on the number of girls in school. / Theory of Change / A draft theory of change is attached as Annex 1.
C. Appraisal of options
D. Comparison of options / The same weighting is used as for CSC above. The score ranges from 1-5, where 1 is low contribution and 5 is high contribution, based on the relative contribution to the success of the intervention. / Analysis of options against Critical Success Criteria (CSC) / Option 1 Option 2 Add more columns as necessary / CSC Weight (1-5) Score / (1-5) Weighted Score Score Weighted Score / 1 / 2 / 3 / Totals
E. Measures to be used or developed to assess value for money

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / Stage 2 and 3 Business Case / DFID will call for a design and implementation proposal during the Stage 2 Business Case for this programme. The successful candidate will develop and appraise the options in collaboration with DFID South Sudan. DFID Sudan will produce Stage 2 and Stage 3 Business cases with inputs from their work. The total value of the Stage 2 work is £300,000. / Implementation of the programme / Subject to the approval of the final Business Case, the successful partner will start implementing the programme. The procurement responsibilities for the programme implementation will lie with this implementing agency. / No resources are expected to be channelled though the GoSS systems due to high fiduciary risks.
B. How does the intervention design use competition to drive commercial advantage for DFID?
C. How do we expect the market place will respond to this opportunity?
D. What are the key underlying cost drivers? How is value added and how will we measure and improve this?
E. What is the intended Procurement Process to support contract award?
F. How will contract & supplier performance be managed through the life of the intervention?

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner?
B. Value for money through procurement

Financial Case

A. How much it will cost / The total estimated cost of the programme £52.3 million including £300,000 design cost. / The total cost for the outputs will be £50 million. Under Option 1, a substantial amount of the programme cost will be asset transfer to the girls and their families in order to reduce the indirect costs of schooling for girls. / The £300,000 design cost will be for hiring consultants to design a programme, appraise the programme options through evidence gathering, analysis and consultation in the field. / The rest of the £2 million will be retained by DFID South Sudan for annual progress reviews, technical assistance and third party evaluations.
B. How it will be funded: capital/programme/admin
C. How funds will be paid out
D. How expenditure will be monitored, reported, and accounted for

Management Case

A. Oversight
B. Management
C. Conditionality
D. Monitoring and Evaluation
E. Risk Assessment
F. Results and Benefits Management