Type of Review: 2nd Annual Review

Project Title: South Sudan Education Programme (SSEP)

Date started: 22 February, 2011
Date review undertaken: 8-12 April 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the LogFrame / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?

The UK is providing £37 million through the Southern Sudan Education Programme (SSEP) for increased access to education in South Sudan. This programme started in February 2011 and runs through to January 2015. / The goal of the support to the education sector is to transform a generation in South Sudan through education. The purpose of the programme is to increase access to primary and secondary education with a special focus on girls and by creating more opportunities for alternative education for out-of-school youth and adult learners. The SSEP will contribute directly to achieving education Millennium Development Goals (MDGs) in South Sudan as well as indirectly to MDGs on Poverty and Health.

What are the expected results?

The specific outputs of the programme will be construction of over 300 primary and secondary classrooms, 51 alternative education centres, 444 toilets and 148 school offices and storerooms. The new infrastructure will accommodate 38,000 students per year for the next 20 years. In addition, it will provide education to over 26,000 out of school children, train 2,400 teachers and 1,055 head teachers, and hold 360 advocacy events to promote education in the programme areas.

What is the context in which UK support is provided?
Since the Peace Agreement of 2005 and Independence in July 2011, South Sudan has faced the multiple challenges of forging all elements of a new nation within a post-conflict situation, with fragile governance structures and limited human and financial resources. / It placed primacy on the development of an education system that can respond to these challenges over the next decades. However, its education, health and social indicators are ‘low’ by international standards but not atypical of those fragile and post-conflict States in which DFID works. This can be no less than anticipated after decades of civil war. / School enrolments have increased dramatically – in the wake of the GoSS “Go to School Initiative” which was launched in 2006. Gross and net enrolments rates are ‘low’ (62.3% and 41.3% respectively) but improving. Secondary education is expanding slowly, and there is gradual momentum behind the imperatives to emphasise education for girls. / In spite of increased enrolments, there remain the challenges of the internal inefficiencies of the system. There is a high drop-out incidence (between 17% and 32%) for both boys and for girls in Grades 1-5 especially and a high repetition rate (approximately 8.5%); in both cases the percentages are higher for girls than boys. Primary schools also contain a high percentage of over age children (87% on average). Gender disparities exist and are perpetuated by cultural and socio-economic factors. Furthermore, an estimated 2 million children remain out of school (including a high percentage of the 6-13 age range). The internal challenges are compounded by insufficient teacher supply and for the need for both pre-service and in-service training to upgrade, up-skill and professionalise the teaching force and fit it for the proposed challenge of ‘participatory teaching’ in the face of major logistics and socio-cultural constraints. / The Ministry of General Education and Instruction (MoGEI) has completed significant policy/planning frameworks. The General Education Strategy (GES) 2012–2017 and the General Action Plan detail the implementation of the General Education Strategy and its five strategic goals: / To improve the quality of General Education / To increase access to General Education and promote equity / To promote adult literacy / To build institutional and human capacity / To increase funding for general education. / SSEP particularly supports the improvement of Alternative Education Systems (AES) in its target locations. AES is placed within GES core goals (‘to promote adult literacy’). AES is intended to assist in the social and economic re-integration of the generations who did not have access to formal education during the war, or who have dropped out of school as a result of the conflict. It is thus a critical dimension of educational provision in the country as a partial response to the human resource development elements of re-integration and educational opportunity as pathways to economic and social development and hoped-for job creation. However, AES faces enormous challenges of logistical and resource constraints in the face of huge demand for access to its various pathways. / Whilst the formal system response has been encouraging (e.g. primary school enrolments have increased from 700,000 in 2005 to 1.4 million in 2012), a MoGEI base-line survey in June 2012[1] estimated that approximately 282,500 learners enrolled in AES in 2012. However, whilst the lofty ‘goal’ is employment generation, AES provides limited coverage of basic literacy and numeracy skills in parallel with the formal primary education system.
[1] A Comprehensive Base Line Survey and Study and Evaluation of the design and implementation of AES, commissioned by the AES Directorate of the Ministry of General Education and Instruction (June 2012).

## Section A: Detailed Output Scoring
(This Annual review assesses the extent to which Milestone 2 of the LogFrame has been reached.)

Output 1: Access to new primary and secondary school infrastructure
Output 1 score and performance description: A++ / Indicator 1.1: Number of schools constructed / Milestone 2 was 17 schools completed/built by December 2013. The actual number constructed by March 2013 is 28 primary schools and 3 secondary schools. / Overcoming the politics surrounding school site locations (identified in the 2012 Annual review) enabled construction work to gather pace. UNOPS continued the momentum identified by the 2012 Annual Review and made substantial progress towards the completion of its overall proposed work programme for SSEP. / Issues surrounding school design (also flagged in the 2102 review) were also overcome: original proposals for low-cost ‘Pavilion schools’ compromised in favour of higher cost but more solid Infrastructure. / In each of Eastern Equatoria (8 primary, one secondary), Warrap (8 primary, 1 secondary), Northern Baharel Ghazal (7 primary, 1 secondary), all community schools were completed and handed over to the State Ministries of Education at various stages between July and November 2012, together with the agreed supply, delivery and installation of School Furniture (which includes both classroom and office furniture). / In Upper Nile State, the construction of all 8 schools (7 primary, 1 secondary) was affected by the perennial problems of insecurity, rains and limited access to sites. Nevertheless, 5 primary schools have been completed (with some handed over to the State Ministry of Education in February 2013). The 2 remaining primary schools are located on the western bank of the Nile, with access only by boat – and fluctuating water levels and flooding impede the transportation of materials. Additionally, some necessary building materials are not available locally and have to be obtained across the Ethiopian, Ugandan (and even Sudanese) borders. Equally (and perhaps obviously), local contractors have not always proved timely and efficient, subject as they are to the surrounding constraints and threats – and their own limited capacities and the availability of a skilled and unskilled (and motivated) workforce. Despite these numerous challenges, the project managed to achieve some cost savings which will be able to construct at least one more school. / Problems of supply and of border controls compound the eternal security threat. Nevertheless, UNOPS anticipates early completion of the roof levels of the 2 remaining primary and the construction work on the 1 secondary school ‘not earlier than April 2013’. Similarly, it anticipates the completion of delivery and installation of school furniture in 4 of the sites in this State. UNOPS has endeavoured to ensure delivery of necessary materials during the dry season (though this is not always feasible). Site supervision and monitoring have also been impeded both by the rains and by the prevalent security threat – it can visit the West bank of the Nile only with force protection. / Indicator 1.2: Number of boys and girls supported by DFID in primary and secondary schools / Milestone 2 was the enrolment of 16,800 primary school pupils and 1,120 secondary school pupils, supported by DFID. The actual achieved (by end-December 2012) was 18,906 primary school pupils, comprising 11,904 (63%) boys and 6,671 (37%) girls, and 440 secondary school pupils, comprising 320 (73%) boys and 120 (27%) girls. / Substantial demand for access to educational opportunity pre-existed SSEP as a result of the GoSS “Go to School” initiative, for example, as well as community and partner responses and support. / There is little doubt that the SSEP new and rehabilitated schools (and the community engagement strategies (see Indicator 3.2 below) have acted as magnets to attract new pupil enrolments and that the primary school enrolment surges are (probably) a direct result of SSEP support – albeit there should be caution in direct attribution without more rigorous empirical evidence. / Over enrolments occur from Grade 1 and upwards before drop-outs commence. There are poverty-related factors in all cases and cultural and domestic factors in relation to girls. Doubtless, though, the incidence of dropping-out can be directly related to issues of school quality – and the failure to have enhanced the overall quality of school and (especially) class-based provision. Lack of adequate child-friendly learner environments, inadequate learning support materials compounded by weak pedagogical skills among the teaching force, that is ill-equipped to undertake pupil-centred learning in large class sizes of up to 100 and more per room without furniture, further complicate the situation. Poor quality learning environments undermine endeavours to increase retention, with few children reaching Grade 8. Paradoxically, ‘child-friendly schools’ are yet to evolve in spite of demand for new schools and new classes. The large numbers of children and the shortage of qualified teachers make ‘child-friendly schools’ a distant reality. / Secondary enrolments have lagged behind expectation and cannot be entirely explained away as a result of lack of teachers or lack of enrolment in 2 of the completed secondary school buildings which are yet to open, though these may be causal factors. Enrolments at this level will increase only slowly – in part because of the limited numbers of children successfully completing Grade 8. The two reasons mentioned above are major institutional constraints outside the remit of the project. For example lack of teachers in two of the secondary schools was due to inability of Ministry of Education to recruit teachers as a result of austerity budgets / What needs assessment was actually carried out to determine the site location? What patterns of population density determined the mapping of the sites? The review team recognises that this is, in part, an outcome of the political decisions taken (see above). One key issue resulting from the decisions over site location is the apparent dislocation of ‘feeder’ primary schools from their intended secondary schools: there are no clear-cut pathways and/or inter-relationships between primary and secondary schools. Rather there appear to be ad hoc or non-existing channels and relationships – and no value-added mutual support that might derive from such linkages, which could have a key influence on learner retention and progress upwards in the system. / The same might be argued for the supposed concept of ‘hub’ and ‘satellite’ primary schools. Do ‘hub’ schools genuinely act as ‘resource schools’ (supporting PTAs, teachers, quality provision)? Is this concept a genuinely active strategy of a ‘cluster’ model that can provide a lesson for future development and expansion? Does the hub help the satellites to retain their enrolment? The potential certainly exists, though it is too early to judge. / The review team was not able to analyse these data and linkages in depth but suggests that SSEP needs to generate an empirical profile of the cohorts attending its schools as a basis for determining whether enrolments and growth in enrolments can indeed be attributed to DFID support. Clarity over the patterns, gender-differentiated, of enrolment, drop out and completion is crucial – not only as basis for determining the success of SSEP at primary school level – but also as a base line to determine patterns of future expansion, demand , school mapping etc. as well as determining how to pre-empt future patterns of attrition and wastage. / Elements of this may be based on the existing EMIS, supplemented by locally-based research.
Progress against expected results: / UNOPS has completed construction work on 31 out of 34 sites (30 primary and 4 secondary) and has delivered furniture to all 34 sites across the four partner States. Work on transportation and installation has continued and installation continues where feasible (within the logistics and security constraints flagged above). 28 primary schools and 1 secondary school were 100% completed: 2 primary schools and 1 secondary school were 87% completed. The procurement and delivery of classroom furniture was 100% completed: installation was 85% complete (in completed schools). The procurement and delivery of office furniture was 100% complete; and installation was 90% complete (in completed schools). / Cash savings made during the construction phase enables the funding of 1 additional primary school. / The milestone for Indicator 1.1 significantly exceeded expectation notwithstanding logistics and security constraints. / The milestone for Indicator 1.2 significantly met expectation at primary school level. However, it moderately did not meet expectation at secondary school level. The lack of teachers in two secondary schools, with government unable to recruit as a result of a budget ceiling is a constraint beyond the project. Similarly low transition rate from primary schools is a much greater long term challenge to achievement of indicator 1.2. / Recommendations: / That SSEP generates a profile of enrolment, retention and completion patterns. / That SSEP re-addresses issues of how to increase secondary school enrolments, especially for girls. / Impact Weighting: 30 % / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Increased access to Alternative Education Services (AES) for out of school children and youth
Output 2 score and performance description: B / Indicator 2.1: Number of out of school children disaggregated by sex supported by AES programme / Milestone 2 was 14,833 enrolled by end-December 2012 of which 8,378 (56.5%) were to be boys and 6,455 (43.5%) were to be girls. The actual achieved by end-December 2012 was 12,715 in total, comprising 7,373(58%) boys and 5,343 (42%) girls. The numbers include learners in the Accelerated Learning Programme (ALP) Basic Adult Literacy (BAL) Youth Education Programme (YEP) and Intensive English Course (IEC). / The review team notes the precise specification of the above milestone and target numbers: and questions by what ‘needs identification’ such precision was achieved. / Much of this output is delivered by a consortium of Save the Children in South Sudan (SCiSS) (Consortium Lead) and the Norwegian Refugee Council (NRC) in collaboration with MoGEI and State ministries of education (SMoEs). / The review did not undertake an analysis of the profile of learner cohorts, their progression, retention or completion rates and subsequent pathways into further education and/or training; or the fate of those who drop out (or seen as ‘failing’ the final Primary 8 examination). / It is clear, however, that notwithstanding the high levels of motivation of those who enrol and remain throughout the learning cycles (4 levels over 4 years) learners continue to participate under harsh learning conditions. The review team observed spartan learning environments (limited teaching and learning materials) with multi-age learner groups and teachers with a limited range of pedagogical skills – some trained, some untrained, some volunteers (highly motivated to support this crucial national provision and themselves hoping for a place on the employment ladder). The teaching force is very transient, with high staff turn-over and serious skills gaps. / The language of tuition (be it English, Arabic or mother tongue[2]) is a potential impediment on the quality of the classrooms and on learning attainment. The IEC upgrading programme faces considerable challenges in equipping Arabic speaking teachers with the necessary English language competencies. / Overall, the putative teacher education strategy is in its infancy with huge gaps facing enormous challenges as high teacher-pupil ratios persist and enrolment growth outpaces teacher supply. DFID anticipates that much of this will be captured in the on-going mid-term review of AES. / ALP provision takes place in the afternoons, is flexible and less formal than primary schooling (e.g. there are no uniforms). It is thus attractive to over-age learners. The entry age can be from 12 to 50 years – which obviously presents a host of challenges for teachers and for learners, hence there are many drop outs (notably amongst girls in the higher classes). / Such learning environments offer valuable opportunities to the target cohorts and some appear to be making flexible responses to the multiple challenges and constraints. The more ‘innovative’ the more likely they can be successful. / Indicator 2.2: Number of learning sites rehabilitated or constructed / Milestone 2 was 9 sites by end-December 2012. The actual achieved by end-December 2012 was 7.These comprised 1 primary school (Rumbek Girls School) together with 6 YEP centres (3 in CE State; 2 in NBeG and 1 in Warrap). There were 3 primary schools ongoing, and 4 awaiting confirmation. / The rehabilitation of Rumbek Girls’ School was completed as per the Bill of Quantities. Memoranda of Understanding have been signed between the County Education Offices and SCiSS relating to rehabilitation of the three primary schools. After the award of contracts, work is proceeding and 2 sites are ready for hand over. / From February 2013, in Bor County (Jonglei State) there are 2 primary schools which are 80% completed and in Twic East there is 1 primary school where rehabilitation has not yet started. In Akobo, contracts are at the signing stage on 2 sites for rehabilitation. / Challenges / AES is a critical programme that meets the needs of a generation or more who have missed out on education – but is seriously in need of policy direction and enhanced provision. A recent workshop report of the AES Thematic working group (March 2013), Making Plans: Setting Policy and Direction in South Sudan, provides a comprehensive platform for moving forwards. So does the provision of institutional support from the SCiSS ALP Technical Adviser on Achieving Education for All, attached to office of DG AES (MoGEI). / A number of observations from the review team’s field visit are pertinent. / Some learners successfully progress to secondary education and/or other training pathways, but it would be more beneficial if ALP, for example, included more than the shadow primary school curriculum and included more life skills, simple business skills and/or basic vocational training. SSEP and its partners cannot tackle the curriculum issue in isolation from the thrust of the national programme. However, by definition AES is intended to be flexible about programme delivery modes, design and implementation. / ‘Training’/pedagogical approaches appear to be purely didactic (in parallel with that in primary schools) and also call for more creativity and innovation. Can the partners seek to break the existing patterns of teaching and learning (based as it is on the content of the learning materials) and seek more innovative approaches? / Language remains a problem for trainers and learners, which calls for further intensification of the use of the IEC approach for these target groups (Arabic speakers being taught English to teach in English.) / Base line data is not available (e.g. enrolments, retention and dropout rates, female participation, employment pathways etc.).
Progress against expected results: / Both milestones and therefore output moderately did not meet expectations, falling short on enrolment targets, gender imbalances and on the number of sites rehabilitated. / Construction work was disrupted in the site location areas (in Rumbek and Akobo) by inter-tribal conflicts, child abductions and by cattle rustling. Youth, women and children are affected by frequent school/site closures and displacement of teachers, families and MoGEI officials. Young men also become actively involved in the conflicts at the expense of participation in AES programmes, with an adverse impact upon attendance and retention rates. / Much of the construction material needs to be imported – including from the north – and transportation is subject to seasonal flooding and delays. / Continued Government austerity measures included non-payment or delay in payment of salaries (for teachers and government employees), with a direct impact upon the quality of support for AES programmes and classroom delivery and upon domestic wealth, with a cyclical impact upon rising costs and consequently lower participation in AES and formal education programmes. / A major challenge is to secure and retain qualified teachers and to pay them (since ALP teachers are outside the government pay roll). Crucially, some programmes have no female teachers: others have a limited number – with an obvious negative impact upon the retention of female learners. / The AES Mid-Term Review commissioned by SCiSS will report on progress. / Recommendations: / That SSEP clarifies (a) the nature of the learner cohorts (enrolment, retention, completion patterns); and (b) the profile of teacher provision (skills sets, pedagogical capabilities, quantitative/qualitative gaps). / Impact Weighting: 30 % / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? Y
[2] In Bor (Jonglei State) the first languages (mother tongues) are Dinka, Nuer, Anyuak, Jiek, Murle and Kachipo.

Output 3: Community capacity developed to effectively participate in school management
Output 3 score and performance description: A / Indicator 3.1: Number of trained Parent Teacher Association (PTA) members participating in school management meetings / Milestone 2 by end-December 2012 was 60% of sites. The actual achieved by end-December 2012 was 92% of sites (based on UNICEF data). This possibly comprised 161 community members trained in school construction and maintenance through UNICEF, although reporting is not clear on the relationship between sites covered and community members trained. In addition 357 PTA members (236 males and 121 females) were trained by SCiSS/NRC. / There is an extremely complex organisational arrangement for the implementation of the community enhancement and child friendly schools strands of the project. The geographical terrain under which the project operates provides challenges for both procurement and logistics for the delivery of this indicator. / UNICEF has subcontracted SNV (Stichting Nederlandse Vrijwilligers). SNV itself works in partnership with 4 Community-Based Organisations (CBOs)[3], with which it has separate MoUs to assist the implementation of the ‘soft-ware component’ (capacity building) of the Community School Development and Construction Project in five sites in Eastern Equatoria State and in 6 sites in Upper Nile State, with which SMoEs it has signed separate MoUs. / UNICEF has a further sub-contract with Ananda Marga Universal Relief Team (AMURT) in 5 Counties of Northern Bahr al Ghazal (NBG) State for capacity building and Child-Friendly School (CFS) development. / UNICEF has another sub-contract with the South Sudan Development Agency (SSUDA) for CFS development and construction in Upper Nile State. / Typically, SCiSS/NRC trained male and female PTA representatives from 3 States in 6-day training sessions covering issues of ‘school governance’, ‘school administration’, ‘school development’, ‘codes of conduct’, ‘roles and responsibilities of PTA members’, ‘child rights and responsibilities’, and ‘girl child education’. / The success of the completion of planned PTA training activities has varied State by State. However, converting training inputs into active participation in school management (the output indicator) is neither easy nor automatic, though the review team has no hard data on numbers participating, the frequency and sustainability of such participation and its impact upon improved school/ALP governance and effectiveness. / In Jonglei all ALP learning sites have established PTAs. Elsewhere, in Central Equatoria State (CES), for example, attempts to establish Community Education Committees (in YEP sites in Supiri and Munuki) have been less successful, with ‘only a few dedicated members showing up and taking an active part in running the centres’. In NBG members are reported to visit centres on a weekly basis and discuss relevant topics, challenges and good practice with Centre leaders, though there remain questions of frequency and impact. / Support is provided on the organisation of meetings, and clarity over roles and responsibilities as well as means to identify and mobilise students. Discussions also take place with Quarter (payam) Councils, with a focus on increased participation and motivation. / In Warrap, a PTA Manual, prepared in collaboration with the AES Directorate SMoE together with the payam, is intended to be more widely shared across SSEP sites. / Indicator 3.2: Number of community advocacy and awareness campaign events conducted / Milestone 2 by end-December 2012 was180. The actual achieved by end-December 2012 was128 through UNICEF and 12 through SCiSS/NRC – including the participation of Student Advocacy Teams (SAT). / The data presented in this commentary (on 3.2) is for Year 2, quarter 3 only: total achievements are higher and SCiSS are in the process of verifying the cumulative results. / 459 members of SATs (comprising 240 males and 219 females) received training and support through SCI/NRC, targeted at improving the roles of the SAT (which is a school club whose members have the mission of encouraging other children to enrol and pursue their education). Training focusses on issues of ‘child rights’; including the importance of education and supporting children to remain in school as well as an emphasis on the different types of education services available. / SCiSS/NRC conducted 10 advocacy and awareness campaigns to mobilise out of school children and youth to enrol in primary school and ALP centres. SCiSS also delivered live radio talk shows on the importance of education, which reached an approximate 4,000 listeners in Bor and Twic East counties, with issues of ‘child rights and opportunities’ (as above) as well as ‘peace’ being highlighted. Likewise, NRC delivered live shows in CES – through Radio Miraya and Radio Bakhita focusing on youth education opportunities and the importance of girls’ education. One was held together with MoE after Girls day in July 2012. Progress again varies across the implementing sites, but has taken the training into a number of payams. / Taken in totality, it is possible to show that there has been a degree of progress towards achievement of the milestone (viz. that it moderately met the expectation); however, there is not sufficient data collected on the effectiveness or impact of these campaigns. / Indicator 3.3: Number of State Education Officers (SEO) trained in school management, administration and supervision / Milestone 2 by end-December 2012 was 500. The actual achieved by end-December 2012 was 32 through UNICEF, together with 129 school inspectors and supervisors (with a focus on classroom observation) and 55 head teachers and County education officers trained through SCiSS/NRC (on aspects of school administration and management). Education officials were trained on effective meeting and report writing skills. Other foci have included monitoring and evaluation tools and participatory monitoring techniques. In Warrap NRC’s AES specialist provided computer-based training to the SMoE in MS Word and Excel packages. / SCiSS/NRC has a specific plan of providing targeted capacity building to County Education and SMoE officials to increase their ability to monitor and oversee AES activities. Joint supervision and monitoring of ALP centres in Lakes conducted between SCiSS and State level inspectors focused on the progress of learning and the challenges of implementing AES. SCiSS have also provided technical support through the AES technical working group to engage the SMoE there on the management and supervision of ALP teachers. / Under this indicator, a wide range of disparate activities continues to be delivered. According to UNICEF, further training was delayed while MoGEI reviewed the Child Friendly Schools training manuals and guidelines. UNICEF considered the delay worthwhile to ensure Ministry buy-in and ownership of the process. This has been done. However, information on the impact of the training inputs is work on progress.
Progress against expected results: / The milestone 2 for indicator 3.1 has substantially exceeded expectation and is providing PTAs with a voice for mobilising community support for improved educational provision, securing pupil enrolment and retention as well as holding local administrations to account. / However, the milestone 2 for indicators 3.2 and 3.3 moderately did not meet expectation, but considerable positive progress was made against logistical and procurement challenges. The review team therefore assess the overall progress of output 3 as output meeting expectation. / A wide range of ‘capacity training’ activities has been conducted in a variety of sites and for a wide variety of target audiences. UNICEF consciously delayed official capacity-building. Austerity measures also undermined progress since government officials proved unwilling to undertake job training without ‘incentives’. The review team is unable to assess its impact on retention and participation, but feels the need for more evidence on this, which may emerge from the Midterm Review of SSEP-AES component being undertaken. It is clear from UNICEF and SCI/NRC plans that capacity development of local education officials is prioritised in the next activity period. / However, a key lesson learned is that PTAs need to be 100% trained before the commencement of construction in order to secure their own commitment to the ownership of the schools being built and engagement and participation in school management. Where decisions have been politically determined, without full community consultation and engagement, it is proving difficult to secure local commitment to engagement with projects which they considered to be ‘externally owned’. / Recommendations: / SSEP needs an assessment of the number of children who have enrolled and stayed in schools, their motivations etc. as a result of these campaigns. / SSEP needs a coherent, holistic training plan which is MoGEI controlled and owned. / Impact Weighting: 20 % / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? Y
[3] Needs Service Education Agency in EES; Mer Kidyer Development Organisation, Organised Mission through Integration for Education and Development and South Sudan Agency for Internal Development in UNS.

Output 4: Improved professional capacity and support to teachers for quality education
Output 4 score and performance description: B / Indicator 4.1: Number of teachers demonstrating participatory teaching skills in classrooms / Milestone 2 (end-December 2012) was 300. The actual achieved by end-December 2012 was not possible to aggregate quantitatively. / The review team had a brief opportunity to observe teaching in classrooms and this revealed limited demonstration of ‘participatory’ teaching and limited participation by children, apart from the occasional rote responses to occasional teacher questioning. Large classes, limited materials support in the classrooms, dim environments and substantially overcrowded classes all militate against the achievement of this ideal, as do existing socio-cultural norms. It will take a massive shift by all players in the system to achieve this goal – which the review team considers extremely difficult in the existing educational context. / Indicator 4.2: Number of AES materials provided to project schools / Milestone 2 (end-December 2012) was 77,690 copies. The actual achieved by end-December 2012 was 94 ALP kits (ALP kit consisted of copy books, pens, pencils, chalks, and makes up to 47,000 pieces), 153 YEP kits and 170 BAL kits. Similarly SCI/NRC undertook distribution of 78,000 textbooks for ALP. / This figure from the SCiSS/NRC Quarter 3 2102 report (8 February 2013) is challenged by NRC on the basis that all YEP and BAL enrolled students receive a ‘learner kit’ when starting the programme. Hence, the figure should be significantly higher, NRC argues, though that additional quantitative data was not available to the review team. / Tracking the indicator, as expressed in the Log Frame and with the ambivalent data presented, has proved problematic. / Importantly, the review team observed limited learning materials in AES sites or in primary schools or in use by teachers or learners. / Indicator 4.3: Number of teachers trained / Milestone 2 (end-December 2012) was 870. The actual achieved by end-December 2012 was 757. This consisted of 432 primary school teachers through UNICEF; 122 primary school teachers, 103 AES teachers, 8 tutors in ‘training-of-trainers’ (ToT) approaches as well as 92 IEC graduates through SCiSS/NRC programmes. It was noted that delays by Ministry of Education in finalising the curriculum framework for teacher education partly delayed implementation and consequently achievement of the indicator. / Those 122 primary teachers trained through SCiSS/NRC were trained in ‘teaching methodologies, classroom management and other related methodologies’ related to the existing modules on in-service teacher training. ToT tutors were trained in ‘necessary skills and knowledge to support teachers’. / There are a number of dimensions to SCiSS/NCR planned activities targeted at improving the status and professionalism of teachers. These include: / (1) Training of experienced tutors in the delivery of AES training, incorporating elements of the existing pre-service training programme in lesson planning and schemes of work, backed up by weekly field-based support from the SALP Teacher Training team (as in Warrap State); / (2) Support for tutors to deliver GoSS approved in-service programmes, including the emphasis on child-centred methodologies – to be delivered by Yei TTC; 150 teachers from Akobo, Bor and Rumbek have completed the first part of this training programme; / (3) Specialist training to YEP and FAE (BAL) teachers and child-centred teaching to primary school teachers. / The review team did not have the opportunity to assess training in action, but suspects that the overall SCiSS training methodologies are generic in approach (rather than child-centred and participatory, as the rhetoric suggests) – as are UNICEF’s, albeit with an emphasis on ‘child-friendly schools’. The classroom teaching that the review team observed indicates the extent of the challenge to reorient teaching performance away from traditional teacher chalk and talk approaches. / Progress against expected results: / From available data, it is impossible to assess whether Milestone 4.1 of teachers demonstrating participatory teaching skills in classrooms was achieved in quantitative terms. However, based even on limited observation the review team is without doubt that the goal of child-centred, participatory classrooms is a long way from realisation in the prevailing context of teacher quality, instructional materials, class sizes and learning environments. / There is also a major shortfall of essential learning materials in classroom contexts – though, from data presented, Milestone 4.2 has substantially exceeded expectation. / Milestone 4.3 for the number of teachers trained met expectation, / Due to centrality of application of teaching skills in the learning process, the review team assess output 4 as meeting expectation / Recommendations: / SSEP revisit the strategy for ‘participatory skills in classrooms’ and the means to achieve it, including pedagogical approaches, classroom environments, teacher availability and capabilities etc. / Impact Weighting: 20% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? Y

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the LogFrame been updated since last review? Y / The Log Frame was revised after the March 2012 annual review. However, the review team recommends revisions to the Log Frame by DFID in consultation with UNICEF, SCiSS, NRC and MoGEI. For example the Review Team identified some similarity of outcome and output indicators of the log frame. / 1.2 Overall Output Score and Description: A / The milestone for the number of classrooms constructed has been substantially exceeded and the construction phase of SSEP nears completion. It is likely to be completed within its timescales. This is notwithstanding severe logistics and security threats. A milestone for the support of primary pupils has also been achieved, albeit not at secondary level. / SSEP met expectation of its milestone under Output 2 – though falling short on enrolment targets, gender imbalances and the number of sites rehabilitated. It exceeded its milestone for the number of PTA members trained and anticipated participation in meetings, although it did not match this with the number of community advocacy campaigns. It fell considerably short of its milestone of the number of State education officials trained – an obvious key impediment to both the ownership and sustainability of the initiative, especially in school and classroom contexts. / The milestone for the number of teachers trained was moderately achieved with good progress made towards quality training at Yei Teacher Training College. From available data, it is impossible to assess whether the milestone of teachers demonstrating participatory teaching skills in classrooms was achieved in quantitative terms. However, based even on limited observation, the review team suggests that without doubt that the goal of child-centred, participatory classrooms is a long way from realisation. There is also a materials shortfall in classroom contexts – though the review team cannot assess whether the milestone 4.2 has been achieved given the data provided. / 1.3 Direct feedback from beneficiaries / Limited time during the review was available for stakeholder discussions, though the key consortia gave substantial, valuable commentaries of the review draft report. / Without doubt, the ultimate beneficiaries – learners, teachers, school managers, PTAs, County and State officials – are gratified at the support provided, which not only enhances their voice and enables a systemic response to the opportunities they are offered and the challenges they face, but provides a range of facilities, resources and materials in an otherwise resource-constrained context. / The multiple range of service providers – the local and international CBOs and NGOs – are also gratified at opportunities afforded them to fulfil their missions and to deliver their ‘services’ (improved educational programmes) to their client Ministries and Counties. / Less gratified are senior officials from Alternative Education Systems (AES) Directorate in MoGEI who, whilst grateful for support and partnership from SSEP, feel that the management and financial arrangements leave them outside the management loop and exacerbate feelings that SSEP in terms of the AES component is more externally driven. / 1.4 Summary of overall progress / The hardware elements of SSEP have almost been achieved. However, the infinitely greater challenges of enhancing the delivery capability of the target systems mean that the soft-ware elements continue to need improvements.
1.5 Key challenges / Ownership. As the review has observed, there is little doubt that there is strong ownership of the initiative amongst most beneficiary and stakeholder levels. This includes State and County MoEs. However, the involvement of AES Directorate of MoGEI in the AES component of SSEP leaves a lot of room for improvement. / Financing. The review is concerned with the manner in which financial reporting takes place, particularly through SCiSS. It suggests that both budgeting and expenditure reporting is harmonised in one format agreed between stakeholders, and that there is a text accompanying all financial reports in explanation of noticeable discrepancies between budget and expenditure. / Management and co-ordination. The review expresses concern at the capacity, efficiency, internal co-ordination and synergies amongst the multiple service providers and stakeholders and suggests the need for a coherent mechanism to ensure participation and co-ordination of all. / Hardware. Considerable endeavour has been put into enhancing the nature of the ‘site’ environments. However, many environments seen by the review team are not conducive to high quality teaching and learning. Sustained efforts to improve existing (and future) learning environments are crucial – particularly in the wake of the conclusion of the construction phase of SSEP. / Nature, range, diversity of programmes. SSEP delivers a diverse range of initiatives. However, it is difficult to perceive intersections and synergies between them. A key dimension of the proposed LogFrame redesign should be the search for linkages and synergies between initiatives that appear to run in parallel rather than in summation. / Profile of learners. At present, the initiatives provided by SSEP (as above) attract a considerable number of learners – some of whom successfully complete their ‘courses’, others who do not. No hard, empirical evidence is available in a collated database about the ‘profile’ of SSEP’s learner cohorts. This is crucial as a base for understanding whether and how the programme is successful, or not, in relation to its intended outputs, outcome and impact. / Profile of trainers, teachers (including staff retention). As above, there is no database that relates to the nature of the teaching force; their qualifications, capabilities, success rates. / Empirical understanding of SSEP’s influence in terms of educational quality and community enhancement. Again, there needs to be a (costed) research, monitoring and evaluation component embedded in SSEP in order to determine the extent to which SSEP is successful in influencing the quality of education and local community participation in and benefit from the process. / Overall inter-relationship/co-ordination between education sector programmes. SSEP cannot operate in a vacuum. There needs to be much greater coordination (through the Local Education Group?) of governmental, NGO and donor-supported education programmes and of basic service programmes (WASH, health, rural development, environmental etc.) with which the education sector interacts. / 1.6 Annual Outcome Assessment / The review team did not undertake an Outcome analysis however; the number of learners enrolled in SSEP sites demonstrates the contribution of SSEP to increased access to education. The review team strongly recommends profiling of learners retention and dropout.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / For the Year 2012 (1st January – 31st December), the project has been on track against financial forecasts regarding the work of UNICEF and UNOPS. UNICEF forecast and spent approximately $1.6 million in each of the first two quarters, $1.2 million in the 3rd quarter and $460,000 in the 4th quarter. UNOPS forecast and spent $8.2 million in the 1st quarter, approximately $195,000 in the 2nd and 3rd quarters, and $200,000 in the 4th quarter – a pattern which signifies approaching completion of the school building contracts. / The total funds received by UNICEF by 31st December 2012 ($[26,999,040].41) are equivalent to £17,111,900.31, which corresponds to approximately 84% of the total amount of the grant (£20,437,469.80). / With SCiSS/NRC the budget for each quarter in 2012 (April-June; July-September; and October-December) is exactly the same for each of the seven Budget Headings and for the Total Budget. Since expenditure is reimbursed to SCiSS quarterly in arrears, it is perhaps considered safe by SCiSS to over-budget, if the budget is accepted by DFID each quarter. However, greater discipline in forecasting what is required each quarter would facilitate better monitoring and explanation of expenditure. As it is, over the three quarters reviewed, SCiSS nominally underspent by 50%. Quarter by quarter under-expenditure has been: Y2Q1 = 58%; Y2Q2 = 44%; Y2Q3 = 32%. / It is not clear from the quarterly reports submitted to DFID whether the under-expenditure is on the part of SCiSS or NRC or both. It would expedite matters considerably if included in the quarterly reports there was a full financial report with explanatory notes. / Since DFID is now focused on harmonization of expenditure and forecasts, it will be necessary to examine the project accounts every month from now on. / With regard to the flow of funds, the team was informed that within SCiSS and its State offices there is a satisfactory control system and replenishment of the SCiSS bank account at State level can be carried out on the same day following the submission of a claim signed by the Field Manager, the Deputy Director for Programme Implementation and the Finance Officer, accompanied by an account of total expenditure to date, the names of staff who have received an advance with the amounts, and bank reconciliation. However, it was reported to the review team that NRC often has to wait for three months before its project expenditure is reimbursed by SCiSS, the lead agency for delivery of AES. / The review team recommends that it would be more efficient if in future DFID dealt with NRC directly rather than through SCiSS. This will require a separate Memorandum of Understanding and Accountable Grant Arrangement. / 2.2 Key cost drivers / As in the previous Annual Review, the key cost drivers, especially at the beginning of the period under review, have been the costs of materials and transportation, especially in Upper Nile State where construction of all 8 schools has been affected by insecurity, rains and limited access to sites. / 2.3 Is the project on-track against original timescale: Y for the most part / Project outputs have been assessed earlier. Suffice it to say that schools construction, furnishing and equipping will be completed ahead of schedule.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is a very weak evidence and database for SSEP. The MTR of AES, which has been on-going in parallel with this review (albeit in much greater depth, coverage and time scales) has been commissioned to provide some base in data, both qualitatively and quantitatively across the range of SSEP’s AES strands. There remains a critical need to assemble hard evidence on the nature of SSEP’s learner cohorts (their successes and shortfalls), the teacher cohorts (their capacities, skills and gaps, qualitatively and quantitatively) and the success or otherwise of the multiple learning/training tracks. Otherwise, not only is SSEP in danger of appearing directionless and/or divergent- as well as un-co-ordinated (in part as a consequence of faulty design) but it will not be able it to demonstrate its outcome and impact as it approaches its termination. / UNICEF’s School Development and Construction Project Monitoring and Evaluation Plan (September 2012) was an update of its July 2012 plan and is intended to guide the project M+E functions from July 2012 to September 2013. At the core, it provides a monitoring, evaluation and reporting matrix intended to map progress against the project LogFrame which shapes its quarterly reporting. Additionally, it presents its intended evaluation schedule based on: (a) a base line study; (b) annual reviews; (c) post-training follow-up surveys; (d) a pilot learning assessment model; and (c) end of project evaluation. / SCiSS has commissioned a two-person consultancy team from Uganda to undertake a Mid-Term Review of its DFID-funded AES initiatives. As well as reviewing monitoring data, it is undertaking focus group discussions with pupils, learners, teachers, communities and Ministry officials. Comprehensive in scope (including AES, ALP, YEP, BAL) its coverage includes progress against milestones for enrolment and completion rates, and qualitative assessment of achievements of all aspects of AES. Its draft report is scheduled for 25th April and after review by the MTR Evaluation Advisory Team, the final report is scheduled for 1st May 2013. / 3.2 Where an evaluation is planned what progress has been made? / The evaluation is planned for 2013. Terms of Reference should be drawn up in the wake of this review and the MTR.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / Security issues continue to have an impact at every project level and will continue to threaten programme implementation and sustainability, though more will need to be known about the full extent of the threats specific to SSEP target groups, girls and women in particular. / Logistics and, for example, transportation problems continue to impede the pace of implementation of the construction and rehabilitation programme – though this decreases as the construction programme nears completion. / These aspects have been well explored in wider analyses of ‘project implementation’ and endeavour to enhance educational opportunity. That, of course, does not diminish the risks. / As the roll out of SSEP continues, the review team considers that the programme risks associated with ‘the implementation of educational innovation’ will assume greater prominence. These were not addressed in the January 2011 SSEP Programme Memorandum which provided a matrix of risks and mitigation related to Political, Social and Environmental parameters. / At this stage, the review team considers that issues associated with – / (a) the capacity and capability of the host management systems (MoGEI at national, state and county levels); / (b) professional capability – namely the capability of the teacher/trainer cohorts to deliver high-quality teaching and learning for the ‘target’ learners; and, consequent upon this, / (c) the sustained commitment and motivation of learners to continue to study in the face of poor quality provision (where that exists) – are all factors in the sustainability of SSEP’s work. / The review team has observed (and heard about) poor quality provision. If proven, this will undermine the intended impact and sustainability of SSEP. For that reason, the review team considers the risk level as still high, as did the January 2011 Programme Memorandum (para 4.1) / 4.3 Risk of funds not being used as intended / There is no reason to believe that funds will not be used as intended. / 4.4 Climate and Environment Risk / As in the last Annual Review, climate and environment risks have been addressed in the Programme Memorandum. Mitigation measures are properly adhered to during construction work.

5. Value for Money
5.1 Performance on VfM measures / The project has performed well against the VfM measure of regarding school construction. The negotiation with the education ministry on school design and the subsequent decision to delete the basketball courts from the design and more importantly are evidences of constant VfM monitoring of the project. These measures in addition to competitive tendering procedures led to cost savings which will now be used to construct an additional school. The average primary school classroom cost takes into account the 8 classrooms per school combined with 1 teacher resource room, 1 store, 1 water point, separate latrines for boys and girls and other rooms and facilities. It ranges from $39,125.75 in Eastern Equatoria State to $54,280.13 in Upper Nile State. Overall the average classroom cost is $47,291, some $9,122 (or 16.2%) below the original estimate made by UNOPS during programme preparation. All schools that have been completed (except two secondary schools) have had huge enrolments, demonstrating the effectiveness of the project in meeting its outcomes. / The average price per secondary school classroom (out of 4) taking account of all facilities/rooms provided ranges from $107,460.59 (EE) to $124,582.01 (UN) = $114,236.25. The average price per secondary school classroom (out of 4 plus 3 laboratories and 1 library) taking account of all facilities/rooms provided ranges from $53,730.29 (EE) to $62,291.01 (UN) = $57,118.12. The latter figure is only slightly more than the original price per primary school classroom estimated by UNOPS during project preparation. / With regard to the other VfM measures mentioned in the SSEP Programme Memorandum, by using partners with good track records and presence across the states DFID has obviated the need for initial start up delays. However, as mentioned in Section B2 above, there are serious differences between forecasts and expenditure with SCiSS. Furthermore, greater VfM may be achieved by dealing with NRC directly rather than through SCI, an initiative worth discussing. DFID and implementing partners to discuss strategies to further improve VfM as the context, costs keep on varying. / The review team was given no information regarding GoSS and SMoEs making cost efficiency savings by developing educational facilities that can be used for a variety of purposes. / 5.2 Commercial Improvement and Value for Money / This review did not look at the commercial aspects of the project. / 5.3 Does the project still represent Value for Money : Y for the most part / The project represents Value for Money in quantitative terms, i.e. the potential benefits to the number of pupils and learners in DFID funded newly constructed schools and alternative education centres inasmuch as they can be realistically quantified are higher than the investment. However, the quality of the education received might not truly equip school and AES centre graduates with skills sufficient for them to get a high return on their own investment. / 5.4 If not, what action will you take? / Focus now on the qualitative aspects of the project, such as teacher supply and training, teaching and learning materials supply and use, and improvement of the physical learning environment.

6. Conditionality
6.1 Update on specific conditions / There is no conditionality applicable to SSEP.

7. Conclusions and actions
DFID to improve relations with AES Directorate over the ownership and financial control of the AES component of SSEP. / DFID to undertake LogFrame redesign. / DFID to ensure a coherent mechanism/structure to involve all stakeholders in streamlining the overall co-ordination of SSEP. Ensure coherent collective project co-ordination with harmonisation and clearer channels of communication between DFID – MoGEI – SCF/NRC – UNICEF/UNOPS et al. / DFID to ensure improved SSEP M+E by all partners– with coherent, structured, sequenced M+E and reporting (and accuracy of reporting), fitted to requirements of DFID LogFrame/template. / Continued emphasis by all stakeholders and service providers on the improvement of the school and classroom teaching and learning environments. / Stakeholders agree the means to assemble a database of SSEP’s learning cohorts. / Stakeholders agree the means to assemble a similar database of SSEP’s teaching force. / SSEP commission research to provide empirical understanding of SSEP’s influence in terms of educational quality and enhancing community participation. / DFID/MoGEI to clarify overall inter-relationship/co-ordination between education sector programmes, and inter-sectoral basic services programmes. / MoGEI to clarify the strategy for learning assessment, an accreditation system (for learners and teachers), and AES policy, strategy etc. oversight. / It would be more efficient if in future DFID dealt with NRC directly rather than through SCiSS. This will require a separate Memorandum of Understanding and Accountable Grant Arrangement. / DFID to undertake a comparative review of project implementation across the target States – for future policy development, lesson learning etc. / PSC agree appropriate time, focus and TOR for next review / PSC agree early collective agreement of dimensions of 2015 Evaluation and Impact Assessment.

8. Review Process
A team of two professional education consultants with complementary skills undertook the review in South Sudan from 8th – 13th April 2013, under contract from CfBT against the agreed DFID Terms of Reference. / Prior analysis of key documents, supplied by DFID (and supplemented by all partners during the in-country mission) provided initial insights into the scope of the work of SSEP and its partners. / Initial briefings by DFID confirmed the boundaries of the consultancy mission, against the agreed TOR (‘the contract’). / Additional briefings from the key agencies in the implementing consortium (Save the Children and Norwegian Refugee Council together with UNICEF and UNOPS) widened the discussions into programme implementation – progress towards achievements of Outputs, Challenges and Risks. Different modalities, sequences and time scales of reporting as well as lack of commonality of LogFrames and consistency with the master DFID LogFrame (understandable in the context) proved a conceptual challenge – which continued in field discussions with sub-contracted implementing partners (see below). / Only limited briefing took place with the Ministry of General Education and Instruction – at the level of Director General for Alternative Education Services. / Juba-based site visits to Lologo and Supiri enabled an understanding of the hardware components of NRC support. / A two-day field visit to Bor, accompanied by the DFID Senior Education Adviser, enabled briefings from SCiSS staff and from Jonglei State / Bor County officials. This included visits to Langbar and Malou Primary schools and Leudiet ALP Centre where the soft-ware elements of SCiSS support were explored, though site observation, classroom observation and discussion with heads, teachers, learners, PTA and community representatives. / A de-briefing meeting scheduled on day 5 was flexibly timed to accommodate office time scales (as well as disruptions occasioned by a watershed State visit). Most SSEP stakeholders were represented and reacted with positive viewpoints and challenges to the review team’s ‘quantitative output analysis’, contextual issues and suggestions for action. / Importantly, the team schedule of short visits did not enable coverage of locations suggested by the TOR, including four comparative sites and a broader selection of ALP, YEP, IEC and BAL programmes. / The reporting context takes into account both the intense rapidity of the visit and the limitations of the network of respondents (as well as the limitations of hard data available)