Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Rashtriya Madhyamik Shiksha Abhiyan (National Secondary Education Mission ) RMSA
Programme Value: £ 80 million (2012/13 to 2015/16); £60 million budgetary support and £ 20 million technical co-operation via management contract.		Review Date: November 2014
Programme Code: 201388	Start Date: October 2012	End Date: FA: December 2015; TA: March 2016

Summary of Programme Performance
Year	2012-13	2013-14	2014-2015
Programme Score	A	A+
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

Strong progress has been made during last year. Extensive work has been done to strengthen both the results framework and the data that informs this. This has enabled accurate monitoring of progress against milestone indicators. Milestones are substantially on track – where milestones have not been reached the deviation is less than a percentage point. The only exception being on children with special needs (CWSN) – where an inaccurate baseline has distorted projections.

The performance of the DFID funded technical cooperation agency has been excellent this year. Their support has contributed to advances in a range of areas from the National Achievement Survey to the evidence base considered by the Joint Review Mission. These contributions have been appreciated by GoI and donor partners alike. With growing trust and reputation for delivery the technical cooperation agency (TCA) is becoming increasingly influential in rationalising and streamlining the delivery of RMSA.

Summary of recommendations for the next year

DFID continues to promote the concept of ‘equity in learning’ using National Achievement Survey (NAS) to emphasise differential levels of learning between groups and to use this data to guide remediation, and resource targeting – particularly at State level.

- DFID supports National Council for Educational Research and Training (NCERT) to make the data sets from NAS and Unified District Information System for School Education (UDISE) more readily available and ‘intellectually accessible’ (with appropriate protocols) to enable secondary data analysis by researchers which could further strengthen our understanding particularly in areas of learning achievement and learning challenges.
- Development Partners (DPs) continue work on strengthening results monitoring - particularly to clarify (i) discrepancies between exit flows from elementary and entry flow to junior secondary. (ii) the number of students who enter grade nine and complete lower secondary education (disaggregated by categories).
- DFID responds to Ministry of Human Resource and Development’s (MHRD) request for additional support to ensure the timely delivery and further enhancing of the NAS and its use in policy formulation and resource targeting.
- DFID undertake work to strengthen understanding of provision for children with special needs including cost effective options on how to improve this.

Introduction and Context (1 page)
DevTracker Link to Business Case:	Quest No. 3717085
DevTracker Link to Log frame:	Quest No. 4539191
RMSA Delivery Plan	Quest No. 4717590

Outline of the programme

Rashtriya Madhyamik Shiksha Abhiyan (RMSA) is a Programme of the Government of India, implemented in partnership with the State Governments and donor partners with the main objective to make secondary education of good quality available, accessible and affordable to all young persons. RMSA was launched in 2009. DP budgetary support began in 2012.
RMSA seeks to enhance enrolment in classes IX and X by providing a secondary school within a reasonable distance of every habitation, to enhance retention and completion of grade X, to improve quality of education imparted at secondary level by ensuring all secondary schools conform to prescribed/ standard norms, to remove gender, socio-economic and disability barriers and to achieve near universal enrolment in secondary level education with the GER exceeding 90 percent by 2017.
RMSA is extensively funded through domestic resources. In addition, the World Bank’s International Development Association (IDA) have committed £300 million and United Kingdom’s Department for International Development (DFID) £60 m (2012-13/14) in budgetary support and £20 million in Technical Assistance (2012-15/16). RMSA programme expenditures include: school buildings, teacher salaries; teacher training; science equipment; school improvement grants.
DFID is the sole provider of technical assistance (TA) to RMSA. DFID’s TA is designed to accelerate the implementation and effectiveness of RMSA thereby amplifying the impact of GoI and World Bank investments. DFID technical support is provided through a competitively selected management agent which operates the Technical Cooperation Agency. Their work is focussed on: learning assessment, management information systems, planning and budgeting and teacher management. The TCA works with MHRD and through the central government apex institutions of the NCERT and National University of Educational Planning and Administration (NUEPA) and associated state level bodies, i.e. State Council of Educational Research and Training and Regional Institutes of Education. The work programme and performance monitoring for this support is governed through a steering committee convened by MHRD and on which DFID and the World Bank sit.
The GoI and DPs carry out a Joint Review Mission (JRM) twice a year. The main objective of the JRM is to review progress in the implementation of the programme with respect to RMSA’ s goals, with a particular emphasis on a small number of issues, and to discuss follow-up actions in the light of the Terms of Reference (TOR) agreed upon for each JRM. There have been four JRMs the latest in August 2014. These can been found at http://mhrd.gov.in/rmsa_jrm .

Strong progress has been made this year. Issues around data availability that resulted in insufficient evidence to give the programme a review score above a B in its first year 2012/13 have been largely resolved. The DFID funded TCA has been widely recognised for delivery of strategic and timely support. The MHRD/ DEA request for continued DFID technical engagement post RMSA closure in full understanding that there will be no further budgetary support is testament to DFID’s reputation as a trusted and responsive technical partner.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Outcome 1: More Girls and Boys Access and Complete Good Quality Education:
Indicator(s)	Milestones ( 2013-14)	Progress
1. Enrolment of students in Secondary ( Grades IX and X) (in millions)	35.5 million	Substantially exceeded expectation: There has been a 7 % increase in enrolment from 34.7 million in 2012/13 to 37.3 million in 2013-14. This denotes a total increase of 18 % from the baseline of 31.6 million in 2010-11. Enrolment in the government and aided schools has also gone up by some 2.9 million (9.4%) over this period due to expansion of schools and additional classrooms under RMSA. Of overall enrolment, girl’s enrolment has risen by 8 % (17.6 million) and boys by 7 % (19.7 million). This denotes a 16% increase in boys’ enrolment and 20% increase in girls’ enrolment from the base year in 2010/11. However, there are still concerns on access and completion amongst some disadvantaged groups. Children with special needs (at 0.6% of total enrolment) appear to be under represented in enrolment data in comparison with normal population distributions of 2-4% CWSN.
2. Elementary to secondary transition rate (%)	93.5 %	Moderately did not meet expectation: The transition rate from elementary to secondary has declined from 92.7 in 2012-13 to 91.9 in 2013-14. Overall there has been a slight decline of 0.6 % from the baseline year of 2010-11. Further, the transition rate continues to be lower in case of girls (89%) in comparison to boys (94%). Given the size of the sample this is not seen as a significant deviation as against the milestone target. However overall trends around gender equity remain a concern.
3. Grade X pass rate	81%	Moderately did not meet expectation: Grade X exam pass rate for 2013/14 was 80% for all categories of schools - as against milestone target of 81%. Overall, there has been an increase from 76.9% in the baseline year 2010-11. Given the size of the sample this is not seen as a significant deviation as against the milestone target. / For Government schools it is 74%; aided schools 83%, and private schools 85%. Interestingly, in all three categories of schools girls are doing better than boys (if pass percentage in State board exams is taken as an indication for quality of learning). / Board examinations may not be fully reflective of the achievements at the secondary stage, in the post RTE scenario, in the absence of entry-level competencies at Class-9.

Key lessons

Extreme care is needed to verify valid comparability of statistics, i.e. ensure that trends are not distorted by tracking progress using one data set for baselines and another as the progress indicator. The likelihood of this happening will decrease over time as UDISE (now confirmed as official government statistics) is established.

RMSAs ability to meet its overall target of GER exceeding 90 percent by 2017 is dependent on through put of students from primary and elementary. While data sets at secondary level show encouraging trends – student drop out in lower school grades (beyond the control of RMSA) will inevitably impact on macro targets.

Key actions

DFID needs to continue to work for increasing levels of data disaggregation and use e.g. around CWSN and trends in girls transition. Findings to be surfaced and discussed and recommendations formulated through the JRM process.
DFID TCA focus on use of NAS data to inform learning improvement strategies.

Has the log frame been updated since the last review?

Yes. The revised Logframe reflects considerable work done to strengthen and consolidate secondary education data in a single data base covering both primary and secondary education. Revisions reflect:

- More reliable data now available from the new integrated EMIS (UDISE);
- DP negotiation of more realistic progress targets (rather than GoI targets established by working back from assumption of 100% attainment rates by16/17);
- to better capture the systems strengthening and policy support work delivered through DFID technical assistance.

Secondary education suffered from a lack of a consolidated data set. This made the compilation of a jointly agreed result framework problematic and establishing commonly agreed baselines challenging. The DPs and GoI have put considerable effort into creating a unified data base covering both primary and secondary level data is now operational and forms the agreed platform for progress monitoring. However, the amalgamation process has meant there is a gap in the unified data set for the year 2011/12.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output 1:	Strengthened planning and management to better deliver quality secondary education
Output number per LF	Output I	Output Score	A++ (see table footnote)
Risk:	Medium	Impact weighting (%):	40%
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N
Indicator(s)	Milestones ( 2013-14)		Progress
1.1 National Achievement Survey for grade X conducted	Training and support in developing instruments, sampling and use of IRT software.		Met expectation: / NAS X Assessment Framework and Technical Standards finalised. / Sampling manual and field pilot of test items completed. / NAS Class VIII technical report finalised and published. / NAS video for strengthening remedial use of NAS in process.
1.2 Govt data system strengthened / Single official data system in place.	Technical analysis and needs assessment of U-DISE conducted.		Substantially exceeded expectation: / The TCA conducted a comprehensive EMIS (U-DISE) review and developed a road map to improve the quality of data management. In addition, and most strategically it supported in making UDISE operational across the 35 states and union territories.
1.3 Capacity and systems for results focussed planning and budgeting strengthened / in place	Needs assessment conducted and discussed with MHRD.		Substantially exceeded expectation: TCA’s support went beyond the milestone target and progressed the following additional activities: / Four states supported in development of medium term plans. / Draft handbook for developing medium term plans being readied for national publication. / Plans for district level planning support in train.
1.4 School standards, evaluation and development systems developed / in place	Report on national and international best practices published and UK OFSTED exposure visit conducted.		Substantially exceeded expectation: / In addition to timely publishing of the report on best practice, / 4 consultative workshops on school quality standards were delivered, and a draft framework on school standards and evaluation shared with MHRD.
1.5 Teacher management and deployment systems developed / in place	Discussion document on recruitment, deployment and supply chain management; 2) Best practices on HR database management.		Met expectation / Desk review and data analysis for two states completed. / HR MIS review report delivered for one state. / Review reports presented at 4th JRM. / The study of RMSA in-service training in partnership with NCERT has commenced in 9 states.
1.6 Rationalised processes for school expansion and improved civil works provision developed / in place	Three research proposals prepared; 2) Constitution of national technical group on civil works		Substantially exceeded expectation. Five research proposals (against milestone of three) have been prepared. The TCA not only helped in setting up the national technical group on civil works with defining its scope and objectives but is also a valued member of the group. Other details include: / Preliminary findings on school siting delivered to 4th JRM / 5 research studies (with NUEPA) to inform revision of programmes in civil works, school design etc. in train.

N.B: The table details some of the areas where the DFID TCA has exceeded specified output indicators. However it is the cumulative impact of the TCA that justifies the A++ ratings.

Key Points

DFID’s TCA has made an important contribution to RMSA implementation, in areas ranging across process reform (results based budgeting); transparency (TA to develop a web portal and interogatable management information data base), and research (the impact of RMSA norms on systems efficiency).

Supportive management and a reputation for delivery has resulted in increasing requests for DFID TCA support in a broadening area of activity. This includes emerging political priorities such as the 'Swach Bharat Swach Vidyalaya'. The trust that this denotes is positive. However, DFID and TCA are carefully managing the opportunities for strategic engagement against the dangers of ‘mission creep’.

Direct Feedback from beneficiaries

‘TCA has accomplished a lot in a short period of time in the selected thematic areas and besides that TCA support on other emergent requirements is appreciated’. Ms Caralyn Deshmukh. MHRD Director RMSA.

‘I have found the work of the TCA to be of extremely high technical quality, using both local and international consultants. Equally important is that the work is built on a strong foundation of trust with the client organisations. As a consequence of these factors, the outputs are likely to have a significant impact on policies and programmes.

Looking forward, it would be useful to have further discussions about how to ensure the sustainability of the technical capacity.’ T. Linden Lead Education Specialist - World Bank

TCAs focus on ‘communication for action’ and knowledge management has had particular impact. E.g. in the National Achievement Survey: As the 4th JRM notes: “The mission praised the efforts made by NCERT and TCA to make the NAS both more scientifically robust and accessible, e.g. through the use of infographics”.

Issue raised in previous annual reviews and response

Securing collective agreement between MHRD and DPs on a mutually acceptable results framework has been largely completed. Only two areas for further work remain and were recorded in the 4th JRM. (i) discrepancies between exit flows from elementary and entry flow to junior secondary. (ii) completion rate - the number of students who enter grade nine and complete lower secondary education (disaggregated by categories).
 DFID has recalibrated and aligned its Logframe to the new RFD and the indicators of the TCA Logframe.

Recommendations

- DFID through TCA work with NCERT in identifying and communicating patterns of learning under-performance disaggregated by gender, socio economic group, parental and school based characteristics (e.g. rural / urban, school size).
- DFID TCA focuses on strengthening the link from diagnosis to remediation ensuring under performance is addressed through practical policy options, guidance, and capacity building most particularly by State level institutions.
- DFID supports NCERT to make the data sets more readily available to the broader education community (with appropriate protocols) e.g. to enable secondary data analysis by researchers which could further strengthen our understanding of learning achievement and learning challenges.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output 2	Schools are given the resources needed to deliver quality secondary education
Output number per LF		Output II	Output Score	A+
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones ( 2013-14)	Progress
2.1 Proportion of schools with full allocation of qualified subject specific teachers (Maths, Science, Social Science, Language)	37%	Moderately exceeded expectation: 40.5 % of schools have full allocation of subject specific teachers in 2013-14 as compared to 35.2% in 2012-13. There is an overall increase from 24.5% in the baseline year 2010-11. However, there are still worrying shortages of trained subject teachers in Mathematics (24.5%), Science (31%), Social Studies (43.6%) and Languages (22.6%).
2.2 Proportion of schools with a complete set of infrastructure components	1%	Moderately exceeded expectation: 3.6% schools have complete set of infrastructure components in 2013-14 as compared to 1% in 2012-13. Overall there is an increase from 0.6% in baseline year 2010-11.
2.3 Annual percentage of teachers receiving in-service training	20%	Moderately did not meet expectation: 17.7% Nationally, more than 188,000 teachers received in-service training as per U-DISE 2013-14.

Key Points

- While the overall number of schools with core facilities has increased, concerns remain on the utilization of approved funds for civil works and the completion of civil works projects.
- Each State has differing civil works procurement and execution arrangements – requiring a state by state approach for the national RMSA administration.

Summary of responses to issues raised in previous annual reviews (where relevant)

Civil works completion (timely utilisation of funds) and quality of delivery are issues that have and will continue to be brought up through the JRM process.

Recommendations

DFID’s technical support is working on the broader issues of planning and budget utilisation – a major component of the TCA policy research agenda deals with programme norms and civil works issues. Findings will be released in the next year – it is important that these are delivered in advance of the next JRM (Q1: 2015) in order to maximise their impact in the DP-GoI dialogue.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output 3	Children, regardless of social background participate in secondary education
Output number per LF		Output III	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones ( 2013-14)	Progress
3.1 Ratio of girls to boys enrolment at secondary level	0.9	Met expectation: At 0.9 to 1 ratio of girls to boys enrolment for 2013/14 indicates near gender parity over the entire system.
3.2 Total CWSN enrolment in secondary education (IX-X) and percentage of CWSN to total enrolment	480,000	Substantially did not meet expectation: U-DISE 2013-14 data reports that 227,000 CWSN are enrolled in secondary classes. This amounts to some 0.66% of total enrolment. This results from significant over reporting in the state of UP.
3.3 Percentage of SC students to total enrolment and b) ST students to total enrolment (Population Share SC: 16.6, ST: 8.6 - Census 2011)	18.2% for SC & 8.6% for ST	Met expectation: U-DISE 2013-14 SC enrolments at 18.4% and ST students at 8.6%.

Key Points

- While the ratio to boys to girls’ enrolment is encouraging – there is no cause for complacency. This year’s transition rate from elementary to secondary suggests a bias in favour of boys – similarly we have limited understanding of the ‘graduation’ rate of students entering and exiting the junior secondary sector. NAS findings from lower grades suggest girls are doing as well and in some instances better in learning achievement – it will be important to look at patterns of learning performance when NAS grade 10 findings are released next year.
- There has been substantial under achievement against the milestone target on children with special needs (CWSN). This results from over inflated base line figures (particularly from the State of Uttar Pradesh). These have been significantly revised. Even the original inflated figures indicate a significant under-representation of CWSN against what would be expected as an against a normal population distribution. Discussions with MHRD reveal CWSN is a ministerial priority – three issues are of particular interest (i) How to expand and provide an inclusive education offer (ii) how to provide specialist services to meet specific needs it an affordable and effective manner (iii) how better to harness ICT to support education of CWSN.
- While numerical enrolment targets are positive, NAS findings on learning performance for lower grades suggest that schedule tribes are significantly underperforming.

Summary of responses to issues raised in previous annual reviews (where relevant)

The revised DFID Logframe includes an indicator on children with special needs in line with DFID HQ efforts to focus and capture progress on CWSN – achieved.

Recommendations

- DFID TC undertakes a rapid situational analysis of the status and issues associated with CWSN – A policy brief detailing possible options drawn from international practice to be developed and circulated to help support future GoI endeavours.
- DFID’s Logframe milestones should be revised in line with the above and realistic projections on CWSN based on the more reliable data now available.
- DFID push for attention on the provision for and performance of schedule tribe students to be included in the terms of reference within next year’s joint review missions.
- DFID to share experience and early results from its Orissa cash transfer programme (OGIP). To provide evidence on innovative ways to support disadvantaged secondary school children.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers of the programme include (i) construction and renovation of school buildings; (2) salaries for additional teachers; (3) training for teachers and school heads; (4) books and science equipment; (5) small grants for community-run school management committees and (6) technical support through the jointly selected technical cooperation agency (constitutes 17.5% of the total DFID allocation).

RMSA spending has and remains heavily dominated by civil works (61.6%) and staff salaries (24.6%) in 2013-14). This is as expected for the early stages of a programme and is a pattern seen in previous DFID support to GoI’s primary / elementary programme Sarva Shiksha Abhiyan (SSA). It would be expected as the programme matures a gradual shift to learning and training related programmes would emerge.

All States are required to follow the RMSA Manual on Financial Management and Procurement issued by MHRD in January 2012 for their procurement of works, goods and consultancy activities. This has ensured that the proposals and budgets from the contractor and grantees are realistic and provide value for money against appropriate benchmarks.

VfM performance compared to the original VfM proposition in the business case

The original VfM proposition in the business case was founded on the economic benefits of an expanded and better educated workforce and that improvements secured by DFID technical support would have an ‘amplifying effect’ to DFID budgetary support and the much larger GoI and World Bank investments. This logic, and the proposition that DFID’s investment in RMSA still holds true.

DFID’s value for money metrics are based around 3 core parameters: Effectiveness, Efficiency and Economy. Progress on VfM metrics for RMSA are detailed in the table below.

Effectiveness	2012/13	2013/14	2014/15
1.1 Gross Enrolment Rate (GER)[1]	68.1%	76.6%
Effectiveness: Greater numbers of students are accessing secondary education. The GER shows a positive trend. Actual enrolment at 37.3 million in 2013-14 has exceeded the milestone (set at 35.5 million for the year). Enrolment in the government and aided schools (included within the RMSA programme) have gone up by some 2.9 million (9.4%) over this period due to expansion of schools and additional classrooms under RMSA.
1.2 Grade 10 State Board Pass rate1	80%	80%
The State board pass out rate gives some measure of conversion of resources to learning – however caution in over interpretation required for two reasons: (i) grade inflation (ii) the pressures of showing a high pass rate are causing some schools to prevent those deemed unlikely to pass from sitting the exam. As from 2015 the NAS survey for class X development of which has been strongly supported by DFID will give a more effective measure of learning performance.

Efficiency
2.1 Ratio of Qualified to Unqualified teachers1 / Percentage of qualified teachers1	2.3:1 / 69.4%	2.4:1 / 70.8%
While RMSA does not support pre-service teacher education it is financing in-service training. In a small number of cases this provision qualifies teachers; however, the majority of teachers get trained but do not become qualified.
2.2 Pupil to Qualified teacher ratio disaggregated by subject1
Language	108	90
Mathematics	90	82
Science	98	89
Social Studies	146	122
This indicator shows that in all core subject areas the number of students per teacher is falling. Since there are more students in the system and more teachers are qualified, this shows a positive improvement in students’ access to learning. National averages however hide acute geographic shortages and the overall task of raising the effectiveness of teachers’ remains.
2.3 / Cumulative physical achievement for civil works		29%[2]
The majority of civil works were sanctioned during the first 3 years of RMSA. Due to the backlog of incomplete civil works created, the MHRD decided not to sanction any additional civil works in 2012/13. Since then, requests have only been sanctioned for states which have demonstrated progress in completing existing projects.
Economy
3.1 Teacher cost as % of RMSA non-recurring expenditure		65.8%[3]
This figure is encouraging as it shows that over a third of the non-recurring budget is being used to support schools through a combination of quality and equity interventions and education management. The rigid norm based approach used to administer RMSA funding applications impedes spending outside defined categories – and is particularly significant for learning focused initiatives. This is a recurrent theme in the JRM dialogue. TCA is working on the finessing of the annual workplan and budget process to secure a balance between flexibility to state needs and the needs of the centre for clarity and a unit cost based approach.
3.2 Ratio of average government school teacher salary to GDP per capita for selected states
Assam (North East State)	N/A	4.6	4.6
Bihar (Plains state)	N/A	4.2	4.3
Odisha (Coastal state)	N/A	2.3	2.3
States are able to use their own norms for teacher salaries and terms and conditions. There is a large range in pay rates both across Indian states but also between different types of contract within states. The global average for this indicator is between 3 to 3.5 thus India has states that both exceed and fall below the international rate.
3.3 Unit cost of classroom construction for selected states[4]	In lakhs
Assam (North East State)	N/A	7	7
Bihar (Plains state)	5.63[5]	N/A	N/A
Odisha (Coastal state)	N/A	9.71	10.5
One of the reasons for the backlog in civil works was the low national norm (based on a GoI PWD norm that has not been revised for many years) for civil works used by MHRD for approvals. Since 2013/14 the states have been able to apply the State Schedule of Rates for civil works. These reflect the very different costs for building dependent on topography, earthquake risk and level of remoteness found across India.
[1] Source: UDISE
[2] Source: MHRD website – figure as of 31 March 2014
[3] Source: 4th RMSA JRM Aide Memoire – source quoted as MHRD IUFR
[4] Source: state AWP&Bs
[5] Source: Bihar RMSA – this figure was used for the last request in 2011-12 – since then no further request has been made

Assessment of whether the programme continues to represent value for money

RMSA is adjudged as continuing to represent value for money. Even small improvements secured by DFID technical support impact across the much larger combined investment of DPs and GoI.

Important systems improvements are being made. For example DFID’s TCA has been instrumental in promoting better use of data and a growing outcome orientation of the RMSA programme. As the 4th JRM notes “The mission was impressed by the RMSA’s efforts to move beyond extractive data collection to encouraging the sharing and use of data so as to promote ‘planning as participation.” DFID TC support to the new integrated data base – UDISE has been particularly important. “Recognition of UDISE as the official database, as recommended in previous two JRMs, is an important step towards better reporting and reduction in data discrepancy for the purposes of programme monitoring. The UDISE is also now regarded as the main data source for development of AWP&Bs which is helpful for the PAB decisions.” Such advances form the foundation for greater scrutiny of value for money, as well as needs based and performance related budgeting.

While efficiency gains are being secured by the DFID’s technical support and are recognised by the JRM there impact may take some time to play out in national data which aggregates across 36 states each of which is reforming at varying pace.

Quality of financial management

DP support to RMSA is informed by clear financial and procurement agreed by MHRD. DP monitoring and support in these areas has resulted in an improved FRM score. Many States have introduced e-procurement systems and are uploading their procurement plans on the official State RMSA website; Electronic accounting software (TALLY) is used in most states for financial management.

FA funds: The Programme expenditure and accounting follows the MHRD Financial Management and Procurement Manual (FMPM). This has been prepared in consultation with states and the World Bank and covers procedures for planning/budgeting, funds flow, accounting and internal controls, staffing and capacity building, and audit.

Development partners (DP) only reimburse expenditure deemed compliant with the FMPM guidelines. DPs jointly monitor RMSA’ s financial management systems based on the review of GoI’s Financial Management Reports (FMRs), Audit Reports, JRM documentation, Institute of Public Auditors of India (IPAI) reports on concurrent reviews, manual and GoI’s external website. DFID additionally undertakes financial risk assessment as per internal guidance.

Efforts to further strengthen financial management are ongoing. During 2013-14, MHRD conducted six regional workshops covering 22 states on financial management. In addition, MHRD held quarterly review meetings on RMSA expenditure for state financial controllers. The 4th JRM (August 2014) and DFID’s Financial Risk Assessment Annual Statement of Progress (EDRM 4687616) advises particular attention be paid to enhancing internal audit and Central Plan Scheme Monitoring System. The 4th JRM also advises attention to reconciliation of statements based on audited vs unaudited expenditure in annual financial statements. Progress on this will be reviewed in the 5th JRM.

TC funds: DFID’s contracted Technical Cooperation Agency (TCA) prepares an annual work plan and budget which is agreed with DFID India.  This is then placed before the MHRD convened Programme Steering Committee for approval prior to implementation.

TCA payments are linked to milestones and are reimbursed against invoices (with necessary documentation) and evidence of satisfactory delivery. The contractors are required to maintain supporting vouchers and other documentation for claims made under their contract along with an asset register. DFID retains a right to examine these at any point without prior warning.

TCA progress is monitored through milestone and quarterly progress reports provided by the contractor. TCA performance is also discussed in the Joint Review Mission.

Component No.	Output no and name	Budget £ (13-14)	Spend (till March 14 end)	Date last f/n report	Date audit*
201388-102 / TA	Mott: Capacity Building Support to Government of India’s Rashtriya Madhyamik Shiksha Abhiyan	6,230,000	4,339,176	N/A	N/A
201388-102 / FA	GoI: Financial Transfer for National Secondary Education Programme	20,000,000	20,000,000	June 2013 (for 2012-13 expenditure)	July 2014

E: RISK (½ page)

Overall risk rating:

Medium: The risk rating remains unchanged. Key risks centre on human and institutional capacity; shortage / retention of competent staff is a challenge. Institutional inertia is also a risk. The new government is focused on generating administrative dynamism and more consultative processes but it is too early to assess impact of this.

Overview of programme risk
The annual statement of progress (ASP) for FRA was conducted in February 2014 to assess management of the identified fiduciary risks and safeguards and identify any new fiduciary or corruption risks. This included review of progress against the 8 good practices principles and 15 benchmarks. The ASP rated 9 out of 15 benchmarks as high or substantial, an improvement over the FRA of 2010, which had rated 11 out of 15 benchmarks as high or substantial risk.
Current level of fiduciary risk (L, M, S, H)	Overall assessment of corruption risk (L, M,S, H)	Comparison to previous FRA/ASP (Improving, Stable or Worsening)
S	S	Improving (EDRM 4687616)

A set of initiatives have been taken by MHRD to improve public financial management, strengthen monitoring and supervision, capacity development and improved management information system for the programme. This includes sharing indicative budgets with States, completing PABs in time resulting in timely release and utilisation of funds, increasing outlay from 2% to 4% for states to meet operational costs for recruitment and training, appointment of third party monitoring institutes and creation of an integrated MIS. DFID’s TCA has been an effective resource for MHRD for RMSA implementation and is being increasingly drawn for additional and other emerging priorities.

Outstanding actions from risk assessment

Continued monitoring. Any required follow up actions on budgetary support elements of RMSA to be addressed through the World Bank (as DP lead on FRM) and the JRM process.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The commercial contractor, Cambridge Education (Mott MacDonald) has consistently scored in excess of 90% in DFID’s commercial performance review denoting an outstanding delivery partner. The TCA team has a proven reputation for quality and on time delivery.

Performance of partnership(s)

The Cambridge team has earned respect from government, World Bank and DFID. It fully meets its role as a service partner to all those engaged in the delivery of RMSA.

Asset monitoring and control

‘In accordance with DFID guidelines on the Procurement of Goods & Equipment, TCA keep a Fixed Asset Register as an inventory of all project goods and equipment which are procured through the project funds. The Register is updated monthly.

For all assets costing over Rs. 5,000, three quotations are called and a timeframe given to vendors to submit. The quotations will be judged by the respective TCA office requiring the items. A vendor is then recommended based on cost, quality, reputation and availability. The quotations and the recommended vendor are checked by the Operations Manager and the finance team before issuing a work order.

No project assets have been written off to date, however in the case that this happens; this will be reported to DFID as necessary and noted in the Asset Register. The need for re-purchase of assets will be assessed on a case by case basis and agreed between DFID and TCA as necessary.’

The last asset inventory was conducted in January 2014 (EDRM 4342082). At the end of the project, the depreciation is completed and the assets disposed of in line with the DFID Fixed Asset Guidance and in discussion with DFID.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

DFIDs four Partnership Principles (PPs) are not specifically detailed in the formal agreement of DP support to GoI’s RMSA programme. However the articulation of DFID support to RMSA both imbue these principles and support broader goals as detailed below:

  1. A commitment to reducing poverty and achieving the Millennium Development Goals (MDGs): The manifesto of the newly elected GoI states “…education is the most powerful tool for the advancement of the nation and the most potent weapon to fight poverty…” It has committed to increase education spending to 6% of GDP.

  1. A commitment to respecting human rights and other international obligations: The joint review missions of RMSA demonstrate a commitment to equality in school access and more recently in learning for all India’s children. Strengthened education can expand life chances, challenges gender, caste and religious  discrimination and equips future generations for sustainable development.

  1. A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption: Partner government has established appropriate systems and procedures for strengthening public financial management and safeguards against corruption. These include mandatory use of financial management and procurement manual for all programme expenditure,  confirmation/certification by annual audit reports of all agencies and states, six-monthly JRMs, third party review by monitoring institutes, use of NIC platform for e-procurement by all states, positioning vigilance officers, Right to Information compliant and Comptroller and Auditors Report on education tabled to the Indian Parliament.

  1. A commitment to strengthening domestic accountability: The Ministry of Human Resource Development is one of the leading ministries in using the web to put policy documents, minutes, monitoring reports and JRM aide memoires into the public domain rmsaindia.org/en/contacts/mhrd-rmsa.html

H: MONITORING & EVALUATION (½ page)

Evaluation: Monitoring progress throughout the review period

The RMSA programme is subject to three levels of evaluation. Firstly through the joint review mission process. This involves two weeks mission twice a year. One field based and one desk based from Delhi. The findings of each review mission are written up in an aide memoire, shared by the Education Secretary with senior State officials and lodged in the public domain on an MHRD website. Recommendations listed in each JRM are followed up in subsequent missions. A summary of key principles under which detailed recommendations were grouped from the latest (August 2014) RMSA JRM aide memoire is provided below:

- Evidence Should Guide Action: Increasing evidence enables more context specific and tailored responses – but also requires more rigorous quality assurance and verification mechanisms:
- Greater collaboration across the delivery structures could both enhance strategic planning and help address human and financial resources shortages: MHRD lead by example and use its convening power at state level to initiate collaboration, exploit synergies, achieve economies of scale and deliver collective strategic planning.
- Data/ information that is publically available and is presented in ways that are easily understood is more likely to be used:
- State short and medium term planning needs strengthening – this can be promoted by MHRD through the AWPB process:
- RMSA should encourage greater use of ICT to accelerate RMSA implementation. ICT has much to offer across: participatory planning, financial management and teacher, administrator and student education.
- RMSA must urgently address the speed with which funds disbursed are converted to expenditure which benefits students.

A second source of insight is provided by the programme evaluation conducted by the consultants. This seeks to measure the impact of TCA activities and accountability against state outcomes and milestones with the purpose to guide programme implementation and course correction. The TCA unit follows a mixed-methods evaluation including individual reflections, developmental evaluation, process validation study, performance measurement studies and case studies.
In addition to the above, DFID India’s monitoring and evaluation team has commissioned an evaluation of the impact of technical cooperation across DFID’s education portfolio. This will begin in November 2014. RMSA TCA unit will be an element of this study.

Evidence:

DFID’s TCA has a role in commissioning and disseminating research to inform the planning and implementation of secondary education. This includes work on conducting, disseminating and using data from the National Achievement Surveys and research on current RMSA funding norms and their implications for equity, efficiency and effectiveness. Findings are intended to inform revision and development of RMSA guidelines.

The following studies are in process by the TCA using primary and secondary data sources:

Study area	First draft deadline
Limits to the expansion of secondary education based on current financial norms	25th December 2014
Growth of secondary education and its implication on equity, efficiency and effectiveness	27th February 2015
A GIS review of school distance norms	8th May 2015
A review of current processes in determining upgrading / locating new secondary schools and there resourcing implications	19th June 2015
Survey to determine: / Effects of school factors on student outcome / Factors contributing to school choice and participation decisions at the secondary level	25th September 2015
	18th December 2015

Additionally, TCA is also supporting NCERT’s initiative to strengthen research capacity in the North Eastern Region.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the Logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the Logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the Logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against VfM measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process