Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Reducing Maternal and Neonatal Deaths in Kenya
Programme Value: £75.3m		Review Date: September 2014
Programme Code: 202549	Start Date: 14/11/2013	End Date: 30/06/2019

Summary of Programme Performance
Year	2013/2014
Programme Score	B
Risk Rating	Medium

Summary of progress and lessons learnt

There has been progress in establishing a solid foundation for the programme. UNICEF has set up programme governance structures, facilitated county health planning processes in five counties (three more than planned in the original business case), conducted facility assessments in these counties and identified potential centres of excellence for Basic and Comprehensive Emergency Obstetric and Neonatal Care (BEmONC and CEmONC), and procured equipment based on these assessments. Liverpool School of Tropical Medicine (LSTM) has started to implement programme scale up which includes baseline facility assessments, facility improvement, training in EmONC, quality improvement and Monitoring and Evaluation (M&E). However, limited progress has been made towards milestones for Year 1. Key issues include:
- Slower programme start-up than anticipated. The programme was approved in November 2013. UNICEF was contracted in December 2013 but due to development of its new country programme and staff restructuring was unable to start recruiting field staff until mid-2014; contracting of local implementing partners has taken longer than expected, in part because of the time required for due diligence. And LSTM was contracted in April 2014 and has trained relatively few health workers to date. There have been delays in contracting the service provider for Bungoma and the Innovation Fund; this is expected to be finalised by November 2014.
- Expanded programme scope. The scope has expanded to include an additional three counties to receive UNICEF support. This was approved by the DFID Kenya Head of Office in May 2014.
- Capacity of county health services to meet increased demand for maternal health care. UNICEF support for community activities is likely to increase demand for services which are already experiencing difficulties in meeting existing increases in demand resulting from the elimination of fees for maternal health care. If services are unable to meet demand or provide quality care, this could undermine efforts to promote uptake of maternal health care.
- Implications of Government of Kenya commitment to free maternal health care in public facilities. The programme design envisaged a voucher scheme targeting the poorest women. This may no longer be relevant. However, some counties need support to put in place county and facility systems to claim reimbursement from national Ministry of Health.
- Implications of the deteriorating security situation for implementation and costs. Conflict in programme counties, for example, Turkana, could limit access. Security concerns in North Eastern and Coast have required LSTM to relocate trainings to different venues and this has increased costs.
- Innovative approaches and operations research. Testing of innovative approaches has not yet started. Some operations research has commenced; other studies are planned.
- Integration of health and nutrition through DFID programmes. DFID is also funding a nutrition programme, which covers some of the same counties as the maternal and neonatal health programme. UNICEF reports that planning, bottleneck analysis and community level engagement are being undertaken jointly. The potential for more integrated approaches in other areas, such as budgeting and data management at the health facility should be explored.

Key lessons include: The expectation that partners would be able to start implementation quickly was over-optimistic; more time has been required for procurement, due diligence, contract negotiation, staff recruitment, assessment and planning than anticipated.
A. Introduction and Context

Dev Tracker Link to Business Case:	QUEST: 4264533
DevTracker Link to Log frame:	QUEST: 4264580

Outline of the programme

Kenya has one of the highest rates of maternal deaths in the world, at 360 per 100,000 live births (WHO, 2013), and there has been little progress in the last decade. Although deaths in young children have declined since 2003, newborn death has not. High death rates are due to poor access to quality delivery and emergency obstetric and neonatal care (EmONC) and low use of available services. Health system challenges include shortages of skilled health workers, equipment and supplies, and weak referral systems. Financial, cultural and geographical barriers also prevent women from using maternal health care services. Devolution of funds and functions to 47 newly-created counties following the 2013 election presents opportunities to improve maternal health services but also challenges, particularly in new counties with limited capacity, poor infrastructure and shortages of health workers.

Under the Reducing Maternal and Neonatal Deaths in Kenya programme, the UK is providing support in a number of ways. Through LSTM to scale up training for all maternity care providers (doctors, nurses, midwives and clinical officers) in EmONC in 32 counties in order to achieve national coverage; through UNICEF to five counties (Homa Bay, Garissa, Kakamega, Nairobi and Turkana) and a separate service provider to one county (Bungoma) to build local government capacity to plan, manage and deliver maternal and newborn health services, strengthen referral and accountability and increase community demand for and uptake of maternal health services; through UNICEF to continue technical assistance for health systems strengthening for the national Ministry of Health; and through the service provider for Bungoma to manage an Innovation Fund that will support testing of innovative approaches in all six programme counties. The other component is evaluation with three retrospective studies planned to assess the impact of the programme.

The business case envisaged health systems strengthening and demand-side support to three counties (Homa Bay, Bungoma and Turkana). In May 2014, the DFID Kenya Head of Office approved an increase in the geographical scope of the programme to include three more counties (Garissa, Kakamega and Nairobi [two peri-urban sub-counties]) and an additional commitment, within the overall programme budget, to UNICEF of £4.5m. The rationale was poor maternal health indicators in Garissa and urban slums of Nairobi; and a large population in Kakamega. The expansion is also consistent with: DFID’s increasing focus on urban areas; recommendations in Save the Children’s ‘Lives on the line-an agenda for ending preventable child deaths’ 2013 report and the Independent Commission on Aid Impact(ICAI) recommendations on the 2014 report on DFID’s Contribution to the Reduction of Child Mortality in Kenya.

DFID is providing £75.3m over five years (2013-2018): £9.3m for scale up of training (note that the LSTM contract ends March 2019); £32.2m for health systems strengthening and demand-side activities implemented by UNICEF in five counties, national health systems strengthening support and overall programme oversight; and £29.3m for health systems strengthening and demand-side activities in Bungoma and the Innovation Fund. Remaining funds - £4.1m are allocated to operational research, monitoring, independent review, evaluation and contingency.

The programme is expected to contribute to the achievement of DFID Kenya’s 2011-2015 Operational Plan results, specifically its commitment to provide skilled birth attendance to an additional 15,000 women by 2015, and to DFID’s overall Business Plan commitment to support at least 2 million safe deliveries, save the lives of 50,000 women in pregnancy and childbirth, and stop 250,000 newborns from dying. The programme impact is: Reduced maternal and neonatal deaths in Kenya. It is expected to contribute to preventing 1,092 maternal deaths and 3,838 neonatal deaths by 2018.

Overall, the programme remains relevant. There is, however, a need to review the demand-side financing component (see Sections C and H), given the change in Government of Kenya policy on free maternal health care.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Milestones for six outcome indicators were expected to be reached during the first year. The first indicator focuses on the skilled birth attendant rate, the second on the number of additional births delivered by a skilled birth attendant, the third on the number of functioning health facilities able to provide CEmONC and BEmONC, the fourth on the caesarean section rate, the fifth on the obstetric case fatality rate, and the sixth on the cost per additional birth attended by a skilled birth attendant.

For the second indicator, UNICEF estimates an additional 1,681 births delivered by a skilled birth attendant in the five counties attributed to the programme during the period January-June 2014. It is too early to assess progress towards achievement of milestones for the other five indicators. Data for these indicators will be collected annually from health facility assessments and government health information systems.

Assuming implementation is accelerated in the second year, the programme should achieve its outcomes, as planned activities will increase demand, availability and quality of MNH services. Previous experience with the Making it Happen(MiH) programme shows that EmONC training can make a significant difference to the knowledge and skills of health workers, and previous UNICEF work on demand creation indicates that this can lead to increased uptake of services. However, as discussed elsewhere in this report, success is also contingent on county health services being able to ensure that adequate staff and supplies are available.

Overall output score and description

The overall programme has been scored a B. The rating takes into consideration the following factors:
The delays in programme start up and limited timeframe for implementation. The time required for partners to establish relationships, recruit staff and develop plans. The milestones were over-optimistic for some outputs. The progress that has been made in laying the foundations of the programme, which provides a sound basis for accelerated implementation in the second year. The track record of the key implementing partners in delivery of results.
For Output 1, LSTM was contracted in April 2014 and started implementing training in May 2014; consequently, the number of health workers trained has been lower than expected and follow-up mentoring and supervision and training to conduct Maternal Death Review (MDR) has not yet started. For Output 2, UNICEF has supported counties to develop county health plans in line with expected progress at this stage and some systems support has been provided; delays in contracting of the service provider to provide health systems support in Bungoma and to manage the Innovation Fund mean that these activities have not yet started. For Output 3, delays in sub-contracting local implementing partners by UNICEF and in contracting the service provider for Bungoma mean that community demand creation activities have not yet started; changes in the wider context, specifically, the Government of Kenya commitment to elimination of fees for maternal health care made since the programme was designed, have also meant that the original plans for a demand-side financing component have been put on hold.

Table 1: Summary of output performance:
Output number	Output Description	Impact Weight (%)	Output Performance
1	Health workers in five provinces (32 counties) have the knowledge and skills to provide quality delivery care	30%	Outputs substantially did not meet expectation (C)
2	Health systems strengthened to manage and deliver maternal and newborn health services in Homa Bay, Bungoma and Turkana	50%	Outputs moderately did not meet expectation (B)
3	Increased demand for maternal health services in Homa Bay, Bungoma and Turkana counties	20%	Outputs substantially did not meet expectation (C)

Key lessons
1. The programme was designed prior to the national election, before the Government’s announcement of the elimination of fees for maternal health care in the public sector. Although the impact of wider reform following the election, in particular of devolution, was anticipated, the process of devolution has been challenging. Responsibility for health has been fully devolved to all counties, rather than through the 3-year transition envisaged, although responsibility for some key health system functions, for example, procurement and training, is still unclear.
2. The programme should assess in advance the ability of implementing partners to commence activities quickly; the time required for tendering, due diligence and contract negotiation should not be under-estimated.
3. In hindsight more could have been learnt from the experience of the DFID-funded Kenya Health Programme in designing ongoing provision of health systems strengthening support to national Ministry of Health.

Programme assumptions have not changed significantly. However, the assumption that county health budgets would be able to fully address supply-side issues such as staff and supplies needs to be monitored. Although most counties are receiving more funding for health, allocation of funding is an issue in some counties, and all counties have resource limitations; even those, such as Turkana, which are relatively ‘cash rich’ post-devolution, cannot cover 100% of their drug and commodity requirements.

Summary of key recommendations for the next year

Action	Timeline to 2015	Team Members Responsible
Accelerate programme implementation in order to deliver expected results	All partner contracts in place by December 2014	UNICEF/DFID
Track whether supply can meet demand for services	November – May 2015	UNICEF
Improve coordination and sharing of information between partners	From November 2014	UNICEF
Monitor the costs of training	From November 2014	LSTM
Support EmONC training for tutors in pre-service training institutions.	November – May 2015	DFID/LSTM
Develop national Ministry of Health and county-specific health system strengthening plans	From November 2014	UNICEF
Redesign the demand-side financing component	Jan – March 2015	Snr Health Adviser and Reproductive Health Adviser with UNICEF and Service provider
Focus on improving the functionality rather than the number of community units	From November 2014	UNICEF/Service provider for Bungoma
Support strengthening accountability at county level	Immediately	UNICEF/Service provider for Bungoma

Improve programme management and reporting	Immediately	UNICEF/DFID Snr Programme Manager
Design and implement pilot and operations research studies/ UNICEF to develop an overarching operations research and evaluation plan	December 2014	All Implementing partners

Has the logframe been updated since the last review? The logframe has not been updated since approval of changes in the programme scope. The logframe should be revised to: include the three additional counties as appropriate in Outputs 2 and 3 and in outcome indicators; reflect the revised approach to the demand-side financing component; and address gaps in baselines and milestones.
## C: DETAILED OUTPUT SCORING

Output Title	Health workers in 32 counties have the knowledge and skills to provide quality delivery care
Output number per LF		1	Output Score	C
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones target	Progress
1.1 Number of additional health workers trained in EmONC (disaggregated by sex[1])	3,000	As of September 2014, 538 health workers trained. Score: C
1.2 Average number of hours of mentoring follow up supervision received in last 12 months	2	No follow up yet provided; training only recently conducted. Score: C
1.3 % of facilities conducting Maternal Death Review(MDR) in past 12 months (i) submitted complete monthly reports (ii) made adequate adjustments to service provision and/or management practices based on evidence	(i) 10% (ii) 5%	No data on % of facilities conducting MDR submitting complete reports or adjusting service provision or practices. However, activities have been implemented. Score: C
[1] Disaggregated data by sex will be reported in the next annual review.

Key Points

Output indicator 1.1:

- There has been limited progress towards the milestones for health worker training and follow up. LSTM’s contract only started in April 2014 and time was required to recruit staff and develop training scale up plans. LSTM plans to train a further 896 health workers by the end of March 2015. It is anticipated that there will be significant scale up in the second year and, based on MiH experience, this component is expected to get back on track.
- Training plans should prioritise counties targeted for health system strengthening and demand side support from the programme. This output focuses on national scale up of training to cover the 32 counties not supported through the LSTM MiH programme. It would be helpful to ensure that all relevant health workers are trained in the six target counties so that the overall programme achieves the best possible results.
- There is a lack of accurate information about human resources for health and training needs at national and county levels. LSTM experiences, and field visits, suggest not all county health teams have accurate information about the number, type and location of health workers or about which health workers require MNH and EmONC training and which have already received training. This information will be important to avoid duplication of effort.
- Better collaboration is needed from some county reproductive health coordinators. Although coordinators are alerted about upcoming trainings, information is not always communicated by counties to participants and consequently, some selected participants do not attend.
Training costs have increased due to the deteriorating security situation in some areas of the country and mobility of health workers. The security situation in North Eastern and Coast regions has required LSTM to relocate trainings; bringing participants from further away increasing travel costs. Rotation and attrition of health workers could also mean that LSTM will need to conduct repeat trainings in counties and facilities that have already been covered.
The programme could have more sustainable impact if EmONC training were integrated into pre-service training. LSTM is in dialogue with other partners about the possibility of providing the 5-day EmONC training to MNH tutors in pre-service training institutions i.e. the 38 Kenya Medical Training Colleges and selected universities.
LSTM is generating wider benefits. LSTM notes that national coordination of EmONC training is weak and that many organisations, including NGOs, are providing training, often using different curricula and sometimes of poor quality. LSTM is mapping training organisations and providing support to NGOs to improve their planning and delivery of training.

Output indicator 1.3:
- There has been good progress with MDR activity. Some health facilities are already conducting MDR as a result of earlier support from UNICEF, LSTM and other partners for the national Maternal and Perinatal Death Surveillance and Response (MPDSR). UNICEF has also been very active on the issue of MPDSR. It will be important to ensure that UNICEF and LSTM training for health workers and reporting on indicator 1.3 is coordinated.
- Coordination between implementing partners on assessment, follow-up mentoring and supervision, and on MDR training, at county level will be critical. There appears to be limited coordination and planning of programme partner activities at county level. UNICEF and LSTM have used different tools for assessment; UNICEF is revising its assessment tool to ensure that it includes all signal functions. Both organisations need to use consistent assessment and monitoring approaches and to share findings.

Summary of responses to issues raised in previous annual reviews
Not applicable

Recommendations
- UNICEF and the Bungoma service provider should ensure that counties have accurate information about human resources for health, and provide support for effective county coordination of training.
- UNICEF, LSTM and the Bungoma service provider should jointly review training plans to ensure that EmONC training covers health workers in facilities identified as centres of excellence in the focal counties and ensure that they jointly provide follow up support to these facilities. LSTM needs to monitor the costs of training, in particular increased costs due to security concerns, and keep DFID informed about budget implications.
- DFID should consider allocation of programme funding to cover the costs of training for tutors in pre-service training institutions.
- Revise the logframe as follows: Output indicator 1.2 change to - the proportion of health facilities followed up quarterly- milestones of 50% in Year 1, 70% in Years 2 and 3 and 80% in Year 4.

## C: DETAILED OUTPUT SCORING
Output Title	Health systems strengthened to manage and deliver MNH services in Homa Bay, Bungoma and Turkana
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones target	Progress
2.1 Innovation Fund demonstrates successful new approaches to improving delivery of quality MNH services	At least one innovative project funded per county in Homa Bay, Bungoma and Turkana	No progress; Procurement process of the service provider responsible for managing the Innovation Fund to be finalised end of November 2014. Score: C
2.2 Counties have consolidated operational plans and budgets that include MNH services	County health plans include budgets for MNH	UNICEF-supported counties have health plans that include MNH budgets. No programme inputs as yet for Bungoma. Score: B
2.3 Number of management systems supported and strengthened to objective standards and implemented at county level	Three (one per county)	UNICEF has supported facility assessments in all five counties and identified centres of excellence for BEmONC and CEmONC with county health teams; systems have been established for county follow up. As yet no systems support in Bungoma pending contracting of service provider. Score: B

Key Points

Output Indicator 2.2:

Support for assessment and planning is reported to have increased county commitment to and funding allocated for MNH. In counties visited for this review, funds have been allocated to upgrade facilities and procure ambulances, and action is being taken to recruit health workers; addressing shortages of health workers will be critical to the success of the programme in specific counties, for example, Homa Bay, Turkana and Garissa. The Governors from five DFID focus counties made commitments to address maternal and newborn health in a recent national high level advocacy meeting.

Output Indicator 2.3:
- Systems’ strengthening to date has included support for evidence-based planning and production of county MNCH investment cases, facility assessments and identifying centres of excellence and their equipment needs. UNICEF helped counties to improve coordination of development partners and to engage with national Ministry of Health.
- It will be critical to ensure that health services can meet demand for MNH care. Field visits suggest that elimination of fees for maternal health care has increased demand for maternal health services and that some facilities are finding it difficult to meet this additional demand, due to lack of staff, space and supplies. Programme community activities intended to further increase demand will need to be planned and phased carefully to ensure that services have the capacity to respond. It is advisable to review the criteria for a centre of excellence. One facility identified as a centre in Turkana had inadequate staff and space to provide adequate delivery care; provision of equipment alone will not be sufficient. Facility assessments also need to consider whether a facility has the capacity to meet increased demand in future.
- Some support has been provided to national Ministry of Health. UNICEF has provided important inputs to the development of MNH and community health plans and strategies, the free maternity care policy review and the national MPDSR strategy, including conducting a recent assessment. The findings should be shared with Ministry and other partners, including LSTM.
Summary of responses to issues raised in previous annual reviews
Not applicable.

Recommendations
- UNICEF should share the findings of facility assessments with LSTM and national Ministry of Health.
- UNICEF and the service provider in Bungoma will need to monitor the balance of programme support for supply and demand-side interventions and adjust this as required.
- Specific systems strengthening plans, including planned technical assistance, need to be developed, implemented and monitored for each programme county, by UNICEF and the service provider for Bungoma. UNICEF should also build on good efforts to date to promote dialogue between county health teams and national Ministry of Health.
- Similarly, UNICEF should develop a specific plan, based on needs assessment, for systems strengthening support for MNH to the national Ministry of Health; this should build on the experience of the Kenya Health Programme.
- UNICEF should revise the title of Output 2 and indicators 2.1, 2.2 and 2.3, and related milestones and targets, to reflect the additional programme counties for DFID approval.
- UNICEF should review the criteria for a centre of excellence for BEmONC and CEmONC and review findings of the evaluation of the centre of excellence and continuum of care approach before scale up across all programme counties.

## C: DETAILED OUTPUT SCORING

Output Title	Increased demand for maternal health services in Homa Bay, Bungoma and Turkana counties
Output number per LF		3	Output Score	C
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones target	Progress
3.1 Number of poor women covered by demand-side financing (disaggregation by wealth quintile)	40,000	Development of voucher scheme originally envisaged in programme design on hold in view of GOK policy on free health care. Need for demand-side financing to be reviewed, including in light of evidence to be available shortly. Score: C
3.2 Number of community units with functioning referral systems	Homa Bay 100; Bungoma 70; Turkana 75	Number of community units has increased but difficult to attribute to the programme; extent to which units have functioning referral systems unclear. Score: B
3.3 % of women receiving at least 4 Antenatal Care(ANC) contacts during pregnancy (a) national and (b) in lowest and second lowest wealth quintiles in the three counties	(a) 52% (b) TBC	Too soon to assess programme impact on ANC. Score: C

Key Points

Output Indicator 3.1:

- Delays in start-up and contracting mean that there has been little progress with this output. Implementation of activities to increase demand for maternal health services through this programme has not started in UNICEF-supported counties; UNICEF is finalising contracts with local implementing partners. DFID is finalising contracting of the service provider for Bungoma.
- Government of Kenya commitment to free maternal health care in public facilities has implications for the demand-side financing component of the programme. Demand side financing may no longer be relevant, given the change in government policy. However, some counties require support to put in place county and facility systems to claim reimbursement from national Ministry of Health. In counties where a significant proportion of health care is delivered by non-government providers, many women will not have access to free care until the government extends its policy to include these facilities. In addition, in some counties, incentives may still be required to encourage women to come to facilities for antenatal and delivery care. Further discussion of possible options is needed; this should consider evidence that will be available soon (see Section H).

Output Indicator 3.2:

- Health facilities report increased demand for institutional delivery but this cannot necessarily be attributed to the programme. The programme will need to find a way to distinguish additional uptake of skilled delivery resulting from programme demand-creation activities from additional uptake resulting from free provision of services.
- Better information is required about the role, functionality and costs of community units. In some counties, community units have already been established. The programme aims to increase the number of units to meet national standards and ensure they have effective referral systems in place. County baseline information is available on the number of community units, but the extent to which these units are functional is not clear.
- Strengthening accountability should be an important element of demand-side activities. In principle, community units include community and facility health committee representatives and accountability is one of their functions. This aspect has received limited attention to date, but UNICEF envisages that the roll out of the Community Scorecard and strengthening of the Community Dialogue approach will enhance accountability mechanisms and community engagement in MNH.

Summary of responses to issues raised in previous annual reviews
Not applicable.

Recommendations
- UNICEF, in consultation with DFID, needs to redesign the demand-side financing component and identify options to be tested. This should involve review of upcoming evidence and dialogue with other key partners including the Ministry of Health, WHO and the World Bank.
- UNICEF should revise the title of Output 3 and indicators 3.2 and 3.3, and related milestones and targets, to reflect the additional programme counties and agree revisions with DFID; and similarly revise indicator 3.1 to reflect redesign of the demand-side financing component.
- The review recommends elevating the ANC output indicator 3.3 to the outcome level, considering there are several output indicators that contribute to achieving this indicator.
- UNICEF and the service provider for Bungoma should focus on strengthening the functionality of community units linked to centre of excellence facilities, rather than achieving an increase in the absolute number of units, collect baseline information about the functionality of these community units, develop a plan to improve the functionality of referral systems and monitor progress.
- UNICEF and the service provider for Bungoma should provide support to county health teams and community units to establish and use effective accountability mechanisms and ensure that community demand creation activities include promoting awareness of these mechanisms and how to use them to register complaints and seek redress. Leadership, management and governance capacity development for county health teams should include accountability.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

As this programme has only been established for one year and some activities have not got underway, the VfM assessment focuses on economy measures and an assessment of the suitability of indicators of efficiency and effectiveness.

Key cost drivers and performance

Cost analysis: Both UNICEF and LSTM highlight staff and office costs (16% of LSTM budget), and the cost of training (27% of LSTM budget) as among their biggest costs. Equipment and supplies accounts for the largest cost item, 29% for LSTM and 36% for UNICEF. Training venues, transport and commodities are listed as the most variable costs in the programme and are driven by market price changes, security and geography. Both partners report procurement strategies as their main tool for managing key costs. Examples include careful planning of supply needs, detailed negotiation, bulk purchasing and coordination with other partners.

Partner actions to maximise VfM: UNICEF’s actions focus on procurement and contract management. UNICEF pursues bulk procurement when possible, ensuring appropriate quality and negotiates purchase and freight costs. They also conduct independent reviews of contract budgets and spot checks. LSTM are managing costs of providing training by employing trainers from within the same region as that in which training is taking place and by utilising training institutions rather than costly hotels. LSTM have outsourced the printing of training manuals, with an estimated saving of £235 per training session (56%). They are also considering use of a training of trainers (TOT) approach. (More details in the annex).

VfM performance compared to VfM proposition in the Business Case

Cost Effectiveness: The business case notes that the programme represents very good VfM compared to international benchmarks and is expected to save about 650,000 DALYs at a unit cost of just over £100 by 2022. However, it acknowledges that the calculations to determine this number are ‘simplistic and uncertain’, as costs are subject to change and benefits are dependent on parameters that are difficult to influence. There is a substantial amount of scope for VfM to deteriorate without the programme ceasing to represent VfM when compared to international standards. As the programme is only a year old it is not possible to compare unit costs per DALY.

Assessment of whether the programme continues to represent VfM

This programme continues to represent VfM. Progress in establishing the foundation of the programme, by both partners, is regarded as acceptable, though slower than planned. As a result it is essential that the recommendations of this annual review are implemented. Programme start-up has been slower than anticipated for a variety of reasons, as noted above. Consequently limited progress has been made towards milestones for Year 1.
At this early stage in the programme the theory of change remains valid. However, it is essential that this is appraised as the programme progresses and any necessary alterations are made. Risks for the programme have increased, but remain within manageable levels. It is essential that risks are closely monitored by partners in the next year. DFID must be alerted to any changes/ consulted on mitigation.

VfM practices appear to be adequate, but the partners should work to improve efficiency, for example through training of trainers, or bundling activities to minimise transport and security costs.
VfM measures were agreed with UNICEF in a meeting in June 2014. These are (i) Cost per percentage point difference in skilled birth attendance each year and by the end of the programme and (ii) Cost per maternal death averted over the four-year period. These measures remain adequate, though no data has been reported against these yet.

Quality of financial management

Both UNICEF and LSTM have effective financial management systems and procedures in place. Narrative and financial reporting requirements have been met by both organisations. However, financial reporting could be improved. Current reporting does not provide information about expenditure against budget line items by activity, particular in the case of UNICEF. It is also difficult to see how much funding is going directly to counties and what this is being spent on. Given the delayed start to implementation, DFID will review financial forecasts with both UNICEF and LSTM to determine whether or not these need to be revised. Financial forecasts for the service provider for Bungoma will also be reviewed once the contract is finalised. The following table shows funds disbursed to date.

Implementing partner	Total budget £	Year 1 budget £	Funds disbursed by DFID as of September 2014 £	Balance £
LSTM	9,318,000	2,776,440	441,991	8,876,009
UNICEF	21,058,796	4,532,616 - year 1 / 2,000,000 - – inception phase / Total-6,532,616	4,461,557	16,597,239
Service provider for Bungoma/Innovation Fund	20,146,294	-	-	20,146,294

Date of last narrative financial report	31/07/2014
Date of last audited annual statement	Not applicable - the programme has not completed one year

E: RISK

Overall risk rating: Medium
The overall risk rating is unchanged.

Overview of programme risks
As required, UNICEF and LSTM have separate risk matrices and systems for monitoring risk in place.

- Changes in the risk context: The risks associated with conflict and insecurity remain high; there are challenges in accessing some areas of Turkana and urban informal settlements in Nairobi, and the security situation in areas of the former Coast and North Eastern provinces has deteriorated, increasing costs associated with training. The Government of Kenya has allocated funds to reimburse counties for free provision of maternal health care. However, not all counties and health facilities have systems to facilitate reimbursement, and the policy only covers government facilities.
- Key risks affecting successful delivery of results: Two key risks affecting capacity to deliver quality maternal and neonatal services are continued shortages of health workers and availability of drugs and supplies. Programme counties are currently recruiting health workers, but attracting and retaining staff is likely to remain a challenge, particularly in Turkana and Garissa. In one faith-based facility visited in Turkana, for example, all nurses (except one) are on short-term contracts funded by development partners. Rotation of health workers is also a challenge for training and follow up. Current uncertainty about where responsibility for procurement resides could undermine availability of drugs and supplies for MNH care. A strike by health workers earlier this year was not anticipated; future industrial action could undermine availability of services and achievement of results.
- New mitigating actions needed: Implementing partners need to develop a clear plan to accelerate implementation, to ensure that the programme delivers and the impact of delays in start-up is minimised. UNICEF and the service provider for Bungoma will need to monitor factors affecting the supply of MNH services and, where necessary, provide support for counties to ensure that staff, drugs and supplies are available. Continued monitoring of the security situation and the impact of this on implementation and costs will be required.
- Additional checks and controls needed: UNICEF will need to monitor closely the use of funds at county level for activities such as renovations, equipment repair, and costs associated with training for community units and community health volunteers.

Outstanding actions from risk assessment
There are no outstanding actions from the risk assessment or due diligence of UNICEF or LSTM. UNICEF has conducted due diligence through micro-assessments of partners that will receive programme funding (sub-contractors and county governments).

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Delivery against the programme timeframe is off track. The procurement of two contracts (LSTM and the service provider for Bungoma and the Innovation Fund) has taken longer than anticipated. This led to delays in start-up of some programme activities, specifically EmONC training, health systems strengthening support in Bungoma County and the launch of the Innovation Fund. UNICEF has also taken longer than anticipated to commence activities, for a number of reasons. The programme start date coincided with development of the new UNICEF country programme and restructuring of staff; consequently, recruitment of programme staff did not begin until mid-2014 and some field staff are only now taking up their positions. It also took longer than anticipated for UNICEF to contract local implementing partners, in part due to due diligence processes, and due to delay in undertaking activities at the county level. Delays in contracting and commencing activities have affected projected spending. This said, the foundations for the programme are in place and it is expected that the pace of implementation can and will be accelerated in 2015, in order to get the programme back on track.

Performance of partnership(s)
UNICEF and LSTM have developed a good working relationship. Both already had effective partnerships with the Ministry of Health; feedback from the Ministry is positive. UNICEF has set up national programme steering and technical committees, with representation of government, implementing partners and DFID. It is too soon to assess partnerships between UNICEF and its sub-contractors, although previous partnerships with these sub-contractors have worked well; however, some concerns were raised about the time that contract negotiation has taken and reduced scope of activities. DFID is seen as an effective and supportive partner by the key stakeholders.
Partnerships could be strengthened as follows:

- Although UNICEF has terms of reference for its oversight role, there is a need to clarify and agree this role with DFID and implementing partners. UNICEF should ensure field staff have specific responsibilities for the programme; ideally this should be one individual in each field office who should have a clear terms of reference.
- A system should be established to share programme reports, assessments and other documents between implementing partners as well as with government officials as appropriate.
- Implementing partners need to improve the quality of progress reporting, in particular to include clear reporting on progress towards milestones and targets for each outcome and output indicator and to provide more detailed information about programme implementation.

Asset monitoring and control

Assets financed by this programme include equipment for health facilities procured by UNICEF, and training equipment procured centrally by LSTM. Neither UNICEF nor LSTM use the DFID asset register template, but both have systems in place to record and monitor assets. UNICEF maintains a computerised record of all items procured and conducts regular spot checks to ensure equipment is in situ; LSTM also maintains an asset register. LSTM has added a session on care of equipment to trainings, and a written agreement contract for partners when borrowing equipment, to improve the management and, hence, the longevity of equipment. The review concludes that DFID Kenya can be confident that assets will be well managed. DFID will work with partners to ensure that assets procured have UKAID branding in line with recent guidelines.

G: CONDITIONALITY

Update on partnership principles

Since we are not providing financial aid using Government of Kenya systems in the delivery of the Maternal and Newborn health programme, the partnership principles do not apply in the detailed management and monitoring of this programme.

H: MONITORING & EVALUATION

Evidence and evaluation
There have been no significant changes in evidence since the development of the business case, and the overall programme design and theory of change remains relevant. However, specific changes are required to the demand-side financing component of Output 3. New evidence to inform a revised approach will shortly be available from: a joint UN partner review of results-based financing; a review of the impact and costs of the free maternity services policy; and the findings of a Conditional Cash Transfer (CCT) initiative in Kakamega, which is being implemented with funding from the county government and technical assistance from UNICEF. The addition of support for EmONC training of tutors in pre-service training institutions is also recommended.

An evaluation is planned for this programme and Terms of Reference has been developed and agreed with partners. UNICEF has advertised for expressions of interest for an independent organisation to lead on this work to start in 2015. In addition to this evaluation, UNICEF and LSTM plans to oversee a number of mini-evaluations or operational research studies on specific components of the programme, to generate evidence on topics deemed important by the Government of Kenya and the international public health community. In addition, the Innovation Fund is expected to generate evidence about innovative and effective approaches.
UNICEF needs to develop an overarching operations research and evaluation plan for the programme, to ensure coherence and coordination and allow progress with different studies to be tracked. In addition, collaboration with AMREF or sharing of lessons learned should be considered, as AMREF is also piloting nomadic clinics and planning to set up mothers’ waiting shelters in Turkana, with DANIDA funding.

Monitoring progress throughout the review period

Each implementing partner maintains its own monitoring system. LSTM provides quarterly reports to UNICEF; the service provider in Bungoma will do likewise. UNICEF submits consolidated six-monthly reports to DFID. As noted earlier, UNICEF and partners need to review the overall monitoring framework to ensure that output and outcome indicators are being monitored in a coherent way by all implementing partners and that monitoring will provide the required data, including disaggregated data. In addition to support to strengthen the DHIS, UNICEF plans to support strengthening of community health information systems. It will be important to ensure that this prioritises key data points, for example, referral and maternal and perinatal deaths. As noted earlier, the balance between support for demand- and supply-side interventions will also need to be monitored carefully in view of the impact of elimination of fees for maternal health care on demand.

There needs to be further discussion between with all partners to agree additional VfM indicators and how these can be measured, and to determine the extent to which it will be possible for the DHIS and facility reporting to generate data that is disaggregated by age, sex and wealth quintile.

At this stage, it is too early to seek feedback from users of MNH services. However, field visits and LSTM feedback from health workers who have been trained through the programme are positive. There is high demand for the EmONC training and quotes from health workers who have attended trainings include: “I feel I have gained knowledge and skills not even learned in basic training”, “I realised I knew very little about emergency obstetric and neonatal care…I’m now able to resuscitate a neonate… I am also able to administer magnesium sulphate well”, “I’m a changed midwife thanks to EmONC”, and “I now have the knowledge and skills and confidence to effectively deal with obstetric complications”.

The annual review was conducted by an external consultant with inputs from DFID staff. Meetings were held in Nairobi with implementing partners, DFID staff and other key stakeholders, including the Ministry of Health, WHO and World Bank. Field visits to Turkana and Homa Bay included meetings with county health teams, UNICEF field staff and local implementing partners, hospital and health centre staff and mothers’ groups. Inputs were also provided by DFID programme staff from verification visits to Homa Bay and Kakamega. The annual review results will be shared with implementing partners.
Annex 1: Value for Money

Top actions to maximise VfM

	No.	Action
UNICEF	1	Posting the majority of programme staff and consultants in field offices to minimise travel-related expenses.
	2	Adhering to UNICEF’s rigorous supply and procurement regulations, which involves bulk procurement and negotiated purchase and freight costs and ensures high-quality products.
	3	Adhering to UNICEF’s stringent contract management requirements, which involve independent reviews of contract budgets, spot checks, regular financial management assessments, and other procedures to ensure proper financial oversight.
LSTM	1	Using training institutions for MiH activities where possible rather than costly hotels.
	2	Reduction of unnecessary expenditure by ensuring good quality equipment, stationery and other consumables are bought.
	3	Using trainers from within the same region that training activities are being conducted.

Biggest costs and drivers

Partner	Biggest costs (insert top three headings from budget template e.g. Staff, Overheads, Transport, Commodities for transfer to beneficiaries)	% Total Budget (from budget template)	Cost drivers (factors that influence the Key Costs e.g. project location, inflation)
UNICEF	Health infrastructure and supplies	36.0%	Rising costs of goods, freight and transport costs, insurance
	UNICEF staff and consultants	24.0%	Large number of highly proficient staff required due to the programme’s complexity and geographic scope
	Meetings, conferences, and training events		Remote project locations necessitate overnight stays for many meetings; government expectations of per diems and transport allowances
LSTM	Staff & office costs	16.0%	Location, qualifications, level of staff
	Equipment	29.0%	Wholesale price and cost of distribution
	EOC&NC Training events	27.0%	Project location, faculty

Variable costs and drivers

	Variable costs (costs with the greatest risk of change during the project e.g. commodities, security costs)	Cost drivers (factors that influence the Variable Costs e.g. changes in security or market demand and supply)
UNICEF	Demand-side financing	Design of the DSF scheme based on policy directives; local costs that are being covered with vouchers; audit fees
	Transport	Airline costs, fuel costs, road conditions, security
	Commodities	Commodity prices, freight charges
LSTM	Equipment	Changes in supplier prices, replacement of parts
	Training venue changes	Security issues
	Transport	Changes in prices due to change in fuel costs and or distances covered

Managing cost drivers

	Cost driver	Actions
UNICEF	Health infrastructure and supplies	Careful review of supply needs (including physical verification), bulk procurements, coordination with counties and partners to leverage other resources, use of local contractors and materials for renovations
	Meetings, conferences, training events	Use of pre-negotiated special UN prices for meeting venues, minimize meetings (combine as many as possible into single events), hold meetings as close to participants as possible, payment of transport fees and room and board but no per diems
	Demand-side financing	Delay project by 1 year and then carefully research and plan the most appropriate approach; consider replacing with another demand-generation strategy if government and partners deem this is less necessary after the free maternity services policy is in place.
LSTM	Changes in supplier prices	Building good relationships and detailed negotiations with suppliers
	Training venues	Ensuring suitable cost effective venues are used
	Transport	Negotiating with the companies on costs

3 E’s

Economy

IP	Action	Evidence	Estimated efficiency saving
UNICEF | LSTM	Use of best practice procurement processes for big ticket items.	UNICEF procures most medical supplies through UNICEF’s Supply division in Copenhagen, to take advantage of pre-negotiated prices of goods and shipping arrangements. UNICEF is relocating most equipment and medical supplies to a Kisumu-based warehouse (instead of Nairobi) to reduce storage and distribution costs.
LSTM	Joining together with other partners to procure goods and services in bulk	Equipment purchases made by LSTM in Liverpool allowing bulk buy and economies of scale savings to take place.
UNICEF	Outsourcing functions which can be done more cheaply externally	Outsourcing most UNICEF staff transport to private companies selected through competitive bidding processes and hence maintaining few office vehicles (LSTM) Outsourcing printing of training manuals for EOC trainings: 25,600 KES (GBP 178) for outsourced printing of manuals for 1 EOC training (64 participants) compared with internal cost of 59,392 KES (GBP 413).	(LSTM) GBP 235 per training (56% saving)
UNICEF	Building capacity of implementing partners in procurement	The UNICEF Health and Supply divisions work extensively with MOH supply managers to improve logistics and supply management systems.

Efficiency

IP	Action	Evidence	Estimated efficiency saving
UNICEF	Selecting the most appropriate types of inputs, balancing cost and quality	UNICEF gives careful consideration to the best sources for medical supply and equipment (eg, mostly through UNICEF Copenhagen, some through local sources) International staff are hired only when the role cannot be filled with local talent. The UNICEF MNH team will be almost entirely Kenyan.
UNICEF	Minimising training costs by using a training of trainers approach	UNICEF employs a TOT approach with most training activities.
UNICEF	Minimising costs using ICT	UNICEF is increasingly conducting staff meetings involving multiple field offices via video conference or Webex rather than in person to reduce travel costs and days away from one’s duty station.
UNICEF	Ensuring quality of Outputs through quality assurance and monitoring	UNICEF’s supply division has rigorous quality assurance practices, including sampling of products, spot checks, etc.

Effectiveness

IP	Action	Evidence	Estimated efficiency saving
	Choosing Outputs to tackle a problem in a holistic way
UNICEF	Ensuring that goods and services (including technical assistance) are targeted (geographically and/or to particular groups and institutions) where they can have most impact.	(UNICEF) The program’s demand-side financing scheme will target the most vulnerable pregnant women using established criteria (to be detailed soon)
UNICEF | LSTM	Building capacity of government to deliver services to ensure sustainability	(UNICEF) 50-60% of the MNH program budget managed by UNICEF will pass directly through the MOH, but with careful financial oversight measures. The remaining funds will go through NGOs. The proportion going to the MOH will be increased as the MOH gains management and absorptive capacity. (LSTM) Strengthening of Kenya Ministry of Health M&E systems (e.g. Maternal and Perinatal Death Surveillance and Review), Quality Improvement initiatives, training of facilitators and health care workers.
UNICEF | LSTM	Building the capacity of community groups to support services to ensure sustainability	(UNICEF) A large portion of this program is developing community health services, including community health committees and facility committees. (LSTM) Linking interested partners with Master Trainers and Ministry of Health to support government-led coordination.
UNICEF	Ensuring that activities are joined-up across Outputs	UNICEF will be implementing the MNH project concurrently with child health and other programs. As much as possible, activities will be combined or leveraged. For example, community newborn care services in Homa Bay and Turkana will be added to existing iCCM services and jointly monitored.
UNICEF | LSTM	Consulting with and influencing government and other key actors in order to maximise Outcomes	UNICEF is establishing Steering Committees in each county to ensure that the MNH program is well integrated with other programs and that all programs leverage results as much as possible. LSTM programmes delivered in partnership with Ministry of Health; key stakeholder and partner meetings held regularly.

Endnotes: