Annual Review – post April 2018

Title: / Animal Health and Veterinary Science Specialist Advice
Programme Value £ (full life): £103,540		Review Date: / 4th December 2018
Programme Code: 300361	Start Date: / 4 January 2017	End Date: / 30th September 2019

Summary of Programme Performance
Year	2017	2018
Programme Score	A	A
Risk Rating	Minor	Minor

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/14392391.odt
DevTracker Link to Log frame:	Not applicable – the programme is governed by a contract/service level agreement rather than a logframe.

A. Summary and Overview (1-2 pages)

This programme enables DFID’s Agriculture Research Team to access specialist animal health and veterinary science expertise – on a short-term and infrequent basis – to support the delivery of a portfolio of agriculture research projects with an animal health or livestock component.

The 32 month call-down contractual arrangement established under this programme provides for a maximum of two days per week of specialist technical animal health inputs to DFID advisers, Senior Responsible Owners (SROs), programme managers and senior managers. This resource enables DFID to target its investments in animal health and livestock research more effectively, and to identify and manage key technical risks robustly.

The programme contributes to an overall intended impact of developing and deploying new technologies (vaccines, diagnostics and medicines) to address livestock disease quickly and effectively. It does this by providing DFID SROs and programme managers with the technical inputs needed to manage risks and challenge implementing partners on delivery approaches and timelines.

The key outcome of this programme is more effective DFID-funded animal health research and programme delivery.

The principal output of this programme is high quality animal health and veterinary science technical support, enabling DFID to make robust and well-informed decisions relating to the programme and risk management of DFID’s animal health research programmes.

The key activities conducted during the reporting period are reported on elsewhere in this Annual Review.

Summary supporting narrative for the overall score in this review

The rapidly growing demand for livestock products (milk and meat) in developing and emerging economies is driving large-scale expansion and change in livestock production systems. This rapid expansion exposes livestock and those who work with livestock or consume meat or dairy products to outbreaks of disease. Zoonotic diseases (diseases which can be transmitted from animals to humans), such as tuberculosis, are estimated to cost more than £15 billion in direct and indirect costs annually.

Nearly 900 million people rely on livestock for their livelihoods, and livestock fulfil important economic, social and cultural roles. Livestock not only provide food, but they are often themselves a highly valuable and productive asset for poor people in developing countries. The loss of animals through disease devastates the lives of individuals, families and communities around the world.

DFID’s Agriculture Research team supports a number of animal health research programmes which aim to reduce the impact of zoonotic disease on poor communities in developing countries, while also helping to identify and halt the spread of pandemics across the globe.

Owing to the relatively limited and fluctuating requirement for deep specialist expertise in these areas, DFID does not currently retain an in-house veterinary and animal health specialist. DFID’s Livelihoods cadre does not attract applicants with specialist expertise in these areas, most likely because – given the limited number of animal health programmes – there is limited demand for specialist inputs and no career path within DFID for specialists in this field.

The development of animal therapeutics, diagnostics and vaccines is a highly complex and rapidly evolving area of science: maintaining in-house capacity to deliver specialist technical inputs in these areas would require the development of deep technical skills which would not be deployable across the rest of the organisation.

This programme addresses the need within DFID for short-term, infrequent access to specialist expertise in animal health and veterinary science. The objective of the programme is to ensure that we are able to maintain strong technical oversight of a complex and technically sophisticated portfolio of investments, at relatively low cost to DFID. Under this programme, DFID has established a call-down contractual arrangement with Livestock Incorporated Ltd., allowing DFID to access high quality technical advice, in a timely manner, to support robust project and risk management of programmes with an animal health or livestock component. By ensuring DFID has a clear understanding of the technical challenges facing its portfolio of animal health research programmes, this project enables DFID to manage and mitigate delivery and operational risks, and to challenge implementing partners on timelines and delivery, ensuring we deliver value for money.

The technical inputs provided during the reporting period have continued to be of a consistently high quality, strongly grounded in development realities. By drawing on these inputs, DFID has been able to work more effectively with key partners including the Bill & Melinda Gates Foundation (BMGF) in the area of animal health research, and has been better equipped to quickly identify and robustly manage risks on animal health and livestock research programmes. The project has successfully supported DFID’s Senior Responsible Owners (SROs) and programme managers in their management and direction of the animal health research portfolio, providing a specialist perspective on the challenges and risks facing these programmes.

This programme also strengthens DFID’s capacity to deliver on both the UK’s development commitments and the UK Government’s Animal and Plant Health Strategy, which sets out a compelling case for the UK’s role in developing integrated approaches to tackling global animal health challenges.

Recommendations for the year ahead

Recommendation #1: DFID should provide a costed extension to the existing contract to cover an additional year taking the contract to September 2020. Discussion are already underway and RED procurement specialists are supportive of this approach.

Recommendation #2: DFID should continue to use the mechanism for prioritising requests for specialist inputs where needed (for example, if there are times when demand for specialist support is particularly high), ensuring the highest priority inputs are commissioned.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	To provide specialist inputs and advice on aspects of a range of animal health research programmes.
Output number per LF		N/A	Output Score	A

Key Points

Livestock Incorporated Ltd. has delivered strongly against the contractual Terms of Reference, providing high quality and timely technical inputs in response to requests for support from DFID advisers and Senior Responsible Owners (SRO’s).

The organisation has established strong and effective working relationships with DFID technical and programme staff, and key external partners for DFID in the animal health research space, including the Bill & Melinda Gates Foundation (BMGF).

Over the reporting period, the technical inputs provided have enhanced the capacity of DFID’s Agriculture Research Team to successfully implement DFID’s animal health research programme portfolio.

The table below provides a breakdown of key inputs commissioned over the reporting period, and the impact of these inputs for DFID programme and risk management. In line with the Terms of Reference for the call-down contractual arrangement, the inputs listed reflect areas where DFID requires specialist, technical support in the area of veterinary science and animal health. Responsibility for the management and overall direction of all animal health research projects funded by DFID remains the remit of the DFID SRO, adviser and programme manager.

Lifestock Inc. Ltd Inputs and Impact Dec. 17 – Nov 18.

Inputs commissioned	Impact on DFID programme and risk management

Pastoralism in protracted crises, evidence review and scoping study, research capacity assessment, consultations with DFID country offices.	Pastoralism review paper and evidence gaps identified in support of the formulation of a draft business case for a new research initiative. / Lifestock Inc. Ltd also supported DFID to identify key research groups working in this area.
Iterative technical advice for GALVmed Veterinary Innovations Transforming Animal health and Livelihoods (VITAL) business case	Improved original Theory of Change, strengthened the overall proposal narrative by questioning technical aspects of R&D plus the roll out of commercial and marketing activities. VITAL whilst building in previous work of GALVmed proposed to formulate vaccines effective against multiple livestock diseases. The implications of this new approach have been assessed. Lifestock Inc. also supported the formulation of a draft impact assessment that will supply impact data to DFID in the longer term.
GALVmed phase III Project Completion Report. Review of documentation, technical review and advice.	GALVmed activities are broad ranging and involves a complex network of partners. DFID was better able to assess the technical achievements and outcomes of the project in advance of funding VITAL.
Relevant technical comments on GALVmed Institutional Review	Lifestock Inc. inputs helped to strengthen a key partner working on livestock health technologies and marketing.
Antimicrobial Resistance review of international conference and suggesting technical inputs	By drawing upon Lifestock Inc. development experience and technical analysis, DFID was better able to strengthen conference design and participation.
BMGF / DFID livestock research projects within collaborative agreement. / Contribute to relevant sections of the Annual Review. / Review BMGF 5-year livestock sector strategy. / African Animal Trypanosomiasis (AAT)Phase 2 supplement and Phase 3 technical review. / East Coast Fever Recombinant Vaccine Research / Bovine TB Research Ethiopia and India. / Global Burden of Animal Disease (GBAD) Initiative. Review of concept, attend inception workshop Paris, review supplementary proposal, regular consultation and technical. / discussion with implementors. / Supporting Evidence based Interventions (SEBI) and the Livestock Data for Decisions initiative (LD4D) liaison and review of data networking and management. / Centre of Tropical Livestock Genetics and Health, technical review of reports for annual review and following annual technical committee meeting.	BMGF has a large team of specialist livestock specialists. DFID does not currently have access to similar capacity in-house. The inputs of Lifestock Inc. Ltd enabled us to continue to work closely with BMGF in a number of complex technical areas. Many of these initiatives use cutting edge technologies and research protocols, the level of risk acceptable to BMGF frequently differs from risk acceptable to DFID. It is important for DFID to be able ensure that our decisions relating to the co-funding of projects with BMGF are firmly backed up by independent technical advice. / By engaging with and strengthening BMGF’s Livestock Strategy we ensure optimal support to Agriculture Research Team, RED. / African Animal Trypanosomiasis (AAT) phase two extension activities will soon reach go / no go decision points and with the support of Lifestock Inc. Ltd. DFID is in a strong position to adequately assess the risks of moving to a new phase of product development or not. AAT phase three proposed activities have now been assessed and a strategy for possible support agreed. / Both the ECF and TB research remain complex areas. The ECF research will be concluded in January 2019 and support will be needed, building on technical reviews of progress so far, to determine if further research will yield a viable product for commercialisation in the next 5-10 years. The on-going TB research has tremendous potential to support TB eradication in both the developed and developing world. By engaging with Lifestock Inc. DFID is in a stronger position to assess the progress and implications of this research. / Lifestock Inc. has maintained close contact with the development of the GBAD initiative, including its technical working groups. GBAD has potential to influence future research decisions as it provides data on the impact and costs of different diseases in a range of geographies and production systems. GBAD is complemented by the work of SEBI and the LD4D network. Through Lifestock’s engagement and advice DFID is better able to assess how to GBAD might rely on LD4D in the future. / Lifestock Inc. support enabled DFID to understand and critique the implementation plans being presented by the CTLGH project team, from a technical and delivery perspective.
Agresults Livestock related projects review and technical inputs through participation in relevant parts of steering committees and review of documentation / draft business cases. Contribute to relevant sections of the annual review.	Lifestock Inc. helped refine and improve the ongoing Brucellosis prize criteria and engage with the pilot manager. Technical rule changes to brucellosis prize were subsequently adequately assessed and commented upon. / Lifestock Inc. provided a portfolio of ideas for new livestock business cases for Agresults to consider funding. This was a two-way process and through Lifestock Inc., DFID was able to also review ideas from other Agresults donors. / With Lifestock support DFID was able help develop and number of new pilot projects ranging from poultry intensification, dairy intensification and Foot and Mouth Disease vaccine development / distribution.
Evidence review on Crimean Congo Haemorrhagic Fever	Improved RED readiness to respond to CCHF outbreaks
Miscellaneous technical requests: e.g. Comment on vaccine efficacy and impact; rinderpest eradication; vaccination technical advice for Central Africa Republic; technical advice on a proposed symposium on livestock, sanitation, hygiene, and child growth. Comment on nutrition and food safety initiatives supported by BMGF.	Independent technical advice on these various topics allowed improved informed decision making by the DFID team.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendation #1: DFID should provide a costed extension to the existing contract to cover an additional year taking the contract to September 2020. Discussion are already underway and RED procurement specialists are supportive of this approach.

Recommendation #2: DFID should continue to use the mechanism for prioritising requests for specialist inputs where needed (for example, if there are times when demand for specialist support is particularly high), ensuring the highest priority inputs are commissioned.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

Not applicable – the programme is governed by a contract/service level agreement rather than a logframe

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year

Key cost drivers and performance

The key cost driver for this project is the level of demand for call-down services from Livestock Incorporated Ltd. Of the maximum £103,540 contract limit, £73,600 has been spent to date. This represents approximately 76% of the contract value, over a time period of just under a 2 year period.

The contract arrangement is on a call-down basis, meaning DFID will only disburse funding to pay for commissioned inputs over the life of the contract. The contract has just been extended for one further year at a no cost basis. At the current spending rate, it is anticipated that spending on this project will be under budget for the original 2 year contact. There is no obligation for DFID to spend the full contract value.

VfM performance compared to the original VfM proposition in the business case

The business case for this project set out the following measures for ensuring value for money. A brief update on progress over the reporting period is included below:

1. DFID will pay for advice on a call-down basis: as noted above, the spend rate over the reporting period indicates that total spend was slightly under budget when the current call-down contract ended in September 2018. A no cost extension has been issued to Sept 2019.
2. The DFID SRO will monitor the quality of support provided by Livestock Incorporated Ltd: as part of this Annual Review process, the SRO sought feedback from the advisers and SROs in the Agriculture Research team who have made use of support from Livestock Incorporated Ltd during the reporting period. This feedback is reported under the output scoring section of this Annual Review, and illustrates the high quality and valuable support provided by this project over the reporting period.
3. Invoices are be checked by DFID on receipt to ensure rigorous financial management: The management team implement a contract oversight process involving 3 month rolling workplans and the issuing of reference numbers to the call-down specialist and to commissioning SROs within the Agriculture Research team. This mechanism continues to work well and provides a highly transparent audit trail of technical support commissioned and received.

Assessment of whether the programme continues to represent value for money

The table below assesses the project against the ‘4 E’ framework, and presents an overall conclusion on the value for money of the programme during the reporting period:

4 Es	Summary of performance
Economy	The project has been strongly economical for DFID over the reporting period. Livestock Incorporated Ltd’s familiarity with DFID’s programme portfolio and administrative procedures meant that the start-up phase of the contract proceeded smoothly, with the supplier able to provide timely and high quality inputs from the outset (rather than requiring a familiarisation phase to understand DFID’s procedures and technical priorities). / The day rate agreed with Livestock Incorporated Ltd prior to contract award stage was assessed as competitive by Research and Evidence Division’s Delegated Procurement Officers. The agreed day rate reflects a 20% discount on the organisation’s typical short-term consultancy rate for specialist advice. This rate has remained constant throughout the second year of the contract?
Efficiency	The project continues to perform well on efficiency measures with a rolling workplan managed by the SRO and DPM.
Effectiveness	‘Effectiveness’ in the DFID value for money framework relates to how well programme outputs achieve their desired outcomes. The programme business case outlined the intended outcome of the programme as ‘more effective DFID-funded animal health research and programme delivery’. As outlined in the output scoring section of this Annual Review, the call-down arrangement continues to allow DFID to draw on high quality technical inputs over the reporting period in support of key animal health research programmes. This support has strengthened DFID’s capacity to identify technical risks in these programmes and steer programme partners to take robust action to mitigate and manage these risks.
Equity	Owing to the nature of this project (a call-down contract supporting broader technical work within DFID), the DFID review team concludes that equity indicators are not relevant in this case.
Overall	The DFID review team concludes that this programme continues to represent good value for money over the reporting period.

Quality of financial management
Livestock Incorporated Ltd invoices DFID on a monthly basis. Detailed time sheets are provided with invoices, which are then cross-checked against the DFID management team’s workplan records.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

DFID should continue from a VfM perspective to fund this programme. DFID’s Agriculture Research team have increased their animal health research portfolio which aim to reduce the impact of zoonotic disease on poor communities in developing countries, while also helping to identify and halt the spread of pandemics across the globe.

Owing to the relatively limited and fluctuating requirement for deep specialist expertise in these areas, DFID does not currently retain an in-house veterinary and animal health specialist and there are currently no plans to change this approach.

This programme therefore should continue from a VfM perspective and DFID should also consider a further costed extension of one year to ensure the team continue to have high quality animal health advice until September 2020.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Risk category	Gross risk description	Mitigation	Residual risk rating	Likely trajectory over the coming reporting period
Context	Owing to the relatively limited and fluctuating requirement for deep specialist expertise in these areas, DFID does not currently retain an in-house veterinary and animal health specialist. As explained elsewhere in this Annual Review, there is limited demand for specialist inputs and no career path within DFID for specialists in this field. Without access to specialist technical inputs in the areas of animal health and veterinary science, however, DFID’s capacity to manage its animal health research portfolio would be constrained.	This project addresses the need within DFID for short-term, infrequent access to specialist expertise in animal health and veterinary science. The call-down arrangement allows DFID to access high quality technical advice, in a timely manner, to support robust project and risk management of programmes with an animal health or livestock component.	Minor
Delivery	There is a risk inherent in contracting call-down specialist support that the technical inputs provided may not be of a consistently high quality.	Livestock Incorporated Ltd provides services to a range of development partners including DFID. The supplier has extensive animal health and development expertise, directly relevant to the objectives of DFID’s Agriculture Research team. Quality of inputs provided has been assessed as part of this Annual Review process, and the DFID review team has found these to be of a consistently high quality, firmly grounded in development realities.	Minor
Operational	Operational risk overlaps with context risk for this project. As noted above, DFID’s capacity to manage its animal health research portfolio would be constrained if the DFID programme team were unable to access specialist expertise in animal health and veterinary science when required.	Drawing on specialist animal health expertise when required has enhanced DFID’s capacity and capability over the reporting period. This reduces operational risks to the DFID Agriculture Research team’s overall portfolio.	Minor
Safeguarding	Given the nature of this project, safeguarding risks are not considered to be pertinent.	Not applicable.	Minor
Fiduciary	There is an inherent risk in all commissioning activity that funds are not used for the intended purposes.	Livestock Incorporated Ltd’s invoices over the reporting period have been 100% accurate. The SRO and DPM have checked each invoice against DFID’s own workplan records and have verified hours claimed with the SROs who commissioned each input.	Minor
Reputational	There is a potential reputational risk inherent in contracting specialist expertise from an external partner.	DFID’s Agriculture Research team, with the support of Research and Evidence Division’s delegated procurement officers, negotiated a competitive rate with Livestock Incorporated Ltd. Given that DFID does not currently require a full time animal health and veterinary science specialist, this project continues to represent good value for money for DFID in the current context.	Minor

Outstanding actions from risk assessment
No outstanding actions.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Delivery against planned timeframe

All technical inputs commissioned during the reporting period were delivered on time.

Performance of partnership (s)

Livestock Incorporated Ltd has established strong and effective working relationships with DFID technical and programme staff, and key external partners for DFID in animal health research, including the Bill & Melinda Gates Foundation (BMGF).

Asset monitoring and control

Not applicable – the supplier has not purchased any assets with DFID funding.

Date of last narrative financial report(s)	November 2018
Date of last audited annual statement (s)	N/A

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Evidence and evaluation

Not applicable to this project, which provides call-down technical services to DFID programme management staff.

Monitoring progress throughout the review period

Throughout the reporting period, the DFID SRO and DPM have managed a rolling workplan within the Agriculture Research team, which sets out required inputs from Livestock Incorporated Ltd. SROs and advisers within the Agriculture Research team are commissioned to update this on a monthly basis. An up to date workplan is then shared with Livestock Incorporated Ltd.

As part of this Annual Review, the SRO sought feedback from SROs and advisers who have made use of call-down support over the year. This feedback is reported in the output scoring section.

Approach to the Annual Review

This Annual Review was conducted by the DFID SRO and DPM, drawing on feedback from other SROs and advisers within the Agriculture Research team who have utilised call-down support from Livestock Incorporated Ltd over the reporting period. The SRO and DPM also reviewed the original programme Business Case, the rolling workplan, and all invoices re

Learning

Progress on recommendations from previous reviews (1/2 page)

Recommendation #1: DFID should retain the best practice contract management approach trialled during the reporting period. This provides for transparent audit trail and efficient and effective management of the call-down contract. Moving to the new reporting period, to support effective management of the programme budget, this mechanism will also be used to prioritise requests for specialist inputs where needed (for example, if there are times when demand for specialist support is particularly high), ensuring the highest priority inputs are commissioned.

Response
The programme team have continued to use the system set up in 2017 to effectively manage the call down contract. This has resulted in an underspend over the original period of the contract which has now been extended by 1 year.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided