## Logframe
LOGFRAME
PROJECT NAME | Somalia Stability Programme (SSP) | [6 empty] | Assumptions
IMPACT | Impact Indicator 1 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 (2014) | Milestone 3 | Target (2016)
Better governed and more stable Somalia | Number of regions that are part of a interim administration (federal member state) | Planned | 2.5 (Puntland: Bari, Nugal, 1/2 Mudug) | 3 New (Gedo, middle Jubba, lower Jubba) | 3 New (Bai, Bakol, Lower Shabelle) | 3.5 new (Hiran, Galgadug, 1/2 Mudug, Middle Shabelle) | 15 in total
|  | Achieved |  | 3 (Gedo, Lower Juba, Middle Juba )
Source
Mogadishu agreements recognising Federal Member States
| Impact Indicator 2 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016)
| Number of districts accessible (as measured by OCHA humanitarian access co-efficient) | Planned |  | No Target Scores required
Achieved
Source
OCHA Humanitarian Access Cooefficient reports
OUTCOME | Outcome Indicator 1 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016) | Survey respondents are informed and aware to the point that they can appraise changes in governance and conflict management
Greater number of areas of stability | Change in percepetions of legitimacy and viability of governance structures in areas in which SSP has made investments | Planned | N/A | N/A | Baseline survey conducted, federal, sub-national and district samples | N/A | Second survey conducted, federal, sub-national and district samples
Achieved
Source
Programme evaluation - perception survey
| Outcome Indicator 2 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016)
| Change in perceptions of effeciveness of conflict management in areas which SSP has made investments |  | N/A | N/A | Baseline survey conducted, federal, sub-national and district samples | N/A | Second survey conducted, federal, sub-national and district samples
Achieved
Source
Programme evaluation - perception survey
| Outcome Indicator 3 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Target (2015) | Target (2016)
| Number of communities where business can operate after dark (Proxy indicator for community/ neighbourhood security) | Planned | TBC (through survey of target areas) | Based on baseline (once defined) + no of commnities (see output 1) |  | plus 89% improvement (based on 428 additional communities benefiting from Stability projects | plus 89% improvement (based on 428 additional communities benefiting from Stability projects
Achieved
Source
Joint USAID/DFID Somalia M&E survey
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 (2014) | Milestone 3 | Target (2016) | Sufficient recognition of and political engagement with Somali Government entities
Output 1: Legitimate, viable governance structures able to make and enforce rules locally | Number of districts receiving support from SSF | Planned | 0 | All Major acceissble population centres (except Somaliland) affected by conflict | 14 new districts | 10 new districts | A total of 40 districts
|  | Achieved |  | 16 districts
Source
Stability Fund Results Framework (Contributing IPs: RDFs (Rapid Disbersal Fund Projects) , NIS, AMISOM, UNSOM, etc)
| Output Indicator 1.2 |  | Baseline (Jan 2013) | Milestone 1 | Milestone 2 | Milestone 3 | Target (2016)
| Number of governance structures supported by SSF | Planned | 0 | 53 total structures inclluding at least 3 Interim administrations/FMSs/Regional governments and at least 50 community-level structures) | 29 new structures | 15 new structures | A total of 97 structures
|  | Achieved |  | 61 total structures (1 Federal structures, 1 Federal State Structure, 3 regional level, 6 district-level structures, 49 community-level structures 1 public) |  |  |  |  | 4060 | 2500
Source
Stability Fund Results Framework (Contributing IPs: All projects)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (Jan 2011) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016)
30% | Number of people directly involved or consulted in decision making on policies and investments that affect them and their communities. | Planned | 0 | 3000 people (1800 male, 1200 female) | 1780 new people (1130 male, 650 female) | 1780 new people (1130 male, 650 female) | A total of 6560 people (4060 male, 2500 female)
|  | Achieved |  | 3,904 people (1,239 male, 2,665 female)
Source
Stability Fund Results Framework (Contributing IPs: All RDF, FCA Central Region, DDG)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016) | Sufficient demand for support to conflict management, and sufficient opperating space for local implementing partners
Existing and emerging conflicts brought to conclusion and risks of future conflicts mitigated | Number of people trained in conflict resolution. | Planned | 0 | 1,350 people (900 male, 450 female) | 1390 new people (780 males, 610 females) | 1390 new people (780 males, 610 females) | A total of 3680 people (2460 males, 1670 females) |  | 1670
|  | Achieved |  | 1,425 people (871 male, 554 female)
Source
Stability Fund Results Framework (Contributing IPs: CESVI, DRC, PACT, FCA-RDF, FCA Central Region, Caretaker Administration)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
| Output Indicator 2.2 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016)
| Number of conflicts managed peacefully | Planned | 0 | 18 conflicts managed peacefully | 42 new conflicts managed peacefully | 20 new conflicts managed peacefully | A total of 80 conflicts managed peacefully |  | 80
|  | Achieved |  | 14 conflicts managed peacefully
Source
Stability Fund Results Framework (Contributing IPs: FCA, Pact)
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016)
30% | Number of youth receiving education, vocational training or economic opportunities. | Planned | 0 | 2,250 youth (1800 males, 1450 females) | 1390 new youth (725 male, 665 female) | 1390 new youth (725 male, 665 female) | A total of 5030 (3250 male and 2780 female) |  | 2780
|  | Achieved |  | 2,469 youth (1550 males, 919 females)
Source
Stability Fund Results Framework (Contributing IPs: CESVI, JCC, DRC, DDG)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016) | Ongoing SSF Donor satisfaction with, and funding for, the fund manager
Stability Fund Management | Public profile – no of people following Stability Fund on media over the previous six months. | Planned | 0 | 1500 visits to the website | 2,500 new visits to the website 750 new twitter followers 15,000 SMS/voicemail responses | 2,500 new visits to the website 750 new twitter followers 15,000 SMS/voicemail responses | A total of 6500 visits to the website, 1500 twitter followers and 30,000 SMS/voicemail responses
|  | Achieved |  | 3248 website visits 248 Twitter followers
Source
Stability Fund Results Framework (contributing channels: website, SMS feedback system, twitter)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
| Output Indicator 3.2 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016)
| Percentage of districts in which SSF or independent monitors have done monitoring or assessments (of total number of districts in which SSF has active investments) | Planned | 0 | 80% of districts in which SSF activities implemented In 2013 | 35 new districts | 80% of districts in which SSF activities implemented In 2015 | 80% of districts in which SSF activities implemented overall
|  | Achieved |  | 1 district
Source
Stability fund reports and implementing partner reports, 3rd party monitoring reports, programme evaluation
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016)
30% | % of Stability Fund investments which have been subject to expenditure verification audits. | Planned | 0 | 80% of active investments in 2013 | 80% of active investments in 2014` | 80% of active investments in 2015 | 80% of total investments
|  | Achieved |  | 80% achieved (JCC, Pact, CESVI, DRC)
Source
Stability fund reports and implementing partner reports, 3rd party monitoring reports, programme evaluation
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Milestone 3 | Target (2016) | Sufficient political commitment to advancing the constitutional review process
Regional discussions on key constitutional isses increased. | Number of intra- and inter- regional discussions around security, revenue and representation | Planned |  | Not Applicable - owing to new focus of work | 2 Discussions | 2 Discussions | 2 Discussions
|  | Achieved |  | Not Applicable `
Source
IP reports
| Output Indicator 3.2 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Target (2015) | Target (2016)
|  | Planned |  |  | TBD | TBD | TBD
Achieved
Source
UNDP and NDI reports
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline (Jan 2013) | Milestone 1 (Dec 2013) | Milestone 2 | Target (2015) | Target (2016)
10% |  | Planned |  |  | TBD | TBD | TBD
Achieved
Stability fund reports and implementing partner reports, 3rd party monitoring reports, programme evaluation
UNDP and NDI reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
IMPACT WEIGHTING (%)
10%
Note on E64: Celeste Hibbert: Pact have not given us intra/inter data.