`
Type of Review: Annual Review

Project Title: Transparency International Programme Partnership Arrangement (PPA)
Date started: 01 April 2013	Date review undertaken: 31 October 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK, through the Department for International Development (DFID), is investing in a 3 year Programme Partnership Arrangement (PPA) with Transparency International between 2011 and 2014. An investment of £3,374,444 for each year has been agreed, £2,670,269 per year for the General PPA - Transparency International Secretariat (TI-S) and £704,075 for the CHASE PPA - Transparency International Defence and Security Programme (TI-DSP). This type of strategic investment can leverage much greater impact than traditional project funding by playing a key role in shaping how Transparency International uses its non-DFID resources.

What are the expected results?
Between 2011-2014 the results expected in this investment in the General PPA are: / 20 TI-research publications and 106 TI National chapter research publications supported by TI-S to develop evidence on corruption issues. / 28 support and legal advice centres supporting citizens to address corruption and promote integrity with 6 national chapters, supported by TI-S, using online corruption reporting tools. / Reaching out to and encouraging external stakeholders with 450,000 views of the TI space for transparency blog and 44 documents published annually on anti-corruption practice and policy. / The capacity of the TI movement strengthened with 85 capacity development activities implemented by TI Chapters with Secretariat support and 85 trainings organised by TI-S for TI National Chapters. / Through the CHASE PPA, TI-Defence and Security Programme (TI-DSP) expects to: / Support nine countries to develop defence integrity or counter-corruption programmes, with a particular focus on conflict or unstable environments / Influence states and national defence industry umbrella organisations to ensure International arms transfers are conducted more responsibly, with improved controls against corruption, with a specific target of an anti-corruption mechanism in the final Arms Trade Treaty. / Deliver 18 practical tools to enable governments, companies and at least 25 civil society organisations to address defence and security corruption. / Ensure that the danger of defence and security corruption is prominent on the agenda of policy makers and international organisations (including the UN, AU, World Bank, EU, and NATO) with 12 defence integrity building or counter-corruption initiatives initiated by international organisations

What is the context in which UK support is provided?
Civil society plays a vital role in supporting citizens to improve their lives. Civil Society Organisations (CSOs) are central to delivering services, enabling citizens to be more active in their own development and ensuring that policies benefit ordinary people – especially the poorest. / To achieve DFID’s priorities, as set out in its Business Plan (Structural Reform Plan), a multi-sectoral and multi-faceted approach to delivery is required, one in which CSOs, along with governments and the private sector, play a pivotal role in helping poor people to improve their lives. / The PPA is one of DFID’s main support mechanisms to CSOs. In line with a commitment by the Secretary of State to support another round of PPAs over the 2011-14 period and following a robust selection process and implementation of a Resource Allocation Model, partners were identified for a 3 year PPA which began in April 2011. This is the last review for that reporting period. However, it should be noted that an additional two years extension has been agreed by the SoS for 2014-2016. Results from 2011-2014 will be progressed further under the extension period. / In 2004, DFID agreed to fund the first phase of the programme, named Corruption in the Official Arms Trade (COAT). This support has continued through to the current CHASE PPA grant, which is implemented by Transparency International UK’s Defence and Security Programme (TI-DSP). / Increasing and improving transparency in the defence and security sectors, delivered through both supply and demand side pressures for transparency, can contribute to the reduction to improved service delivery and a reduction in violent conflict. It has been a challenging sector for civil society, which has lacked technical knowledge and access, and has been confronted with secrecy and vested interests. The CHASE PPA has been supporting Transparency International to take risks and innovate in uncharted territory, to build the evidence base of what works and how best to use the concept of transparency to support defence and security sector reform. It aims to empower governments, the private sector, and civil society around the world with practical tools and increased capacity.

## Section A: Detailed Output Scoring

General PPA - Output 1: To develop evidence on corruption issues.
Output 1 score and performance description: / A+ - Outputs moderately exceeded expectation
Progress against expected results: / TI – S has made good progress against output 1. The number of research publications either produced by TI-S or produced by TI Chapters with the support of TI-S has been exceeded for both indicators. DFID notes that the milestones for both indicators were not met in 2012/13 which makes this year’s achievements impressive. / TI-S has, over the three year PPA period, produced the number of research products which it intended to produce. TI-S research publications continue to reach wide audiences and ensure corruption remains on the radar of people, business, policy and decision makers. / PROGRESS AGAINST INDICATORS / Indicator Statement Milestone/target for 2013/2014 Actual Achievement / 1.1 Number and description of TI-S research publications 10 12 / 1.2 Number and description of TI National Chapter research publications supported by TI-S 25 38 / Recommendations: / Following on from the progress made this year, TI-S needs to ensure that targets set for next year are challenging enough. TI-S should ensure that they provide as much detail as possible in their accompanying narrative to ensure stakeholders have a clear understanding of TI-S’ work and progress. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

General PPA - Output 2: To support citizens to address corruption and promote integrity
Output 2 score and performance description: / A – Outputs met expectation
Progress against expected results: / TI-S has made good progress against indicator 2.1, but has not had the same success with indicator 2.2. This was a new indicator. At the end of 2013 TI-S developed a standardised online reporting tool to support chapters and other organisations in utilising online tools, rather than supporting individual chapters with small-scale grants in developing their own specific website. This would allow a much wider coverage of online reporting opportunities worldwide. Whilst developing one tool rather than multiple is excellent in terms of Value for Money, this has meant TI-S has not achieved the target for this indicator. Nevertheless, during 2013/14 TI-S supported three chapters to build online reporting tools, two of which were finalised and utilised by the chapters. / PROGRESS AGAINST INDICATORS / Indicator Milestone/target for 2013/2014 Actual Achievement / Number of contacts received by Advocacy and Legal Advice Centres (ALACs). ALACs provide free and confidential legal advice to witnesses and victims of corruption) 85 96 / 2.2 Number of National Chapters utilising online corruption reporting tools, supported by TI-S. (New indicator) 5 2 / Recommendations: / It is important when setting indicators that TI-S ensures targets are realistic and achievable and take into account external factors that may hinder progress. / Impact Weighting (%): 25% / Revised since last Annual Review? Yes / Risk: Low / Revised since last Annual Review? Yes

General PPA - Output 3: To reach out to and influence external stakeholders
Output 3 score and performance description: / A+ – Output moderately exceeded expectation
Progress against expected results: / Indicator 3.1 was massively overachieved, but given that the 2012/13 target was exceeded by over 435,000, this milestone should have been reviewed and increased, as was requested in the 2012/13 annual review. Similarly indicator 3.2 should also have been reviewed to ensure the target accurately reflected TI-S’ progress in this area. / PROGRESS AGAINST INDICATORS / Indicator Milestone/target for 2013/2014 Actual Achievement / 3.1 Number of page views of the TI Space for Transparency Blog 199,650 454,156 / 3.2 Number and description of TI documents with recommendations on Anti-Corruption practise and policy annually 14 21 / Recommendations: / TI-S should take DFID feedback into account, making sure that the PPA logframe is updated and monitored regularly, to ensure that milestones have been set appropriately. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

General PPA - Output 4: To strengthen the capacity of the TI movement
Output 4 score and performance description: / A++ - Outputs substantially exceeded expectation
Progress against expected results: / TI-S has made excellent progress against both indicators. Year 3 achievements include: / 43 trainings organised, covering a range of topics, including fundraising, communications, MEL and financial management. It is too early to assess the mid- to long-term outcome of these workshops and training efforts. However, following the financial sustainability workshop in Douala in June 2013, TI Senegal implemented an institutional audit and has begun to analyse its funding requirements, donor environment and key success factors from previous fundraising efforts. / Participants in the January 2014 MEL training are now in the process of developing robust MEL systems and the respective tools and skills to maintain, use, update and revise them, with draft frameworks developed by all Chapters less than 3 months after the training / PROGRESS AGAINST INDICATORS / Indicator Milestone/target for 2013/2014 Actual Achievement / 4.1 Number of capacity development activities implemented by TI Chapters with Secretariat support 25 59 / 4.2 Number of trainings organised by TI-S for TI National Chapters 25 43 / Recommendations: / TI-S should seek to build on this momentum in years 4 and 5 / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low / Revised since last Annual Review? No

CHASE PPA - Output 1: Conduct high level governmental workshops and events addressing Defence and Security Reform best practice and initiatives worldwide, including in Southeast-Asia, Africa, and wherever in the world governments express an interest.
Output 1 score and performance description: / A+ Outputs moderately exceeded expectation
Progress against expected results: / Indicator 1.1 Number of overall TI-DSP engagements (invitations, meetings). / Baseline 80 / 2011/12 2012/13 2013/14 / Milestone 100 265 370 (revised upwards from 140) / Achieved 199 318 635 / Variance +99 +53 +265 / Disaggregated Data* Available upon request / Indicator 1.2 Number of ANSF senior officers and officials course participants. / Baseline 60 (in 2010) / 2011/12 2012/13 2013/14 / Milestone 90 132 132 / Achieved 132 132 132 / Variance +42 0 / Disaggregated Data* Of the Afghan ethnic groups represented in or impact report, the respondents included 17 Tajiks, 10 Pusthuns, 2 Sadaats, and 2 Hazaras.21 / Indicator 1 / TI-DSP has exceeded the target for this indicator by 265. 317 engagements took place around the world this year, excluding intra-Transparency International engagements, phone conferences and international TI-DSP strategy meetings. Examples include: / Speaking at VIKING 14 preparation workshops to over 130 participants, representing 28 nations and 22 organisations, about the need to minimise corruption risks in peace support operations / Holding meetings with the UN Economic and Social Commission for West Asia (UNESCWA) and the Arab Administrative Development Organisation (ARADO) to lobby for a joint research project to explore the extent of defence corruption risks in the MENA region / Presenting the findings of TI-DSP’s “Watchdogs?” report to members of Public Accounts Committees (PACs) in Malaysia and from Burma in collaboration with the Commonwealth Parliamentary Association (UK Branch). / Indicator 2 / The target for this indicator was fully achieved in the first year so is not reflected in this AR. Further discussion is needed on what future work will be undertaken in this area and how it should be assessed. / Output 1 progress: / External engagements are a key element of TI-DSP’s strategy. They are significant opportunities for sharing TI-DSP’s expertise in defence and security corruption, keeping the agenda in different defence establishments and increasing the capacity of in-country partners for anti-corruption reform. / While indicator 1.1 has been exceeded, this does not adequately capture the quality of TI-DSP’s outreach. In turn, this makes attribution to outcome level more difficult. More narrative around TI-DSP’s approach to engagement in annual reporting would be helpful – in particular to draw out examples of where engagement has been successful (e.g. the specific approach of winning confidence by using military-savvy personnel to engage ‘peer-to-peer’ in the language the military understand), and where it has led to increased capacity of partners, or to spin-off initiatives. This is a key element of the programme’s theory of change. / Recommendations: / The extension logframe should also include at least one qualitative indicator capturing quality of high-level engagements and a greater emphasis on qualitative measures throughout to support attribution at outcome level. / The extension log-frame should also consider where in TI-DSP’s reporting any future work with the Afghan National Security Forces should be reflected. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

CHASE PPA - Output 2: Reach out and influence the defence industry and governments worldwide to address the arms trade and transfers, with improved controls against corruption, industry standards and codes of conduct.
Output 2 score and performance description: / A+ Outputs moderately exceeded expectation
Progress against expected results: / Indicator 2.1 Cumulative number and description of states TI-DSP engages (including via regional organisations) to convince them of the need for and practicality of an anti-corruption mechanism in the UN Arms Trade Treaty (ATT). / Baseline 20 (as of February 2011) / 2011/12 2012/13 2013/14 / Milestone 50 70 A-C in an ATT / Achieved 75 82 A-C in an ATT / Variance +25 +12 / Disaggregated Data* N/A / Indicator 2.2 Number of regional and national defence industry umbrella organisations TI-DSP works with increases. / Baseline 2 / 2011/12 2012/13 2013/14 / Milestone 3 4 9 / Achieved 5 7 16 / Variance +2 +3 +7 / Disaggregated Data* 6 in Western Europe; 1 in Turkey; 1 in the US; 1 in South Asia / Indicator 2.1 / The ATT was adopted in April 2013 with three anti-corruption provisions. This means that the target for the first indicator for the entire three-year period was achieved in the second year, and is therefore not reflected in this AR. / Indicator 2.2 / TI-DSP engaged with 9 defence industry umbrella associations: Confederation of Indian Industry (CII)’s Defence Committee, Turkish Defence Industry Association, Norwegian Defence Industry Association; FSI (The Norwegian Defence and Security Industries Association); the Swedish Security and Defence Association; European Club for Countertrade and Offset (ECCO); European Defence Agency (EDA); Aerospace and Defence Association of Europe (ASD); and the Defence Industry Initiative on Business Ethics and Conduct (DII). / The target for the second indicator has been exceeded by 7. This is partly due to the increased level of engagement with defence industry associations after the launch of the ‘Defence Companies Anti-Corruption Index’ (CI) and spin-off reports such as the ‘Raising the Bar’ report that prompted follow-up discussions. / Output 2 progress: / These indicators remain largely quantitative, and there is a need for more substantial reporting on the quality of TI-DSP’s work, as well as the numbers. / One key outcome is that CII in collaboration with the TI chapter in India will organise a conference on enhancing integrity in defence bidding and procurement in India in the next reporting year. This has come about as a result of TI-DSP’s visit and persuading CII in collaboration with TI India. Similarly, TI-DSP’s engagement with the Norwegian Centre for Integrity in the Defence Sector (CIDS) will result in a publication of an Integrity Plan Handbook and a development of a joint database that will result in the sharing of information between TI-DSP, the UK’s Defence Academy and CIDS on trained experts in defence integrity. / Recommendations: / Extension logframe indicator 2.1 should be amended to reflect the new focus on implementation of the ATT anti-corruption mechanisms [in current draft] / Extension logframe indicator 2.2 should aim to capture the quality and effect of existing engagements with defence industry organisations, rather than setting a new quantitative target. This relates to the issue of TI-DSP potentially spreading itself too thinly. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

CHASE PPA - Output 3: Produce practical tools that can be directly applied by civil society, governments, and the defence industry so that they are better able to address defence and security corruption and have increased capacity to do so.
Output 3 score and performance description: / A+ Outputs moderately exceeded expectation
Progress against expected results: / Indicator 3.1 Cumulative number of new practical tools developed by TI-DSP to address defence and security corruption. / Baseline 1 / 2011/12 2012/13 2013/14 / Milestone 2 8 (increased from previous milestone of 4) 18 (increased from previous target of 6) / Achieved 4 14 21 / Variance +2 +6 +3 / Disaggregated Data* 1 targeting International Organisations; 2 governments; 3 national security services and 1 company. / Indicator 3.2 Number of TI-DSP trained experts available to civil society, industry, and governments. / Baseline 10 / 2011/12 2012/13 2013/14 / Milestone 15 20 30 / Achieved 19 25 38 / Variance +4 +5 +8 / Disaggregated Data* 5 trained to work with governments, 1 with International Organisations, 3 with CSOs, and 4 with militaries. / Indicator 3.3 Number of civil society organisations engaged by TI-DSP to build their capability in tackling defence and security corruption / Baseline 10 / 2011/12 2012/13 2013/14 / Milestone 15 65 (increased from previous milestone of 20) 90 (increased from previous target of 58) / Achieved 58 84 95 / Variance +43 +19 +5 / Disaggregated Data* 7 from Eastern Europe; 1 Caribbean; 1 from Sub-Saharan Africa; 1 from East-central Asia; and 1 from South Caucasus, Eurasia. / Indicator 3.4 Cumulative number of new TI-DSP publications. / Baseline 2 / 2011/12 2012/13 2013/14 / Milestone 3 15 (increased from 3) 20 (increased from 3) / Achieved 10 19 27 / Variance +7 +4 +7 / Disaggregated Data* NA / Indicator 3.1 / In this reporting period, TI-DSP produced seven innovative tools. The ‘Corruption and Peacekeeping: Strengthening Peacekeeping and the UN’ report contains a typology of peacekeeping corruption risks with detailed recommendations for both the UN and member states. Two new Building Integrity (BI) courses were developed: the BI Senior Leadership course (which was successfully trailed), and the OF5 Colonel-level foundational course. The “Watchdogs?” and “Raising the Bar” reports, both spin-offs from the GI and the CI respectively, aggregate best practice information for parliamentarians and defence companies and associations for controlling corruption risks. TI-DSP, in collaboration with TI Burundi (ABUCO), carried out corruption risk assessments of the army and the police. These were presented to the Ministry of Good Governance and top army and police leadership. The visit was helpful in increasing knowledge of how to take a Government Defence Anti-Corruption Index assessment through a detailed in-country challenge, to work from Q&A to actions, and to apply the TI-DSP police assessment methodology. / Other examples of tools being used include NATO’s Allied Rapid Reaction Corps (ARRC), based in Gloucester, and NATO’s 1 German Netherlands Corps (1GNC), who have both become engaged with TI-DSP on addressing corruption in intervention operations. Both are planning to further incorporate anti-corruption into doctrine and exercises, and 1GNC would like to second experts to TI-DSP, which is an element in a concrete list of follow-up plans. Additionally, TI-DSP continues to engage the UN and its Department for Peacekeeping Operations (DPKO) to address corruption in peacekeeping missions, most recently with constructive meetings in New York and through actively contributing to the “Challenges Forum” in Beijing. A TI-DSP leadership course has also been run in Afghanistan, for a selected number of generals identified based on their skills and commitment, as well as in light of the 2015 withdrawal and how to best sustain positive developments. / Indicator 3.2 / In this reporting period, TI-DSP trained eleven experts drawn from target countries. Several of the experts are now doing joint projects with TI-DSP and other NGOs, including mentoring other trainees and developing pre-deployment training courses (e.g. for the National Defence University in Ukraine). TI-DSP has been working to expand and diversify its available pool of senior advisors based on the increased demand, including in various African states but also through TI-DSP’s partnership with the UK Defence Academy. This has led to increased language skills and regional backgrounds as well as additional expertise, particularly regarding fragile and conflict states. There is additional experience and expertise focused on e.g. Afghanistan, Algeria, Azerbaijan, China, East Timor, Egypt, Kosovo, Malawi, Mali, Mauritania, Morocco, Pakistan, Saudi Arabia, Sierra Leone, Uganda, the UAE, and Zambia. / Indicator 3.3 / TI-DSP engaged 11 civil society organisations: 3 Croatian NGOs: Center for Peace Studies, Eko-Zadar, Obris, and Zelena Istria; 4 Georgian NGOs: Civil Council of Defence and Security, Future Initiatives, Georgian Foundation for Strategic and International Studies (GFSIS); TI Haiti; TI Mongolia, TI-Armenia and TI-Burundi (ABUCO). These engagements took the form of training, holding meetings, etc. and resulted in joint projects in Armenia, Burundi and Croatia. TI-Haiti launched a corruption and peacekeeping report as a way of engaging the UN peacekeeping mission there, UN MINUSTA. / There have also been additional dividends from civil society engagement, leveraging the relationship between TI-DSP and TI country chapters. Based on engagement with TI-DSP the TI chapter in Palestine has begun training their Ministry of the Interior on ethics and anti-corruption, helped draft the new code of conduct, and founded a new civil society forum to oversee defence. In Yemen, through engagement with TI-DSP, the TI chapter’s advocacy led the Ministry of Defence (MOD) to appoint a spokesperson to engage with civil society and media, and the country’s first MOD press conference. In Indonesia, the TI chapter was trained by TI-DSP on how to best use the Government Defence Anti-Corruption Index (GI). One of their follow-up activities was a media launch of and engagement around the TI-DSP report on classified information. / Indicator 3.4 / TI-DSP produced 9 publications this year including Corruption and Peacekeeping, Corruption as a threat to stability and peace, Watchdogs?, Raising the Bar, Single Sourcing, Procurement: understanding, identifying and addressing corruption risk (a chapter in the Getting the deal through: Public Procurement 2014), the Freedom of Information report and an academic article that has been accepted for publication after peer review by the Economics of Peace and Security Journal (EPSJ) titled ‘Identifying Corruption Risks in Defence and Security: Empirical Evidence Using the Government Defence Anti-Corruption Index’. There is some evidence that these tools are actively used by governments, companies and civil society. For example, the ‘Watchdogs?’ report has been used by Georgian and Czech parliamentarians and the Flemish Peace Institute as a check-list for anti-corruption reform in this reporting period. The report on Corruption as a Threat to Stability and Peace has informed TI-DSP’s engagement with the ARRC and 1GNC (see the details above). The report also informed a discussion at the Munich Security Conference (MSC) 2014 where TI co-hosted a panel – a rare privilege for an NGO. One of the panellists was then UK Secretary of State for Defence Philipp Hammond, and TI has been asked to co-host another panel at the MSC in 2015. The report has also informed discussions within TI as a global movement in over 100 countries – TI-DSP and others within TI have built on it to capture the attention that the nexus of corruption and conflict (peace, stability) is receiving at the moment. / TI-DSP’s reliance on quantitative indicators makes it difficult to assess the level of achievement on formal measures of progress alone. However the narrative reporting, and our familiarity with TI-DSP’s work in this area, permits a more considered assessment. The challenge involved in persuading stakeholders of the merits of using practical tools to measure integrity in the defence sector, and TI-DSP’s successes in doing this, merit a high score. / Recommendations: / The revised logframe should include indicators that will help TI-DSP to measure the up-take of its products and absorption of the knowledge it generates. While this is not an easy task, it is a much more robust indicator of influence. Indicators could cover areas such as the specific uptake of tools, uptake of expertise as a result of training, and measures of CSO capacity, for example. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

CHASE PPA - Output 4: Reach out to and influence policy makers and international organisations worldwide (including UN, AU, African Development Bank, World Bank, EU, and NATO) to address the danger of defence and security corruption as a prominent issue on their agenda.
Output 4 score and performance description: / A+ Outputs moderately exceeded expectation
Progress against expected results: / Indicator 4.1 Number of international organisations TI-DSP is engaged with to convince them to initiate defence integrity building or counter corruption initiatives. / Baseline 2 / 2011/12 2012/13 2013/14 / Milestone 4 8 (increased from previous milestone of 6) 15 (increased from previous milestone of 8) / Achieved 6 13 22 / Variance +2 +5 +7 / Disaggregated Data* NA / Indicator 4.2 Number of high-level decision makers in international organisations TI-DSP is engaged with who acknowledge the importance of tackling defence/security corruption. / Baseline 15 / 2011/12 2012/13 2013/14 / Milestone 20 35 (increased from previous milestone of 6) 65 (increased from previous milestone of 35) / Achieved 28 55 92 / Variance +8 +20 +27 / Disaggregated Data* NA / Indicator 4.1 / This year, TI-DSP engaged 9 international organisations. For example, TI-DSP approached the Regional Offices of the World Bank and UNODC in Nairobi to undertake corruption risk assessments of police forces in the East Africa region. TI-DSP has also been engaging EU DEVCO and EEAS to do a thorough corruption risk assessment of security forces in the Sahel region and to design and deliver capacity building activities for CSOs in the region in order to reduce corruption and associated transnational organised crime and terrorism. / Indicator 4.2 / TI-DSP’s engagements with high-level decision-makers have been both broad and deep. Strong strategic relationships are formed with high-level defence and security personnel, and individual engagements have been with various UN agencies, host government Ministers, NATO officials, and senior personnel in other multi-lateral organisations. / The targets under this output have been exceeded year-on-year, including against revised and extended milestones. However the reporting format makes it difficult to assess the depth and quality of TI-DSP’s relationships with policymakers and organisations over time. Feedback from DFID staff and others working closely with the programme confirms that these relationships are strong. There is also a question over the balance between breadth and depth, which TI-DSP needs to consider in its future business planning. / Recommendations: / It will be essential for TI-DSP moving into its second decade to take stock of where it has deep connections that can be leveraged for systemic change, and where it finds the balance between breadth and quality. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? / General PPA – Yes / Output indicator 2.2 now reads “number of National Chapters utilising online corruption reporting tools, supported by TI-S”. / CHASE PPA – Yes / The targets for 4 outcome and 7 output indicators have been revised upward. This is in line with TI-DSP’s “outstanding” ranking from Coffey International for its performance against the log frame indicators and as agreed with DFID CHASE policy leads. / The results for the period 2011 – 2014 were better than expected. Milestones and targets have had to be revised upward every year. The milestones and targets for the 2014/16 logframe still retain the ambitious drive that has characterised the previous period, but more focus has been given to intensifying and consolidating positive change. / 1.2 Overall Output Score and Description: / General PPA: / A+ - Outputs moderately exceeded expectation / CHASE PPA: / A+ - Outputs moderately exceeded expectation / 1.3 Direct feedback from beneficiaries / General PPA / DFID welcomes the comprehensive overview of TI-S’ different types of beneficiaries; proximate, intermediate and ultimate and of the beneficiary feedback tools used. / Proximate beneficiary feedback has enabled the refinement and acceleration of strategies to engage poor and marginalised people in policy and advocacy development. DFID notes the intermediate beneficiary feedback and appreciates the quantified user perception data provided in relation to the TI Helpdesk’s performance, responding to increasing demand, feedback and queries from Chapter and other stakeholders. / The main direct beneficiaries of TI-S’ work remain however, TI Chapters. TI-S works on their behalf at the global level and seeks to strengthen their ability to advocate for change. Feedback from Chapters to TI-S indicates that in this reporting year the TI-S continues to serve the movement well / TI-S has taken feedback from their 2012/13 annual report on board and included more information on the nature of beneficiary groups and wider direct and indirect beneficiaries reached, for example: through ALACs and the Global corruption Barometer (GCB). / DFID would like to see TI-S detail how beneficiary feedback enables the resolution of aspects of work which are not so successful or are problematic. This was also mentioned in feedback for last year and should be noted for future reporting. / CHASE PPA / The nature of TI-DSP’s work means that it is less directly engaged with its ultimate beneficiaries than those organisations working in service delivery or humanitarian relief. Its proximate and intermediate beneficiaries are governments, companies, TI chapters and other civil society organisations, industry associations and media. TI does this through: / Beneficiary feedback from training courses which aims to accurately capture feedback and incremental change within an individual, an organisation or even a government across a range of geographic regions and project funding streams. / Direct involvement of beneficiaries and direct observation through quarterly MEKANIC (Monitoring, Evaluation, Knowledge gathering and dissemination, Affirmation, Building Effective Networks, Influencing and Theory of Change) meetings. External participants are invited to these, and provide feedback as part of the process. / Some general feedback from training participants was that participants felt a need for increased support after completing courses, as well as before and during the course. Other specific comments from participants included: / “The course was useful for me and my officers because all my staff have become aware of [the] issues discussed. Best activity I participated in as Inspector General of [XXX] MoD.” / Inspector General of a Ministry of Defence / “My awareness was raised one level up.” / Head of Training at a national Peacekeeping Operations Center / “We have recommended tools and methodologies [from the course] through briefings to our BI working group, on what was done on the course. We have pointed out what we thought were the most useful tools. Especially on how to approach whole [sector].” / Defence Counsellor from a country’s mission to NATO / TI-DSP is developing a wider new monitoring and evaluation strategy for the integrity and anti-corruption training and capacity building component of its work. This new M&E strategy is currently in development across a range of TI-DSP initiatives in an attempt to accurately capture feedback and incremental change within an individual, an organisation or a government across a range of geographic regions and project funding streams. / Recommendations: / TI-DSP should continue to ensure effective follow-up on the impact their training has had after the event. TI-DSP is making progress on this, but are not unique in finding it difficult to measure the long term benefits. Their planned systematic evaluation approach should be followed up within the year to see how it develops. / 1.4 Summary of overall progress / General PPA / TI-S has made good progress this year, either exceeding or meeting the majority of targets. Where targets have not been fully achieved, DFID is pleased to note that TI-S has demonstrated a clear understanding of issues that have impacted on progress and proposed changes in their reporting to ensure that all targets are accurate and attainable. / Marked achievements for TI-S this year include: / TI-S reaching an increasing number of citizens and supporting chapters in their work doing the same. The ALACs continue to operate as powerful, credible and viable mechanisms for people to pursue their corruption-related complaints. The whistleblower principles developed in 2013, contributed towards a vast array of changes in discourse and policy over 2013, as described in the annual report. / Strengthening the TI movement remains a priority for TI-S. In this reporting year, TI-S focussed on supporting chapters in the areas of organisational assessment and planning; governance and leadership; advocacy and communications and resource mobilisation. TI-S continued to support both capacity development of individual chapters as well as a number of global activities to address common capacity needs shared by chapters across the TI Movement. / Engaging with and influencing global debates on governance remained one of TI-S’ strengths in this reporting year. Advocacy efforts directed towards a number of key initiatives and organisations yielded successes such as through the G20, in the form of an agreement on automatic exchange of information; a policy position on beneficial ownership at EU level; and a G8 commitment to establish public registries of beneficial owners. / CHASE PPA / While mere numbers of engagements might not usually be regarded as a key indicator, they have been used so far because of the traditional difficulty of getting the military to take up corruption as an issue, either doctrinally or practically. The same goes for defence industry associations. Often we find that such bodies are, individually, interested in ‘doing something’ but need an external catalyst to make all those with a partial interest come together collectively. Over the last decade, DSP has played that crucial catalytic role, but it will be essential in the future for TI-DSP to define and report on the depth and quality of its work, as well as the numbers. / 1.5 Key challenges / General PPA / TI-S’ challenges in 2013/14 include: / Civil society movements have many opportunities today to engage at the global level, for example in the G8/G20 and post-2015 processes, but the space for civil society to operate at national level is shrinking in many countries. This remains a serious concern to the movement. Chapters within the TI movement were put under threat in a range of countries in this reporting year. / While TI has seen growth over recent years, the changing political priorities of some of their traditional donors has put financial pressure on the organisation, making it more difficult to matching ambitions with the necessary resources. While TI-S is working hard to diversify its donor base, for example to foundations, decisions by some bilateral partners to reduce funding due to a shift in their priorities, has meant some programming, including in Africa, had to be scaled down. / While citizen demand for social accountability is evident in a range of countries around the world too many people consider corruption to be ‘normal’ or ‘acceptable’. TI-S’ research among youth in Asia and Pacific found for example that while over 80 per cent of young people believe that youths want to take action against corruption, 72% admit they are willing to behave corruptly if it yields personal benefit. / CHASE PPA / TI-DSP identified three main challenges to their work, although the challenge of physical risk to the lives of the team is more appropriate in the risk section of this review. The remaining two challenges are: / (1) That TI-DSP chooses countries where corruption is so deeply entrenched that it is impossible to make visible progress; / (2) That TI-DSP spreads itself too thinly / TI-DSP’s response to these challenges has been: / (1) evaluating target countries with internal and external actors before planning any intervention; / (2) preparing multiple year plans; / We recognise that some of the challenges faced in this programme are politically sensitive (e,g, political will for integrity reforms), and so a complete narrative in this report is not advisable. However TI-DSP does need to better understand and present the challenge posed by overstretch. Further comments on this are in section 4.2 below. The first challenge identified here is appropriate, but TI-DSP is also facing similar issues of political will in countries and with organisations where corruption is not typically thought to be deeply entrenched. / Recommendation: / TI-DSP should look at its strategic challenges afresh alongside the recommendation below for a more robust risk matrix. / 1.6 Annual Outcome Assessment / General PPA / There is evidence of positive progress across both of the outcomes for 2013/14. Due to problems with the new ALAC database, which is used by Chapters to report on ALAC related indicators, in regard to outcome indicator 1.2, TI-S are unable to report accurate figures of initial contacts this year. As well as bringing Chapters onto the new database during 2013, it was also off-line for the last four months of the 2013 calendar year. TI-S cannot completely exclude a hostile takeover at this stage; however, has no evidence that this has occurred. / TI-S has used this as an opportunity to undertake a number of improved upgraded data and security measures, including changes to the database, a new hosting provider and a 2-factor authentication system including a virtual private network (VPN). Throughout 2014 TI-S will continue to get more Chapters using the new database and enter data from the September to December period, but until this process is finalised they are unable to report on this indicator. / DFID notes that this is not an ideal situation but it is good to see TI-S is using this as an opportunity to upgrade data and security measures. DFID would be interested in seeing the final report on this indicator once all of the data for September to December 2013 has been input. / CHASE PPA / TI-DSP has been generating significant reflection of the issues within Ministries of Defence worldwide, which is a unique and significant achievement by an advocacy NGO. TI-DSP manages to shape and convey to military minds the proposition that they themselves have incentives to reform. Likewise with companies, the evidence is that after the initial Companies Index, an increased number have engaged with TI-DSP on continuing improvements. The Index has sparked a competitive dynamic amongst defence companies, which would not have happened in the absence of the Index. / Saudi Arabia and Burundi are clear examples of TI-DSP engagement leading to tangible outcomes in institutional reforms, with an important lesson emerging about the need for long-term engagement. The emerging recognition on the international agenda that corruption is a national and international security issue is a powerful change of tone, and the momentum needs to be kept up. TI-DSP can claim substantial credit for this. / TI-DSP’s products and tools are influential, timely, and well-respected. They undoubtedly have an influence in a sector that is notoriously closed to external, especially NGO, influence. Likewise its engagement and advocacy is performing highly. The examples of VIKING 14 and the EU DEVCO and EEAS show influence in the right places and at the right level – the challenge for TI-DSP will be making sure its capacity internally is able to service the expectations now raised for what can be done on defence and security corruption. The challenge of resistance within the UN to this agenda is revealing, and is itself an indicator of TI-DSP’s influence. / This review makes the following observations about outcome indicators in the previous logframe. These could usefully be considered when making final revisions to the extension logframe: / Outcome 1 – Defence or security reform initiatives underway and publicised / • It is not clear if indicator 1.2 refers to TI-DSP-influenced reports in the news or to general reporting (except in the Russia case, where TI-DSP clearly influenced). It would be helpful to get a sense of what the increased reporting actually means in terms of shaping public opinion (e.g. in Russia, did change come about as a result of the cited reporting? Were the articles influential?). Work to monitor this could be labour intensive – TI-DSP could think about using online technical tools for tracking influence and opinion, if appropriate. / Outcome 2 – International arms transfers are conducted more responsibly / • Indicator 2.2 is difficult to rate, as it’s cumulative, and affected by a strong overachievement in Year 2. While the result is +1 compared to the milestone, if we look at the expected improvement from Year 2 to 3, the result is -7 (as the year 3 milestone expected a 15-company jump, but achieved 8). This sounds like a bureaucratic technicality, but underscores the point made in the previous annual review about needing qualitative as well as quantitative metrics. / • It would be helpful to have objective measures of the size and integrity of the global arms trade, and for TI-DSP to be able to link their work to these measures (if not score on them directly). / • Extra-territorial legislation is a noted factor affecting the progress of transparency reforms. It would be useful for TI-DSP to assess G77 country reactions to this legislation and calibrate its future messaging around it based on this assessment. / Outcome 3 – CSOs, Governments and companies have capacity to counter corruption with practical tools / • As above, the indicators on this outcome force essentially qualitative things into a countable format, with resulting confusion. / Recommendations: / TI-DSP should review the outcome indicators in the extension logframe to help show more clearly the connection between its work and the outcomes achieved, building on the theory of change. This will also help to trace through the programme’s contribution at Impact level at the end of the programme period. / TI-DSP to ensure that expectations of performance are clear year-on-year, as well as from the baseline to the final milestone

2. Costs and timescale
Is the project on-track against financial forecasts: / General and CHASE PPA / Yes, annual funding through the PPA is disbursed in four equal amounts on a quarterly basis. The full annual allocation was disbursed as expected. / Key cost drivers / General PPA / The main costs drivers for TI-S in delivering their interventions are staff costs, along with travel, training costs, consultancy costs, and publications. All these costs are relevant and necessary for TI to achieve its mission. Project management, research, advocacy and other key activities are undertaken by staff members. / TI-S’ reporting on key cost drivers consists of a list of cost categories which don’t provide an indication of how significant each category is, or what drives these costs. DFID would like to see more detail here with information on what drives costs within the different categories. TI-S should bear this in mind for future reporting. / CHASE PPA / The principal cost drivers are the following: / Senior advisors / TI-DSP’s way of working is to pair up a young professional with a highly experienced senior person in each of the areas where they work. They attract these senior advisors – typically former Ambassadors, Permanent Secretaries, and Generals – by the high quality of their work, the high political levels they work at, and the evident impact they have. This would be prohibitively expensive if TI-DSP were to pay market rates, which range from £1000 per day for public sector work to £2000 for private sector work for individuals with such experience. TI-DSP’s rate is £250 per day. / Young and highly qualified professionals / TI-DSP has 12 young(er) professionals in the team. Again, they ensure the quality of the team because of their reputation. In an effort to keep costs down, TI-DSP salaries are kept at median rates. They add to this with interns and engaging research students who are keen to do their thesis or dissertation on a subject that TI-DSP propose. / Travel arrangements / Face-to-face contact is key in TI-DSP’s work, and the programme attempts to maximise the working time available from overseas visits. Senior experts also try to introduce TI-DSP’s work into their agendas when travelling for other purposes. This means TI-DSP reaches many countries they otherwise do not have the budget to get to. / Is the project on-track against original timescale: / General PPA / Yes many of the milestones have been met and in some cases exceeded. / CHASE PPA / Yes.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / General PPA / The collection and use of evidence is central to the work of TI-S. Output one from TI-S’ PPA logframe is; ‘To develop evidence on corruption issues’. / In 2013/14 TI-S’ evidence-based publications covered a wide range of relevant aspects of corruption and anti-corruption, ranging from sports, whistleblowing, climate change, to party financing, access to information and the enforcement of international conventions. These publications contributed tremendously to the global discourse on corruption, and in particular, to the work of the anti-corruption community. / TI-S has supported the publication of research reports by the TI Chapters, this has almost exclusively been part of a larger evidence-based advocacy effort to improve anti-corruption efforts. This combination of strong and valid evidence, the engagement of key stakeholders in the process and subsequent constructive advocacy is a hallmark of TI’s approach to stopping corruption. In most cases, the advocacy efforts of the reports published during this reporting period are still ongoing. The main role of TI-S was the development of research methodologies, as well as training, assistance in data analysis and quality assurance. / Changes in Capacity / Changes made in the management systems of TI-S over the last three years and enabled by the PPA include: / Results reported in the PPA logframe. These are a reflection of investment in programmes such as TI-S’ People Engagement work and their support in strengthening the capacity of the TI movement. For example, trainings reported on under output 4 were partly funded through unrestricted support such as the PPA. Investment in TI-S’ communications work allowed TI-S to reach more citizens than ever before through social media and their website. Additionally, the improvement of organisational processes and systems allow for more efficiency and effectiveness in TI-S’ operations, in turn allowing them to target resources towards achieving their objectives as outlined in the PPA logframe. / The PPA logframe is a good reflection of the priorities of the TI Secretariat but does not cover all of these. Hence, the organisational improvements, such as on M&E and work processes, profit all of their work, including work funded outside of the PPA. / Increasing capacity will remain an iterative process in which TI-S will continuously need to respond to changing priorities. / CHASE PPA / The PPA has facilitated TI-DSP’s transition from a project to a more strategic and longer-term programmatic approach, with increased learning and feedback mechanisms. It has facilitated engagement with key actors in the defence and security sector, and is careful to remain open to new opportunities for influence. The array of networks that TI-DSP has spawned is impressive, but the current theory of change underplays the sophistication of their approach. DSP could set out more clearly their unique way of doing business. In practice, the unique aspect of the theory of change is that there needs to be shown incentives to the military to reform: as in Afghanistan, recognising that corruption threatened the military mission was the ‘light-bulb’ moment for the International Security Assistance Force. TI-DSP’s capturing of these insights, and reflection back into military establishments through doctrinal reforms and using uniformed advocates to engage in language the military understands is central to DSP’s way of working, and could come out more clearly in the theory of change. / The MEKANIC process allows TI-DSP to capture lessons from the programme in a systematic way, based on: / Evaluations of current and recent activities / Discussions of the external environment and trends in defense and security. / Further detail on this process is available at http://www.intrac.org/data/files/140120_TI-DSP_Praxis_Note_MEKANIC_for_INTRAC_FINAL.pdf and information on specific lessons themselves is published by TI-DSP under Output 3. A full list is available in the Evidence Table produced as part of the reporting process for this review. Key lessons for TI-DSP (and work on anti-corruption in defence and security more generally) for this year include: / Using the company and government indices is a constructive way to increase engagement with both companies and governments, leading to increased sharing of sensitive internal information; / Corruption was a significant factor in the efficacy of stabilisation operations in Afghanistan, and there is strong demand to learn lessons from this. TI-DSP has developed a report based on in-depth interviews with 70+ international and local stakeholders which will be published in 2015; / Using existing NGOs, especially TI chapters, is a valuable entry point in countries where a relationship is new. This approach has led to productive work in the West Bank, Yemen, and Indonesia / 3.2 Where an evaluation is planned what progress has been made? / The PPAs as a whole are served by an umbrella evaluation strategy, the first of its kind for DFID, which also encompasses the Global Poverty Action Fund. This strategy examines progress at fund and at individual, organisational level. Following the announcement of the extension to the PPA fund in 2013, the evaluation strategy was reviewed and, in addition to the individual progress reviews (IPRs) and meta evaluation that took place in 2012, a further two evaluations are planned for 2014/2015 and 2016/17. The evaluation is managed by an externally contracted evaluation manager. / The 2014/15 evaluation has started and focuses on the assessment of the fund-level effects of PPA grants. This fund-level evaluation will use 12 organisations, TI among them, to illustrate the effects of the PPA fund and evidence from all 41 organisations to evaluate progress and outcomes. The aim is to provide timely, fund level evaluation information for the design of any future strategic funding modalities in 2014/15 ahead of fund completion in 2016. The evaluation in 2016/17 will focus on the impact of PPA funding for organisations.

4. Risk
Output Risk Rating: / General PPA / Low / CHASE PPA / Medium / Assessment of the risk level / General PPA / In regard to the PPA logframe outputs, TI-S has assessed the risk rating and all four will remain at ‘low’ risk. TI-S has stated that there is low probability of objectives not being met. Over the three years of the PPA a range of organisational processes have been improved, including, but not limited to, an advance project design and development process, delegation of authority, and a comprehensive risk management policy. Additionally TI-S’ finance manual, including procurement processes, were updated and improved. / CHASE PPA / TI-DSP has identified and rated the following as key risks to their work: / That governments for a variety of reasons lose the political will to engage with TI-DSP. TI-DSP considers this a ‘medium’ risk. Medium likelihood and medium impact. / That defence industry associations stop engaging with TI-DSP. Medium likelihood and medium impact. / That anti-corruption CSOs prioritise working in other sectors rather than defence. Medium likelihood and medium impact. / That international organisations do not take up anti-corruption as a prominent agenda. Medium likelihood and medium impact. / That staff are put in physical danger due to working in conflict-affected areas. (rating not given) / TI-DSP has identified mitigation measures for most of these, such as diversifying their influencing tools, building public support through civil society and media advocacy, and building partnerships with key member states to keep their agenda prominent. However it is not clear which of these risks pertain to TI-DSP’s stated aims and outcomes, and which to the actual delivery of outputs. / Recommendations: / TI-DSP to redesign the risk matrix to separate risks to achievement of outcomes from risks to achievement of outputs. / TI-DSP to identify and record appropriate mitigation measures for these risks. The substance of this already exists in TI’s work, but needs to be brought out in annual reporting. For example, TI-DSP could describe how the risk to TI country chapters from publishing the Government Index was managed. / Risk of funds not being used as intended / TI-S underwent pre-grant due diligence checks carried out by KPMG. The pre-grant due diligence assessed capacity to manage the proposed level of DFID support in the following areas: / Governance / Financial Capacity / Operational Capacity / Value for Money / Results / Satisfactory completion of the due diligence process was required before any money was disbursed. This helps to reduce the risk of diverted funding while establishing an environment of accountability and transparency. Organisations also had baseline up-dated due diligence assessments carried out in March 2014 to ensure that processes and strategies were current and complementary to DFID’s due diligence framework and modules. / Transparency International is adhering to the outcome of the March 2014 due diligence assessment as part of their PPA extension MOU. / Climate and Environment Risk / General PPA / TI-S does not have a stand-alone climate and environment strategy but measures to prevent and address climate change are integrated into the TI code of conduct. / As part of the code of conduct TI-S are committed to reducing their environmental impact. The main environmental risks associated with TI-S’ work remain the number of flights undertaken. DFID is pleased to note that in an attempt to avoid excess travel, TI-S has increased their use of technology, providing the example of using video-conferencing for their engagement with the PPA Learning Partnership avoiding the need to travel. Additionally, environmental considerations are integrated into the everyday running of the TI-S office, with measures including an office-wide recycling programme and conversion to 100% green energy. / As mentioned, flights are the main environmental risks for TI-S. PPA funds have contributed to the setting up of systems to monitor CO2 emissions. TI-S has reported that emissions stayed at around the same level in 2013 as in 2012, (3.258 tons in 2013 compared to 3.260 tons in 2012), despite a rise in staff numbers and an increased number of chapters with whom they engage. / In terms of programming, TI-S’ main work in this area is the Climate Governance Integrity Programme. Following direct engagement with the Climate Investment Funds (CIF), the CIF website was updated in June with a page on transparency and accountability, highlighting how to access information and how to send a complaint, including from/on the implementing entities. This information was previously only available in hard copy, thus difficult to access. / DFID would have liked more detail on the Climate Governance Integrity programme and feel TI-S could have expanded this section, providing more detail on the programme and its impact. TI-S should note this for reporting in the future. / CHASE PPA / Transparency International UK has a relatively small environmental impact. TI-DSP also has a policy designed to minimise our environmental footprint. Their target is 100% compliance in the areas of energy use, travel, procurement, and waste recycling. TI-UK aims to operate in compliance with all relevant environmental legislation, trains, educates and informs its employees, interns and consultants about environmental issues that may affect their work, and makes them aware of the policies in place. This includes printing in particular, which is sourced from environmentally-friendly printers (e.g. those with ISO 14001 accreditation). Paper is FSC-certified, recycled or from sustainable sources. In addition, TI-UK is based at Community Action Network (CAN) Mezzanine. CAN Mezzanine works to clear environmental policies, which include cleaning being 100% eco-friendly; collecting refuse for recycling and using a PIR lighting system, which is movement sensitive reducing energy waste.

5. Value for Money
Performance on VfM measures / General PPA / TI-S are currently developing a set organisational approach to VfM. VfM is defined as being an assessment of whether or not TI-S is obtaining the maximum benefit for its beneficiaries from the goods and services it both acquires (procurement) and provides (delivery), within the resources available to it. The ultimate goal is to maximise the positive impact of the investment made. / Within TI-S’ work VfM serves to: / Ensure TI-S are clear on their cost drivers / Demonstrate greater openness and transparency in the management of donated funds. / Maximise the chance of achieving the desired ends without unnecessary expenditure and effort. / Improve budget planning and effectiveness in budget management and procurement. / Produce pertinent information to evidence-based choices and decisions / Track efficiency and effectiveness in their work / Provide clarity on why particular decisions and approaches are decided upon when seeking to achieve objectives, as opposed to alternative decisions and approaches. / DFID appreciates the work TI-S is taking forward on VfM and looks forward to seeing the benefits of TI-S’ new set organisational approach to VfM in future reporting. / CHASE PPA / The 3 E model of VfM (Economy, Efficiency, Effectiveness) is built into TI-DSP’s thinking and organisational design. In particular the MEKANIC process for monitoring progress on a quarterly basis, drawing on external views and establishing a clear workshop methodology has been impressive. / DSP secures some of the most influential military minds within the UK at limited cost to the programme. The grade of advisers – ex-Perm Secs and Ambassadors is testimony to both the importance of the topic and TI’s reputation as a solid technical body to do business with. They also attract an impressive range of young professional researchers, again on the basis of the kudos working for TI brings in the anti-corruption field. The latter does bring ‘churn’ difficulties, but these are outweighed by the quality of the staff. / Commercial Improvement and Value for Money / General PPA / Competition and effective commercial practice is used to drive improved value for money. Procurement guidelines require competitive bidding for procurement of goods or services over EUR 5,000. This includes consultancies, travels, publications and other activities, and ensures economy of cost for the input needed. TI-S’ travel policy further requires that all staff travel economy class, and ensure that accommodation is reasonably priced, while taking safety and country costs into account. / TI-S tracks the costs of support departments, including finance, human resources, and office management and information technology. These departments provide the necessary support for the organisation to continue functioning effectively, and are monitored and controlled on a systematic basis. DFID finds it interesting that TI-S identifies overhead/ support costs as VfM measures. Whilst this could potentially be developed into a measure, for example, support costs as a percentage of total spend, the way it is currently set out in the report doesn’t state what is measured or tracked. TI-S should consider this when discussing VfM in future reports. / CHASE PPA / TI-DSP reports that it collects multiple quotes before committing to a supplier, for example for printing publications. Tracking the unit printing costs, and getting quotes for bulk printing, has meant TI-DSP reports a 25% reduction in printing costs compared to the start of the programme. This annual review did not audit these claims, but they are consistent with TI-DSP’s overall approach to VfM. / 5.3 Role of project partners / General PPA / Working in partnerships lies at the core of TI-S’ work and approach. Partnerships relating to the work of TI-S, take place at different levels. TI-S’ key partners are TI National Chapters, to which TI-S is ultimately accountable. Collectively the Chapters are, through Annual Membership Meetings, the highest decision making body within the TI movement. / Working with, for and on behalf of the Chapters, TI-S has three key roles: / TI-S leads in global and regional advocacy for the TI movement, which includes shaping the international anti-corruption agenda, coordinating TI Movement collective action around international issues and developing internationally relevant evidence-based advocacy products and actions. / TI-S promotes common anti-corruption approaches across the TI movement. TI-S identifies what is working to stop corruption and actively promotes successful approaches. / Support to, and servicing of, the global TI Movement is central to TI-S’ mandate. Work in this area is complex and multi-faceted, but is central to the ability of the Movement to act effectively against corruption. / PPA support allows TI-S to continue to engage with a range of further stakeholders, including media, academia, policy and decision makers, and others. This engagement will ensure TI-S remain abreast of and share developments and challenges related to their work, in turn ensuring interventions are informed and purposeful, and rooted in partnerships with others. For example, TI-S’ partnership with the BBC around the launch of the 2013 Global Corruption Barometer, saw the BBC produce a special interactive web section on the Barometer results, as well as a series of TV, radio and website reports during the weeks around the launch on bribery. The partnership generated 14 interviews and 25 articles on BBC outlets around the world. / CHASE PPA / This programme is an excellent example of coalition building of connected, but extremely diverse, interest groups. Its forte of using ‘allies in uniform’ to speak to military in the language they understand is a core insight which others could learn from. A few examples of partnerships include: / a) TI-DSP is partnering with the ‘Associacion para una Sociedad Mas Justa’, a coalition of NGOs in Honduras (including TI Honduras) to develop more effective ways of civil society engagement to reduce corruption in the police force. / b) TI-DSP has also partnered with the Independent Kenyan Police Oversight Authority with a similar objective. / c) TI-DSP and TI colleagues are developing a partnership with the Institute for Security Studies in South Africa to develop a centre for security and police integrity based in Africa. / d) TI-DSP is partnering with numerous individual TI Chapters to work together in their countries on defence and security corruption. Examples include Armenia, Burundi, Mongolia, Yemen, and the OPT. TI-DSP is in regular contact with c. 50 TI Chapters worldwide. / TI-DSP is also forming strategic partnerships with defence academies and training institutions in the global South. TI-DSP’s anti-corruption modules have been delivered at the International Peace Support Training Centre (Nairobi), the National Defence College (Abuja), the Southern African Development Community Regional Peacekeeping Training Centre (Harare), and the Malawi Armed Forces Staff College (Salima). / 5.4 Does the project still represent Value for Money : / General PPA / Yes. TI-S has met most of the milestones for 2011-14. Where targets have not been achieved TI-S has proposed changes/improvements as they move into the extension phase. / CHASE PPA / While there is no doubt about the value of TI-DSP’s current operations, there remains a question over how far the organisation can stretch in response to growing demand, and over the internal resilience of its business model. Key long-term personnel have been essential to TI-DSP’s success and it would be useful to understand whether their departure would present a risk to the programme. While a successful 10 years of operations does suggest strong resilience, it isn’t clear from the annual reporting where the weak points in the organisation are and what changes could put the programme at risk. These issues should be elaborated in the risk matrix with appropriate mitigation steps. TI-DSP has responded to increasingly stretching quantitative targets for numbers of engagements and breadth of work, and it is important for the programme not to lose sight of core goals and ways of working in this expansion. / If not, what action will you take? / N/A

6. Conditionality
Update on specific conditions / N/A

7. Conclusions and actions
General PPA / Overall TI-S’ Annual report presents a positive picture of the third year of the PPA, but DFID believes that TI-S is capable of reaching higher reporting standards in the extension period. TI-S should take into account the feedback given on the Annual Report, in particular TI should reflect on the quality of discussion as it can impact on our assessment. The narrative can ensure that scores can be adapted where new situations have arisen or circumstances out with the organisation’s control have impacted on results. / TI-S is required to submit a final extension logframe by 30 September 2014 incorporating any feedback given on it in the annual report feedback letter and subsequent discussions. They must ensure that learning and results from this PPA period are reflected in their milestones and targets for 2014/2016. Organisations have also been asked to set out the substantive and measureable steps they will be taking to enhance work on transparency and value for money. / CHASE PPA / This programme shows the importance and necessity of sustained support over many years to penetrate a previously thought to be impenetrable sector. What started as a narrow – but seminal – exercise against corruption in the arms trade, has flourished through developing strong civil-military links into a global programme that has the confidence of some of the key global institutions in defence planning and administration. It illustrates two things: that given the right approach, the most difficult arenas can be penetrated with effect; but that patience is required, and short-term support needs to be seen in a longer context for enduring impact. / TI-DSP appears to be making progress, albeit tentatively, in some of the most intractable places, and where military influence is often key to the political and social landscape. DSP’s approach of winning confidence, usually by using military-savvy personnel to engage ‘peer-to-peer’ in the language the military understand, enables DSP to penetrate otherwise impenetrable institutions. An important strategic lesson shown by DSP is that they would not succeed if they presented themselves as a typical advocacy NGO. They have mastered a technique that should be emulated in other settings where ‘professional’ barriers often allow interest groups to remain aloof and immune from influence. / Recommendations for the coming year: / The extension logframe should include at least one qualitative indicator capturing quality of high-level engagements, and a greater emphasis on qualitative measures throughout. / The extension log-frame should also consider where in TI-DSP’s reporting any future work with the Afghan National Security Forces should be reflected. / Extension logframe indicator 2.1 should be amended to reflect the new focus on implementation of the ATT anti-corruption mechanisms [in current draft] / Extension logframe indicator 2.2 should aim to capture the quality and effect of existing engagements with defence industry organisations, rather than setting a new quantitative target. This relates to the issue of TI-DSP potentially spreading itself too thinly. / The revised logframe should include indicators that will help TI-DSP to measure the up-take of its products and absorption of the knowledge it generates. While this is not an easy task, it is a much more robust indicator of influence. Indicators could cover areas such as the specific uptake of tools, uptake of expertise as a result of training, and measures of CSO capacity, for example. / It will be essential for TI-DSP moving into its second decade to take stock of where it has deep connections that can be leveraged for systemic change, and where it finds the balance between breadth and quality. / TI-DSP should continue to ensure effective follow-up on the impact their training has had after the event. TI-DSP is making progress on this, but are not unique in finding it difficult to measure the long term benefits. Their planned systematic evaluation approach should be followed up within the year to see how it develops. / TI-DSP should look at its strategic challenges afresh alongside the recommendation below for a more robust risk matrix. / TI-DSP should review the outcome indicators in the extension logframe to help show more clearly the connection between its work and the outcomes achieved, building on the theory of change. This will also help to trace through the programme’s contribution at Impact level at the end of the programme period. / TI-DSP to ensure that expectations of performance are clear year-on-year, as well as from the baseline to the final milestone. / TI-DSP to redesign the risk matrix to separate risks to achievement of outcomes from risks to achievement of outputs. / TI-DSP to identify and record appropriate mitigation measures for these risks. The substance of this already exists in TI’s work, but needs to be brought out in annual reporting. For example, TI-DSP could describe how the risk to TI country chapters from publishing the Government Index was managed.

8. Review Process
General PPA / TI-S submitted a self-assessment annual report of their progress and performance against the General PPA log frame during this third year of PPA funding. DFID reviewed this annual report and provided feedback on both strengths and weaknesses reminding TI-S of the need to improve year-on-year on VfM, results and transparency. The feedback incorporated comments from a range of officials in relevant country and policy teams. / CHASE PPA / This Annual Review was conducted by the Security and Justice Team in CHASE. TI-DSP submitted a self-assessment annual report of their progress and performance against the PPA log frame during this third year of PPA funding. DFID reviewed this annual report and provided feedback to TI-DSP on both strengths and weaknesses. Feedback was also incorporated from DFID’s Senior Anti-Corruption Adviser.