Type of Review: Annual Review

Project Title: Support for Electoral Reform in Pakistan (SERP)
Date started:	April 2012
Date review undertaken: April and May 2014, final report June 16 2014

Description	Scale
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

## Introduction and Context

What support is the UK providing?
DFID is providing £5.5 million for IFES to implement the Support for Electoral Reform Programme (SERP) from April 2012 to December 2014 in Pakistan (although the programme continues until the end of 2015). / DFID funding amounts to approximately 40% of the $20.4 million project, which is jointly funded with the Canadian International Development Agency (CIDA) and the European Union (EU). This support is intended to build capacity of the Election Commission of Pakistan (ECP) and the delivery of its Five Year Strategic Plan in order to deliver credible federal, provincial and local elections. / Total DFID costs are: £5.5 million to support SERP, and £0.18 for monitoring and evaluating costs.

What are the expected results?
The ultimate impact is contribution to a stable, inclusive and tolerant democratic state in Pakistan that is accountable and responsive to all of its citizens. The outcome is a more credible inclusive electoral process focusing on the conduct of the 2013 general elections and the local government elections. The indicators for this outcome are observer mission assessments of the legal framework, confidence in ECP capacity, voter turnout, the percentage of the ECP’s strategic plan achieved, and confidence in the electoral roll. / Outputs were revised following the 2012 Annual Review. They now cover: / Improved legal framework that ensures transparent electoral procedures that promote genuine and competitive elections – IFES is assisting with drafting and updating legislation including a proposal for a unified electoral law. / Coordination with the international community and advocacy for electoral reforms – IFES is the secretariat for the Election Support Group (ESG). / Increased professionalism and competence of election officials – IFES is assisting the ECP with its short-term and long-term training needs. / Improved and accurate electoral rolls that can be updated and challenged for any inaccuracies –IFES is offering on-going technical assistance that builds on previous support work. / Enhanced capacity of ECP to conduct electoral operations – IFES is assisting with updates and improvements to electoral systems and procedures, and the procurement of ballot boxes. / Strengthened ECP capacity in the conduct of voter/civic education – IFES is assisting with the preparation and implementation of the ECP voter education plan 2012-13. / Increased voter outreach by local organisations ­­– IFES is supporting local organisations to conduct civic and voter education campaigns. / The anticipated results are a more capable and independent ECP that delivers to citizens. This would increase public, political party and civil society confidence in the ECP which would make acceptance of electoral processes and results more likely. This would in turn support more peaceful political transition and more legitimate, accountable and democratic government. Evidence shows that more accountable and responsive states are better at meeting the needs of their citizens and are more likely to be stable than are autocracies or transitional democracies[1]. Moreover, democracies generally have higher economic growth rates than autocracies[2] and faster growth generally means faster reduction in absolute poverty.[3] Effective governance is a key factor underlying economic growth[4] and poverty reduction.
[1] Sen, A (2009) Development as Freedom, Oxford University Press.
[2] Low income democracies have average growth rates 30% higher than low income autocracies. See Halperin H, Siegle J and Weinstein M (2010) The Democracy Advantage: How democracies promote prosperity and peace.
[3] World Bank (2005) Economic growth in the 1990s – learning from a decade of reform. Washington DC
[4] Kaufmaan D. and Kraat, A. (2002) Growth Without Governance, World Bank Policy Research Working Paper No 2928.

What is the context in which UK support is provided?
Pakistan is assessed by the Freedom House Freedom In the World 2013 index as “partly free” and “not an electoral democracy”. It scores 4.5 for freedom, 5 for civil liberties, and 4 for political rights (with 1 being the best and 7 being the worst score)[5]. / The federal and provincial elections in May 2013 were the first in which a civilian Pakistani government completed its full term and transferred power through elections, to another democratically elected government. These elections were held in difficult circumstances with militant attacks, particularly on parties regarded as secular but also on the election administration. / Overall, observers commented that the 2013 elections, although not perfect, were a significant improvement over 2008. Of note, was a rise in voter turnout by about 23%, resulting in 55% registered voter turnout in 2013 compared to only 44% in 2008. There was an improved computerised electoral roll which was duplicate free and based on national identity card data with photographs to verify voter identify. Together this helped to improve trust in the electoral process and reduce potential for fraud. / Nevertheless, there is also recognition of the continuing systemic shortcomings and legal weaknesses. There is some evidence of legitimate grievances. The on-going work of the tribunals from the general elections has, for the first time, categorically evidenced election fraud in some national and provincial assembly constituencies. However, despite this, nobody has suggested that the elections in 2013 could have resulted in a different government, and the overall the outcome of the general elections is accepted. Controversy persists about some individual constituency results and these need to be addressed properly. / Recent protests about the 2013 elections continue and electoral reform is an increasingly political issue. There are moves afoot for a cross-party committee on electoral reform which is a positive move, and the ECP’s commitment to reform is illustrated by their recently launched Strategic Plan 2014 – 2018 which aims to build on progress to date. / IFES supported the ECP with essential election basics necessary for the process, such as working out procedures, training and ballot box procurement. Without such support from IFES, and also UNDP, it is not clear how the ECP would have been able to fulfil its responsibilities effectively and for the general election process to have been overall accepted. / The long-overdue local elections (LEs) have been problematic with the Supreme Court ruling for their implementation, but provincial legislation and delimitation not being ready or sufficient. LEs were held in Balochistan in December 2013 in very challenging conditions, particularly in regards to security and a problematic legal framework. There was a lack of scrutiny of these elections, but it is clear that there were very serious and pronounced problems with their implementation (see assessment report by Democracy Reporting International). At the time of writing it is not clear when the LEs will take place in other parts of Pakistan. Again this points for the need for continued improvements in the electoral process. / Some decisions of the ECP, which have been criticised by observer groups and other stakeholders, have limited the effectiveness of the institution and the impact of IFES’s work. The ECP has historically been less active in developing its long-term capacity and integrity. The politically sensitive nature of the ECP and its entrenched institutional culture make for a demanding work environment. For instance, the ECP has been operating without a permanent Chief Election Commissioner (CEC) since the resignation of the former CEC following the (indirect) presidential elections of 2013. Clear leadership is needed to spearhead and champion the needed reforms. / The media is generally regarded as having become increasingly free in recent years in Pakistan. The beneficial effect of this on elections was commented upon by recent key informants in an impact evaluation of DFID-election programming in Pakistan. However some issues and locations in Pakistan remain difficult if not impossible to report on; for example parts of Balochistan, Karachi, and the Federally Administered Tribal Areas (FATA). / In addition to the DFID funding to support the ECP, the BHC/FCP Conflict Pool is providing £800,000 to IFES to support training of election officials. The ECP is also supported by a $14.5 million for the phase 1 by United Nations Development Program (UNDP) / UN Women implemented programme (2012-2014).
[5] See Freedom House Index Freedom in the World 2013. http://www.freedomhouse.org/report/freedom-world/2013/pakistan#.U1-XW15N1Fw.

## Section A: Detailed Output Scoring

Output 1.1: Improved legal framework that ensures transparent electoral procedures that promote genuine and competitive elections
Output 1 score and performance description: A Outputs met expectations
Progress against expected results: / Indicator Baseline Milestone 2 Dec 2013 Achieved Target Dec 2014 Score / 1. Number of new and revised regulations drafted with IFES assistance that improve the electoral process, and the number of these approved by the ECP 0 +2 drafted (1 approved) 37 drafted and 37 approved by the ECP Baseline+4 drafted (2 approved) A / 2. Number of laws or amendments designed to improve credibility of elections that were drafted with IFES assistance and approved by the ECP, including recommendations that have been advocated for by local organizations with IFES support and by international stakeholders based on international standards. 0 +2 drafted (1 approved) 38 amendments drafted and 38 approved by the ECP Baseline+4 drafted (2 approved) A / Indicator 1: Number of new and revised regulations drafted with IFES assistance that improve the electoral process, and the number of these approved by the ECP. / For the May 2013 general elections IFES worked with the ECP in the preparation of four codes of conduct that served as a regulatory framework. These were for: contesting candidates and political parties, observers, security personnel and polling staff. The Codes of Conduct were very positive in promoting a level playing field and confidence in the Election Commission. More broadly some stakeholders argued that this helped develop cross-party consensus which helped to reduce overall levels of pre-election violence during the campaign period which in turn helped to increase voter confidence and belief that there was a fair chance of winning in these elections. / However the ECP was criticized for not establishing in the regulations a sufficient mechanism for their enforcement. Also for not regulating other key parts of the election process, in particular electoral dispute resolution (EDR). For example NDI/ANFREL (National Democratic Institute / Asian Network for Free Elections) noted “… several important issues were insufficiently addressed, including the electoral dispute resolution system, candidate scrutiny process, gender equality measures, rules for observers, campaign finance, and results compilation and consolidation mechanisms, among others.” Therefore continued focus is needed on this area. However further ECP regulatory control is challenging given the organizational and political implications of increased ECP management authority. Increased ECP control of the process could reduce opportunity for local-level arrangements that are seen by some as providing opportunity for fraud. / Although the ECP has undertaken consultation, in marked improvement to previous administrations, there is some criticism for not having undertaken a stronger consultation process in the development of the codes of conduct.[6] IFES and UNDP’s support to the ECP in post-election consultative review workshops is a positive initiative. Inclusion of political parties in addressing the regulatory framework more widely beyond the codes of conduct is advisable for improving the quality of regulations and political confidence in the ECP. / For the local elections IFES assisted the ECP and the Sindh government to draft or revise regulations (known as “rules”). However establishment of a regulatory framework for the local elections is problematic as to date all provinces have given powers to establish secondary administrative legislation to provincial authorities rather than the election commission. This fundamentally weakens the ECP’s ability to have control of the election administration process. The ECP did not explicitly call for increased powers, but rather sought to have influence with the respective provinces in the drafting of their rules. / An assessment of the Balochistan LEs by Democracy Reporting International (DRI) noted “This is in keeping with the constitutional provision for provinces to ‘by law, establish a local government system’[7]. However, this arrangement strips the ECP, the federal body constitutionally mandated to hold local government elections[8], of the ability to determine how it will meet its mandate. This is problematic in that the provincial government, who is not always trusted to be neutral, has involvement in election administration, deciding matters such as what results forms will be used. Under these arrangements rules can be crafted without full election expertise and experience, and the ECP can be left operating in an uncertain legal environment as rules can be changed at any time. Thus the ECP is powerless[9], and accountability for the election is dispersed and thereby weakened.[10]… The ECP advocated for some ECP commentary and involvement in the rules. They wrote a letter to the provincial governments (Chief Secretaries) on 18 July 2013, intended for consideration ‘at the time of legislation or prescribing the Rules for local government elections’. This notes ‘the ECP would appreciate if these are shared with it before finalizing them.’… However, the ECP does not appear to have emphasised the fundamental problem it has in not being able to determine the rules needed for administering elections.” Thus it appears that further ECP efforts are needed to be in control of its ability to regulate its own actions. / Indicator 2: Number of laws or amendments designed to improve credibility of elections that were drafted with IFES assistance and approved by the ECP, including recommendations that have been advocated for by local organizations with IFES support and by international stakeholders based on international standards. / IFES assisted the ECP in drafting a bill to amend the Representation of the People Act 1976 (RoPA). Twenty three proposed amendments were all approved by the ECP. However late timing meant the bill was not considered due to the dissolution of the National Assembly at the end of its term. While this limited impact as amendments were not secured in law, procedural improvements were still incorporated for the 2013 general elections through various regulations issued by the ECP. / The high level of approval by the ECP of IFES proposals appears to indicate a strong working connection between IFES and the ECP. It may also be beneficial for IFES to make more legislative reform proposals to the ECP that may not be approved in order to help increase understanding of ways forward for the legal framework. / Similarly IFES assisted the ECP and Sindh Government to draft six amendments to the Sindh Local Government Act, 2013. IFES also assisted the ECP and cantonment authorities to draft nine amendments to the Cantonment Board Ordinance. / However observation mission reports document the continued shortcomings in the legislation and the on-going need for legal reform.[11] Primary responsibility for such reform rests with law-makers, but the ECP has a key role to play in advocating for reform and in making practical proposals. Tracking of timely submissions by the ECP of proposals for legislative amendments is important for assessment of impact of the SERP programme. / The legal framework for the Balochistan LE was subject to criticism. The DRI assessment noted “[p]primary legislation is weak, giving excessive powers to the government including deciding aspects of the election system, having responsibility for delimitation, and determining the rules and regulations (secondary legislation)… The legal framework does not sufficiently cover time limits for elections and does not adequately provide for scrutiny of the electoral process. A further problem with the legislation was its lack of availability leaving some stakeholders referring to obsolete laws and old arrangements.” Thus further efforts are needed by the ECP, and others, to establish a legal framework that better provides for electoral activities. / Additional comment / IFES have clearly exceeded the identified indicator targets and there have been consequent improvements in the legislative framework for elections. This spurt in regulatory activity may be attributed to the general elections and therefore may not be sustained. However, as noted by observer groups, problems remain with both primary legislation and regulations (or lack of) in core aspects of the election process. Therefore while targets have been greatly exceeded, the continued shortcomings in fundamental aspects of the legislative framework, mean that overall a score of A (outputs met expectations) has been given. / Recommendations: / Consideration be given to amending one or both of the 2014 targets, which have been exceeded. Alternative or additional target(s) could include the holding of consultations, or the number of amendments passed to respective legislatures and/or promulgated (prepared with IFES’s involvement).[12] / IFES work with the ECP to undertake more systematic consultations with political parties and civil society organisations at all stages of development of ECP regulations. / Further work is undertaken to build the ECP’s own capacity so that it is demonstrating self-sufficiency with reduced reliance on IFES for preparation and drafting. / IFES work in coordination with UNDP and others also advocating and working for legal reform, including Free And Fair Election Network (FAFEN) and DRI (through the EU’s parliamentary assistance programme). / Impact Weighting (%): 20% / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? N
[6] For example the EU Election Observation Mission (EOM) final report 2013 notes: “Based on varying levels of consultation, the ECP issued five codes of conduct... [These] … were limited in their lack of clear legal status and provision for enforcement mechanisms, with discretion typically left to ROs and DROs. Shortcomings in some of the codes might have been prevented by more substantial consultation. For instance the Code of Conduct for Observers has little provision for the rights of observers, and instead contains a clause that if not followed in full good faith, could compromise observers’ independence (‘Observers shall follow instructions issued from the Election Commission and State authorities including security officials and maintain a respectful attitude towards them’).”
[7] Constitution of Pakistan, article 140A.
[8] Constitution of Pakistan, articles 140A and 219D.
[9] For the national and provincial assembly elections, the Representation of People Act (RoPA) section 107 gives the ECP the power to make rules (although approval of the President is required). Similarly in the Electoral Rolls Act (section 28).
[10] Responsible staff of the provincial authority involved in drafting the rules indicated to the EAM a preference for the ECP framing the rules for their own operational activities.
[11] For further information also see DRI’s “Pakistan Election Laws and International Standards” and Local Election Framework Assessments for individual provinces. http://www.democracy-reporting.org/publications/country-reports/pakistan.html.
[12] This would increase the risk rating given the ECP’s track record with some delay in referral to law-makers, and parliamentary approval is clearly beyond the programme’s control. One such measure may provide an indication not just of IFES/ECP activity, but of impact/effect. Consequent programmatic efforts to promote approval of legislative proposals would be necessary and are in keeping with the coordination and advocacy role covered by IFES (see output 1.2).

Output 1.2.Coordination with international community for the advocacy of electoral reforms
Introduced after the last Annual Review. / Output 1.2 score and performance description: A+ Outputs moderately exceeded expectation
Progress against expected results: / Indicator Baseline Milestone 2 Dec 2013 Achieved Target Dec 2014 Score / 1. Scale of the outreach of ESG meetings per year 0 100[13] 256 100 A++ / 2. Number of times the electoral stakeholder speaking points are revised and officially endorsed by members 0 2 2 Baseline + 4 A / Indicator 1: Scale of the outreach of ESG meetings per year / Sixteen Electoral Support Group (ESG) meetings were held with an average of 16 participants, well exceeding the milestone target. However such levels of interest in electoral matters will unlikely be sustained as typically there is increased interest at the time of national elections and then a decline in interest. IFES play a key role in positively supporting the involvement of different organisations and the smooth running of the ESG, the primary information and coordination mechanism on electoral matters for donors, implementers and embassies. / Indicator 2: Number of times the electoral stakeholder speaking points are revised and officially endorsed by members / IFES report that the speaking points were revised by a small group and shared with all ESG members for their endorsement in February and September 2013, thus the target has been achieved. / Efforts to have coordinated messaging on electoral reform will be of increased importance in the remaining part of the project as the period between elections is an optimal time for reform when there is reduced operational pressure (although the outstanding local elections are anticipated). Furthermore the advocacy undertaken by DRI will no longer be complementing the work of IFES and others working with the ECP (as DRI’s main funding in Pakistan has now finished). / Additional comment / The ESG has provided a forum for coordination on technical and political levels. It has effectively provided for a circulation of information and collective discussion on electoral needs. IFES have ensured that the ESG runs smoothly and efficiently and is responsive to changing electoral circumstances and the needs of members. Under the current programming period the ESG has been extended to include national implementers (including FAFEN who receive DFID funding for their election programming) allowing for greater information exchange and organizational understandings. / IFES’s circulation of electoral news clippings is positive in promoting up-to-date electoral knowledge and engagement in electoral matters. Similarly IFES’s factsheets (ten in total) provide helpful factual information in a user-friendly format that facilitates greater understanding, and it is thus positive that they are publicly available. The ESG website is in need of updating to reflect the changed membership and the current electoral situation. / Recommendations: / The ESG website is revised as currently it is out of date (referring to the 2009 elections) and does not provide for transparency of donor actions. The Wikipedia page on the ESG would also benefit from updating for accuracy. / Impact Weighting (%): 5% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? Y
[13] Calculated by (number of meetings) x (average number of organizations per meeting).

Output 2.1 - Moved to outcome level based on 2012 Annual Review.

Output 2.2: Increased professionalism and competence of election officials
Output 2.2 score and performance description: A – Outputs met expectation
Progress against expected results: / Indicator Baseline Milestone 2 Dec 2013 Achieved Target Dec 2014 Score / 1. The percentage increase in the performance of temporary election staff on election day as a result of IFES trainings = Average of 70% of PrOs and 30% of ROs performed Election Day duties correctly during the 2008 election N/A N/A Average of 75% of PrOs and 40% of ROs performed their Election Day duties correctly during Pakistan’s General Election - / 2. Percentage increase in job skills and knowledge for the permanent ECP staff through the trainings supported by IFES 0 An average 15% increase in knowledge An average 15% increase in knowledge An average 15% increase in knowledge A / 3. Number of permanent and temporary ECP staff trained with support from IFES 0 ECP Temporary Staff: 236,000 / ECP Permanent Staff: 100 ECP Temporary / Staff: 245,689 / (61,713 [25%] / female) / ECP Permanent / Staff: 120 (119 male / and 1 female) Total ECP Temporary Staff: 238,000 (15% female) / Total ECP Permanent Staff: 300 (33% of female permanent ECP staff) A+ / Indicator 1: The percentage increase in the performance of temporary election staff on election day as a result of IFES trainings. / IFES note “The source of this information is FAFEN’s Election Day Process Analysis. The report was not released in time and we did not originally expect to have it by the end of the year, which is why the milestone is N/A.” In January 2014 FAFEN published their “National Assembly Election Results Analysis – Parallel Vote Tabulation (PVT), Comparative Turnout and Party Trends” only. FAFEN only published their final report in June 2014 so that this information will be used for the final analysis of SERP programme at project completion report stage in December 2014. / One of the major constraints faced, is a lack of ECP data about the performance of polling staff, with again responsibility for management of polling being deferred to Returning Officers (ROs). Similarly data is not collected by the ECP on the performance of ROs. This is significant as ROs carry responsibility for an election within a constituency and therefore are wielding extensive power and authority. The lack of data on performance makes it hard for the ECP (and donors) to see any improvements or to understand and then act on problems arising. The evidence being found by tribunals shows the need for further ECP investigation of problems, and that serious malpractices are occurring in some areas due to ROs. The problems indicate that further measures are needed to control the work of ROs, so that election laws and arrangements are consistently implemented and there is a swift check and response to any shortcomings. / The EU Election Observation Mission (EOM) observers were only present in a limited number of locations, including Balochistan, FATA and large parts of KP. The EOM’s final report notes “[m]ost of the polling booths observed were rated as satisfactory or good. However 9% were rated as poor or inadequate… Counting was more problematic, with 9 out of 64 stations rated as poor or inadequate. In 17 cases results forms were not correctly filled in, and in half of the observations the results forms were not displayed. Similar transparency problems were also found in consolidation at the constituency level”. NDI/ANFREL note in their final report that “[m]ost aspects of election day were assessed positively by NDI-ANFREL observers, though administrative problems were noted in polling stations throughout the country and there were allegations of irregularities in several areas where NDIANFREL observers did not visit…The process benefited from greatly improved electoral rolls and the widespread use of a text message-based system that allowed voters to verify their polling locations… While these administrative problems did not seriously impair the integrity of the elections, they could be damaging in future elections if allowed to persist.” Thus, whatever improvements there have been, there still remains a high number of stations rated negatively, which could be problematic in future elections (particularly if results are overall less accepted). / The EU EOM also notes that there were “[l]ast-minute changes in polling personnel resulting in untrained staff being used.” And that the extent of this problem is not known. IFES also identify that there was a lack of ownership by District and Regional Election Commissioners which caused problems with training. The high level of negative ratings by EU EOM observers, and the highly concerning practice of untrained staff being used, show the continued need for training and stronger ECP management and accountability mechanisms. / The ECP took the positive initiative to introduce the collection of gender-disaggregated polling data. However in practice this was not sufficiently realised with large numbers of polling staff failing to fulfil gender reporting requirements. / It remains the case that IFES and UNDP are providing the training rather than supporting the ECP in delivering the training (although some ECP master trainers were involved). This is consistent with the programme’s focus on immediate general election delivery needs. Some progress was reportedly made with for example the conducting of two training needs assessments, a training advisor was provided to the Federal Election Academy (FEA) and six provincial training officers. However the lack of ECP involvement in and responsibility for the training raises serious sustainability questions. / IFES’s third-party monitoring of 27% of all trainings rolled-out was positive in providing a check on how later stages of the training were conducted. Ninety-one percept of presiding officer participants were reportedly satisfied with the training. / IFES worked under time pressure with the ECP to develop and dispatch the District Returning Officer (DRO)/RO handbook for the Balochistan LEs. However this was only in English, which according to DRI interviewees made it difficult to use, and there was no accompanying training. DRI noted that for the Balochistan elections ROs “were from the civil administration which resulted in accusations of partisan bias, a problem exacerbated by a lack of written instructions from the ECP with parts of the process left open to subjective interpretation and inconsistent application. Various stakeholders indicated that if they had problems with the election process it was more effective to go to the Deputy Commissioners rather than ECP bodies, as the civil administration has more authority over ROs, and therefore more influence on the election process.” It therefore appears that the ECP did not take sufficient measures to provide for improved performance of ROs during the Balochistan LEs. / Indicator 2: Percentage increase in job skills and knowledge for the permanent ECP staff through the trainings supported by IFES. / IFES report an average 15% increase and that for some BRIDGE (Building Resources in Democracy, Governance and Elections) training pre- and -post tests were not appropriate given the seniority of the participants, “but a questionnaire administered at the end, and the discussions during the workshop, showed that participants were able to think critically about the polling, counting and results process.” / Continued training remains important given the weaknesses identified and that the apparent capacity gap among mid-level officers who would be next in line for management positions. / Indicator 3. Number of permanent and temporary ECP staff trained with support from IFES / IFES has organised BRIDGE training and has implemented training for temporary officials (ROs, polling staff and for tribunals). Handbooks and materials have been prepared and training delivered. Training delivery was divided with UNDP on a geographical basis for electoral staff. / Additional comment / IFES activities appear to have been undertaken according to plan and have responded to ECP interests. However ECP and RO management decisions have limited the effectiveness of IFES (and UNDP’s) assistance. Furthermore responsibility for training has been with IFES and UNDP, without the ECP substantially building its own capacity. / Recommendations: / Increased focus on supporting ECP management of polling officials (as opposed to deferring this responsibility to ROs). For example through requiring training to be mandatory, record-keeping, routine supervisory checks, active investigation of possible problems arising, and responding to malpractices. / By-elections and local elections are used to promote ECP capacity development through increased ECP involvement in and responsibility for training of polling officials. / Increased training on polling staff providing gender-disaggregated data (as required for national elections). / There is more focus on planning with the ECP and FEA on how to build long-term capacity, including of mid-level officers. / Documentation of actions by the ECP that are or are not consistent with the ECP establishing its own capacity rather than relying on donors. / Revise indicators to include 1) more focus on ECP management of election officials and 2) increased ECP capacity to deliver trainings rather than relying on donor assistance. / Impact Weighting (%): 20% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N

Output 2.3: Improved and accurate electoral rolls (ERs) that can be updated and challenged for any inaccuracies
Output 2.3 score and performance description: B - Outputs moderately did not meet expectation
Progress against expected results: / Indicator Baseline Milestone 2 Dec 2013 Achieved Target Dec 2014 Score / 1. Number of procedures to improve the management of the electoral roll developed by IFES and the number of these accepted by the ECP 0 2 drafted (1 accepted) +4 drafted, still / under consideration / by the ECP (2 / address / recommendations / made by / international / observer missions) Baseline + 4 drafted (2 accepted) (at least 1 procedure will be based on the recommendations of international observer missions including EU EOM) B / Voter turnout for the 2013 General Election increased by about 23%[14] compared to turnout in the 2008 elections. Overall, 55% of registered voters went to the polls to cast their votes on 11 May, in comparison to only 44% in 2008. While there may be many reasons for the increased turnout, the numbers indicate more trust among voters in the electoral process since 2008. All of the reforms put in place since the last elections have helped increase voter confidence in the system. / Indicator 1: Number of procedures to improve the management of the electoral roll (ER) developed by IFES and the number of these accepted by the ECP / IFES has been working with the ECP to accomplish the objectives set out in its first Five-Year Strategic Plan (2010-2014). This included producing a significantly improved computerized, duplicate free electoral roll based on voters’ national identity card data and with photographs. / This involved IFES producing ER concept papers for the ECP prior to the general elections, however there was limited engagement on these. Later an Additional Director General (Electoral Rolls) was appointed to whom IFES sent four highly relevant concept papers: / 1. ECP’s strategy for future voter registration and updating of electoral rolls / 2. Sorting of electoral rolls on voter’s NIC number or name as mentioned on the NIC / 3. Anonymization of electoral rolls / 4. One electoral roll for one polling station / Whilst there have been some clear short term improvements in the ER which made a difference to the 2013 elections as outlined above, setting a precedent to follow and build on in the future, the ECP’s full acceptance of suggested procedures is beyond IFES’s control. IFES is continuing its discussions with ECP on this as well as presenting written papers. It will be important to build on progress to date for future sustainability and consolidation. / Additional comment: / The ER is critical to electoral integrity and confidence in the administration. The political ramifications of a problematic voter list can be seen from the 2007 controversies. / Key informant interviews from DFID’s recent impact evaluation found that improvements in the ER was regularly cited as one or the main improvements in the 2013 general elections process. Whilst recognising the role of the SERP programme and IFES, it is important to note that the improvements were also in large part attributed to the involvement and actions of NADRA (responsible for civil registration). IFES, along with FAFEN played a key role in supporting the ECP in opening up its doors and working in positive collaboration with NADRA. IFES are also planning on supporting ECP understanding through BRIDGE training on voter registration. IFES made efforts in relation the reduced levels of female registrants (there are over 10 million fewer women registered than men), in particular through a research study on the subject. / To date, the arrangement with NADRA was a one-off agreement, and to date, no formalized and systematic mechanism has been established for how the ER will be comprehensively updated in the future. Additionally the NADRA leadership has been changed. The ECP’s earlier door-to-door exercise (to allocate voters to the correct location) was subject to criticism by FAFEN which noted “Many reports suggest that the ECP verification officials, drawn from government departments, particularly education, are not visiting the neighborhoods, rather requiring people to come to a central place for verification… There have also been reports that the verification officials have not been trained adequately, and therefore, performing bare minimum task of verification, avoiding addition and deletion of voters or correction in credentials”.[15] / Basic ER data was not made available for the Balochistan LEs, for example on the total number of registered voters. There is a risk that the ER will be controversial in the upcoming LEs as there will have been a longer intervening period since the general election (and therefore the ER records will be more out-of-date), and also smaller constituency sizes mean that small inaccuracies in the ER can more easily affect an outcome. / Within this context where short term improvements had a major impact, it is also important to recognise that further improvements and consolidation are critical for the strengthening of the electoral process. Continued advocacy by IFES is therefore important given the severe negative impact there can be to a faulty ER and the time it takes to establish and update a reliable inclusive ER. / Recommendations: / IFES continue to advocate for implementation of necessary ER developments presented in concept papers, and also support advocacy by others. This could include working with NADRA and political parties to promote a sustainable solution. Research could also be undertaken to show the risks and problems arising if enduring agreed mechanisms for ER updating are not found. / Should the ECP be unresponsive to implementation of positive concepts promoted by IFES, it is recommended that IFES consider how else to use the allocated budget/resources. For example on further research, audits etc. / Impact Weighting (%): 10% / Revised since last Annual Review? Y / Risk: High / Revised since last Annual Review? N
[14] In the 2008 General Elections, 35,637,072 people participated. In comparison, 46,217,482 voters voted in the 2013 General Elections.
[15] FAFEN, “10 million citizens missing on the draft electoral rolls 2011”, undated.

Output 2.4: Enhanced capacity of the ECP to conduct electoral operations
Output 2.4 score and performance description: A+ – output moderately exceeded expectation
Progress against expected results: / Indicator Baseline Milestone 2 Dec 2013 Achieved Target Dec 2014 Score / 1. Number of electoral operations systems and procedural improvements proposed by IFES, and the number of these approved by the ECP 0 +4 drafted (2 approved) +7 drafted (4 / approved) Baseline +7 drafted (including one concept note on Integration of gender in ECP’s operations) and (4 approved) (at least 2 of the improvements will be based on the recommendations of international observer missions including EU EOM) A+ / 2. Number of ballot boxes procured for elections through SERP 0 41,000 ballot boxes used for general and other elections 41,000 ballot boxes used for general and other elections 41,000 ballot boxes used for general and other elections A / Indicator 1: Number of electoral operations systems and procedural improvements proposed by IFES, and the number of these approved by the ECP / During this election year, with maximum pressure on ECP electoral operations, IFES supported the ECP with seven guidelines. Four were approved – on IDP voting, uniform voting/closing/results procedures for LEs, appeals before Appellate Tribunals and the tribunal process. Three were not approved. These were related to aspects of the election process that became controversial - scrutiny of candidate nominations, options for out of country voting, and a handbook for the complaints process. The ECP’s lack of guidance and provision for consistency in candidate registration and for complaints was subject to criticism by the observation missions. / Indicator 2: Number of ballot boxes procured for elections through SERP. [Note there is no opportunity for exceeding expectations on this indicator.] / The ECP’s dependence on the international community for a basic predictable election commodity such as ballot boxes raises questions about the ECP’s capacity to plan for its own needs and of sustainability. This was a result of a Supreme Court ruling that affected the number of polling stations and ballot boxes required. However the ECP’s apparent lack of ability to respond to changing circumstances shows further need for support in self-sufficiency. There continues to be a lack of linking of constant and fluctuating ECP election administration costs to the federal budget and insufficient clarity over responsibility for the financing of local elections. / Additional comment / The actions of ROs have been subject to criticism both in the general elections (when they were from the judiciary) and Balochistan LEs (when they were from the local government). The ECP has used its own staff as ROs for by-elections. Problems have arisen related to allegations of partisan behavior by ROs from the local administration, and from wide variation in RO actions, resulting in inconsistent fulfillment of citizens’ rights. For example in the general elections the same candidate was rejected in one constituency and accepted in another. Therefore fulfillment of electoral operations, beyond merely logistical implementation, requires the ECP to address the issues of RO independence and consistency. / Recommendations: / IFES continue to support the ECP with proposing improvements for the implementation of general elections (based on lessons learned) and for the upcoming local elections. / Greater focus is given to ECP advance planning capacity and to securing state funding for basic election commodity items and unforeseen circumstances. / IFES try to support the ECP in addressing issues of RO independence and consistency. However ECP interest in asserting itself more strongly, and in taking more responsibility for constituency-level actions, may be limited. / Impact Weighting (%): 25% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N

Output 3.1: Strengthened ECP capacity in the conduct of voter/civic education
Output 3.1 score and performance description: B - Outputs moderately did not meet expectation
Progress against expected results: / Indicator Baseline Milestone 2 Dec 2013 Achieved Target Dec 2014 Score / 1. Number of components in its voter/civic education plan(s) implemented by the ECP with the support of IFES 0 = first time for establishment of plan 6 components of the voter education plan implemented; 1 civic education focal person appointed/ / designated / Civic education plan developed 6 components of / the voter education / plan implemented; TBD after development of civic education plan B / Indicator 1: Number of components in its voter/civic education plan(s) implemented by the ECP with the support of IFES / IFES report that to varying degrees the six voter education components were implemented with assistance from IFES and UNDP. The civic education plan was due to be developed after the post-general-elections review. However LE preparation has diverted attention away from long-term planning and development, to immediate voter education needs This is likely to continue with the further LEs planned. No designated civic education focal person has been appointed by the ECP. / For the LE civic/voter education IFES hosted consultative meetings with the ECP, CSOs and parties in the provincial capitals and Islamabad. IFES is working with the ECP on province-specific voter education. For the Balochistan LE, held at somewhat short notice, DRI noted “The low turnout and high number of invalid ballots for the 2013 general elections put an onus on targeted voter education initiatives. The United Nations Development Programme (UNDP) assisted the ECP in production of voter education posters and IFES with spots for the electronic local media. However their impact appears to have been limited with stakeholders generally unaware of any such initiatives.” / The ECP appears to continue to rely on IFES (and UNDP) for implementation, not just technical support. The extent of actual capacity development of the ECP for voter/civic education is not yet evident. IFES have made constructive attempts to build ECP capacity on voter/civic education, through for example a second BRIDGE training module for high ranking ECP officials. This included a focus on the participation as voters and candidates of women and other marginalised groups. / IFES will conduct a series of surveys to assess the impact of voter education efforts. / Additional comment / Specialised voter and civic education for groups marginalised in the election process continues to be of particular importance and worthy of dedicated resourcing. In particular, women (especially in some parts of the country), and Ahmadis and other religious minority voters. / Recommendations: / Increased focus on building ECP capacity to provide civic and voter education, rather than on delivery. To include working on ECP planning for costs involved and advocating for such funding. Documentation of actions by the ECP that are or are not consistent with the ECP establishing its own capacity rather than relying on donors. / Intensified focus in civic and voter education promoting the participation of women (in coordination with UN Women) and other vulnerable groups. / By-elections and local elections are used to promote ECP involvement in and responsibility for development and delivery of civic and voter education. / Specialist voter education may be advisable to show any improvements the ECP is undertaking to mitigate against election fraud, in order to counter the on-going narrative of fraud in the general elections that continues. / Impact Weighting (%): 10% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N

Output 3.2: Increased voter outreach by local organizations
Output 3.2 score and performance description: A+ - Outputs moderately exceeded expectation
Progress against expected results: / Indicator Baseline Milestone 2 Dec 2013 Achieved Target Dec 2014 Score / 1. Number of voter/civic education campaigns conducted supported by IFES 0 +4 +7 Baseline +7 A+ / 2. Number of citizens reached by voter/civic education campaigns conducted supported by IFES 0 +500,000 Approximately 880,000 Baseline +550,000 A+ / Indicator 1: Number of voter/civic education campaigns conducted supported by IFES / IFES have supported CPDI PakVoter website, CCP social mobilization through students and Ulema (two campaigns), Mindmap social media (three campaigns), and PAK Women voter education and advocacy for people with disabilities. Campaigns were varied in the mediums used, for example in working with religious scholars and social media. / Indicator 2: Number of citizens reached by voter/civic education campaigns conducted supported by IFES / IFES report that a minimum of 30,321 women were reached by the campaigns, which is a modest number relative to the total and to need (with over 10 million less women registered than men). IFES also note that the actual number reached is likely to be much higher given that a significant number of women would have seen banners, heard radio campaigns etc. / Additional comment / The engagement of a variety of CSOs in voter outreach is positive to avoid over-reliance on a few involved NGOs. The use of smaller local NGOs may also have particular use in addressing issues of severe under-participation by women in certain parts of the country. / The milestones were strongly exceeded. However on-going work in this area may be undertaken in regards to by-election and any LEs that take place. / Recommendations: / Civic and voter education campaigns are more targeted to women and other under-represented group, adapted to local patterns of participation. / Impact Weighting (%): 10% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the log frame been updated since last review? Yes, to incorporate recommendations of the previous Annual Review. / 1.2 Overall Output Score and Description: A+ Outputs moderately exceeded expectation / Output Score Weighting / 1.1 Improved legal framework that ensures transparent electoral procedures that promote genuine and competitive elections A 20% / 1.2 Coordination with international community for the advocacy of electoral reforms A+ 5% / 2.1 (Moved to outcome level based on previous Annual Review) - - / 2.2 Increased professionalism and competence of election officials A 20% / 2.3 Improved and accurate electoral rolls that can be updated and challenged for any inaccuracies B 10% / 2.4 Enhanced capacity of ECP to conduct electoral operations A+ 25% / 3.1. Strengthened ECP capacity in the conduct of voter/civic education B 10% / 3.2. Increased voter outreach by local organizations A+ 10% / Overall Score A+ 100% / 1.3 Direct feedback from beneficiaries / N/A (desk review undertaken based on documents and prior experience with elections in Pakistan up to and including 2013).
1.4 Summary of overall progress / IFES have made strong progress with most SERP indicators. IFES fulfilled the required outputs, all of which have relevance to improved electoral processes in Pakistan. / In keeping with donor and ECP priorities, there was a strong focus on election delivery for the national elections, which were overall accepted. This is an important achievement given Pakistan’s history of troubled elections and interruptions of the democratic mandate. The work of IFES, and UNDP, has been crucial in supporting, and at times directly undertaking, the responsibilities of the ECP. Without the supply of ballot boxes, the training of staff, the voter education etc. it is not clear how the election would have been administered and accepted. The domestic and international importance of completion of this democratic test cannot be over-estimated, especially in the face of direct militant challenge to the election process and therefore the democratic order. / However dispute over the 2013 general elections still continues about a number of constituencies and weaknesses in the system. The findings from the tribunals show the on-going systemic vulnerabilities. / Some of the ECP actions have limited some of the effectiveness of the organisation and the impact of IFES’s work. This has resulted in shortcomings in meeting some indicators and has limited impact of IFES’s positive actions. For example enforcement of the codes of conduct is dependent on ROs, however ROs have been very variable in their actions and the ECP has not asserted authority to address this variation in implementation. Similarly training of polling staff has more limited effect if some trained staff are then not used and instead untrained personnel work, and there is no system to record or review such changes thereby impeding institutional responsibility and learning. Another example is that the ECP did not provide the ECP-prepared unified electoral law draft to the parliament for consideration until the very last moment just some months before the general elections[16]. / The more-challenging part of IFES’s work of building sustainable increased capacity is now of a greater priority, given that the general elections have been held and there is limited time remaining in the programme. However the on-going LEs may further delay capacity building in the name of operational pressure. The extent to which the ECP will be seeking or accepting of technical assistance that is focused on institutional reform (beyond planning) is not yet evident. / Overall DFID’s funding to SERP has an important role and financial value, especially given the size of the population affected by the contribution and the political risks at stake. The achievements of the programme to date can form the basis of consideration of long-term strategies to build the integrity and sustainability of the institution.
1.5 Key challenges / The political context that the ECP operates in with elections being historically and currently highly controversial. / The timing and extent of required ECP activities for the LEs are not certain making ECP and assistance planning difficult. / The uncertain level of interest of the ECP leadership in election reform and capacity development. To date although the ECP has and is undertaking strategic planning, implementation has been inconsistent, including on major points (such as polling station results transparency). / Returning Officers continuing to work with high levels of autonomy meaning that the ECP has limited control over electoral activities. / Building ECP capacity as opposed to implementing on behalf of the ECP. / Uncertain ECP leadership with an Acting CEC in post for an extensive period. / Limited capacity of ECP staff base overall. / Lawmakers’ limited progress with legal reform. / Changed NADRA leadership may make electoral roll arrangements more complex. / Coordinating with the UNDP programme. / Reduced international scrutiny of local elections, thus there is less information available on implementation issues and reduced focus on the ECP. / Reduced international community interest in electoral issues between elections.
1.6 Annual Outcome Assessment / Outcome Indicator 1: Percentage of international and domestic observer missions that report that the legal framework provides a sound basis for credible elections / The EU EOM noted “… some aspects of the current legislation, such as the subjective candidacy requirements, are not consistent with the ICCPR. Furthermore there are some omissions, specifically in regards to access to administrative remedy in case of dispute, and a lack of provisions for transparency… The legal framework has been improved through various amendments to the Constitution.” / NDI/ANFREL noted “The elections took place under an improved legal and regulatory framework... However, several important issues were insufficiently addressed, including the electoral dispute resolution system, candidate scrutiny process, gender equality measures, rules for observers, campaign finance, and results compilation and consolidation mechanisms, among others.” / FAFEN’s final report is not yet available. / In conclusion observer groups note an improvement but still a problematic legal framework and do not comment that it is a sound basis for credible elections. Therefore further work is need in this area by the ECP to support an enhanced framework (although final responsibility lies with law-makers). / As noted above the ECP’s submissions to parliament were not at an optimal time, and ultimately the legal framework is a parliamentary responsibility. / Outcome Indicator 2: Percentage of international observer and domestic observer missions, political parties and citizens reporting confidence[17] in the capacity of the ECP / The DFID election impact evaluation found that key informants reported increased confidence in the ECP prior to the general elections, primarily as a result of its new leadership, the electoral roll and the SMS service. It was noted that these improvements were largely due to the constitutional amendments providing for a more inclusive appointment process for ECP leadership, and that the improvements in the electoral roll and the SMS service involved NADRA. / Confidence was seen as reducing following the general election. The ECP’s general capacity was commonly seen as fundamentally limited, with the organisation having a dependence on external agencies for significant parts of its core responsibilities and for its achievements. / It was also noted that the perceptions at the macro level on overall improvements in the process, differed with the perceptions at the community level which very much depended on the experience of voters on election day. Similarly, the impact assessment emphasised the importance of group voting behaviour at the community level rather than individual agency, where group identity, family affiliation, patron-client relationships, local power relations all impacted on the elections. This is a useful reality check and points to the structural, political, social and cultural context which shape behaviour in Pakistan. It is in this context that the development interventions are working and change is necessarily a long term process. / This partly explains the findings of the PILDAT’s September 2013 “Assessment of the Quality of Democracy”[18], based on 23 senior experts’ opinions, gave the independence of the ECP a score of 58.8%, down from 63.4% in 2012. The effectiveness of the ECP to enforce its writ was assessed at 51.3%, slightly down from 52.4% in 2012. A September 2013 survey by PILDAT of 3,568 people found that despite the improvements made by the ECP, two thirds of those surveyed did not think that the election was “more honest, free and fair”[19]. / The EU EOM noted “The ECP has undertaken some consultation with political parties and civil society, which has contributed to increased confidence in and performance by the institution. However the ECP has not used its broad powers to establish a complete regulatory framework, leaving critical aspects of the election open to discretion. The ECP has also not taken full responsibility for all aspects of the election administration, instead deferring some key matters to temporarily appointed Returning Officers (ROs) without sufficient regulation or central oversight.” FAFEN’s report on the general elections is not yet available. / The DRI assessment of the Balochistan LEs notes that “the ECP did not centrally provide sufficient electoral data” and noted that the final results announcements “were inadequate in not providing any numbers, giving only the name of the winning candidate.” / Thus in conclusion despite the work undertaken by IFES and UNDP in support of the ECP, the ECP’s performance is seen as mixed and problematic in a very difficult environment. Progress needs to be viewed incrementally and as a necessarily political and negotiated process rather than just a set of technical fixes. / Outcome Indicator 3: Percentage of registered voters participating in the elections is increased / Measuring increase in voter participation is problematic given the different registration requirements and problems with the electoral roll in 2008 (the baseline measure referred to), and the lack of accurate population data. It is further complicated by fraudulent ballots likely being cast in both elections (as evidenced in tribunal findings in 2013). / The DFID impact evaluation found consistent confidence that the turnout was significantly higher than in 2008 relative to the population increase. Although there is some variation in this between constituencies and genders in particular. The key informant interviews showed increased turnout was largely attributed to the improved sense of political competition, political frustration with the incumbent, improved electoral processes increasing voter confidence, and the influence of the media. Thus it appears that people voted despite the militant threats and violence. / Promoting confidence in future electoral processes will be of importance given the on-going documentation of fraud through the tribunals and on-going allegations of fraud that continue to have political ramifications at the national level. / Despite positive initiative taken by the ECP to gather gender-disaggregated turnout data in the general elections, this did not work out in practice. A large proportion of polling staff did not record the necessary data as required in the results form. / No information was made available by the ECP on the number of registered voters or the voter turnout for the LEs in Balochistan. No reason has been given for this to date. / Outcome Indicator 4: The percentage of the ECP's Strategic Plan achieved, including objectives that are completely achieved and in progress / It is reported that 79% of the plan is achieved (68 objectives are achieved, 12 partially achieved and 34 are in progress). / The DFID impact evaluation noted that the ECP’s strategic plan was praised for being a positive initiative that shows good intent, made better by public ECP self reporting on implementation. However it appeared to be widely seen by key informants as limited in lacking ownership, not having an implementation plan, and self-reporting on its implementation lacking credibility. / PILDAT’s State of Electoral Reforms in Pakistan[20] generally affirmed the ECP’s assessment of implementation. However other PILDAT assessments note that despite such changes the most significant reforms are still outstanding and therefore, the overall confidence in ECP’s organizational capacity has not increased (see above). / Thus overall it is impressive that the ECP has the strategic plan and is undertaking public reporting on its implementation. However overall there remains a lack of confidence in the institution and identified weaknesses and vulnerabilities remain within the institution. Therefore fundamentally important areas of ECP development still need to be addressed in practice. / Outcome Indicator 5: Number of parties, domestic observer groups and percentage of citizens with confidence in the electoral rolls / Observer missions praised the improvements in the electoral roll, although the pronounced gender disparity was noted as a point of concern. The good collaboration with NADRA was positively commented upon. / Citizen survey results show strong confidence in the electoral rolls. Parties have not been forthcoming about their views, indicating likely sufficient levels of satisfaction. / Improved confidence in the electoral rolls is at risk of diminishing given that the ECP has not established a full updating mechanism. / Recommendations: / Reporting be strengthened to more clearly identify: / Attempts made by IFES to undertake activities focused on reform and self-sufficiency / sustainability, and ECP responses, including any negative response and reasons for this. In order to better understand ECP interest and ECP and IFES effectiveness in this critical area. / Increased focus on the risk log to record a greater number of risks, including to individual activities and the electoral process overall. / Increased information on problems and shortcomings encountered and reasons and measures being undertaken to prevent recurrence. / Coordination being undertaken with UNDP and others working with the ECP. / Increased coordination between IFES and UNDP so that there can be coordinated messaging and actions and mutual learning. IFES keep UNDP fully informed of IFES actions and invite comment and involvement. / Donors meet with the IFES/UNDP and the ECP to discuss the need for more sustainability and reform activities as originally envisaged, and that such activities were part of the agreement of the current programming and are also critical when trying to justify any possible future funding at the end of the current programming. Particularly important issues identified from the 2013 general election process include transparency and ECP management of RO actions. / Donors and respective embassies maintain political pressure on the ECP to undertake reform to prevent future election controversies. Demand is also maintained through separate on-going programmatic support to scrutiny of election processes including by-elections and local elections.
[16] The ECP presented its proposed unified election law to one of the final sessions of the Senate Special Committee who rejected considering it as at that late stage, just some months before the general elections (the Committee only wanted priority proposals for reforms).
[17] IFES: “The definition of ‘confidence’ in this indicator will be overall positive assessments by observers and political parties of the ECP’s ability to perform its duties. The ECP’s duties may include, but not limited to: carrying-out election preparation activities; adequate training of polling officials; effective communication between all levels of the ECP; satisfactory handling of the complaints and appeals process; and, to the extent possible under the current legislative framework, maintain its role as an independent body.”
[18] http://www.pildat.org/publications/publication/SDR/AssessmentoftheQualityofDemocracyinFirst100daysofNationalandProvincialGovernments_Sep2013.pdf
[19] The PILDAT survey of 3,568 people found that 30% thought the 2013 general election was “more honest, free and fair”, while 31% thought it was “less honest, free and fair” and 31% thought there was no difference (and 7% did not know). Amongst non-PML-N voters confidence levels appear to deteriorate further with only 23% reporting a “more honest, free and fair” election, while 43% thought the process was “less honest, free and fair” and 28% thought there was no difference. “Public Verdict on Performance of Governance and Democracy” http://www.pildat.org/Publications/publication/SDR/PILDATNationwidePollon100Days_Report_September2013.pdf.
[20] http://www.pildat.org/publications/publication/elections/StateofElectoralReformsinPakistan_CitizensMonitoringReport2ndQtrMarch2012.pdf.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / Funds worth SERP £3.57 million funds have been disbursed to IFES up to March 2014. IFES has forecasted £1.43 million until December 2014. IFES will continue its work in 2014 on / 1. Technical Assistance (participate in developing the ECP’s Second Strategic Development Plan (2014-18) and its launch, improve and develop the relegations related to Electronic Voting Machines (EVMs) and biometrics, supporting provincial governments on legal reforms relating to local government elections as required). / 2. Electoral Management (advocate with the ECP on institutionalisation of Gender, Research, Electoral Rolls, Training and Political Finance functions within the organisation, supporting the ECP in finalising the SOPs for voter registration and establishing GIS (Geographic Information System) lab in the ECP for the delimitation purposes, continue the BRIDGE and other trainings of the ECP officials, supporting newly established ‘Research and Gender Unit’ function within the ECP etc.) / 3. Voter Participation (Nation-wide campaign on CNIC and voter registration with emphasis on Women, minorities and sensitivity towards persons with disability and transgender and monitoring of campaigns and supporting the ECP, in coordination with UNDP, in the incorporation of democratic awareness in the school curriculum etc.) / Programme activities are on track to spend the disbursements of £5.5m by the end of project. / 2.2 Key cost drivers / To date the largest portion of expenditure is programmatic at 24% of total expenditure. This involved subcontracting to other organisations focused on voter/ civic education in the run up to the elections. / Secondly, international and local staffing costs are collectively 34%. These represent a critical input into this technical assistance-focused programme and are a key contribution to programme activities. This breaks down as follows:- 10% headquarter & international technical assistance and 13% local field staff costs. Fringe benefits 6%. Direct labour benefits and international staff benefits are 5%. Consultancies costs have been 4% so far providing TA to increase the capacity of ECP Staff. / The general administration and indirect costs which include management fee and overheads are charged at a rate of 11%. / 2.3 Is the project on-track against original timescale: Y / The programme is on track against the original timescale. EU funding was extended for another six months in early 2014; this may have implications for the end date of our funding. However IFES is very optimistic that it will spend these funds as originally planned and budgeted.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is likely to be a lack of independent assessments on the work of the ECP given that there is no general election and therefore no international observation missions. For the local elections, for Balochistan only DRI assessed the process and the main part of DRI’s work is now completed, so as things currently stand they will not be assessing upcoming LEs. Subject to funding FAFEN may observe, as may other local organisations. / Some form of independent assessment at the end of the programme will be useful to record views and assess programmatic actions, successes, and areas of reduced impact and reasons for this. Such findings could be especially useful in view of negotiating new upcoming programming with the ECP. / 3.2 Where an evaluation is planned what progress has been made? / An impact evaluation was contracted in mid-2013 to The Collective for Social Science Research (based in Karachi). The impact evaluation covered the IFES SERP programme and the FAFEN programme Supporting Transparency, Accountability and Electoral Processes in Pakistan (STAEP). A draft report has been submitted to DFID for comment.

4. Risk
4.1 Output Risk Rating: Low/Medium/High Medium / 4.2 Assessment of the risk level / Many factors are beyond the programme’s control, such as decisions of the ECP, the parliament and the Supreme Court. The political nature of the work of the ECP further complicates implementation and increases risk. The flexibility in the programme allows for IFES to adapt. However there is a risk that then the ECP relies on IFES more for short-term immediate needs rather than for long-term capacity building as envisaged in the programme and by donors. / There is risk of IFES providing good quality support, but this having limited impact due to the decision-making of the ECP (for example not to implement positive advice). While such actions are of course fully within the ECP’s right as an independent sovereign institution, it is important that donors are aware of the extent and impact of this, in order to consider how best to use public finances in the future.
Risk of funds not being used as intended / IFES corporate policy corporate policy regarding procurement of goods and services is based on regulations of United States Government (USG). It also takes on board donor policies, rules and regulations governing the accountable grant agreements. IFES’ procurement principles conform to parameters of the procurement guidelines as outlined in DFID’s Blue Book, Section D, and UK procurement policies. Where procurements are intended for international use for overseas programme implementation, IFES comply with the principles of Value for Money. / IFES procurement activities adhere to following principles: / 1. Full and open competition / 2. Fair and reasonable price / 3. Fair and objective evaluation of offers / 4. Responsible suppliers / 5. Documentation / IFES regularly reports the process of all major procurements completed in the quarter in SERP quarterly progress report. / Under the accountable grant agreement IFES is required to carry out external audit of SERP funding. The recent audit report covering Oct 2012 to Sep 2013 has been received recently. This report does not have any major observation regarding misuse of funds. / IFES also carry outs monitoring and evaluation of its programme activities. This includes the pre and post tests of trainings support to ECP officials. / For the sub contracts, IFES out sources the M&E function to third party monitoring / survey companies and findings of these reports feeds into the quarterly progress reports. / Climate and Environment Risk / Addressing climate and environment issues through the programme: The SERP project does not address climate change and environmental issues directly. / Risks to disruption of programme activities: Though there has been a recent history of flooding in Pakistan. Other natural disasters cannot be discounted. / Mitigation of environmental impact of programme activities: Most SERP project activities have low environmental impact associated with maintaining central office facilities, limited office supplies and coordination of events. Additional –but still low– impact is associated with maintaining the presence of trainers at provincial level and periodic staff field visits for participation in activities and for monitoring purposes. DFID management of the SERP programme has very low environmental impact associated with limited office supplies and periodic short field visits for monitoring purposes. IFES report that environment-friendly office policies have been established.

5. Value for Money (VfM)
The EU is undertaking an in-depth election evaluation of the work of SERP to date on behalf of the donor group. This will look at VFM in more detail including more quantitative information and headline results on VFM. The report will be available at the end of September and will feed into the project completion report in December 2014. Unfortunately this report was not available in time for our own internal controls despite best efforts to avoid duplication of effort. / DFID has supported both the supply side of elections through the SERP project and demand through the STAEP project implemented by FAFEN. Other donors are supporting a UNDP / UN Women project working with the ECP. / 5.1 Performance on VfM measures / Headline messages on VFM / IFES has been successful in contributing to some of key results with its support in the electoral processes in Pakistan as below:- / Codes of conduct decrease electoral violence / IFES worked extensively with the ECP to develop a Code of Conduct for Political Parties and Contesting Candidates, which was released in 2013 prior to the general elections. While the ECP had issued codes of conduct for previous elections, there was very limited adherence. However, the consultative process used by the ECP to develop the codes of conduct for the 2013 General Elections created more buy-in from political parties and candidates, which led to a less violent political atmosphere in the lead-up to the elections. / IFES also worked with the ECP to draft an initial code of conduct for media, but recognizing that it would be difficult to impose a code, the ECP turned the responsibility of drafting a code over to the media. Like with political parties and candidates, this new approach led to improved adherence by the media, and more responsible reporting on electoral violence. The cost of code of conduct development, consultations with stakeholders were negligible, especially considering the human and economic costs of electoral violence that they likely prevented. / Increased trust in the electoral process / Voter turnout for the 2013 General Election increased by about 23%[21] compared to turnout in the 2008 elections. Overall, 55% of registered voters went to the polls to cast their votes on 11 May, in comparison to only 44% in 2008. While there may be many reasons for the increased turnout, the numbers indicate more trust among voters in the electoral process since 2008. All of the reforms put in place since the last elections have helped increase voter confidence in the system. IFES has been working with the ECP to accomplish the objectives set out in its first Five-Year Strategic Plan (2010-2014), including producing a significantly improved computerized, duplicate free electoral roll based on voters’ national identity card data and with photographs. Under the SERP project, the ECP has undertaken many reforms, including the introduction of monitoring committees, codes of conducts for electoral stakeholders, training for temporary election staff, and a nomination booklet for contesting candidates, a comprehensive voter education plan and improved arrangements for internally displaced persons. Many of these improvements were highlighted in the media and helped improve voters’ trust in the electoral process. / Change in ECP mindset on training and capacity building / Since the 2008 elections, there has been an appreciable evolution in the ECP’s view of training and capacity building. For years, IFES has been working to help the ECP to understand the value of training for temporary election staff and capacity building for its permanent officers. Previously, it was the prevailing opinion at the ECP that training for polling staff was not necessary since many had worked in polling stations during previous elections, and that since Returning Officers and District Returning Officers were from the judiciary, they could simply be provided a copy of the law. By consistently demonstrating the value of training and capacity building, IFES has helped change the mindset of the ECP on the subject. Now, ECP leadership proactively requests support from IFES to help conduct training activities, which routinely involve ECP trainers. Under the SERP project, IFES has worked with the ECP to develop an extensive collection of training material for polling staff, Returning Officers and District Returning Officers, Election Tribunal Staff, Monitoring Teams, and other election stakeholders. The ECP now sees training as an integral part of election operations, since trained temporary staff performs their election duties better than untrained staff. Under the SERP project, IFES worked with the ECP to conduct training for District Returning Officers, Returning Officers and Assistant Returning Officers, and polling staff ahead of general elections. The ECP has also specifically requested IFES’ assistance in conducting trainings for election staff ahead of local government elections. / Success of first strategic plan leads to commitment to further reform / After the 2008 General Election, IFES worked with the ECP to develop its first Five-Year Strategic Plan (2010-2014). The SERP program was designed to help the ECP accomplish the objectives outlined in the strategic plan. According to the last progress report, the ECP completed approximately 80% of its strategic plan by 2013. National and international election observation missions, including the Free and Fair Election Network, the European Union Election Observation Mission and the National Democratic Institute/ Asian Network For Free Elections all noted that the reforms since 2008 led to a more technically sound election process. The success of the ECP’s first strategic plan has led to a push within the organization to develop a second strategic plan outlining the reform agenda for the next five years, leading up to general elections in 2018. / Cost of elections and reforms / The cost of elections per voter in Pakistan is significantly lower than in other countries. The 2013 General Elections cost the government approximately £39.4 million (Rs. 6 billion or $60.7 million), excluding the support from donor agencies. With 86,189,802 registered voters, the cost is approximately £0.46 per voter (Rs. 69.61 or $0.70). While it is difficult to find up-to-date statistics, in 2006, the ACE network released comparative information about the cost of elections in the following countries with longer multi-party democratic experience: Chile ($1.2), Costa Rica ($1.8), Brazil ($2.3), Benin ($1.6), Botswana ($2.7), Ghana ($0.7), Senegal ($1.2), India ($1) Pakistan ($0.5) and Australia ($3.2). While the low overall cost of Pakistani elections is good because it does not put inordinate pressure on the national exchequer, a major drawback is that improvements to the system have the potential to inordinately raise the cost of the elections given the size of the country. Through its technical assistance to the ECP, IFES has been mindful of the cost of reform and sought solutions that can be sustained on the government’s budget in the long-term. For example, when discussing options for out of country voting and introduction of electronic voting machines, IFES has clearly outlined the financial implications of various options for ECP decision makers. In its analysis of the Supreme Court’s Judgment on Constitutional Petition No. 87 of 2011, IFES provided the ECP with an analysis of the feasibility of the directions and suggestions outlined by the Court. One recommendation for the 2013 general elections that IFES urged the ECP not to pursue because the cost would be tremendously higher than the value was the suggestion that the ECP arrange official transportation for all voters on Election Day. / Training of polling staff / Ahead of the 2013 General Elections, IFES worked with the ECP and the UNDP to conduct training for polling staff across the country. IFES and UNDP split the training geographically; IFES conducted training in Balochistan, KPK/FATA, and Sindh, and was responsible for printing training material. For those three provinces, the total cost of training 241,630 polling staff was approximately £1.9 million from DFID and UK FCO combined. The amount spent to train each poll worker was approximately £7.86. / Voter education sub-grants / IFES’ sub-grants to local organizations for voter education provided high value for money. IFES awarded sub-grants to four organizations to conduct voter education initiatives before the general elections and civic education activities in the post-election period. Combined, the four organizations directly reached approximately 880,000 people. The combined cost of all four sub grants was approximately £207,000, bringing the amount spent per voter reached to approximately £0.24. / However the ECP’s apparent performance in the Balochistan LEs shows the need for sound documentation and independent assessment of performance in order to see the extent to which the ECP is effectively using the support from IFES and UNDP / UN Women. Clarity on shortcomings may then be used as a basis for political messaging for reform to prevent further problems. / DFID’s considerable support to the ECP, including for election basics such as training of polling staff and ballot boxes, should help give DFID and the UK some influence in promoting reform. / The importance of accepted electoral processes is of high importance for Pakistan at this time, for the establishment of continuity of civilian rule and to strengthen the writ of the state. UK support has a symbolic value in supporting democratic forces as well as practical benefit. Now is a particularly important time for support to the ECP given the on-going criticism there is of the institution and push for reform, meaning the ECP is under pressure to be undertaking sound reform initiatives. / In conclusion / Overall IFES’s work to date has been effective in supporting ECP election delivery. The overall political acceptance of the election process, and the peaceful transfer of power from one elected government to another, has a great significance given Pakistan’s turbulent democratic history. As some of the examples above indicate much of our investment has played an important contribution to improving the elections, representing value for money. / However value for money may be seen as more limited in regards to capacity building of the ECP, with such assistance and activities essentially deferred by the ECP until after the general elections, and now likely until after the local elections (the timing of which is not finalised). Thus there has been a valuable fulfilment of the operational and political imperatives of the general elections, but the developmental aspects of support remain weaker. There will be only limited opportunity for capacity development during the remaining part of the programme given the limited time and the on-going local elections. / Efficiency is maximised if IFES and UNDP / UN Women can work in a complementary way, as they did with geographically dividing training of election staff. Complementary working is more likely to increase overall impact of programming towards the desired outcomes. Therefore a strong focus on coordination is important. / There is a need to recognise the politicised context in which the ECP is working, the capacity constraints it faces, and the potential resistance to electoral reforms from within the ranks of the bureaucracy from vested interests. / Within this context, since some of the ECP decisions have limited some of the impact of IFES technical assistance, the ECP should be encouraged to / 1) Be active on election reform and capacity building, / 2) Be clear in advance as far as possible about changes it is not interested in (that IFES and others are proposing), and / 3) be more accountable for actions it has committed to in programming. / IFES are encouraged to document ECP decision making that does not appear to support election reform and capacity building, so that in future donors can consider if they wish to continue support knowing if it is likely to be used for development, or more for immediate operational needs. / The upcoming local elections have been and are likely to continue to be sensitive and controversial. Therefore support to improve the supply side could have significant value in smoothing the democratic roll-out in Pakistan. / 5.2 Commercial Improvement and Value for Money / IFES report that for procurement of consumables to be provided over one calendar year, annual market research is conducted. Major procurement actions conducted in 2012-13 included ballot boxes, poll worker trainings, establishment of long-term blanket ordering contracts, and post-election review workshops. IFES report that procurement activities adhere to principles of 1) full and open competition, 2) fair and reasonable prices, 3) fair and objective evaluation of offers, 4) responsible suppliers, and 5) documentation. A minimum of three formal quotes are collected for each procurement action, in accordance with an advertised request for quotations (RQF). / 5.3 Role of project partners / The SERP project is being implemented directly by IFES. IFES commitment to the economy component of VfM in particular is clear from its inclusion of VfM analysis in its quarterly reporting that demonstrates some good examples of economy. / During the year 2013 IFES did a lot of procurement mainly for Training Firms – for Training of Polling Staff, Recruitment Firms, ME Outsourcing, Transport Firm and other general items. IFES managed to save a lot of funds by having robust negotiations with the vendors; / Total cost savings: / Training PR 135,871,150.00 / Recruitment PR 1,231,200.00 / ME PR 635,200.00 / Stationary and packing PR 650,426.50 / Transport PR 3,729,324.00 / Total PR 142,117,300.50 / 5.4 Does the project still represent Value for Money : Yes / The ECP’s need of assistance for the general elections was pronounced, and without support in basic areas of election administration, there would have been a far greater risk of dispute, contention and risk of rejection of the electoral process. Furthermore in Pakistan there is a risk of consequent rejection by some of the democratic system as a whole. Such potential for political instability and the consequent risks to security, mean that there is a strong imperative to support the ECP in fulfilling its basic role. The significance of a peaceful transfer of power in the 2013 general election is strongly emphasised, especially as there was also an increase in the number of voters, thereby giving a democratic mandate to the political leadership. This is of particular importance given the threats to state powers in various parts of the country. / The work of IFES and UNDP was key to the ECP being able to conduct an election process that was overall accepted, even if problems were and continue to be evident,. There are similar risks with the local elections, albeit with any problems likely having reduced ramifications. There are on-going electoral risks in Pakistan, thus support to the ECP continues to be of value in trying to support the ECP through immediate election delivery responsibilities and to develop its overall capacity. / DFID and IFES appear to have been trusted partners to the ECP. / 5.5 If not, what action will you take? N/A
[21] In the 2008 General Elections, 35,637,072 people participated. In comparison, 46,217,482 voters voted in the 2013 General Elections.

6. Conditionality
6.1 Update on specific conditions - Not applicable

7. Conclusions and actions
Current Performance: / IFES is working in difficult conditions, with an institution that has an entrenched dependency on donor support and has been subject to varied criticism. The political sensitivity of the institution and election work, the prevailing security conditions, and uncertain and often time-pressured operational demands make programme implementation and impact challenging. / IFES has supported the ECP through two difficult elections, the general elections and LEs in Balochistan. The holding of both have historical significance. The shortcomings of both do not reflect on the quality of IFES’s work, which appears to have been of a consistent very high standard, but on the conditions the elections were being held in, and the decisions of the ECP. It remains important for IFES to 1) continue their quality support based on ECP interest and donor interests (i.e. not just ECP interests which may be more implementation-focused), and 2) to be clear about where their support has had limited impact, so that donors can also address impact problems with the ECP and can make informed decisions about future programming. / The 2012 Annual Review noted “… the future success of the project will depend on defining and agreeing on post-election plans and priorities with the ECP that include an emphasis on in-house capacity and confidence, longer-term strategic planning, increased ECP staff involvement and matched financial commitments over time in areas such as training and promoting and nurturing initiative and innovation within the ECP.” This is likely to be a difficult area for IFES to achieve success in, given the local elections and limited time remaining. Therefore strong donor messages to the ECP on the importance of capacity building are important. Alternatively donors could consider accepting that the remaining part of the programming is focused on implementation for the LEs, and that capacity building is for future programming. / Relationships and donor coordination: / IFES reports a strong relationship with the ECP. / Donor coordination is critical in this politically sensitive work. There is opportunity for donor leverage and influence, which is particularly important given some of the decisions the ECP has made to date that have limited programming impact and more importantly limited opportunity for development of electoral good practice. / It will continue to be important for IFES and UNDP to demonstrate to their donors what efforts they are respectively making to work collaboratively. Given the on-going need for ECP support there are plenty of activity opportunities for both organisations. Strong efforts are needed 1) to compliment rather than duplicate each other’s work, 2) to support each other’s work in the interest of the greater good, and 3) to include each other in respective areas of work (so that there is maximum information exchange and opportunity for involvement to get the best result and to show unity to the ECP). One example of an area in need of clarity is in UN Women’s reference to establishing a Gender Unit within the ECP, and IFES’s proposals for a Research and Gender Affairs unit at the ECP.

8. Review Process
It was agreed to undertake a light touch desk review bringing in an elections expert consultant. The EU is currently undertaking a more in-depth mid-term review, but results will not be available to meet ARIES reporting deadline. This will be added once available. DFID commissioned this light touch review, had a debrief from the consultant and provided comments on the draft report before finalisation. A more in-depth analysis of VFM will be taken as part of the PCR at the end of the year. / The desk review was undertaken by consultant Hannah Roberts, Deputy Chief Observer with the EU Election Observation Mission 2008 and 2013, consultant with DRI and part of the DFID-contracted impact evaluation team (implemented by The Collective for Social Science Research).