Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Public Financial Management Reform Programme
Programme Value: 13.86 million		Review Date: October 2014
Programme Code: 201584	Start Date:Nov 2010	End Date:31 March 2015

Summary of Programme Performance
Year	2010	2011	2012	2013	2014
Programme Score	B		B	B	B
Risk Rating	High		High	High	High

Summary of progress and lessons learnt since last review

The Ghana Integrated Financial Information System (GIFMIS) Procure to Pay (P2P) expenditure commitment module has been rolled out to all central Ministries, Departments and Agencies (MDAs) and piloted in 7 MMDAs

Coverage of budget and financial management extends to the Consolidated Fund (CF) representing about 66% of budget expenditure (though 70% of this is accounted for by the largely automated payment of salaries and wages).

Ex ante commitment controls for CF expenditure has been instituted through GIFMIS at the budgeted spending unit level. However the unavailability of funds for expenditure on goods and services, and investment due to the weak fiscal framework (persistent over estimation of revenue and the diversion of budgeted funds to meet underestimated salary and interest payments) has resulted in highly limited funds flowing through the system. The robustness of the implementation has therefore not been fully tested.

Internally Generated Funds, Statutory Funds and Donor Funds continue to remain outside the GIFMIS control system limiting the extent and effectiveness of the financial control framework.

The roll out of the Electronic Funds Transfer (EFT) appears to have brought efficiency savings and is an important step towards a fully-fledged Treasury Single Account (TSA).

The Ministry of Finance (MoF) report that they are on course to use the budgeting module Hyperion to prepare the 2015 budget and implement Programme Based Budgeting (PBB).

The Oracle based payroll system has been upgraded and is now live for all GoG employees except the Ghana Education Service which accounts for about 60% of total GoG staff and about 50% of payroll costs.

Key lessons learnt include:

The benefits from project implementation continue to be undermined by an increasingly unsustainable fiscal framework which is neither consistent with, nor supportive of the PFM reforms being implemented.

Continued high level sponsorship from the Ministry of Finance has been crucial to maintaining support within the Government of Ghana (GoG) for the reform programme in what has been an increasingly difficult operating environment. However, the focus on delivering technical solutions has been at the cost of adequately addressing important sequencing issues and behavioural and institutional barriers to reform which have slowed progress in some areas such as increasing system coverage. As has been the case for many countries, PFM reform appears to have been IT led, with the implementation of GIFMIS coming to be viewed by the GoG as “THE” PFM reform rather than as a vehicle for other reforms.

A fracturing of the partnerships between key stakeholders which came to a head over the review period may have been avoided if an adequate governance structure, that clearly defines roles and allows sufficient channels for all stakeholders to participate effectively at each stage of the reform process, was in place.

The documentation of business processes and other project changes such as changes in scope is currently insufficient and inconsistent.

 Summary of recommendations for the next year

The project is concluding in less than six months, therefore the scope for implementing realistic and meaningful recommendations is limited, particularly in light of the decision by DPs to hold back remaining funds in response to substantiated financial management irregularities. Nevertheless the following recommendations are presented for consideration:

Project related
- Accelerate efforts to increase system coverage through the piloting of IGF, Donor Partner and Statutory funds as recommended in the May 2014 World Bank aide memiore which called for pilots in the Ministries of Health and Education and the Road Fund.
- Seek to widen the channels for dialogue and decision making by all key stakeholders, particularly relating to changes in project scope.
- A clear strategy and work plan relating to change management initiatives should be developed as soon as possible.
- To maximise the returns from the GIFMIS implementation, it is essential to review all business processes, redesign them to allow maximum automation and prepare a plan for implementation of the redesigned processes.
- Related to the above, there is a need to ensure adequate documentation of business processes and changes in project scope and to reflect this fully, in term of metrics of success in the results framework. There is a current initiative to collect all the Project documentation and store them in a central repository which is regularly backed up. This should be completed as soon as possible.

Wider PFM support
- Actively engage with GoG and other stakeholders on the wider PFM reform agenda, building on the first draft of the GoG’s new PFM strategy. This should include a more considered approach to the sequencing of reforms which avoids getting out of step and over-reaching. It should aim to achieve an adequate level of financial compliance before advancing to medium term budget planning, and similarly secures this to an adequate level before attempting to introduce advanced reforms like performance budgeting.
- Seek opportunities to support PFM reforms that leverage any prior actions and benchmarks from a possible IMF programme which underpin or are supportive of PFM reform and achieving a fiscal sustainable framework.
- Consider support to the IMF Regional Technical Assistance Centre which draws on IMF expertise in revenue, macro-fiscal management and PFM.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme
### The UK agreed to provide £13.86 million over four years (2010-2014) to the GoG for the implementation of the Public Financial Management Reform Project. Funds are to be used as follows:
£10 million contribution to the $60.26 million GIFMIS pooled fund to support systems implementation and other PFM reforms, amounting to 25% of the total fund contributions. Other contributors are the World Bank (47%), the EU (20%) and DANIDA (8%).
£2 million for Technical Cooperation in support of the GIFMIS implementation managed by DFID-Ghana outside of the pooled fund; and
£1.86 million to develop the Project and Financial Analysis (PFA) and Public Private Partnership (PPP) Unit in the MoF to improve the public investment framework to ensure that it supports economic growth and social development and delivers value for money.

Key project activities include:
- The roll-out of the GIFMIS commitment control module to all MDAs and MMDAs;
- Integration of the Hyperion budget preparation module to GIFMIS to bring together budgeting, expenditure and accounting under a single chart of accounts under a programme based format;
- The implementation of a Treasury Single Account;
- Reform to the public investment management framework including its integration into the medium term expenditure framework.

It is expected that successful implementation of these reforms will result in an integrated Public Financial Management system with universal coverage which provides improved:
- aggregate expenditure control;
- ability to monitor expenditures throughout the year;
- predictability for financial flows;
- efficiency and effectiveness in expenditure and investment planning in support of development priorities; and
- accountability for financial compliance and the achievement of results.

The goal is to have a well-functioning PFM system that helps to ensure that public funds are being used in an efficient, transparent and accountable manner to achieve Ghana’s economic and social development objectives, within a fiscally sustainable framework.

The emergence of large fiscal and external imbalances in recent years has created significant challenges. The fiscal deficit rose to 12 percent of GDP in 2012, fuelled by a large public sector wage bill, costly energy subsidies and rising debt interest costs. The fiscal expansion was accompanied by a growing current account deficit. As a result, public debt increased significantly and the international reserve position weakened alongside a depreciating currency. The Government is currently in negotiation with the IMF on adopting a fund sponsored adjustment programme.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome statement - An integrated Public Financial Management system which provides improved: expenditure controls; predictability for financial flows; expenditure and investment planning; monitoring of expenditures and accountability.

Mixed progress is being made towards the achievement of the outcome as stated above:

With the rollout of GIFMIS to all central MDAs and the planned use of the Hyperion budgeting interface for the preparation of the 2015 budget, progress is being made towards integrating the PFM system under a common chart of accounts.

GIFMIS has delivered ex ante expenditure controls for the CF but this currently only covers 66% of budget expenditure, 70% of which is a centrally executed lump sum payroll payment. IGF, Statutory funds and Donor funds remain outside the GIFMIS control environment providing a significant channel for committing extra budgetary expenditures.

Predictability for financial flows is undermined by a weak fiscal framework (Revenues continue to be overestimated – by 22% for the year to September 2014) which has resulted in only a fraction of the budgeted funds for goods and services, and investment being available to MDAs (about 20% for the year to September 2014).

The implementation of PBB should in theory contribute to improving accountability for the use of funds but this may be too early a reform for Ghana considering the weak fiscal environment and lack of compliance in the PFM system.

As a result, it is unlikely that the Outcome will be achieved by the end of the programme.

Overall output score and description

B - Outputs moderately did not meet expectation.

Key lessons

See summary section above.

Key actions

See summary section above.

Has the logframe been updated since the last review?

Yes. An additional output - Output 5, has been included (weighted at 15%) with weightings reduced for Outputs 2 (by 5 percentage points) and 3 (by 10 percentage points) to accommodate this. However, the logframe was only partially updated with numerous milestones not in place, a problem with the original logframe. This has made scoring the outputs challenging. Where milestones have not been presented, an attempt has been made to score based on the reviewers’ subjective view on progress made over the review period in against the stated indicator.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Upgrade Oracle e-business suite installed and in use throughout government
Output number per LF		1	Output Score	B
Risk:		High	Impact weighting (%):	35
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Treasury sites servicing MDAs	Phased MMDA rollout commences	The Procure to Pay module has been rolled out to seven pilot MMDAs
MDAs registering commitments in commitment module	All central MDAs recording all commitments from CF in the commitment module	All commitments made from the Consolidated Fund (CF) are recorded in the commitment module
Proportion of government transactions covered by IFMIS	No milestone	The whole CF representing 66% of budget expenditure.

Key Points

The core GIFMIS system has been rolled out to all central MDAs with ex-ante commitment controls instituted through the system for all the Consolidate Fund (CF).

The P2P expenditure commitment module has been rolled out to seven pilot MMDAs ministries over the reporting period but no progress was made in transacting funds through the system as planned as a result of no fund releases made to the MMDAs from the CF. The GoG had targeted rolling out the P2P module to a further 46 MMDAs by the end of the project.

At present all CF related budget expenditures, constituting about 66% of the GoG appropriation budget, are being executed through the GIFMIS system. However the majority of these transactions (70%) relate to wages and salaries, which enter the GIFMIS by way of a centrally administered single lump sum transfer from an external payroll system.

Internally Generated Funds (IGFs), Statutory Funds and Donor Partner Funds, where much of the fiduciary and fiscal risks in the PFM system lie, are still executed outside the GIFMIS system. Limited progress has been made in piloting two IGFs (Ministries of Health and Education) onto GIFMIS. Although some technical, legal and procedural obstacles have been cited as key impediments to achieving this, the most significant obstacle appears to an issue of trust - the MDAs are wary of a loss control in the administration of scarce and reliable funds to the MoF.

The progress that has been made in implementation continues to be undermined by the challenging fiscal framework that currently exists in Ghana. Nearly all available government funds are directed to meet wage and debt service commitments[1] which have resulted in very little funding being available to the MDAs to spend through the system on goods and services and investment.[2] As a consequence, the robustness of the system has not been fully tested.
[1] Interest and wage costs combined accounted for 93.9% of tax revenue in 2013. If payment of arrears are included this rises to 101.8% of tax revenues
[2] Expenditure on goods and services and investment has fallen from 30% of tax revenues in 2009 to just 10% in 2014

In other developments, (reflecting an expansion in project scope which saw the GoG decide to embark on a full HRM information system as well as the planned payroll system upgrade), the payroll system has been upgraded from Oracle version 11 to version 12 and is now live for all GoG employees. However, this does not include the payroll for Ghana Education Services which accounts for 60% of government centrally contracted employees and about half the wage bill[3]. This will be important to fully realise the expected benefits in the form of improved controls and better workforce planning, from the integration of payroll with the Human Resources Management Information System (HRMIS) and the Budget Management System currently being undertaken. . However the fiscal impacts will be limited in the short term without a clean –up the payroll which currently contains significant irregularities.
[3] as a result of concerns from the GES by the length of time it takes to process the payroll but this appears to be have been addressed by the payroll upgrade which has seen processing days fall from 22 to five

Summary of responses to issues raised in previous annual reviews (where relevant)

Not relevant

Recommendations

Accelerate effort to increase system coverage by bringing on IGF, DPs Funds and Statutory Funds initially through a piloting approach as already planned.

There is a need to put as much emphasis on change management as technical implementation issues and ensure these are addressed in the right sequence.

Push for GES payroll to be brought on to the updated payroll system.

Improve documentation for both changes in project scope and business processes implemented

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	New approaches to planning and budgeting introduced with the Government of Ghana
Output number per LF		2	Output Score	B
Risk:		High	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
Number of MDAs that implement annual program, sub-program budgeting and activity classification	No milestone presented	All MDAs producing their budgets in the Programme Based Budgeting (PBB) format
Number of MDAs preparing budgets on Oracle platform using new programme budgeting format	Final acceptance testing of the Hyperion	Final acceptance testing for Hyperion has been completed
Firm application of budget ceilings (percentage of budget)	No milestone presented	Wages and salaries 10.4% higher than budget; interest payments 37.6% higher than budget for 2013

Key Points

Though the initial project included the implementation of the budget module implementation in GIFMIS, in 2013 the scope of the reforms was significantly increased to include a full budget reform process with PBB, the centre piece reform.

The MoF has provided training to what they describe as critical mass of staff of all MDAs in the preparation of PBB. All MDA are now preparing budgets on a programme basis but according to the MoF, there is significant variability on the quality of these budgets. The 2014-2016 Budget was prepared and approved using the PBB format and the 2014 Budget Appropriation was passed on the basis of programmes by Parliament, though the detailed activity basis previously developed under Activity based approach (with over 26,000 activities in the budget) was retained in the budget preparation and presentation process.

However, as noted by the May 2014 aide memoire, the advantages of a more strategic approach to budget preparation are not, for the moment, being carried through into budget execution. Release warrants continue to require extremely detailed identification down to the economic classification within activities. As a result, the procedures for release of funds continue to require the issuance of thousands of warrants.

According to the MoF, the final acceptance testing for Hyperion budgeting module has been completed. The MoF has confirmed that they are on course to use Hyperion for compiling the 2015 budget. The adoption of Hyperion should seamlessly integrate the budget preparation software with the financial accounting system, with a single Chart of Accounts for all stages of the budgetary cycle.

Though commendable that the GoG is keen to introduce a performance element to the budgeting process, PBB would be considered by most observers to be an advanced PFM reform. Continued major weaknesses in the financial control environment, and a currently unsustainable fiscal framework resulting in very little in the way of programmable funds in the system, raises questions about if this is the right time for Ghana to undertaking such an ambitious reform.

Summary of responses to issues raised in previous annual reviews (where relevant)

From 2013 AR recommendation: The Hyperion system has been acquired; a study on optimal sequencing of PBB reforms does not appear to have been undertaken; the logframe has not been revised.

Recommendations

The MoF is keen to press on with PBB but in terms of the sequencing of reforms the focus of energy and resources should be on getting the “basics” in place to deliver a high degree of financial compliance and coverage across the budget.

As noted in the May 2013 World Bank aid memoire, consideration should be given to identifying measures which could be adopted to streamline the release warrant process as part of the wider process of moving to a more strategic system of budgetary management.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	New systems in place for the planning of investment expenditure
Output number per LF		3	Output Score	C
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y down from 20

Indicator(s)	Milestones	Progress
Links between investment budget and forward estimates (FE)	No milestone	Limited – see key points
Procurement plans prepared as part of the national budget	No milestone	No evidence presented
Investment budget directly links to national investment plan	No milestone	No evidence presented

Key Points

Many commitments to borrowing and capital projects continue to be made outside the regular budget approval process. In some cases, major projects with very substantial long-term costs are incorporated in the next year’s budget, while major costs occur in later years - sometimes even beyond FEs period. As noted in the May aide memoire, such activities should in principle be fully appraised in terms of potential use of fiscal space alongside regular activities under the MTFF process, and long-term contracts need to be appraised in the context of their medium-and long-term impact, not just the budget year.

There has been some data migration from the existing PIMS to the Project Financial Planning sub-module (PFP) of Hyperion be over the review period, an important step in ensuring integration between public investment and budgeting.

There is a standalone custom-developed system in ACTIVATE at the MoF for recording and tracking long-term contracts. This database houses the contracts of the GoG funds as well as some SoEs. The recording of GoG contracts in this database does not create commitment in the GIFMIS and has yet to be migrated to GIFMIS under an integrated platform. This apparently could not be completed due to technical challenges in defining the detailed business process for recording of multi-year contracts as long term commitments, though the requisite functionality called ‘Contracts Purchase Order’ is available in GIFMIS/Oracle.

Summary of responses to issues raised in previous annual reviews (where relevant)

From 2013 AR recommendation – DFID-C has advocated for a comprehensive PFM strategy with clear sequencing and prioritisation of reforms. The GoG has produced a first draft document but it lacks both sequencing and prioritisation of reforms. It does however provide a basis for further dialogue between stakeholders.

Recommendations
None.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	New system in place for improved cash management
Output number per LF		4	Output Score	B
Risk:		/High	Impact weighting (%):	20
Risk revised since last AR?		Y from medium	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Per cent of total government funds in Treasury Single Account	No milestone	66% the budgeted expenditure are now transacted through GIFMIS
PEFA Indicator 16 (predictability of funds for commitment of expenditures)	No milestone	No PEFA produced for 2014

Key Points

The Loans and Fiscal Agency Agreement (LFAA) between the MoF and Bank of Ghana (BoG) is now fully operational and consolidation of CF accounts with the BoG is now complete. With respect to BoG’s accounts, interest is being charged only when the overall net balance falls below a defined threshold, which should be resulting in a significant savings of interest payments to the GoG.

Electronic Funds Transfer (EFT) has been rolled out across all MDAs, strengthening efficiency and migration to a Treasury Single Account (TSA). The BoG SWIFT interface with GIFMIS has now been extended to all MDAs. The basis for EFT and system cheques transactions will enable real time bank reconciliation for all MDAs. As the TSA begins to incorporate commercial bank accounts, full system-based reconciliation of the Controller and Accountant General (CAGD) accounts with bank balances should be in place.

However IGFs, Donor Funds, and Statutory Funds in GIFMIS remain outside the system. Timely inclusion of these funds in budget and accounts is a key condition to achieving a fully-fledged TSA.

In regard to predictability in the availability of funds for commitment of expenditures it is unlikely that there has been any significant improvement in the D+ score registered in the 2012 PEFA. MDAs continue to lack reliable information on the availability of funds which make reliable cash planning impossible.

The continuing weakness in the fiscal framework means budget ceilings have continued to be unreliable for the MDAs in planning their expenditure commitments. Wages and interest payments – protected payments and the bulk of primary expenditure, continue to be underestimated which contributes significantly to the unpredictability in funds available for expenditure on goods and assets.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not relevant

Recommendations

Press for acceleration of a phased approach that has already been agreed, to bring all budgetary funds into the TSA framework.

Press for plan to address behavioural and institutional obstacles that cause resistance form the MDAs for rationalisation of bank balances currently held in commercial banks in tandem with technical reforms to establish a fully functioning TSA.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved fiscal control
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	15
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
CEPA policy briefs for informing macroeconomic decisions	Policy briefs produced	10 policy briefs produced
Expenditure Audits	Expenditure Audits implemented in key spending Ministries	Inception report has been produced
Technical Assistance to GRA	Reports on HMRC Scoping mission	Mission report with recommendations produced

Key Points

CEPA policy briefs - A review of the supported provided to CEPA can be found in the project completion report: Examining Ghana’s Economic Management Process.

Expenditure Audits - With financing from DFID-Ghana, a reputable international accountancy firm is under engagement by the Ministry of Finance to provide “Expenditure Audit Services” to validate the stock of outstanding arrears and commitments for the Government of Ghana held at the Ministry of Finance and the Controller & Accountant General’s Department. The firm will also validate outstanding claims for seven selected MDA’s that have arrears/claims against the Government of Ghana (Ministry of Finance). A draft report is expected on 21 November with a final report due 21 December. The firm have confirmed that they are on track to meet these deadlines.

Technical Assistance to GRA - Two officers from HMRC, conducted this mission on behalf of DFID in conjunction with HMRC’s International Relations team. This was a scoping mission for Ministry of Finance, Ghana (MoF) in relation to revenue raising and tax compliance within Ghana Revenue Authority (GRA). The mission took place between 23rd-29th July 2014 and was mainly focused on GRA offices in Accra. The report identifies a number of key strategic issues for the GRA to take forward and provides DFID-Ghana with some ideas for practical support for revenue reform.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not relevant – new output

Recommendations

No recommendations

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

GHC 33 million of expenditure was recorded under the project in 2013. Of this, 55% was spent on goods and services, 35% on the purchase of assets and 15% for employee compensation. This can compared to splits of 38%, 53% and 8% respectively for 2012.

VfM performance compared to the original VfM proposition in the business case

The Project Document proposes significant project returns from: (a) improved allocative efficiency arising from improved planning and budgeting systems (b) savings from reduced interest payments from the operation of a Treasury Single Account; (c) a reduction in expenditure arrears due to a strengthened commitment control system; (d) a reduction in waste owing to tighter expenditure controls; and (e) increased efficiency of investment expenditures as a result of improved prioritisation, value-for-money analysis and management of investment projects.
World Bank reporting suggests that savings in interest payments of GoG accounts with the BoG have been made following the operationalization of the LFAA. The roll-out of the P2P model to all MDAs does bring commitment controls at least to the CF portion of the budget though the benefits from this are undermined by the lack of funds available to transact through the system (a consequence of the currently weak and unsustainable fiscal framework operating in Ghana and the significant proportion of the budget which remains outside the GIFMIS control framework).

Assessment of whether the programme continues to represent value for money

DFID has not disbursed funds to the project since December 2012 following whistle-blower reports over the misuse of project funds (see next section) and concerns about project performance. A $3 million outstanding balance remains undisbursed. The EU and DANIDA and the World Bank have also taken the decision not to disburse remaining outstanding funds - $1.66 million, $0.68 million funds and $0.98 million respectively, resulting in a total funding shortfall of approximately $6.3m. The GoG cites this as the primary reason for the slowdown in reform over the review period.

A performance audit carried out by an independent international accounting firm estimated the current implementation level of the project to be 60%. However this is assessed against the original project baselines set in 2010 and do not include the achievements in the areas of expanded scope i.e. PBB, HRMIS/Payroll. It should be noted that the scope of the project increased significantly from the original conception.

VfM is undermined by the weak fiscal framework operating in Ghana which means that the GIFMIS system cannot be fully utilised. It is also questionable whether reforms have been sequenced in a way where potential benefits from the significant resource outlay will be maximised. For example, the implementation of an advanced reform such as PBB, when Ghana’s PFM system is some way from achieving a solid level of financial compliance and funds predictability.

Quality of financial management

Following whistle-blower allegations of financial irregularities in the project’s financial management, DPs withheld remaining disbursements totalling about $6.3m. The UK alone withheld $3 million.

An international accounting firm was brought in at the request of DPs to carry out an independent financial audit of revenue and expenditure covering the period from 21 December to 31 December 2013. The audit found GHC 8,185,875.44 representing about 7.9% of the total audited expenditure, relating to hotel accommodation, allowances paid, procurement of goods and services was ineligible for funding under the Contractual Conditions of the project. This aside, the audit found that the financial report presents fairly, in all material respects, the actual expenditure incurred and revenue received for the Project for the period in question in conformity with the applicable contractual conditions.

When interviewed, the senior management team at CAGD refuted the findings that ineligible expenses had been made and insisted that they were compliant with Government-wide policy.

Date of last narrative financial report	09/10/2014
Date of last audited annual statement	29/07/2014 (Draft)

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk

A number of key risks exist for the project:

Macroeconomic risk – Ghana’s short term vulnerabilities have risen significantly amid high fiscal and current account deficits which have thwarted a return to macroeconomic stability. The consequence has been that very little in the way of budgeted funds have been available for anything other than wages and interest payments and the credibility of the budget continues to be undermined.

Implementation/delivery risk:

- Funding – The holding back of $6.3m of programme funds by DPs will impact on further implementation of the GIFMIS related reforms – particularly the roll out to MMDAs and the provision of training. The Government is fiscally constrained and will not be able to make up the shortfall. DFID has sought to maintain the impact of its PFM support by supporting related interventions represented under the new Output 5, and also in the area of tax administration.
- Stakeholder - The inability for donors to speak with one voice likely reduces their influence and impact on the direction of the programme. This is compounded by limited clear opportunities for DPs to contribute effectively to the reform dialogue process.
- Sequencing – A reform focus on the technical side of the implementation at the expense of addressing institutional and behavioural barriers to reform. Also the impact of the PBB reform is likely to be limited in the context of the current fiscal framework and an inability to ensure adequate levels of financial compliance.
- Documentation - The documentation of business processes and changes in project scope is currently insufficient and inconsistent.
- Monitoring - The performance audit also found that project objectives are broad and are not, in some instances, readily connected to project execution, making it difficult to clearly measure the extent of progress.

Financial risk – Whistle-blower allegations about financial irregularities were substantiated by two independent reviews, which found GHC 8,185,875.44 representing 9.98% of the total expenditure reported for the project relating to hotel accommodation, allowances paid, procurement of goods and services was ineligible for funding under the Contractual Conditions of the project. DFID and other DPs have withheld remaining funding as a result.

Outstanding actions from risk assessment

See recommendations in Summary section.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

A weak logframe with a number of missing milestones makes this difficult to assess.

A performance audit carried out by an independent international accounting firm estimated the current implementation level of the project to be 60%. However this is assessed against the original project baselines set in 2010 and does not include achievements in the areas of expanded scope i.e. PBB, HRMIS/Payroll.

Performance of partnership (s)

The World Bank’s six monthly reviews and subsequent aide memoires have superseded the project’s formal reporting structure as the primary accountability framework as it proved to be inadequate.

Strains in relations between development partners have emerged following disagreements between the World Bank and the other DPs on the extent of the project progress reported in the aid memoires. This has resulted in DFID, EU and DANIDA being reduced to “observer” status during the assessments, effectively losing their voice in one of the few effective channels available to influence the project’s outcomes.

Strains also emerged between the GoG and DPs following the decision by DPs to withhold funds in light of allegations of financial irregularities, later substantiated by two independent reviews, reducing the impact of co-operation.

An Independent performance audit review also found a number of deficiencies in the project governance and reporting structure.

Asset monitoring and control

There were delays in receiving the asset register from GIFMIS.  An audit by the Ghana Audit Service observed items not kept under properly storage conditions (e.g. computers kept in rooms with excessive heat). The recent external audit commissioned by the Donors observed the following:  Fixed assets’ unique identifying numbers were not documented in the Assets Register and the Assets Distribution Schedule; Discrepancies were noted between the Assets Register and the Assets Distribution Schedule, these were subsequently updated following auditors reviews. It was observed that a high level of assets purchased have not been distributed to the MDAs. The team will continue to monitor this as the project ends in March 2015.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The Partnership Principles (PPs) are central to the management and monitoring of GIFMIS. This is mainly done in the context of the MoU, annual reviews, quarterly and month progress reports. DFID also separately assesses the PPs before any disbursement.

As no GIFMIS disbursements have been made this year, DFID has not carried out a formal assessment separate from the office-wide assessment (the last general assessment of DFID’s Partnership Principles, in June 2014, deemed that the Government of Ghana had upheld all four PPs over the 2013/14 period).

Beyond GIFMIS as a project, Public Financial Management has been a focus of dialogue with Government. There has been little progress on PFM reforms, although overall indicators have not deteriorated significantly either. As outlined elsewhere in this report, there is continued progress in terms of roll-out of systems while at the same time there has been limited or no progress in terms of substance.

The DFID general assessment on the other three PPs (commitment to poverty reduction and MDGs; respect of human rights and international obligations; and strengthening domestic accountability) was that they are all fulfilled. In summary, Ghana has made impressive progress on reducing poverty, already achieving MDG 1, although the trend is negative on other MDGs; Ghana consistently scores well in international rankings on human rights and freedom of expression, although accelerated progress will be important particular around violence against girls and women; and the political settlement is inclusive and stable, with strongly established democratic processes, although the trend on corruption is negative.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Two independent reports– A financial and a performance audit have been produced in the review period.

Monitoring progress throughout the review period

- World Bank aide memoires followed by monthly progress meetings – DFID, EU and DANIDA has observer status in this process
- GIFMIS secretariat performance and financial reports have been produced over the period
- Two independent reports have been produced in the review period – A financial and a performance audit.
- For this Annual Review interviews were carried out with officials from the MoF including the CAGD leadership responsible for the GIFMIS implementation, Budget department official responsible for PBB, officials from key MDAs (Education, Health, Local Government);and all DPs

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process