Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / PATH Meningitis Vaccine Programme 2010-2015
Programme Value: £3,619,788		Review Date: October 2014
Project Code: / 202045	Start Date: / 1 November 2010	End Date: / 31 March 2015

Summary of Programme Performance
Year	2011	2012	2013	2014
Programme Score	75/100	A	A	A
Risk Rating	High	High	High	High

Summary of progress

The Meningitis Vaccine Programme (MVP) continues to make good progress, with its work contributing to the elimination of meningitis as a public health problem in Sub-Saharan Africa.

During the reporting period funding from the Department for International Development has enabled MVP to continue the development of a vaccine designed to protect against five serogroups of the bacteria that cause meningitis, (that is, the polyvalent meningococcal vaccine) in collaboration with their partner, the Serum Institute of India Ltd (SIIL). The successful development and introduction of the polyvalent meningococcal vaccine has the potential to prevent meningitis epidemics not currently covered by MenAfriVac (a vaccine against serogroup A meningococcal bacteria) and lead to the elimination of meningococcal meningitis from Sub-Saharan Africa.

The work has progressed well and SIIL have: developed methods to increase the yield and scaled up production of the Men X polysaccharide; shown that vaccine formulations were immunogenic in animals and have selected a heat stable formulation which has similar, or better, immune responses to existing (quadravalent) licensed vaccines. The World Health Organisation (WHO) have supported the proposed product and clinical development plans.

The programme has made significant progress towards the goal of developing a vaccine that does not need to be refrigerated for an extended period of time, which can ensure major cost savings in the distribution of the vaccine. The work has included commissioning a facility dedicated to the production of the vaccine; discussion about the clinical development plan with the Drug Controller General of India (DCGI) and WHO; and planning a Good Laboratory Practice (GLP) toxicology study for early 2015. Permission to conduct a Phase 1/2 safety and immunogenicity clinical trial in adults and children will be applied for in 2015.

MVP has continued to roll out MenAfriVac, bringing the total number of vaccine recipients in the African meningitis belt to more than 151 million, since first introduced in Africa in 2010. Research published in the Lancet of a surveillance study across Chad showed reductions in meningitis incidence by 94% (http://www.path.org/news/press-room/644/).

Lessons learnt
The development of the polyvalent meningococcal conjugate vaccine (active against five serogroups) has been slowed down by a complex patent landscape. MVP and SIIL coordinated with outside patent counsel to complete a detailed patent landscape in 2011, which was updated in 2012. In addition, in 2012, the programme commissioned a freedom to operate analysis. The update provided further information on the activities of third parties in the field and identified conjugation methodologies that could be selected by MVP and SIIL, as distinct from those claimed by third parties, to allow them to move forward with no patent infringements. MVP and SIIL continue to monitor the patent activities of these selected third parties in an effort to ensure freedom to operate is maintained as the development activities advance.

Recommendations from the last review:

- MVP has adjusted its operational plan, to take into account the delays (outside their control) in development of the conjugate vaccine, described during the last reporting period.
- MVP has kept DFID up to date with developments throughout the year; through written exchanges, face to face meetings and telephone conversations. They have routinely provided details of achievements and key challenges that may affect their research activities.
- The regulatory research environment in India is still causing operational difficulties. MVP has confirmed that a Phase 1 safety trial co-funded by SIIL is likely to be moved to the Centre for Vaccine Development in Mali. The move to Africa for this initial clinical trial is designed to accelerate the overall clinical development timeline as it will include both adults and children compared with the originally planned Phase 1 trial in India that included adults only. The accelerated clinical development plan is likely to increase costs at this stage, because of the inclusion of children, but overall will result in the vaccine achieving licensure quicker and with reduced overall development costs. The programme is currently in discussion with DFID about the possibility of an extension beyond its current end in March 2015.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202045/documents/
DevTracker Link to Log frame:	No logframe – DFID uses the programmes operational plan

Summary of Programme

The UK is supporting a product development partnership, the Meningitis Vaccine Project (MVP) to develop a polyvalent Meningitis vaccine for Sub-Saharan Africa that will control the remaining 15% to 20% of meningococcal infections, not covered by the existing vaccine MenAfriVac. MVP engages private-sector collaborators to apply their development, manufacturing, and distribution strengths to innovate technologies that would not be a private-sector priority, and therefore achieve maximum sustainable benefit for public health in developing countries. DFID will provide £3,619,788 over 5 financial years (2010 – 2015) to this project.

There are currently research gaps into essential technologies, such as vaccines and medicines, to treat neglected diseases that affect the world’s poorest populations. This occurs where there are no current products or where those that exist are either too expensive, difficult to access, no longer produced, highly toxic or ineffective. These factors have resulted in a limited research base with PATH MVP being one of only a small number of organisations engaged in this area.

Meningitis is a deadly and debilitating disease that causes an estimated 70,000 cases/year alone in an area of sub-Saharan Africa known as the “African meningitis belt”, which stretches from Senegal to Ethiopia and has the largest burden of meningitis in the world. Meningitis kills one in ten people who are infected and leaves one-quarter of survivors severely debilitated. The number of cases of meningitis has dramatically reduced since the introduction of MenAfriVac in 2010, but this vaccine does not target all the disease-causing serogroups. New vaccines are required to prevent the remaining 15% to 20% of meningitis infections caused by other meningococcal serogroups.

The MVP, based at PATH is aiming to contribute to the elimination of meningitis as a public health problem in Sub-Saharan Africa. The intended outcomes of the research are:

- Development of an affordable, thermostable, polyvalent meningococcal conjugate vaccine that has a four-year shelf life at room temperature and meets a target-price of between £0.82 and £1.65 per dose.
- Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrate the vaccine’s safety and immunogenicity, in partnership with the Serum Institute of India Ltd.

Support to PATH MVP will, in the longer term, contribute to the impact of reduced poverty through improved and affordable treatment for a common disease among the poor. The short term target is to develop and test a new polyvalent meningococcal vaccine that will build upon the successes of MenAfriVac, which has provided such positive results in treating affected populations across the African Meningitis Belt.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual Outcome Assessment A – Outcome met expectation.

The MVP programme continues to benefit from strong leadership and brings together staff with a high level of skills and experience in product development. Progress towards both outputs (i. affordable, thermostable, polyvalent conjugate meningococcal vaccine and ii. production of thermostable Group ACWXY meningococcal conjugate vaccine) has been encouraging and MVP continues make positive advancements.

Aggregate Output Score and Description A- Outputs met expectations.

Although there have been some delays during the past two years, there has also been good progress and MVP has continued to develop clinical material in preparation for clinical trials. The delays, which are technical in nature are out of control of the programme and commonly encountered when developing a vaccine of this complexity. Following discussions with MVP last year, the milestones and targets were changed to take account of the technical delays. DFID is content that the PDP has taken appropriate action to overcome the difficulties. Because of the excellent preclinical data demonstrating very strong immune responses compared to licensed quadravalent meningococcal conjugate vaccines; measures are now in place to accelerate the clinical development and to make up some of the lost time.

Lessons

The difficulties encountered in India with regulations and intellectual property have raised a number of challenges, particularly as MVP’s main partner, SIIL, is based in India. Measures are now in place to transfer some of the clinical trials to Africa, although SIIL will continue to lead on much of the research and development.

Actions

DFID will continue to discuss with MVP the potential for further support beyond the current programme end date (March 2015) and will seek both programmatic and financial details about future plans. The vaccine development work to date has been very positive and DFID will liaise closely with MVP. MVP will update DFID on progress and will alert DFID if any further delays occur. Despite the delays over the past two years, the product development is back on track and we expect there to be further positive results in the future.

Has the logframe been updated since the last review? No
The programme does not have a logframe, but uses an operational plan, which has been revised and will be kept under close review during the next 12 months.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Development of an affordable, thermostable, polyvalent meningococcal conjugate vaccine that has a four-year shelf life at room temperature and meets a target price of between £0.82 and £1.65 per dose.
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	75
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Group ACWYX meningococcal conjugate vaccine developed according to good manufacturing practices (GMP) for use in Phase 1 trials	Polyvalent vaccine ready to go into GMP manufacture by 2014. / GMP facility and equipment validated in 2014. / GMP material released by the end of 2014.	On Track: Polyvalent vaccine is ready to go into GMP manufacturing at SIIL during 2014. / On track: validations ongoing during 2014 / On track: production and release of the phase 1 material targeted for release by the end of 2014.

Key Points
Scale-up production of individual meningococcal polysaccharides: four out of five individual polysaccharides (Men A, C, W and Y) were produced in 2011. In early 2012, a third party laboratory provided Men X strains to SIIL, who produced and purified polysaccharide at (small) bench-scale. However due to technical hurdles, the final GMP scale-up efforts for Men X were not completed as planned in 2013. The SIIL team worked to optimise the yield for the Men X polysaccharide. In addition, they commissioned a new GMP facility for the polyvalent product, production and release of GMP material for clinical trials is expected to continue until the end of 2014. Production is on track for the vaccine to cost between £0.82 and £1.65 per dose

Delays, due to technical issues, are to be expected in the development of complex vaccines of this nature. The programme has worked hard to ameliorate delays and to make up time at other stages of the vaccine development process.

Summary of responses to issues raised in previous annual reviews (where relevant)
The target dates for achieving different stages of the development process were revised in previous years, to take account of delays, largely outside of MVP’s control.

MVP has kept DFID fully informed of difficulties surrounding IP patent issues and have developed a work-around approach that will enable them to speed up progress and gain much of the ground previously lost.

MVP has kept DFID up to date with production difficulties and (in particular) the issues relating to the planned movement of safety and clinical trials, originally planned to take place in India, now being moved to Africa. Technical delays (including intellectual property rights and other issues that were difficult to predict) have caused an overall delay estimated between 12 and 15 months. As a result, the Phase 1/2 trial will now begin in January 2016 instead of late 2014. It is expected that much of this delay can be made-up, by expediting the next stages of clinical development.

Recommendations
MVP must continue to inform DFID of progress and whether there are likely to be any further delays in the development of the polyvalent vaccine, or the conduct of the clinical trials.

Output Title	Produce thermostable Group ACWXY meningococcal conjugate vaccine to meet desired specifications and demonstrates vaccine safety and immunogenicity, at Serum Institute of India Ltd, and conduct Phase 1 study.
Output number per LF		2	Output Score	B
Risk:		High	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)		Milestones		Progress
Study stability characteristics of individual conjugate polysaccharides to successfully stabilise individual conjugates.	Stability studies conducted by 2013 / Toxicology studies competed by 2014		Stability studies achieved: Completed stability studies at 45 degrees centigrade out to 3 months with the lead lyophilized formulations for the Men A, Men C and Men X strains with positive results. / Toxicology studies delayed until early 2015
Phase 1 clinical trial of pentavalent Meningococcal C Vaccine (MCV) completed	Phase 1 study started by 2015		Plans for a Phase 1/2 trial to take place in Africa are progressing. Work plan, including proposed clinical development plan through licensure and prequalification, has been developed and discussed with DCGI and WHO.

Key Points
Progress has been made developing a thermostable pentavalent MCV and MVP are on track to conduct the Phase 1 clinical trial in early 2016. Strain selection has occurred; fermentation optimised and yields of purified polysaccharide for each serogroup optimised. The conjugation proteins have been selected and pre-clinical data generated that demonstrated similar or better immune responses generated in animal studies, when compared with the licensed quadravalent vaccines Menactra and Menveo. Preparation of the GMP polysaccharide and conjugates is ongoing at SIIL, with an expectation that pentavalent conjugate material will be ready to initiate a GLP toxicology study by the beginning of 2015.

The Phase 1 trial scheduled for India (adults only, safety only), as agreed with DFID will transfer to Africa and become a Phase 1/ 2 trial (adults and children, safety and immunogenicity), which would potentially gain back around 12 months of the time that has been lost on the programme. MVP has indicated that this approach will require additional funding due to the more complex nature of the trial and discussions between DFID and other funders are currently underway regarding options and risk assessment.

Summary of responses to issues raised in previous annual reviews (where relevant)
Over the past two years technical problems, out of MVP’s control, have been responsible for some targets being missed. MVP are addressing the issues, have revised their operational plan in discussion with DFID, and appropriate action is being taken to get the trials back on track. Actions taken include resolution of intellectual property barriers, optimisation of strain selection, and resolution of Men X scale up issues. It is very likely that the modified plans aimed at the acceleration of clinical trials will enable some time to be made up towards the end of the licensure process.

Recommendations
The current programme is scheduled to end on 31 March 2015. Discussions with MVP, DFID and other funders are currently on-going, regarding a possible extension to the programme. MVP have been asked to submit a clearly defined business case for the extension, with clear outputs and a timetable for completion of key stages.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1-2 pages)

Performance of key cost drivers
Vaccine development is a very costly process, particularly in the final stages of development. As new vaccines progress through the pipeline, they enter into successively more costly phases of development. MVP has a partnership arrangement with SIIL, who provide cost effective approaches to development of new vaccines.

The main drivers are staff time, together with laboratory equipment and consumables. MVP is managing costs appropriately and has been upfront regarding the potential additional costs associated with clinical testing in Africa instead of India.

How does VfM performance compare to the original VfM proposition in the business case?

Funding product development through a PDP structure such as MVP provides value for money through:

- Responsive organisational structures with small core teams and open research models, which reduce operating costs.
- A robust pipeline of vaccines and provision of support for the most promising candidates, ensuring greater prospect of success. Early go/no go decision making using in-house Scientific Review Committees.
- Leveraging contributions from the private sector and/or in-country funds. The relationship with SIIL demonstrates success in this aspect.
- Developing partnerships with other entities to support joint activities (e.g. clinical trial site development, development of assays).
- MVP staff constantly looking for better technical solutions to develop vaccines and are able to share knowledge and expertise with other vaccine development colleagues.

Additionally strong partnerships with other PATH PDP’s and global organisations including the Global Alliance for Vaccines and Immunisation (GAVI) has greatly benefitted the likelihood of vaccine uptake. Knowledge sharing opportunities have also been enhanced significantly through MVP’s developed professional networks.

Does the project continue to represent value for money? If not, why, and what actions need to be taken?

MVP continues to represent value for money and a good investment for continued DFID funding. As with the other PDPs, MVP uses stage gates as decision points on the potential success of a vaccine and poorly performing candidates are dropped quickly, ensuring funds are protected and used appropriately. Decision trees are used to analyse the probability that a candidate will make it to the next gate. This ensures a healthy portfolio of candidates that have a higher degree of certainty of being successful.

Quality of financial management
MVP is core funded by DFID and although it is part of the PATH organisation the funds are ring-fenced for meningitis vaccine development. Spend continues to be on-track and is disbursed in accordance with the agreed Memorandum of Understanding (MoU). PATH is routinely audited; annual audited statements have been submitted and have been assessed as satisfactorily.

PATH has a robust policy on Fraud, Corruption and Dishonesty and in addition provides protection to informants through its Whistleblowing policy, which reflects best practice and provides funders with a high level of assurance. No changes were made to these policies in 2013 and no incidents of fraud or corruption were identified during the past year.

As mentioned elsewhere in the report MVP has requested an extension to the programme and DFID is in the process of assessing the details.

Date of last narrative financial report	15/05/2014
Date of last audited annual statement	15/05/2014

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk
Product development is high risk and potential vaccine candidates can fail at any stage in the development process. MVP (like the other units within PATH) maintains a robust pipeline of potential vaccine candidates that are constantly monitored, to ensure that only the most promising products are taken forward. PATH staff have good experience in their fields of expertise and lessons learned from one programme are applied across the wider portfolio. The scientific basis for the MVP approach is firmly grounded behind the success of a technically similar vaccine, MenAfriVac. Technical and regulatory challenges continue to be overcome and there is a full expectation that the MVP candidate vaccine will be tested in a clinical trial where its success and impact can first be measured.

Even taking recent delays into consideration, financial risk remains relatively low. PATH has well established internal and external audit procedures. An external audit is conducted annually and the results are used to determine the liquidity of the organisation. Each year DFID receives a copy of the Audit Statement which is reviewed carefully to ensure that DFID funds are correctly recorded and used for their intended purposes. The 2013 Audited Statement has been received and is “unqualified”.

A main partner of MVP is SIIL and MVP has a right of access to all SIIL’s project-related data, including all financial records. As in previous years, there has been no indication of impropriety nor have they reported any issues relating to SIIL’s financial management or performance under the programme.

Risk is assessed by the DFID team regularly throughout the year and risk categories are changed to reflect current developments within the programme. The research regulatory problems in India have been a major challenge to many research programmes, both funded by DFID and by other funders. This remains a challenge to the programme and MVP with its partner SIIL has advised us of their intention to move some of their clinical testing from India to Africa. This is an appropriate approach, to mitigate the risk of further delays and complications.

Outstanding actions from risk assessment
There are no outstanding actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
MVP has its own operational plan, which is used by many funders (including DFID) instead of a standard DFID logframe. There were 13 organisational objectives in 2013 and a further 9 for 2014. The majority of these objectives are on-track, with four delayed, as highlighted above. It is anticipated that the delays will largely be overcome using the revised plans, which will provide opportunities for time savings.
Technical problems out with the control of MVP have been responsible for these targets being missed. The issues are under continuous review and are being addressed, and appropriate action planned and taken to get the timings back on track. Actions taken include resolution of intellectual property barriers, optimisation of strain selection, and resolution of Men X scale up issues. The plans for the Phase 1 trial to be conducted in Africa (in place of India) have the potential to recover up to 12 months of time lost on the programme. It is possible that the accelerated plans for the clinical trials will enable some time to be made up towards the end of the licensure process and discussions are currently underway regarding options and risk assessment.

Performance of partnership (s)
The DFID-PATH relationship is strong and there is regular communication on issues affecting the programme. There is good coordination inside PATH and this helps to ensure a common understanding of how PDPs should operate and all responsibilities under the arrangement (e.g. reporting) are presented in a standard format.

Asset monitoring and control
PATH maintains an appropriate asset register.

G: CONDITIONALITY (½ page)

Update on partnership principles

DFID provides core funds to MVP. There are no specific conditions attached to this funding other than that it is retained within MVP solely for use in activities feeding into the development of meningitis vaccines. SIIL is another key partner to MVP and provides both funding and researcher resources for meningococcal vaccine development in addition to the DFID contributions. As MVP does not provide support through government systems we do not use the partnership principles to inform the management and monitoring of the programme.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The vaccine against the Meningitis A serogroup (MenAfriVac) continues to be a huge success. It has now been introduced in 12 countries across the African Meningitis Belt. MVP vaccine and development activities are focussed on informing vaccine policy regarding sustainable strategies to maintain population immunity against Men A disease. Following the initial mass vaccination campaigns, countries will have the option of protecting new birth cohorts through routine immunisation, catch-up campaigns or mixed approaches. MVP is leading efforts to obtain a vaccine license variation for a paediatric indication of the vaccine, which is based on assessing the persistence of vaccine-induced antibodies.

Clinical studies, that enrolled infant subjects in Ghana and Mali, have just been completed and are providing comprehensive information on the safety, immunogenicity and optimal dosage of MenAfriVac when co-administered with other routine Expanded Programme on Immunisation (EPI) vaccines. In addition, data from a recent follow-up observational antibody study on Gambian, Malian and Senegalese subjects (who had been vaccinated four to five years ago), have confirmed that a single dose of MenAfriVac induces long-lasting sustained levels of Men A antibodies.

Monitoring progress throughout the review period

This review was carried out by members of the Human Development Team in DFID’s Research and Evidence Division, with input from other funders and PATH. Members of the review team met with MVP at the PATH headquarters in Seattle and have had a number of teleconferences during the year, during which progress and challenges have been discussed.

As funding is currently scheduled to end in March 2015, DFID will shortly need to make a decision on the future of the programme. There is a request for an extension for the programme to continue beyond the current end date. MVP will produce a detailed business case outlining progress to date, tactics for expediting progress and reasons why the extension is being sought.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action headlines.
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the project Outcome by the end of the project
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Actions / Any further information on actions (not covered in Summary Sheet)
Has the logframe been updated since the last review?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at project approval. If so, why?
Is the project value for money / Overall view on whether the programme is good value for money / Performance against vfm measures and any trigger points that were identified to track through the programme
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / Changes to the overall risk environment/ context / Review the key risks that affect the successful delivery of the expected results. / Any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks. / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from due diligence / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the project and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for which it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the project / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the project design working out in practice in this project? Are modifications to the project design required? / Is there any new evidence available which challenges the project design or rationale? How does the evidence from the implementation of this project contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process